ADDENDUM TO BUSINESS CASE

INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Fighting Corruption Globally (FCG) - 301267
Country or region targeted	Worldwide
Type of cost extension (if applicable)	Cost Extension
Original project budget	£31m
Original project start and end dates	24/07/23 – 30/06/28
Cost extension value (if applicable)	£5m (takes new BC value to £36m)
New reduced budget (if applicable)	N/A
New project end date (if applicable)	N/A
Business Case Quest Document No.	Saved in teams

INFORMATION
What is the project’s purpose?
The FCG programme will contribute to achieving UK and FCDO strategic objectives international development, in particular the achievement of Sustainable Development Goal 16 and on economic crime and anti-corruption as outlined in the UK Economic Crime Plan 2 and a new UK Anti-Corruption Strategy which is being drafted. FCG provides a foundation for a set of activity that will help deliver the Foreign Secretary-led campaign to tackle the interrelated challenges of corruption, illicit finance and kleptocracy. / The additional £5m funding is to provide support to civil society and investigative journalists. This was a commitment under the previous White Paper and resonates well with the emerging priorities of the Foreign Secretary’s campaign. There is significant scope for CSOs globally to help to shape the broader objectives of the FS’ campaign, including outcomes of the proposed Summit of International Financial Centres through evidence-based advocacy and convening power. / HMG prioritises tackling grand corruption and illicit finance because they undermine national security, threaten global security, harm democracies, hamper economic growth, slow development and harm its victims. To combat corruption, evidence demonstrates that building capacity amongst ‘demand-side’ actors complements top down, ‘supply’ type interventions. Many large-scale, transnational corruption cases have been investigated and exposed by civil society organisations and investigative journalists. Civil society organisations (CSOs) play an important role in demanding accountability from governments, serving as a link between citizens and decision-makers, and engaging in advocacy and monitoring of national and international reform efforts. / Over the past six months, IFAC spoke to a range of stakeholders and reviewed our existing and previous funding to CSOs to consider past effectiveness and where FCDO could add maximum impact. This review process recommended that new efforts should focus on the following areas: / Funding - Increase FCDO funding to support organisations working internationally to investigate and expose corruption and advocate for effective policy solutions and accountability; / Diplomatic and Ministerial Engagement - Identify opportunities for Ministers to promote the importance of CSOs’ and journalists’ work in fighting corruption and CSOs’ attendance in multilateral fora. Make better use of existing networks, such as the Media Freedom Coalition’s Embassy Network and political counsellor and governance networks to engage with and support CSOs/journalists in-country; and / Greater policy engagement with CSOs to deepen our understanding and inform our policy responses. The review found that local work by CSOs often benefits from being connected to a wider, donor-funded policy movement e.g., local efforts to improve beneficial ownership transparency benefit from docking into donor-led, high level policy campaigns.
What is the objective of the cost extension or other changes?
This extension will increase the effectiveness and impact of CSOs combating corruption. Increased efforts in this area by FCDO will enable investigative journalists to expand investigations, taking advantage of the growing movement towards open beneficial ownership registers for example, invest in appropriate security and risk management and develop material that can be shared with law enforcement. Civil society organisations will be better positioned to develop and advocate for policy measures and reforms aligned with HMG policy priorities, and to assist in holding corrupt actors to account.
What is the additional and total support the UK will provide?
An additional funding of £5 million ODA over three years which will be allocated: / FY 24/25 - £1m, FY 25/26 - £2m, FY 26/27 - £2m. / The funding is being added to the Fighting Corruption Globally Programme to enable funding to be allocated quickly and minimise the programme management burden. / Funding will be allocated in two tranches: i) a 3 year, direct grant to the Global Anti-Corruption Coalition and Transparency International in 24/25 (with break clauses to allow for the range of possible Spending Review outcomes and future resource allocation rounds within FCDO) followed by ii) a limited call for proposals for remaining funding allocations in 25/26-26/27. / This additional funding to bring the new programme total to £36m, subject to future spending reviews and resource allocation rounds.
What are the expected results?
The Global Anti-Corruption Coalition (GACC) / The GACC was established in 2016 to breakdown silos amongst journalists and civil society organisations often working on similar aims but not working together as much as they could. The two partners in the GACC, the Organised Crime and Corruption Reporting Project (OCCRP) and Transparency International (TI) brings together two international networks to investigate and expose corruption, and advocate for change. OCCRP has more than 65 member centres of individual journalists and media outlets; TI has more than 100 Chapters globally. By working together, OCCRP investigations and TI advocacy for reforms and efforts to secure legal accountability have delivered results. For example, in 2022 and 2023, GACC’s work resulted in: / 26 investigations into sanctions evasion, corruption, electoral interference and environmental crime; / 23 indictments or arrests in 18 countries; and / 89 government actions including sanctions, policy reforms and legislative amendments. / FCDO funding is expected to deliver a similar level of results over 3 years, as well as new outputs listed below: / Investigative journalism: investigating and exposing grand corruption / New investigations into grand corruption initiated, working cross-border, and developing campaigning and newsworthy material. Investigations will be shared with law enforcement where appropriate. Civil society organisations will use these investigations to increase the evidence base for specific policy reforms, and campaign for such reforms in specific jurisdictions. / Safety - Increased number of journalists to benefit from OCCRP’s security training (digital and physical), ability to analyse specific security threats and help to leave a country where needed. More journalists benefit from OCCRP tools to share information securely to protect their data and sources. / Wider data analysis: Investigative journalist organisations maintain rich, wide-ranging databases of information and data drawn from their historic investigations, which have not been fully analysed and mined to date due to resource constraints. Additional deep dives into specific aspects of illicit finance and corruption, such as professional enablers, use of trusts, or geographic focus would be funded by FCDO, building on a successful pilot of this approach with one investigative journalism organisation in 23-24. This funded deep analyses of their extensive database across hundreds of investigations, to identify trends and patterns in relation to so-called ‘professional enablers’ of corruption. This work yielded useful results that have led to further work with academic research programmes and have been used to inform FCDO thinking and work on this issue. / Training on emerging areas such as AI, crypto, climate corruption for investigative journalists to ensure skills and knowledge are kept up to date with emerging illicit finance issues. / Supporting civil society advocacy on illicit finance and corruption will lead to the below outcomes: / Civil society organisations maintain and extend existing levels of national and international advocacy on illicit finance, kleptocracy and corruption, offering evidence-based policy proposals and holding governments to account when reforms are committed. New illicit finance risks are identified to policy makers. / Stronger cross-border collaboration amongst CSOs that reflects the cross-border nature of illicit finance, grand corruption and kleptocracy. / Civil society organisations are able to maintain their safety and security, particularly in higher risk countries. / Knowledge and advocacy from civil society is used to inform policy work by FCDO and others in HMG, on priority policy issues such as professional enablers, corporate and trust transparency, kleptocracy and state capture.
What is the approach to implementation?
Fund the GACC; £3 million over 3 years; funding split between GACC partners 40% OCCRP and 60% TI. / OCCRP are one of the few organisations who look at the safety of journalists fighting corruption and already have a workstream in place; they have noted that funding for this core work can be hard to sustain. We have an existing funding relationship with OCCRP which has delivered solid research and advocacy work to date using OCCRP’s investigations data. OCCRP plan to expand their collaborations to other journalist organisations, including a recent agreement with the Bureau of International Journalists. / FCDO funding would enable OCCRP’s ongoing and new work as part of the GACC, as well as contribute a proportion or core funding to ensure enabling activity such as database software and maintenance or journalist security take place at appropriate levels. GACC currently receives funding from the HO-managed Global Economic Crime programme in 24/25; we will discuss how best to manage complementarity and coordination of our respective funding streams. HO are not likely to fund from 25/26. / Transparency International – There is no other organisation in the anti-corruption field who can provide research and advocacy at the global level combined with a large network of local CSOs. This review has highlighted the need within IFAC, including our International Centre of Expertise (ICE), for a network of CSOs to draw on. We currently lack a network of NGOs with local knowledge, particularly those based in the global south, and we often draw on the work of western NGOs. Transparency International’s global secretariat undertakes a range of highly-regarded knowledge and evidence work as the foundations for global advocacy on a number of high-priority areas critical for addressing illicit finance and kleptocracy. These include work on professional enablers, legal accountability routes, beneficial ownership transparency and high-risk jurisdictions. TI’s added value is that its work in these areas is rooted in, and able to utilise the 100+ national TI chapters in its network. / FCDO funding would support the advocacy and accountability work that TI leads within the GACC alongside core funding to implement its Global Strategy where those priorities align with FCDO’s. / In 25/26 and 26/27, use a competitive process to identify suitable funding options for the following, with £2m available over the two years. The final development of a call for proposals will determine which of the following options to prioritise: / Call for funding proposals for a wider range of CSOs to support advocacy and consultation on illicit finance, linked to the preparation and delivery of the FS’ campaign and summit. / Many NGOs, including UK organisations have played a constructive role in analysing deficits in national and multilateral responses to illicit finance and kleptocracy, and successfully influenced legislative and regulatory change. In addition to funding TI, the programme would seek to identify a small number of other partners, ideally in a consortium format. This could involve UK CSOs building stronger networks and collaborations with a wider range of NGOs working internationally (eg based in Africa, or Indo-Pacific regions) and link to advocacy work by partners in Europe and the US. Partnerships with the private sector or professional bodies would be considered. A focus of this funding would be to ensure that the FS’ campaign on illicit finance, and particularly the centrepiece summit of international financial centres, engages credibly with civil society. This could take the form of policy deep-dives on relevant themes, regional or national convening to inform Summit commitments and deliverables. / Call for funding proposals to deliver training to CSOs and journalists and support and mentorship afterwards. / The review noted that smaller CSOs or investigative journalism outfits may lack sufficient knowledge and skills to work on emerging, technically challenging issues such as AI and crypto finance. FCDO will do further work to assess needs and identify options for meeting these. / III) Consider co-funding proposals with other donors in Y2 and Y3 of funding. / Overall analysis recently has suggested that donor funding for work on financial integrity, corruption, illicit finance and accountability has declined in recent years (in line with overall declines in spend on governance). This is true for both public donors, but critically for private donors who historically invested significant funding in this sector. To maximise the impact of our funding, IFAC could usefully invest time in connecting with the more active donors, either in the context of existing relationships (e.g. with USAID, U4 donors) or with groupings such as the Trust Accountability and Inclusion Initiative (TAI). This would give us access to a better understanding of who is funding whom to do what and where there may be unmet needs, as well as opportunities to engage in policy focused conversations and lesson learning. A new donor in this space is the US-based National Endowment for Democracy, which has established a countering-kleptocracy programme this year and is potentially interested in co-funding with FCDO and others. / Geographic areas of priority: / IFAC will undertake further consultation with priority posts and central Directorates to identify whether additional funding in specific regions would add value to existing efforts or meet currently unmet needs. Consultation may identify options for co-funded programming or buy-in from Posts or regional departments.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
No key changes to the original business case. The objectives of this funding are already reflected at strategic levels in the programme Theory of Change (ToC). A recent first Annual Review of FCG recommended further work to enhance the programme ToC and logframe; this new funding will be incorporated into that.