## Annual Review

Title: Zambia Democratic Governance Programme
Programme Value £ (full life): £12,000,000		Review date: 22/03/2025
Programme Code : 301270	AMP start date: 22/03/2021	AMP end date: 31/05/2026

Summary of Programme Performance
Year	2021/22	2022/23	2023/24	2024/24
Overall Output Score	A	A	A	A
Risk Rating	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:		https://iati.fcdo.gov.uk/iati_documents/90000596.odt
DevTracker Link to Results Framework:		https://iati.fcdo.gov.uk/iati_documents/D0004870.xlsx
	A. SUMMARY AND OVERVIEW

Programme Description
The Zambia Democratic Governance Programme (ZDGP) strengthens democracy and governance in Zambia. It does this by working with the Zambian Government to support more effective policy making, by strengthening Zambia’s institutions to deliver more effectively for citizens and by working with communities to increase their participation in, and demand for transparency and democracy.

A more inclusive democracy will support Zambia to achieve its development ambitions. Evidence shows that, on average, democracies outperform autocracies in multiple measurements: democracies have higher economic growth, better health outcomes, improved access to education, better gender equality and are less prone to domestic and international conflicts. But Zambia’s democracy suffers from weaknesses in the functioning of government, high levels of corruption, insufficient economic growth and deficient delivery of public goods. By supporting Zambia to have a more resilient democracy, the UK contributes to a prosperous and stable future for Zambia’s people based on inclusive and sustainable growth, and resilience to poverty and shocks.

This year, FCDO extended the value and time of the programme. The value increased from £4,950,000 to £12,000,000. The end date was extended from 31/12/2024 to 31/05/2026. The extension ensured FCDO could continue providing support to a critical economic reform and will allow FCDO to smoothly transition from ZDGP to its successor programme (currently in design). The structure of the programme has remained broadly the same since the last Annual Review. Most of the programme is delivered through the Deepening Democracy Facility (DDF). The DDF is implemented through an Accountable Grant with Diakonia and BBC Media Action worth £1,376,298 in 2024/25. The ZGDP also funds the Basel Institute on Governance’s International Centre for Asset Recovery (ICAR) to embed anti-corruption expertise in Zambia’s law enforcement agencies. In 2024/25, FCDO provided funding to ICAR in Zambia bilaterally (through ZDGP) and centrally (through the Illicit Finance and Anti-Corruption Dept) at a combined amount of £811,039.00.

Overall Score

This year the programme has scored an A (met expectation), which is testament to partners’ achievements this year. This is the fourth consecutive ‘A’ this programme has scored in FCDO’s annual reviews. We therefore recommend that the programme should continue until its planned closure in May 2026. The programme has adapted well to the evolving context. The IMF debt restructuring has increased the Zambian Government’s impetus for reform in key growth sectors. This created opportunities for the UK to support evidence-based policy design and implementation. While the space for supporting economic reforms widened, progress on governance reforms has been markedly slower. Throughout 2024/25, there have been concerns about growing restrictions on civic space, eroding judicial independence, and weakened oversight of key institutions. The overwhelming mandate for change that underpinned the 2021 elections and the early commitments of the current administration to undertake governance reforms led to an expectation of extensive reforms that haven’t materialised as expected. These changes in the context underscore the importance of adaptive programming; the extent to which partners can analyse these changes and adapt their work to seize new opportunities (and withdraw where necessary) determines how successful the programme will be. We assess that ZDGP has adapted well this year. Key achievements include:
- Supporting the Government to successfully implement a critical IMF-backed reform to its agriculture subsidy regime. This reform is projected to save the Government up to $80,000,000, removed 200,000 ‘ghost’ beneficiaries (and added 200,000 eligible beneficiaries) and creates thousands of rural jobs.
- Supporting Zambia to recover assets lost to illicit activity at an estimated value of £41,000,000, with further cases under investigation that have potential combined recoveries of £300 million.
- Coalescing civil society to successfully oppose repressive new cyber-security legislation, which would significantly damage political freedoms and growth.
- Creative use of media and journalist mentoring to widen possibilities for local authorities/ representatives and citizens to hold meaningful discussions on issues of common interest.
Output Scoring Summary

Output		Impact weighting	Output Score
1	DDF facilitates dialogues with key actors to produce solutions to governance challenges identified in at least two DDF themes.	23%	A
2	DDF supports the implementation of agreed initiatives to address governance challenges.	22%	A
3	DDF uses learnings and best practices to influence governance policy and reforms.	22%	A
4	ICAR equips Zambia with appropriate competences and skills to effectively use their legal and enforcement instruments to recover stolen assets.	16.5%	A
5	ICAR supports Zambia to introduce suitable tools, procedures, instruments, policies or institutions to recover and manage stolen assets.	16.5%	A+
Total		100%	A

Summary of recommendations for the year ahead

#	Recommendations	Target Completion Date	Owner
1	In the next year the DDF should think more broadly about what constitutes civil society and how coalitions of non-traditional development actors can help drive reform.	March 2026	DDF partners
2	Learning outputs must be closely tied to advocacy and engagement plans. In addition, DDF should involve policymakers earlier in the research process and tailor briefs to address specific policy questions. This increases the likelihood that evidence will be seen as relevant and lessons acted upon.	March 2026	DDF partners
3	ICAR to work with the law enforcement agencies on a structured model of staff training (career pathways, curriculums, accreditation etc.) that the agencies can implement beyond the life of UK funding. FCDO to support with advocacy.	March 2026	ICAR/ FCDO
4	ICAR should use 2025/26 as a transition year to support the agencies to sustain the approach to asset recovery beyond UK support.	March 2026	ICAR

A review of progress made against last year’s Annual Review recommendations is in Annex A.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Theory of Change

The Theory of Change for this programme is: IF CSOs and media organisations receive targeted support to strengthen their capacity to test and learn, build networks and coalitions, AND if stakeholder engagement is broadened to engage policy and delivery institutions as part of a multi-stakeholder approach, AND if policies and decision-making are increasingly based on evidence (through research, analysis and technical assistance), THEN CSOs and media organisations have strengthened skills, greater influence and stronger networks, AND DDF is seen as a trusted partner and critical friend AND there is a more constructive engagement between government and civil society. Taken together, THEN demand and supply side governance stakeholders make significant positive changes on policy and behaviour priorities, WHICH will result in more sustainable pathways to change and a deepening of democracy in Zambia ahead of the 2026 elections.

Our assessment is that the Theory of Change remained valid in 2024/25, and that the investments made under ZDGP are leading to the intended outcomes and impact. There are five key lessons which we have learned this year which help us progress towards (and understand whether we’re reaching) the outcomes:

1. Flexibility: At the input and output level, flexibility matters for achieving outcomes. For example, a window of opportunity opened this year for Kivu to support reform of the Farmer Input Support Programme (FISP)[1]. We couldn’t have predicted that this would happen at the programme’s inception; the UK has been advocating for reform of FISP for over 20 years, but by successfully lobbying for the reform to be a requirement under the IMF programme, the balance finally tipped. Through ZDGP, Kivu provided technical assistance to support the Government to move to an e-voucher model. Moving to an e-voucher model saves the government money on procurement and delivery, reduces opportunities for corruption, incentivises private sector growth and creates jobs, but it is politically contentious and technically difficult to implement. To support the reform, ZDGP had to flex its focus and approach rapidly. In practice, that meant providing Kivu with additional resources and using significant diplomatic influencing to secure political support. Kivu verified every beneficiary to remove 200,000 ‘ghost farmers’, worked with mobile companies to design the SMS code system, and supported the Ministry of Agriculture on a payment system for agriculture outlets. BBC Media Action (another partner under the DDF) used its networks to share communications about the e-voucher model nationally. This demonstrates that the assumptions that underpin the Theory of Change (flexible budgets, working politically, combining programming with diplomatic influencing) hold.
  [1] FISP is a government agricultural subsidy programme that supports one million farmers every year with maize seeds and fertiliser. Since inception, the government has directly procured seeds and fertiliser and delivered it to farmers across the country. This model is expensive (accounting for 5.5% of the total budget and 80% of public spending on agriculture), inefficient, highly prone to corruption and undermines climate-resilience growth. Under the e-voucher model, farmers receive credit directly to their phone which they can they spend on any farming input at agro-dealer businesses.
2. Coalitions: Building wider, more inclusive coalitions is critical to achieve ZDGP’s outcomes. The Theory of Change assumes that by identifying and providing early support to coalitions, it is possible to translate broad informal and formal consensus into impact. This year, DDF supported a broad CSO coalition that influenced the deferment of the Cybersecurity and Cybercrimes Bills. The Cyber campaign highlighted the impact that coalitions can have on influencing national policy, and the way that coalitions for change often form organically in times when they are most needed. The DDF previously attempted to create a formal CSO alliance of likeminded organisations, but the lack of a common agenda to coalesce around meant it never gained traction. This demonstrates the importance of driving issue-based coalitions (that can be formalised but more likely represents an alignment of interests behind an issue) to maintain momentum and unified action on longer-term governance issues.
3. Government buy-in: The Theory of Change assumes that if government institutions are actively engaged and the engagement is more constructive, then it will lead to better outcomes. The social accountability training demonstrated the value of engaging with government institutions. In Chongwe district, PAAGZ co-created training content with local government and this had a notable impact on the partner’s ability to operate and the effectiveness of their work. By contrast, partners who implemented their projects solely with citizens struggled with execution due to bureaucratic delays and coordination challenges with government stakeholders.
4. Technical solutions to political challenges: Government engagement supports partners to deliver more effectively, but it doesn’t automatically translate to political will to achieve sustainable change on an issue. The 2024 Annual Review of ZDGP noted that at the agency level, the buy-in of the law enforcement agencies to ICAR’s approach to financial investigations has resulted in significant asset returns to the state. This remains true. However, through 2024/25, the political will to tackle corruption at the highest levels of government waned. The Government has yet to make any significant legislative (and policy) improvements. The revised Anti-Corruption Act is due to go to Parliament, but it won’t make any significant steps towards increasing the independence of the agencies. This undermines the impact partners can have on reducing corruption. Returning assets is a novel domestic resource mobilisation strategy but only if the system sustains it beyond UK support, which requires political will.
5. Balancing risk versus reward. Under ZDGP, FCDO implements a diverse portfolio of work, FCDO is focused on the hardest most intractable development challenges. Many policy reforms in this space are challenging to influence, making change difficult. At the same time if the programme invests in areas with no political traction, it will not deliver value for money. Balancing the portfolio with areas that are high risk/high reward (like economic reforms) with interventions that are low risk and contribute to incremental progress (like social accountability) is important for ensuring this programme achieves its objectives within FCDO’s risk appetite.
Progress Towards Impact and Outcomes

	Baseline	2024/25 Progress
Impact: To support the deepening and consolidation of democracy in Zambia to build resilience and stability, and enable development and reform.
Indicator 1: Zambia’s overall governance ranking guided by Mo Ibrahim Index of African Governance indicators is improved.	52%	56.6%
Indicator 2: Impact stories demonstrating the programme's contribution to fighting corruption and establishing an asset recovery regime in Zambia.	0	Planned: 2 / Achieved: 2 / ICAR support leads to the discovery of a high-profile money laundering syndicate operating in Zambia. / ICAR supports Zambia to strengthen international cooperation in investigating and recovering assets.
Outcome 1: Key democratic institutions and processes are supported and strengthened in national policy/reform to deepen transparency and accountability.
Indicator 1.1: The level to which democratic institutions or processes have been supported to work on a reform/policy on two or more DDF themes.	0	Planned: 4 / Achieved: 4 / Supported MoA/MoF to successfully roll out FISP e-voucher in 74 districts. / Supported State House to make effective policy decisions on job creation. / Increased accountability of local authorities to citizens on the CDF. / Supported MoHA and MoS&T to revise cyber legislation.
Outcome 2: Civil Society (CSOs, citizens, media, business entities etc) engagement and participation in local and national governance processes is enhanced through establishment/strengthening of civil society platforms/mechanisms.
Indicator 2.1: Civil society platforms/mechanisms that have been established/strengthened because of DDF contribution foster accountability and transparency in any of the DDF four themes.	0	Planned: 5 / Achieved: 5 / DDF established 5 platforms in Nkana, Bwacha, Milanzi, Mkaika, Mazabuka Central, Magoye,and Chongwe constituencies through townhall meetings, interface meetings, public discussions, community dialogues and radio stations.
Indicator 2.2: Civil society perception/opinion of willingness of democratic institutions to engage in dialogue to address governance issues on any DDF theme.	Perception of civil society to engage low.	Planned: Civil society perception has improved since baseline. / Achieved: In progress.
Indicator 2.3: The level to which civil society are engaged through DDF to address governance issues in identified DDF themes.	Conduct 126 CDF radio programs & a listenership survey and 300 members of community take part in community meetings through partners.	Planned: 50 radio programmes (and a listenership survey), 50 members of civil society attend debates, 80 members of community take part in community meetings. / Achieved: 110 radio programmes, 528 people attended 10 public discussions across Lusaka, Kabwe, Kitwe, Katete and Mazabuka.
Outcome 3: Anti-corruption chain is better equipped to deliver sanctions and recover assets.
Indicator 3.1: Percentage of ICAR supported cases making four steps or more towards conviction or asset confiscation.	0	Planned: 40% / Achieved: 76%

Lusaka community debate on CDF effectiveness

## C. DETAILED OUTPUT SCORING

Output Title	DDF facilitates dialogues with key actors to produce solutions to governance challenges identified in at least two DDF themes.
Output number:		1	Output Score:	A
Impact weighting (%):		23%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of key actors engaged in various dialogues to discuss governance issues (iterative)	20 Key Actors	Exceeded. 38 key actors engaged in dialogues to discuss key governance issues like corruption, transparency and accountability, CDF Act amendment, and Cyber Security and Crimes Bills.
1.2 Number of workstreams that have developed in at least two DDF themes (cumulative)	1 Workstream	Met. 1 work stream: Transparency, Accountability and Anti-Corruption (TAA).
1.3 Number of ideas generated through the Problem-Driven Iterative Adaptation (PDIA) methodology with different key actors in each work stream (iterative)	9 Ideas	Partially met. 8 new ideas generated, including under the TAA workstream.
1.4 Number of viable initiatives that have been prioritized for implementation with DDF funding in each work stream (iterative)	4 initiatives	Partially met. 3 initiatives prioritised.

Output 1 assesses Diakonia’s ability to identify governance and democracy challenges and produce solutions. As the DDF is an iterative, adaptive model, it was not possible to define expected results during the inception phase. Instead, the DDF outputs demonstrate the process that Diakonia takes to address governance challenges under its four focus themes:
- Reforms and strengthening of key democratic institutions and processes.
- Expansion and protection of civic space.
- Deepening democracy through active citizen participation.
- Enhancing and deepening accountability, transparency, and anti-corruption measures.
The DDF has exceeded expectations in stakeholder engagement (Indicator 1.1), with 38 key actors involved across various governance dialogues. Discussions on transparency, accountability, and anti-corruption, CDF guidelines, and cyber legislation were particularly active. The discussions brought together a broad spectrum of actors, from government, CSO, and media.

One new workstream (Indicator 1.2) emerged from the discussions with stakeholders- the Transparency, Accountability and Anti-Corruption workstream. For each workstream, DDF then holds discussions using the Problem-Driven Iterative Adaptation (PDIA) methodology to break down the problem and generate ideas for how to promote change (Indicator 1.3). Eight ideas were generated using the PDIA approach, which are reflective of the issues that Zambians care about and those that are most pressing:
1. Promote public participation and accountability (Short-term)
2. Strengthen oversight institutions and legal protections (Long-term)
3. Promote transparency in judicial proceedings (Short-term)
4. Promote integrity and evidence-based practices (Medium-term)
5. Decentralize services and improve access to information (Long-term)
6. Leverage digital platforms and public movements (Short-term)
7. Support civil society and community involvement in Anti-Corruption efforts (short term)
8. Monitor public procurement (long term)

Viable initiatives are then prioritised for funding (Indicator 1.4). Three new initiatives were started:
1. The My ID Campaign implemented by Alliance for Accountability Advocates (AAAZ), addressing inefficiencies and corruption in Zambia’s national registration process, in collaboration with the Anti-Corruption Commission (ACC) and the Ministry of Home Affairs.
2. The Corruption Spotlight Series, implemented through BBC Media Action in collaboration with investigative journalists, worked to expose everyday corruption in service delivery through four investigative pieces.
3. The Cyber Security Bill CSO alliance campaign, led Chapter One Foundation, reviewed the draft legislation and engaged constructively with government agencies to revise the bills to protect human rights and civic space.
While this output achieved its objectives, it could go further by engaging more widely across civil society. It is common in development programmes for partners to coalesce with other organisations that share their objectives and intent, typically other NGOs and CSOs. However, in practice, many actors play a role in achieving development, such as politicians, bureaucrats, business leaders, social movements, religious groups, traditional structures and citizens. Coalitions of these actors can be formalised, but more often they represent an alignment of interests behind an issue and may never meet. Convening, coalescing and strengthening coalitions of these actors on different issues can build broader and more sustained momentum towards reform.
Recommendation: In the next year the DDF should think more broadly about what constitutes civil society and how coalitions of non-traditional development actors can help drive reform.

Output Title	DDF supports the implementation of agreed initiatives to address governance challenges.
Output number:		2	Output Score:	A
Impact weighting (%):		22%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of grants provided to implementing partners (iterative)	2 grants	Met. 1 grant provided to SAIPAR. 2 activity-specific grants provided to AAAZ and the CSO Alliance.
2.2 Degree to which the partners have implemented and completed the grant in a satisfactory manner (iterative)	90%	Partially Met. 85%. All partners, except for CTPD have implemented and completed their grant in a satisfactory manner.

Output 2 measures the extent to which DDF-funded initiatives are effectively implemented to address governance challenges. Over the past year, the programme provided grants and activity-based funding to three new partners (Indicator 2.1), taking the total number of partners under the DDF to 14. One new grant was provided to SAIPAR to conduct a longitudinal research study on the dynamics of constituency political developments in the run up to the 2026 elections. SIAPAR will also undertake an evaluation of the Government’s Cash for Work initiative. AAAZ was provided activity-based grant funding to implement the My ID Campaign. Additionally, the DDF provided emergency support to CSO alliances advocating against restrictive cybersecurity legislation, contributing to the deferment of the Cyber Security and Cyber Crimes Bill in Parliament.

Grant implementation (Indicator 2.1) has been largely on track:
- The social accountability work delivered by Alliance for Community Action (ACA), Jesuit Centre for Theological Reflection (JCTR) and People’s Action for Accountability and Good Governance in Zambia (PAAGZ) continued, but has achieved mixed results. In the short-term, monitoring has shown that following the trainings, citizens and local committees requested additional information from local authorities and held them to account for delayed or unsatisfactory projects. However, longer-term monitoring shows that many trainees did not continue accountability activities beyond the facilitated sessions, suggesting that knowledge alone wasn’t enough to spur ongoing action, and social accountability interventions do not become self-sustaining (i.e. when project activities pause, so does the accountability momentum). In districts where there was strong government engagement, like Chongwe, social accountability efforts gained more traction, demonstrating that partnerships with local authorities are critical to success. Early indications suggest that this approach is increasing the sustainability of interventions. Similarly, there is also indication that social accountability training has varied impact across rural and urban settings. In rural settings, where traditional and community authority structures influence how communities engage with governance issues, direct confrontation with officials does not align with the cultural approach to resolving issues. As such, DDF has incorporated traditional leaders and community leaders, such as headmen and women, to champion accountability and participation.
- BBC Media Action supported six community radio stations (BYTA, Ichengelo, KNC, Mphangwe, Chongwe radio and Radio Mazabuka) to deliver 167 radio programs on the CDF. BBC Media Action provided mentorship to all the stations to deliver interesting, unbiased and evidence-based content. Under the Corruption Spotlight Series, BBC Media Action worked with MakanDay Centre for Investigative Journalism to support five investigative journalists to produce and broadcast four investigative pieces on everyday corruption.
- Kivu provided technical assistance to central government stakeholders (State House, Presidential Delivery Unit, Chief Economist Office etc) on economic policies such as youth employment, the Sustainable Agriculture Financing Facility, Cash for Work and Animal Health. Kivu focussed this year on implementing the FISP e-voucher rollout, which supported the government to achieve a benchmark related to the IMF Extended Credit Facility.
One partner did not complete their grant as anticipated. The Constituency Development Fund (CDF) dashboard being developed by the Centre for Trade and Policy Development (CTPD) faced obstacles in securing buy-in from the Ministry of Local Government and Rural Development. As such, the CTPD grant was discontinued. Unsuccessful interventions are expected in adaptive programmes. For every transformational change that is supported, several others may fail. To achieve value for money, it is therefore critical that partners focus selectively on issues with political traction that are likely to achieve results, and exit non-performing interventions quickly.

Output Title	DDF uses learning and best practices to influence governance policy and reforms.
Output number:		3	Output Score:	A
Impact weighting (%):		22%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of short learning papers/policy notes developed and shared by DDF (iterative)	19 Learning Papers	Partially Met. 15 Learning Papers developed (3 pending).
3.2 Number of communication products developed (infographics, articles, brochures, interviews, posters, radio shows etc) (iterative)	179 communication products	Exceeded Expectations. 183 communication products developed.
3.3 Number of learning events/reflection meetings with partners, CSOs/governance actors to share lessons and best practices on the DDF (iterative)	8	Exceeded Expectations. 15 learning events/reflection meetings held.
3.4 The level to which initiatives prioritized have been scaled up under any DDF theme (iterative)	4 DDF Partner initiatives scaled up	Met. 4 Partners scaled up their programming and included new geographical areas.

Output 3 focuses on ensuring that lessons from DDF-funded initiatives contribute to broader governance reforms. Over the past year, DDF partners produced a range of learning papers, policy briefs, and reflection reports to capture insights from project activities (Indicator 3.1). Papers covered themes such as decentralization, public financial management, the role of traditional leaders in social accountability and the role of media as a platform for strengthening governance. These documents provided an evidence base for policy advocacy and governance reforms. The CDF learning paper in particular fed into national discussions on improving the transparency of local government financing and was shared with the MLGRD.

The learning papers were complemented by learning events, stakeholder dialogues, and media engagement, all aimed at translating evidence into policy influence (Indicators 3.2/3.3). DDF facilitated media-driven knowledge dissemination, using radio dialogues and policy forums as platforms for citizen engagement, bridging the gap between grassroots learning and national policymaking. In total, 183 communication products were developed. This includes 167 radio programme, 4-episode drama series, posters and brochures. There were 15 learning and reflection events held, focused on cross-learning amongst partners and policy makers. 12 of these events were internal to DDF partners and FCDO. One learning event was held on the CDF and two dissemination meetings were held to share findings on the CDF and corruption studies.

Indicator 3.4 measures the extent to which initiatives have been scaled up under any DDF theme. At a micro level, initiatives which have proved successful under the DDF have been scaled. JCTR expanded its social accountability approach into new wards in Bwacha and Nkana constituencies. ACA expanded its work into new two constituencies (Magoye and Mkaika) and used a Train the Trainer model to reach more citizens in the four constituencies where the project is operating. PAAGZ also scaled up to two new urban wards – Madindo and Ntandabale. At the macro level, Kivu supported the Government to roll out the FISP e-voucher model in 74 districts. The Government has committed to completing the roll-out to all other districts in the 2025 farming season.

The 2024 Annual Review recommended that the ZGDP should increase learning across the programme through issue and partner-based learning papers. This recommendation recognised that the real impact of the DDF will be its ability to advocate for wider reforms. In developing learning papers, FCDO encouraged the DDF to keep in mind that the spirit of this output is not in the production of the papers themselves, but the extent to which they are used to advocate for change with decision makers (Outcome 1). While the uptick in learning papers and events this year is positive, government responsiveness remains limited, and advocacy strategies have not been effective in increasing the uptake of recommendations. Ensuring the lesson learned are integrated into policymaking requires more sustained engagement with reform-minded actors in government.

Recommendation: Learning outputs must be closely tied to advocacy and engagement plans. In addition, DDF should involve policymakers earlier in the research process and tailor briefs to address specific policy questions. This increases the likelihood that evidence will be seen as relevant and lessons acted upon.

Output Title	ICAR equips Zambia with appropriate competences and skills to effectively use their legal and enforcement instruments to recover stolen assets.
Output number:		4	Output Score:	A
Impact weighting (%):		16.5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1. Percentage of ICAR trainees who testify to the effectiveness of ICAR training for their work (iterative)	65%	Met expectation. 65% of trainees reported improvement in effectiveness.
4.2. Number of trainees successfully completing ICAR training (iterative)	110	Met expectation. 125 trainees participated in the Train the Trainer sessions, from ACC, the Judiciary, NPA, DEC, ZRA, and FIC as of October 2024

Output 4 measures ICAR’s anti-corruption training and capacity-building efforts. The training is aimed at equipping Zambian law enforcement agencies with the skills and tools necessary for effective asset recovery. It has scored an A (met expectation).

There has been strong progress in training delivery, knowledge retention, and the application of best practices by investigative teams. The Train the Trainer (TTT) model continued, with 125 professionals from ZACC, DEC, NPA, FIC, and ZRA successfully completing specialized financial crime investigation training by March 2025 (Indicator 4.2). To ensure long-term sustainability, a core group of five trainees is being mentored to become certified trainers, enabling in-country institutions to conduct future training independently.

As usual practice, feedback surveys were carried out three months post training to assess the effectiveness of the training. 65% of trainees reported an improvement in their effectiveness (Indicator 4.1), though low response rates suggest actual impact may be higher. Case based learning through mentorship yielded the best results, demonstrating how skills are applied in real investigations.

Alongside the formal trainings, ICAR’s embedded experts also mentor staff within the law enforcement agencies. This ensures that training is translated into practical application. Investigative teams successfully employed ICAR-informed asset-tracing techniques, contributing to cases involving cross-border money laundering, procurement fraud, and illicit financial flows.

There are key lessons for enhancing sustainability, retention, and practical application of skills. The TTT model has proven effective, but its institutionalization within ZACC, DEC, and NPA is necessary to ensure long-term impact. In practice this would be a training resource dedicated within agencies including personnel, curriculums and materials, and accreditation. Retention of trained officers remains a challenge, as frequent staff reassignments create knowledge gaps. There is need for structured career pathways for specialized investigators.

Recommendation: ICAR to work with the law enforcement agencies on a structured model of staff training (career pathways, curriculums, accreditation etc.) that the agencies can implement beyond the life of UK funding.

Output Title	ICAR supports Zambia to introduce suitable tools, procedures, instruments, policies or institutions to recover and manage stolen assets.
Output number:		5	Output Score:	A+
Impact weighting (%):		16.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1. Examples of ZACC, DEC and/or NPA employing ICAR informed approaches and tools (iterative)	4	Met expectation. 4
5.2. Number of multi-jurisdictional operational or case-based meetings conducted because of ICAR’s intervention and with ICAR participation/facilitation (iterative)	8	Exceeded expectation. 23
5.3. Progress on policy and legal reform, key system or process change influenced because of ICAR interventions to strengthen the anti-corruption environment and institutionalise asset recovery (iterative)	ICAR introduce at least one system or process change initiatives to strengthen the anti-corruption environment and institutionalise asset recovery.	Met expectation. ICAR has supported 2 key reform and process changes: one policy on asset recovery and management of assets; and one legal reform in Mutual Legal Assistance aimed to address institutional gaps.

This Output measures the extent to which agencies implement the best practice approaches to strengthening the anti-corruption environment that ICAR has introduced, and how these approaches can be made more sustainable in the Zambian context through legal, policy, and process reforms. This output has scored A+, exceeding expectations.

For example, with ICAR support, ACC has increased its capacity for structured financial investigations, directly enhancing Zambia’s capacity to investigate and recover stolen assets. The ACC investigative teams applied ICAR-informed approaches and tools, including asset-tracing, forensic analysis, and cross-border cooperation, in at least four high-profile cases. These techniques helped to secure the forfeiture of $32 million in corruption-linked assets. Investigators also integrated forensic auditing tools to strengthen evidence collection in two procurement fraud cases. ICAR’s expertise in asset-tracing led to the freezing of $11 million in Switzerland and improved handling of digital evidence in money laundering cases. ACC successfully presented forensic evidence gained through engagement with Hong Kong authorities to track illicit financial flows.

To achieve results, Zambia has had to improve its coordination across jurisdictions (Indicator 5.2). Throughout 2024, ICAR facilitated 23 multi-jurisdictional meetings for Zambia with Hong Kong, China, Panama, Spain, Saudi Arabia, India, Mauritius, Nigeria and others. This has significantly enhanced Zambia’s international cooperation on asset recovery and financial crime investigations, which is critical for securing evidence, freezing illicit assets, and strengthening legal cooperation. Five meetings were held across South Africa, Jersey, and Switzerland, leading to the freezing of $11 million and intelligence-sharing on money laundering cases. 12 meetings, including engagements at the Global Forum for Asset Recovery (GFAR) Action Series in Vienna, allowed Zambia to expand cooperation with 10 jurisdictions including UK, UAE, and USA. Six meetings were conducted, with a focus on cooperation with Hong Kong, Turkey, and the Isle of Man, resulting in progress on a £150 million money laundering case.

ICAR has successfully introduced multiple system and process change initiatives that have enhanced inter agency cooperation and modernized the investigative processes, resulting in higher efficiency and effectiveness (Indicator 5.3). In 2024, ICAR progressed the previously identified opportunities to influence policy/legal reforms and process change opportunities). This includes:
1. Streamlined Mutual Legal Assistance (MLA) request procedures under the DPP’s office.
2. Established an Asset Management Unit and new guidelines.
3. Drafted an Inter-Agency Asset Recovery and Management Bill for Cabinet approval.
4. Challenged restrictive judicial interpretations to safeguard asset recovery.
5. Procured forensic tools and software to enhance digital investigations.
6. Conducted legislative review and developed a draft MLA bill.
7. Proposed a shared case management system for DEC, NPA, and FIC.
8. Proposed amendments to the anti-corruption act that strengthen provisions on public officials, conflicts of interest, and prohibited gifts.
9. Drafted a national asset management policy.
The streamlining of the MLA process significantly reduced delays and increased the level of cooperation with other jurisdictions, which has previously been a major barrier to retrieving evidence that leads to recovery of assets. The creation of the asset management unit, along with new guidelines, has created a dedicated structure for managing seized assets. Previously, the lack of an asset management system led to the depreciation of value of assets, meaning that although the asset was recovered, this did not result in a material gain for the state. This newly established unit will create the capability for the state to maximize the value of seized assets. However, there is still a need to put into effect the national asset management policy and to pass the Asset Management Bill to more deeply institutionalize asset management. In the coming year, there is need to prioritize the legal reforms that will further strengthen asset recovery in Zambia. The lack of concrete progress on key pieces of anti-corruption legislation demonstrates that while UK support has made considerable impact in fighting corruption (and particularly on recovery of assets), that support continues to be delivered against a context of vested interests that have prevented deeper reform.

Recommendation: ICAR should use 2025/26 as a transition year to support the agencies to sustain the approach to asset recovery beyond UK support.
## D: VALUE FOR MONEY

We assess that this programme continues to deliver value for money (i.e., the benefits of our investment on development impact in Zambia outweigh the costs). The programme model (a combination of technical assistance, research and adaptive support to CSOs and media organisations) means the UK can have impact at scale for relatively small investments. The focus on testing and learning ensures that programme activities are delivering the desired impact and creates the culture for adjusting where required. It also builds the evidence base for future UK investments in this space. Value for Money (VfM) is analysed through the lens of the ‘fours E’s’: economy, efficiency, effectiveness and equity.

The 2024 Annual Review highlighted two key findings:
- Firstly, running an adaptive programme at a small scale (with multiple small initiatives) is less efficient than if it were run at a larger scale. It would be more cost-effective to operate at a larger scale because the ratio of management costs to project delivery would be optimised. Progress has been made on this area in 2024/25. There has been a 38% increase in the forecast outturn for Diakonia this year. Management costs (as a proportion of forecast outturn) have reduced from 34% in 23/24 to 31% in 24/25. This shows that the DDF is delivering more, and the management is becoming more efficient. Diakonia produced a series of papers on adaptive programming to support the DDF and wider development programmes, including on monitoring and evaluation mechanisms and processes and procedures. Processes and procedures have improved in 2024/25 (in part due to the consistency of the programme teams).
- Secondly, the real impact is not just in the activities themselves, but the extent to which the learning and evidence generated from activities are translated into advocacy for policy and legislative reforms. There has been some success in translating activity from projects into policy and legislative reforms. Support to the FISP e-voucher is the most notable success, where an investment of £240,000 in technical assistance led to a reform with significant macroeconomic impacts, saving the Government $80,000,000 and creating thousands of rural jobs. This is a strong example of how programmes like this can be effective.
More broadly, we remain confident that the partners are achieving value for money in their work. For example, to achieve economy, Diakonia uses its procurement guidelines to secure the lowest cost when paying for goods and services. This includes using community halls/schools/churches for community trainings, which are either free or low cost. Diakonia also used in-house trainers from the Diakonia Regional Office to build capacity on value for money and risk management, meaning no facilitation fees needed to be paid. ICAR seeks multiple quotes for goods and services to minimise cost and utilises its Conflict-of-Interest policy to reduce the risk of staff involvement in transactions where a conflict of interest exists.

By maintaining a clarity of purpose in reducing poverty and promoting growth in all aspects of the programme, we can contribute towards more equitable development in Zambia. Supporting policies which better meet the needs of the poorest Zambians are critical for having impact at scale in this area. The programme must also ensure it engages with the widest variety of individuals possible. For example, through its community engagements, ACA reached 2,769 citizens. This included 1,451 men, 1,318 women and 33 people with disabilities. JCTR reached 282, of which 136 were men, 146 were women and 16 were people with disabilities. The geographic spread of projects helps ensure diversity of engagement (rural/urban etc). It also helps address the disconnect in Zambia between national policy making and rural populations. For ICAR, equity is most directly achieved through the make-up of the training attendees. In total, there were 27 females and 43 males, making up the 70 participants across the three TTT sessions. This is a lower gender parity ratio than last year, but ICAR is restrained by the trainees put forward by the agencies.

Both ICAR and Diakonia have VfM frameworks that are regularly updated to assess VfM against the ‘Four Es’. FCDO reviews this through its regular monitoring. Spot-checks provide assurance that the policies that underpin the partners approach to VfM are being followed.

E: RISK

The overall risk rating for ZDGP remains moderate and the programme continues to operate within BHC Lusaka’s risk appetite. Both ICAR and Diakonia regularly update their risk registers (including for risk across their delivery chains) to reflect evolving contexts and ensure proactive risk mitigation. FCDO updates its programme-level risk register at least quarterly (or on an ad hoc basis) and escalates risks where necessary.

Risk Category	Summary of Risks	Risk Appetite	All risks within appetite?
Policy and Programme Delivery	ZDGP was scheduled to close in March 2025. FCDO subsequently decided to extend the programme, but this created potential difficulties for partners who were planning to wind down activities. Risks included a high possibility of staff turnover, delays in replacing staff, and subsequent delays in implementing and completing project activities. The programme team and implementing partners proactively and collaboratively mitigated potential challenges by closely monitoring recruitment and retention of staff, maintaining detailed project plans, and developing a comprehensive exit strategy. Local stakeholders were also engaged to ensure smooth transitions and minimize the impact on communities if project activities ended. These mitigation measures were crucial in ensuring the programme's stability and the sustainability of key project activities.	Receptive	Yes
Strategy and Context	As we approach the 2026 General Election, heightened political competition and government civil and political discourse pose risks to project activities. Proximity to an election is often marked by a reduction in long-term legal and constitutional reforms in favour of those that provide short-term political advantage instead. These risks are compounded in Zambia by socioeconomic challenges, including high poverty levels, significant food and non-food inflation (such as fuel prices), the worst drought in living memory and severe loadshedding, which add additional pressure on the government. The flexible and responsive nature of the programme is designed to meet an evolving context. The programme team continues to closely monitor and evaluate the evolving political context, collaborating with like-minded stakeholders to design interventions that protect and expand civic space and contribute to progressive reforms. Considering the above, the strategy and context risks for the ZDGP remains within our risk appetite.	Receptive	Yes
Financial and Fiduciary	The programme has consistently operated within the FCDO's acceptable risk levels. The model used by Diakonia, working through several downstream partners, brings a higher risk of financial mismanagement, which is actively managed by the project team. ICAR does not provide any downstream funding, reducing the risk. All partners implement a strict zero-tolerance policy towards fraud and monitor financial risks. Diakonia conducts expenditure verifications before disbursing grants and performs random spot checks on downstream partners to provide further assurance on these risks. FCDO conducted a Fraud Risk Assessment for Diakonia covering the entire delivery chain, which revealed an overall risk rating of "major." This indicates the variety of financial risks under this programme, but it also shows that risks remain broadly stable and are being managed appropriately. / The poor performance of the kwacha against major currencies increased the risk of exchange rate fluctuations, potentially leading to underspending. However, the programme team collaborated with the Diakonia to maximize the gains by redirecting funds towards project activities.	Cautious	Yes
Safeguarding	Like Finance and Fiduciary risks, the FCDO and its partners adhere to a zero-tolerance approach towards Sexual Exploitation, Abuse, and Harassment (SEAH). The risk remains within acceptable limits, recognizing the possibility that staff involved in the programme might abuse their positions of power, leading to harassment, sexual exploitation, or abuse of participants or beneficiaries. To mitigate this, FCDO ensures that details on how to report SEAH concerns are shared and well-known among partners, local authorities, and participating communities. Additionally, the FCDO ensures that staff from Diakonia, BBCMA, downstream partners, and consultants sign and adhere to the Code of Conduct, which prescribes appropriate conduct and outlines the consequences of misconduct related to SEAH.	Cautious	Yes
Public Service Delivery & Operations	The reduction in the UK's Official Development Assistance (ODA) budget from 0.5% to 0.3% of Gross National Income (GNI) is likely to significantly impact various aid programmes. With less funding available, there will be a decrease in the number and scale of supported programmes. The impact on Zambia will be exacerbated by the pause and termination of USAID-funded programs globally. The UK government will need to make strategic decisions on how to allocate the reduced budget, potentially leading to difficult trade-offs and underfunding in some areas as a mitigation.	Cautious	Yes
Reputational	The year under review mirrored the previous year, featuring activities that promote democratic governance, such as media freedom, civic space, and perception surveys on public services and corruption. These activities are politically sensitive and could potentially lead to issues that may affect the long-standing partnership between the UK and Zambian governments, thereby posing reputational risks for the UK Government. Reputational risks are mitigated through effective diplomacy, political analysis and adapting programmes where necessary.	Cautious	Yes

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery Performance

- Diakonia- Diakonia have performed well this year. Diakonia consistently submits quality quarterly reports and compliance documents on time. All the due diligence actions have been closed, and the asset register is up to date. Funding cuts from the Swedish government posed a significant challenge to programme resources. However, the gap was mitigated by additional funding from FCDO which helped stabilise the budget and maintain programme staff responsible for the implementation of the DDF project. The Diakonia team improved its financial forecasting (which proved challenging in previous years) by strengthening financial oversight and improving internal processes. Frequent power outages in Zambia disrupted daily operations and programme activities; FCDO therefore agreed to cover the partial cost of back-up solutions to ensure uninterrupted functionality. Staff transitions were carefully managed to prevent operational disruptions.
- ICAR- BHC Lusaka’s Accountable Grant agreement with the Basel Institute of Governance came to an end on 30/10/2024. However, FCDO continued supporting the Basel Institute’s work with the Zambian Government through funding from the Illicit Finance and Anti-Corruption Office (IFAC) until 31/03/2025, under the Fighting Corruption Globally Programme. As BHC Lusaka’s grant ended, closure requirements were completed (though BHC Lusaka intends to restart funding to ICAR in April 2025). During the reporting period, ICAR actively coordinated the quarterly Steering Committee meetings to facilitate strategic oversight and cross-departmental coordination and. ICAR consistently submitted high quality narrative and monthly financial reports. Assets (particularly those given to agencies) are carefully monitored, with tracking systems in place to ensure proper maintenance and accountability.
- FCDO- There have been no changes in the FCDO management team this year which provided continuity and stability to the programme. The FCDO team maintained a robust governance structure, fostering collaborative decision making and alignment. Through monthly and quarterly meetings, the team provided oversight, managed risk and reviewed project performance. FCDO has supported various DDF workstreams, providing technical guidance, and oversight to strengthen the democratic process. The team successfully managed the closure of the ICAR project, ensuring a structured exit process that included responsible disposal of project assets in compliance with FCDO guidelines. Recognising the delay in finalising the successor Effective State to Democracy Business Case, the programme team extended the current programme to ensure continuation of critical project activities and facilitate a smooth transition to the new programme.

Financial Performance
Financial management has been satisfactory across both partners. Diakonia and ICAR submit monthly financial reports. All reports have been received and approved by the SRO. The financial reports have clear information on spend against budget and summary notes on any changes made to budget lines.

Diakonia- The overall 2024/25 budget of GBP699,940 was adjusted to GBP1,376,298. The programme spend between April 24 and February 25 is at 62%. The 38% difference is expected to be spent in last month of 2023 FY (March) with a very minimal variance. An overview of Diakonia’s finances is presented in this table:

Activity	Budget 23/24	Actual Spend (as of Feb 24)	% Burn Rate (as of Feb 24)	% of budget allocated to activity
Programme activities	1,043,503.00	636,170.00	61%	76%
Staff Costs	168,484.00	142,731.00	85%	12%
Management Fees	94,024.00	45,053.00	48%	7%
Overheads (Office costs)	70,357.00	34,241	49%	5%
Total	1,376,298.00	858,125.00	62%	100%

ICAR- ICAR utilised the entire 24/25 budget of £461,039. The spend mainly covered programme activities, including training expenses, expert fees, travel, and asset procurement. An overview of ICAR’s finances is presented in this table:

Activity	Budget 23/24	Actual Spend (Full programme spend)	% Burn Rate	% of budget allocated to activity
Programme activities and expert fees	361,407.00	361,407.00	100%	78%
Staff Costs	39,845.00	39,845.00	100%	9%
Overheads (Office costs)	59,787.00	59,787.00	100%	13%
Total	461,039.00	461,039.00	100%	100%

Commercial Performance

- Diakonia- The DDF adopts Diakonia and BBC Media Action processes for contracting downstream partners, selecting strategic civil society organizations with aligned development goals and values through partnership assessments, risk management, and capacity development. The procurement in this reporting period included venue hire for partners, media campaigns, training and capacity building. The spend was in line with the agreed budget and workplan.
- ICAR- ICAR has internal controls systems and standards for finance and a procurement policy. ICAR conducts thorough market surveys as part of the procurement processes. This reporting period, ICAR procured a solar back up power system, two pieces of forensic lab equipment and a bulk evidence storage system. Other procurements include hiring venues for training workshops on financial investigations and asset recovery.

G: MONITORING, EVIDENCE AND LEARNING

For the 2024/25 year, ZDGP was scheduled to be monitored through annual spot checks, monitoring visits, outcome harvesting, steering committee meetings, quarterly narrative reports and bi-monthly reflection meetings. Below is the presentation of monitoring activities implemented in the year under review with examples drawn from the activities of implementing partners.

Monitoring

- Quarterly and ad-hoc reporting/ meetings- ICAR and Diakonia provide FCDO with quarterly narrative reports, covering contextual changes, progress on implementation and updates on risks. Reporting has been of a good quality throughout the year. Following submission of the reports, FCDO holds reflection meetings with partners. Diakonia held reflection meetings with its downstream partners on a bi-monthly basis. In 2024/25, 15 meetings were held, showing the importance of pausing during implementation to reflect on the progress and course correct to improve outcomes in future interventions.
- Spot checks- Annual spot checks are conducted to provide assurance to FCDO that controls are in place and operational. The spot check conducted on Diakonia in March 2024 did not flag any major risks on financial management, downstream partner assessment, risk management, due diligence, fraud or safeguarding. The spot check for ICAR was completed in July 2024; similarly, it did not flag any major risks.
- Monitoring visits- Both FCDO and Diakonia have done monitoring visits this year. FCDO visited projects in Katete and Chongwe. Diakonia visited all partners/ constituencies when project activities were being undertaken. In Kitwe, Mazabuka and Katete, the monitoring visits also accompanied outcome harvesting exercises. The visits included field observations, interface meetings, and in-depth interviews with key stakeholders and community members.
- Outcome Harvesting- Diakonia uses outcome harvesting to monitor observable changes that occurred due to project activities, especially in rightsholders and duty bearers. Observable changes are recorded in the outcome register shared with FCDO on a quarterly basis. For example, one of the results recorded in Mkaika constituency revealed that community members that attended training sessions facilitated by the project-trained trainers started demanding that their local committees and councillors provide detailed reports on how CDF funds were used in their area. These trainers also began to be regarded as advisors, supporting the community members in the filling in of various forms in CDF applications. This was a shift from previous year when such discussions were avoided, as the baseline in 2023 showed.
- Steering Committee Meetings- ICAR holds Steering Committee meetings each quarter. These are attended by FCDO and the heads of agencies (Anti-Corruption Commission, National Prosecution Authority, Drug Enforcement Committee, Financial Intelligence Centre). The meetings are used to foster inter-agency cooperation, agree the strategic direction for the programme and assess the extent to which embedded advisors have achieved their goals.

Evidence and Learning

The evidence underpinning this programme has not changed this year. Stronger democracies have on average, higher economic growth, better health outcomes, improved access to education, better gender equality and are less prone to domestic and international conflicts. There is evidence that Zambia’s democracy suffers from weaknesses in the functioning of government, corruption, insufficient economic growth and deficient delivery of public goods. The programme is targeting relevant areas to address these issues, and we are increasingly learning how best to target our support to have the greatest impact. Key lessons learned are outlined in Section 2.

In 2024/25, DDF conducted four research pieces: CDF Follow-Up study, Everyday Corruption study, CDF Corruption Perception study, and the Transparency International Zambia study on assessing transparency in Zambia's political party financing. The Everyday Corruption Study showed that Zambians perceive corruption to be a normal aspect of life and useful for getting around slow government services. This study was evidence for the creation of the TAA Workstream, focusing on public education and changing attitudes toward corruption, not just legal fixes. The CDF Follow-Up Study provided insights into the implementation challenges of CDF, influencing DDF’s approach to strengthening community participation, improving local committee engagement, and enhancing accountability mechanisms. These studies helped DDF focus on real issues, guide advocacy work, and improve community involvement in governance.

FCDO has reviewed the evidence underpinning the anti-corruption work. Broadly, corruption hampers economic growth by diverting public resources, distorting market efficiencies, increasing the cost of doing business, and deterring investment. There is some evidence that corruption can ‘grease the wheels’, particularly in places with weak institutions (but this evidence is inconclusive). Evidence does show that the negative effect of corruption on growth is substantially larger in democracies than in autocracies. This suggests that anti-corruption efforts and resources should be targeted to where corruption is most harmful –young democracies like Zambia (where institutions are weaker, and corruption is more decentralised). The evidence on what anti-corruption interventions are most effective is mixed. Under ZDGP, the focus has been on the response side (increasing the risks involved with engaging in corruption) rather than prevention. But asset recovery/ prosecutions have not thus far shifted the underlying causes of corruption in Zambia, and in an environment where institutions can be politized, the risks of targeted prosecutions remain high. FCDO is in a mode of continual learning to ensure that investments in anti-corruption leads to sustainable change.

Date of last narrative financial report	27/02/2025	Date of last audited annual statement	19/02/2025

Annex A: Progress on Recommendations from March 2023 Annual Review

Recommendation	Progress
At present, the community training is small-scale. There is value in scaling this work up, particularly in rural areas and for Ward Development Committees. This should be considered for the next year of the programme.	Complete. JCTR expanded its social accountability approach into new wards in Bwacha and Nkana constituencies. ACA expanded its work into new two constituencies (Magoye and Mkaika) and used a Train the Trainer model to reach more citizens in the four constituencies where the project is operating. PAAGZ also scaled up to two new urban wards – Madindo and Ntandabale.
Increase learning across the programme through issue and partner-based learning papers (with corresponding advocacy plans to contribute to Outcome 1).	Partially complete. There has been an uptick in learning this year, which is positive, but this remains a focus area for the programme moving forward. Learning outputs must be closely tied to advocacy and engagement plans. In addition, DDF should involve policymakers earlier in the research process and tailor briefs to address specific policy questions. This increases the likelihood that evidence will be seen as relevant and lessons acted upon.
De-conflict ICAR training from training delivered by other suppliers to reduce the risk of duplication or low take-up.	Complete. ICAR engaged with other service providers to ensure trainings are not duplicative. However, the agencies advised that some duplication is helpful because not all their staff can attend every training course, so they can manage attendance to allow all staff to expand their skills.
Conduct a programmatic review to streamline the administrative and approval processes. If required, consider extending the external consultant to provide additional technical support.	Complete. Diakonia produced a series of papers on adaptive programming to support the DDF and wider development programmes, including on monitoring and evaluation mechanisms and processes and procedures. Processes and procedures have improved in 2024/25 (in part due to the consistency of the programme teams). Clarifying administrative and approval processes should be done at the outset of future programmes.
Complete a Fraud and Safeguarding Risk Assessment to identify risks, reviews controls that are in place and assess the extent to which these controls are working.	Partially complete- A fraud risk assessment was undertaken for Diakonia in February 2024. There was no fraud risk assessment of ICAR in 24/25 because of the lapse in the agreement. FCDO did not undertake Safeguarding Risk Assessment’s, but all partners attended FCDO-led trainings and have the required policies in place. Assessments will be completed in 25/26.