BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Zambia Democratic Governance Programme (ZDGP)
Directorate/ Post	BHC Lusaka	Contact name	Kate Wilkinson
Original programme budget	£4,500,000 (increased to £12,000,000 in Mar 25)	Country or region targeted	Zambia
Cost extension value (if applicable)	£3,000,000	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	HoM (+ Ministerial approval in Sep 24)
New increased or reduced programme budget (if applicable)	£15,000,000	Original programme start and end dates	20/10/2020 – 31/03/2024 (extended to 31/05/2026 in Jan 25)
Latest AR programme score	A	New programme end date (if applicable)	31/03/2027
		Programme ID	301270

Detailed information
Programme summary	The UK is providing £12,000,000 to strengthen democracy and governance in Zambia. We do this by working with the Zambian government to support more evidence-based decision making, by strengthening Zambia’s institutions to deliver more effectively for citizens and by working with communities to increase their participation in, and demand for transparency and democracy. The programme aims to bring stakeholders together to address key challenges or opportunities that we foresee in the lead up to the 2026 elections and immediately after. These include the need to strengthen key democratic institutions, the closing of civic space, combating corruption, the move towards decentralisation and the need for continued push for strong government policy reforms, with a strong and adaptive delivery model. / The programme has performed well over its lifetime, scoring an ‘A’ (met expectation) in all four of its Annual Reviews. In 2025, Diakonia’s Deepening Democracy Facility drove major governance reforms and civic engagement across Zambia. It facilitated the deferment of Constitutional Amendment Bill No. 7 through coordinated CSO advocacy, established seven provincial hubs, and advanced inclusive reform dialogues. The programme secured government buy-in for a national Ward Development Committee curriculum and piloted a CDF dashboard to strengthen transparency. It operationalized the Access to Information Act and accelerated Data Protection implementation, enabling enforceable citizen rights. Civic space was strengthened through advocacy on digital rights and reforms to safeguard freedoms, while media programming amplified citizen voice and improved responsiveness from duty bearers. Social accountability initiatives enhanced oversight of public funds and service delivery in sectors such as health, education, and agriculture. Economic governance advanced with the full rollout of the FISP e‑Voucher system, adoption of SME tax measures, and progress on agricultural legislation toward parliamentary review and possible enactment. Anti‑corruption efforts included campaigns and investigative reporting that exposed systemic abuse, reinforcing transparency and accountability.
Changes	This addendum will increase the programme value by £3,000,000, to £15,000,000. As of the last quarter of FY25/26, there is ~£2,500,000 remaining headroom in the Business Case. BHC Lusaka has reviewed the opportunities in 2026, which is an election year in Zambia, and have identified several areas that the UK should continue/begin investing in. These include (but are not limited to): / Cyber security and media freedoms- Strengthening and promotion of viable and independent media, promote digitally literate, cyber secure users and inclusive online spaces of engagement, and strengthen the enabling environment for independent and new media. / Elections- This will include voter education, sensitization on the new constitutional changes, long-term pre-election observation, political polling to ensure a free, fair and credible election in 2026 and immediate post-election support to include rapid-response mechanisms for electoral petitions and public communication strategies to maintain transparency and trust during results collation. / Civic space- Advocacy on civic space issues, including reform of the Public Order Act, Electoral Code of Conduct revisions, Access to Information Act operationalization, and Media Freedom and Safety protocols / Agricultural reforms- We will support the Government of Zambia finalize the reform of three pieces of legislation before parliament dissolves in the lead up to the elections: the Food Reserves Act, the Agriculture Marketing Act, and the Agricultural Credits Act. These acts will address key constraints within the country’s agriculture and agro-processing sectors and once reformed, will unlock a $500 million compact between the Government of Zambia and the Millenium Challenge Corporation. / This is the sixth addendum to the programme. The first addendum (in June 2022) expanded the scope beyond the 2021 elections support. The second addendum (in September 2023) increased the value by £450,000 and extended the end date by nine months. The third addendum (in August 2024) extended the value by £2,050,000, to £7,000,000 in total and extended the life of the programme by one year, to December 2025. The fourth addendum (in January 2025) extended the end date to 31/05/2026. The fifth addendum extended the value by £5,000,000, to £12,000,000 in total without extension of the programme life. This addendum will increase the programme value by £3,000,000 and extend the life of the programme by ten months to 31/03/2027. It will not materially change the focus of this programme or its Theory of Change. We expect Value for Money to improve because there will be an increase in delivery relative to the input costs. / If we do not approve the cost and time extension, the programme will conclude on 31/05/2026. FCDO is designing a successor programme to the ZDGP. However, this programme will not be mobilised by the Aug 2026 election, which is a critical period for safeguarding democratic space and accountability. Extending the ZDGP ensures there will be no gap in UK support.
Implementation	The Theory of Change will remain unchanged, as will the existing lead partner, Diakonia. Under the extension, Diakonia will continue to manage delivery across all workstreams, ensuring continuity and leveraging established systems and relationships. The wide partner portfolio of the programme will focus will be on consolidating gains and scaling interventions in electoral support, civic space and media freedoms, anti-corruption journalism, decentralisation, and economic governance reforms. The log-frame and other management tools (risk register, etc) will be updated to reflect the extension period. ZDGP will maintain its strong emphasis on gender equality and social inclusion as an integral part of all activities.
Budget	Original Budget- £4,500,000 / 1st Cost Extension-£4,950,000 / 2nd Cost Extension- £7,000,000 / 3rd Cost Extension- £12,000,000 / Total amount already spent- £9,500,000 / Amount of this cost extension- £3,000,000 / Revised total- £15,000,000 / This cost extension will give us an approved envelope of funding to spend on democratic governance in Zambia. Exact budgets will be confirmed with Diakonia depending on BHC Lusaka’s ODA budget for FY26/27.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	Existing risks will continue to be monitored, with updates to the risk register either quarterly or ad hoc as required. Risks we are monitoring that will impact this funding increase include: / Civic Space – As the 2026 elections draw closer, civic space might be reduced, which could impact the ability of this programme to operate. For example, journalists may be targeted or the space for opposition gatherings may be tightened. In this case, we will adapt activities accordingly and use diplomatic channels to raise concerns. / Electoral Environment – Heightened political tension could lead to misinformation campaigns, intimidation of observers, or disruption of election-related activities. We will counter this through media monitoring, rapid-response mechanisms, and support for conflict management committees. / Reform Fatigue & Political Pushback – Risk that government delays or reverses reforms (e.g., ATI, Data Protection, agricultural bills) due to political sensitivities. We will manage this through sustained engagement, technical support, and coalition advocacy.
Results/Monitoring and Evaluation	The Theory of Change will remain the same, although partners’ targets will be amended based on the additional funding provided. / Impact Statement: To support the deepening and consolidation of democracy in Zambia to build resilience and stability, and enable development and reform. / Theory of Change: IF CSOs and media organisations receive targeted support to strengthen their capacity to test and learn, build networks and coalitions, AND if stakeholder engagement is broadened to engage policy and delivery institutions as part of a multi-stakeholder approach, AND if policies and decision-making are increasingly based on evidence (through research, analysis and technical assistance), AND DDF is seen as a trusted partner and critical friend. THEN there is a more constructive engagement between government and civil society. AND CSOs and media organisations have strengthened skills, greater influence and stronger networks. THEN demand and supply side governance stakeholders make significant positive changes on policy and behaviour priorities, WHICH will result in more sustainable pathways to change and a deepening of democracy in Zambia ahead of the 2026 elections.