## Outputs
OUTPUT 1 | Output 1 Indicators | Baseline: |  | Milestone 1 - 2023/2024 | Milestone 2 - 2024/2025 | Milestone 3 - 2025/2026 | Milestone 2 - 2024/2025 | Assumptions
[Design] DDF facilitates dialogues with key actors to produce solutions to governance challenges identified in at least two DDF themes | 1.1- Number of key actors engaged in various dialogues to discuss governance issues |  | Planned | 15 | 20 | 45 key stakeholders | 20 | Key actors have a thorough understanding of the governance issues that affect them.
|  |  | Achieved | 25 | 38 | 40 different key stakeholder engaged especially during the constitution amendment compaign
Source:
Quantitative indicator: Partnership reports and meeting minutes
| 1.2- Number of workstreams that have been developed in at least two DDF themes | 0 | Planned | 3 | 1 new workstreams | 1 new workstream | 1 new workstreams | Key actors have understanding of the PDIA process and apply it to solve governance problems.
|  |  | Achieved | 3 | 1 | 2 new workstream - Constitution amendment compaign & Cyber legislation Compaign
Source:
Quantitative indicator: Quarterly narrative reports
| 1.3- Number of ideas generated through the PDIA process with different key actors in each work stream | 0 | Planned | 5 in each workstream | 9 ideas from the new workstream | 10 ideas | 9 ideas from the new workstream | Key actors have understanding of the PDIA process and apply it to solve governance problems.
|  |  | Achieved | 26 | 8 | 7 ideas (4 constitution amendment ideas, 3 Cyber legislation Campaign, 2 ideas on MLGRD M&E Framework)
Source:
Quantitative indicator: Strategy notes
| 1.4- Number of viable initiatives and funding support that have been prioritized for implementation with DDF funding in each work stream | 0 | Planned | 3 in each workstream (9 total) | 4 | 4 initiatives | 9 | The initiatives prioritized for funding align with DDF focus.
|  |  | Achieved | 18 | 3 | 5 (Activity based initiatives - Constitutional amendment activities, WDC ciirrulum pilot, MLGRD M&E Framework for radio programs with BBC MA, TIZ Studies, Cyber security compaign)
IMPACT WEIGHTING (%) |  | Source:
23% |  | Quantitative indicator: Strategy notes
OUTPUT 2 | Output 2 Indicators | Baseline: |  | Milestone 1 - 2023/2024 | Milestone 2 - 2024/2025 | Milestone 3 - 2025/2026 | Milestone 2 - 2024/2025 | Assumptions
[Implementation] DDF supports the implementation of agreed initiatives to address governance challenges | 2.1- Number of grants provided to implementing partners | 1 | Planned | 10 | 2 grants | 8 new grants | 2 grants | Partner funds are disbursed on time.
|  |  | Achieved | 13 | 3 | 8 (NDI, Bloggers, Mankaday, MISA, Panos, AAAZ, COF, AIPRI)
Source:
Quantitative indicator: Project/Quarterly narrative reports, Meeting minutes
| 2.2- Degree to which the partners are implementing and completed the grant in a satisfactory manner | 0 | Planned | 90% | 90% (Partner scores 9 questions out of 10 questions) | 90% (Partner scores 9 questions out of 10 questions) | 90% (Partner scores 9 questions out of 10 questions) | Partners are accountable to DDF in implementing grant.
IMPACT WEIGHTING (%) |  |  | Achieved |  | 85% | In progress
22% |  | Source:
Qualitative indicator: Partner Project reports/ Monitoring reports (Partners complete the agreed upon deliverables and submit reports)
OUTPUT 3 | Output 3 Indicators | Baseline: |  | Milestone 1 - 2023/2024 | Milestone 2 - 2024/2025 | Milestone 3 - 2025/2026 | Milestone 2 - 2024/2025 | Assumptions
[Learning and Influencing] DDF uses learnings and best practices to influence governance policy and reforms | 3.1- Number of short learning papers/policy notes developed and shared by DDF | 0 | Planned | 1 per quarter per partner | 19 total (1 learning paper per DDF partner per quarter plus learning papers per workstream) | 15 learning products (Learning papers, policy briefs, PEA reports, Reaserch/mini study reports) | 16 total (1 learning paper per DDF partner per quarter plus learning papers per workstream) | There is a culture of continuous learning, prompting the systematic documentation and dissemination of lessons learned and best practices.
|  |  | Achieved | 10 | 15 | 8 learning products (Study on legal reforms, Cash for Work, Elections work, Corruption Study, TIZ study, DDF Evaluation, 2 Constitution position papers, Learning paper on TOT)
Source:
Quantitative indicator: Quarterly narrative reports and Activity Reports
| 3.2- Number of communication products developed (infographics, articles, brochures, interviews, posters, radio shows etc) | 0 | Planned | 50 | 170 communication products | 250 communication products | 170 communication products | Key governance actors are willing to engage in the dissemination events.
|  |  | Achieved | 118 | 183 | 160 communication products (In progress)
Source:
Quantitative indicator: Quarterly narrative reports & Activity Reports
| 3.3- Number of learning events/reflection meetings with partners, CSOs/govervance actors to share lessons and best practices on the DDF | 0 | Planned | 3 | 8 (4 learning events & 4 reflection meetings) | 12 (4 National Level dialogues, 4 Partner reflection meetings, Learning Events) | 8 (4 learning events & 4 reflection meetings) | DDF is capturing and sharing good practices and communication products to generate change.
|  |  | Achieved | 10 | 15 | 7 (2 public forums on constitution amendment, 1 constitutional reflection, 2 partner reflection meetings, 2 study dissemination meetings)
Source:
Quantitative indicator: Quarterly narrative reports & Activity Reports
| 3.4- The level to which inititatives prioritized have been scaled up under any DDF theme (DDF partner scale up) | 0 | Planned | 3 | 4 DDF partner inititiatives scaled up | 8 partner iniatives scaled up | 4 DDF partner inititiatives scaled up | There is a culture of continuous learning, prompting the systematic documentation and dissemination of lessons learned and best practices.
IMPACT WEIGHTING (%) |  |  | Achieved | 0 | 4 | In progress
22% |  | Source:
Quantitative indicator: Quarterly narrative reports
OUTPUT 4 | Output Indicator 4.1 | Baseline: Dec 2022 |  | Milestone 1 - 2023 | Milestone 2 - 2024 | Milestone 3 - 2025 | Assumptions | Assumptions
Output 1: ICAR equips Zambia with appropriate competences and skills to effectively use their legal and enforcement instruments to recover stolen assets | Percentage of ICAR trainees who testify to the effectiveness of ICAR training for their work | 0 | Planned | 65% | 65% | 65% | Output 1 requires that staff of partner agencies will be made available to attend ICAR training activities. To capture participant feedback, we anticipate that participants will be responsive to ICAR survey questions. | Output 1 requires that staff of partner agencies will be made available to attend ICAR training activities. To capture participant feedback, we anticipate that participants will be responsive to ICAR survey questions
|  |  | Achieved | 63% | 65%
Source:
ICAR training team impact study
| Output Indicator 4.2 | Baseline: Dec 2022 |  | Milestone 1 - 2023 | Milestone 2 - 2024 | Milestone 3 - 2025
| Number of trainees successfully completing ICAR training | NA | Planned | 50 | 110 | 150
|  |  | Achieved | 55 | 125
IMPACT WEIGHTING (%) |  | Source:
16.5% |  | ICAR training records based on signed participant lists. Please note that milestones are cumulative.
OUTPUT 5 | Output Indicator 5.1 | Baseline: Dec 2022 |  | Milestone 1 - 2023 | Milestone 2 - 2024 | Milestone 3 - 2025 | Assumptions | Assumptions
Output 2: ICAR supports Zambia to introduce suitable tools, procedures, instruments, policies or institutions to recover and manage stolen assets | Examples of ZACC, DEC and/or NPA employing ICAR informed approaches and tools | 0 | Planned | 2 | 4 | 4 | Output 2 requires that the ICAR advisers will have access to live cases at ZACC, DEC and the NPA Partner agencies have expressed an openness to introducing new approaches as a result of ICAR adviser inputs. Based on access to partner processes, procedures and approaches, through case work and other engagements, ICAR advisers will identify systems and process-change opportunities. Further work to address these opportunities will be subject to partner willingness and interest to address identified issues, and programme period and programme resources. | Output 2 requires that the ICAR advisers will have access to live cases at ZACC, DEC and the NPA Partner agencies have expressed an openness to introducing new approaches as a result of ICAR adviser inputs. Based on access to partner processes, procedures and approaches, through case work and other engagements, ICAR advisers will identify systems and process-change opportunities. Further work to address these opportunities will be subject to partner willingness and interest to address identified issues, and programme period and programme resources.
|  |  | Achieved | 2 | 4
Source:
Source: Quarterly Reports
| Output Indicator 5.2 | Baseline: Dec 2022 |  | Milestone 1 - 2023 | Milestone 2 - 2024 | Milestone 3 - 2025
| Number of multi-jurisdictional operational or case-based meetings conducted as a result of ICAR’s intervention and with ICAR participation/facilitation | 1 | Planned | 4 | 8 | 40
|  |  | Achieved | 11 | 23
Source:
ICAR case tracking tool
| Output Indicator 5.3 | Baseline: Dec 2022 |  | Milestone 1 - 2023 | Milestone 2 - 2024 | Milestone 3 - 2025
| Progress on policy and legal reform, key system or process change influenced as a result of ICAR interventions to strengthen the anti-corruption environment and institutionalise asset recovery. | NA | Planned | ICAR identify systems and process change opportunities which can be supported by the ICAR embedded investigations expert | ICAR introduce at least one system or process change initiatives to strengthen the anti-corruption environment and institutionalise asset recovery. | ICAR to encourage and evidence uptake and utilisation of the provisional asset recovery and management and MLA drafted instruments aimed at addressing institutional gaps/gaps in succesful handling of cases
IMPACT WEIGHTING (%) |  |  | Achieved | 8 opportunities, cutting across policy and legal reforms as well as institutional-level gaps in procedures and business processes identified. | Two reform areas: one policy on asset recovery and management of assets; and one legal reform in Mutual Legal Assistance (MLA)aimed to address institutional gaps.
16.5% |  | Source:
ICAR embedded advisers to identify policy and legal reforms, key system or process change opportunities influenced or which could be influenced as a result of ICAR interventions to strengthen the anti-corruption environment and institutionalise asset recovery.
100%

## Outcomes
FCDO-DIAKONIA - DEEPENING DEMOCRACY FACILITY
IMPACT | Impact Indicators | Baseline: |  | Milestone 1 - 2023/2024 | Milestone 2 - 2024/2025 | Milestone 2 - 2025/2026 | Milestone 2 - 2024/2025 | Assumptions
To support the deepening and consolidation of democracy in Zambia to build resilience and stability, and enable development and reform. | Indicator 1: Zambia’s overall governance ranking guided by Mo Ibrahim Index of African Governance indicators is improved. | 50% | Planned | 52% | 53% | 52% | 53% | 1. The Zambian government is committed to implementing reforms related to security, rule of law, justice, accountability, transparency, and anti-corruption. 2. Key stakeholders, including law enforcement agencies, judiciary, and anti-corruption bodies, actively cooperate to achieve improvements in these areas. 3. There are no major external shocks or political disruptions that could impede progress in security and law-related reforms. 4. There is a conducive environment for meaningful civic participation and respect for human rights and inclusion.
|  |  | Achieved | 53% |  | 0.53
| Indicator 2: Number of impact stories demonstrating the programme's contribution to fighting corruption and establishing an asset recovery regime in Zambia. | 0 | Planned | 0 | 2 | 5
|  |  | Achieved | 1 | 3
Source:
Mo Ibrahim Index of African Governance indicators, quarterly program reports, programme team's reflections, and feedback from Government of Zambia anti-corruption partners.
OUTCOME 1 | Outcome 1 Indicators | Baseline: |  | Milestone 1 - 2023/2024 | Milestone 2 - 2024/2025 | Milestone 2 - 2025/2026 | Milestone 2 - 2024/2025 | Assumptions
1. Key democratic institutions and processes are supported and strengthened in national policy/reform to depeen transparency and accountability | 1.1. The level to which democratic institutions or processes have been supported to work on a reform/policy on two or more DDF themes | No institutions/processes being supported by DDF | Planned | DDF support to SH (via KIVU) on job creation policies, ZNBC/ MoLG Partnership on CDF radio programs (BBC media), ACA, PAAGZ and JCTR's work on social accountability, CTPD's work on CDF dashboard. | Support MoA/MoF to successfully roll out FISP e-voucher in 74 districts. Support SH to make effective policy decisions on job creation. Support MoLGR and PDU to collect and present data (through merged dashboard) on the CDF. Increase accountability of local authorities to citizens on the CDF. | 1. Constitutional amendment advocacy on Bill 7 2. Curriculum for Ward Development Committees (WDCs) 3. The Pilot Integrated CDF Management Information System 4. Operationalization of the Access to Information (ATI) and Data Protection Act 5. IAPRI’s Work on the Agricultural bills - the Food Reserve Act No. 6 of 2020, the Agricultural Credit Act No. 35 of 2010, and the draft Agricultural Marketing Bill of 2012 6. BBC MA support to M&E framework for the CDF Radio Programs | Support MoA/MoF to successfully roll out FISP e-voucher in 74 districts. Support SH to make effective policy decisions on job creation. Support MoLGR and PDU to collect and present data (through merged dashboard) on the CDF. Increase accountability of local authorities to citizens on the CDF. | 1. Government institutions actively demonstrate a commitment to transparency, accountability, and responsiveness to CSOs and citizens' concerns
|  |  | Achieved | 4 | 4 - Kivu e-voucher work, cyber security bill compaign, PAAGZs work with Chongwe Municipal Council, ACA & JCTRs work with LAs | In progress | 4 - Kivu e-voucher work, cyber security bill compaign, PAAGZs work with Chongwe Municipal Council, ACA & JCTRs work with LAs
Source:
Qualitative indicator: KII with representativies of democratic institutions, Partner reports, period reports of supported institutions
OUTCOME 2 | Outcome 2 Indicators | Baseline: |  | Milestone 1 - 2023/2024 | Milestone 2 - 2024/2025 | Milestone 2 - 2025/2026 | Milestone 2 - 2024/2025 | Assumptions
2.Civil Societys' (CSOs, citizens, media, bussiness entities etc) engagement and participation in local and national governance processes is enhanced through establishment/strengthening of civil society platforms/mechanisms | 2.1. Civil society platforms/mechanisms established/strengthened as a result of DDF contribution in any of the DDF four themes | No coordinated platforms/mechanism for civil society | Planned | Establishment/strengthening of 3 platforms/mechanism under any DDF theme | Establishment/strengthening of 5 platforms/mechanism under any DDF theme through partners (BBC MA Radios, ACA, PAAGZ & JCTR community meetings, CTPD dashboard) | Establishment/strengthening of 5 platforms/mechanism under any DDF theme through partners | Establishment/strengthening of 5 platforms/mechanism under any DDF theme through partners (BBC MA Radios, ACA, PAAGZ & JCTR community meetings, CTPD dashboard) | 1. CSOs work together to influence and engage democratic institutions on governance issues
|  |  | Achieved | In progress | DDF established 5 platforms in Nkana, Bwacha, Milanzi, Mkaika, Mazabuka Central, Magoye, and Chongwe constituencies through townhall meetings, interface meetings, public discusssions, community dialogues and CDF radio stations | In progress | DDF established 5 platforms in Nkana, Bwacha, Milanzi, Mkaika, Mazabuka Central, Magoye, and Chongwe constituencies through townhall meetings, interface meetings, public discusssions, community dialogues and CDF radio stations
Source:
Qualititative indicator: Project reports, meeting minutes/reports
| 2.2. Civil society perception/opinion of willingness of democratic institutions to engage in dialogue to address governance issues on any DDF theme | Perception of civil society to engage low (Source: Baseline study) | Planned | Development and admistration of data collection tools to capture perceptions of civil society on willing of democratic institutions to engage. | Civil society perception positive compared to baseline | Civil society perception positive compared to baseline | Civil society perception positive compared to baseline
|  |  | achieved | In progress | In progress | In progress | In progress
Source:
Qualitative indicator: Sample opinions/perceptions of civil society through surveys, key informant interviews & focus groups.
| 2.3. The level to which civil society are engaged through DDF to address governance issues in identified DDF themes | Engagement meetings with civil society are non-existent | Planned | Conduct 50 radio programs & a listenership survey, 50 members of civil society attend debates and 80 members of community take part in community meetings | Conduct 126 CDF radio programs & a listenership survey and 300 members of community take part in community meetings through partners. | Conduct radio programs, citizens participate in govervance. | Conduct 126 CDF radio programs & a listenership survey and 300 members of community take part in community meetings through partners.
|  |  | Achieved | 110 radio programmes, 528 people attended 10 public discussions | 167 radio programmes, 38 key actors attend DDF governance discussions, 3,401 people attended 10 DDF trainings | In progress | 167 radio programmes, 38 key actors attend DDF governance discussions, 3,401 people attended 10 DDF trainings
Source:
Qualitative indicator: Project reports, meeting minutes/reports
OUTCOME 3 | Outcome 3 Indicator | Baseline: |  | Milestone 1 - 2023/24 | Milestone 2 - 2024/25 | Milestone 3 - 2025/26 | Assumptions | Assumptions
Anti-corruption chain is better equipped to deliver sanctions and recover assets | Percentage of ICAR supported cases making making 4 steps or more towards conviction or asset confiscation | 0 | Planned | 40% | 40% | 40% | This assumes that the Government of Zambia and partner agencies are committed to increasing Zambia's effectiveness in successfully investigating and prosecution cases of corruption, and wish to recover stolen assets within Zambia, and from other jurisdcictions. Outcome Indicator requires that the ICAR advisers will have access to live cases at ZACC, DEC and the NPA. | This assumes that the Government of Zambia and partner agencies are committed to increasing Zambia's effectiveness in successfully investigating and prosecution cases of corruption, and wish to recover stolen assets within Zambia, and from other jurisdcictions. Outcome Indicator requires that the ICAR advisers will have access to live cases at ZACC, DEC and the NPA.
|  |  | Achieved | 54% | 76%
Source:
ICAR case tracking tool. Case progress is measured using ICAR's Case Progress Tool, which is used by ICAR across its portfolio for this purpose. ICAR's experts log the support provided as well as important achievements that occur. A ‘step’ is a completed task in the Case Progress Tool. A completed task is one that is marked as done, and indicates that a specific action or process has been completed or that a specific milestone has been reached. The tasks in the Case Progress Tool represent what ICAR considers to be substantive and important actions that must be undertaken at the investigation, prosecution and/or other court-related stages to successfully recover (and realise) assets whether through conviction or non-conviction based confiscation mechanisms. The tool's data analysis function counts the steps completed in a given period (usually a 12 month period) by country. The denominator for the calculation is the number of active cases (whether by country programme, or for ICAR's global portfolio) in the same period. This indicator is not cumulative.

## Specifications & Definitions In
| Programme |  | DDF
| Author of last update: |  | 22.07.27
| Result |  | Indicator | Definition and Specification | Data Source | Disaggregation | Assumptions
Impact
| Zambia’s overall governance ranking guided by Mo Ibrahim Index of African Governance indicators is improved |  | Rule of Law
Accountability and Transparency
Anti-Corruption
Participation
Rights
Outcome
1 | Key democratic institutions and processes are supported and strengthened in national policy/reform to depeen transparency and accountability | 1.1 | The level to which democratic institutions or processes have been supported to work on a reform/policy on two or more DDF themes | This indicator will measure the level to which democratic institutions (e.g SH, PPDF, PDU, Cabinet Office, Ministry of Finance, ZDA, local government, ZNBC etc) or processes (Public Order Act, access to information bill etc) have been supported by DDF through analysis, advocacyand provision of data and evidence.
2 | Civil Societys' (CSOs, citizens, media, bussiness entities etc) engagement and participation in local and national governance processes is enhanced through establishment/strengthening of civil society platforms/mechanisms. | 2.1 | Civil society platforms/mechanisms established/strengthened as a result of DDF contribution in any of the DDF four themes | This indicator will measure;1) The number of new platforms/mechanisms that have been created for engagement on democratic and governance issues by DDF supported initiatives. 2) The number strengthed platforms/mechanisms that have been created for engagement on democratic and governance issues by DDF supported initiatives. 3) The number of platforms/mechanisms facilited by other actors that DDF has contirbuted to. Strengthened refers to the platforms/mechanisms that were previously not utilized and have been revamped due to DDF contribution. Type of mechanisms created/strengthened/supported by DDF responding to specific issues of interest related to DDF priority themes and governance at local and level national level.
|  | 2.2 | Civil society perception/opinion of willingness of democratic institutions to engage in dialogue to address governance issues on any DDF theme | This indicator will measure the perceptions of civil society on any DDF theme who indicate that democratic institutions (local authority, regulatory agencies & legislature etc) are: a) always; b) usually; c) sometimes; d) rarely or never open to dialogue. This will be captured through sample opinions/perceptions through surveys, key informant interviews & focus groups discussions of the DDF targeted groups.
|  | 2.3 | The level to which civil society are engaged through DDF to address governance issues in identified DDF themes | This indicator measures the level of engagements of civil society by in the identified DDF themes. The civil society refers to The engagements can be categorised (i) consultation, (ii) collaboration (iii) information generation and sharing, and (iv) partnership with the the various governance actors/institutions. It encompasses the work that DDF is doing with different partners such as BBC Media Action radio programming and debates, ACA and JCTR under the social accountability projects, CTPD establishing the CDF dashboard and various other works aimed at enabling civil society to participate in goverance activities at local and national level.
Output
1 | [Design] DDF facilitates dialogues with key actors to produce solutions to governance challenges identified in at least two DDF themes | 1.1 | Number of key actors engaged in various dialogues to discuss governance issues | This indicator measures the number of key actors engaged in various dialogues to discuss governance issues. Dialogues bring together various actors to discuss issues under each DDF theme.There are four themes which guide the work of the DDF:1) Reforms and strengthening of key democratic institutions and processes. 2) Expansion and protection of civic space.3) Deepening democracy through active citizen participation. 4) Enhancing and deepening accountability, transparency, and anti-corruption measures. Key actors are reffered to as citizens or non-state actors such as civil society organizations, academia, private sector and business groups who are brought together to engage in dialogue over governance issues. The indicator will capture how many key actors DDF/DDF partners will bring together, whether in terms of core groups, comparison groups or individuals from different walks of life to engage in dialogue in addressing governance issues. | Primary source | Partner | Key actors have a thorough understanding of the governance issues that affect them.
|  | 1.2 | Number of workstreams that have developed in at least two DDF themes | This indicator measures the number of workstreams that have developed in at least two DDF themes. Through the dialogues, DDF assesses and agrees the most promising areas for intervention. These are workstreams. The workstreams are highly focused - with their own goals and objectives - and making it easier to plan, monitor and execute activities/initiatives under each DDF theme. Some of the workstreams developed under the DDF so far includes CDF and Civic space. | Primary source | Partner | Key actors have understanding of the PDIA process and apply it to solve governance problems
|  | 1.3 | Number of ideas generated through the PDIA process with different key actors in each work stream | This indicator measures the number of ideas generated through the PDIA process with different key actors in each work stream. Idea generation under the DDF is described as the process of creating, developing and communicating ideas that will solve goverance issues through the PDIA process/engagements.For each workstream, DDF then holds PDIA discussions to identify the problem and generate ideas for how to promote change. | Primary Source | Partner | Key actors have understanding of the PDIA process and apply it to solve governance problems
|  | 1.4 | Number of viable initiatives and funding support that have been prioritized for implementation with DDF funding in each work stream | This indicator measures the number of viable initiatives that have been prioritized for implementation with DDF funding in each work stream. If viable, the ideas generated from the PDIA process then become initiatives which are allocated funding.Prioritizing an initiative comes as a result of understanding the impact of its efforts to provide clarity to key actors/partners about how the initiative is going to contribute to overall DDF objective of deepening democracy. | Primary source | Partner | The initiatives prioritized for funding align with DDF focus.
2 | [Implementation] DDF supports the implementation of agreed initiatives to address governance challenges | 2.1 | Number of grants provided to implementing partners | This indicator measures the number of grants/funding support provided to implementing partners. Funding is money which DDF provides for a particular initiative to a downstream partner through a cooperative agreement/MOU. This ensures that all activities that the downstream partner implements are focused on specific objectives to maximize impact of the DDF. Funding support on the other hand refers to funds which DDF provides to individuals or institutions to support a specific activity that aligns with DDF (Activity Based grant). | Primary source | Partner | Partner funds are disbursed on time
|  | 2.2 | Degree to which the partners are implementing and completed the grant in a satisfactory manner | This indicator measures the degree to which the partners are implementing and completed the grant in a satisfactory manner. This indicator will be assessed using the following score; 1. Project team composition possessing requisite skills in project management, M&E, finance, and activity facilitation including effective communication with the DDF, timeliness of project planning and the quality of reports. 2. Application of PDIA implementation approach including the utilization of feedback loops and flexibility in activity implementation. 3. Grant compliance - adherence to grant conditions, including meeting deadlines, risk awareness, and SEAH protocols. 4. Stakeholder engagement - assess the partner's engagement with targeted stakeholders and project participants on both demand side (RHs) and supply side (Bereaucrats) in implementation sites. 5. Activity implementation - partner's ability to timely implement planned activities with high quality and monitoring 6. Capacity building and RH engagement - assess the frequency and effectiveness of capacity-building efforts and engagement with RHs in project sites. 7. Assess the potential for scaling up project activities or extending geographical coverage based on the effectiveness of current activities in influencing change, lessons learned, capacity for expansion, and the appetite of project participants for further engagement. 8. Stakeholder perception - gauge the perception of RHs and duty bearers regarding the type, quality, and frequency of project activities. 9. Observable changes – assess changes among RHs and duty bearers resulting from implemented activities. 10. Sustainability - determine the extent to which targeted groups can sustain project activities without the implementing partner's support. The score to each partner will be given according to how much each of them score out of 10. | Primary source | Partner | Partners are accountable to DDF in implementing grant
3 | [Learning and Influencing] DDF uses learnings and best practices to influence governance policy and reforms | 3.1 | Number of short learning papers/policy notes developed and shared by DDF | This indicator measures the number of short learning papers/policy notes produced under DDF and shared through influencing and dissemination meetings. Learning papers are articles/documents produced under DDF to learn from the experience of partners in developing and implementing of various governance initiatives for the use of approaches in the different contexts in which DDF works.The dissemination events refer to meetings targeting at a wide audience ranging from policy makers, industry workers, bussiness owners, media private sectors and are aimed at sharing the findings of the DDF and how they influence policy/reforms in the governance space. | Primary source | Partner | There is a culture of continuous learning, prompting the systematic documentation and dissemination of lessons learned and best practices.
|  | 3.2 | Number of communication products developed (infographics, articles, brochures, interviews, posters, radio shows etc) | This indicator measures the number of communication products developed (infographics, articles, brochures, interviews, posters, radio shows etc). These communication products can be written, audio, visual, or web-based depending on the audience that is intended to be reached.Their aim is to capture and share DDF good practices to generate change in the governance space. | Primary source | Partner | Key governance actors are willing to engage in the dissemination events
|  | 3.3 | Number of learning events/reflection meetings with partners, CSOs/govervance actors to share lessons and best practices on the DDF | This indicator measures the number of learning events/reflection meetings with CSOs/govervance actors to share lessons and best practices on the DDF. This will include corporating partners, downstream partners, government institutions etc. These reflection meetings are held every quarter. | Primary source | Partner | DDF is capturing and sharing good practices and communication products to generate change
|  | 3.4 | The level to which inititatives prioritized have been scaled up under any DDF theme | This indicator will measure the number of inititiatives that will be scaled up by the DDF as a result of testing and learning of various initiatives prioritized, to different geographical areas for example. | Primary source | Partner | There is a culture of continuous learning, prompting the systematic documentation and dissemination of lessons learned and best practices.