## Annual Review

Title: Zambia Democratic Governance Programme
Programme Value £ (full life): £15,000,000		Review date: 22/03/2026
Programme Code: 301270	AMP start date: 22/03/2021	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2021/22	2022/23	2023/24	2024/25	2025/26
Overall Output Score	A	A	A	A	A
Overall programme risk rating	Major	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000596.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S30127026.xlsx

## A. SUMMARY AND OVERVIEW

Programme Description
The Zambia Democratic Governance Programme (ZDGP) aims to strengthen democratic governance in Zambia by supporting the state to be more effective, transparent, and accountable so it can respond to the needs of its population, and by providing a platform for bottom-up social accountability and participation by civil society, the media and citizens.
The UK views democratic governance as a critical enabler of Zambia’s development agenda. By supporting Zambia to strengthen democratic institutions, enhance oversight, and improve government responsiveness, the UK is helping to create the stable, predictable environment needed for inclusive economic growth and poverty reduction. It also helps position Zambia as a steadfast geopolitical ally to the UK in a contested region. Global evidence consistently shows that on average, democracies achieve higher productivity, improved human capital outcomes in health and education, greater gender equality, and reduced risks of conflict.
The ZDGP achieves this by working across four themes:
- Reforms: Helping Zambia put in place better economic policies and stronger institutions to boost growth.
- Civic Space: Expanding and protecting the space people have to speak up, organise, and participate in shaping their communities and government.
- Citizen Participation: Making Zambia’s democracy stronger by supporting active involvement from citizens.
- Transparency and Anti-Corruption: Strengthening Zambia’s ability to fight financial crime by being more transparent and recovering stolen assets.
Programme Structure
The structure of ZDGP remains broadly unchanged from the 2025 Annual Review, with implementation centred on two main components: the Deepening Democracy Facility, delivered through an Accountable Grant to Diakonia in a consortium partnership with BBC Media Action (£3,648,151 in 2025/26), and an Accountable Grant to the Basel Institute on Governance’s International Centre for Asset Recovery (ICAR) (£400,000 in 2025/26) to embed anti‑corruption expertise within Zambia’s law‑enforcement agencies.
The programme was originally approved with a value of £4.5 million. Following three approved cost extensions, the budget increased to £12 million, with completion scheduled for 31 May 2026. Towards the end of the review year, FCDO extended the programme to 31 March 2027, and the total programme value was increased to £15 million. This extension will build on progress achieved this year, continuing existing work on economic reforms, civic space, media freedoms, and transparency up to (and slightly beyond) Zambia’s elections in August 2026. Continued implementation will allow FCDO to transition smoothly from ZDGP to its successor, the Effective State and Democracy Programme.
Overall Score and Summary of Programme Achievements
This year, the programme has scored an A (met expectation), which is a testament to partners’ achievements this year. With consecutive ‘A’ scores in the five previous annual reviews, we recommend that the programme continues until its planned closure in March 2027. During 2025/26, key achievements include:
- Mobilising civil society to press for a transparent and meaningful consultation process in response to the Government announcement of major changes to Zambia’s Constitution. The Bill was ultimately passed, but civil society concerns were heard and acted upon. By documenting citizen submissions, tracking the process, and building provincial reach, the DDF contributed to strengthening democracy in Zambia both in relation to the constitutional issue and for the future
- Major reforms in Zambia’s agriculture sector, which contributes only 3% to GDP, yet employs nearly 60% of the total labour force and is the main source of income and employment for rural people. Reforms included:
  - Supporting the Government to roll-out the Farmer Input Support Programme (FISP) using the e-voucher model nationwide, reaching 1 million Zambian households (one quarter of the population) with more flexible, transparent agriculture subsidies. The e-voucher model saves the government money on procurement and delivery, reduces opportunities for corruption, incentivises private sector growth, creates jobs and gives farmers more agency.
  - Developed a model to demonstrate Zambia’s agricultural export potential, demonstrating the potential for ZMW 31 billion (USD 420 million) in fiscal savings and ZMW 185 billion (USD 2 Billion) in economic benefits over 10 years, informing Cabinet‑level reform discussions.
  - Worked with the Ministry of Agriculture to draft three pieces of legislation that will collectively transform the way the agriculture sector operates by reducing government intervention, creating the conditions for private sector growth and ensuring national food security.
- Supporting the Ministry of Small and Medium Enterprise Development (MSMED) to reduce the tax burden on MSMEs and expand the tax base. These tax measures were adopted in the 2026 national budget.
By providing case investigation support to law enforcement agencies working on corruption and financial crime cases, Zambia recovered £4.3 million in forfeited assets (with a further £316 million in potential recoveries), including two helicopters, high‑value real estate and cash, and a landmark environmental forfeiture involving a full factory, machinery and hardwood logs. In one case, assets were repurposed as safehouses for women and girls affected by GBV, demonstrating the social value of returning the proceeds of crime.
Supporting election‑related preparedness and protection of civic and media space through police–media dialogues to strengthen protection of journalists, public debates on Zambia’s national TV broadcaster and local radio stations of key public policies, operationalising Statutory Instruments on Access to Information and providing cybersecurity and digital rights awareness for youth, CSOs and media to mitigate surveillance, online harassment and dis/misinformation risks associated with election cycles.

Output Scoring Summary
Output		Impact weighting	Output Score
1	DDF facilitates dialogues with key actors to produce solutions to governance challenges identified in at least two DDF themes.	23%	A
2	DDF supports the implementation of agreed initiatives to address governance challenges.	22%	A
3	DDF uses learnings and best practices to influence governance policy and reforms.	22%	A
4	ICAR equips Zambia with appropriate competences and skills to effectively use their legal and enforcement instruments to recover stolen assets.	16.5%	A
5	ICAR supports Zambia to introduce suitable tools, procedures, instruments, policies or institutions to recover and manage stolen assets.	16.5%	A
Total		100%	A

Summary of recommendations for the year ahead
#	Recommendations	Target Completion Date	Owner
1	In the final phase of the programme, the DDF should focus on securing the sustainability of its initiatives beyond the life of the project. In practice, this will mean consolidating its workstreams into packaged proposals which can be taken on by others (particularly the Government), including the evidence based and lessons learned, realistic recommendations for institutional actors responsible for implementation and explicit policy‑influence routes.	March 2027	DDF partners
2	To strengthen accountability outcomes, the DDF should more systematically connect community‑level actors and investigative media to formal oversight and enforcement institutions (including ACC, NPA, DEC, and relevant parliamentary committees), through agreed referral pathways, coordination protocols, and risk‑mitigation measures, ensuring citizen‑generated evidence can trigger institutional response.	March 2027	DDF partners
3	ICAR should use 2026/27 as a transition year to embed the non‑conviction‑based forfeiture (NCBF) model within partner institutions, finalise and operationalise the Asset Management Bill and standards, and maintain steady case progression through the electoral cycle, to secure durable asset‑recovery capability beyond UK support.	March 2027	ICAR
4	Given the innovative approach being tested through the Provincial Hubs model, design Value for Money indicators (across the four Es) to assess whether this model is a cost-effective way of improving democratic governance.	December 2026	DDF Partners

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Theory of Change
The Theory of Change for this programme is: IF CSOs and media organisations receive targeted support to strengthen their capacity to test and learn, build networks and coalitions, AND if stakeholder engagement is broadened to engage policy and delivery institutions as part of a multi-stakeholder approach, AND if policies and decision-making are increasingly based on evidence (through research, analysis and technical assistance), THEN CSOs and media organisations have strengthened skills, greater influence and stronger networks, AND DDF is seen as a trusted partner and critical friend AND there is a more constructive engagement between government and civil society. Taken together, THEN demand and supply side governance stakeholders make significant positive changes on policy and behaviour priorities, WHICH will result in more sustainable pathways to change and a deepening of democracy in Zambia ahead of the 2026 elections.
Our assessment is that the Theory of Change remained valid in 2025/26. The evidence underpinning it remained relevant and lessons learned this year demonstrate that the inputs, outputs and assumptions are leading to the intended outcomes and impact:
1. Timing matters for influencing change, and programmatic flexibility is therefore critical to delivery. During this year, several reform windows arose that were not predictable (the reopening of the constitutional reform process, the issuance of Access to Information Statutory Instruments, and providing advice to the Government on managing the fiscal burden of government maize purchases. The DDFs ability to adapt and to engage at the precise political moments when they could shift incentives underpins the Theory of Change.
2. Decentralised Coalitions Increase Legitimacy and Reach of Governance Reforms: The Theory of Change relies on broad networks of diverse actors to shift progress. The Constitutional reform process brought to bear that civil society in Zambia is Lusaka-centric. Most CSOs don’t have a presence outside the capital, nor do they represent constituencies across the country. This weakens their advocacy and legitimacy. The DDF responded by designing Provincial Hubs. The DDF now supports Hubs in all 10 provinces which reach governance actors in every district across the country. Building this network of actors is resource-intensive; achieving value for money will depend on the impact the network can have on strengthening democracy.
3. Government Co-Ownership Drives Reform Uptake and Sustainability: This year showed that reforms are most likely to endure when DDF and partners co‑create solutions with ministries rather than presenting finished products. A national Ward Development Committee (WDC) orientation manual was co‑created with the Ministry of Local Government and Rural Development (MLGRD) and prepared for validation and nationwide rollout after the August 2026 elections. MLGRD’s active role in shaping the WDC orientation manual, and its request to adapt and adopt BBC Media Action’s citizen‑feedback radio M&E model, show that co‑production creates ownership and accelerates national rollout. Similarly, the Access to Information and Data Protection operationalisation processes, both of which moved forward only after sustained CSO-government engagements, illustrate that reform durability rests on deliberate, ongoing government buy‑in, not one‑off advocacy.
4. When multiple actors reinforce each other’s authority, rather than working in silos, behavioural change becomes faster, more visible, and more institutionally anchored. Across multiple locations and sectors, accountability increased most rapidly when citizen monitors, investigative media, local authorities, and oversight agencies interacted within a shared feedback loop. DDF quarterly results show that media investigations triggered service‑delivery corrections (e.g., Solwezi hospital renovations), CDF committees responded to citizen‑initiated audits in Katete and Mazabuka, and police-media forums improved journalist protections that subsequently shaped community engagement.
While the Theory of Change still holds, the monitoring of progress (through the log-frame) continued to prove challenging in an adaptive programme like ZGDP. The ZGDP log-frame tracks quantitative progress against predefined indicators at the outcome and output levels. This is helpful for guiding partners towards the expected scale of delivery (e.g. number of workstreams developed, number of grants provided), but its rigidity is less useful in fluid political contexts where informal behaviours, incentives and power dynamics drive change, and where rapid policy or leadership shifts outpace fixed targets. As a result, this review (and previous reviews) relied on complementary qualitative and politically informed MEL tools (such as outcome harvesting, reflective learning, and documentation of adaptive decisions) to understand why change occurred and to support real‑time learning in sensitive reform environments. Future programmes would benefit from more flexible results frameworks that maintain accountability while enabling adaptation, richer interpretation of change and stronger strategic learning in complex governance settings. At the outcome level, defining the real-world change that partners are working towards at the outset would enable a clearer reflection on whether partners achieved their objectives. Flexibility can then be provided at the output level to allow partners to pivot their delivery plans in line with the changing context.
Progress Towards Impact and Outcomes
	Baseline	2025/26 Progress
Impact: To support the deepening and consolidation of democracy in Zambia to build resilience and stability, and enable development and reform.
Indicator 1: Zambia’s overall governance ranking guided by Mo Ibrahim Index of African Governance (IIAG) indicators is improved.[1]	50%	Planned: 53% / Achieved: 56.6% / Zambia’s governance performance in 2024 is recorded at 56.6/100 on the IIAG- ranking 17/54 among African countries.
Indicator 2: Number of impact stories demonstrating the programme's contribution to fighting corruption and establishing an asset recovery regime in Zambia.	0	Planned: 5 / Achieved: 5 / International cooperation of a high-profile political corruption case / International cooperation in asset recovery / Investigations of money laundering syndicate in Zambia / Overseas asset freeze through international cooperation with the economic and Confiscation Unit (ECCU) and Swiss Federal office of Justice (FOJ) / Asset forfeiture following investigations of illegal trade in forest produce.
Outcome 1: Key democratic institutions and processes are supported and strengthened in national policy/reform to deepen transparency and accountability.
Indicator 1.1: The level to which democratic institutions or processes have been supported to work on a reform/policy on two or more DDF themes.	No institutions/processes being supported by DDF	Planned: Provide support to 4 institutions/ reforms / Achieved: 8 / Constitutional amendment advocacy on Bill 7 / Curriculum for Ward Development Committees (WDCs) / The Pilot Integrated CDF Management Information System / Operationalization of the Access to Information (ATI) and Data Protection Act / IAPRI’s Work on the Agricultural bills - the Food Reserve Act No. 6 of 2020, the Agricultural Credit Act No. 35 of 2010, and the draft Agricultural Marketing Bill of 2012 / BBC MA support to M&E framework for the CDF Radio Programs / SME tax reforms / FISP e-Voucher Reform scale-up
Outcome 2: Civil Society (CSOs, citizens, media, business entities etc) engagement and participation in local and national governance processes is enhanced through establishment/strengthening of civil society platforms/mechanisms.
Indicator 2.1: Civil society platforms/mechanisms that have been established/strengthened because of DDF contribution foster accountability and transparency in any of the DDF four themes.	No coordinated platforms/mechanism for civil society	Planned: Establishment/strengthening of 5 platforms/mechanisms under any DDF theme through partners / Achieved: 10 platforms / 10 engagement mechanisms for CSOs and citizens created through provincial hubs and partner initiatives (including MISA, MakanDay, Bloggers, JCTR) providing regularised platforms for CSOs and citizens to participate in governance processes, hold duty bearers to account, and engage on reforms at both local and national levels. / These mechanisms include provincial CSO coordination hubs, police-media dialogue forums, governance radio call‑in programmes and debates, CDF radio feedback platforms, freedom of expression monitoring systems, community social‑audit forums, citizen–duty bearer interface meetings, and investigative journalism networks.
Indicator 2.2: Civil society perception/opinion of willingness of democratic institutions to engage in dialogue to address governance issues on any DDF theme.	Perceptions of civil society willingness to engage with government were low, characterised by poor communication and limited feedback on decisions (as evidenced in the baseline study).	Planned: Civil society perception has improved since baseline. / Achieved: The DDF Evaluation 2025 Topline Survey (Aug 2025; n=1,507) provides evidence of improved engagement readiness among respondents exposed to DDF-supported programming, / 68% reported increased confidence to engage, with confidence levels varying by district (52–87%). The survey also highlights remaining constraints on perceived openness (e.g., favouritism in decisions 22% and perceptions that officials only listen to people they know 9%), indicating that perceptions are improving but not yet consistent across settings.
Indicator 2.3: The level to which civil society are engaged through DDF to address governance issues in identified DDF themes.	Engagement meetings with civil society are non-existent	Planned: Conduct radio programs, citizens participate in governance. / Achieved: 171 radio programs conducted, 12,200 citizens participated in civic awareness on Bill 7 civic awareness.
Outcome 3: Anti-corruption chain is better equipped to deliver sanctions and recover assets.
Indicator 3.1: Percentage of ICAR supported cases making four steps or more towards conviction or asset confiscation.	0	Planned: 40% / Achieved: 53%
[1] Zambia’s governance ranking for 2024 cannot yet be updated using the Mo Ibrahim IIAG because the latest IIAG release remains 2023; however, other 2024‑cycle indices allow a similar assessment.

The intended impact of ZDGP (as outlined in the Theory of Change) is to support more sustainable pathways to change and a deepening of democracy in Zambia ahead of the 2026 elections. In 2023 (the most recent year for which there is IIAG data), Zambia scored 56.6 out of 100, ranking 17th out of 54 African countries on the Mo Ibrahim Index of African Governance. Although updated IIAG data are not yet available for 2024, other governance indices reviewed indicate that Zambia’s governance trajectory is not improving year‑on‑year. Freedom in the World 2025 records no change in Zambia’s overall democratic score, which remains at 53/100 (Partly Free), showing neither an improvement nor deterioration in political rights or civil liberties in 2024. The Global State of Democracy 2025 report presents a more mixed but generally negative picture: Zambia recorded a sharp decline in Rule of Law (falling 23 places year‑on‑year) and a decline in Representation (down nine places), offset only by a modest improvement in Participation and no movement in Rights. Taken together, these datasets suggest that relative to the 2023 IIAG baseline, Zambia’s overall governance environment in 2024 shows marginally more signs of strain than progress, with weakening institutional checks and constraints outweighing limited improvements in civic participation.
Outcomes 1 and 2 measure support to ‘supply and demand side’ governance stakeholders through the DDF. This means supporting the state to be more effective, transparent, and accountable so it can respond to the needs of its population (the ‘supply’) and providing a platform for bottom-up social accountability and participation by civil society (the ‘demand’). In general, this means that where we invest in direct engagement with the state on reform, we will also facilitate reform coalitions to sustain the political pressure necessary to embed change. Outcome 3 measures whether cases investigated with ICARs support progress through to conviction or asset confiscation.
Under Outcome 1, ZDGP provided sustained support to eight democratic institutions or reforms, exceeding the target. The programme contributed to the Bill 7 constitutional amendment advocacy, the co‑creation of the WDC curriculum, technical support to the pilot Integrated CDF MIS, policy and legislative engagement on ATI and Data Protection operationalisation, SME tax reform and the FISP e-Voucher Reform scale-up. Evidence from Diakonia and BBC Media Action shows that these engagements were strengthened by inputs from the provincial hubs, which enabled more diverse voices, including communities outside Lusaka, to influence institutional processes. This is consistent with the Theory of Change’s assumption that structured multi‑level engagement fosters more responsive and transparent policy outcomes.
Evidence generated this year demonstrates significant progress toward Outcome 2. Across five BBC Media Action focus districts, 38% of adults were reached by governance programming (approximately 300,000 of 850,383 adults), with 15% reached regularly. Citizens exposed to DDF‑supported media content were consistently more active in local governance: 62% engaged in at least one CDF‑related action (compared to 43% non‑exposed), 78% felt confident applying for grants/bursaries (vs 70%), and 73% were more willing to question authorities (vs 67%). These behavioural shifts, combined with 212 weekly governance radio programmes, 161 social‑media explainers and animations, and national/public debates on sensitive governance issues, indicate that the programme is not only expanding civic space but also strengthening citizens’ willingness and ability to participate in governance processes.
Progress towards Outcome 3 continued strongly over the year. The percentage of ICAR‑supported cases making four steps or more towards conviction or asset confiscation stands at 53% against a 40% milestone. This improved trajectory is reflected in substantive case outcomes and recoveries, including approximately £4.3 million recovered/forfeited in Q3 alone and high‑profile results such as the conviction‑based forfeiture of two helicopters, high‑value real estate and cash, an unexplained‑wealth settlement repurposed for GBV safehouses, and a landmark environmental forfeiture involving a factory, machinery and hardwood. Final verification will be completed in April as part of routine results assurance, but the current end‑year position confirms that the programme has exceeded the milestone.
International cooperation also expanded significantly, improving the pace and quality of evidence gathering. ICAR-supported more than 20 case‑based bilateral meetings under the Global Forum for Asset Recovery (GFAR) Action Series, including with the Isle of Man, Jersey, Austria, the United States, Nigeria, and Hong Kong, accelerated mutual legal assistance, improved access to financial intelligence, and strengthened parallel investigation capability across borders. The signing of three major cooperation treaties with Hong Kong (Mutual Legal Assistance, Surrender of Fugitive Offenders, Transfer of Sentenced Persons) formalised long‑term avenues for cross‑border cooperation. This architecture now operates as a system‑level asset for Zambia’s justice institutions, reducing vulnerability to politicisation and enabling sustained pursuit of high‑value, transnational corruption cases. Collectively, these developments indicate strengthened institutional capacity within the anti‑corruption chain and a maturing enabling environment for asset recovery.

## C. DETAILED OUTPUT SCORING[2]
[2] For this review, progress that is within a 10% variance of the target is considered met. Progress above 10% is considered exceeding and below 10% is either partially met or not met.

Output Title	DDF facilitates dialogues with key actors to produce solutions to governance challenges identified in at least two DDF themes.
Output number:		1	Output Score:	A
Impact weighting (%):		23%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of key actors engaged in various dialogues to discuss governance issues (iterative)	45 key stakeholders	Met. 47 different stakeholders engaged (mostly under the constitution amendment campaign)
1.2 Number of workstreams that have developed in at least two DDF themes (cumulative)	1 new workstream	Exceeded. 2 new workstreams - Constitution amendment campaign & Cyber legislation campaign
1.3 Number of ideas generated through the Problem-Driven Iterative Adaptation (PDIA) methodology with different key actors in each work stream (iterative)	10 ideas	Partially met. 7 ideas (4 constitution amendment ideas, 3 Cyber legislation Campaign, 2 ideas on MLGRD M&E Framework)
1.4 Number of viable initiatives that have been prioritized for implementation with DDF funding in each work stream (iterative).	4 initiatives	Met. 6 (Activity based initiatives - Constitutional amendment activities, WDC curriculum pilot, MLGRD M&E Framework for radio programs with BBC MA, TIZ Studies, Cyber security campaign, Provincial hubs initiatives)

Output 1 assesses Diakonia’s ability to identify emerging governance and democracy challenges and to facilitate politically informed solutions through an adaptive, iterative approach. As with previous years, the Deepening Democracy Facility (DDF) does not define rigid outputs at inception. Instead, Output 1 focuses on how governance problems are identified, broken down, tested, and addressed across its four inter‑related themes:
- Reforms and strengthening of key democratic institutions and processes.
- Expansion and protection of civic space.
- Deepening democracy through active citizen participation.
- Enhancing accountability, transparency, and anti‑corruption.
During the review period, the DDF strengthened how it uses adaptive programming. It moved away from launching many separate activities and instead concentrated on key governance issues, such as constitutional reform, civic space, and accountability. By linking citizen action, media coverage, evidence, and engagement with institutions around these issues, DDF began to see more consistent and system‑wide responses rather than one‑off results.
Engagement during the review period expanded in scale, diversity, and geographic footprint. DDF engaged 47 different stakeholders across civil society, traditional authorities, media representatives, government officials, oversight institutions, and community‑level actors (Indicator 1.1). These engagements centred on constitutional reforms, decentralisation and CDF accountability, cyber legislation, information integrity, and civic‑media protection in pre‑election contexts. This broadened engagement from nationally led dialogues to locally grounded, issue‑based platforms that linked provincial realities to national reform processes.
Two new workstreams emerged around constitutional reform and cyber legislation, each bringing together recurring actors, iterative analysis, and coordinated engagement at national and provincial levels (Indicator 1.2). The constitutional reform workstream focused on supporting coordinated civil‑society engagement in the Bill 7 process and Technical Committee consultations, including expert‑led dialogues, provincial mobilisation and evidence‑based submissions. The cyber legislation workstream addressed the implications of the new cyber laws for civic space and media freedom, through awareness‑raising, police–media dialogue, regulatory engagement and support to CSOs and journalists. Both workstreams operated at national and provincial levels and were implemented adaptively as political conditions evolved. These were formalised as PDIA workstreams with clear problem framing, adaptive testing, and pathways toward influence.
DDF applied PDIA to refine problem definitions, test approaches, and adapt strategies across the constitutional reform and cyber legislation workstreams (Indicator 1.3). Through iterative reflection, political‑economy analysis, and stakeholder feedback, partners generated 7 new ideas focused on constitutional process integrity, cyber law safeguards, and improved decentralisation monitoring.
1. Provincial Constitutional & Civic Hubs as Adaptive Governance Infrastructure
2. The “Twangale‑type” Model of Issue‑Based Coordination (Not Broad Coalitions)
3. Co‑Creation of the Integrated CDF Information System Dashboard With MLGRD
4. Community‑Led Social Accountability Through the TOT (Training of Trainers) Model
5. Constitution Watch & Evidence‑Driven Public Oversight Journalism
6. Hybrid Accountability Media Model (Radio + Social Media Feedback Loops)
7. Multi‑Stakeholder Anti‑Corruption “Accountability Pathways” Model
Viable initiatives and partnerships were prioritised for scale, institutionalisation, and sustainability across DDF workstreams (Indicator 1.4) included:
- Completion and preparation for handover of the Ward Development Committee (WDC) Orientation Manual, anchoring citizen participation within formal decentralisation systems and providing a nationally scalable tool.
- Embedding radio‑based citizen feedback and monitoring mechanisms into CDF oversight discussions, with growing interest from government actors in adopting these approaches.
- Strengthening links between community accountability actors, investigative media, and oversight institutions (including ACC, NPA, and DEC), helping to close the accountability chain from citizen concern to institutional response.
- Supporting system‑level reforms that reached adoption or advanced decisively, including the incorporation of all four SME tax reform proposals into the 2026 National Budget, the progression of three agricultural reform Bills through Parliament, and the national rollout of the e‑Voucher FISP achieving scale and government ownership.
- Establishment and activation of seven Provincial Governance and Constitutional Engagement Hubs, enabling decentralised civic participation, coordinated submissions, and sustained engagement in reform processes across the country (Ongoing initiative and will be finally assessed at the end of March 2026 implementation).
- Institutionalisation of community‑led social accountability through the Training‑of‑Trainers (TOT) model, enabling independent community‑run social audits and replication across multiple districts.
While Output 1 achieved significant progress, a key challenge remains in sustaining and expanding reform coalitions beyond the traditional civil‑society space. This is not primarily due to lack of interest, but reflects the time and trust required to engage non‑traditional actors, such as professional bodies, faith‑based organisations, private‑sector actors and local leadership structures, who often face different incentives, risk considerations and mandates, particularly in politically sensitive reform contexts. Engaging these actors effectively requires more deliberate relationship‑building, tailored issue framing and sequencing, which the programme has begun to test but will need to deepen to ensure reform momentum is broad‑based and durable beyond the programme period.
Recommendation: In the final phase of the programme, the DDF should focus on securing the sustainability of its initiatives beyond the life of the project. In practice, this will mean consolidating its workstreams into packaged proposals which can be taken on by others (particularly the Government), including the evidence based and lessons learned, realistic recommendations for institutional actors responsible for implementation and explicit policy‑influence routes.
Output Title	DDF supports the implementation of agreed initiatives to address governance challenges.
Output number:		2	Output Score:	A
Impact weighting (%):		22%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of grants provided to implementing partners (iterative)	8 new grants	Met. 9 (National Democratic Institute (NDI), Bloggers of Zambia, The MAKANDAY Centre for Investigative Journalism, Media Institute of Southern Africa (MISA), Panos, AAAZ, Chapter One Foundation, IAPRI, ThirdWay Partners)
2.2 Degree to which the partners have implemented and completed the grant in a satisfactory manner (iterative)	90% (Partner scores 9 questions out of 10 questions)	Met. 100% All partners completing planned delivery by March 2026.

Output 2 measures the effectiveness and quality of implementation across DDF‑funded initiatives and activity‑based grants. During the review period, the programme provided nine new strategically targeted grants, in addition to the six existing partnerships (Kivu, ACA, JCTR, PAAGZ, SAIPAR, CTPD), to respond to emerging reform opportunities, consolidate delivery, and strengthen institutional uptake as the programme enters its final year (Indicator 2.1). Grant implementation (Indicator 2.2) has been largely on track for all the partners, with all planned delivery expected to conclude by the end of the review year. New partners built on the existing work being undertaken under the DDF to support delivery of the objectives. This included:
- Media & information integrity: In addition to BBC Media Action, the DDF brought on Bloggers of Zambia, Panos, the MAKANDAY Centre for Investigative Journalism and the Media Institute of Southern Africa (MISA) to strengthen media‑driven accountability and improve information integrity through investigative reporting, digital content formats, and radio programming. These partners collectively contributed to increased public scrutiny of governance issues and safer media operating conditions. Activities included journalist mentorship, radio debates, digital‑rights and cyber governance awareness, and constructive engagement with regulatory institutions such as the Independent Broadcasting Authority, supporting safer, plural, and evidence‑based discourse.
- Agricultural Reforms: Kivu has made substantial progress embedding the FISP e-voucher model. Following the closure of USAID, an opportunity arose for the UK to widen its support for agricultural reforms. The US was previously funding IAPRI to reform three pieces of legislation: the Food Reserve Act, the Agriculture Marketing Act, and the Agricultural Credits Act, which, if passed, would unlock the US Millenium Challenge Corporation’s $500 million compact with the Zambian Government. Through the DDF, IAPRI supported the Ministry of Agriculture to draft and consult on the legislation. As of March 2025, the Bills have passed third reading in Parliament and are awaiting Presidential Assent. In addition to IAPRI, the DDF took on ThirdWay Partners to provide rapid analysis and build a model to demonstrate Zambia’s agricultural export potential, demonstrating the potential for ZMW 31 billion (USD 420 million) in fiscal savings and ZMW 185 billion (USD 2 Billion) in economic benefits over 10 years, informing Cabinet‑level reform discussions.
- Electoral Integrity: Given Zambia’s upcoming elections in August 2026, the focus on elections has increased substantially. The DDF brought on NDI and Chapter One Foundation to support the constitutional reform workstream, including by providing legal analysis and observation of the consultation process
- Transparency and Anti-Corruption: To complement the work being undertaken by ICAR, the DDF brought on AAAZ to strengthen community-level anti-corruption action in Mandevu constituency through workshops that brought together Ward Development Committee (WDC) members, journalists, youths, and community-based organisations. Participants demonstrated increased confidence and capacity to identify, document, and report corruption, with improved understanding of reporting mechanisms and accountability channels. AAAZ’s engagement was reinforced through collaboration with Transparency International–Zambia and the Makanday Centre for Investigative Journalism, enabling concerns to be systematically channelled to Law Enforcement Agencies and reported through investigative journalism pieces. This shows the synergies that DDF is creating within the programme to influence on various issues.
- Energy governance: Although not a new partner, CTPD pivoted to a new strand of governance work focused on transparency and oversight in the energy sector. Since inception in December 2025, the project progressed from conceptualisation into analysis and engagement, completing a structured review of laws, policies and regulatory frameworks governing the electricity sector and identifying emerging governance and accountability risks. It facilitated the formation of a parliamentary caucus on mining, energy and minerals, strengthening legislative oversight, and prepared a national forum on debt and energy sector reform, including concept and agenda development. Upcoming outputs, such as the energy analysis paper and national stakeholder forum, are expected to feed directly into parliamentary scrutiny, policy dialogue, and public engagement on forthcoming electricity and petroleum sector reforms.
In addition to new partners, the existing partners under the DDF continued to perform well.
- Economic Reforms: KIVU provided real‑time technical assistance to the Government on core economic and agricultural reforms, supporting nationwide implementation of the FISP e‑voucher system, policy analysis for programmes such as Cash‑for‑Work programme, youth employment, SMEs, and agricultural financing, and support towards inter‑ministerial decision‑making through on‑demand modelling and advisory work.
- Community accountability & citizen participation: The DDF has been investing in citizen participation since its inception through ACA, JCTR, PAAGZ and CTPD. Partners working on social accountability, demonstrated strengthened sustainability and localisation of accountability processes. In multiple districts, trained community facilitators and Ward Development Committees independently convened social audits, conducted interface meetings with duty‑bearers, and escalated concerns that led to tangible responsiveness, including completion of stalled CDF projects and improvements to service delivery. These outcomes signal that DDF’s long‑term investments in capacity building and PDIA‑style facilitation are maturing into self‑sustaining accountability practices at local level.
- Research and Analysis: SAIPAR produced high-quality research and analysis examining continuities and changes in Zambian politics ahead of the 2026 elections. This included primary research in a sample of constituencies across Zambia – including in UPND strongholds, swing constituencies and former PF strongholds to understand 1) the local nature of the parties, 2) the base of their power, and 3) how that power is expressed to influence policy and governance outcomes. SAIPAR also produced an evaluation of the Cash for Work programme. This research will be used to inform policy briefs and political economy analysis, helping to ensure the DDF is thinking and working politically (which is integral to the DDF Theory of Change).

Output Title	DDF uses learning and best practices to influence governance policy and reforms.
Output number:		3	Output Score:	A
Impact weighting (%):		22%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of short learning papers/policy notes developed and shared by DDF (iterative)	15 Learning Products	Exceeded. 19 learning products / Mini Study on legal reforms, Corruption Perception Study, TIZ political financing study, Study on Political Cadres and DDF CDF Evaluation, 2 case studies shared with PDU, M&E pilot of CDF hour radio programs to MLGRD, Cash for Work study and Elections study by SAIPAR. 5 Constitution position papers, 1 Learning paper on constitution amendment advocacy, 2 policy briefs on energy by CTPD, Kivu Evaluation on e-voucher FISP
3.2 Number of communication products developed (infographics, articles, brochures, interviews, posters, radio shows etc) (iterative)	250 communication products	Exceeded. 330 communication products / 113 pieces of content for social media by BBC MA on various governance issues, 171 radio programs by all partners, PSAs for Kivu on 24 radio stations in 8 languages, 25 content papers done by Bloggers, 21 investigative pieces by MankanDay
3.3 Number of learning events/reflection meetings with partners, CSOs/governance actors to share lessons and best practices on the DDF (iterative)	12 (4 National Level dialogues, 4 Partner reflection meetings, Learning Events)	Met. 12 / 3 public forums on constitution amendment, WDC curriculum manual validation meetings, 1 constitutional advocacy reflection, 4 partner reflection meetings, 3 study dissemination meetings on Legal reforms, TIZ political financing and Corruption Perception Study
3.4 The level to which initiatives prioritized have been scaled up under any DDF theme (iterative)	8 partner initiatives scaled up	Met. 8 new partners / NDI, Bloggers, MakanDay, MISA, Panos, AAAZ, COF, AIPRI, ThirdWay Partners) added to DDF plus 4 partners (ACA, JCTR, BBC MA, PAAGZ) scaled up initiatives

Output 3 assesses the extent to which DDF generates actionable learning, communicates evidence effectively, and facilitates reflection processes that lead to initiatives being scaled by others. In 2025/26, DDF significantly expanded its learning pipeline.
The 19 learning products produced under the DDF in the previous year covered themes aligned with live reform processes, particularly constitutional reform, cybersecurity governance, agricultural market reform, and decentralisation, demonstrating a sharper link between evidence generation and policy influence (Indicator 3.1). These were complemented by learning events, production of communication products, radio programmes, investigative pieces, stakeholder dialogues, and media engagements aimed at translating evidence into policy influence (Indicator 3.2/3.3).
Indicator 3.4 measures the extent to which initiatives have been scaled up under any DDF theme. At a micro level, several partner initiatives demonstrated expansion or replication of effective practices, including the use of ‘Training‑of‑Trainers’ model in social accountability, the extension of community‑led monitoring into new wards, and the application of media‑driven accountability approaches across additional districts. At a macro level, learning from DDF‑supported initiatives informed system‑level scaling, most notably through the national rollout of the e‑Voucher FISP model, increased government interest in radio‑based feedback mechanisms for CDF oversight, and steps toward institutionalising the WDC manual.
The 2025 Annual Review recommended tighter links between learning, advocacy, and engagement, with earlier policymaker involvement and more policy‑specific outputs. Progress since then has been tangible but uneven. DDF exceeded its learning‑product milestone, producing 19 learning products against a target of 15, and used them more strategically, timing constitutional, electoral, anti‑corruption, social protection, and public finance outputs to active reform windows so they fed directly into submissions, public debate, media work, and advocacy rather than sitting as standalone learning interventions or reports. Integration between learning, communications, and engagement improved, with evidence amplified through radio, digital platforms, journalism, and public forums, and learning events increasingly serving as adaptive decision‑making spaces. However, policymakers’ early and sustained engagement in research remains inconsistent, and government uptake is still constrained where evidence challenges entrenched interests. Overall, learning became more relevant and better timed, but its translation into formal policy adoption or implementation remains selective rather than systematic.
Recommendation: In the final phase of the programme, DDF should prioritise producing decision‑ready evidence for specific institutional actors responsible for implementation, while using the provincial hubs to track whether learning is being applied in practice.
Output Title	ICAR equips Zambia with appropriate competences and skills to effectively use their legal and enforcement instruments to recover stolen assets.
Output number:		4	Output Score:	A
Impact weighting (%):		16.5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1. Percentage of ICAR trainees who testify to the effectiveness of ICAR training for their work (iterative)	65%	Met: 65%
4.2. Number of trainees successfully completing ICAR training.	150	Met: 154

Output 4 measures the extent to which ICAR’s training and capacity‑building efforts strengthen Zambia’s ability to investigate financial crime and recover stolen assets. This Output has scored A, reflecting strong performance across both indicators and further consolidation of skills within Zambia’s anti‑corruption chain.
Across the reporting year, ICAR delivered a robust programme of technical trainings, case‑based mentorship, and specialised support to investigators and prosecutors. A total of 154 trainees successfully completed ICAR training, meeting the milestone of 150. These included officers from the Anti‑Corruption Commission (ACC), Drug Enforcement Commission (DEC), National Prosecution Authority (NPA), Financial Intelligence Centre (FIC), Zambia Police Service, Zambia Revenue Authority (ZRA), and other specialised units engaged in complex asset recovery work. Training coverage remained strongly multi‑agency, ensuring coordinated investigative approaches across the anti‑corruption chain.
Post‑training surveys showed that 65% of respondents testified that the training had improved their effectiveness. A key strength this year has been the continued integration of case‑based mentoring into formal training. ICAR’s embedded experts provided continuous hands‑on guidance to investigators and prosecutors, helping them apply skills in real time ranging from analysing complex financial records to preparing affidavits, developing investigative strategies, and presenting evidence in court. ICAR training this year demonstrated high levels of knowledge retention, with trainees contributing directly to:
- Drafting Non‑Conviction Based Forfeiture applications
- Improving the quality and structure of financial analysis
- Strengthening cross‑border cooperation with jurisdictions such as the Isle of Man, Jersey, Austria, Hong Kong, and the USA
- Supporting investigations that led to the recovery or freezing of millions of dollars in illicit assets
However, sustainability challenges remain. High staff turnover in partner institutions continues to dilute institutional memory, and several cases were disrupted due to staff reassignments or leadership transitions, particularly within ACC. This reinforces the need for institutionalised training structures and consistent deployment of trained officers to specialised units. Despite these constraints, ICAR’s continued mentorship and multi‑agency training approach helped maintain momentum and consistency in investigative practice.
Output Title	ICAR supports Zambia to introduce suitable tools, procedures, instruments, policies or institutions to recover and manage stolen assets.
Output number:		5	Output Score:	A
Impact weighting (%):		16.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1. Examples of ZACC, DEC and/or NPA employing ICAR informed approaches and tools (iterative)	4	Exceeded: 7
5.2. Number of multi-jurisdictional operational or case-based meetings conducted because of ICAR’s intervention and with ICAR participation/facilitation (iterative)	40	Met: 44
5.3. Progress on policy and legal reform, key system or process change influenced because of ICAR interventions to strengthen the anti-corruption environment and institutionalise asset recovery (iterative)	ICAR to encourage and evidence uptake and utilisation of the provisional asset recovery and management and MLA drafted instruments aimed at addressing institutional gaps/gaps in successful handling of cases	ICAR helped draft a new asset‑management bill, approved in principle by Cabinet, and advanced the Mutual Legal Assistance Bill now under review, with further progress expected in early 2026. Reforms are already influencing practice, reflected in stronger cross‑border cooperation and the repurposing of recovered assets in line with best‑practice standards. ICAR also informed amendments to the Companies Act to enable deregistration of entities used for money‑laundering, strengthening Zambia’s preventive framework.

Output 5 measures the extent to which ICAR supports Zambian institutions to adopt tools, procedures, and legal frameworks that strengthen the country’s asset recovery system. This output has scored an A, reflecting strong performance and clear evidence of institutional uptake of ICAR‑supported reforms.
There has been substantial progress in the use of ICAR‑informed investigative and prosecutorial approaches across partner institutions. During the reporting period, seven examples of ZACC, DEC and NPA applying ICAR methodologies were recorded, well above the milestone of four. These included applying structured financial‑investigation techniques, preparing Non‑Conviction Based Forfeiture (NCBF) applications, improving the quality of Mutual Legal Assistance (MLA) submissions, and integrating forensic financial analysis in high‑value cases such as the helicopters case, environmental‑crime forfeitures, and major procurement and money‑laundering investigations.
Cross-border cooperation was a major highlight this year. ICAR successfully facilitated 44 multijurisdictional operational and case-based meetings. These engagements involved counterparts in the Isle of Man, Jersey, Austria, Hong Kong, Switzerland, the United States, and several other jurisdictions through the GFAR Action Series. These interactions enabled critical evidence exchange, and accelerated progress in complex transnational cases, including the execution of MLAs, parallel investigations, early intelligence sharing, and the unblocking of long‑standing evidentiary bottlenecks.
Significant advances were also made in legal and policy reform. ICAR supported the drafting of a new Asset Management Bill, which refocuses national policy on the management and disposal of seized and forfeited assets; the Bill received Cabinet approval in principle and is expected to move forward in early 2026. ICAR also helped progress the Mutual Legal Assistance (MLA) Bill, now under review following its earlier submission. Evidence from the last three quarters indicates that these reforms are already influencing practice: investigative teams improved the timeliness and quality of cross‑border cooperation and recovered assets in at least one case were repurposed in alignment with best‑practice standards reflected in the draft legislation, such as the use of forfeited properties for social protection purposes.
Additionally, ICAR contributed to amendments to the Companies Act, enabling the deregistration of companies used as money‑laundering vehicles. This reform originated from trends identified in ICAR‑supported cases involving Nigerian and Chinese syndicates and now strengthens Zambia’s preventive framework by closing a recurring vulnerability exploited in financial‑crime schemes.
Recommendation: ICAR should use 2026/27 as a transition year to help partner agencies institutionalise asset‑recovery practices and operationalise the potential forthcoming anti-corruption reforms, particularly the Asset Management and MLA Bills, so that skills, systems, and procedures are sustainably embedded beyond UK support.
## D: VALUE FOR MONEY

We assess that this programme continues to deliver value for money (i.e., the benefits of our investment on development impact in Zambia outweigh the costs). Supporting governance in Zambia is critical to UK objectives, both because the UK values democratic governance and partnerships, and because democratic governance underpins other UK objectives in poverty reduction, inclusive growth, trade and security. The ZDGP is the primary mechanism (alongside diplomatic influencing) through which the UK supports its governance objectives.

Both ICAR and Diakonia have VfM frameworks that are regularly updated to assess VfM against the ‘Four Es’. FCDO reviews this through its regular monitoring. Spot-checks provide assurance that the policies that underpin the partners approach to VfM are being followed. This review focusses on lessons that have emerged this year across the programme that build FCDO’s understanding of evaluating VfM in adaptive programmes.

Financial reporting (detailed in Section F) shows that programme activities make up most partners spend (80.47% for Diakonia and 87.02% for ICAR), with the rest on staffing and overhead costs (19.53% and 12.98% respectively). Given the nature of the programme, the key cost drivers continue to be expert technical assistance and facilitating engagements. FCDO Malawi’s TRACTION programme (which operates in a similar way to the ZGDP) reviewed its approach to VfM this year and the findings provide relevant lessons for this programme. For example, regarding economy, rather than measuring whether inputs were at the lowest cost, instead were they the right quality for what was needed? In this regard, we assess that experts engaged across ZDGP were the right quality and delivered the expected outcomes. For example, through IAPRI, the DDF engaged one of Zambia’s leading legislative drafters to provide zero drafts of all three agriculture bills. For a relatively modest investment (£50,000), the legal drafter produced drafts which provided the basis for government review and consultation, and were largely unchanged during the Parliamentary period. These bills will have a transformational impact on Zambia’s agricultural sector, demonstrating that with the right quality technical assistance, targeted at a specific issue at a pivotal moment, the UK can have impact at scale.

Ensuring key inputs are the right quality for what was needed, combined with strong procurement processes for ensuring other goods and services are secured at the lowest cost for the required quality, help ensure the programme is economic. For Diakonia, achieving economy means procuring goods and services through open, transparent, and competitive processes, ensuring that staffing and consultancy costs represent fair market value for skills and expertise, and leveraging shared services, partnerships, and in-kind contributions where feasible to reduce administrative costs and maximize investment in direct programme activities. For ICAR, economy means seeking multiple quotes for goods and services to minimise cost and utilising its Conflict-of-Interest policy to reduce the risk of staff involvement in transactions where a conflict of interest exists.

The programme’s flexibility continues to support efficiency. The programme was efficient to the extent that the processes worked in a way that generated (what broadly turned out to be) good decisions on investments, and it did so quickly. For example, when the constitutional amendments arose, within weeks the DDF was able to design a strategy, make budget reallocations and provide a platform for civil society advocacy that didn’t previously exist. Likewise, the decision to bring on ThirdWay Partners was a rapid decision taken to address a specific gap in the UK’s approach. Part way through the legislative process, FCDO recognised that economic analysis on the costs and benefits of the proposed reforms would build the technical and political case amongst the Government and Parliamentarians. This rapid action (and having systems in place that can enable these kinds of shifts) is critical to achieving VfM.

On effectiveness, the ZDGP is assessing whether the investments made achieved the intended outcomes and contributed to improvements in democratic governance. The nature of an adaptive programme is that effectiveness will differ across the investments; the critical determinant to achieving VfM is whether decisions to scale or exit investments were made efficiently. For example:
- We assess Kivu’s support to the Farmer Input Support Programme (FISP) to have been a highly effective investment. The evaluation of the 24/25 season showed that with Kivu’s support, the Government delivered the subsidies on time (99% of farmers successfully redeemed their e-vouchers before the rains), removed over 200,000 ineligible beneficiaries, added 200,000 new eligible farmers, created at least 5000 jobs in rural areas and reduced the price of inputs for farmers (a 50kg bag of fertiliser was on average K73 cheaper under e-voucher). Supporting the Government to spend its own resources better (FISP accounts for 80% of public spending on agriculture) is an effective way to achieve VfM.
- The picture on the constitutional reforms is mixed. Despite civil society pushback, the Government passed the amendments with few changes, which raises a question about whether the intervention was effective. It could be deemed as ineffective insofar as many of the concerns raised by civil society were not addressed. However, DDF partners made significant and worthwhile contributions to the consultation process by providing legal analysis, engaging citizens and directly lobbying the Government. This has value, regardless of the outcome. It also coalesced civil society organisations around a common issue and led to the decision to set up Provincial Hubs across the country. On that basis, the investment was effective. A lesson, therefore, is that it is important for FCDO to assess what of significant value has been created, as seen from relevant perspectives.
- As reported in the last Annual Review, the work by CTPD to design a dashboard showing real-time information on the Constituency Development Fund wasn’t taken up by the Government. Recognising this investment wasn’t effective, the DDF decided to keep CTPD as a partner but pivot their focus towards transparency and oversight in the energy sector.
By maintaining a clarity of purpose in reducing poverty and promoting inclusive growth in all aspects of the programme, we can contribute towards more equitable development in Zambia. Supporting policies which better meet the needs of the poorest Zambians are critical for having impact at scale in this area. However, equity can at times conflict with the other ‘Es’ (particularly economy), as it is more expensive to reach marginalised populations. This is compounded in a country as vast geographically as Zambia. For partners in Lusaka, reaching marginalised populations across the country is resource intensive but is critical to achieving the aims of the programme. At the impact level, governance indices show that the trajectory is not improving year-on-year; Zambia’s overall governance environment in 2024 shows marginally more signs of strain than progress. However, an area that is improving is civic participation. The DDF has focussed heavily on its convening function this year, creating and sustaining platforms that build accountability and inclusivity. The Provincial Hubs model is an innovative approach to building equitable civic participation. A key test in the coming year will be whether the Hub model can achieve VfM. It is more expensive than delivering solely through Lusaka-based CSOs (early financial reporting shows the Hub model is costing ~£60,000 per month), but building meaningful ‘coalitions of change’ requires more ambition on broadening coalition membership beyond traditional civil society actors and across the country.

Recommendation: Given the innovative approach being tested through the Provincial Hubs model, design VfM indicators (across the four Es) to assess whether this model is a cost-effective way of improving democratic governance.

E: RISK

Overview of risk management
The overall risk rating for ZDGP remains moderate, consistent with previous years. The programme continues to operate within BHC Lusaka’s risk appetite. During this review period, political uncertainty ahead of the 2026 General Elections, evolving cyber-security and information‑integrity dynamics, and ongoing constitutional and electoral reform processes elevated contextual sensitivity. All risk appetites have remained the same since the last Annual Review, except FCDO has revised the reputational risk appetite from cautious to receptive, recognising that work in this space can be contentious but a higher risk appetite in this area can lead to greater results. We will maintain a case-by-case assessment in this space. Mitigation measures included strengthened coalition‑based facilitation, expanded use of provincial hubs for decentralised engagement, continued application of political‑economy analysis to guide sequencing, and reinforcement of impartiality across programme interventions. Partners maintained updated risk registers, with Diakonia, BBC Media Action and ICAR providing quarterly revisions to reflect emerging risks and adapt implementation accordingly.
Risk Category	Summary of Risks	Risk Appetite	All risks within appetite?
Policy and Programme Delivery	Delivery risks this year reflected the increased pace of governance processes, as well as heavy workloads across DDF’s downstream partners. Staff turnover, particularly within investigative institutions, added operational strain on ICAR’s work. In the asset‑recovery strand, adverse jurisprudence posed risks to NCBF case outcomes, while the receipt of large volumes of Suspicious Transaction Reports (STRs) created analysis backlogs, especially within the Drug Enforcement Commission. Mitigation included strengthened accompaniment of partners, frequent progress reviews of downstream partners, clearer onboarding around adaptive programming, targeted measures to ensure inclusive engagement, intensive ICAR mentoring for newer investigators, recommended pairing of junior and senior case officers, and targeted analytical assistance sourced through the Malawi ICAR office.	Receptive	Yes
Strategy and Context	As Zambia moves toward the 2026 General Elections, heightened political competition and government civil and political discourse pose risks to project activities, including risks of shrinking civic space, leadership changes and potential politicisation of accountability institutions. The Cyber Security and Cyber Crimes Act and related measures may constrain civic engagement and accountability efforts. Mitigation focused on continuous political‑economy monitoring, coalition‑based engagement, careful sequencing of sensitive interventions, and working with like‑minded stakeholders to protect civic space; these measures kept risks stable and within appetite.	Receptive	Yes
People	People-related risks centred around staff turnover both within ZDGP partners and across government institutions. ICAR reported delays caused by resignations, slow reassignment of cases, and junior officers struggling with complex investigations. Diakonia and BBC Media Action managed internal restructuring and maintained delivery continuity. Mitigation included encouraging retention where feasible, detailed handovers, use of mentoring and peer support models, and for ICAR, pairing inexperienced investigators with seasoned officers to safeguard case progress.	Receptive	Yes
Financial and Fiduciary	Financial risk remained moderate and the programme continues to operate within the FCDO's acceptable risk levels. The risk of financial mismanagement is highest under Diakonia because of the increased number of downstream partners. Diakonia maintained strict financial controls, including pre‑disbursement expenditure verifications, random spot checks, and fraud‑awareness sessions. FCDO’s early‑year spot check identified 18 issues (all minor/moderate), with corrective actions progressing well, including updates to SEAH policy and VfM documentation. Diakonia also reported £9,000 in exchange losses, largely due to the Kwacha strengthening and put up a mitigation of immediate conversion to ZMW upon receipt of FCDO funds. ICAR’s financial risk remained low, with no downstream partners and strong internal controls	Cautious	Yes
Safeguarding	Safeguarding and SEAH compliance remained a key priority. Diakonia finalised its SEAH policy, trained focal points, and cascading training to downstream partners continued through the end of this review year. Additionally, both ICAR and BBC Media Action confirmed continuous SEAH awareness through partner engagements. No SEAH or fraud incidents were reported this year, and partners maintained active prevention and reporting arrangements throughout, including regular awareness‑raising and the dissemination of clear reporting pathways to partners, local authorities and participating communities, alongside confidential whistle‑blowing channels. Going forward, safeguarding remains an ongoing concern, and both partners and downstream partners are encouraged to continue strengthening awareness-raising efforts to ensure consistent understanding and adherence across all levels.	Cautious	Yes
Public Service Delivery & Operations	The reduction in the UK's Official Development Assistance (ODA) budget from 0.5% to 0.3% of Gross National Income (GNI) is likely to significantly impact various aid programmes. With less funding available, there will be a decrease in the number and scale of supported programmes. This situation has been exacerbated by the pause and termination of USAID-funded programs globally, including in Zambia. The UK government will need to make strategic decisions on how to allocate the reduced budget, potentially leading to difficult trade-offs and underfunding in some areas as a mitigation.	Cautious	Yes
Reputational	Given the politically sensitive nature of governance and civic‑space work, programmes risk being perceived as partisan. Reputational exposure also arises from third‑party statements/actions and, in asset recovery, from the risk that legitimate cases could be misused for political targeting. Mitigation included strict impartiality and message discipline, partner orientation with sign‑off protocols for public statements, refraining from commentary on sensitive political issues, and adapting interventions in response to political‑economy analysis. Risks remained contained.	Receptive	Yes

In addition to the risk categories discussed above, climate and environmental risks were assessed through a proportionate Climate and Environmental Risk Assurance process. As a governance and accountability programme, DDF and ICAR activities present a low level of direct environmental risk and do not involve infrastructure, extractives, or work in or near critical habitats. Indirect risks, such as disruption from extreme weather events, power outages, disease outbreaks, and environmental impacts associated with travel and convening, were mitigated through adaptive delivery approaches, business continuity planning, and remote engagement where appropriate. The programme does not support fossil fuels, does not undermine Zambia’s Nationally Determined Contribution, and is considered aligned with the Paris Agreement. Climate and environmental risks therefore remain low and within appetite.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Overall Assessment of Programme Management Performance
Programme management performance across all the ZDGP implementing partners was strong throughout the reporting period. Collectively, partners demonstrated sound financial control, compliance with FCDO requirements, and credible adaptive management, despite operating in a complex governance environment characterised by legislative uncertainty, leadership changes within accountability institutions, and heightened political activity ahead of the 2026 elections. Effective coordination between partners ensured that delivery momentum was maintained, with financial execution and risk management remaining broadly on track. Below is a summary of partner performance.
Delivery Performance
Diakonia and BBC Media Action
Diakonia and BBC Media Action continued to deliver the programme reliably, with consistent reporting and steady operational management throughout the year. To strengthen coordination and respond to the growing downstream partner portfolio under the DDF, Diakonia undertook several targeted staffing adjustments. These included recruiting a Project Officer to support partner management, engaging an issue‑based programming consultant to provide strategic guidance across interventions, and adding an additional Monitoring, Evaluation and Learning Adviser to improve adaptive learning and oversight across the facility. These changes contributed to stronger internal systems and smoother coordination between partners.
Delivery timelines improved after early‑year delays. Forecasting became more accurate as the year progressed: although there was underspend in Quarter 1, activity delivery increased in subsequent quarters, helping expenditure align more closely with plans. Continued attention will be needed to ensure activities match the disbursement schedule more tightly to avoid future variances. Regular field monitoring by Diakonia, BBCMA and FCDO helped identify operational challenges early and provided direct support to partners during implementation. These visits also strengthened communication between programme teams and downstream partner staff
On compliance, Diakonia continued to meet its obligations, submitting quarterly reports and FCDO compliance documents on time. Diakonia developed a Value for Money policy, updated its safeguarding (SEAH) framework, and supported partners to create and monitor risk and fraud registers. Fraud‑prevention measures remained strong across the chain, and Diakonia actively delivered fraud and safeguarding training to downstream partners. Overall, compliance performance remained good, with steady improvements in partner oversight and risk management.
Basel Institute on Governance – ICAR
ICAR’s performance during the period was satisfactory, with strong financial systems, clear budget monitoring, and reliable procurement controls. Forecasting generally aligned well with planned activities, and overall programme oversight remained steady. ICAR also contributed approximately £75,700 in core/in‑kind support, covering specialist fees, programme oversight, and delivery of NCBF training at no cost to ZDGP, ensuring continuity under reduced FCDO funding. ICAR continued to lead the quarterly Steering Committee, coordinating senior leadership across ACC, DEC, NPA and FCDO to ensure priorities and casework were aligned. Although one embedded specialist left mid‑year and was not replaced, the remaining two advisors sustained delivery while absorbing additional responsibilities across multiple law‑enforcement agencies. Adversely, this has increased pressure on their time, especially as more support requests are coming from the law enforcement institutions with limited capacity.
Compliance was mostly good, though some reports were submitted later than required. These delays did not disrupt delivery but point to the need for improved internal scheduling. ICAR’s internal processes remained solid, and financial management was consistently strong. With more timely compliance submissions and strengthened workforce planning, ICAR’s overall performance is expected to remain robust.
FCDO
FCDO strengthened programme oversight during the reporting period by adding a Programme Manager in the 3rd quarter of this reporting period, which improved coordination, financial oversight and engagement with all partners. FCDO held regular meetings with Diakonia, BBC Media Action, and ICAR to ensure that risks, delivery issues and compliance concerns were identified early and resolved. In addition to the monthly check-ins and ICAR-led strategic meetings with agencies, FCDO would benefit from a quarterly meeting with ICAR which brings together the programmatic and strategic sides of the project.
The confirmation of ODA budgets was delayed, constraining partners’ spending at the start of the financial year, which affected their ability to plan and commit resources early. More predictable ODA budget timing would help partners manage delivery more efficiently. FCDO strengthened risk management by delivering tailored safeguarding training and supporting fraud prevention training for all ZDGP partners. This improved SEAH systems, financial controls and fraud risk awareness across the delivery chain.
Overall, FCDO played an active and effective role in keeping delivery on track and strengthening risk management, helping the programme respond proactively to emerging risks ahead of the elections.
Financial Performance
Budget summary – Diakonia/BBC Media Action
During this reporting period, 80% of the FCDO funds was spent on programme activities channelled through grants to downstream partners. Staff costs were at 7.31% of total budget, aimed at providing technical support through consultancy and key programme staff costs. A 9.0% management fee covered leadership, coordination, and organisational support. Overhead costs stayed low.
A summary of Diakonia’ s/BBC Media Action finances is presented in the table below:
Activity	Budget (Total)	Actual Spend (YTD)	% Burn (YTD)	% of Budget Allocated
Programme activities	2,935,825	2,167,396	73.83%	80.47%
Staff costs	266,778	164,637	61.71%	7.31%
Overheads (office costs)	113,898	42,581	37.39%	3.12%
Management fees	331,650	249,096	75.11%	9.09%
Total	3,648,151	2,623,710	71.92%	100%

Budget Summary – ICAR
Key cost drivers during the reporting period included experts’ technical assistance relating to the salaries for senior anti‑corruption specialists deployed to Zambia, field allowances, international cooperation (GFAR) engagement and domestic travel and office running costs.
ICAR does not charge a management fee to the programme. Instead, ICAR’s contribution includes an in‑kind component, and the only indirect cost applied is the standard 14.6% overhead on eligible fees and reimbursable expenses.
An overview of ICAR’s finances is presented in this table:
Activity	Budget 23/24	Actual Spend (YTD)	% Burn Rate	% of budget allocated to activity
Programme activities and expert fees	278,631.00	213,397.01	76.59%	69.66%
ICAR Management Team Expenses - ICAR Staff costs	69,440	54,906.75	79.07%	17.36%
Office costs - Equipment procurements	970	969.78	99.98%	0.24%
Overheads (Office costs)	50,959	39,313.94	77.15%	12.74%
Total	400,000	308,587.48	77.15%	100.00%

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
Monitoring of the programme in 2025/26 combined routine reporting, structured partner reflection meetings, field‑based verification, and targeted assurance processes across both DDF and ICAR systems. Monitoring was designed not only to track progress, but to support adaptive decision‑making in a politically dynamic environment. These mechanisms, as detailed below, provided both accountability and real‑time learning.
- Quarterly and ad-hoc reporting/ meetings – ICAR and Diakonia/BBC Media Action submitted quarterly narrative reports covering contextual developments, implementation progress, risks, and emerging learning. Reporting quality remained consistently strong and supported timely management decisions. FCDO convened reflection meetings following each submission, while Diakonia maintained bi‑monthly partner reflection sessions that enabled downstream partners to pause implementation, analyse progress, and adjust approaches based on emerging evidence and political signals.
- Spot checks & follow‑up actions – FCDO conducted spot checks to strengthen assurance on financial management, due diligence, safeguarding, fraud controls, and risk management across the delivery chain. The Diakonia spot check conducted in Q1 2025/26 assessed overall risk as moderate, identifying 18 issues (5 minor, 13 moderate). Recommendations included finalising the SEAH and VfM policies, strengthening partner risk registers, and improving fraud‑risk documentation. By Q3 (Oct–Dec 2025), Diakonia reported completion of a SEAH policy, progress on VfM, and routine risk register reviews with partners. These findings informed corrective actions and reinforced compliance and accountability systems.
- Monitoring visits – FCDO and DDF partners undertook joint and individual monitoring visits across Livingstone, Chipata, Mazabuka, Katete, Chongwe, Kitwe, and Lufwanyama. Visits combined field observation, constituency‑level engagement, interface meetings with duty bearers, and in‑depth interviews with community members and local officials. In several locations, outcome verification was conducted alongside monitoring, strengthening both evidence validation and course‑correction.
- Stakeholder Engagement as a Monitoring Tool – Stakeholder engagements with ministries, parliamentary committees, regulators, CSOs, media, and community representatives doubled as implementation and monitoring, giving real‑time signals on institutional openness, reform traction, and political timing. Insights from these dialogues informed sequencing of engagements, adjustments to advocacy, and prioritisation of reform windows. The Bill 7 experience highlighted CSO coordination gaps with government counterparts, reinforcing the need to strengthen coalition management and engagement strategies in early 2026.
- Outcome Harvesting – Diakonia continued to use outcome harvesting to track observable behavioural and institutional change, particularly among rightsholders and duty bearers. Outcomes were recorded in an outcome register shared with FCDO on a quarterly basis. Examples from 2025/26 include:
  - Community‑initiated CDF dialogues and independent audits in Mazabuka and Katete.
  - Duty‑bearer responsiveness in Lufwanyama and Chongwe following community monitoring.
  - Media‑catalysed improvements in service delivery (e.g. renovations at Solwezi General Hospital following sustained radio coverage)
- Steering Committee Meetings (SCMs) – ICAR convened quarterly SCMs with FCDO, ACC, DEC, NPA, and ZRA. These meetings reviewed case progression, inter‑agency cooperation, institutional risks, and strategic priorities. The April 2025 SCM reaffirmed strong partner demand for ICAR support, the need to manage caseloads to preserve quality, and the value of multi‑agency coordination on complex cases.
Overall, monitoring systems functioned as adaptive feedback loops, enabling the programme to respond to political timing, operational constraints, and emerging reform opportunities rather than relying solely on linear delivery tracking.
Evidence
The evidence underpinning this programme has not changed this year. Stronger democracies have on average, higher economic growth, better health outcomes, improved access to education, better gender equality and are less prone to domestic and international conflicts. Evidence suggests that Zambia’s democratic system continues dealing with challenges in government effectiveness, corruption, economic performance, and public service delivery. During 2025/26, the programme generated high‑quality, politically informed evidence across workstreams, with increased emphasis on behavioural change, institutional responsiveness, and political feasibility, rather than activity alone. The evidence base deepened and diversified through a combination of outcome harvesting, investigative journalism, community monitoring, and case‑based asset recovery.
New evidence demonstrates change at multiple levels:
- Citizen demand & participation: Evidence shows increased citizen‑led CDF oversight (e.g., independent social audits, citizen‑run townhalls) and uptake of ATI/Data Protection pathways, with local officials demonstrating improved procedural readiness (e.g., digital record‑keeping and response commitments)
- Institutional responsiveness, and evidence-led policy design and delivery: Duty bearers responded to citizen monitoring and media scrutiny, including infrastructure fixes (e.g., Solwezi hospital) and CDF project adjustments, WDC tools progressed toward national adoption (manual and facilitator’s guide finalised). On the agricultural reforms, State House/line ministries acted on KIVU’s evidence (e‑Voucher 2025/26 adjustments and MSME TWG/platform) and ThirdWay Partner’s Cost Benefit Analysis quantified reform payoffs, together demonstrating a shift from ad‑hoc response to analytically guided implementation.
- Inter‑agency cooperation & legal effectiveness (ICAR): ICAR’s case‑based support underpinned high‑value recoveries, strengthened NCBF jurisprudence, and improved cross‑border cooperation (e.g., the helicopters case, Ops Athena, fire‑trucks). The programme facilitated 40 multi‑jurisdictional case meetings and advanced key legal instruments (Asset Management Bill approved in principle; MLA Bill under review), with early practice shifts (faster information sharing, better MLA quality, repurposing of forfeited assets in line with best practice).
Evidence quality is generally strong and draws on mixed methods, including qualitative outcome narratives, structured outcome registers, media analytics, administrative data, and court records. Monitoring and evidence generation increasingly reflect a ‘Leave No One Behind’ approach, with attention to participation by women, youth, persons with disabilities, and rural communities, and geographic disaggregation across provinces and constituencies. While quantitative disaggregation remains uneven across partners, qualitative evidence consistently highlights increased engagement by marginalised groups, particularly through community‑based accountability initiatives and local media platforms.
Learning
Learning over the past year has been generated through deliberate, embedded processes, including quarterly reflection meetings, joint monitoring and learning visits, outcome‑harvesting reviews, steering committee discussions, and case‑based learning within ICAR’s investigative and prosecutorial support.
These processes enabled partners and FCDO to adapt programming in real time and to test assumptions in politically contested environments. Key lessons emerging across the programme include:
- The importance of linking community‑level accountability efforts to credible institutional pathways for response and reform.
- The effectiveness of media as an accountability amplifier when paired with structured feedback and follow‑up mechanisms.
- The greater traction achieved through issue‑based coalitions compared to fragmented, theme‑based interventions.
- The limits of evidence uptake where reforms challenge entrenched political or institutional interests, even when evidence quality is strong.
These learning practices will be carried forward into the wider BHC Lusaka governance portfolio by strengthening portfolio‑level learning loops and the systematic use of adaptive MEL tools. In line with the BHC Lusaka M&E Strategy, learning from programmes such as ZDGP will be synthesised through existing platforms (Business Plan Delivery Meetings, Programme Scrutiny Boards and Annual Reviews), using outcome harvesting, contribution analysis and influencing tools to inform risk management, engagement strategies and future programme design, rather than serving reporting purposes alone.
Forward‑looking MEL Focus
Sharpening outcome-output linkages: In the final programme phase, MEL will place greater emphasis on tracing how specific outputs (e.g. learning products, media platforms, community accountability mechanisms, and technical assistance) combine to generate observable outcomes at citizen, institutional, and system levels. This will involve more deliberate articulation of outcome pathways, linking engagement, evidence use, and behaviour change, to strengthen understanding of how and why ZDGP‑supported interventions contribute to reform momentum, rather than treating outputs as ends in themselves.
Leveraging adaptive programming to strengthen contribution and attribution: ZDGP’s adaptive design provides a critical opportunity to strengthen contribution analysis by documenting decision points, adaptations, and political timing alongside observed outcomes. MEL will therefore prioritise capturing how iterative adjustments, such as pivoting workstreams, pacing engagement, or withdrawing from low‑traction interventions, shaped results. This will help distinguish ZDGP’s contribution within complex reform environments, demonstrating where outcomes are plausibly attributable to adaptive choices made by the programme rather than to contextual change alone.
As part of programme learning and reflection, engagement between FCDO and implementing partners during the review period highlighted important strengths and limitations of the logframe‑based results framework in politically sensitive governance programming. The logframe was viewed as useful for tracking and reporting changes in formal governance processes through clear, measurable indicators that support compliance and upward accountability. However, its usefulness was seen as more limited in fluid political contexts, where change is often driven by informal dynamics such as behaviour, incentives, relationships and power. In practice, the framework prioritises predefined indicators and targets, offering clarity on what has changed but providing limited insight into why change occurred. While revisions were possible, the logframe was not considered sufficiently flexible to respond to rapid policy shifts or leadership changes or to consistently integrate political‑economy analysis.
ZDGP’s implementation therefore demonstrates the importance of complementing logframe monitoring with qualitative, adaptive and politically informed MEL approaches, including outcome harvesting, reflective learning processes, and documentation of adaptive decision‑making. These tools have been essential for understanding contribution, supporting real‑time learning and navigating sensitive reform environments. Future programme design would benefit from more flexible results frameworks that retains accountability while better enabling adaptation, interpretation of change and strategic learning in complex democratic‑governance contexts.
Date of last narrative financial report	05/03/2026 - Diakonia / 03/02/2026 - ICAR	Date of last audited annual statement	17/02/2026 - Diakonia / 30/04/2025 - ICAR