## Annual Review Template

Title: Tackling Serious and Organised Crime in Ghana
Programme Value £ (full life): £3.5 million		Review date: 27 September 2025
Programme Code: [301282]	AMP start date: 27/09/21	AMP end date: 30/11/28

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A+	A	C	B
Risk Rating	Major	Major	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Project GB-GOV-1-301282 (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Project GB-GOV-1-301282 (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW

Description of programme
Serious and Organised Crime (SOC) poses a challenge to development in Ghana and the delivery of HMG’s strategic objectives. The Tackling Serious and Organised Crime in Ghana (SOC-G) programme aims to increase resilience to SOC in Ghana and in particular the resilience of vulnerable people, communities, businesses, government systems, and reduce SOC threats to the UK. It is designed to increase the capacity and commitment within government, civil society, and business to tackle SOC. The programme focuses on key priority threats to the UK and Ghana: grand corruption, cyber-enabled crime, illicit financial flows (IFFs), narcotics, and organised immigration crime. It is designed to enhance the effectiveness of His Majesty’s Government’s (HMG) SOC operations by supporting long-term institutional and political changes required for combating SOC. The SOC-G programme is designed to focus on Ghana, but recognising the transnational nature of these issues, it also looks to build better cooperation and partnership with Nigerian and UK agencies to deliver a trilateral institutional partnership to tackle SOC between these jurisdictions.
SOC-G delivers three inter-related outputs: i) enhanced capabilities of key state intelligence and law enforcement agencies to detect, investigate, prosecute, adjudicate and recover asset related to SOC; (ii) strengthened national, regional and international cooperation to tackle IFFs; and (iii) strengthened capacity of civil society organisations to advocate policy reform, raise public awareness, and conduct evidence-based research on SOC/IFF. An additional output: (iv) successful tendering of the contract, supplier mobilisation, and partner engagement – was introduced following the 2024 AR to capture key preparatory activities for rebooting the programme. This output has now been fully met and will be retired in the next reporting period.
The expected outcomes of SOC-G are: (i) strengthened policy reforms and better policy implementation; (ii) effectiveness of key state intelligence and law enforcement agencies in tackling SOC and corruption strengthened; and increased detection and investigation of illicit financial flows (IFFs), leading to higher asset tracing and recovery.
The SOC-G programme was designed to build on previous UK investments in Ghana related to tackling corruption and organised crime. Particularly, the Strengthening Action Against Corruption (STAAC) programme. The programme has faced significant delivery challenges over the years hindering its ability to achieve intended outcomes. Specifically, ODA budget reductions and pauses, gaps in advisory support and the absence of a reliable implementor have affected the programme delivery.
Over the past four years, three delivery phases have taken place:

- Pilot Phase: Gap analysis and some pilot interventions were initially delivered through Adam Smith International (ASI). These are reviewed in the 2022 SOC-G Annual Review (AR).
- Phase two: working through a third-party programme: Subsequently, the programme worked through the GIZ’s Governance for Inclusive Development Programme (GovID) from January 2022 until it closed in September 2023. This alternative delivery option was the most suitable option given the prevailing programme context (reduced ODA availability and limited advisory oversight). The outputs from this collaboration are described in the 2023 AR.
- Phase three: limited implementation: In the absence of an implementor and to maintain momentum following the closure of GIZ’s GovID programme, a short project intervention with the Africa Centre for Energy Policy (ACEP), jointly implemented with Ghana Anti-Corruption Coalition (GACC) and Ghana Integrity Initiative (GII), was delivered under Output 3. This intervention had the objective of integrating SOC awareness into the 2024 electoral process and to catalyse a collective commitment to combating corruption and SOC. The outputs from this partnership are reviewed in the 2024 AR.
To ensure that SOC-G delivers across the three programme outputs, the 2024 AR recommended securing a service provider through a framework arrangement. This delivery option provides more cohesive management of all programme outputs, overcoming the fragmented approach of previous delivery models. Importantly, this strategic shift is aligned with the original design of the SOC-G programme, which envisioned delivery through a bespoke service provider.

During the reporting period, the SOC-G programme did not implement any programme-funded interventions under its three core output components, as it was undergoing a strategic reboot to bring the programme back on track. However, the FCDO team conducted a targeted stakeholder engagement session with GoG counterparts to revalidate the programme’s relevance, reaffirm institutional commitment, and secure renewed buy-in for implementation. To capture the key preparatory activities undertaken during this phase, an additional output – successful tendering of the contract, supplier mobilisation, and partner engagement – was introduced, based on a recommendation from the 2024 AR. This process-oriented output served as a critical enabler, ensuring that the programme was fully operational and well-positioned to transition into the implementation phase. The output has now been fully achieved and will be retired in the next reporting period.

Summary supporting narrative for the overall score in this review
The table below provides a summary of performance scores for each of the SOC-G programme outputs during the reporting period. Note: Although no programme-funded interventions were implemented under the three core output components during the reporting period, significant progress was made in laying the groundwork for future outcome achievement.

Output	Output Description	Score
Output 1	Enhanced capabilities of key state intelligence and law enforcement agencies to detect, investigate, prosecute, adjudicate, and recover assets related to SOC	C
Output 2	Strengthened national, regional, and international cooperation to tackle Illicit Financial Flows (IFFs)	C
Output 3	Strengthened capacity of civil society organisations to advocate policy reform, raise public awareness, and conduct evidence-based research on SOC/IFF	C
Output 4	Successful tendering of the contract, supplier mobilisation, and partner engagement (fully met; to be retired)	A
Overall Programme Score		B

The programme is scored at B for the year under review. Although the programme did not fully meet its logframe targets for the three core outputs during the reporting period, primarily due to the ODA budget pause that delayed the implementation start date, substantial progress was made in positioning the programme for full delivery. A clearly defined pathway for the programme’s future years was established and a new implementing partner brought on board.

Stakeholder engagement was a major success. The programme secured strong buy-in from the GoG stakeholders during the reporting period, reinforced by the direct formal request from the President for UK’s technical support on corruption cases. These strategic engagements have helped revalidate the programme’s strategic relevance. In addition to appetite from stakeholders within the new GoG, the programme secured renewed support from HMG departments and agencies, with promising collaboration opportunities emerging. Notably, collaboration opportunities are being explored with the NCA to leverage its expertise, resources, and networks to enhance delivery of targeted interventions.

A key milestone achieved during the review period has been the development of a unified logframe, replacing the fragmented frameworks previously used for piecemeal interventions. The consolidated logframe provides a comprehensive structure for tracking and monitoring progress across the full duration of the programme. The logframe will be further refined during the inception phase for the new implementing partner to ensure alignment with the prevailing context and evolving priorities.

The successful completion of the procurement process and the selection of ASI as lead implementor for the remainder of the programme marks a critical milestone. To date, the absence of a consistent implementor has disrupted the programme’s execution. The contract award to ASI marks a shift from fragmented delivery, addressing a long-standing challenge in programme execution. ASI’s prior experience with the SOC-G pilot and the STAAC programme, combined with its strong track record in delivering high-impact, locally led anti-corruption and SOC initiatives across Ghana and other jurisdictions, positions the programme for future success.

Finally, recognising the financial constraints, the programme has embedded measures into its design (including break clauses in the supplier contract) to allow for adaptive planning and re-scoping if necessary. This ensures that the programme remains strategically focused and impactful within available resources.

Major lessons and recommendations for the year ahead

The following lessons and recommendations are considered necessary to keep the programme on track:

Recommendations:

In the evolving context, the SOC-G programme must remain strategically agile and politically informed, ensuring that its technical interventions are grounded in a deep understanding and real-time analysis of shifting power dynamics, institutional vulnerabilities, and reform incentives. Action: the programme (both FCDO and the new implementor) must maximise political cover throughout the programme to advance sensitive reforms by leveraging on top-level support (e.g. the President’s request for UK’s technical support to build GoG capacity on anti-corruption) and the broader UK-Ghana security relationship (e.g. where agencies such as the NCA maintain a strong position to advocate reforms).

To achieve strategic impact, the programme must move beyond siloed interventions and ensure integrated delivery across all programme outputs even under a reduced budget. Action: the new implementor should maintain the programme’s strategic coherence by delivering across all three outputs but in a phased and prioritised manner throughout programme implementation. During ASI’s inception phase they should focus on identifying high-impact, low-cost interventions under each output, sequencing activities based on urgency, feasibility, and available resources – ensuring that each output remains active, even if at reduced scale. This approach avoids the pitfalls of past fragmentation, preserves stakeholder confidence, and ensures that the programme remains responsive, relevant, and impactful even under constrained conditions.

Embed financial contingency planning into programme design. Given the uncertainties around future budget allocations, the programme must adopt a flexible and resilient delivery model. This includes break clauses in supplier contracts to allow for re-scoping if necessary. Action: the new implementor is expected to develop a scenario-based planning for different funding levels; prioritise high-impact, low-cost interventions and a reserve plan for scaling down without compromising strategic relevance by end of year one. This approach preserves the programme’s integrity while ensuring adaptability in a constrained financial environment.

Fast-track high-priority interventions during ASI’s inception phase. Use the inception phase not only for planning but also for early strategic wins. Action: the new implementor should implement urgent interventions during the inception phase including support to the FIC ahead of the FATF Mutual Evaluation and other short-term interventions that demonstrate impact and build momentum (should be achieved by end of year one) and will help build credibility, maintain stakeholder engagement, and lay the ground-work for longer-term reforms.

Action: the new implementor should maintain strong HMG stakeholder coordination and leverage complementarity, notably focusing on NCA, Home Office, SOCNet, and other bilateral and Centrally Managed Programmes (e.g., Ghana Governance Programme and the UK-Ghana Gold Programme) to maximise efficiency and impact of HMG support throughout programme implementation.

The current logframe and Theory of Change (ToC) were updated following the 2024 AR. Unlike previous fragmented logframes developed for the specific piecemeal interventions (ASI, GIZ, and ACEP), the consolidated logframe is designed to guide delivery across the entire remaining programme duration. As the programme transitions to unified delivery, the current logframe must be adapted to institutional realities and prevailing context, and serve as the foundation for strategic planning, performance monitoring, and adaptive management throughout the remaining programme implementation. Action: the logframe and ToC should be refined by ASI during their inception phase setting out clear milestones to guide implementation, monitoring and impact of programme throughout 2025-26 and beyond (due November 2025).

Action: The new implementor is expected to monitor risks associated with politicisation of anti-corruption efforts and judicial independence, adapting engagement strategies to mitigate institutional backlash or reputational exposure. The new implementor throughout the programme implementation should sustain political neutrality and system-strengthening approach, ensuring its support remains focused on institutional resilience and not entangled in politically sensitive outcomes.

Below are some lessons learnt over the review period:

One of the most critical lessons from the SOC-G is that stakeholder engagement is not a one-off event, it is a continuous strategic process that must be embedded into every phase of programme design and delivery. In contexts like Ghana, where reform is politically charged and institutional capacity varies, stakeholder engagement is essential. Regular dialogue with stakeholders provides real-time feedback on programme relevance, effectiveness and risks. It acts as a living monitoring mechanism, helping the programme adapt to changing political and institutional dynamics. During the review period, engagements with LEAs, CSOs, and other senior government officials were instrumental in revalidating the programme’s strategic direction, particularly, given the change of government in Ghana.

A unified delivery mechanism is essential to ensure synergy across programme outputs and to maintain strategic direction. The SOC-G programme’s fragmented delivery over previous years, through multiple short-term and piecemeal interventions has resulted in inconsistent progress across its three core outputs. This fragmentation has diluted the programme’s strategic coherence and hindered its ability to build momentum and to drive systemic change.

Budget constraints and uncertainties disrupt planning and delivery. The SOC-G programme’s trajectory has been significantly shaped by budgetary constraints and unpredictable funding allocations. The reduction in bilateral ODA funding not only prevented the engagement of a lead implementing partner early on but also forced reactive planning and short-term fixes. Even with the recent no-cost extension and the selection of ASI to implement the remaining years of the programme, uncertainty around future funding allocation for the outer years (post 2026) poses a serious risk to long-term planning. In the absence of financial predictability, adaptive planning and contingency mechanisms must be embedded from the outset.

A capable, experienced, and contextually grounded delivery partner is essential for coherence, continuity, and credibility. The selection of ASI as the lead implementor is not just a logistical milestone, it addresses fragmented delivery and institutional drift. ASI’s experience, prior involvement in the SOC-G pilot and contextual understanding positions the programme for more coherent and impactful implementation.
Abbreviations are expanded in Appendix B.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SOC-G programme’s ToC outlines a strategic pathway toward achieving its intended impact: increased resilience to SOC in Ghana and reduction in SOC-related threats to the UK. The programme’s impact is expected to be realised through three key outcomes: strengthened policy reforms and better policy implementation; improved effectiveness of key state intelligence and law enforcement agencies in tackling SOC and corruption; and increased detection and investigation of illicit financial flows (IFFs), leading to higher asset tracing and recovery.

To support these outcomes, the programme focuses on strengthening the capacity of key LEAs in Ghana, fostering regional and international cooperation to address IFFs and money laundering, and empowering civil society to advocate for reform, raise public awareness, and build coalitions to tackle SOC. These outputs are delivered through a combination of technical assistance, targeted financial support, diplomatic engagement, and coordinated cross-HMG collaboration. The ToC is underpinned by several critical assumptions, including the capacity of state and non-state actors, UK’s ability to influence political will, the availability of quality data for advocacy, and effectiveness of regional cooperation. While many of these assumptions remain valid, they require ongoing monitoring to inform adaptive programming, particularly in navigating politically sensitive issues.

During the reporting period, both the Logframe and TOC were reviewed. No significant changes were made to the underlying ToC. However, the logical framework was updated to reflect the focus on restarting the programme and, as shown in the diagram below the wording of the three outcome and output statements were refined to improve clarity and consistency. These adjustments were made to enhance understanding and alignment and do not alter the fundamental intent or strategic logic of the original business case. As set out above, a fourth output to contract an implementing partner was added, now that this has been completed, it will be removed.

Increased resilience to SOC in Ghana (vulnerable people, communities, businesses and systems) and reduced SOC threats for the UK emanating from Ghana
Strengthened policy reforms and better policy implementation
Effectiveness of key state intelligence and law enforcement agencies in tackling SOC and corruption strengthened

IMPACT
Increased detection and investigation of Illicit Financial Flows, leading to higher asset tracing and recovery
OUTCOMES
Enhanced capabilities of key state intelligence and law enforcement agencies to detect, investigate, prosecute, adjudicate and recover asset related to SOC

Strengthened capacity of civil society organisations to advocate for policy reforms, raise public awareness, and conduct evidence-based research on SOC/IFF
Strengthened national, regional and international cooperation to tackle Illicit Financial Flows (IFFs)
OUTPUTS
GOG, GON, HMG buy in
Momentum sustained
Data exists or can be generated
Partners available with capacity
Capacity exists
INPUTS
Grants and technical support to civil society
No unanticipated disruptions
Engagement with policy makers
Shaping political will
Active sharing of information
Managing politically sensitive issues
Political and administrative ownership
Investment in systems and processes
Financial support to build capacity
Diplomatic support and influencing
One-HMG platform for better coordination
Technical assistance to government agencies
Data and evidence gathering

As the programme enters its inception phase, the current ToC will be further refined to reflect the prevailing operational context and evolving priorities. This process will ensure that technical activities are clearly aligned with the programme’s outputs, outcomes, and impact, and that the ToC continues to serve as a practical and strategic tool for guiding implementation and measuring progress.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The SOC-G programme, after experiencing a period of being off track due to delivery challenges, is now firmly back on track to contribute to its expected outcomes and long-term impact. Previous years were marked by implementation disruptions stemming from shifts in delivery models, constrained funding, and transitions between implementing partners, which resulted in fragmented interventions and limited strategic coherence. Recognising these challenges, the current reporting period was deliberately used as a strategic reset, allowing the programme to recalibrate its approach, strengthen its delivery mechanism, and lay the groundwork for full implementation in the remaining years. It is worth noting that the timing of the programme’s re-launch was aligned with political transitions following the 2024 general elections. Key senior GoG stakeholders previously engaged by the programme team had changed, necessitating renewed engagement with the new leadership. This reporting period was therefore used to re-establish institutional relationships, reaffirm government commitment, and secure buy-in for continued programme implementation.

The programme has made significant progress in strengthening its strategic foundations. A unified logframe and ToC were developed, replacing fragmented frameworks used in earlier delivery models. This positions the programme to track progress effectively and manage future delivery. Importantly, there has been a strong buy-in from key stakeholders, reaffirming the programme’s strategic relevance within the evolving operational context. The programme also successfully secured approval for a no cost extension, which has extended its end date to November 2028 as well as securing UK ministerial approval for the programme to proceed. The successful contracting of ASI, as lead implementor, marks a critical milestone, shifting away from fragmented delivery and addressing a long-standing challenge in programme execution.

Looking ahead, the programme will move into full implementation, beginning with a 6-month inception phase led by ASI. This will deliver foundational outputs including a refined ToC, an updated results framework, and a detailed implementation plan. Urgent interventions including support to the FIC ahead of the FATF Mutual Evaluation will be fast-tracked in addition to other short-term interventions to build momentum.

In summary, the programme is firmly positioned for full delivery in the remaining implementation period, despite facing notable implementation challenges in previous years. While uncertainties remain around future ODA budget allocations, the strategic groundwork laid during this reporting period provides strong assurance for the programme to deliver impactful outcomes even within a constrained funding environment.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The objectives of the business case remain relevant, and delivery is still feasible even under a reduced budget due to ODA cuts. The programme remains relevant and has a clear niche based on ongoing need and gaps in the support being provided by other development partners especially regarding wider UK SOC priorities. The programme has received strong buy-in for collaboration from GoG stakeholders, as evidenced during an engagement session with potential beneficiary partners during the programme refresh phase. The programme also supports the new government priorities – President John Mahama has directly requested UK’s technical assistance on corruption-related cases. SOC-G has been used as one of the primary vehicles to assure the President of UK’s continued commitment to supporting Ghana’s anti-corruption and wider SOC priorities. The urgency of continued support is further underscored by Ghana’s upcoming 3rd Round Mutual Evaluation by the FATF in 2026 - a critical assessment of the country’s AML/CFT frameworks. The evaluation has already prompted increased activity around technical compliance, regulatory enforcement, and institutional effectiveness, areas that align closely with SOC-G’s objectives. The programme is well-positioned to provide targeted support to the FIC and other key stakeholders in preparation for this evaluation.

The SOC-G programme will directly support Home Office strategic priorities, including the planned signing of a Fraud Memorandum of Understanding (MoU) with the GoG, and complements ongoing NCA operations in-country. It is strategically aligned and complementary to both the Ghana Governance Programme (GGP) and the UK Ghana Gold Programme, ensuring coherence and synergy across UK’s anti-corruption and wider SOC priorities. Furthermore, SOC-G programme contributes to the BHC Country Business Plan focus on growth and security. Ghana is a key source country of SOC activity directly impacting the UK. GoG collaborates strongly with the UK to address these shared challenges.

Considering the above, and despite operating within a constrained budget environment, the SOC-G programme offers strong alignment. Its strategic focus, high-level political endorsement, and alignment with both national priorities and UK objectives make a strong case for its continuation. With key delivery enablers now in place and strong institutional buy-in, the programme is well-positioned to deliver targeted, high-impact results. In this context, scaling back or withdrawing support at this stage would risk undermining stakeholder confidence, and diminish the UK’s strategic influence in a space where demand for engagement is growing and the programme is primed to deliver.

## C. DETAILED OUTPUT SCORING

Output Title	Enhanced capabilities of key state intelligence and law enforcement agencies to detect, investigate, prosecute, adjudicate and recover asset related to SOC
Output number:		1	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	35%

Indicator(s)	Milestone(s) for this review	Progress
Number of personnel from key intelligence and law enforcement agencies (intelligence analysts, investigators, and prosecutors) trained with increased knowledge and/or skills in detection, investigation, prosecution and recovery of asset	Agree future milestones and methodology for tracking indicator including an assessment of the gender proportion within the agencies approved by FCDO	Not Met: This could not be met due to ODA budget pause that delayed the programme start date.
Number of judges trained with increased knowledge and/or skills to process and adjudicate SOC and corruption cases	Agree future milestones and methodology for tracking indicator including an assessment of the gender proportion within the specialism approved by FCDO	Not Met: This could not be met due to ODA budget pause that delayed the programme start date.
Number of implemented recommendations from National Risk Assessment (NRA) on ML/TF	Conduct assessment of NRA recommendations and agree with FCDO recommendations to be resolved.	Partially Met: The SOC-G Advisor in collaboration with the HMT reviewed the NRA and provided technical recommendations to the FIC for consideration.
Number of legal and policy reforms (national policies, legislative acts, regulations, institutional strategies, operational guidelines, or action plans) revised, developed or influenced with support of the programme to tackle SOC	Agree future milestone and developed methodology for tracking indicator approved by FCDO.	Not Met: This could not be met due to ODA budget pause that delayed the programme start date.

During the reporting period, no programme-funded interventions were implemented under Output 1, primarily due to the delayed programme start following the ODA budget pause. Whiles the core output indicators set out in the logframe could not be met during the reporting period, the period was used to
establish foundations for accelerated delivery in the upcoming implementation phase. Recognising the critical importance of this output in strengthening institutional responses to SOC, the programme maintained momentum through preparatory and enabling activities. This included engagement with state intelligence (FIC) and LEAs to assess institutional appetite, identify capacity gaps, and align with emerging national priorities following Ghana’s elections. As part of these efforts, the programme (though its Advisor and HMT advice) provided initial preparatory support to the FIC ahead of Ghana’s upcoming FATF 3rd Round Mutual Evaluation. This included advisory input on the National Risk Assessment (NRA), where the programme had the rare opportunity to review the draft NRA and submit technical recommendations. These recommendations were formally acknowledged by the FIC, underscoring the programme’s strategic value and positioning it as a trusted technical partner. This has laid the foundation for continued support to the FIC. The programme will build on this momentum by delivering targeted technical assistance and advisory support in the lead-up to the evaluation scheduled for first quarter of 2026, ensuring institutional readiness and alignment with FATF requirements. The programme is also now positioned to deliver future interventions that are demand-driven, context-specific, and strategically aligned. As a result, institutional strengthening efforts under this output will be better targeted to enhance the effectiveness of detection, investigation, prosecution, adjudication, and asset recovery related to SOC. The inception phase will be leveraged to validate the priorities identified during stakeholder engagement and conduct further scoping to ensure impactful interventions under this output.

Output Title	Strengthened national, regional, and international cooperation to tackle Illicit Financial Flows (IFFs)
Output number:		2	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	30%

During the reporting period, no programme-funded interventions were implemented under this output, primarily due to the temporary pause in ODA, which delayed programme resumption. Nonetheless, the period was used to initiate groundwork that will enable accelerated implementation in the coming phases. The programme engaged key national stakeholders to begin identifying priority areas for intervention and to explore potential entry points for enhanced national, regional and international cooperation. These include intelligence sharing, joint cross-border financial crime investigations, and capacity-building initiatives. The upcoming inception phase will be used to validate the priorities identified during these engagements and to conduct further scoping to uncover additional entry points for regional and international cooperation.

Output Title	Strengthened capacity of civil society organisations to advocate policy reform, raise public awareness, and conduct evidence-based research on SOC/ IFF
Output number:		3	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	35%

During the reporting period, no programme-funded interventions were implemented under this output, primarily due to the temporary pause in ODA, which delayed the programme’s start date. Nonetheless, the period was used to initiate groundwork that will enable accelerated implementation in the next phase. The programme conducted targeted engagements with some CSOs to assess potential entry points for future interventions under this output. Again, the programme undertook a strategic review of its previous interventions undertaken under this output. This included the Political Economy Analysis (PEA) of SOC vulnerabilities at the Tema Port conducted by IMANI Ghana, the Political Party Financing initiative led by the Centre for Democratic Development (CDD-Ghana) and the SOC-related elections intervention led by ACEP. While the CDD-Ghana and ACEP interventions are currently being continued under the GGP, there remains significant opportunity to revisit and build upon the IMANI-led intervention during the upcoming inception phase. The inception phase will be used to assess the feasibility of continuing and adapting the intervention to the current context, ensuring relevance and alignment with evolving national priorities. The inception phase will also create an opportunity to identify additional high-impact interventions that leverage the strengths of CSOs in advancing policy and public awareness.

Output Title	Successful tendering of the contract, supplier mobilisation, and partner engagement
Output number:		4	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Submission of a technical and commercial bid that meets FCDO specifications and result in the successful singing of contract	Contract signed	Met: Contract has been signed with ASI, the selected implementor following successfully procurement process.
Engagement with key partners to secure buy-in for programme implementation and initial preparatory support to the FIC for the upcoming FATF 3rd Round Mutual Evaluation.	Engagement with key partners	Met: Strategic stakeholder engagement sessions were conducted with GOG stakeholders and CSOs to build momentum, reaffirm institutional commitment, and secure buy-in for programme implementation.
	Initially preparatory support to FIC	Met: The programme in collaboration with HMT provided initial preparatory support to the FIC ahead of Ghana’s upcoming FATF 3rd Round Mutual Evaluation. This included timely advisory input on the NRA, where the programme had the rare opportunity to review the draft NRA and submitted technical recommendations to the FIC.
Supplier mobilised to begin stakeholder engagement	Supplier begins stakeholder engagement with both state and non-state actors	Met: Following the successful contract award to ASI, a formal kick-off meeting was held to initiate programme mobilisation. This engagement marked the official start of the inception phase, which will lay the foundation for full-scale implementation. ASI has subsequently commenced stakeholder engagement with both state and non-state actors, marking a key milestone in the inception phase.

Briefly describe the output’s activities and provide supporting narrative for the score.

During this reporting period, this output was fully met. The output was introduced following recommendations from the 2024 AR, with the aim of capturing the key processes and preparatory activities to reboot the programme. It serves as a foundational pillar, ensuring the programme is fully operational and well-positioned to transition back to implementation.

Indicator 4.1: Submission of technical and commercial bid that meets FCDO specifications and results in the successful signing of the contract – Met

During the reporting period, this output indicator was fully met. The programme team successfully developed a comprehensive Statement of Requirements (SOR), which served as the basis for the competitive procurement process. The SOR was designed to reflect the programme’s strategic objectives, technical requirements, and delivery expectations, ensuring alignment with FCDO procurement standards. Following its publication, the programme received expressions of interest from 24 suppliers, who participated in an Early Market Engagement session. This high level of interest is indicative of strong market confidence in the programme’s relevance, design, and potential impact. Ultimately, six suppliers submitted formal bids through the FCDO commercial framework. However, the evaluation process was temporarily paused due to the ODA budget suspension, which affected all programmes, including SOC-G. This necessitated an exemption process, during which SOC-G received ministerial approval, allowing the procurement process to resume. Following this approval, the programme successfully completed the evaluation of bids, resulting in the contract award to ASI. This milestone not only fulfilled the procurement requirements but also reactivated programme delivery, ensuring technical continuity and readiness for implementation.

Indicator 4.2: Engagement with key partners to secure buy-in for programme implementation and initial preparatory support to the FIC for the upcoming FATF 3rd Round Mutual Evaluation – Met

This indicator was met during the reporting period. Stakeholder engagement sessions were conducted with relevant intelligence and LEAs including the FIC, Economic and Organised Crime Office, Office of the Special Prosecutor, Narcotics Control Commission, Ghana Revenue Authority and the Criminal Investigation Department of Ghana Police Service. These engagement sessions revalidated programme relevance, reaffirmed institutional commitment, and secure buy-in for programme implementation and ensured that stakeholders perspectives were integrated into planning process. In addition, initial preparatory support was provided to the FIC including advisory input into the NRA process and strategic guidance and encouragement for the reconvening of the Law Enforcement Coordinating Bureau meetings. This step was instrumental in revitalising inter-agency coordination and operational readiness, both of which are critical for demonstrating effectiveness under the FATF evaluation framework.

Indicator 4.3: Supplier mobilised to begin stakeholder engagement – Met

This indicator was met during the review period. Following the successful contract award to ASI, a formal kick-off meeting was held to initiate programme mobilisation. This engagement marked the official start of the inception phase, which will lay the foundation for full-scale implementation. ASI has commenced stakeholder engagement activities and begun scoping work to refine intervention areas and delivery modalities. The inception phase will also accommodate some urgent national priorities, including continued support to the FIC ahead of the FATF evaluation, and the rollout of some short-term interventions that align with stakeholder needs and programme objectives. This concurrent approach ensures that while foundational work is being completed, the programme remains responsive to time-sensitive demands.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As part of recommendations from the 2024 AR, an additional output was introduced to capture the critical process and preparatory work to reboot the programme. This output sought to reflect the strategic and operational milestones required to re-establish programme momentum and readiness for implementation. During the reporting period, this output was fully met, marking a significant turning point in the programme’s trajectory and laying the groundwork for delivery across all other outputs. This output will be removed in the next reporting period, with focus returning to outputs 1-3.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The 2024 AR marked a pivotal turning point for the SOC-G programme, setting in motion a strategic reboot that has since reshaped its trajectory. Over the past year, the programme has made substantial progress in addressing the recommendations from the previous AR (Appendix A). All core recommendations were met or substantially advanced. A new Governance Advisor was appointed and a competitive procurement process led to the selection of ASI, a proven implementor with deep contextual experience. Two no-cost extensions were approved, extending the programme’s end date to November 2028, thereby enabling a more robust and strategic implementation. The programme also completed a thorough review and update of its logframe, with further refinements planned during the inception phase. Stakeholder engagement was revitalised, securing strong buy-in from GoG partners following Ghana’s elections, and aligning with complementary HMG programmes, reinforcing programme relevance. While the value for money framework was not fully delivered due to delays in implementation, interim progress indicators were developed to maintain accountability and track progress during the review period. The selection of ASI as lead implementor marked a strategic shift, addressing inconsistent delivery and positioning the programme for coherent future execution. Budgetary constraints and funding uncertainties emerged as critical risks, reinforcing the need for adaptive planning and embedded contingency measures and scenario-based implementation.

Looking ahead, the programme must remain politically informed and strategically agile, leveraging the President’s reformist posture to advance sensitive anti-corruption and SOC reforms. It should deliver across all the programme three core outputs in a phased and prioritised manner and fast-track high-impact interventions (including tailored support on upcoming FATF evaluation). Financial contingency planning must be embedded into programme design, including scenario-based planning and flexible contracting. Continued strong coordination with HMG departments and other bilateral programmes will be essential to maximise synergies and avoid duplication. Finally, an updated logframe and ToC must serve as the foundation for strategic planning and adaptive management throughout the remaining programme duration.

## D. VALUE FOR MONEY

Key cost drivers and performance

Although there was no programme spending during the reporting period, significant progress was made in advancing the roadmap developed in response to last year’s review recommendations, aimed at bringing the programme back on track. With the onboarding of the new supplier, ASI, which commenced implementation in August 2025, the programme is now positioned to accelerate delivery. A key priority moving forward is the development of a Value for Money (VfM) framework to ensure that the VfM proposition in the Business Case is tracked through to programme completion, with any changes to the original proposition appropriately documented. The VfM framework will include indicators on economy, efficiency, effectiveness, equity, and cost effectiveness, as defined in FCDO’s Approach to Value for Money. So far, the selected Supplier has presented interim information on VfM that depicts a comprehensive approach to VfM and once revised during inception, will inform VfM judgements, decision making and improve programme performance. The VfM framework will be developed and monitored alongside the logical framework. The Supplier will report on selected VfM indicators in the Quarterly and Annual Reports which in turn will inform FCDO Annual Review reporting.

Assessment of whether the programme continues to represent value for money

While output 4 was the main focus for the year under review (to bring the programme back on track), some progress was made against the other outputs of the programme that has positioned the programme for full delivery. Strategic actions have been undertaken to rekindle the programme during the reporting period, despite the absence of direct programme expenditure. The programme is currently well-positioned to begin inception and subsequent implementation. The next year will see full implementation albeit within a constrained ODA funding environment. Any necessary programme adjustments required as part of future ODA directives will be incorporated accordingly. These may include downscaling specific components, discontinuing certain activities, or, in the most constrained funding scenario, full termination of the programme. However, even in the lowest funding scenario, the programme remains relevant, its strategic focus (priority areas are receiving limited attention and support from other donors, with some previously supported state partners no longer receiving assistance in these targeted areas), high-level political endorsement, and alignment with both national priorities and UK objectives make a compelling case for its continuation. Implementing this programme not only enhances the effectiveness of HMG SOC operations, but also support long term institutional and political changes required for sustained improvement in the environment for combatting SOC.

E: RISK

Overview of risk management

The overall programme risk was initially assessed as major at last year’s review and subsequently reassessed as moderate following the successful recruitment of a dedicated Governance Adviser to lead the programme and the recent identification of a Supplier to manage the programme. During this same period, the programme experienced a pause whilst the implications of cuts to the overall UK ODA budget were worked through. The team successfully secured a ministerial exemption to continue the evaluation of Supplier bids, effectively mitigating the risk of an early programme closure. However, the temporary pause resulted in a three-month delay to the planned contract signing and implementation start date, shifting it from May to August 2025. Risks have been managed using the risk register and risk appetite tools. These tools were reviewed and updated on a quarterly and biannual basis on the system (AMP) to ensure compliance with risk reporting requirement.

The new Supplier is expected to develop a risk management plan with a robust approach to managing risks and will maintain a risk register aligned with FCDO’s risk register. The risk register would cover the following categories: strategy & context, policy & programme delivery, public service delivery & operations, people, safeguarding, financial & fiduciary, and reputational. The Supplier has shown as part of its bid, a detailed risk management approach including safeguarding, conflict and fraud risk measures which will be discussed with the team as implementation commences.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery and Commercial Performance

This year focused on bringing the programme back on track and align its delivery model with the Business Case, which proposed the engagement of a Supplier to oversee programme management. A detailed roadmap was developed to guide this transition, encompassing key activities such as drafting of ToR/SOR to secure a Supplier, collaborating with the procurement team to issue an ITT, and evaluating Supplier bids. The process also involved targeted engagement with key external partners including EOCO, FIC, OSP, NACOC among others and holding internal discussions with HMG departments such as NCA, HOIO, and HMT. Efforts were made to ensure complementarity with existing internal programmes, notably the UK-Ghana Gold and Ghana Governance programmes. A formal contract has been signed with the selected Supplier and a kick-off meeting held in August, marking the start of mobilisation for full programme implementation. With this milestone achieved, the Supplier (ASI) will now collaborate with the programme team and key internal and external stakeholders to begin implementation, beginning with inception phase deliverables and other priority interventions including targeted support for the FATF upcoming evaluation.

Financial Performance

There was no programme expenditure during this reporting period, as the in-house roadmap activities undertaken to bring the programme back on track did not require use of the programme budget. The programme has an approved budget of £3,500,000 and between 2022 to 2024 expended £1,083,617, exclusive of returned funds of £10,967 from GIZ following its project completion. The unallocated fund of £2,416,383 has been earmarked for programme implementation from August 2025. Out of this, £2.3 million has been allotted to the new Supplier to deliver on the programme objectives. The outstanding amount will be used for internal programme activities like independent programme reviews. All planned expenditures remain subject to ODA availability in the remaining years on the programme. However, the programme’s flexible and adaptive design ensures it can respond effectively to any ODA decision(s) in the future. The programme has embedded contingency measures into its design to allow for adaptive planning and re-scoping, if necessary, to ensure that it remains strategically focused and impactful within available resources (0.3 ODA scenario)

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Learning

In the year under review, the programme team, in collaboration with the Results & Evaluation Adviser, slightly edited the Theory of Change (ToC) and thoroughly revised the logframe (result framework) to make it comprehensive and fit for purpose, aligning it with the programme’s strategic direction. A new output was introduced to the logframe to capture key process indicators and milestones towards addressing delivery challenges to bring the programme back on track. The selected Supplier (ASI) is expected to further review and refine the existing ToC and logframe to reflect the prevailing context. In addition, the Supplier will design and implement a robust Monitoring, Evaluation and Learning Strategy during the Inception Phase to track programme performance and assess contribution towards achieving programme impact. Key findings from this will be captured in future Annual Reviews. A formal kick-off meeting has already been held with the selected Supplier. An inception meeting, along with regular programme update meetings, is planned in the ensuing months. Progress reports will be prepared by the Supplier and submitted to FCDO on quarterly and annual basis for review and approval.

2025 Annual Review Process

The SOC team drafted the review report following a desk review of key documents including SOC business case, logical framework, and risk register. The report has been peer reviewed, and quality assured by the Programme’s SRO (also Upstream Threat Team Leader) and approved by the Development Director. The final Annual Review report will be uploaded on the FCDO system (AMP) and published on Development Tracker.

Date of last narrative financial report	Nil	Date of last audited annual statement	Nil

Appendix A

Table 1: Progress against recommendations from the 2025 AR

2024 Recommendations	Progress on Recommendations
FCDO explores possible delivery options, under the leadership of the new Governance Advisor, to deliver across the three programme outputs. Three options have been identified, and they are (i) secure a service provider through the FCDO procurement framework/resource centre and/or in addition to an accountable grant agreement with a CSO/NGO, (ii) arrangement with another UK SOC unit combined with an accountable grant agreement with a CSO/NGO (iii) technical assistance contract and an accountable grant agreement with a CSO/NGO. For the first and preferred option, a draft Terms of Reference (ToR) is currently being developed to secure a service provider for the outstanding years.	Met, a new Governance Advisor has been at post since September 2024. The first option which is to secure a service provider through the FCDO procurement process has been completed resulting in contract award to ASI to begin implementation for the remaining years of the programme.
Given the limited time remaining on the programme, a time extension (and if essential, a cost extension) is likely to be necessary to ensure full implementation and impact. Extending the programme’s end date would allow for sufficient time to implement this strategic shift. The other two options serve as alternatives in case a suitable service provider is not secured. It is important to note that additional options may emerge as the situation evolves (November 2024).	Met, two time extensions (no-cost extension) have been approved. The first was a two-year no cost extension to the SOC-G programme from 31 August 2026 to 31 August 2028. This became necessary to allow sufficient time for a more robust implementation that ensures delivery of the outcomes originally envisioned. Subsequently, an additional three month no cost extension was approved following the ODA budget pause which prevented the planned implementation date of 01 May 2025. Both extensions were needed to enable the contract to be signed at its intended length (40-months). With these approvals, the programme now has an end date of 30 November 2025. / A cost extension was not essential at this point since about 69 percent of the programme value was yet to be spent. Additionally, the ITT attracted a strong array of bids from reputable Suppliers which showed good demand for the programme at its existing value.
The log-frame/result framework should be thoroughly reviewed and updated to align with the existing context. A log-frame should be completed by November 2024 setting out clear milestones for 2024-25, covering process as well as delivery. It should then be further updated together with the Theory of Change (ToC) when suppliers are engaged.	Met, the logframe has been thoroughly reviewed and updated with guidance and oversight from the Results & Evaluation Adviser. As new implementing partner enters its inception phase, the logframe together with the ToC will be further refined to reflect the prevailing operational context and evolving priorities. This is expected to be completed by the selected implementer (ASI) as part of inception phase deliverables.
Stakeholders must be re-engaged as well as Government of Ghana (GoG) partners. The NCA, Home Office and FCDO SOCNet (all represented in Ghana) have a clear development interest in building the capability of state actors and work regionally. There are also stakeholders in the UK, who provide relevant support, notably HMT in relation to the Financial Action Taskforce (FATF). The programme should seek complementarity of effort, and where possible, leverage existing HMG work for development outcomes. The programme should seek to complement two relatively new programmes: the UK-Ghana Gold Programme (led in country by FCDO SOC Network with Home Office funding) and the new Ghana Governance Programme (led by the BHC Political and Governance Team) (January 2025).	Met, the FCDO/BHC Accra team has engaged key partners internally (NCA, SOCNet, HOIO, HMT) and externally (EOCO, OSP, NACOC, FIC, GRA, CID) and has had collaborative discussions with the Ghana Governance and UK-Ghana Gold programmes in the FCDO to seek synergies in addressing the drivers and enablers of SOC in Ghana. These stakeholder engagements have helped revalidate the programme relevance, build momentum, and secure buy-in for programme implementation.
Establish a programme wide VFM framework, that may include process indicators for 2024-25, that holistically tracks and measures the VFM proposition in the Business Case.	Partially met, the VFM framework was not completed as planned due to delays in programme implementation, which were caused by the temporary pause in the ODA budget. As the VFM framework was designated as an inception phase deliverable, the delay in start directly affected its timely delivery. However, the programme team under the guidance & oversight from the Results and Evaluation Adviser developed progress indicators. These indicators were designed to capture key processes and preparatory activities undertaken during the programme’s reboot phase, ensuring continued monitoring and accountability despite the delay.

Appendix B

ABBREVIATIONS

ACEP	Africa Centre for Energy Policy
AML/CFT	Anti-Money Laundering and Countering the Financing of Terrorism
AMP	Aid Management Platform
AR	Annual Review
ASI	Adam Smith International
BC	Business Case
CID	Criminal Investigation Department
CSO	Civil Society Organisation
EOCO	Economic and Organised Crime Office
EOI	Expression of Interest
FATF	Financial Action Task Force
FCDO	Foreign Commonwealth and Development Office
GACC	Ghana Anti-Corruption Coalition
GGP	Ghana Governance Programme
GGP	Ghana Governance Programme
GII	Ghana Integrity Initiative
GIZ	Gesellschaft fuer Internationale Zusammenarbeit
GoG	Government of Ghana
GOV-ID	Governance for Inclusive Development
GPS	Ghana Police Service
GRA	Ghana Revenue Authority
HMG	His Majesty’s Government
HMT	His Majesty's Treasury
HOIO	Home Office International Operations
IFF	Illicit Financial Flows
ITT	Invitation to Tender
LEA	Law Enforcement Agency
MEL	Monitoring, Evaluation and Learning
MoU	Memorandum of Understanding
NACOC	Narcotics Control Commission
NCA	National Crime Agency
NGO	Non-Governmental Organisation
NRA	National Risk Assessment
ODA	Official Development Assistance
OSP	Office of the Special Prosecutor
PEA	Political Economy Analysis
SOC	Serious and Organise Crime
SOCG	Serious and Organised Crime in Ghana
SOR	Statement of Requirements
SRO	Senior Responsible Owner
STAAC	Strengthening Action Against Corruption in Ghana
ToC	Theory of Change
ToR	Terms of Reference
UK	United Kingdom
VfM	Value for Money