## Annual Review Template

Title: Research Secondment and Academic Advisory Programme (ReSAAP)
Programme Value £ (full life): £4.8m		Review date: Nov 2024
Programme Code : GB-GOV-1-301290	AMP start date: 12 Jan 2022	AMP end date: 31March 2028

Summary of Programme Performance
Year	Nov 2023	Nov 2024	Nov 2025
Overall Output Score	C	A	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301290 Documents (fcdo.gov.uk)
	D0003868.xlsx

Acronyms

AHRC	Arts and Humanities Research Council
AI	Artificial Intelligence
AR	Annual Review
BC	Business Case
DFID	Department For International Development
DSIT	Department for Science, Innovation and Technology
ESRC	Economic and Social Research Council
FCDO	Foreign Commonwealth and Development Office
FTE	Full Time Employment
LMs	Line Managers
MENA	Middle East and Northern Africa
ODA	Overseas Development Assistance
PFs	Policy Fellows
PIAP	Performance Improvement Action Plan
PMG	Programme Management Group
PWG	Programme working group (previously PMG)
PRO	Programme Responsible Officer
PRoF	FCDO’s Programme Management Rules
PSC	Programme Steering Committee
RED	Research and Evidence Directorate of FCDO
ReSAAP	Research Secondment and Academic Advisory Programme
RCC	Research Commissioning Centre
SRFs	Senior Research Fellows
SRO	Senior Responsible Officer
UKRI	UK Research and Innovation
VfM	Value for Money
XSD	Expertise and Science Department of FCDO

## A: SUMMARY AND OVERVIEW

Description of programme

Successful delivery and decision-making in FCDO relies on the organisation having expert, independent scientific and technical advice and challenge in the right place at the right time. Furthermore, the advice needs to be of a high quality – in a rapidly changing scientific and policy environment - and across a scope appropriate to FCDO’s changing requirements.

The Research Secondment and Academic Advice Programme (ReSAAP) provides funding and a partnership mechanism to increase access to deep expertise from trusted academic and research networks, including independent academic challenge and engagement on the FCDO’s priorities. Senior Research Fellows are matched to top priority requirements through a competitive process, supporting the Chief Scientific Advisor’s mission to support science advice into key priorities across the FCDO.

The programme is supported by partnership arrangements between a) FCDO and UK Research and Innovation (UKRI), and b) a partnership with the Research Commissioning Centre (RCC). During this reporting period it has been decided to move to using RCC as the sole partner for future Senior Research Fellows (SRF)s and UKRI will continue to manage the Fellows under their scheme until the end of their fellowships.

The programme provides funding for three types of expertise.

Senior Research Fellows (SRFs): Professorial-level senior academics who come into FCDO under a Fellowship Agreement to provide robust advice and independent challenge on research portfolios, policy development, and programme design. SRFs also produce rapid analytical products, draw upon their links and networks, help to build capability, and demonstrate thought leadership. FCDO partners with UKRI and the RCC, under ReSAAP, to fund a) legacy SRFs already seconded to the department pre-merger and whose universities were previously paid by FCO and DFID directly, and b) new cohorts of SRFs c) the extension period of two non-oda SRF’s previously paid for by UKRI.

Policy Fellows (PFs): FCDO partners with the Arts and Humanities Research Council (AHRC) and Economic and Social Research Council (ESRC), under ReSAAP, to place early- mid career academics up to Junior Professor Level, into the FCDO to work on discrete, policy impact-focused projects for an 18-month period. These 18-month placements of are fully funded by ESRC/AHRC with any subsequent extension paid for by the FCDO through ReSAAP.

British Academy Innovation Fellows (BA fellows): The FCDO partners with the British Academy, under ReSAAP, to identify early mid-career academics who are placed in the FCDO to work on discrete policy areas for a 12-month period. The Innovation Fellows are fully funded by the British Academy in their 1st year. Any subsequent years are funded by the FCDO through ReSAAP.

This is the third Annual Review of ReSAAP. The Business Case was approved in August 2021 and the project commenced on AMP in January 2022. This review covers the period November 2024 to November 2025. During this period ReSAAP’s progress included the extension of 2 PFs, the placement of 3 BA Fellows and the Board’s agreement to extend 9 SRFs from cohort 1 from FY 2026/27a and the placement of 3 new SRFs under cohort 2

Summary supporting narrative for the overall score in this review

The programme receives an overall score of A+. Progress has been made since the last review; however, not all previous recommendations have been fully implemented. Satisfaction levels for SRFs and Policy Fellows exceed targets, though the quality of data remains a concern, particularly the lack of feedback from stakeholders beyond policy and research teams.

Value for Money (VfM) during this reporting period compares less favourably with previous iterations of the SRF scheme. While the RCC delivery model has delivered clear benefits, such as a reduction in FCDO staff time to manage the programme, further work is required to rationalise costs and reduce the overall expenditure per Fellow under ReSAAP.

Progress on Recommendations form last review.

Recommendations from Nov 2024	Status
PMG /PSC should consider what measures will need to be put in place to effectively measure Impact/Outcomes	Ongoing. RESAAP Steering Board that meets every 6 months and a RESAAP Policy Working Group, however a process to capture impact beyond ResearchFish has not yet been finalised.
OUTPUT 1 Milestone currently 80% of policy teams satisfied with SRF . Suggest milestone is amended to 80% of stakeholders satisfied as SRF remit goes beyond policy teams.	Ongoing Logframe updated, but stakeholders was not defined and same survey (just policy/research teams was used)
OUTPUT 2 Suggest milestone is amended to 80% of stakeholders satisfied with PF	Ongoing Logframe updated, but stakeholders was not defined and same survey (just policy and research teams was used)
That the meetings of the PMG and PSC take place on the revised schedule as planned to ensure appropriate levels of governance and oversight of the Programme. Terms of Reference have been agreed and circulated. This will finalise and formalise the final elements of the programme governance arrangements and will provide a monitoring and challenge function going forward to ensure all elements of the programme remain on track. The PMG and PSC should also ensure that the overall activities being undertaken by the SRFs are fully aligned with the programme log frame and the wider strategic research priorities of the FCDO.	Actioned . RESAAP Steering Board that meets every 6months and a RESAAP Policy Working Group meets every quarter. A 2nd cohort of SRFs have been decided on in this reporting period and align with strategic research priorities of the FCDO.
The Output indicator around VFM should be removed as this is routinely measured in another section of the Annual Review.	Actioned
It is recommended that Programme Governance Structures are finalised as soon as possible to ensure that the monitoring of risk is being handled in as robust a manner as possible.	Actioned. Risk is a standing agenda item in both the steering group and the PWG.
The programme team should consider how Fellows recruited outside the UKRI partnership agreement are being monitored throughout the year in terms of delivery, commercial and financial performance. A process needs to be put in place to ensure these elements are being measured and monitored in the round for all Fellows.	Partial actioned. Commercial and financial performance are monitored by RCCs the 6 monthly surveys will pick up on delivery to some degree but there is currently no formal method to monitor output 1.2 and 2.2

Summary of recommendations for this Annual Review
1. Review Use of Academic Expertise
   Revisit previous work on how academics are utilised within FCDO to define which SRF impacts are most valued and should be prioritised. (Sept 2026)
2. Update Theory of Change (ToC)
   Revise the ToC to reflect the current delivery model beyond the original UKRI partnership. (June 2026)
3. Revise Logframe Targets and strengthen Monitoring, Evaluation and Learning (MEL)
   Board to review Logframe indicators and targets including the introduction of analysis of case studies, supported through strengthened MEL system from RCC. (December 2025)
4. Expand Satisfaction Measurement
   Develop a process to capture satisfaction and outcomes from stakeholders beyond policy and research teams, including external actors where relevant, capturing 2-3 outcomes Fellows have contributed to over the year. (May 2026)
5. Governance and VfM Monitoring
   Conduct a more thorough VfM analysis for consideration by the Board, with a comprehensive assessment of impact, demonstrating impact types aligned and prioritised to FCDO strategic objectives. (Ongoing)
6. Diversity Targets
   Update Indicator 3.1 to define “suitably qualified and diverse,” tracking gender, ethnicity, and institutional spread (target: 70% of Fellows from unique institutions). (May 2026)
7. Contracting and Financial Clarity
   Ensure clearer articulation of contracting requirements and formalise financial documentation expectations in agreements. (Ongoing)
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

ReSAAP provides the FCDO access to expert, independent academic advisers through Fellowship Agreements. These experts provide FCDO with high quality evidence and knowledge thus informing the FCDO’s policy and programme decisions directly and indirectly. Better policies and programmes, in turn, increases the FCDO’s development and diplomatic impact and reputation.

Theory Of Change (TOC)

The theory of change (TOC) for ReSAAP addresses potential knowledge gaps in the FCDO and ensures access to the most up to date thinking and evidence on specific topics by proposing a strategic alliance with a complementary knowledge partner such as UKRI (and its individual Research Councils). A strategic alliance is based on a shared funding / joint venture (JV) business model that is more integrated than a basic commercial relationship. Strategic alliances work best when they pool complementary assets, are structured to reduce transactional uncertainty; and encourage investment by both parties to create processes that meet both their needs, including:

Co-specialization to support wider strategic objectives
- Partnering to maximise potential to maximise opportunities for knowledge exchange
- Programme innovation through setting up mechanisms that build better understanding of each organization’s priorities, including building career opportunities through internships, fellowships, and developing expert networks (a preparatory step in the provision of rapid advice for emergencies).
Since the last AR for ReSAAP, major changes have occurred in the way the FCDO operates. These changes, the shift from 0.5% to 0.3% in ODA spend and the FCDO 2030 transformation programme, will have implications for how ReSAAP functions moving forward, particularly regarding the type of organisation in which SRFs are embedded. SRFs work across FCDO priorities including development programming, fortunately ReSAAP is already well positioned to adapt in this evolving environment and the underlying logic within the theory of change still holds.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact
Impact: FCDO delivers increased impact in its development, security and prosperity goals, through being informed by external expertise.
Indicator: Case studies demonstrating where ReSAAP-funded advice has contributed to delivering development, security and prosperity goals.
Impact is currently being captured through 6 monthly surveys, but the system can be improved. The current logframe does not require case studies against this indicator until project completion in 2028, however, given evolving FCDO priorities and the importance put on the project’s ability to evidence outcomes, it is recommended that RCC submits a MEL proposal for strengthening evidence of impact, including the analysis of case studies, and the Board revises logframe targets.

Outcome
Outcome: Qualitative feedback from FCDO policy makers and programme decision makers on where expert advice or capacity building has led to better decisions (at least 7 examples by Nov’25).
Indicator 1: Qualitative feedback from FCDO policy makers and programme decision makers on where expert advice or capacity building has led to better decisions.
Indicator 2: Qualitative feedback from the ReSAAP programme team shows that the partnership modality is demonstrating Value for Money.
For indicator 1 There is some qualitative evidence to suggest that SRFs/PFs are having a positive impact and there are at least 7 examples of them providing steers and options including where SRFs have strengthened decision-making and policy formulation through expert advice and capacity building. Fellows have enabled access to critical datasets, such as Altana, supporting new research programmes on global supply chains and economic security. Others have provided rapid, high-quality analysis during crises, such as the Bangladesh political situation, directly informing policy responses.

SRFs have also shaped strategic priorities in areas including antimicrobial resistance, quantum technologies, and food systems, ensuring investments are evidence-based and scientifically robust. In the MENA region, expert input on water security has influenced ambassadorial briefings and policy steer, while in Africa, fellows have delivered timely analysis on disinformation and security issues. Across portfolios, fellows have introduced innovative methods, challenged assumptions, and enhanced FCDO’s analytical capability, contributing to more informed and resilient decision-making.

Indictor 2 is discussed in a later section on VFM

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme continues to deliver against its core objectives and remains relevant to FCDO priorities. However, more work is required to capture and evidence impact across a diverse policy and research landscape. As FCDO priorities and approaches evolve, it will be essential for the programme to maintain flexibility and alignment, ensuring it continues to provide high-quality expertise that supports strategic decision-making.

Recommendations

- Review Use of Academic Expertise
  Given the changing organisational context and diverse application of SRFs, it is recommended that previous work on how academics are utilised within FCDO is revisited. This will help define which aspects of SRF impact are most valued and should be prioritised. (May 2026)
- Update Theory of Change (ToC)
  The current ToC was developed for a programme delivered solely in partnership with UKRI. It should be reviewed and updated, informed by the above analysis, to reflect the current delivery model. (June 2026)
- Revise Logframe Targets
  It is recommended that logframe targets are updated to include analysis of case studies by the next reporting period, covering both SRFs and Policy Fellows. These should demonstrate the full range of ReSAAP’s impact. This work to be supported by the additional MEL system proposed by RCC. (May 2026)
## C. DETAILED OUTPUT SCORING

Output Title	Senior Research Fellows (SRFs) deliver expert independent scientific and technical advice
Output number:		1	Output Score:	A+
Impact weighting (%):		60%	Weighting revised since last AR.	The wording of the output has changed since last year

Indicator(s)	Milestone(s) for this review	Progress
(FCDO's research and policy teams' satisfaction with advice provided by Senior Research Fellows. / Satisfaction measured in terms of the advice's relevance, timeliness, independence and easy to understand).	80% of Stakeholders satisfied	Exceeded as 100% of respondents responded they were satisfied with SRFS in sept survey. However the survey is still only going to host teams only and therefore there is limited data on wider stakeholder satisfaction.
1.2 Estimated percentage of SRFs' contracted days delivered.	80%	Achieved, Timesheets indicate no issue with contracted days delivered

Briefly describe the output’s activities and provide supporting narrative for the score.

A survey (sept 2025) was conducted to assess host team satisfaction and the perceived value of Strategic Research Fellows (SRFs). The response rate was 65%, representing a significant improvement from the previous round in March 2025 and providing a robust evidence base for assessing programme performance.

Headline Findings:
- Expertise and Value Addition: 86% of respondents were very satisfied with the expertise and knowledge of their Fellow, with the remaining 14% somewhat satisfied.
  100% agreed that their Fellow added value to their work, citing contributions such as depth of expertise, quality analysis, access to networks, and constructive challenge.
- Policy and Programme Impact: All respondents confirmed that Fellows contributed meaningfully—either through direct technical input or by enhancing policy formulation, programming rigour, investment decision-making, and strategic awareness within FCDO.
- Relevance and Communication: 86% found the Fellow’s advice relevant, and 14% somewhat relevant. 100% felt the advice was delivered in a way that was accessible and actionable for decision-makers.
- Sustained Engagement: All respondents indicated they would host a Fellow again

 UKRI Fellows

For current UKRI Fellows, they also report on impacts they are having to UKRI, which is summarised below

The UKRI-FCDO Senior Research Fellows (SRFs) initiative continues to provide strategic research input into UK foreign policy priorities. In the 2024–2025 reporting period, seven SRFs were active, with notable contributions in gender equity, conflict research, and critical minerals policy.
Key Achievements
- Policy Engagement & Influence
  - Prof. Sally Theobald (Women and Girls Empowerment) established a support network for SRFs and contributed to gender equity and inclusion efforts within the FCDO’s Research Evidence Department (RED).
  - Prof. Jonathan Goodhand (Conflict) facilitated research partnerships and organised a high-profile event on global order transitions for international policymakers.
  - Dr. Daniel Smith (Critical Minerals) convened a strategic workshop engaging policymakers, industry leaders, and civil society on supply chain resilience.
- Research Collaboration
  - Two SRFs reported active collaboration with academic and policy institutions, including briefing sessions and knowledge-sharing events involving southern partners.
- Capacity Building
  - Three SRFs contributed to advisory committees and practitioner training, reinforcing the programme’s role in shaping future expertise in priority areas.
UKRI Engagement
- Prof. Ruth Oulton participated in EPSRC’s quantum technologies fellowship review panel and presented at the “Science and Sandwiches” staff engagement event, exemplifying cross-council collaboration.
- UKRI aims to enhance proactive engagement between Research Councils and SRFs in the coming year.

RCC fellows

RCC the sole supplier for SRF going forward do not currently capture any additional impact stories and are reliant of the above survey sent by the programme team to manage performance. As responses to survey are low it is recommended RCC provides a costed proposal for the more systematic monitoring of impacts and following up with users of research projects outside FCDO.

  1. Estimated percentage of SRFs' contracted days delivered.
Achieved, Timesheets indicate no issue with contracted days delivered

Describe any changes to this output during the past year, and any planned changes because of this review.

The last annual review recommended milestone for Output 1.1 to be changed from 80% of policy teams satisfied to 80% of stakeholders satisfied (which will include the research and policy teams). however, all the surveys are still being sent only to host teams.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead

There has been no progress on capturing satisfaction of SRFs outside of policy teams and research teams. It is recommended A process to do this should be discussed at steering board and formalised with RCC. The term stakeholder will need to be defined and where appropriate include non FCDO actors as well, particularly were a SRF has been utilised to strengthen influencing (May 2026)

## DETAILED OUTPUT SCORING

Output Title	Policy Fellows deliver expert independent scientific and technical
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR.	No – not in log frame for previous AR in this format

Indicator(s)	Milestone(s) for this review	Progress
FCDO's research and policy teams' satisfaction with advice provided by Policy Fellows (PFs) [Satisfaction measured in terms of the advice's relevance, timeliness, independence and easy to understand]	80% of policy teams satisfied	Performance against this indicator exceeded expectations, with 100% of respondents reporting satisfaction with PFs in the September survey. However, the survey was limited to Research analysts and received only one response (of two active PF) , restricting the breadth of stakeholder insight. Future cycles should expand the survey to include a wider range of stakeholders to ensure a more representative assessment of programme impact.
Estimated percentage of PFs' contracted days delivered	80%	Achieved, Timesheets indicate no issue with contracted days delivered

2.1 FCDO's research and policy teams' satisfaction with advice provided by Policy Fellows (PFs)

Of the three teams hosting Policy Fellows only one responded to the survey. response noted that the Fellow has significantly enhanced FCDO’s analytical capability by enabling access to the Altana dataset, supporting the development of a new research programme on global supply chains and economic security. While it is too early to quantify impact, this work is shaping decision-making and building long-term expertise.

The Fellow has also led innovative methods for Russia/Ukraine analysis, piloting the use of satellite-derived night light data to assess the impact of attacks on energy infrastructure and regional recovery. These approaches, now in high demand, would not have been tested without her leadership and have strengthened FCDO’s capacity for complex, data-driven analysis.

2.2 Estimated percentage of PFs' contracted days delivered

Achieved, Timesheets indicate no issue with contracted days delivered

Describe any changes to this output during the past year, and any planned changes because of this review.

The last annual review recommended milestone for Output 1.1 to be changed from 80% of policy teams satisfied to 80% of stakeholders satisfied (which will include the research and policy teams). however, all the surveys are still being sent to host teams.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead

There has been no progress on capturing satisfaction of SRFs outside of policy teams and research teams.
It is recommended A process to do this should be discussed at steering board and formalised with RCC. The term stakeholder will need to be defined and where appropriate include non FCDO actors as well, particularly where a PF has been utilised to strengthen influencing (May 2026)

## DETAILED OUTPUT SCORING

Output Title	SRFs and PFs recruited, seconded and perform effectively
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR.	NO

Indicator(s)	Milestone(s) for this review	Progress
Suitably qualified diverse SRFs and PFs recruited and seconded to relevant policy and/or research teams in FCDO [ disaggregated by gender, ethnicity and disability]	tbd (dependent on decision on whether to recruit a second cohort of SRFs and PFs in 2024)	Cohorts are qualified and there is a mix of genders across all current fellows. 40% male 60% female
Programme governance structures effectively manage programme performance and risk	Policy board convenes and reviews programme spend against forecasts and risk. Strategy board established and meets at least once.	Two boards have been meeting in this reporting year. The RESAAP steering board (twice ) and the policy working group(PWG) (4 times)

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme scores A for this output. While the logframe target has not yet been updated (3.1), a review of all SRFs confirms a diverse mix of highly qualified individuals. Governance arrangements have also strengthened since the last review period, with both groups meeting regularly and providing clear strategic steer for the programme.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead

Governance and Monitoring
The governance structure has now been formalised and is meeting at an appropriate cadence. It is recommended that both governance groups continue to monitor Value for Money (VfM) and strengthen approaches to capturing impact, including identifying which types of impact are most critical to align with FCDO’s strategic priorities. (Ongoing)

Logframe and Diversity Targets
It is further recommended that the logframe is updated to include a clear target for Indicator 3.1, defining what “suitably qualified and diverse” means within the context of this programme. In addition to gender and ethnicity, diversity should also be tracked by home institution, with a proposed target that at least 70% of Fellows are the sole representative from their institution. This will help ensure a broad institutional spread and maintain programme inclusivity. (May 2026)

.

## VALUE FOR MONEY

Value for Money (VfM)

Economy
The ReSAAP programme’s key cost drivers, as outlined in the Business Case, include:
- Labour costs for technical advice
- Travel, subsistence, and meeting expenses
- Overheads
- Administration and partnership management costs

Initially, FCDO anticipated funding all SRF roles. However, under the partnership arrangement with UKRI, 7 out of the original 10 SRF roles agreed via UKRI partnership for cohort 1, were recruited – 5 ODA and 2 non-ODA. All 7 are 20% funded by their academic institutions with FCDO funding 80% of the 5 ODA SRFs and UKRI funding 80% of the 2 non-ODA SRFs. The additional 7 SRFs subsequently recruited via RCC in cohort 1 are fully funded by FCDO. Any savings are re-profiled to support additional SRF or Policy Fellow requirements. With RCC now confirmed as the delivery partner for all SRFs, future cohorts will be 100% FCDO-funded.

Although sourcing fellows through RCC was noted as a more expensive option, the model has proven successful and less administratively intensive. However, costs have risen significantly. For the first cohort, RCC’s non-staff administration costs totalled £395,186.33. In Phase 2, RCC has committed to reducing these costs to £115,245, reflecting both a smaller cohort and a reduction in non-direct fees charged to FCDO.

This reduction marks a positive step towards improved economy. Nonetheless, it is recommended that the fee structure be monitored and the VfM of the expertise is benchmarked against alternative sourcing models, including internal provision, to ensure VfM.

Efficiency
Programme decisions have contributed positively to efficiency:
1. Single Supplier Model: Engaging RCC as the sole supplier for future cohorts is expected to streamline placements and unify systems.
2. Strategic Sourcing: Sourcing multiple fellows for certain fellowship roles enhanced selection efficiency and optimised staff time and Board supporting broader government needs. These decisions, endorsed by the Chief Scientific Adviser, enabled timely access to critical expertise in areas such as AI and climate-resilient agriculture.
Effectiveness
Effectiveness is currently difficult to quantify due to the diverse roles of SRFs across teams. Early feedback suggests positive contributions, but further work is needed to systematically capture and measure impact.

Equity
FCDO and UKRI have embedded equality, diversity, and inclusion considerations into all SRF opportunities, adhering to standard recruitment practices. All current SRFs are from UK institutions, a legacy of the UKRI-led approach. Future cohorts may consider expanding the applicant pool, though this may affect working arrangements (e.g. remote vs hybrid) and security clearance requirements.

Assessment of VfM
The ReSAAP Business Case’s theory of change remains valid: external expertise continues to add value to diplomatic and development decision-making. However, a comprehensive analysis of VfM and assessment of impact is needed.

Recommendations
1. Clearly communicate travel and subsistence policies to fellows at placement.
2. RCC to implement proposed reductions in overheads for Phase and non SRF fees to continue to be monitored to ensure total cost in comparable with other approaches of sourcing expertise
3. Board to explore option of RCC providing dedicated MEL (Monitoring, Evaluation, and Learning) time in Phase 2 to better capture impact across all SRFs.
4. Conduct a more thorough VfM analysis for consideration by the Board.

E: RISK

Overview of risk management

The last AR recommended that the PMG (programme management group) should take responsibility of risk. In the report period the RESAAP Steering Board that met every 6 months and a RESAAP Policy Working Group that sits underneath this that meets quarterly. Risk was a standing item on the agenda for both groups

During the reporting period, several key risks were identified that could impact programme delivery and financial integrity. These included:
- Contracting Delays: Feedback loops with university partners and internal RCC approval processes contributed to slower-than-anticipated contracting timelines.
- Budget Estimation and Forecasting Challenges: Inaccuracies in initial budget projections created downstream issues in financial planning and tranche disbursements.
- Financial Compliance: A notable case at one University revealed ineligible travel costs during RCC spot checks. This underscored the importance of rigorous financial scrutiny.

In response, RCC implemented targeted mitigation measures:
- Requested 100% supporting documentation for the affected quarter at with a conditional offer to reduce sample sizes in future quarters upon demonstrated compliance.
- Maintained tranche-based reconciliations to ensure ongoing financial oversight and safeguard public funds.
- Introduced regular FCDO check-ins, streamlined selection processes, and phased approvals to reduce operational bottlenecks.
- Strengthened communication protocols with university partners to improve clarity and responsiveness.
Recommendations include:
- Clearer articulation of contracting requirements and eligible cost.
- Formalisation of financial documentation expectations within contractual agreements.

The overall risk rating for the programme is Moderate. This falls within the Research and Evidence Directorate’s appetite for risk.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Both UKRI and RCC are responsible for providing quarterly reports on finance, and risk is discussed at monthly meetings with partners individually and reviewed in both Governance Group meetings.
The programme also supports the placement of other Fellows, such as those from the British Academy. This extra support for these wider fellowship campaigns is an added benefit of the programme, with some extensions of Fellows covered from the programme budget.

Financial management, the FCDO has agreed to transfer funds to UKRI on a quarterly basis, as set out in the Memorandum of Understanding. Costs for the RCC SRFs are paid on receipt of quarterly invoices as part of the FCDO umbrella a with the Research Commissioning Centre.
ReSAAP spend as of September 2024 is £ 2,110,455.56. A no-cost extension to 31 March 2028 has been agreed to allow the programme to complete its implementation. It is expected that ReSAAP will fully spend its budget in its new project time frame with the extensions of 9 SRFs, and fellowship awards for 3 new SRFs that is currently underway by RCC FCDO.

 Management arrangements: Through the partnership documents, , UKRI and RCC have agreed that:
ReSAAP Strategic Board, comprising of senior representatives from UKRI, RCC and the FCDO. The Board meet on a six-monthly basis to review progress and take major strategic decisions. Two meetings have taken place over the course of the annual review period.

ReSAAP Policy Working Group is made up of delivery representatives from FCDO, UKRI and the RCC. This group meet quarterly to sustain the co-ordination, oversight, and direction of the Programme. This includes reviewing the risk register, monitoring arrangements, and finances. There have been 3 Policy Working Group meetings in the annual review period.

Date of last narrative financial report	UKRI August 2025 / RCC October 2025	Date of last audited annual statement	UKRI – July 2025 / RCC – 29th May 2025