Programme Completion Review

Title: Partnership for Maternal, Newborn and Child Health (PMNCH)
Final Programme Spend £ (full life): £6,000,000	Review Date:	20/09/2025
Programme Code: [AMP ID#] 301302	Start Date: 15/10/21	End Date: 31/08/25

Summary of Programme Performance

Year	2022	2023	2024
Programme Score	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Major

DevTracker Link to Business Case (and any addendum):	Business Case
DevTracker Links to all logframes used during programme lifetime:	Log frame

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]
The Partnership for Maternal, Newborn and Child Health (PMNCH) is the world’s largest global advocacy programme for advancing the health and well-being of women, children and adolescents (WCAH). It is hosted by the World Health Organisation and works through a secretariat mostly based in Geneva. It brings together more than 1500 members across 130 countries, collaborating across six constituencies. The 2021-2025 strategy aimed to focus on three thematic areas - to contribute to reducing preventable maternal, newborn and child morbidity and mortality (MNCH), including stillbirths; ensuring progress on financing and equitable access to comprehensive Sexual and Reproductive Health and Rights (SRHR); and advancing the health and well-being of adolescents (AHWB). Every day in 2023, over 700 women died from preventable causes related to pregnancy and childbirth, suggesting that the need for global advocacy to drive forward progress to reduce preventable maternal, newborn and child deaths remains high.

PMNCH’s outputs over the reporting period were;
1: Knowledge synthesis- creating knowledge products to support PMNCH to advocate for commitment-generation and to hold commitment makers accountable for implementation;
2: Partner engagement- providing advocacy skills and networks for PMNCH members through PMNCH’s member engagement process;
3: Campaigns and Outreach- increased participation by PMNCH members in advocacy campaigns due to PMNCH’s products, events or outreach;
4: Ways of working- streamlining of systems and governance including introduction of a Monitoring, Evaluation and Learning Strategy and clearer evidence of strategic prioritisation of the workplan.

In the reporting period PMNCH has secured 34 LMIC commitments to PMNCH’s Call to Action on COVID-19 and for improvements to adolescents’ health and wellbeing. They have secured seven global and regional commitments, as well as 15 commitments from non-governmental stakeholders. Some examples of these commitments are Ethiopia’s commitment to reducing teenage pregnancy rates from 13% to 7% by 2030, Nigeria committed to a dedicated adolescent health budget line at the Federal Ministry of Health. Malawi’s advocacy goals focus on boosting health financing, reducing teen childbearing, and ensuring 30% youth representation in decision-making bodies, and Zambia is prioritising financing, policy harmonisation, and governance reforms to secure meaningful adolescent engagement.

PMNCH readjusted their focus during the grant period from generating new commitments for women, children and adolescents, to advocating for action against existing commitments and only generating new commitments in gap areas such as adolescent health and wellbeing. These commitments are then followed up through PMNCH’s Collaborative Advocacy Action Plans. PMNCH has delivered 31 country-based advocacy and accountability initiatives and processes focused on accelerating the delivery of commitments using the Global Leaders Network, the Collaborative Advocacy Action Plans and 11 youth-led advocacy and accountability initiatives. PMNCH have consistently achieved agreed outcomes throughout the reporting period. The Global Leaders Network (GLN) and Collaborative Advocacy Action Plans (CAAPs), although in early stages, show potential. For example, the GLN secured additional commitments at high level forums such as UNGA and the World Health Assembly, as well as facilitating the alignment of key women’s, children’s and adolescent health priorities. The CAAPs have allowed government commitments to be mapped, often for the first time, and key gaps in implementation of these commitments to be identified. The Global Forum for Adolescents that was organised by PMNCH in 2023 achieved commitments for adolescent well-being from 18 Member States, 2 regional bodies (African Union and European Union), 13 philanthropic and other funding organisations, and 3 non-state actors. The virtual event brought together a global community of adolescents, advocates, and leaders and partners supported the campaign by hosting 125 national events in 48 countries. The Call to Action on COVID-19 campaign resulted in a total of US$ 32.1 billion committed for health and social services for women, children and adolescents) and the 1.8 Billion Young People for Change campaign resulted in policy and financing commitments of $1.83 billion having been made from 19 LMIC and 5 HIC.

Although PMNCH have overachieved on their logframe targets, the impact of their work on improving real world health outcomes has been harder to demonstrate. PMNCH, along with many other advocacy programmes, face challenges in objectively quantifying their unique contribution (e.g. some of the achievements may have happened anyway or because of other advocacy efforts). For PMNCH it has been particularly difficult to quantify since they previously focused on achieving new commitments and producing knowledge products with little or no measure of how the commitments were being implemented and whether the knowledge products were reaching intended audiences and achieving their advocacy goals. This concern has been raised in Annual Reviews and multiple recommendations were made to improve measurement and follow up on commitments made, the events held and the take up and use of knowledge products. Previous annual reviews have also raised questions about PMNCH’s strategic focus, and the balance of their effort across different initiatives. PMNCH are in the process of designing a monitoring, evaluation and learning framework for their new strategy, and shifting their focus onto measuring the impact of their advocacy rather than simply generating new knowledge products or commitments. However, their lack of ability to measure their impact has contributed to their raised risk rating and the difficulty in quantifying PMNCH’s contribution towards global outcomes.

An additional output was added during the grant period related to streamlining and improving the efficiency of PMNCH’s ways of working. PMNCH have recently had a change of leadership, with Rajat Khosla taking over as the new PMNCH executive director on 15 May 2024. This has led to an important inflection point: as he commissioned three externally led reviews on: (i) developing PMNCH's Strategic Priorities Framework 2026-30; (ii) conducting an external evaluation of PMNCH’s 2021-25 Strategy; and (iii) simplifying governance structures and processes at PMNCH. Independent consultants undertook this work from September to December 2024, reporting to the Board at its December 24 meeting. FCDO was on the steering committee for the governance review. The reviews exposed significant concerns relating to governance and effectiveness, and recommended key changes.

The changes that have been implemented so far consist of i) a new Board transitioning from 24 members in 2022 to 15 in 2025; (ii) a move from 10 to now six constituencies; (iii) one Standing Committee consisting of five members has been established replacing six committees and working groups and up to 50 task teams; and (iv) a membership review has been instigated. Since the changes made by the new executive director, significant progress has been made on efficiency. For example, PMNCH have moved from managing more than 200 meetings in 2022 to only four in 2025. In line with this streamlining, PMNCH have also reported improvements in financial efficiencies by achieving a 40% reduction in total Geneva-based salary costs and more than 60% in ongoing consultancy costs, as reported to its Standing Committee in May 2025. New leadership has also injected new energy, drive and purpose to the organisation.

Financial reporting since the independent reviews showed very large reductions in consultancy costs, travel and conveying budgets, service contract budgets, operational costs and grant budgets. The reviews were able to identify a significant amount of “non-essential” spend very quickly and make savings. Although PMNCH have taken positive steps to correct this, it raises questions over the value of previously distributed funds, and the lack of transparency to enable FCDO to identify inefficiencies of this sort. PMNCH’s financial reporting has not been clear, with several, varying, versions of budgets being sent which have made it difficult to ascertain the value for money that we have achieved, as well as clarity around the overall financial picture for PMNCH and how necessary further FCDO funds would be for their budget.

PMNCH find themselves now in a much more difficult context than when the programme began in 2022. Given the shifting geopolitical landscape and the need to respond to direct funding challenges for their organisation as a result of reduced ODA, it will be more important than ever for PMNCH to use their funds as efficiently as possible, to streamline the organisation, and to demonstrate their impact, as they intend to do until the new ED. There is a continued need to refine their theory of change for global advocacy on maternal, newborn and child health in light of wider reform of multilateral institutions and the wider global health architecture, the global rollback on SRHR, and a transition towards increasing domestic resource mobilisation and restoring government sovereignty. They will need to define and effectively communicate PMNCH’s strategic direction in light of this evolving context, and to identify its discreet value in relation to similar initiatives such as Every Women Every Newborn Everywhere (EWENE), Align MNH, FP2030 amongst others.

FCDO is also operating in a very different funding context, including the UK Government’s difficult decision to reduce the ODA budget to 0.3% of GNI. FCDO is working to prioritise our time and resources in order to deliver maximum value and impact. This includes considering the role of global advocacy and commitment making organisations as part of a whole ecosystem approach and consider it alongside organisations that seek to drive positive change at local level, or through networks and movements.

Major lessons learned, evidence generated and recommendations [1/2 page]
- Global Leaders Network (GLN)- Recently, PMNCH have made progress on increasing membership to the GLN to its current 10 Heads of State and the GLN has great potential to make positive changes globally. However, so far the GLN is yet to deliver any actual change. The purpose and plan for GLN activities should be organised well in advance to allow for maximum engagement and synergy with the CAAPs and other processes. If necessary, PMNCH should promote virtual GLN events or written articles that do not require in-person attendance. It is important not to lose the GLN momentum. Recommendation: PMNCH to seek other leaders from the Global South, but outside of Africa to join. GLN should consider how best to advocate for MNCH at regional level, as well as at the global, multilateral level.
- Collaborative Advocacy Action Plans (CAAPs)- PMNCH is coordinating in 10 Sub-Saharan countries’ plans on advocacy and accountability for delivering commitments made towards women’s, children’s and adolescents’ health and, if needed, identifying gaps and advocating for new commitments. PMNCH partners have fed back on how the CAAP is supporting country led efforts to improve health outcomes for women, children and adolescents. They praised the clear commitments and coordinated action, that the coalition is unlocking collective power and that they have built trust, strengthened ownership and embedded shared goals in national processes. Recommendation: PMNCH to ensure that sufficient funds are allocated to implement the CAAPs. PMNCH to extend the CAAPs into other Global South countries outside of Africa, and to increase opportunities for cross country/region collaboration to share best practices between CAAP countries.
- Global Forum for Adolescents (GFA)- One of PMNCH’s key achievements in this reporting period was the organisation of the Global Forum for Adolescents, in October 2023. The virtual event brought together a global community of adolescents, advocates, and leaders for two days of debate, dialogue, and action. Partners supported the campaign by hosting 125 national events in 48 countries. Commitments for adolescent well-being were mobilised from 18 Member States, 2 regional bodies (African Union and European Union), 13 philanthropic and other funding organisations, and 3 non-state actors. The CAAPs have been tracking and following up on these commitments.
- Collaboration- PMNCH aims to bring partners together to collaborate on knowledge products rooted in evidence and collaborate on events to avoid duplication of efforts. However, PMNCH have not always collaborated with external partners (e.g. the UK’s SRHR campaign in 2024) or optimised opportunities to avoid duplication. Improved alignment could have helped to build more coherent and coordinated action across partners. Independent reviews also revealed a somewhat bloated membership system, with varying levels of involvement. PMNCH are clarifying their membership requirements to ensure members can be more involved and access opportunities for collaboration. There remains potential overlap and duplication in the system with other advocacy organisations such as EWENE and Align MNH. Collectively, the international community need to work to map and align portfolios to better avoid duplication and identify gaps. Recommendation: membership is clarified to optimise the skills and expertise of existing members, and more opportunities are sought for cross constituency, and external collaboration.
- Reforms- PMNCH have made noteworthy progress in the last year towards making PMNCH a more streamlined organisation. The three independent reviews have led to positive changes in the governance structures and strategic priorities. PMNCH’s change in focus to following up existing commitments rather than obtaining new ones and reducing the number of knowledge products have been welcome changes. PMNCH have undergone governance reforms previously, only for the constituencies and Board to subsequently grow again. Recommendation: PMNCH maintain the current governance structure rather than allowing it to grow again and continues to adapt to evolving context.
- Measuring impact and accountability- This has been a key recommendation from the FCDO over the reporting period but had not been implemented until the final year. The importance of having a clear monitoring, evaluation and learning strategy has now been agreed and PMNCH has incorporated this into their 2026 to 2030 Strategy, with a new MEL framework underpinning its strategy and work planning processes. Recommendation: PMNCH should only deliver knowledge products, or commit to supporting and organising events, where there is significant value in doing so and where specific objectives can be measured through their input.
- Activity and financial reporting- Over the reporting period there has been difficulties in obtaining accurate activity and financial reporting from PMNCH, with some larger pieces of work not being properly reported to the FCDO at all. In the last year of the reporting period reports have mainly focused on reform progress on PMNCH ways of working, new strategy and governance, leading to issues with ascertaining an overall picture of what PMNCH is currently working on. The financial reports have lacked clarity, leading to issues with establishing PMNCH’s overall financial situation and requirement for additional funding. Recommendation: FCDO should challenge poor financial reporting in all programmes.

How this report was conducted [1 paragraph]
This report was developed through a consultative process drawing on inputs from PMNCH Secretariat and partners. It was peer reviewed internally in FCDO. Evidence sources included internal progress tracking data, regional and country-level commitment updates, partner feedback, and documentation from technical convenings and working groups held over the past four years. The process was informed by PMNCH’s monitoring framework and aligned with the Theory of Change, allowing for a structured analysis of progress, challenges, and emerging trends. It was also informed by an internal review of our global advocacy partnerships on sexual and reproductive health and rights, and against a new draft theory of change for our work on global advocacy.

Actions following approval of this report [1-2 paragraphs]
All payments have now been made to PMNCH, and there are no assets to return or dispose of. Whilst the programme is closing, FCDO will continue engage within PMNCH and remain coordinated with key SRHR and maternal and newborn health partners.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£6,000,000	£6,000,000
Timeframe	15/10/21- 31/08/25	15/10/21- 31/08/25
Outcomes	30 low- and middle-income countries make policy, financing and services commitments that promote equity and are aligned with PMNCH’s advocacy efforts to support MNCH, SRHR and Adolescents impact objectives.	Achieved. / PMNCH mobilised a cumulative total of 34 LMIC commitments: / • 15 LMIC and 5 HIC commitments (Country commitments) to PMNCH’s Call to Action on COVID-19. / • 19 LMIC and 5 HIC (Country commitments) associated with adolescents’ health and wellbeing.
	5 global political commitments on protecting and promoting MNCH, SRHR and Adolescents impact objectives, ensuring a focus on equity and aligned with PMNCH advocacy efforts (e.g. UN Resolutions, Declarations at high-level political forum)	Achieved / PMNCH secured 7 global and regional commitments prioritising women’s, children’s, adolescents’ health & well-being.

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]
Over the programme duration the logframe outcomes have been achieved (even slightly exceeded) within the timeframe and budget originally planned.
- PMNCH has potential to achieve significant value for money. As the world’s largest alliance for women’s, children’s and adolescent’s health with around 1500 partner organisations, PMNCH has the potential to play a key role to build effective coalitions and reduce duplication of efforts to achieve their objectives. PMNCH’s Global Leaders Network and Collaborative Advocacy Action Plans should work to achieve change from the grassroots up to world leaders. However, PMNCH have not yet been able to achieve the potential value for money for several reasons. Firstly, in the past their governance structures have been inefficient making it difficult for partners to engage effectively and to build useful coalitions across organisations. Secondly, the membership responsibilities to PMNCH have not been clear, leading to many of PMNCH’s members not being actively engaged. Lastly, the lack of an effective Monitoring, Evaluation and Learning strategy has led to efforts being directed into workstreams where it was difficult to gauge the impact. PMNCH have made substantial improvements in the last year which will improve the value for money that they are achieving. There has been a change of focus, reducing knowledge products, meetings and events, and instead focusing on the impact of each of these. This is already improving cost effectiveness. With this shift in focus, PMNCH will hopefully be able to realise its potential as a cost-effective organisation, able to utilise its large member base, to advocate through from grassroots level in the CAAPs up to the Global Leaders.
- PMNCH’s core role is to advance gender equity by advancing the rights and needs of women, children and adolescents. PMNCH does this by prioritising interventions that meet the needs of women and girls; reinforcing a focus on equity and recognising that women and girl’s health and wellbeing is directly affected by their economic, legal and cultural contexts. PMNCH also has a strong focus on disability inclusion. There have been some significant gains in this area. For example, PMNCH Governance Manual now includes the Diversity Equity and Inclusion policy (DEI), Code of Conduct and Value Charter. PMNCH has also worked with FCDO and disability focused development partners to explore how it can mainstream and advocate on the issues of inclusion and equal opportunities for all as part of its core work. However, there have also been concerns over this reporting period on a lack of interventions in humanitarian contexts. Because of this, PMNCH risk not addressing equity issues for some of the most marginalised women globally.

Significant changes and unexpected outcomes:
In January 2025, the Mexico City Policy was reinstated (as expected), resuming the previously expanded version of the policy that was adopted in the Trump administration’s first term. A freeze on foreign aid was first put in place, followed by the unexpected dismantling of USAID, which ended USAID-funded activities. Restricting funding to organisations that provide integrated healthcare undermines global health programmes and will exacerbate challenges in addressing maternal and newborn mortality, unintended pregnancies, and sexually transmitted infections, including HIV/AIDS. PMNCH partners work in a range of organisations, providing contraceptive provision, prenatal care and post- abortion care, as well as advocating for comprehensive sexual and reproductive health and rights. The reinstatement of the Mexico City Policy will have affected the funding and operation of many of PMNCH’s partner organisations. PMNCH are in the process of designing a partner survey to seek inputs on the effects of aid cuts and policy regression like Mexico City, DEI regulation and others on partner programmes. Although PMNCH was not directly funded by USAID, the overall cuts to the sector will likely have knock on impacts.

Summarise the programmes theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]
The intermediate outcomes have been exceeded (as shown in the table below). High-level outcomes will be achieved through a contribution from PMNCH, but there is a clear link between these and the intermediate outcomes.

Impact Indicator	Starting Target	Final Logframe Target	Final Result Achieved
1.1 # low- and middle-income / countries mobilised new / commitments for WCAH, / specifically in areas where gaps / are identified.	15	25	Exceeded: At the end of 2024, PMNCH has mobilised a cumulative total of 39 commitments, of which 35 are from LMICs.
1.2. # global and/or regional / bodies that make public / commitments prioritising / women’s, children’s, / Adolescents’ health & well-being	0	5	Exceeded: At the end of 2024, cumulative total to 6 commitments (e.g., WHA77, G7 SRHR and nutrition). Work continues with GLN and G20 to potentially secure more global / regional commitments during 2025.

The theory of change is outlined in PMNCH’s results framework (below) and is used by all donors as the basis for their interaction with PMNCH. The theory of change was updated in 2024 and is now more relevant given the changes to PMNCH since the independent reviews have been completed.

Overall relevance of the Theory of Change
Throughout the delivery of this Strategy, PMNCH continued to deliver according to the agreed Theory of Change, with inputs, outputs and short-term outcomes all leading to commitments (Intermediate Outcomes) by national governments as well as non-state actors – at national, regional and global level.
Adjustments that were made to the approach overall are reflective of the global health and ODA environment more broadly. The work of PMNCH moved from securing new commitments to setting in motion nationally owned and led processes to accelerate the implementation of those commitments, strengthened by engaging highest level political national leadership. This reflects the fact that it was unclear to donors whether commitments were implemented and the status of them, and so to what extent they have improved maternal, newborn and child health outcomes. To this end, PMNCH has taken a leading role in supporting Global South engagement and leadership in taking forward the implementation of those commitments, through CAAPs and GLN processes.
- Improving ways of working- PMNCH has delivered governance and ‘ways of working’ reforms, which have strengthened the work of the partnership and Secretariat, ensuring it is fit for purpose into its 2026 to 2030 strategy. Near the end of the grant period, the newly reformed PMNCH Board adopted PMNCH’s new 2026 to 2030 strategy, which builds on the work to date and reflects many of the lessons learned from this grant period.
- Adapting and aligning products and processes for and with specific audiences- Throughout the delivery of its 2021-2025 strategy, PMNCH has tailored its products and processes to specific audiences across all constituencies. For example, the 1.8 Young People for Change campaign had a sub-brand directed specifically at adolescents and youth. Specialised social media and messaging was also used for COP28 (climate activists) and for the IPU (parliamentarians), and messaging was adopted to either national stakeholders or national leaders. PMNCH has also played a role in supporting cross-constituency collaboration anchored in robust evidence, supportive partner engagement, and targeted campaigns. These knowledge resources ensure alignment on evidence-based priorities and support coordinated action for effective WCAH advocacy. Work is also currently underway to create a process to adapt the global briefs to country level, to better leverage on-the-ground resources, priorities and partner-coordination and collaboration. In addition to this, PMNCH has made strides towards increasing the alignment of actors across the continuum of women’s, children’s and adolescents’ health space. Over the last year or so in particular, PMNCH’s efforts have seen it pivot towards increasing its collaboration and providing the platform for alignment across organisations and initiatives, such as Every Woman Every Newborn Everywhere (EWENE), Child Survival Action, FP2030, GFF, and many others. Building on these lessons and approaches during the grant period, PMNCH is taking forward this alignment effort into its new strategy, where these issues and principles feature prominently.
- Monitoring, Evaluation and Learning Framework: Lessons shaping PMNCH’s new strategy- Underpinning all these processes has been a shift towards building PMNCH into a ‘Learning Organisation’, at all levels and in everything that it does. The recognition that this element of PMNCH’s institutional structure and work has to be strengthened has led to the development of a new Monitoring, Evaluation and Learning (MEL) Framework for the partnership’s 2026 to 2030 Strategy. The Learning aspect of the Framework underscores the forward-looking approach taken up by PMNCH in support of effective implementation – gearing up in 2025 and for full rollout in 2026. The Framework outlines PMNCH’s approach to tracking progress towards strategy implementation and learning to guide decision-making. It is flexible and adaptable to respond to new insights gained through implementation and remain relevant to evolving political, economic and environmental contexts and conflict-related shifts that influence the strategy’s execution.
## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title		1.Knowledge synthesis: Increased knowledge for advocacy by PMNCH members, as a result of exposure to and use of PMNCH knowledge products. Evidence products synthesised and/or developed to equip PMNCH members to advocate for commitment-generation and hold commitment makers accountable for implementation
Output Score		A+ (exceeded)
Impact weighting (%)		25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Number of PMNCH flagship knowledge products facilitated and developed: advocacy briefs, reports, speeches, multimedia assets e.g. videos. PMNCH facilitates partners from different constituencies to engage in the development of knowledge products, through reaching out to partners to invite them to participate, setting up and running product specific task teams / working groups, providing secretariat support (in terms of project management, drafting and reviewing of documents, meeting support), managing dissemination processes, etc.	Baseline for 2021: 38 (knowledge synthesis / briefs)		Cumulative: 198	Cumulative: More than 520
1.2 Number of page landings recorded for flagship knowledge products available on the PMNCH website, as a measure of usage	Baseline was introduced in 2023 with the update of the indicator to 250 average page view per product.		330 average page view per product	479 average page per view
1.3 Number of social media interactions on flagship knowledge products, e.g. Born too Soon report, as a measure of engagement. Interactions may be understood as re-posts, comments, sharing, reactions.	Baseline was introduced in 2023, 21,800 average reach per product, 1000 average interactions		26,400 average reach per product, 1400 average interactions	111,280 average reach (or impression if channel only allows for impressions), 1097 average Interactions (excluding organic interactions from new channels)
1.4 Number of community voices collected and presented in knowledge products for advocacy through PMNCH. These are life experiences of people in diverse settings, e.g. What Young People Want Initiative; Finding Hope Report	30,000		1 000 000 (cumulative)	More than 1.5 million achieved cumulatively

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
PMNCH used its knowledge synthesis function to drive more responsive and equity-enhancing WCAH policy, financing, and service delivery. This includes synthesising, translating, and contextualising evidence and knowledge tools to drive WCAH advocacy and accountability. This work is the basis for the other outputs, enabling partners to work together and advocate, based on strong evidence, towards new commitments as well as accelerated implementation of existing commitments. Work is presented below, grouped according to the three thematic areas:
- Maternal, newborn and child health (MNCH):
  - Evidence for the implementation of the WHA77 Resolution on MNCH. PMNCH has supported the synthesis and translation of important MNCH priorities and evidence-based solutions put forward in the WHA77 resolution. This included PMNCH-led convening to develop key WCAH asks to Member States for the negotiations around the Resolution and promoting strong adoption and implementation. PMNCH also led knowledge synthesis efforts in support of the MNCH Resolution including the Key WHA77 advocacy messages, and the Joint brief with ENAP-EPMM and CSA, outlining critical actions necessary to accelerate progress towards 2030.
  - MNCH financing: PMNCH has developed a series of advocacy briefs and commentaries highlighting the rippling effects that investing in WCAH has on communities and economies and providing recommendations to PMNCH constituencies on how to advocate for increased investments. PMNCH also developed a series of papers on climate and health financing. The papers focused on advancing intersectoral financing in order to align health and climate co-benefits. PMNCH then leveraged these findings for advocacy at COP29 to influence financing negotiations.
  - Born too Soon. The 2023 Born too Soon (BTS) report sought to elevate the voices of parents and caregivers and features a series of human stories to highlight real-life experiences with preterm birth. Its messaging and targets were aligned with the Every Woman, Every Newborn, Everywhere (EWENE) movement. Following this, PMNCH led ongoing development of a journal supplement in BMC Reproductive Health, entitled Born too Soon: progress, priorities and pivots for preterm birth, which includes 7 papers and 4 comments, published in June 2025. The BTS supplement was closely linked with the GLN political advocacy efforts.
  - WHO Campaign on MNH “Healthy Beginnings, Hopeful Futures”: PMNCH has supported the 2025 World Health Day campaign on maternal and newborn health with knowledge products focused on drivers of child mortality. These have included work with The Child Survival Action Initiative, as well as the Launch Event for the Born Too Soon Supplement.
  - Upholding MNCH in emergencies: PMNCH has developed the COVID-19 vaccine and pregnancy animated video. A total of over 115 million views have thus far been recorded on the entire video series. PMNCH also developed the Women and children first: Delivering solutions in conflict-affected settings
- Sexual and reproductive health and rights: PMNCH has produced an advocacy brief to support comprehensive sexual and reproductive health and rights in national universal health coverage plans. It also spearheaded reproductive health and rights-specific needs of young people through the Global Agenda for Action for Adolescents. Other recent examples include a comprehensive SRHR landscape analysis to inform and shape advocacy strategies for 2024 and beyond; developing key SRHR advocacy messages for UNGA79; developing a film presenting the progress, challenges and next steps on adolescents’ sexual and reproductive health and rights; the PMNCH Statement on Reinstating and Expanding the Global Gag Rule: A Threat to the Lives of Vulnerable Girls and Women; and the Lancet commentary: Age of distrust: impact of hegemonic policy decisions on sexual and reproductive health and rights co-authored by the leadership of PMNCH and WHO / HRP.
- Adolescent well-being: As part of its “1.8 Billion Young People for Change” campaign, PMNCH has been mobilising new commitments. PMNCH has led the development of an adolescent well-being investment case and, in partnership with WHO, has developed a set of indicators and a monitoring framework for measuring adolescent well-being. PMNCH promotes adolescent and youth engagement through leading the Global Consensus Statement on Meaningful Adolescent and Youth Engagement.
  - Call to Action. Prioritizing What Young People Want for a Sustainable Post-2030 Era, launched at the Youth Power Summit (YPS)
  - “What Young People Want” Chatbot to access real time presented in a searchable dashboard format. To date, more than 1.5 million young people have responded, enabling their voice to be heard and making this the largest-ever survey of young people in relation to health and well-being needs and aspirations. This work informed the 7-point global Agenda for Action for Adolescents and forms the basis of PMNCH’s AWB focus in 24-25.
  - The Economic Case for Investment in the Well-being of Adolescents in India, a tool for ensuring enhanced and sustained financing for adolescents, providing a framework for mapping out future actions and strategies.
  - Adolescent Health and Well-being Measurement Guidance, the Economic Case for Investment in the Well-being of Adolescents in Colombia and the Economic Case for Investment in the Well-being of Adolescents in South Africa (in progress) alongside messaging briefs, social media assets, infographics and talking points.
  - The Adolescent Well-being BMJ Collection with three more analysis articles and a three-part podcast series to further amplify the BMJ Collection.
  - The Adolescent Well-Being Investment Case, facilitated by PMNCH through Victoria University of Australia, was launched in May 2024 at the World Health Assembly.
Social media use: PMNCH state that social media use is integral to their advocacy efforts. The table below demonstrates the potential reach that PMNCH have previously had, as well as the decline in interactions over the past 18months. This decline is due to the peak in interactions achieved during the Global Forum for Adolescents and the return to usual levels.
Platform	Followers June 2025	Interactions as a measure of engagement Dec 2023	Interactions as a measure of engagement Dec 2024	Interactions as a measure of engagement June 2025
X (formerly Twitter)	32,500	56,586	17,118	7,547
Facebook	23.600	433,865 (Includes paid campaigns)	2,448	929
Instagram	3k	13,743	3,671	2,824
Linkedin	8,700	6,248	26,545	15,223
BlueSky	106	N/A
Youtube	2000	62,238	73,308	63,600 (Shorts views are counted differently from March 31, 2025)

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
In terms of core advocacy functions, PMNCH's knowledge synthesis products have been valuable and perceived by partners as robust and reliable sources to support evidence-based advocacy efforts, aiming at bridging critical gaps in women’s, children’s and adolescents’ health. PMNCH has demonstrated clear added value by positioning knowledge as the foundation for driving policy influence and constituency engagement.

A unique feature for PMNCH is their potential reach to bring partners together to collaborate on knowledge products rooted in evidence. Covering timely topics like sexual and reproductive health and rights in universal health coverage, climate change, and WCAH financing, these briefs ensure that advocacy is grounded in shared, evidence-informed priorities. This alignment has supported in building more coherent and coordinated action across partners.

PMNCH has also recognised that global evidence alone is insufficient. A major lesson has been the need to promote the uptake of context-sensitive knowledge, including local data, lived experiences, and implementation insights. The development of national investment cases on adolescent well-being reflects this localised approach, offering practical examples of what works and why. By embedding local realities into broader policy dialogue, PMNCH helps ensure that advocacy remains responsive to the needs of the most vulnerable populations. While PMNCH has made significant progress in this area, supporting the uptake of evidence for local decision-making remains a critical challenge that requires continued and intensified efforts.

Within the reporting period one of the main lessons that was discussed and implemented by PMNCH was to further streamline the knowledge products, reducing the number of products and instead focusing on their use and impact. In order to measure usage output indicators 1.2 and 1.3 were added to the logframe. Measuring impact has now been reflected in the workplan for 2025, but so far PMNCH has not been able to demonstrate the impact of their knowledge products or to gather data on how relevant they are and to make improvements to future products. In future, PMNCH could consider other ways to measure this impact, including through an outcome harvesting approach.

The importance of having a clear monitoring, evaluation and learning strategy was a long-standing FCDO recommendation and agreed upon during the grant. PMNCH has now incorporated this into their 2026 to 2030 Strategy, with a new MEL framework underpinning its new strategy and work planning processes.

Output Number and Title		2. Partner Engagement: Increased advocacy skills and networks among PMNCH members, as a result of exposure to and use of PMNCH’s member-engagement processes. Events, grants, products developed and implemented to support PMNCH members to advocate for commitment-generation and hold commitment makers accountable for implementation
Output Score		A+ (moderately exceeded)
Impact weighting (%)		25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1 Development of products by coordinating partners involved in the process of the Collaborative Advocacy Action Plans (CAAPS) per country: (For example, Commitments Scoping and Analysis, Country Advocacy Plan, etc.)	Baseline for 2022: / CAAP Concept Note Developed and Priority Countries selected		Commitment Scoping Analysis in 10 countries (cumulative) and CAAP Country Plan in 10 countries (cumulative)	Commitment Scoping Analysis in 10 countries (cumulative) and CAAP Country Plan in 10 countries (cumulative)
2.2 Engagement on the 10 Digital Advocacy Country Hubs, as measured through a set of engagement indicators, including: number of members, visits by members of at least one time, observing, following, endorsing/contributing, owning/leading. These will be collated together into an 'engagement score', demonstrating the percentage of members who moved from observers to followers.	Baseline for 2023: / 35% year on year increase in observers to followers		15% year on year increase in observers to followers	Membership on the Hubs has seen a 20% increase from July 2024 to July 2025.
2.3 Number of political advocacy interventions (through events, publications, correspondence) undertaken by Global Leaders Network (GLN) members. Correspondence refer to communication among peers in the GLN, i.e. bilateral communication to encourage action on WCAH, also from one GLN member to another Head of Government.	Baseline for 2021: / GLN Concept note finalised		15 (cumulative) political advocacy interventions undertaken	In excess of 40 interventions from GLN leaders and / or delegates.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
- CAAPs:
  - PMNCH is coordinating work in 10 Sub-Saharan countries on advocacy and accountability for delivering commitments made towards women’s, children’s and adolescents’ health and, if needed, identifying gaps and advocating for new commitments. The 10 countries are: Ethiopia, Kenya, Liberia, Malawi, Nigeria, Senegal, South Africa, Sierra Leone, Tanzania, and Zambia.
  - PMNCH has finalised the establishment or strengthening of, and institutional underpinning for, multi-stakeholder platforms (MSPs) across 10 CAAP countries. These platforms are linked to the government-led accountability processes, which provide an entry point for civil society and other partner voices to be considered as part of formal government processes. CAAPs are supported by each country-specific digital advocacy hub.
  - Strengthened focus within each of the CAAPs on safeguarding gains and accelerating progress on SRHR has resulted in all 10 CAAPs now having plans related to advocating for the implementation of commitments on SRHR.
  - PMNCH partners reflected on how the CAAP is supporting country led efforts to improve health outcomes for women, children and adolescents. Feedback praised the clear commitments and coordinated action, that the coalition is unlocking collective power and that the small steps have built trust, strengthened ownership and embedded shared goals in national processes.
  - As an example in Kenya, CAAP is helping formalise a multi-stakeholder advisory role within an MNCH bill.

Digital Advocacy Hubs: Membership on the Hubs has seen a 20% increase since July 2024. Ten country Hubs for CAAP countries have been activated, which are complete with a commitment and CAAP plan dashboard, resource library and events page. Membership on the Hubs enables global and national coalition strengthening, providing a platform to share best practices, resources, and opportunities.

Global Leaders Network:

  - The Global Leaders Network now has its own website, and comprises of 10 Heads of State: H.E. President Cyril Ramaphosa, President of South Africa, as Chair, with members including H.E. Prime Minister Mette Frederiksen of Denmark; H.E. Prime Minister Abiy Ahmed of Ethiopia; H.E. President William Samoei Ruto of Kenya; H.E. President Joseph Nyuma Boakai, Sr of Liberia; H.E. President Lazarus McCarthy Chakwera of Malawi, H.E. President Bola Ahmed Tinubu of Nigeria, H.E. President Bassirou Diomaye Faye of Senegal; H.E. President Julius Maada Wonie Bio of Sierra Leone; H.E. President Samia Suluhu Hassan of Tanzania, and H.E. President Bassirou Diomaye Faye of Senegal.
  - At UNGA79 President Cyril Ramaphosa of South Africa hosted and PMNCH organised the GLN event “Securing the health of every woman, child and adolescent: Political leadership to achieve the 2030 Sustainable Development Goals’’. The event saw the participation of four Heads of State and two Ministers, who delivered interventions on behalf of their Heads of State, and all three principals of UN Agencies with the presence of Dr Natalia Kanem, UNFPA, Catherine Russell, UNICEF and Dr Tedros, WHO. A total of 14 ministers were in attendance in the room as well as numerous dignitaries and participants across constituencies.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Partner engagement works best when it is integrated, coordinated and multifaceted. PMNCH have been able to demonstrate this at times over the reporting period, but have unfortunately not been able to consistently deliver on this throughout the reporting period. PMNCH have recently made progress integrating their advocacy goals at the grassroots level via the CAAPs with that at the national leadership level with the GLN.

The GLN was very slow to be established, with few leaders committing. However, this past year has seen the GLN membership increase from 4 to 10 heads of state and now work is progressing. The purpose and plan for GLN activities should be organised well in advance to allow for maximum engagement and synergy with the CAAPs and other processes. As outlined in the earlier recommendation, PMNCH should promote virtual GLN events or written articles that do not require in-person attendance to increase opportunities to engage whilst keeping costs down. With women’s health being so highly politicised, and with an intensification of efforts to rollback progress on SRHR – the GLN could be a key asset through which to encourage global leader to stand firm on the importance of comprehensive, universal SRHR and its critical role in ending preventable maternal and newborn deaths. However, as of yet, we have not seen much of this potential realised, particularly through bilateral engagements or at the regional level (for example, in support of the Maputo protocol).

With both the CAAPs and GLN, it would be good to see the momentum increasing to include countries outside of Africa. Currently membership is solely from African countries, except for Denmark. It would be beneficial to see similar structures develop in South America and South Asia, keeping the onus on global south partnerships.

Another recommendation for future programming would be to see more cross-country collaboration between regional groups to share best practices.

A significant amount of money was invested in establishing the Digital Advocacy Hubs, and so far, there has been limited usage. PMNCH made the decision in 2024 to not put any further funding into the Digital Advocacy Hubs. A recommendation is to evaluate how useful the Hub is, despite the increase in membership, before any decision is made on additional funding in the future.

Output Number and Title		Output 3: Campaigns & Outreach: Increased advocacy campaigns participation by PMNCH members, as a result of exposure to PMNCH products, events and/or processes. Advocacy campaigns organised and delivered enable Members to advocate for commitment-generation and hold commitment makers accountable for implementation"
Output Score		A+ (moderately exceeded)
Impact weighting (%)		25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1 Number of Tier 1 and Tier 2 advocacy events that PMNCH is leading and co-organising. / Tier 1: PMNCH organised / flagship event / Tier 2: PMNCH supported event (support with concept note and/or support provided for the participation of speakers and/ or attendees)	Baseline for 2021: 7		65 (cumulative)	Approximately 60 to 70 events (Tier 1 and Tier 2) / Around 500 PMNCH events supported through dissemination of information
3.2 Number of media hits on products, i.e. earned media products, e.g. op-eds, press releases, media interviews, as measured through potential cumulative media reach (as the industry standard measure)	Baseline for 2021: 450,000,000		500,000,000	19,407m* / Please note that this is not separate individuals, but an industry accepted metric, which will duplicate audience figures, as individuals may encounter PMNCH content across multiple media outlets and social platforms. Currently, there is no universally applied method for de-duplicating audiences to ensure only unique individuals are counted. Thus, the metric reflects the potential exposure rather than a unique audience count.
3.3 Global Forum for Adolescents (GFA) conceptualised and implemented, with a focus on number of registrants / number of national events / development of the investment case / Agenda for Action, together with other follow up post-Forum (e.g., mobilising champions, training resources, etc.)	Baseline for 2021: Concept note finalised		Several targets, changing over time, related to initially the event itself and then follow up work. / Development and implementation of the action plan to take forward the Agenda for Action for Adolescents in countries / Finalisation of the Investment Case and AWB indicators and measurement approaches	125 national events, with nearly 8,000 participants / Range of knowledge products supported the work, including the investment case(s). / Agenda for Action for Adolescents / Investment cases developed and published / Guidance for countries to assess adolescent health and well-being.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

The Call to Action on COVID-19 campaign (resulting in 21 commitments from governments and foundations amounting to a total of US$ 32.1 billion for health and social services for women, children and adolescents) and 1.8 Billion Young People for Change campaign (world’s largest online gathering for adolescent well-being which brought together some 10,000 individuals) were some of PMNCH’s major achievements. To date, policy and financing commitments of $1.83 billion have been made from 19 LMIC and 5 HIC associated with adolescents’ health and wellbeing, two regional bodies, as well as numerous nongovernmental stakeholders, to support adolescents’ well-being. Work in this area focused on supporting the development and implementation of campaigns and coordinating partner participation in order to align and amplify key advocacy and accountability messages. As part of its workplans, PMNCH organised more than 15 flagship events and actively supported some 45 to 55 partner events. In addition, information on around 500 partner events was disseminated through the Partnership online Events Hub during the period. PMNCH’s flagship campaigns have included:

In addition, PMNCH has also supported partners through a number of other organised campaigns throughout the grant period, such as: 38th Assembly of the African Union Heads of State and Government; Catalytic public-private-philanthropic partnership (PPPP) models; Accelerating the implementation of the WHA77 MNCH Resolution.
In the final phases of this grant, PMNCH is taking forward three regional workstreams to bring partners together in coalition building efforts. At present three regional efforts have commenced: Strengthening Southern African Leadership and Global Health Diplomacy in Multilateral Decision-Making Spaces; Creating dialogue spaces in Asia Pacific on women’s, children’s and adolescents’ health and wellbeing; and Opportunities for dialogue in the Latin American and the Caribbean region.
The score has been marked as moderately exceeding due to the lack of follow up on the impact of these campaigns. For example, in output 3.1 for the 500 events that PMNCH has supported, there is no measure for the impact of these events and as such, no learning can be derived from them. Again, for output 3.2, the media hits, as noted, is a potential exposure, but there has been no monitoring and evaluation of the impact of this. Again, in output 3.3, although a significant number of commitments were generated at the Global Forum for Adolescents there is no data on follow up from the event on implementation.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
PMNCH have capitalised on opportunities that have arisen from the broader global health community, leveraging the movements in a way that accentuated their impact whilst reducing the resource requirements. PMNCH have also been influenced by varying agendas and earmarked funding from partners and as such have not always been able to balance their work equally across the three thematic areas. The Global Forum for Adolescents took a significant amount of capacity to organise. However, the other two workstreams were not prioritised as much during this time (although some elements were integrated). It is recommended that PMNCH continue to attempt to secure mostly core funding, allowing them the autonomy to balance their workstreams equally and keep all PMNCH members engaged in their work.

Work has also shifted to a greater emphasis on accountability for the work and processes delivered, to ensure that they are embedded in follow on efforts by partners. The importance of having a strong MEL framework in place was recognised by all involved and this lesson has been taken forward so that a MEL framework is now an important aspect of PMNCH’s 2026 to 2030 Strategy. It is recommended that PMNCH only commit to supporting and organising events where there is significant value in doing so and where specific objectives can be measured through their input.

Output Number and Title		Output 4: Ways of working: increased streamlining of systems and governance, including more responsibility and accountability to constituencies. Developing a monitoring, evaluation and learning (MEL) strategy, including reporting on existing measurement indicators. Establishment of the Country Advocacy and Action Planning (CAAP) process. Clearer articulation and evidence of strategic prioritisation of issues under the 3 main workstreams of SRHR, MNCH and AWB.
Output Score		A (met expectation)
Impact weighting (%)		25%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
4.1 Streamlining of PMNCH governance, through implementation of the recommendations provided in 2023 light-touch governance assessment and Good Governance & Good Management. This also includes clarifying the functions of constituencies and their leadership in the short term, and re-evaluate the constituency structure and engagement into the Strategy period evaluation process.	Baseline for 2022: / i. 240 annual meetings led by the secretariat (including EC, Board, Standing Committee, working groups, constituency and task team meeting) / ii. 6 committees/working groups / iii. 50 task teams / iv. Partners rely heavily on secretariat for facilitation, e.g. developing talking points, NFRs and presentations / v. Roll out of Digital Advocacy Hubs (11 Hubs launched)		i. 100 annual meetings for secretariat / ii. 4 committees / working groups / iii. 20 task teams / iv. Partners continue to take on more tasks e.g. developing/reviewing presentations, agendas, drafting summary notes / v. Roll out of Digital Advocacy Hubs (5-6 additional Hubs launched)"	i. 4 meetings a year / ii. One committee / iii. No Task Teams / iv. Partners have been taking on more tasks / v. Ceased to additionally invest in digital hubs but used the hubs for CAAPs
4.2 Setting up “developmental evaluation” as means to do effective measurement, evaluation and learning of PMNCH to it's 21-25 evaluation. This evaluates how programs, organisational structures or change management initiatives have contributed to strategic policy goals in a complex (where outcomes are influenced by multiple factors) and fluid (where a program needs to be adaptive to changing situations to achieve its goals) environment.	Baseline for 2023: / Plans have been put in place and consultations undertaken with experts		Product 1: Evaluability Assessment. The findings from the Evaluability Assessment will lead us to a more detailed development evaluation plan to move towards the next set of products in this process. / Product 2: Development of MEL Strategy and Action Plan. The MEL Strategy and Action Plan will see the implementation of our monitoring framework move forward. / Product 3: Independent evaluators reports. / Product 4: Outline and key elements of the PMNCH 2026-30 Strategy.	Evaluation undertaken and delivered and available on PMNCH’s website. / MEL framework developed as part of the new 2026 to 2030 Strategy, as available on PMNCH’s website / PMNCH 2026 to 2030 Strategy developed and published, as available on PMNCH’s website
4.3 Development of a Disability Inclusion workplan and mainstreaming advocacy workplan, subject to ongoing discussions with FCDO and related governance structures (Subject to ongoing discussions with FCDO and related governance)	Baseline in 2023: / PMNCH makes strides to mainstream disability inclusion internally and in advocacy		FCDO and PMNCH agree and start implementing how PMNCH will mainstream disability in their advocacy work and internally	PMNCH Justice, Equality, and Inclusion Policy developed and presented to the PMNCH all member Townhall in April 2025, as part of a partner consultation on this subject.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
PMNCH Secretariat and its Board focused significant attention on improving the ways of working for the Partnership. This has included the following workstreams:
- Independent reviews and priorities framework. Three externally led workstreams/ reviews were procured, managed and delivered, including: (i) developing PMNCH's Strategic Priorities Framework 2026-30; (ii) conducting an external evaluation of PMNCH’s 2021-25 Strategy; and (iii) simplifying governance structures and processes at PMNCH. Independent consultants undertook this work from September to December 2024, reporting to the Board at its December 2024 meeting. The documents and related discussions at the PMNCH Dec 2024 Board meeting are available on PMNCH’s website.
- Governance reforms. PMNCH has been working on delivering the governance reforms that were discussed and agreed at the closed Board session in December 2024 and based on the external review. In summary: (i) a new, smaller and more focused, Board has been constituted; (ii) rapid constituency reform has seen PMNCH move from 10 to now six constituencies; (iv) moving ahead with the establishment of the Board’s Standing Committee; and (v) started a membership review and reengagement process, guided by the Board’s discussions on this issue and much constructive feedback received to date.
- Strategy development and consultations. PMNCH has delivered the strategy development related agreements reached at the Board meeting in December 2024. Progress has been noted in the following areas: (i) Strategy Development Working Group (SDWG) met in February 2025 to review initial work by the Secretariat; (ii) Draft Strategy Paper; and (iii) external consultants, Spark Street Advisors, as led by Nina Schwalbe, were commissioned to develop a Theory of Action to underpin the Strategy, as well as Monitoring, Reporting, Evaluation, and Learning Framework to support the delivery of our strategy. The Strategy and the MEL have now been adopted by the Board and are available on PMNCH’s website.
- PMNCH Justice, Equality, and Inclusion Policy developed and presented to the PMNCH all member Townhall in April 2025, as part of a partner consultation on this subject.
Work and partner consultations are currently under way to develop PMNCH’s 2026 and 2027 workplan and budget.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
PMNCH implemented a governance review and reform process in consultation with Board members. The Board voted to not introduce the most radical option that was presented from the independent review, but PMNCH have still made good progress towards cutting down their governance structures. The changes have included streamlining significantly the governance structures, reducing numbers of meetings, consolidating its constituency structure and undertaking a membership review process. PMNCH enters its next strategic period 2026 to 2030 as a much leaner and more streamlined organisation, focused on the value it is able to deliver for women, children and adolescents.

It is a concern that PMNCH’s governance structures had become so unwieldy in the period of the grant, despite having undertaken governance streamlining previously under pressure from FCDO. It is recommended that the current structures are not increased again, so that this is process does not have to be repeated. It is also concerning that PMNCH can cut the annual meetings the Secretariat were hosting from 240 to 4 over a 3-year period, whilst seemingly still delivering on their objectives. This demonstrates a potential waste of resources that was occurring in 2022, although it is too early to see if there is any impact on the partnership aspects of PMNCH.

Developing an evaluation framework has been a recommendation to PMNCH throughout the grant period on each of the annual reviews. It is positive that PMNCH have now initiated this, but it is a concern that this took such a long time to do and has contributed to the lack of evidence of PMNCH’s overall impact.

D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case
- Economy: PMNCH set their essential budget at $10m per year within the reporting period and this had stayed the same for recent years. Staff and consultancy costs were forecast to be approximately $6m per year. Previously (at business case) staff and consultancy costs were 90% of the budget, so PMNCH have demonstrated a significant reduction in staffing and consultancy costs over the reporting period. Many of the remaining staff are on temporary contracts thus giving the Secretariat the flexibility that it needs in order to meet the requirements of its workplan, enabling it to employ professionals with the right skills set and to scale up or down its size relatively quickly. However, PMNCH have faced challenges with financial reporting through the reporting period, with, at one time, many varying versions of budgets having been received and a reluctance to share the overall financial picture for PMNCH, rather than solely a report on how FCDO funds have been used. This has made it difficult to assess how effectively PMNCH used its budget.
- Efficiency- PMNCH has potential to be highly efficient, a world leading convening power amongst political leaders with huge potential for impact, streamlining efforts between organisations, capitalising on opportunities for collaboration and reducing duplication of efforts. However, the previous governance structures and constituencies had become unwieldy, restricting this potential. Within this reporting period PMNCH have made good progress on making their governance structures more streamlined. Due to this being a recent change, it is not possible to evidence the benefits of this yet.
- Effectiveness- By strengthening partnerships PMNCH works as a global public good achieving large scale, cross-national impacts and reducing multiple (and therefore inefficient) efforts. The appraisal of options in the business case demonstrated that there were no other organisations that operate on this scale. Establishing an entity to do so would entail a major cost and takes years to parallel PMNCH’s impact. Some examples of PMNCH’s effectiveness include the 1.8 Billion Young People for Change campaign, establishing the Global Leaders Network and the Collaborative Advocacy Action Plans. The FCDO’s engagement provides the UK with a platform to engage strategically with political leaders on the shared agenda. However, the lack of a functional Monitoring, Evaluation and Learning strategy has hindered PMNCH’s ability to demonstrate its value. In the current context with a significant reduction in donor funding for aid, the global health architecture is entering into a period of likely reform. As part of this, PMNCH needs to understand and articulate its unique value in relation to other initiatives such as EWENE and Align MNH and align efforts to identify gaps and realise any further efficiencies. It is hoped that in future PMNCH will be better able to demonstrate its effectiveness and efficiency given the recent addition of the MEL strategy.
- Equity- PMNCH’s core role is to advance gender equity by advancing the rights and needs of women. And therein to address the needs of the poorest women, children and adolescents. PMNCH does this by prioritising interventions that meet the needs of women and girls; reinforcing a focus on equity and through recognising that women and girl’s health and wellbeing is directly affected by their economic, legal and cultural contexts. PMNCH has also maintained a strong focus on disability inclusion. This has been done by empowering and capacity building some of the constituencies which in turn will enable country members to advocate for disability inclusion within national women, child and adolescent health engagement.
- Cost effectiveness- Over this reporting period the FCDO has provided £6m and PMNCH has had potential to deliver significant objectives with this money. Unfortunately, the previous governance structures and focus on developing lots of knowledge products/new commitments without capturing their impact has affected PMNCH’s cost effectiveness. With the shift in focus on measuring impact, streamlining knowledge products, following up on implementation of commitments, PMNCH will hopefully be able to show itself to be a cost-effective organisation, able to utilise its large member base to advocate through from country level in the CAAPs up to the Global Leaders.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]
The overall risk rating for this programme has increased from minor on the business case and moderate at implementation to the current rating of major at the last annual review in June 2024. The main drivers of this increase in overall risk were:
1. Contextual risks around a global weakening in commitment and reduction in funding for MNCH and SRHR rollback
2. Reduction in PMNCH’s focus on MNCH in humanitarian contexts
3. Lack of MEL framework preventing PMNCH from accurately measuring and demonstrating the impact of their interventions.
4. Risk that funds have not always achieved value for money

Risk has been managed throughout the programme via regular meetings with the PMNCH team. Emerging/ increasing risks have been discussed with mitigation strategies being implemented.

The risk of funds not achieving value for money is the only risk that is outside of the risk appetite. This risk is currently scored at major, due to inefficiencies in PMNCH’s operations as exposed by the independent reviews commissioned by the partnership’s new leader. New leadership at PMNCH have driven significant improvements in this risk since the independent reviews were conducted, and the reforms have now begun to be implemented. Financial reporting since the independent reviews showed very large reductions in consultancy costs, travel and conveying budgets, service contract budgets, operational costs and grant budgets. The reviews were able to identify a significant amount of “non-essential” spend very quickly and make savings. Although PMNCH have taken positive steps to correct this, there is a question over why these savings could not have been made earlier. PMNCH’s financial reporting has made it difficult to ascertain the value for money that we have achieved, as well as clarity around the overall financial picture for PMNCH and how necessary further FCDO funds would be for their budget.

The lack of a MEL framework is also in the process of being rectified, however it is too soon to see evidence of how PMNCH use feedback to improve the impact of their activities. In both the 2022 and 2023 Annual Reviews, the FCDO recommended PMNCH develop a measurement, evaluation and learning strategy to assess the impact of their advocacy and learn and adapt to what is the most effective approach. The previous focus had been on achieving new commitments and producing knowledge products with little or no measure of how the commitments were being implemented and whether the knowledge products were reaching intended audiences and achieving their advocacy goals. This year has seen an improvement in this, with more of a focus on following up previously made commitments, rather than generating new ones. This has been reflected in the workplan for 2025, but so far PMNCH has not been able to demonstrate the impact of their knowledge products to gather data on how useful they are and to make improvements to future products.
	Description	Risk	Mitigation Strategy	Likelihood	Impact	Residual Risk
C0	Various factors impacting commitment and focus on WCAH: weakened political commitment in national and global priorities and rollback; pressures on the global economy and wider aid sector as a result of aid cuts and rollback lead to insufficient financial resources allocated to achieving SDGs 3 and 5.	Strategy & Context	In delivering its Strategy, PMNCH, FCDO and others will: advocate nationally and globally to ensure commitments to WCA are made and delivered; co-produce the evidence base and advocate on it to support sufficient funding / investments for SDGs 3 and 5; argue the case for political commitment to WCAH in the context of Climate Change, Conflicts and aid cuts. It is not clear if PMNCH’s strategies are effective. This has been increased to Major.	Likely	Major	Major
C2	Increase in political fragility and incidence of conflict in countries with high WCA burden.	Strategy & Context	PMNCH’s previous strong work on humanitarian contexts does not seem to have continued. PMNCH have now identified the countries of which they will focus on the implementation of existing commitments. These do not include FCAS at present.	Likely	Major	Major
D19	PMNCH does not measure the impact of their advocacy and therefore cannot assess and learn from what actions are the most impactful.	Policy & Programme Delivery	This has been a major issue with the programme. In the 2022 and 2023 annual review, the FCDO recommended PMNCH develop a measurement, evaluation and learning strategy so that they are able to assess the impact of their advocacy and learn and adapt to what is the most effective approach. This was a little delayed in 2023 due to the change in PMNCH’s leadership, but work has started at the end of 2023 and into 2024 that the new Executive Director can lead. The process will be overseen by the Governance and Ethics Committee and build on advice and discussions with WHO and other partners. A MEL strategy has now been designed to be implemented in the 2026-2030 period. This risk will be monitored closely and has been increased to Major.	Likely	Major	Major
F14	Funds are not used for the intended purposes; do not achieve value for money; and/or are not properly accounted for. The realisation of fiduciary risk can be due to a variety of factors, including lack of capacity, competency or knowledge; bureaucratic inefficiency; and/or active aid diversion.	Financial & Fiduciary	PMNCH fully follows WHO’s financial rules and regulations processes, subject to both internal WHO and external audits, and integrated within WHO’s financial and fiduciary monitoring systems. PMNCH also adheres to all relevant WHO’s policies and procedures and has processes in place to manage all procurement processes to secure best value for money, ensure transparency, and fairness. Results and outcomes of any audits and reviews are made available to the PMNCH governing bodies. WHO representatives sit on all PMNCH governance bodies (including the board on which the UK also sits), and they would raise issues if they saw any emerging. PMNCH have taken strides to streamline their ways of working (outlined in output 4) in order to ensure better value for money but the outcome of much of the social media and event related work is not clear. It feels that PMNCH’s function is following its form instead of the other way round. This has been increased to Major. PMNCH is also fully integrated into and follows the best practice global public procurement rules and regulations of WHO.	Possible	Major	Major
C3	Increased fragmentation of focus and delivery modalities amongst leading global health actors. Reducing this fragmentation should be a key role for PMNCH.	Strategy & Context	To mitigate this, PMNCH’s Board comprises of leads from all relevant global health actors in the WCA space, and therefore provides a space to raise awareness and promote dialogue on aligning financing, policies and service approaches. PMNCH could further strengthen this and utilise other opportunities. Since 2023, PMNCH have established lead partners in country who are engaging CSOs and other stakeholders at a national level through the CAAPs process to better work together. PMNCH are undergoing a strategy and governance reform and working to improve strategic coherence and sharpen focus amongst global health actors. Current funding gaps in the broader system provide opportunities to readdress fragmentation.	Possible	Moderate	Moderate
D4	Opportunities missed to capitalise on impact through joint working with other initiatives (FP2030 and UHC2030).	Policy & Programme Delivery	One of PMNCH’s priorities is to work closely with complementary initiatives to maximise its impact. Despite its large constituency membership and sitting on boards for some key mechanisms such as the GFF, it is not clear that PMNCH is maximising its partnerships to achieve outcomes. This has been increased to Moderate.	Possible	Moderate	Moderate
C1	Climate change and environmental degradation impacts on the health and wellbeing of WCA	Strategy & Context	PMNCH and its partners will use their convening power to advocate for awareness and action on mitigating measures. PMNCH has recognised this link and is advocating for a focus on WCAH in the context of climate change. In 2023, the UK supported the development of PMNCH’s advocacy brief on ‘prioritising women’s, children’s and adolescents health in the climate crisis’.	Possible	Moderate	Moderate
D9	The focus on three outcomes of PMNCH could be not each be given balanced attention-namely SRHR, MNCH and adolescent health and well-being.	Policy & Programme Delivery	In previous years, more budget was allocated to the AHWB outcomes due to the 2023 Global Forum for Adolescents, and less resource and attention was concentrated on the other two outcomes. PMNCH’s budget in 2024 and into 2025 has now balanced the investments equally in all three areas. PMNCH supports the work of three thematic workstreams, one for each of the three thematic / priority areas, who in theory advise on what PMNCH should focus on for each thematic area. However in practice, the AHWB Workstream has been more active than the others. FCDO has concerns that there is not a clear process for deciding which areas to focus on within each theme by these thematic workstreams, and PMNCH’s focus is not data driven without a clear process for prioritisation. The FCDO has recommended PMNCH to address transparency of prioritisation.	Possible	Moderate	Moderate
D18	Secretariat staff, governance and constituencies are not appropriately organised, or funded, to effectively manage the focus on PMNCH's mandate.	Policy & Programme Delivery	Two independent reviews have been conducted and the recommendations for streamlining are being implemented. The Board will be reduced to 13 members and the constituencies are being reorganised. The UK will be coming off the Board.	Possible	Moderate	Moderate
D12	PMNCH essential budget for 24-25 and 25-26 workplan is not fully funded	Policy & Programme Delivery	For the final two years of its strategy period (2024-25), PMNCH has secured approximately US$ 12 million, which is 60% of the US$ 20 million that is usually budgeted for a two-year period. On this basis, PMNCH has developed its workplan for this period and has had it approved by the Executive Committee in March 2024. One of the primary tasks for the new Executive Director will be to work on securing new resources for the work of PMNCH. PMNCH’s financial situation will be regularly reported on to the governance structures. Current UK funding ends in 2025. We have assessed PMNCH's budgets to ensure there are no gaps in essential budget	Possible	Moderate	Moderate
R21	FCDO will not be providing further funding to PMNCH and there is a risk of reputational damage for the UK.	Reputational	Submission has been approved for a decision not to renew funding, including assurance that FCDO exit will not be irresponsible or unduly threaten sustainability of the organisation. Director has been consulted and ministers will be updated, and provided with lines to take. Deputy Director and Director will meet with PMNCH leadership to explain UK rationale. Deputy Director has agreed to remain involved with the constituency group at PMNCH's request and to support sustainable exit/ mitigate reputational risk of UK exit.	Unlikely	Minor	Minor
S7	Intervention results in harm to people or the environment.	Safeguarding	PMNCH adheres to all of WHO’s ethic policies. In addition, staff undergo all WHO scheduled mandatory training on sexual exploitation and discrimination. In addition, all organisations applying to become PMNCH members have to complete the relevant application form (Becoming a partner (who.int)), including signing a mandatory disclaimer as set out on the webpages. They also go through a due diligence process, which involves both the Secretariat and relevant WHO internal departments. As the nature of PMNCH’s work is through global advocacy rather than through program work at country level, the safeguarding risks decrease as it doesn’t include much country level engagement and implementation, but rather works more at the high-level government policy degree. The term "safeguarding" encompasses a broad range of practices. Regarding risk management and security, most of PMNCH’s events are held in Geneva, where security is provided by the diplomatic police force. This area is under 24/7 surveillance by this force. PMNCH always require registration prior to the event, and there is always a check-in counter. In terms of accessibility, PMNCH ensure that their venues are accessible to people with reduced mobility, and sign language interpretation is provided for all PMNCH events. In terms of national events, as were held in relation to the Global Forum for Adolescents, these were partner-led. Nevertheless, PMNCH did provide a checklist to the organisers and instructions on how to report back from these events. PMNCH also include language in the guidance for these events that encourage inclusion.	Possible	Minor	Minor

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

- PMNCH have delivered well against the programme results framework and complied with all FCDO requirements.
- PMNCH have been approachable and supportive across the programme lifespan – FCDO and PMNCH met on a regular basis to discuss programme delivery, although in the final year of the grant PMNCH have been less receptive to meeting regularly.
- FCDO and PMNCH worked each year to update the results framework for the programme, to ensure it captured PMNCH’s contribution to the sector and ensure the right level of ambition.
- There have been some challenges around financial reporting. This has in part been due to differences in the financial reporting requirements between PMNCH and FCDO, however, it has been challenging to ascertain PMNCH’s overall financial situation.
- PMNCH has faced wider financial challenges with reductions in available funding from a range of donors. PMNCH have adjusted their operational structures and workplans to adjust to lower budgets.

Programme-level approach to monitoring and evaluation [1/2 page]
This programme has been monitored through regular (quarterly) meetings between FCDO and PMNCH. In the final year of the programme PMNCH have been less able to meet and prefer to send written updates. This in part has been due to changes in staffing within the secretariat. PMNCH have remained approachable to answer any questions.

In June 2024 PMNCH visited the FCDO to introduce their Executive Director, Rajat Khosla, to the programme team. Since this time PMNCH and FCDO have met in person a number of times at other events.

FCDO have been active on the PMNCH Board for the duration of this programme and have engaged via the Governments and Intergovernmental Organisations Constituency (previously Donors and Foundations constituency). FCDO also engaged with the independent consultants who completed the three reviews on (i) developing PMNCH's Strategic Priorities Framework 2026-30; (ii) conducting an external evaluation of PMNCH’s 2021-25 Strategy; and (iii) simplifying governance structures and processes at PMNCH. FCDO played a leading role in the steering committee of the governance review.

For the entire duration of the programme FCDO have recommended that PMNCH initiate a more effective Monitoring, Evaluation and Learning framework. Lacking this data has led to difficulties in assessing PMNCH’s value add and in ascertaining risk levels. The recognition that this element of PMNCH’s institutional structure and work has to be strengthened has led to the development of a new Monitoring, Evaluation and Learning (MEL) Framework for the partnership’s 2026 to 2030 Strategy. By 2026 PMNCH is aiming to manage its learning processes through information, deliberation, and action, applying the learning at all levels – the Board, Secretariat, partners, country stakeholders, and adolescents and grassroots movements.

Date of last narrative financial report	25/03/2025	Date of last audited annual statement	18/9/25