## Annual Review

Title: Lebanon Humanitarian Programme (LHP)
Programme Value £ (full life): 18,700,000 GBP as of 31 March 2024		Review date: 30/06/2024
Programme Code : [AMP ID#] 301315	AMP start date: 09/10/2023	AMP end date: 31/03/2025

Summary of Programme Performance
Year	2024
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	D0005375.odt (live.com)
DevTracker Link to Results Framework:	D0005376.xlsx (live.com)

## A. SUMMARY AND OVERVIEW

Context

As indicated in the Business Case for the Lebanon Humanitarian Programme (LHP), since 2019, Lebanon has been experiencing severe and protracted political and economic crises. This threatens the stability of Lebanon and, with it, UK interests. The collapse of the economy has led to a significant increase in poverty. Humanitarian need, once largely limited to the c.1.5 million Syrian refugees and 250,000 Palestine refugees in Lebanon, is now experienced by all population groups with growing poverty pockets among the Lebanese and poverty rates tripling over the past decade. Refugees remain particularly reliant on humanitarian assistance and are likely to continue so for the foreseeable future, despite growing hostility towards the Syrian population. Gender-Based Violence (GBV) has been on a steady increase with the compounded crises disproportionately affecting women and girls and other marginalised populations like migrant domestic workers and the LGBT+ community. During the period covered by this first Annual Review, the situation was further compounded by the escalation in the south of Lebanon linked to the outbreak of the Israel-Hamas war in Gaza in October 2023, causing internal displacement and an increase in humanitarian needs.

The programme context has remained challenging. Lebanon’s political and economic crises have continued, and the humanitarian situation has become more precarious with the outbreak of the Gaza crisis. In Lebanon this had seen, as of 28 May 2024: 375 people killed, 1,159 injured, and 94,126 internally displaced; loss of education and livelihoods; and extensive damage and destruction of civilian infrastructure and agricultural assets, including contamination of crop land.

There are challenges in ensuring humanitarian assistance across Lebanon, including the south, is gender-sensitive and disability inclusive with the GBV and protection sectors facing major funding gaps. International resources for assistance and protection remain limited, including reductions in UK funding since FY 21/22 following the shift to a 0.5% of GNI Official Development Assistance (ODA) target. The need to continually focus resources on emergency response has meant that specific activities related to longer-term systems building and social policy reform needed for resilience building, have been deprioritised or postponed. However, the prioritisation of digital cash for emergency food assistance, given the potential for multiplier effects on local economies and other developmental impacts, plus the emphasis on education, localisation, and social protection system strengthening, will continue to help build sustainability and resilience and ensure a more inclusive socio-economic recovery.

Description of programme

The 18-month LHP was approved in October 2023 with three main objectives: i) address growing humanitarian needs across the country; ii) improve educational outcomes for the most vulnerable and marginalised out of school children; and iii) support more inclusive, sustainable, and accountable national support systems for all vulnerable population groups focussing on social protection and other social sectors.

The LHP addresses the humanitarian crises, supports national systems, and has in-built flexibility to prepare for and respond to emergencies through an Internal Risk Facility allowing funding of up to £1.7m to be added to the original allocation of £17m. The period covered by this first Annual Review (October 2023 – March 2024) included launching of the programme and mobilising partnerships in the context of the outbreak of the Israel-Hamas war. The resulting escalation in the south of Lebanon and continued cross-boundary hostilities continue to have a profound impact on the country.

This first Annual Review of the LHP has been brought forward from the one-year mark of October 2024 to allow the LHP team within the British Embassy Beirut (BEB) to measure progress and build on lessons earlier in the programme lifecycle; to adapt the response to emerging needs to better target the intended impact; and to align reporting with the financial year.

Summary supporting narrative for the overall score in this review

LHP performed well during the difficult launch period under review, largely delivering to expectations on all outputs. Longstanding BEB partner UNICEF and new partners OCHA and IOM adapted exceptionally well to the challenging circumstances, including the demands of preparing for and responding to the new crisis and growing humanitarian needs in the south in the context of access challenges and limitations (including due to stringent Lebanese Hizballah security restrictions), ensuring business continuity and relevance of activities.

Despite having the activities agreed before the onset of the Israel-Gaza crisis on 7th October 2023, activities under the OCHA-managed Lebanon Humanitarian Fund (LHF), for example, were re-prioritised and adapted to the increase in humanitarian needs in the south. The LHF launched a reserve allocation to provide immediate aid to the displaced and those affected who remained in the conflict zone, including support to ongoing critical response efforts, particularly those focused on safeguarding the safety and welfare of children. Through in-built flexibility the LHP contributed urgent bridge funding to IOM for the Displacement Tracking Matrix (DTM), given its importance across all partners active in the humanitarian response in the south, including to help determine if triggers in the Humanitarian Country Team Contingency Plan were met. This was complimented by a UK-funded Civil Military Coordination (CIMCOORD) position as part of the OCHA Access Working Group that facilitated access for partners to unlock blockages in response to the south unrest, including restrictions to data collection for the IOM DTM.

The programme has provided an effective vehicle for HMG support to Lebanese, refugees, and other vulnerable populations at scale in Lebanon in critical areas including food assistance, education, child protection, multi-sector support (e.g. shelter, WASH), social protection system strengthening, and aid coordination, enabling the UK to uphold its humanitarian commitments.

The LHP also complements Centrally Managed Programmes (CMPs) active in Lebanon (e.g. the Global Alliance for Vaccines and Immunisation). Through funding from the Basic Assistance in Crises CMP, the Institute of Development Studies is conducting global research on social protection with Lebanon selected as one of the focus countries. The research which is due to be completed this year will contribute to evidence-based decision-making for policies in the social protection sector and will tackle topics such as informal social protection mechanisms. Lebanon is also a focus country for the Education Research in Conflict and Protracted Crisis CMP which aims to conduct and disseminate research on the most effectives approaches to education in emergency contexts.

Despite the challenging context described above and pressures on the team due to crisis, including temporary drawdown, the LHP performed well in terms of continued strong delivery by partners; adaptability to respond to emerging priorities in the south, notably through the LHF and IOM; and complementarity between activities.

Major lessons and recommendations for the year ahead

Key lessons and recommendations from this first Annual Review are presented here. Output-specific lessons and recommendations are presented under the Detailed Output Scoring section.

Strengthen transparency and quality of reporting across various partners and revise LHP logframe in conjunction to ensure a breadth of outputs and outcomes and more streamlined tracking of progress in line with UK objectives.

Plan an indicative programme of field visits for the current year, ensuring broad geographic and programme coverage to the extent possible, and factor in adequate time for security clearances.

Seek surge / temporary cover / increase resilience measures for programme mobilisation, management and technical advisory oversight during emergency / crisis periods to minimise delay and disruption to the smooth and timely implementation of business-as-usual programme and policy activities. Operating in a continuous emergency and crisis state has reduced resilience and flexibility amongst other team members to provide extended cover.

Continue to use the LHP’s Technical Assistance component to support placements with catalytic potential with key partners to the benefit of humanitarian coordination and delivery in Lebanon.

Develop value for money (VfM) indicators for the programme, as initially planned in the Business Case to inform future programming design.

Continue to advocate for inclusion of Lebanon in relevant CMPs to further leverage and complement the LHP, including the Global Mine Action Programme to support recovery and the Social Protection Technical Assistance, Advice, and Resources Facility, bringing in management to reinforce advocacy when needed.

Engage with women’s rights and other local organisations working on gender and disability inclusion to better understand the inclusiveness of the humanitarian response in Lebanon and explore potential avenues to fund GBV and inclusion activities to address the funding gaps.

The Theory of Change (ToC) remains valid, but given some changes in context, including the conflict in the south, and likely time and cost extensions, the ToC and the key assumptions underpinning it should be reviewed as a separate exercise.

Consider a bid for a thematic or portfolio evaluation under the next available window, factoring in BEB capacity and priorities.

Complementary to the LHP logframe, the team should finalise a system to define, track and measure the impact of development and humanitarian diplomacy / influencing efforts in support of programme objectives and which are critical in maximising impact and VfM, including policy progress with the Government of Lebanon (GoL).

The next Annual Review process should be launched one month earlier, as there will be new outputs and possibly new partnerships to incorporate.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original Business Case.

The LHP focuses primarily on humanitarian interventions alongside long-term system strengthening and development objectives. In these early stages, the programme is already delivering against agreed outputs under most of these objectives. The programme impact, as set out in the ToC (attached at Annex A), is humanitarian needs are reduced for the most vulnerable across Lebanon and further increases in vulnerability are mitigated. The expected outcomes are effective delivery of humanitarian support for the most vulnerable; improved educational outcomes and protection for the most marginalised out of school children; and progress achieved towards more inclusive, sustainable, and accountable support systems. These outcomes align with UK priorities for Lebanon as outlined in the Country Business Plan. The ToC remains valid, but given some contextual changes, including the conflict in the south and likely time and cost extensions, the ToC and the key assumptions underpinning it should be reviewed as a separate exercise.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This is the first review of the programme, covering the first six months of delivery. At this stage, outcome indicators are not measured due to unavailability of data by the time of this review (please see below). For this reason, this review is mainly based on output level reporting and qualitative assessment of this initial implementation stage. Based on this, the LHP is on track, having delivered most of its outputs for FY 23/24. The programme continues to deliver lifesaving assistance and protection services to large numbers of highly vulnerable people, and there is scope for education and social protection system strengthening to have a lasting impact. As indicated under the recommendations, we should invest in research, evidence, and evaluation to continually assess the effectiveness of our approaches, to ensure limited resources target the most effective interventions, and to encourage other donors to support the response. This includes new programming aimed at addressing the drivers of irregular migration.

Outcome	Effective delivery of humanitarian support for the most vulnerable; improved educational outcomes and protection for the most marginalised out of school children; and progress achieved towards more inclusive, sustainable, and accountable support systems.

Indicator related to LHF	Milestones for this review	Progress
1.1 Number and percentage of targeted people in need reported to have been reached by partners through the Fund’s allocations (standard/reserve) disaggregated by gender, age, sector, and geographic area	100%	Data not yet published by OCHA, pending completion of extended projects from 2023.Projects will end in November 2024; accurate data will be available in February 2025.
1.2 % of boys and girls enrolled in multiple flexible pathways programmes who show enhanced learning outcomes of at least 50% after finalizing the different education programmes	NA	NA

It is not yet possible to assess progress on Outcome Indicators 1.1 and 1.2. For Outcome Indicator 1.1, the figures for people reached are not yet published by OCHA as some projects from 2023 are still ongoing, bridging activities until new projects are set under the new allocation. For Outcome Indicator 1.2, there is no target for this reporting period, as education cycles have not been completed, so benefitting children have not yet completed their final assessments.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The LHP has shown early satisfactory performance, achieving the agreed outputs, and should therefore continue. This is reflected under the detailed output scoring, and this is the basis upon which we are confident that the LHP will deliver against the outcomes in the context of multiple crises.

## C. DETAILED OUTPUT SCORING

Output Title	Multi-sectoral humanitarian support delivered to the most vulnerable.
Output number:		1	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR.	NA

Indicators	Milestones for this review	Progress	Achievement
1.1 Amount and percentage of Country Based Pooled Fund (CBPF) funding allocated through standard and reserve allocations* broken down by type of implementing partner, sector and geographic area	At least 70% of funds allocated through standard modality and up to 30% kept in reserve	64% of funds allocated through standard modality and 36% allocated to reserve modality	91% on standard modality / 120% on reserve modality
1.2 Amount and percentage of CBPF funding (included as a component of funded projects) allocated for activities to promote the participation of affected people, making sure the response is inclusive (Accountability to Affected Populations - AAP)	100% of approved proposals to include AAP	100% of the approved proposals included AAP	100%
1.3 Amount and percentage of CBPF funding allocated to in‐kind and cash assistance (conditional, unconditional, restricted, unrestricted, sector‐specific, or multi‐purpose cash transfers), as well as mixed in‐kind and cash projects by sector and geographic area	At least 15% of LHF allocation	7.38%	51%
[note] LHF provides two modalities to allocate funds to humanitarian partners and projects: the standard modality that takes place against the backdrop of in-country collective humanitarian plans, and the reserve modality that is intended primarily to respond to rapid onset and unforeseen circumstances and address corresponding needs.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 focuses on delivering aid to the most vulnerable through a multi-sectoral humanitarian approach, delivered by OCHA through the Lebanon Humanitarian Fund (LHF). Over the reporting period, this output met expectations and scored an A. The insights provided below were informed by the 2023 LHF Annual report, a field visit that was undertaken in February 2024 and the annual review self-assessment report shared by OCHA.

LHF is a CBPF established in 2014 to support critical humanitarian needs in Lebanon. The UK contributed to the pooled fund as third largest donor in 2023. LHF support targeted 223,000 individuals overall of which 120,000 were women and girls, 13,000 people had disabilities 55,000 received food assistance, 38,000 received protection assistance and 7,000 students at risk of dropping out of education were enrolled in catch-up and retention programmes.

Indicator 1.1 measures the percentage of LHF funds allocated through standard and reserve modalities based on the yearly allocation strategy, and in alignment with the CBPF standards.
Under the 2023 allocation strategy, LHF allocated $26.1m in total, of which $16.7m (64%) was through the standard allocation and $9.4m (36%) was through a reserve allocation. The reason for the discrepancy of the target funding split of 70/30 was the activation of an emergency reserve allocation in November to respond to needs emerging from the hostilities in the south. This required frontloading funds to key pre-identified partners to enable them to rapidly response to the emerging needs. The only possible way to provide funds to pre-identified partners, without going through standard proposal reviews is to use the ‘48Hrs response’ reserve allocation mechanism, set in the LHP operating framework as an agile tool to respond to emergencies. Therefore, the split of funds between standard and reserve allocation differed to the target percentage initially set in the log frame; however, the overall allocation was fully spent, hence the assessment that the indicator was fully met.

Indicator 1.2 measures the percentage of funding allocated for activities to promote AAP, making sure the response is inclusive. This indicator was fully met. The person-centred approach adopted by LHF under all its allocations ensures that AAP is considered at all stages of the projects. For this review period, all project submissions funded by LHF provided details on AAP, participation and inclusion in project planning and design stage. Project monitoring and reporting subsequently tracked progress throughout project implementation.

LHF prioritised protection with a community-based, person-centred approach, targeting vulnerable individuals (elderly, female-headed households, GBV survivors, and women and girls). LHF funded activities that supported child protection, GBV, prevention and response activities, including awareness campaigns, community engagement, and capacity building for caregivers. LHF also strengthened child protection services and continued enhancing the Preventing Sexual Exploitation and Abuse (PSEA) framework among partners.
        LHF funded various initiatives for children and elderly individuals with disabilities, including health, protection, education, and essential items, supporting approximately 13,000 individuals with disability, under the standard allocation.

Indicator 1.3 measures the percentage of the allocation dedicated to cash support, through diverse types including multipurpose, sector-specific, and both conditional and unconditional cash assistance. This diverse approach to cash assistance aims to maximise the impact of the funding, ensuring that it meets the varied and dynamic needs of the beneficiaries effectively. In 2023, $3.3m (7.38%) of the total allocated funding was programmed as cash assistance. This was below the target of 15% – however the justification as to why the target was not met is well evidenced and aligned with the purpose and scope of LHF. The fund is designed with a flexible multi-sectoral approach, building on coordination between sectors to reach to most vulnerable. Cash assistance for 2023 shifted to meet different needs as follows:
- For the south response, sectors did not use cash as first response and opted for in-kind support until needs were clearly identified. Seven months from the beginning of hostilities, cash is now prioritised, and we expect this target to be reached through the 2024 allocations.
- LHF partners were requested to provide retention and homework support instead of cash for education given this is already delivered by UNICEF.
Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes took place to this output during the reporting period. Any updates to indicator targets for the coming year will be aligned with the overall LHF results framework.

Lessons learned this year and recommendations for the year ahead

Lessons learned for this output are:

The indicators in the LHF results framework do not reflect the actual number of beneficiaries reached. This is common for CBPFs. We are therefore relying on data from the LHF annual report, updates from quarterly meetings and field visits to support our monitoring of programme impact.

Cash remains the primary modality for food assistance; food in-kind or hot meals are provided where there is limited access to markets or a kitchen. Although the most food insecure are targeted, discussions with beneficiaries indicate they prioritise other expenses such as rent and healthcare over food.

The short duration of projects under the standard allocation may hinder the ability to create long term impact. The current duration is set for 12 to 18 months. For the 2024 allocation round, the Advisory Board approved a longer timeline (18 to 24 months projects) for initiatives that integrate resilience-building elements to help increase the impact and sustainability of humanitarian efforts.

Recommendations for this output are:

Building on observations made during the February 2024 field mission, the LHP team should use its Advisory Board membership and role in the Donor Working Group and Lebanon Donor Cash Forum to influence cash support through LHF, for better coordination and ability to reach LHF targets on cash assistance.

Noting LHF’s own results framework and standard indicators are largely process-orientated, the LHP team should consider incorporating output and outcomes indicators in the LHP logframe linked to the narrative provided in LHF’s reporting.

The LHP team should conduct more field visits in line with current security measures, visiting the other locations targeted with LHF’s geographical approach (Tripoli or Akkar) to see if coordination is as strong as in Zahle (visited in February), and better understand how protection issues vary from region to region.

Output Title	Literacy, learning, protection, health, and nutrition support delivered for marginalised youth and out of school children
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR.	NA

Indicator(s)	Milestones for this review	Progress	Achievement
2.1 Number of children enrolled in non-formal education programmes. / a. Early Childhood Education programme (4 - 5 years) / b. Basic Literacy and Numeracy programme (6 – 12 years) / c. Adapted Basic Literacy and Numeracy programme (13 -14 years)	2131 (50% girls, 5% children with disabilities) / 650 / 856 / 625	2,131 (50% girls, 5% children with disabilities) / 650 / 856 / 625	100%
2.2 Number of in-school children provided with Retention Support (11 – 15 years)	344 (50% girls, 5% children with disabilities)	344 (50% girls, 3% children with disabilities)	100%
2.3 Number of children with disabilities aged 3-18 years provided with (a) specialized assessments, services/rehabilitation, support for enrolment or assistive devices in education and/or education supplies and (b) cash assistance	a. 148 (50% girls) / b. 148 (50% girls)	a. 148 (50% girls) / b. 0	50% (activities under b were still delivered but through funding from another donor)
2.4 Number of school personnel trained on topics including PSEA, psycho-social support (PSS), digital learning, social emotional learning pedagogy, foundational learning, and inclusive education	180 (no specific gender target)	180 (60% female)	100%
2.5 Number of children, adolescents and caregivers provided with community-based psychosocial support services	2,725 (no specific gender target)	2,725 (60% female)	100%
2.6 Number parents/caregivers of children under 5 reached with messages aiming to protect breastfeeding, infant and young child feeding, healthy diets, and maternal nutrition	418 (no specific gender target)	418 (70% female)	100%

Briefly describe the output’s activities and provide supporting narrative for the score

Output 2 focuses on the provision of education, child protection and wellbeing services for the most vulnerable out of school children and their caregivers through a network of ‘Makani’ multi-service community centres. This output is delivered under the Transition and Resilience Education Fund (TREF) managed by UNICEF. While Makani centres are operational across Lebanon, FCDO funding was used to support centres in Baalbek and Bekaa, where the needs are highest. Over the reporting period, this output met expectations and hence is scored A. The narrative outlined below was informed by discussions with UNICEF and their progress report, in addition to a field visit that was undertaken earlier this year in March.
[note] ‘Makani’ means my place in Arabic.
[note] The TREF, which was initiated in June 2022, includes two funding windows: (1) formal education and (2) non-formal education (also known as multiple flexible pathways). While SMB meetings for the first window have been ongoing since inception, when LHP was launched SMB meetings for the second window were not yet underway.

Indicator 2.1 measures the delivery of non-formal education programmes which aim to support vulnerable out of school children to develop basic literacy, numeracy, and social emotional skills. The programmes provided include:
- Early Childhood Education (ECE) for children aged 4-5. This is aligned with the Ministry of Education and Higher Education (MEHE) ECE programme and enhanced with psycho-social support (PSS), music, art therapy and play-based learning. Upon completion, children should be able to enrol in grade 1 in public schools. During the reporting period, 650 children benefitted from ECE, 50% girls and 4% children with disabilities.
- Basic Literacy and Numeracy (BLN) for out of school children aged 6-12. The children are required to complete a cycle over several months (approx. 300 hours) with the hope of transitioning to technical and vocation education and training (TVET) or UNICEF’s school bridging programme (Dirasa). 856 children were supported with BLN during the reporting period, 50% girls and 7% children with disabilities.
- Adapted Basic Literacy and Numeracy (ABLN) for children aged 13-14 suffering from multiple deprivations including child labour, child marriage and disabilities. The ABLN curriculum is reduced to 120 hours, in recognition of other pressures that might prevent children from regular attendance. Upon completion, children should be referred to youth programming. 625 children were supported with ABLN, 50% girls and 5% children with disabilities.
These non-formal education programmes target children based on vulnerability (rather than nationality). However, the majority of children reached are Syrian refugee children as they account for most out of school children in Lebanon. According to UNICEF estimates from 2022, there are approximately 700,000 out of school children, up to 500,000 of whom are Syrian.

Indicator 2.2 focuses on retention support. This targets in-school (primarily Lebanese) children aged 12-15 (grade 7-9) who are at risk of dropping out. The focus is at this grade level because retention support provided by other partners, including LHF, primarily target children under 12. Furthermore, statistics from the Centre for Educational Research and Development indicate school dropout rates are highest at these grades. Retention support is normally carried out in the children’s schools rather than in the Makani centres, and covers key subjects including Arabic, Maths, Foreign Languages and Sciences over a period of 160 hours. During the reporting period, 344 children were reached (50% girls).

Indicator 2.3 focuses on specialised support for children with disabilities. During the reporting period, 148 children (50%) were supported with an individualised action plan, specialised services, and referrals, where required, following an initial assessment using the Washington Group Questions. UNICEF’s social assistance cash support, though delivered as planned to 148 children, was supported with funding from another donor during the reporting period (due to the need to spend their funds by a certain date). The result in this programme log frame is therefore recorded as nil.
[note] The Washington Group Questions are designed to help identify disabilities and special needs in an efficient and cost-effective way

Indicator 2.4 measures the number of staff trained on key topics including pedagogy, safeguarding, gender mainstreaming and community engagement. 180 staff benefitted in total. During our field visit we also learnt that they benefit from coaching. Going forward it will be important to follow up on what personal development plans are in place, what their career trajectory is, and whether there is any additional training from which they would benefit.

Indicator 2.5 measures the number of children and caregivers supported with PSS services. PSS is a key element of education in emergencies, and priority is given to caretakers of children who have experienced child violations or show symptoms of trauma. During the reporting period, 2,725 were reached, the majority (60%) are girls and women, with community-based (non-specialised) PSS services such as emotional support groups and referrals. Where referrals are made, however, it is not clear what the case management capacity of partners is and whether people are able to receive the required support.

Indicator 2.6 focuses on early childhood development (ECD) services provided to caregivers of children under 5. During the reporting period, 418 caregivers were supported with integrated nutrition and ECD services including through group sessions, counselling, and home visits. Recommendations and guidance were primarily related to parenting, breastfeeding and nutrition. Screening for malnutrition was also undertaken with referrals made as necessary.

Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes to the output were recorded during the reporting period. However, as outlined above, social cash assistance (indicator 2.3) – though delivered to children with disabilities – was not supported with FCDO funding, despite this being the original intention. UNICEF have confirmed no changes are required to the milestone for the coming year as FCDO funding will be used.

Lessons learned this year and recommendations for the year ahead

Lessons learned for this are:

Governance was identified as a key risk during the due diligence exercise. However, during the reporting period, high level Strategic Management Board (SMB) meetings were initiated for the non-formal education window under the TREF. These have helped highlight pressing policy issues e.g. related to transition and accreditation, and how the TREF is supporting a holistic response to key policy and programmatic issues through key systems work.

Programming under the TREF is effectively complemented by systems strengthening workstreams. The systems strengthening under window two (funded by other donors) focusses on ensuring children (beyond just ECE) can transition to public schools through the development of a transition framework (anchored within existing provisions under Lebanese law), improved data management, work on accreditation and certification processes, and the development of teacher competencies and training programmes. This will help address a major weakness in the non-formal education sector i.e. limited transition to formal education.

While output 2.1 was delivered in line with the logframe targets (with 2,131 children reached, 50% of whom were girls, 5% children with disabilities), there is limited information on the quality of services provided, how often children are attending their classes and the extent to which they are benefitting from their lessons and learning. This is a key challenge. While UNICEF have introduced a new ‘quality’ outcome target on learning outcomes, this should be complemented by more real time data, based on regular and formative assessments in the classroom. Data on attendance should also be made available.

More data is required on the extent to which children are benefitting from their lessons. While the Makani centres are designed to provide a holistic and integrated package of services, the focus on delivering quality education should be maintained. UNICEF’s results framework focuses almost exclusively on access, though data on impact and quality is collected through its regular monitoring e.g. on attendance and attainment.

During our field visit, we observed that no men attended the community engagement and ECD sessions. Male engagement should also be encouraged and sought for critical support sessions as this is key to enabling behavioural change e.g. in terms of attitudes towards education.

Building flexibility into the budget (approximately £100,000) is key to support emerging priorities. During the reporting period the LHP team approved a small sum (approx. £15,000) to cover a funding gap for the Joint Education Needs Assessment which will provide key insights into the supply side of education (as opposed to demand). The flexibility should be maintained this year.

Recommendations for this output are:

The LHP team should continue to engage on the systems strengthening work and consider how formal education (i.e. public schools) can be supported especially if the finalisation of a transition pathway leads to a significant increase in the number of students in public schools.

UNICEF should report key monitoring data, in particular on attendance, achievement, retention and transition (particularly from ECE as this is already ongoing) and in the next progress report. The LHP team should also consider coordinating with other Makani donors to push for an increased focus on quality and learning outcomes.

FCDO/UNICEF should consider whether an impact evaluation can be conducted. This would ideally focus on the full integrated service provision, not just education.

The LHP team should conduct more regular field visits to gain critical insights into programme delivery in practice.

In addition to Makani, various other non-formal education centres are being supported across the country. Despite this, there are still many out of school children (estimated at 700,000). The LHP team should better understand how outreach is undertaken, e.g. whether men are actively engaged, and key insights such as whether parents are resistant to enrolling their children in education and why, or whether centres are oversubscribed and turning children away. This is essential to try and improve coverage going forward.

There is anecdotal evidence that protection case management capacity among partners is low. The LHP team should enhance synergies under outputs 1 and 2 of this programme and see how LHF could better support protection providers.

Output Title	Progress towards inclusive and sustainable social protection systems.
Output number:		3	Output Score:	NA
Impact weighting (%):		NA	Weighting revised since last AR.	NA

Briefly describe the output’s activities and provide supporting narrative for the score

Output 3 focuses on supporting inclusive social protection systems through technical assistance with ILO. This output is not formally scored in this review as activities were delayed and instead scheduled to start in FY 24/25, after this review period. However, commentary is provided on mobilisation phase up to March 2024.

Initially, this component was planned to start in November 2023. Delays in the set up included a lack of a central agreement between FCDO and ILO which led to extensive back and forth between both institutions in-country and at HQ level on the MoU, and diversion of staff capacity from the LHP team to BEB’s crisis response to the Israel-Hamas war, preventing other team members providing cover for the component’s lead advisor (the Social Development Adviser (SDA)) during maternity leave. The delayed start did not significantly affect the purpose and planned activities given a staggered approach was planned with most activities of planned for FY 24/25, in line with the return of the SDA from maternity leave.

Under this output, ILO will provide technical assistance (TA) to GoL and relevant public institutions for the implementation of the national social protection strategy. The focus will be on operationalising the private sector pension reform law 314, exploring health insurance reforms and strengthening national social assistance systems including the national disability allowance. The pension reform law was approved by parliament in December 2023 and the national social protection strategy was launched in February 2024; this will lead to more impactful spending on activities and TA given the strategy and policy grounds were well established.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to the output in the past year as its kick-off was planned for FY 24/25.

Lessons learned this year and recommendations for the year ahead

Lessons learned for this output are:

Developing and strengthening national social protection systems in a fragile context like Lebanon with compounded crises requires a patient development approach. The national social protection strategy completion took almost four years, and the pension reform law was decades in the making. ILO is a key social protection player and has been working on the policy level for years to secure these achievements.

Social protection systems are a relatively new area for FCDO globally; historically FCDO has focussed more on social assistance/cash provision. This shift is in response to an increased focus on fragile middle-income countries and a rise in protracted crises and forced displacement. The political paralysis and high-risk context should not be deterrents for engaging in such long-term system building activities as they contribute to the sustainability of our humanitarian activities and may help lay foundations for greater reforms when political conditions allow.

Recommendations for this output are:

The LHP team should manage expectations in terms of expected impact in the short implementation timeframe (LHP is an 18-month programme). FCDO should work closely with ILO on building our social protection network and leverage our diplomatic, political and technical expertise to support with the delivery of this component.

The team should closely engage with the FCDO social protection team, the ILO institutional leads, and the FCDO social protection team in Jordan for knowledge sharing, development of lessons learned and to contribute to policy development in relation to social protection systems strengthening.

Continue central discussions with the FCDO social protection team and ILO institutional leads to push for a central agreement between FCDO and ILO. This will facilitate contract set up and management in the future given social protection is a focus area in the White Paper, and ILO is a leading agency in the development and implementation of social protection systems.

The LHP team should continue closely engaging with key social protection donors (EU, Germany, Netherlands) to enhance programme complementarity and maximise impact.

The LHP team should undertake a field visit to the Ministry of Social Affairs (MoSA) Rights and Access (R&As) centres for people with disabilities, which will be supported through our ILO TA partnership.

Output Title	Strengthened humanitarian delivery and coordination systems.
Output number:	4	Output Score:	A
Impact weighting (%):	10%	Weighting revised since last AR.	NA

Indicators	Milestones for this review	Progress	Achievement
4.1 Number of local and national partners eligible for LHF funding supported through targeted partner training sessions focused on building capacity to design, manage and implement LHF projects, and consider cross-cutting issues including PSEA and risk management processes.	60 local and national NGOs	62 local and national NGOs	103%
4.2 Number and percentage of organisations engaged in the development of allocation strategies, and the prioritisation (strategic) and selection (technical) of projects through Review Committees broken down by type (INGO, NNGO, UN) and by sector	6 members of the Review Committee	Average of 6 to 8 members per Review Committee, depending on sector type (average of 2 representatives per INGO, NGO and UN)	100%
4.3 Number of Displacement Tracking Matrix (DTM) reports issued	5	5	100%

Briefly describe the output’s activities and provide supporting narrative for the score

Output 4 focuses on strengthening humanitarian delivery and coordination systems. This output was delivered under this review period through OCHA and IOM. The output met expectations and scores an A. The insights provided below were informed by the 2023 LHF Annual report, a field visit that was undertaken in February, and the annual review self-assessment report shared by OCHA and IOM.

To enhance overall humanitarian delivery, through OCHA, FCDO central funding supported one CIMCOORD position in 2023. This is not formally measured under this output since not funded via the LHP but is relevant as part of overall UK support to coordination of aid and humanitarian delivery in Lebanon and effective engagement of the LHP team with centrally managed funds to support bilateral delivery. The CIMCOORD position is part of the OCHA Access Working Group that facilitated access to a few donors/partners to unlock blockages in response to the south unrest, including the access to IOM for the Displacement Tracking Matrix.

Indicator 4.1: measures capacity building for local and national partners on programme management and cross-cutting issues. In 2023, 62 national partners received capacity building sessions to design, manage and implement LHF projects, and consider cross-cutting issues including PSEA and risk management processes. 58% of the local organisations supported were women-led.

One of LHF’s key priorities is the focus on localisation when disbursing the funds. The LHF localisation strategy is aligned with approach set out in FCDO’s White Paper. LHF allocated 39% of its funds to initiatives that actively involve and empower local and national entities across all stages of humanitarian interventions.

Indicator 4.2: measures the number of organisations represented in the Review Committee that were involved in the development of allocation strategies, and the prioritisation and selection of projects. In the 2023 allocation review, technical experts from NGOs specialising in disability-related issues were invited to participate in the allocation review committees to provide advisory and guidance on disability inclusion in practice. In addition, LHF works closely with the UN Women Peace and Humanitarian Fund (WPHF) through on-going knowledge exchange and capacity building support and review of proposals from women’s rights organisations (WROs) and women led organisations (WLOs). This ensures grassroots WROs and WLOs receive the needed capacity building support to eventually become eligible for LHF funding.

Indicator 4.3 measures the number of reports submitted under the DTM. The DTM was funded via the LHP for a period of one month (from period 29 February to 31 March), allowing IOM to deliver five DTM reports tracking the situation in the south, providing vital data on impacts of the conflict and continuity of reporting. The purpose of the tracker was to allow humanitarian actors in the country to assess needs and reallocate aid accordingly. The matrix was a key tool for OCHA to re-channel funds through the reserve allocation to the south response.

As outlined in the Summary and Overview section, DTM enumerators faced access challenged in Nabatiyeh and were unable to reach key informants. The access challenge first arose in November 2023. Rather than independent data collection, the Governor requested IOM use information from the Lebanese Red Cross instead. IOM agreed to this while continuing advocacy efforts with support from the OCHA Access Working Group (including the CIMCOORD funded by FCDO). After coordination and negotiation, this was resolved by the end of March and IOM was regranted access for its enumerators in Nabatiyeh.

Describe any changes to this output during the past year, and any planned changes as a result of this review

As this is the first annual review for the programme, no changes took place to this output. The IOM activity was not outlined in the Business Case, but flexibility was built in for such activities. The LHP team will determine the indicators and milestones for next review period based on agreed LHF activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned for this output include:

In 2023, LHF piloted a capacity assessment using new tools and informing prospective and existing partners about eligibility requirements. Recurring weaknesses in financial controls and procedures were identified, prompting LHF to provide further targeted support and guidance to local partners as part of efforts to enhance humanitarian delivery through local partners (this is in line with the UK’s International Development Strategy).

Close collaboration with partners and OCHA was maintained following escalation in the south to promptly mitigate concerns. Flexibility was essential to ensure projects achieved their objectives while maintaining a coordinated humanitarian approach.

There is potential for complementarity even between small-scale interventions to improve delivery and coordination, as demonstrated by the FCDO-funded CIMCOORD enabling vital access for continuation of IOM displacement tracking. This in turns provides data for one of the triggers for the Humanitarian Country Team’s Contingency Plan for the conflict in the south.

Recommendations for this output are:

It would be a valuable exercise for LHF to develop trend reports on findings from monitoring to inform future programming. While this is done informally, more regular analysis of monitoring findings at an overall fund level could help inform both LHF and sectors-level planning and partner engagement.

D: VALUE FOR MONEY

Key cost drivers and performance

FCDO uses the ‘5 Es’ framework (economy, efficiency, effectiveness, equity and cost-effectiveness) to ensure that UK Aid maximises impact. Considerations against the 5 Es for this programme are set out below.

Economy

- Under LHF, cost per beneficiary for a multi-sector emergency response varies by sector and balance of sector allocations.
- Management costs for UN pooled funds are 2%. FCDO is contributing 3% to OCHA core office costs as this also includes funding of key coordination roles which are essential for the wider humanitarian response. Management costs for downstream partners did not exceed 7% (in line with the percentage agreed centrally by FCDO).
- UNICEF’s budget included 10% education staff costs in addition to its cost recovery of 8%. FCDO HQ confirmed that each UNICEF country office has its own formula in relation to technical assistance/staff costs, especially where there is an overall decline in donor funding. While this reduces the overall amount spent on programme activities, ongoing policy development in relation to non-formal education, led by UNICEF, is critical to ensuring sustainable impact.
- Most budgeting and transfers for the Makani centres (over 90%) are done in USD; this helps minimum VfM losses associated with the use of Lebanese Lira (LBP). If partners need to make payments in LBP, they are required to use the 89,500 LBP/USD exchange rate which is in line with the market rate.

Efficiency

- Delivering through LHF enables an efficient way for FCDO to reach a wider range of sectors, partners, and projects in comparison to bilateral arrangements with a range of partners. Pooling funds and participating in collective governance means the UK can also influence total funds, not just UK funding, in line with our in-house expertise and priorities.
- The TREF enables FCDO funding to be leveraged with other donors to support a wider range of activities than would be practical with separate programmes and funding arrangements. This has enabled systems support work on non-formal education to complement service delivery.
- For the Makani centres, UNICEF has developed standard ToRs for staff to maintain quality standards whilst also ensuring resources are allocated efficiently and transparently. In addition, the community care worker and health worker roles have been merged, helping reduce the number of staff required by 5%.

Effectiveness

- Under LHF, funding allocations in 2023 were designed based on assessments of where needs were greatest, with input from sector leads and in consultation with the LHF Advisory Board on the overall strategy, ensuring that interventions were effective in meeting the overall outcome of reducing poverty and suffering.
- Reserve allocations are an efficient back up for emergency response. Following the onset of the Gaza crisis in October, the LHF’s reserve allocation was successfully initiated to respond to the emergency situation in southern Lebanon, through its 48-hour rapid response modality.
- LHF pivoted humanitarian response towards the delivery of more coherent area-based programming in a landscape of limited funding. LHF’s 2023 allocation strategy piloted this area-based approach with the aim to provide a multi-sectoral integrated package of services in targeted geographic locations to maximise impact.
- The five DTM reports contributed to shaping the humanitarian response in the south by allowing humanitarian actors including OCHA to identify vulnerable displaced people and tailor interventions accordingly.
- While data on learning is not yet available, a comprehensive analysis of children's learning outcomes will be included in the next Makani progress report, following post-tests conducted for ECE, BLN and ABLN. In addition to assessing learning competencies gained by children in the different education programmes, the report will also highlight the development of enhanced critical thinking skills, problem-solving abilities, and other core life skills essential for their overall growth and development.

Equity

- LHF standard allocation are designed to deliver a localised, multi-sectoral response to humanitarian needs of all vulnerable people in targeted areas of highest severity in Lebanon. The LHF pillar focussing on localisation ensures that national NGOs and grassroots organisations such as women’s rights, LGBT+ rights and disability rights organisations have direct access to funding and are treated as equal partners in the decision-making process from the design to the delivery of funded projects. Through their close ties to local communities, national NGOs employ a participatory approach from design to delivery ensuring the most marginalised social groups are identified, heard and supported.
- Makani is designed to be inclusive, ensuring all children, regardless of gender or ability, have access to education. As outlined under output two, targets for gender and children with disabilities were met. However, more data is required to ascertain whether the services provided are of high quality.

Cost-effectiveness

With Makani, the integration of services in one location allows for the streamlining of resources and administrative overheads. Before the launch of the Makani program, it cost UNICEF approximately $2,000 per child to benefit from all individual services in Makani, including non-formal education, PSS, health and nutrition, and child protection. The current cost per child in Makani for the range of services is $375, excluding the cash assistance for children with disabilities. This represents an 81% reduction in the costs.

Assessment of whether the programme continues to represent value for money.

The programme continues to deliver VfM as initially planned in the Business Case. Both the LHF and TREF components proved that channeling FCDO funds through pooled / multi-donor funds provides VfM by reaching more beneficiaries, creating a bigger impact; reducing bureaucracy of bilateral projects, and providing opportunities to influence other actors.

As outlined in the Business Case, VfM indicators were to be developed at the start of the programme. This was not done due primarily to pressure on staffing capacity as a result of BEB entering crisis mode at the launch of the programme (October 2023). As captured in the recommendations section, the programme team will work with partners to develop the indicators this year.

E: RISK

Overview of risk management

The overall risk rating for the programme is moderate. The main risk remains an ongoing or escalating conflict in the south. This would have impacts at multiple levels: rising needs against flat or declining international funding will undermine our desired impact to reduce humanitarian need nationally; operationally, this would prolong access restrictions, hindering the ability of implementing partners to reach people in need; and in terms of internal BEB resourcing, risks detracting the LHP team from programme delivery.

This risk is outside of the LHP team’s direct control. However, we are taking steps to mitigate this where possible through prioritisation with BEB and cover for key roles during absences. The overall risk register for the LHP is used to ensure the programme is managed effectively, considering climate, gender, safeguarding and counter terrorism financing (CTF).

During the due diligence assessment stage for the LHP, a thorough CTF assessment was conducted in consultation with a central FCDO CTF advisor to consider related risks in Lebanon given the proscription of Lebanese Hizballah (LH) in 2019.

Summary of top risks and mitigation are set out below:

Risk	Description	Mitigation	Net rating
Strategy and Context	Ongoing conflict in the south and potential escalation across Lebanon creates additional needs and access restrictions. These restrictions may hinder the ability of implementing partners to reach people in need and impact on overall project delivery.	Advocacy by FCDO on access is ongoing but limited due to no-contact rules with LH. Raise awareness internally with HQ on impact and secure additional funds. / Makani - Programming in the south has already been affected but partners have contingency plans in place, including moving services to other areas. These should be kept under review. / LHF - Coordinating with relevant authorities, humanitarian partners, and community representatives to ensure safe and unhindered access to affected populations. Strengthening the capacity of national and local partners to deliver humanitarian assistance in hard-to reach areas. Close collaboration and funding with OCHA’s Access and CIMCORD Teams and UNIFIL and UNRWA (in case of tensions in Palestine refugee camps) on access constraints and incidents and adapting the response accordingly.	Major
Strategy and Context	Increased anti-refugee rhetoric leads to restrictions on service delivery for refugees and inability of humanitarian partners to meet the needs of refugee communities.	Use political advocacy channels to engage with GoL on policy and rhetoric, in coordination with likeminded actors, RC/HC and partners. / Ensure flexibility within programmes to adapt as necessary. / Communicate programme results to demonstrate positive impact on both Lebanese and refugees.	Moderate
Policy and Programme Delivery	Anti-UN sentiments cause resistance to international humanitarian operations.	Partners are engaging in dialogue and consultation with the relevant stakeholders, including the government, civil society, media, and local communities, to explain the UN’s mandate, objectives, and activities, and to address any concerns or objections they may have and promote the principles and values of the United Nations including the humanitarian principles. / Enhanced visibility and transparency of the UN’s humanitarian work through various communication channels and platforms, such as social media and public events, to showcase the impact and benefits of its assistance to people in need. / LHP team continuing to monitor and assess the political and security situation in the country, and ensure the UN adjusts its humanitarian strategy and operations accordingly, to ensure the safety and security of its staff and beneficiaries, and to prevent or mitigate any potential risks or threats. / BEB should continue to advocate for additional funding to diversify partners (e.g. ICRC).	Moderate
People	Protracted crisis as a result of the Israel-Hamas war diverts LHP team capacity, disrupts business as usual programme activities and delays effective induction of new leadership.	Ensure lessons from first crisis response relating to humanitarian and development staffing inform approach. Protect mandatory programme activities in crisis prioritisation. Build resilience and understanding of LHP in related teams (the UK Office for Syria, Humanitarian Response Group, MENA regional) and seek surge support as necessary during times of pressure on the LHP team. Implement internal audit recommendation linked to Business Continuity by ensuring that all key documents are stored, key contacts and decisions are logged in Teams/AMP and Delivery Plan is regularly updated. Ensure minimum one week in-person handover for Team Leader and Development Director roles. Protect a minimum level of induction activity for new staff. Seek extension for Policy & Programme Manager/Education lead.	Moderate

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Activities under LHP during this period were governed through the following agreements:
1. MoU with OCHA.
2. Contribution Arrangement with UNICEF, drawing on the centrally agreed Framework Agreement between FCDO and UNICEF.
3. MoU with IOM.

OCHA

During the set-up of LHF component, OCHA proved to be cooperative and flexible going through the DDA process and different FCDO requirements related to CTF specifically. Overall, OCHA has been a reliable partner, delivering a complex humanitarian programme against a backdrop of emergency response and rising needs in the south. OCHA organised a successful field visit to the Bekaa in February, joined by Deputy Head of Mission/Development Director, despite the need to change the visit date at short notice. OCHA have been responsive to FCDO requirements, and all reporting was submitted on time. OCHA spent the full allocation of £3.85m over the period of this review (December 23 – March 24).

In terms of governance, the UK is a member of the LHF Advisory Board, allowing oversight and decision making on shaping overall allocation objectives and delivery decisions. OCHA have shared prompt updates, including on risk and finance, both through the Advisory Board, and through the standard FCDO/partners quarterly meeting.

UNICEF

UNICEF have delivered programming in line with expectations. Programming was not significantly impacted by developments in the south because all FCDO-funded centres are in the Bekaa and Baalbeck. While formal quarterly reviews are not in place, regular engagements are ongoing to discuss issues related to the programme. A key area to focus on over the coming year relates to data on the effectiveness of the interventions e.g. in relation to attendance, retention and learning Though this data is collected through UNICEF’s Child Level Monitoring (CLM), it is not proactively shared.

IOM

Through the LHP, FCDO provided short-term funding for IOM to continue delivering the DTM in response to the situation in the south. The support provided was for one month, allowing IOM to deliver five reports and feeding into the overall south response across humanitarian actors, including LHF.

IOM were very agile and flexible in responding to FCDO requirements to finalise the project component, including submission of proposal, and sharing the weekly DTM promptly.

FCDO / BEB

Mobilisation and monitoring of the programme were impacted by the onset on the Israel-Hamas war and continued hostilities between LH and Israel. In October, BEB entered crisis mode, with a drawdown of majority of the UK LHP team (Humanitarian Advisor and the Policy & Programme Manager/Education lead) and the Team Leader being re-deployed on the crisis response. This affected the ability to engage at country level, delayed development of results and VfM indicators and delayed meetings in person with partners. A change in travel advice also meant more limited movements in-country so only two field visits were possible during this review period with significant paperwork and lead-in time required to arrange.

Budget and Spend FY 23/24

Project Name	Budget Allocation FY23/24	Actual Spend FY23/24
Contribution to OCHA Lebanon Humanitarian Fund LHF	£3,850,000	£3,850,000
Contribution to the Transition and Resilience Education Fund (TREF)	£1,100,000	£1,100,000
Displacement Tracking Matrix	£50,000	£50,000
Total	£5,000,000	£5,000,000

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

OCHA

At a project level, LHF partners are monitored through regular reporting requirements as set out in the LHF Standard Operating Procedures, including field visits and post-implementation checks conducted by the OCHA programme and finance teams. All partners receive detailed feedback from LHF to ensure they can action any required changes identified from the monitoring. This feedback helps to provide course corrections to partners where issues are identified. It also supports LHF in identifying any possible compliance issues to be addressed.

The LHP team conducted one field visit to the Bekaa during this review period. This visit helped improve the team’s understanding of the LHF’s area-based approach to programming and the positive impacts on coordination among project partners. More visits were planned but cancelled due to the escalation in the south and surrounding areas including Bekaa. During the reporting period, the LHP team also conducted its first quarterly meeting with OCHA. In addition, FCDO is highly engaged as a donor to the fund through the Advisory Board which ensures full transparency on the allocation process, selection of projects, risk management and spend.

UNICEF

UNICEF has strong monitoring arrangements in place for the Makani centers. Focal points from the main office in Beirut conduct one visit per month and hold fortnightly meetings with implementing partners to discuss progress and issues. In addition, focal points from the field offices visit the centres at least twice a month and meet with partners at least three times per week. Three M&E consultants have also been hired to support monitoring of implementation, visiting each centre at least once a month. The LHP team should request that insights from the monitoring visits are included in the next progress report.

During the reporting period, the LHP team conducted a visit to two Makani centres in Bekaa (in Saadnayel and Taanayel). As outlined under the section on output 2, the visit helped provide several insights, including from both children and caretakers who spoke highly of the services provided. Both centres were accessible for children with disabilities and appeared to offer safe, happy spaces for the children to learn. Local staff spoke about how they used the Washington Group Questions to help identify and support children with special needs. The absence of men in caretaker support lessons was notable and there was also limited information on whether children’s learning levels are regularly assessed. Both areas will be followed up on in upcoming discussions with UNICEF.

Due to security restrictions, further visits to Bekaa and Baalbek are not currently possible. If the security situation does not change, the LHP team should consider visits to other centres closer to Beirut. (These are funded by other donors but will provide helpful insights nonetheless.)

IOM

IOM monitors the use and dissemination of its regular DTM reports and observes that these serve as the official data source on displacement through this crisis, with UN agencies, governments, and embassies relying on the data. The reports have become a reference point for the UN Humanitarian Country Team planning and response in Lebanon, including LHF.

The DTM project was funded via the LHP for one month. During this time the programme team remained in touch to ensure reporting was on track.

Learning

The LHP team should bid for a thematic or portfolio evaluation under the next available window, factoring in team capacity and priorities.

Date of last narrative financial report	Annual LHF report issued in May 2024. / UNICEF quarterly report shared in May 2024. / IOM report submitted in June 2024.	Date of last audited annual statement	All audit reports are shared at HQ level for UN partners.

Annex A: LHP Theory of Change