## Annual Review

Title: Lebanon Humanitarian Programme (LHP)
Programme Value £ (full life): £104,700,000		Review date: 31/08/2025
Programme Code: 301	AMP start date: 09/10/2023	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2023	2024
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case and Addendums:	D0005375.odt (live.com) / D0005730.odt D0005731.odt / D0006391.odt
DevTracker Link to Results Framework:	D0005376.xlsx (live.com)

## A: Summary and Overview

Description of programme

Lebanon is experiencing several severe and protracted political, economic and humanitarian crises. The Lebanon Humanitarian Programme (LHP) was designed in 2023 with an initial budget of £18.7m and a planned duration of 18 months. It was designed prior to the Israeli-Gaza and Israel-Hezbollah conflicts when the primary humanitarian challenges in Lebanon related to the economic crisis and the large Syrian refugee caseload. Despite significant shifts in the security context, the original humanitarian programme goals[1] remain relevant, underlying activities have adapted largely successively to meet evolving needs, and LHP remains the primary vehicle for the UK’s humanitarian response in Lebanon.
[1] i) address growing humanitarian needs across the country; ii) improve educational outcomes for the most vulnerable and marginalised out-of-school children in Lebanon; and iii) support more inclusive, sustainable, and accountable support systems for all vulnerable population groups.

The past year has been particularly challenging due to the conflict between Israel and Hezbollah which escalated significantly between September and November 2024 and at its peak led to the displacement of over 1,000,000 people (20% of the population). According to the World Bank, Lebanon now faces over $11 billion of damages[1] and high sectarian tensions. Over 60,000 Lebanese remain displaced[2] due to ongoing Israeli bombardments and destruction of homes.
[1] Associated Press, 2025. World Bank estimates $11B needed to rebuild Lebanon after Israel-Hezbollah war. [online] AP News. Available at: https://apnews.com/article/lebanon-world-bank-damages-israel-hezbollah-war-reconstruction-33dc0fe973d5fbd3fd3d3fc6ff2e82ff [Accessed 9 Nov. 2025].
[2] International Organization for Migration (IOM), 2025. Mobility Snapshot – Round 88, 15 October 2025. [pdf] Available at: local file [Accessed 9 Nov. 2025].

Another key contextual development was the fall of the Assad regime in Syria in December 2024. In addition to leading to new refugee arrivals from minority groups in Syria facing severe protection challenges, it also led the return of hundreds of thousands of existing refugees in Lebanon. The fall of Assad marked a fundamental shift for Lebanon given it has hosted the largest number of refugees per capita globally for the past decade due to the Syrian crisis, and the presence of Syrian refugees has underpinned the significant international aid presence in the country. The formation of a new reform-minded Government of Lebanon in February 2025 after over two years of political paralysis and a pause on USAID funding were also key contextual shifts. Due to its weak economic resilience, Lebanon was identified by ODI[3] as one of three countries facing the greatest vulnerability to the double shock of aid cuts and US tariffs.
[3] Raga, S., Agarwal, P. and Fur, V. (2025) Vulnerability of low- and middle-income countries to the impacts of aid cuts and US tariff increases. London: ODI Global. Available at: https://odi.org/en/publications/vulnerability-of-low-and-middle-income-countries-to-the-impacts-of-aid-cuts-and-us-tariff-increases/ [Accessed: 20 October 2025].

Summary supporting narrative for the overall score in this review

1. This Annual Review covers the period April 2024 to March 2025. In total, the UK’s budget for 2024/25 increased over four-fold from £12m to £56m and LHP was adapted significantly during the reporting period through three addenda as follows:
  1. Addendum 1 approved in June 2024 – cost extension to incorporate an additional activity under the Prime Minister’s Tackling Drivers of Upstream Migration Campaign, bringing the total Business Case value to £21.7m.
  2. Addendum 2 approved in July 2024 – cost and time extension to incorporate conflict preparedness and further activity under the Migration Campaign, bringing the total Business Case value to £39.7m and extending the end date to 31/03/2027.
  3. Addendum 3 approved in November 2024 – cost extension to incorporate significant additional crisis support, bringing the total Business Case value to £104.7m.

1. Despite the many contextual and operational challenges, including limited access to areas in the south, LHP demonstrated resilience and effectiveness and scores an A. The second and third addenda in particular proved critical in enabling the UK to respond to the severe spike in needs caused by the conflict escalation through the expansion of existing components and the addition of new ones as follows:
  1. Cash assistance for vulnerable conflict-affected Lebanese
  2. Multi-sectoral preparedness and response
  3. Site management support for collective shelters hosting thousands of displaced.

The adaptations over the past year reflect positively on the programme’s design, which built in flexible response mechanisms and laid foundations to allow scale-up against its stated objectives. In some instances, however, the rapid and significant expansion led to challenges including delayed and inaccurate updates to the logframe. Furthermore, the security situation impacted the team’s fragmented bandwidth during crisis response and ability to undertake monitoring visits to assess delivery on the ground.
Major lessons and recommendations for the year ahead

Key lessons learnt include:

  1. Flexibility in project implementation proved essential during the escalation, enabling a timely and effective response. The Business Case’s adaptability allowed British Embassy Beirut (BEB) to scale up rapidly by working with existing partners. Despite the complexity of securing approvals for three addenda, the team managed the process effectively. Preserving this level of responsiveness will be critical in future planning.

  1. Advanced planning and preparedness paid off. The programme team was in a strong position when the conflict escalated in 2024 as a “Lebanon Humanitarian Scenarios and Strategy” had been drafted in April 2024 and maintained up to the escalation, which provided the underpinning for subsequent programming decisions. The strategy also provided supporting evidence for a successful bid for preparedness funding, which in turn helped the UK rapidly mobilise assistance when the conflict escalated.

  1. Due to the emerging needs and priorities identified by partners, the team became involved in new sectors, stretching resource and requiring increased understanding of these sectors. The team had to draw on support from London-based sectoral and humanitarian response specialists. Future programming and response strategies could usefully identify UK priorities in advance to guide more prioritisation and trade-offs in emergency contexts.

  1. There was an issue with the accuracy of targets when the programme was expanded to include crisis components. While needs were rapidly changing and there had to be flexibility for partners to adapt to the situation on the ground, more accurate targets are needed to meaningfully measure performance and value for money. For future crisis response programming, there should be regular engagement with partners to ensure up-to-date assumptions and revised targets in an evolving context.

  1. It was important for BEB to triangulate assumptions about partners' capacity/comparative advantages in crisis response, with overlapping mandates and proliferation of parallel funding requests. BEB will continue to support clear mandates and joint analysis of critical gaps in line with the Humanitarian Reset and via roles on the Humanitarian Country Team (HCT) and the LHF Advisory Board.

  1. It is important to support adequate in-country presence of humanitarian staff during crisis. Drawdowns, caps on the number of BEB staff in Beirut, frequent location rotations and extensive hybrid working during the crisis hindered collaboration at peak response periods and limited ability to engage meaningfully with the Government of Lebanon (GoL) on response efforts, attend key external meetings and conduct monitoring visits.

Recommendations include:

  1. A risk-based and prioritised plan for field visits should be developed and implemented. Despite security challenges in the context of an active conflict, field visits were undertaken to the extent possible during this reporting period, and it is important to keep up the momentum.

  1. During crisis, changes to projects and allocations of new funds should be more streamlined by collating and prioritising questions to feed back to partners, agreeing on a subsequent set of questions, expediting the review process, adapting expectations to emergency context, delegating in the team and defining clear roles in review process.

  1. Given contextual changes, such as a new government and including the time and cost extensions, the ToC, including the inputs and the key assumptions underpinning it (especially “UK and other donors’ ODA levels maintained”), should be reviewed and updated in 25/26. This will also support the development of a new Business Case.

  1. Ensure future preparedness projects integrate lessons learned from this year’s emergency preparedness and response programmes. The programme team should continue to maintain a response strategy for 2025 and explore options for continued investment in preparedness and anticipatory action. In parallel, as member of the HCT, BEB should continue to advocate for concrete preparedness plans by the UN including in collaboration with GoL.

  1. Offers of technical assistance to partners through standby partnerships (or through rosters managed by FCDO) require clear terms of reference and time-bound deadlines on the part of both the requesting organisation and BEB/FCDO to avoid lengthy and time-consuming back-and-forths. For example, months of discussion took place between FCDO and OCHA about support to Civil Military Coordination capacity. During those months, the conflict had evolved (as had the nature of the original need) and it was eventually concluded that existing rosters could not respond with the required skill set.

Due to the challenges faced during the reporting cycle, linked to the escalations and changes in delivery context throughout the year, the following recommendations from the previous Annual Review were put on hold during the reporting period, but should still be taken forward.

  1. Develop value for money indicators for the programme, as initially planned in the Business Case to inform future programming design.

  1. Complementary to the LHP logframe, the team should finalise a system to define, track and measure the impact of development and humanitarian diplomacy / influencing efforts in support of programme objectives and which are critical in maximising impact and value for money, including policy progress with GoL.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

LHP focuses primarily on humanitarian interventions alongside long-term system strengthening and development objectives. The programme impact, as set out in the Theory of Change (ToC) (diagram attached at Annex A), is “humanitarian needs are reduced for the most vulnerable across Lebanon and further increases in vulnerability are mitigated’'. The expected outcomes are ‘‘effective delivery of humanitarian support for the most vulnerable; improved educational outcomes and protection for the most marginalised out-of-school children; and progress achieved towards more inclusive, sustainable and accountable support systems”. These outcomes align with UK priorities for Lebanon as outlined in the Country Business Plan that was in effect during the period under review.

As indicated above under lessons and recommendations, the ToC, especially at outcome and impact levels and the steps to achieving them, remains valid. Given contextual developments, such as the escalation of the conflict and the formation of a new Lebanese government, and programme adaptations including the time and cost extensions, the ToC, including the inputs and the key assumptions underpinning it should be reviewed and updated in 25/26. This will also support the development of a subsequent Business Case.

Also in 25/26, a clearer, more results-oriented logical framework will be devised that better illustrates how our work contributes to positive impact. Key changes will include thematic grouping of outputs and outcomes, and a rewording across all sections to emphasise measurable results. The impact, outcomes and outputs as set out in the logframe will be adjusted in accordance with the new ToC. Instead of consolidating all indicators under a single outcome, the revised logframe will include all three outcomes, with outputs and indicators reorganised under their respective categories. Indicators will be added or rephrased to ensure they meet the SMART (Specific, Measurable, Achievable. Relevant, Time-bound) criteria. To better capture the programme’s effectiveness, relevant qualitative indicators will be introduced at the impact, outcome and output levels in coordination with implementing partners.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As indicated in the detailed output scoring section and qualitative assessment, LHP is on track, having delivered its outputs for 24/25, and contributing to the outcomes and impact. The programme continues to deliver lifesaving assistance and protection services to large numbers of highly vulnerable people during both protracted crises and escalation, and there is scope for social protection system strengthening to have a lasting impact. Despite limited resources, it is important to invest in research and evidence to continually assess the effectiveness of our approaches, to ensure limited resources target the most effective interventions. This includes new programming launched during the period under review aimed at addressing the drivers of irregular migration. In 25/26 the LHP team will review the range of activities and evidence base to check for opportunities to consolidate and optimise the UK’s humanitarian response efforts in Lebanon.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

LHP has shown robust performance in its second year, achieving the agreed outputs and adapting to the changing context to meet new needs. It should therefore continue as per its extended timeframe through to 2027. The strong overall delivery is reflected under the detailed output scoring, and this is the basis upon which we are confident that LHP has good potential to continue delivering against the stated outcomes in the context of multiple crises.
## C. DETAILED OUTPUT SCORING

Output Title	Multi-sectoral humanitarian support delivered to the most vulnerable
Output number:		1	Output Score:	A
Impact weighting (%):		70	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress	Achievement
1.1 Reserve allocations (48-hour response) under the Lebanon Humanitarian Fund launched in a timely manner in response to emergencies and increase in needs	Yes	Yes	100%
1.2 Number of times transportation assistance is provided to beneficiaries that are at risk of irregular migration to access primary health care services	40,000	55,697	139%
Number of pre-procured essential supplies delivered to beneficiaries during the escalation and increase in needs / (i) Hygiene kits, (ii) Litres of fuel, (iii) Health kits, (iv) Medical commodities, (v) Information, Education and Communication materials, (vi) Dignity kits, (vii) Education supplies, (viii) Emergency supplies for Palestinian camps	(i) 4,500 / (ii) 678,000 / (iii) 22,640 / (iv) 20,000 / (v) 10,500 / (vi) 13,730 / (vii) 2,500 / (viii) 4,000 dignity kits / 19,700 hygiene kits	(i) 4,500 / (ii) 1,650,260 / (iii) 100,000 / (iv) 20,462 / (v) 700,000 / (vi) 12,900 / (vii) 3,280 / (viii) 4,000 dignity kits / 19,700 hygiene kits	(i) 100% / (ii) 243% / (iii) 442% / (iv) 102% / (v) 6,000[2]% / (vi) 94% / (vii) 131% / (viii) 100%
1.4 Number of children and caregivers provided with essential nutrition and child development services to respond to urgent needs during escalation of conflict	55,000 (30,000 children and 15,000 caregivers)	79,967 (61,639 children and 18,328 caregivers)	145% (205% for children and 122% for caregivers)
1.5 Number of vulnerable beneficiaries receiving cash assistance disaggregated by nationality, % female, % male, % with a disability, % children <18	1,081,240 Syrian refugees (≥51% female, ≥49% male, ≥5% with a disability, ≥ 55% children) / 132,316 Lebanese (≥52% female, ≥48% male, ≥4% with a disability, 28% children)	1,122,445 Syrian refugees (51% female, 49% male, 5% with a disability, 58% children <18) / 219,528 Lebanese (52% female, 48% male, 4% with a disability, 39% children)	Syrian refugees: 104% / Lebanese: 166%
1.6 Number of IDPs provided with psychosocial support disaggregated by location (in site / outside site), gender and nationality	4,000, of whom / - 1,000 in collective sites / 3,000 outside / - 2,800 women / 1,200 men / - 3,2000 Lebanon / 800 migrants and refugees	4,753, of whom / - 477 in collective sites / 4,276 outside / - 4,238 women / 515 men / - 3,456 Lebanese / 901 migrants / 396 refugees	118% overall
1.7 Number of site management (SM) staff and other stakeholders benefitting from SM sector capacity building initiatives	100	157	157%
[2] The wide discrepancy between achievement and milestones is due to inaccurate targets rather than overperformance.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 focuses on the delivery of aid to the most vulnerable in response to the multiple humanitarian crises in Lebanon. This output is delivered through multiple partners and was expanded significantly to support the humanitarian response during the severe conflict escalation between September and November 2024. Overall, this output met expectations and scored an A.

Indicator 1.1 focuses on the responsiveness of the UN OCHA Lebanon Humanitarian Fund (LHF). In 2024, the UK contributed £4.5mthe LHF, including a £1m uplift during the conflict escalation. This contributed to the LHF’s overall allocation of $65.6 million delivered through one Standard Allocation (SA)[3] and three Reserve Allocations (RA)[4]. Both the SA and RAs demonstrated responsiveness to the context, with the SA having launched in April 2024 to address multi-sectoral humanitarian needs in line with the wider UN/GoL Lebanon Response Plan (LRP). During the reporting period, three RAs were launched as follows:
[3] Standard Allocation refers to the planned distribution of funds for priority humanitarian projects, guided by an allocation strategy outlining eligible sectors and criteria.
[4] The Reserve Allocation is designed to be a flexible and rapid funding mechanism to respond to unforeseen emergencies or urgent needs.
- First RA / October 2024 - $12m during the escalation to 18 partners to support displaced populations, including those in collective shelters.
- Second RA / December 2024 - $30m post-ceasefire to support remaining displaced, those trying to return home and those who never left conflict-affected areas.
- Third RA / February 2025 - $150,000 to provide temporary, strategic funding to UNFPA for the Inter-Agency Community Accountability Platform, approved by the HCT. It enabled recruitment of a dual-role Protection from Sexual Exploitation and Abuse (PSEA) and Accountability to Affected Populations (AAP) Advisor in the absence of other resources, pending long-term funding.

Collectively, the allocations for 2024 supported over 480,000 beneficiaries (of whom 53% were women and girls and 11% were people with disabilities) through 89 projects. Approximately 7% of the results for 2024 are attributable to FCDO. 2024 also saw an enhanced focus on localisation, as outlined under the narrative for output indicator 4.2.

Indicator 1.2 tracks the number of times transportation assistance is provided to individuals at risk of irregular migration to access primary health care services. This activity was delivered through the UK’s £1m contribution to IOM’s Safe in Lebanon: Promoting Health and Well-being in Communities Prone to Irregular Migration project which aimed to address key drivers of irregular migration in high-risk communities by improving access to health, mental health, and psychosocial support, while also evaluating the effectiveness of these interventions. Despite operational challenges, including service suspension in Bekaa and resource shifts to North Lebanon due to the conflict, the project exceeded its target by delivering 55,697 transportation services (including 4,496 to IDPs), surpassing the original goal of 40,000. This success was driven by higher-than-expected beneficiary demand and appreciation, overcoming an initial project risk on low uptake. IOM negotiated with the transport company to increase daily capacity at no extra cost thereby maximising efficiency and value for money.

More broadly, IOM adopted a holistic approach to service delivery which included beneficiary outreach, booking medical appointments, providing transport to primary health care centres (PHCCs) and ensuring follow-up visits. To further enhance access to healthcare, IOM equipped 18 PHCCs (exceeding the initial target of 12) for telehealth services. This was done in coordination with the Ministry of Public Health, alongside the development of a feasibility study and Standard Operating Procedures (SOPs). Telehealth services are scheduled to launch in Phase 2 (25/26). In addition, IOM provided mental health and psychosocial support to 200 individuals identified as being at high risk of irregular migration. In parallel, an external evaluation covering IOM’s protection programming from 2022 to 2025 assessed how psychosocial, legal, and community-based interventions influenced the intentions and behaviours of at-risk individuals, including both Lebanese and Syrian refugees. Findings confirmed that psychosocial, legal, and community-based interventions contributed to reduced reliance on irregular migration by strengthening emotional resilience, informed decision-making, and perceptions of viable alternatives. The recommendations for future programming, which are informing Phase 2, included scaling up psychosocial and awareness interventions, pairing behavioural support with structural solutions (e.g. legal guidance and livelihood pathways), and sustaining impact through community focal points.

Finally, the project also initiated a research grant for Lebanese universities to study the drivers of irregular migration. The Terms of Reference were issued late in the year (and outside the reporting period) due to the conflict, but the grant will be awarded to the selected university in time for Phase 2 (25/26).

Indicator 1.3 measures the number of essential supplies procured and delivered during the conflict response. This was an additional component delivered through a new preparedness and response grant with UNICEF. A £5m contribution was originally agreed in August 2024 to support the procurement and prepositioning of critical supplies to ensure continuity of essential services in case of a conflict escalation. The grant was subsequently increased by £6.42m to support humanitarian response efforts. Activities spanned multiple sectors with UNICEF delivering:
1. 4,500 hygiene kits supporting approx. 22,5000 individuals to maintain basic hygiene conditions and reduce health risks in the context of displacement and overcrowded living conditions in collective shelters.
2. 1,650,260 litres of diesel to support the operation of 255 public water stations and water supply to more than three million people. Diesel distribution was prioritised for areas hosting a high number of IDPs.
3. 117,670 acute/chronic medications to 100,000 people through Primary Satellite Units (PSU). This exceeded the target of 22,640 because of a failure to update the target when the decision was made to increase the number of PSUs supported when the grant was topped up.
4. Over 700,000 Information, Education and Communication (IEC) materials on risks of unexploded ordnance and family separation and reunification.
5. 12,900 dignity kits to support women and girls to address challenges in accessing menstrual hygiene items and the disruption of regular health and sanitation services. This did not meet the initial target of 13,730 due to increased unit costs of dignity kits and transportation during the conflict.
6. 3,280 education kits and materials for 54,500 children to support learning continuity and continued engagement in education.
7. 4,000 dignity kits and 19,700 hygiene and baby kits to support hygiene and protection for people in Palestinian refugee camps.

A key challenge in delivery included delays in procuring water heaters for shelters – initiated in February 2025 with deliveries beginning in March, this meant that the heaters arrived after Lebanon’s harsh winter season had already passed. These delays occurred due to vendors importing heaters from abroad, highlighting the importance of aligning procurement timelines with seasonal needs and prioritising local sourcing where feasible to avoid logistical setbacks. UNICEF did not proactively communicate the issue to FCDO and it was only uncovered during a field visit.

Indicator 1.4 measures the number of children and caregivers supported with comprehensive nutrition and child development services through the UNICEF emergency preparedness and response grant. UNICEF targeted the most vulnerable children under five and pregnant and lactating women (PLW) in high-risk areas, particularly in the south and along border regions. To address the immediate nutritional needs of young children and PLW and prevent nutritional deficiencies, emergency nutrition rations including micronutrient supplements and emergency food rations were procured for displaced children and PLW in collective shelters and districts with high food insecurity. Key services provided included screening, referral for acute malnutrition among children and PLWs, education on optimal nutrition practices include Infant and Young Child Feeding (IYCF), rapid assessments, counselling and follow up, and distribution of anthropometric equipment. Overall, 61,639 children and 18,328 caregivers were reached, exceeding the initial targets.

Indicator 1.5 measures the number of vulnerable people supported with cash assistance. Prior to the escalation, the UK had provided £7m to WFP to support essential cash assistance to approx. 460,000 Syrians refugees. Syrian refugees were exclusively targeted as they are among the most vulnerable in Lebanon. Due to the conflict escalation, however, this component was significantly expanded to support vulnerable Lebanese too (for the first time) in addition to a higher number of Syrians impacted by the conflict. The UK provided £31m in total in 24/25. This represented 55% of the total LHP budget. Cash for Syrian’s has been a long-standing pillar of the UK’s response in Lebanon and there is a wealth of evidence supporting cash as a critical tool in humanitarian emergencies. The decision to fund cash for Lebanese due to the conflict was essential to quickly meet emerging needs, especially outside of collective shelters, and was also in line with UK efforts to reinforce national crisis response and social safety nets.

The expansion was designed to minimise risks of duplication and ensure coverage for unmet needs through strong coordination and centralised beneficiary management systems. Support to vulnerable Lebanese is led by the Ministry of Social Affairs (MoSA) which, with WFP support, created a single consolidated list of beneficiaries reducing the risk of overlap from multiple parallel registries. Cash assistance is coordinated through established humanitarian architecture, including the Basic Assistance Working group and the Lebanon Donor Cash Forum, where the UK plays a leading role. These mechanisms ensure alignment across partners, harmonised targeting approaches, and complementarity between interventions.

In total, 1,122,445 Syrian refugees and 219,528 Lebanese were supported, compared to respective targets of 1,081,240, and 132,316. More people were reached because WFP adjusted how it would utilise UK funds - to support more people with UK funding over a smaller period of time (two months instead of three). This adjustment was made following a pro-rata exercise. (Multiple donors fund cash via WFP, the funds are considered a joint pooled fund and the pro-rata exercise is required to develop an allocation plan.) As such, this indicator is deemed to have met expectations rather than exceeded them.

Cash assistance has long been a vital lifeline for Syrian refugees in Lebanon, particularly given restrictions on their right to work and the lack of local integration. It helps support vulnerable households to meet essential needs such as food, rent, healthcare and education until safe and voluntary return to Syria is possible, while also addressing socio-economic drivers that could lead to irregular migration to Europe. To account for inflation and declining purchasing power, monthly support was increased from USD 115 to USD 145 per family of five during the review period, ensuring continued relevance and impact.

During the conflict escalation, providing cash assistance to the most vulnerable Lebanese was essential to help alleviate the impact of the conflict, displacement and ongoing economic decline. Moreover, supporting vulnerable Lebanese communities is key to reducing social tensions. Insights from our field visits and discussions highlight that the poorest and most marginalised Lebanese individuals often compete with Syrian refugees for limited (often informal) job opportunities, which exacerbates social friction. Targeted cash assistance to Lebanese aims to ease these pressures and foster greater social cohesion.

While the cash transfer value is the same for both populations, the approach to cash assistance is different for conflict-affected Lebanese. WFP has been assisting MoSA to centralise the recovery response under government leadership and implement a Shock Responsive Safety Net (SRSN) which provides cash support to conflict affected families. The UK played a key role in supporting the development of this approach during the 2024 escalation, including through funding and technical support which enabled MoSA to establish its first shock-responsive safety net and deliver emergency cash assistance through national systems. From the outset, the programme was structured to be led by MoSA, with WFP providing targeted technical assistance to enable MoSA to coordinate, manage, and eventually institutionalise shock-responsive social protection within its systems. This includes joint development of targeting methodologies, strengthening MoSA’s data management and operational systems, and establishing SOPs that can be reactivated in future shocks—aligned with Lebanon’s National Social Protection Strategy. Recent WFP evaluation evidence highlights the added value of this approach, demonstrating how cash delivery has both met immediate needs and strengthened national systems, while recommending continued alignment of transfer values with the Survival Minimal Expenditure Basket, clearer communication on targeting, and stronger linkages to complementary services.

Indicator 1.6 tracks the provision of psychosocial support (PSS) to people displaced due to the conflict. This activity was delivered through a contribution to IOM’s Flash Appeal for the conflict response. PSS is a critical component of humanitarian response, helping individuals cope with trauma, displacement and uncertainty, while also strengthening community resilience. Under this indicator, 4,753 individuals received PSS (4,238 women and 515 men), exceeding the initial target of 4,000. Among them, 3,456 were Lebanese nationals, 901 were migrants, and 396 were refugees.

In addition to PSS, IOM reached 1,413 people with case management support, 539 people with legal assistance and 1,862 people with emergency cash assistance to address complex protection risks and facilitate access to essential services.

Indicator 1.7 focused on capacity building on site management to strengthen coordination and service delivery through IOM’s Flash Appeal. Capacity building aimed both to enhance immediate local capacity in site management and coordination, and support sustainability by equipping local actors to lead future responses. The project exceeded its target by a significant margin, with 157 staff, partners, and community focal points trained and mentored, compared to the initial target of 100. Four structured training sessions, including a training-of-trainers, were delivered between November 2024 and February 2025, complemented by ongoing on-the-job technical support. Training topics included site consolidation, decommissioning, durable solutions, safety audits, working in collective sites for migrants, adult learning methodologies and knowledge transfer techniques. The indicator’s overachievement was driven by both an increase in operational needs and IOM’s ability to scale up outreach efficiently within the same budget envelope, expanding training coverage without additional cost.

The UK’s contribution to IOM’s Flash Appeal also supported the deployment of site management support teams to 127 collective sites across Bekaa, with 73,100 individuals (approx. 20.600 families) estimated to have benefitted from improved management of the sites through enhanced monitoring, service mapping and coordination. Following the ceasefire and the rapid return of IDPs, IOM, in consultation with BEB, rapidly reprioritised activities in line with shifting post-conflict needs to facilitate returns and the decommissioning of 90 public facilities, including schools. across Bekaa, Akkar, Mount Lebanon, and Beirut. The decommissioning scope of work included cleaning, minor repairs, lock and window replacements and painting to help restore them to pre-displacement conditions and in the case of schools, enable the smooth resumption of education. IOM also continued site improvement activities to 13 remaining collective shelters housing hundreds of individuals to improve conditions, particularly for the winter.

Other activities not captured in the logframe

In addition to the indicators captured above, the UK supported the deployment of a UK Emergency Medical Team (EMT) in partnership with UK-Med. Following assessments in July and October 2024 and a formal request from the Minister of Public Health (MoPH), the EMT was deployed to the newly opened Turkish Trauma and Emergency Hospital in Saida from November 2024 to January 2025, later extended to March 2025. While the initial focus was on treating burns victims from the ongoing Israeli airstrikes, following the ceasefire the programme pivoted towards longer-term capacity building, specifically to strengthen burns and trauma rehabilitation services, developing ICU capacity, training healthcare staff (including physiotherapists), and donating specialised medical equipment and supplies to the hospital.

The EMT’s most significant achievement was establishing a fully equipped physiotherapy department within the Turkish Hospital and training 40 physiotherapists nationwide, alongside training 44 nurses to support a new ICU. The team delivered rehabilitation services to 94 patients with complex injuries across 593 sessions, achieving measurable functional improvements and integrating mental health screening into care pathways. Close coordination with MoPH and partnerships with national and international organisations supported knowledge transfer and service delivery.

While the performance of the EMT was positive, its overall impact was hampered by several factors. First, because the ceasefire was agreed soon after the decision to deploy the EMT, the actual number of patients treated in the Turkish Hospital was much lower than expected, which meant that a critical part of its capacity building plans – on-the-job training with real patients – was difficult to achieve (94 patients over five months). This was exacerbated by the precarious financial and management situation of the Turkish Hospital itself. Because the hospital had just opened after a decade of dormancy, it was understaffed and not yet integrated into national (MoPH) and humanitarian (health) systems. This meant that the number of counterparts for training on burns treatment and physiotherapy was lower than expected, and that patient referrals from around the country to the specialised centre were low. To boost the sustainability of the EMT’s work, a concluding stakeholder workshop was organised to raise awareness of the capacity built and the importance of strengthening hospital management and national referral systems to expand patient access for longer-term viability.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to the output description. The previous Annual Review recommended a revision of the logframe to improve outcome and impact measurement. Indicator 1.1 (LHF) was revised to focus on the efficiency of the Reserve Allocation mechanism, rather than the percentage of funds allocated. However, the focus on the 48-hour response timeline should be revisited as while RAs are launched promptly and have mechanisms in place to ensure rapid contracting (e.g. pre-identified partners), they are rarely launched within 48 hours of a crisis.

A number of new indicators were added as a result of the conflict escalation to reflect the various programme uplifts and mobilisation of new components. Targets were then revised after subsequent uplifts (though not accurately in all cases as per indicator 1.3).
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous Annual Review were focused on LHF as the only live component under this output at that stage. Progress against these is outlined below:

2024 Recommendation	Progress
Building on observations made during the February 2024 field mission, the LHP team should use its Advisory Board membership and role in the Donor Working Group and Lebanon Donor Cash Forum to reduce cash fragmentation in LHF and improve coordination with other cash sector actors including government.	Ongoing. Discussion has been held with OCHA on the importance of reducing fragmentation and alignment with sector guidelines. The UK continues to co-chair the Lebanon Donor Cash Forum influencing cash support across the sector for 25/26.
Noting LHF’s own results framework and standard indicators are largely process-orientated, the LHP team should consider incorporating output and outcomes indicators in the LHP logframe linked to the narrative provided in LHF’s reporting.	LHF indicators for this reporting period were updated. Indicator 1.1 was revised as outlined above. Indicator 4.1 (under output 4 below, relating to local partners) was amended to measure the number of interventions delivered by local NGOs instead of the number of local NGOs eligible to apply for funding to better measure localisation efforts.
The LHP team should conduct more field visits in line with current security measures, visiting the other locations targeted with LHF’s geographical approach (Tripoli or Akkar) to see if coordination is as strong as in Zahle (visited in February 2024), and better understand how protection issues vary from region to region.	Due to the conflict, ability to conduct field visits was limited due to security restrictions. While some visits were undertaken, none focused on LHF’s geographical approach. Where the security situation remains a recurring challenge for field visits, we should explore other monitoring mechanisms, e.g.engaging partners on reporting from their own monitoring visits, triangulation with downstream partners and other NGOs in the sectors, and encouraging more sharing of information between donors on their visits.

Lessons learned for this output are:

Obtaining clear indicators including target beneficiaries within LHF remains challenging and continues to be an area for improvement from the last reporting period. This is common for OCHA country-based pooled funds. We are therefore integrating data from the LHF annual report and updates from quarterly meetings and field visits into our monitoring of programme impact. It is essential to continue encouraging OCHA to identify indicators at the beginning of the year.

Investing in and leveraging the existing national social protection system is critical to reach newly vulnerable households during crisis. The rapid deployment confirmed that shock-responsive social protection is a highly effective and context-appropriate model for Lebanon that should be further strengthened.

Donor and government-led coordination are key to avoid fragmentation of emergency cash responses. Through active engagement as co-chair of the Lebanon Donor Cash Forum, the UK played a leading role in promoting harmonised targeting approaches, alignment of transfer values, and adherence to a common donor approach to cash assistance. This and our focus on strengthening national ownership helped reduce duplication and fragmentation across partners for a more coherent and efficient cash response. Going forward, sustained investment in these coordination mechanisms will be critical to maintain system-wide coherence, particularly during rapid scale-up.

Embedding emergency preparedness within the LRP and national frameworks is essential for effective future responses. The UK will continue to prioritise this through targeted advocacy and programming.

Preparedness funding was very beneficial, enabling UNICEF to preposition supplies ahead of the conflict escalation (when procurement and delivery might have been obstructed or more costly) and UK assistance to be scaled up rapidly upon onset of the escalation in conflict. However, overall HCT planning could have been more timely and directive.

Recommendations for this output are:

Preserving flexibility will be critical in future programming to pivot or scale-up activities in light of evolving needs and rapid onset crises such as conflict re-escalation. However, given challenges with accuracy of targets during expansion of the programme, it is also critical to obtain up-to-date assumptions and revised targets from partners in an evolving context.

Ensure future preparedness projects integrate lessons learned from this year’s emergency preparedness and response programmes. The programme team should continue to maintain a response strategy for 2025 and explore options for continued investment in preparedness and anticipatory action. In parallel, as member of the HCT, BEB should continue to advocate for concrete preparedness plans by UN including in collaboration with GoL.

1. Overlapping mandates of partners, proliferations of parallel funding requests and a lack of critical gaps analysis in a rapidly evolving crisis made selecting priority interventions difficult. Future UK programming and response strategies could usefully explore comparative advantages of different partners and options for UK priority sectors/partners in advance to guide a more strategic and focussed response in advance of emergency onset. BEB should continue to advocate to the HCT, with other donors, for clarity on the most critical gaps to inform programming choices.
2. FCDO should consider how it might influence funding mechanisms such as the Lebanon Humanitarian Fund (LHF) and the Central Emergency Response Fund (CERF) to allocate resources for preparedness in line with the Humanitarian Reset.

Output Title	Literacy, learning, protection, health and nutrition support delivered for marginalised youth and out-of-school children
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicators	Milestones for this review*	Progress*	Achievement**
2.1 Number of enrolments in non-formal education programmes *** / a. Early Childhood Education programme (3 -5 years) / b. Basic Literacy and Numeracy programme (6 – 12 years) / c. Adapted Basic Literacy and Numeracy programme (13 -14 years)	a. 3,248 / b. 3,371 / c. 2,375	a.3,504 (2,216 unique beneficiaries**) / b. 3,473 (2,159 unique beneficiaries) / c. 2,545 (1,224 unique beneficiaries)	108% / 103% / 108%
2.2 Number of in-school children provided with Retention Support (11 – 15 years)	7,228	7,373 (6,436 unique beneficiaries)	102%

*Milestones and results are cumulative (since January 2024).
**Some children may benefit from two cycles of the same programme, so UNICEF also includes a breakdown of number of unique beneficiaries.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 focuses on the delivery of non-formal education (NFE) to the most marginalised out-of-school children (OOSC) through a network of Makani (‘my place’ in Arabic) multi-service community centres. Over the reporting period, this output met expectations and scored an A, a score that reflects a modest over subscription of children in the programme due to cost savings and the introduction of shorter cycles rather than a commentary on the quality and impact of the intervention.

NFE remains a critical lifeline for Lebanon’s large OOSC population, particularly among Syrian refugees, with UNICEF estimating up to 500,000 children are currently out of school. The Makani centres, supported through the joint UNICEF/Ministry of Education and Higher Education (MEHE) Transition and Resilience Education Fund (TREF), are central to this response, targeting children who have been out of school for at least two years. Delivery of NFE through the Makani centres has been a core component of LHP since its inception.

During the reporting period, several factors negatively impacted children’s wellbeing and education continuity:
- In September 2024, the Cabinet of Ministers issued a decision requiring all children to have UNHCR refugee registration or legal residency to enrol in public schools. This requirement had been waived for the previous decade and has now led to the exclusion of 28,000 children who were previously enrolled in schools, thereby increasing demand for NFE. The documentation requirements have also hampered ongoing TREF systems level work on pathways for children from NFE to eventually transition to public schools.
- The conflict escalation between September and November 2024 led to widespread school and NFE centre closures and delays to the start of the school year. It also had a significant psychological toll on children. In one survey conducted by UNICEF in January 2025, 72% of caregivers indicated their children were anxious during the war and 62% said they were depressed[5].

To respond to these challenges, FCDO increased its initial contribution of £2m for Makani during the reporting period to £4.5m to support the scale up of Makani centres to meet the needs of displaced children. This enabled UNICEF to successfully reach a substantial number of children between January and March 2025, especially as a shorter three-month cycle was introduced instead of the standard one-year funding cycle. Despite numerous challenges including the initial closure of nearly all Makani centres in response to the conflict escalation, and subsequent damage to 20 centres due to Israeli airstrikes, UNICEF succeeded in continuing its support for the most vulnerable children. UNICEF were also able to provide more data insights e.g. on attendance, but critical gaps in data remain, particularly on learning outcomes. These are not currently measured as part of UNICEF’s results framework but should be a key focus area going forward.

Indicator 2.1 measures the number of children enrolled in various NFE programmes. This indicator met expectations, with modestly higher numbers of children benefitting from the programmes than initially targeted, as outlined below:

1. Early Childhood Education (ECE) for children aged 4-5 who are unable to access public school kindergartens. Activities are aligned with MEHE SOPs for early education and aim to enhance children’s cognitive, physical, social and emotional development. 3,504 children have been supported through ECE with FCDO funding since January 2024, exceeding the target of 3,248. Of the 3,504 children, 2,216 were unique beneficiaries (children who have benefitted from two cycles are not double counted). 49% of the children reached were female and 6% had disabilities.
2. Basic Literacy and Numeracy (BLN) for children aged 6-12. The MEHE-endorsed BLN programme offers three levels of literacy and numeracy support with children grouped according to their age (6-7 years, 8-9 years and 10-12 years). FCDO funding has supported 3,473 enrolments (2,159 unique beneficiaries) since January 2024, exceeding the target of 3,371 enrolments. 50% of children supported were female and 8% had disabilities. 8.2% were engaged in child labour, highlighting the high protection risks OOSC face.

Adapted Basic Literacy and Numeracy (ABLN) for children aged 13-14. UNICEF developed ABLN in 2019 to address the needs of the most marginalised children who might be engaged in child labour, married at an early age or living with disabilities. As such, the package is lighter in terms of both content and duration. 2,545 enrolments for ABLN have been supported through FCDO since January 2024, exceeding the target; 52% of beneficiaries were females, 28% were engaged in child labour and 28% had disabilities.

A key challenge for the NFE programmes was the negative impact of the conflict on children’s education continuity. This significantly impacted attendance: while broadly positive trends in attendance were observed from January to August 2024, these were followed by a sharp decline with the start of the escalation in September 2024. Following the ceasefire in November 2024, attendance rates began to recover gradually as the situation stabilised and re-engagement efforts were scaled up, but they took three to four months to reach close to pre-crisis levels again. Overall, ABLN had lower attendance rates compared to the other programmes due to the protection characteristics of the children supported.

Indicator 2.2 measures the number of children enrolled in public schools (both Lebanese and Syrian) who benefit from Retention Support (RS). RS targets children at risk of dropping out of school with support in Arabic, Maths, foreign languages, science and psycho-social support. UNICEF initially targeted children aged 12-15 (in grades 7 to 9) as children under 12 were already targeted through various learning recovery programmes. UNICEF then expanded the age criteria to children from the age of 7 in January 2025 to help protect younger children’s learning outcomes following the intense conflict escalation. . UNICEF has reached 7,373 children (6,436 unique beneficiaries) with RS since January 2024, slightly exceeding the target of 7,228. 55% of the children supported were girls and 6% had disabilities.
Other activities not captured in the logframe

Makani centres are multi-service community centres that provide a holistic package of support to vulnerable children and their caregivers. While wider activities designed to address vulnerabilities are ongoing and tracked through our regular engagement with UNICEF, they no longer form part of the broader LHP logframe (which was streamlined following last year’s Annual Review). Significant achievements with FCDO funding include:
- specialised support for 997 children with disabilities and cash assistance for 1,517 children with disabilities;
- training for 1,1,27 personnel on topics such as safeguarding, socio-emotional learning pedagogy and inclusive education;
- the provision of psychosocial support sessions for 5,035 caregivers; and
- support to 2,913 caregivers of children under 5 to enhance nutrition and early childhood development outcomes.
Describe any changes to this output during the past year, and any planned changes because of this review.

This output was significantly slimmed down during the past year to focus solely on the provision of NFE services rather than the wider package of services (as outlined above). As such, four sub-indictors focussing on these services were removed. The overall output wording should therefore be amended to reflect the education only focus. The simplistic output-only indicators should also be complemented with additional indicators on quality of education. These could also be reinforced in future annual reviews with more qualitative narrative based on informal discussions with partners, partner monitoring reports and BEB field visits. While the NFE focus to date has been on access and inclusion, going forward it is essential that contributions to children’s learning is also being measured.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous Annual Review is outlined below:

2024 Recommendation	Progress
Continue to engage on systems strengthening work and consider how formal education (i.e. public schools) can be supported especially if the finalisation of a transition pathway leads to a significant increase in the number of students in public schools.	Engagement on systems strengthening efforts is ongoing e.g. through processes linked to global education funds include Education Cannot Wait and the Global Partnership for Education, and through coordination fora including the TREF Strategic Management Board and the Local Education Group . Transition of students from NFE into public schools, however, remains restricted. Instead, the additional barriers now faced by refugee children in public schools has led to increased demand for NFE, meaning FCDO is currently engaging more on wider NFE system strengthening, specifically testing how there can be a more robust focus on children acquiring foundational literacy and numeracy skills.
UNICEF should report on key data related to attendance, achievement, retention and transition (particularly from ECE as this is already ongoing).	UNICEF has significantly enhanced reporting on attendance. Data on achievement is still poor. UNICEF currently reports on the percentage of children enrolled in NFE that show an improvement in learning outcomes as measured be pre and post-tests. However, this indicator doesn’t measure what the actual learning outcomes are i.e. if children acquire foundational literacy and numeracy skills. This should be an area of focus going forward. As highlighted above, transition from NFE to formal education is currently restricted, including for children in ECE, due to documentation requirements. FCDO should ensure there is reporting on completion rates/retention.
FCDO should consider coordinating with other Makani donors to push for an increased focus on quality and learning outcomes.	There is ongoing engagement with UNICEF and other donors to ensure indicators on learning are included in the results framework for the academic year 2025/26.
FCDO/UNICEF should consider whether an impact evaluation can be conducted. This would ideally focus on the full integrated service provision, not just education.	Discussions on an evaluation were deprioritised because of the crisis context. However, UNICEF has commissioned research to help inform the programme and support continuous learning. More information on this is included in the final section of this Annual Review.
In addition to Makani, various other NFE centres are being supported across the country. Despite this, there are still many OOSC. FCDO should better understand how outreach is undertaken, e.g. whether men are actively engaged, and key insights such as whether parents are resistant to enrolling their children in education and why, or whether centres are oversubscribed and turning children away. This is essential to try and improve coverage going forward.	UNICEF’s reporting includes information of effective outreach strategies such as partnering with trusted community leaders, encouraging self-referrals, establishing male-only groups for psychosocial support sessions and assigning facilities within communities to build trust and encourage participation. With USAID cuts, however, and the overall reducing funding landscape including from FCDO, there has been little progress in expanding coverage to meet the demands of the OOSC population..

Lessons learned for this output are:
Adaptability is key for the Makani model. During the rapid escalation of the conflict, Makani partners and staff were able to transition to deliver services to vulnerable displaced populations residing in collective shelters. Following the ceasefire, additional FCDO funding enabled the establishment of temporary Makani centres to address the increasing number of OOSC in need. While programme delivery was heavily impacted, these adaptations ensured the core objectives of reaching the most vulnerable children were maintained. FCDO wasn’t proactively notified of these adaptations in all instances, highlighting the need for more effective communication between FCDO and UNICEF.

The conflict underscored the necessity of having robust Education in Emergencies (EiE) strategies and contingency plans in place, including a shelter strategy. At its peak, the conflict resulted in the closure of all schools and the education of all children being disrupted. Integrating EiE into wider humanitarian response is essential to provide a sense of normalcy for children and ensuring their basic rights are met even in periods of crisis.

NFE remains critical given the growing size and complexity of the OOSC file, with the needs of many children unmet. The OOSC file has always been complex due to limited data, particularly on Lebanese OOSC. The exclusion of 28,000 refugee children from public schools since September 2024 and the arrival of new refugees from Syria since the fall of the Assad regime in December 2024 means there are now multiple types of OOSC with varying education levels and needs. A comprehensive mapping is required.

Recommendations for this output are:
The new Minister for Education and Higher Education has highlighted improving learning outcomes for all children as a key priority. FCDO and UNICEF should capitalise on this momentum behind quality to explore the possibility of piloting Teaching at the Right Level (TaRL) in Makani centres as part of its 25/26 contribution. TaRL is a global best buy for enhancing learning outcomes. The World Bank and Save the Children implemented a pilot in public schools last year which showed positive results. Testing the feasibility of TaRL in community-based NFE settings should be a key learning aim for the upcoming year.

Makani is delivered through a network of national and international NGOs. FCDO should enhance engagement with local delivery partners to get a better sense of challenges on the ground and insights from local communities e.g. in relation to refugees’ intentions to return to Syria and how education provision may influence decision making.

As part of the wider Humanitarian Reset, FCDO should challenge UNICEF on sustainability. UNICEF has a vital role on the systems side e.g. through supporting NFE curriculum development in partnership with the Centre for Education Research and Development (CERD). However, in the long term, NFE service delivery itself may be more feasible through NGOs.

FCDO should push for more data on new Syrian arrivals and a strategy outlining how they will be supported with both GoL and UNHCR. As it stands, there is no data on the number of school-aged children among the new arrivals, and the types of support they can receive is restricted.

To enhance the effectiveness of its education programming, it is essential FCDO increases the frequency and depth of its monitoring visits. These visits should include observing lessons delivered to children and engaging in in-depth discussions with teachers regarding their training, instructional methods, and the challenges they face. These visits could also enrich the narrative of future annual reviews. During periods of tighter security restrictions, these visits should be conducted within the designated "green" area as indicated in UK Travel Advice to minimise logistical and operational constraints which have been a significant barrier over the past year.

Data on learning outcomes remains poor and there is a need for more granular information. UNICEF’s current indicator on the number of students who show an improvement upon completion of a course doesn’t indicate what skills they acquire and whether they are at the expected level in accordance with their age/grade. A more robust indicator on learning outcomes should be agreed with UNICEF and included in the wider LHP logframe.

Output Title	Progress towards inclusive and sustainable social protection systems
Output number:		3	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress	Achievement
3.1 Number of evidence / dialogue / assessments contributing to formulation of policy proposals on pension system reform, including amendments of current draft legislation.	2	3	150%
3.2 Number of measures enforced or discussed amongst government stakeholders that contribute to building national systems for the delivery of social grants.	2	2	100%
3.3 Improved capacity (at least one training), operational measures and standard operating procedures (at least 1 document) within the R&A programme that contribute to enhanced service delivery to persons with disabilities, including women with disabilities.	2	2	100%

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 focuses on progressing an inclusive and sustainable national social protection system through a contribution to the International Labour Organisation (ILO). Over the reporting period, this output met expectations and scored an A, based both on meeting / exceeding targets for numbers of interventions, reflecting a strong alignment with national priorities and a high degree of adaptability in a challenging context, and contributing substantively to policy dialogue and development.

Indicator 3.1 measures the outputs (evidence, dialogue, assessments) contributing to the formulation of policy proposals on pension system reform, including amendments to current draft legislation. This indicator exceeded expectations during the reporting period. ILO implemented three key contributions versus an initial target of two, each directly supporting the refinement and operationalisation of the pension reform agenda with a focus on technical assessments and policy dialogue. ILO played a pivotal role in facilitating the development and approval of key implementation decrees, including the formal recognition of the most representative entities among employers and workers, which is foundational for the governance of the National Social Security Fund (NSSF). Additionally, ILO contributed to the drafting of a second decree establishing a competencies matrix for the NSSF Board, ensuring that governance structures are informed by merit-based criteria. These efforts were complemented by a comprehensive financial assessment of the End-of-Service Indemnity (EOSI) scheme, which informed reform proposals presented to both tripartite partners and parliamentary committees.

Indicator 3.2 determines the number of measures enforced or discussed amongst government stakeholders that contribute to building national systems for the delivery of social grants. Over the reporting period, this indicator met expectations. ILO focused on strengthening national systems for social grants, particularly the National Disability Allowance (NDA) and the Rights and Access (R&A) programme, meeting the set target. ILO supported the expansion of NDA coverage to children aged 0–14 as of January 2025, adding 6,000 new beneficiaries and marking a significant step toward inclusive, lifecycle-based social protection.

To support the institutionalisation of the NDA, ILO supported the design of a dedicated Management Information System (MIS) for MoSA’s R&A programme. This includes development of core modules and workflow prototypes covering registration, eligibility assessment, benefits management and monitoring modules. The modular design ensures flexibility for future scale-up and integration with national systems such as the Unified Registry for Social Protection. Next steps include system development, testing, and rollout by MoSA with ILO support. These efforts will result in a high-level upgrade plan that will enhance service delivery and integration with national systems.

Indicator 3.3 measures the improved capacity, operational measures and SOPs within the R&A programme that contribute to enhanced service delivery to persons with disabilities, including women with disabilities. Over the reporting period, this indicator met expectations. ILO implemented one programmatic report based on review of R&A to propose enhancements to services and workflows, assess human resources readiness and support measures, identify key information gaps, and elaborate recommendations. This was done in parallel to a review of the R&A Information System technology stack, digital infrastructure, and business processes and the design of high-level solutions for its upgrade (both were financed through another project, with technical support from the project team).

Moreover, with ILO technical and operational support, the data of 30,000 holders of valid Personal Disability Cards (PDCs) were verified and updated in preparation for the emergency NDA transfer. This effort was guided by newly developed SOPs and helped to streamline beneficiary identification and payment coordination. Both actions contributed to reinforcing the administrative and technical foundations of a more inclusive and accountable NDA programme. Moreover, during the peak of the conflict, staff at the R&A temporary verification centre received specialised training in effective and inclusive communication tailored for individuals with disabilities. This initiative aimed to ensure respectful and accurate outreach to citizens for the purpose of updating and validating their PDCs, thereby promoting accessibility and equity in service delivery.

These activities reflect a high level of technical delivery and strategic responsiveness. The outputs were achieved despite a volatile political and security environment. It is important to note that an activity focusing on supporting GoL’s sustainable health financing was not implemented by ILO due to the shift in government priorities toward emergency response following the escalation of the conflict, prompting ILO to reallocate efforts from policy-level engagement to supporting the delivery of social assistance. Resources were redirected to assist MoSA and R&A in expanding the NDA and leveraging national budget allocations, while also initiating system-level support to NSSF for improved health benefits management.
Describe any changes to this output during the past year, and any planned changes because of this review.

This output was not reviewed in the last Annual Review as it was still being mobilised. No changes were made to this output during the reporting period. For the coming year, more qualitative indicators will be considered.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous Annual Review is outlined below:
2024 Recommendation	Progress
The LHP team should manage expectations in terms of expected impact in the short implementation timeframe (LHP is an 18-month programme). FCDO should work closely with ILO on building our social protection network and leveraging our diplomatic, political and technical expertise to support with the delivery of this component.	Ongoing – FCDO and ILO are working closely on delivering the best outcome possible for this component. ILO was agile in reallocating funds when needed during the crisis, moving from a policy focus to an emergency response one to continue delivering impactful activities.
The team should closely engage with the FCDO social protection team, the ILO institutional leads, for knowledge sharing, development of lessons learned and to contribute to policy development in relation to social protection systems strengthening.	This will be captured as a pending recommendation to continue this year
Continue central discussions with the FCDO social protection team and ILO institutional leads to push for a central agreement between FCDO and ILO. This will facilitate contract set up and management in the future given social protection is a focus area in the White Paper, and ILO is a leading agency in the development and implementation of social protection systems.	Engagement with FCDO’s central social protection team is ongoing. The programme manager for this component will lead on pushing for a central agreement between FCDO and ILO, even though this does not affect the current in-country bilateral agreement anymore.
The LHP team should continue closely engaging with key social protection donors (EU, Germany, Netherlands) to enhance programme complementarity and maximise impact.	Ongoing – the BEB Social Development Adviser is engaging closely with key social protection donors.
The LHP team should undertake a field visit to the MoSA R&A centres for people with disabilities, which will be supported through our ILO technical assistance partnership.	This was undertaken on the International Day of People with Disabilities

Lessons learned for this output are:

1. As mentioned under output 1 (para 40), investing in and leveraging the existing national social protection system is critical to reach newly vulnerable households during crisis.
2. The escalation of the conflict in 2024 necessitated rapid adjustments to planned activities. ILO’s ability to re-programme and re-budget initiatives in real time, with the support of the UK, allowed the successful emergency deployment of support to R&A during the escalation of the war.

National systems can be strengthened even amid crises. Despite the fragile context, Lebanon has demonstrated that national institutions can act as responsible actors in delivering shock-responsive social protection, especially when backed by sustained technical assistance from specialised agencies. Throughout the war, the NSSF continued covering the benefits of people in the south even where Social Development Centres were closed.

Recommendations for this output are:
Continue investment in digital infrastructure and data governance. The project highlighted the need for robust data systems and verified beneficiary information. The successful delivery of emergency NDA transfers was made possible through ILO’s investment in data readiness, which enabled the rapid mobilisation of resources and ensured that assistance reached those most in need. This underscores the important elements of effective social protection.

Looking ahead, we recommend that ILO and its partners prioritise the formal adoption of pending legal instruments, particularly those related to pension reform. Efforts should also focus on resuming policy-level engagement on health financing, building on the technical groundwork laid during the past year. Continued support for the digital transformation of social protection delivery, including the rollout of the R&A MIS, will be essential for scaling up services and improving efficiency.

ILO should deepen its collaboration with other development partners in Lebanon to enhance coordination and leverage complementary strengths. The joint workplan with UNICEF and WFP provides a strong foundation for this approach and should be expanded to include other actors where appropriate. By fostering a more integrated and coherent approach to social protection, ILO can help ensure that its interventions deliver maximum impact in support of Lebanon’s most vulnerable populations.

BEB should continue to support technical assistance to GoL in areas that promote response mechanisms for vulnerable populations, particularly if humanitarian funding reduces. Support to ILO in alliance with the EU provides a model for using limited FCDO funds strategically to effect systemic reform and national capacity. The current government has also shown commitment to using public funds for social assistance programmes, reform and to promoting social protection. Based on ongoing state commitment to the social protection agenda, BEB should continue to capitalise on this momentum and support the state to be the primary service provider to its citizens. In turn, this can help further strengthen a fractured social contract.

Output Title	Strengthened humanitarian delivery and coordination systems
Output number:		4	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress	Achievement
4.1 Number of capacity strengthening initiatives to national and local NGOs funded by LHF to enhance and support localisation	2	2	100%
4.2 Number of (i) partner staff and community stakeholders benefitting from training on emergency preparedness and response and (ii) people reached with key messages on Explosive Ordnance Risk Education (EORE)	(i) 2,220 (51% female) / (ii) 10,500 (65% female and 80% children)	(i) 1,138 / (ii)13,691 individuals (56% female and 80% children)	(i) 51%
			(ii) 130%

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 focuses on strengthening humanitarian delivery and coordination systems. This output was delivered through OCHA and UNICEF. The output met expectations and scored an A, reflecting achievement on the number of planned activities by OCHA but, more importantly, the resulting increase in the number of national NGOs integrated into international aid delivery mechanisms.

Indicator 4.1 measures the number of capacity building initiatives for national and local NGOs delivered under the LHF. This indicator met expectations with two initiatives being delivered:

  1. To broaden its reach and promote more inclusive access to funding, OCHA conducted a comprehensive capacity assessment to identify strengths and gaps among both existing and potential national partners. Many of the NGOs then received targeted support to meet eligibility requirements and were subsequently onboarded as LHF partners, contributing to a more diverse and representative partner base. The assessment targeted 73 NGOs (40 new and 33 for re-assessment) focusing on those that had not received funding in the past three years or whose eligibility had expired. Of these, 31 passed the initial screening and underwent a full assessment, which included a review of internal structures, policies, and field visits. 15 NGOs then became eligible for funding. NGOs that did not pass received detailed feedback and may reapply after one year.

  1. Throughout the project cycle, OCHA implemented a follow-up support mechanism to national NGO partners, addressing challenges related to project development, reporting, activity monitoring, coordination with sectors, proposal revision and financial tracking. This sustained engagement strengthened the operational capacity of local organisations.

Both of these initiatives have been critical in supporting the localisation agenda. Currently, 96 NGOs are eligible for LHF funding, 52% of which are national NGOs. In 2024, 42% of LHF funds were allocated to national and local NGOs, 38% directly and 4% indirectly. This narrowly missed LHF’s target to allocate 45% of funding to local organisations, largely due to the need to channel funding to larger organisation with extensive capacity and experience to adapt to the conflict context. Furthermore, although the 42% allocation is only a marginal increase from the 39% allocated to national and local NGOs, the volume of funding to these organisations increased substantially given the overall allocation amount was $65.6m in 2024 compared to $26.1m in 2023.

Output 4.2 measures the number of (i) partner staff and community stakeholders benefitting from training on emergency preparedness and response and (ii) people reached with key messages on Explosive Ordnance Risk Education (EORE). During the reporting period, this indicator met the expectations. The quality of the training and its relevance for (or its application by) participants is not captured by the indicator.

For indicator 4.2 (i) UNICEF carried out a series of capacity-building activities and training sessions to strengthen the skills of first responders and frontline workers. These efforts aimed to ensure that humanitarian aid is delivered in a safe and respectful manner, while also reducing protection risks and promoting inclusive support systems during emergencies. By equipping these workers with essential knowledge, UNICEF sought to minimise the chances of exploitation and abuse and improve their accountability to the communities they serve. 1,138 people were reached - 50% of the initial target - but the focus on cascading knowledge and skills to community members by master trainers resulted in 12,940 community members reached.

For indicator 4.2 (ii), UNICEF partnered with the Lebanon Mine Action Centre (LMAC) and Mines Advisory Group (MAG) to deliver 590 face-to-face EORE sessions, reaching 13,691 individuals, overachieving the original target of 10,500 individuals. Throughout the programme, EORE information, education, and communication materials were disseminated to children, caregivers, and community members. All training materials adhered to International Mine Action Standards and were adapted to be child-friendly, ensuring accessibility and impact. The target was overachieved due to the high demand by the targeted population for these sessions. Thus, UNICEF and its implementing partners scaled up the delivery of EORE sessions and supplemented training opportunities with online sessions for some inaccessible localities. To assess effectiveness of the EORE interventions, UNICEF and MAG conducted pre- and post-session surveys, revealing that 87% of participants showed improved knowledge, and 95% reported feeling safer.

Another critical activity delivered through UNICEF was mine clearance operations in West Bekaa through MAG in coordination with LMAC. A total area of 178,723 square meters was cleared, 1,407 hazardous items were detected and destroyed, and 2,286 individuals directly benefited from the Explosive Ordnance Disposal activities (607 girls, 657 boys, 488 women, and 534 men).
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to the output description. Indicator 4.1 was redrafted to be more aligned with LHF framework. Indicator 4.2 was added to reflect new humanitarian mine action activities under the programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous Annual Review is outlined below:
2024 Recommendation	Progress
It would be a valuable exercise for LHF to develop trend reports on findings from monitoring to inform future programming. While this is done informally, more regular analysis of monitoring findings at an overall fund level could help inform both LHF and sectors-level planning and partner engagement.	Deprioritised due to the exceptional circumstances during the reporting period. This should be considered for 25/26.

Lessons learned for this output are:

EORE and demining efforts are effective during heightened conflict. Continued advocacy for Lebanon’s inclusion in the FCDO Global Mine Action Programme (GMAP) remains a priority even if crisis-related funding at BEB is no longer available for support to demining activities.

Recommendations for this output are:

Through Advisory Board membership, FCDO should actively promote localisation by engaging further with LHF local NGOs partners, ensuring their perspectives and concerns are meaningfully represented and integrated into decision-making processes.
## D: VALUE FOR MONEY

Key cost drivers and performance

FCDO uses the ‘5 Es’ framework (economy, efficiency, effectiveness, equity and cost-effectiveness) to ensure that UK Aid maximises impact. Considerations against the 5 Es and examples of good practice for this programme are set out below.
Economy
- The LHF maintained a staffing cost plan of just 1.9%, well below the country-based pooled fund average of 5%.
- IOM maximised transport efficiency by deploying high-capacity buses at no additional cost.
- UNICEF leveraged long-term agreements and local procurement to reduce costs. A cost analysis led to the adoption of the Primary Healthcare Services Unit (PSU) model within the UNICEF programme, delivering comprehensive healthcare at just USD 4,000 per unit.
- ILO benchmarked all costs against market rates.
Efficiency
- LHF’s direct engagement with partners and in-person monitoring enhanced oversight and reduced reliance on third-party services.
- UNICEF merged staff roles and expanded shifts in Makani shelters located in safe areas to maintain services for displaced children.
- WFP’s structural review redirected savings to beneficiaries.
Effectiveness

- Programmes were responsive, and results driven. LHF’s RAs enabled rapid emergency response.
- IOM’s co-leadership in the shelter sector and use of the Displacement Tracking Matrix data improved targeting.
- Makani centres continued to deliver education, protection, and psychosocial support despite crisis conditions.
Equity
- LHF prioritised localisation, ensuring national NGOs, including those focused on women’s needs, disability, and LGBT+ rights, had direct access to funding.
- Makani centres exceeded inclusion targets, with girls comprising over 50% of participants and children with disabilities reaching up to 8% in some areas.
- ILO supported national systems targeting the most vulnerable.
- Gender-segregated, disability-accessible WASH facilities, dignity kits, and virtual safe spaces funded through UNICEF further supported equitable access to services.
Cost-Effectiveness

- Integrated service delivery models significantly reduced per-beneficiary costs. Makani’s multi-sectoral approach brought the cost per child down from $2,000 under previous child protection and NFE programming to $375.
- WFP’s large-scale cash assistance benefited from economies of scale, reducing per-person costs.
- Local procurement and pre-positioning of supplies minimised logistics costs and enabled rapid deployment during crises. Youth-led initiatives and mobile outreach further reduced overheads while expanding reach in hard-to-access areas.
- Supporting preparedness proved to be highly cost-efficient in several ways. UNICEF’s strategic pre-positioning of essential supplies such as hygiene kits, dignity kits, medical items, nutrition supplies and educational materials enabled rapid response to displacement and conflict escalation, thereby avoiding the inflated costs and delays of emergency procurement during crises. Additionally, sourcing and warehousing these items locally reduced transportation, customs, and logistics costs compared to international procurement, while simultaneously boosting the local economy. The availability of pre-positioned contingency stocks ensured immediate deployment during emergencies, maintaining uninterrupted service delivery and eliminating the need for costly last-minute interventions or parallel systems.
Assessment of whether the programme continues to represent value for money.

77. The programme represents value for money as outlined by the above examples and by proving to be an effective response mechanism for the UK’s humanitarian response to the conflict escalation. However, as outlined in the previous Annual Review, it is essential that value for money indicators are developed to enable more robust assessment and benchmarking. This was deprioritised last year due to the conflict.

E: RISK

Overview of risk management

The overall risk rating for the programme remains moderate, though the risk profile has been elevated at several points throughout this reporting period.

The programme risk register was updated to reflect significant changes in the operating context including escalation of conflict, mass displacement, deterioration in the security environment affecting access and FCDO staff restrictions, the fall of the Assad regime, international funding cuts in early 2025 and the formation of a new government. The primary focus of mitigating efforts was on managing the UK’s humanitarian crisis response to the conflict, managing operational pressures and challenges, and adapting to changes in the context such as the arrival of new refugees from Syria.

Routine risk management structures and governance such as the BEB Delivery Board were disrupted due to repeated and prolonged periods in crisis mode, but risks were actively managed through regular team engagement, coordination crisis structures within BEB and with HQ, and via UK membership of the HCT.

Key risks and mitigations are summarised below:
Risk Category	Risk Description	Mitigation Strategy	Residual Risk
Strategy & Context	Breakdown of ceasefire leads to renewed conflict escalation, creating additional needs and access restrictions. These restrictions may hinder the ability of implementing partners to reach people in need and impact on overall project delivery	Partnerships with organisations experienced in crisis response and in Lebanon. Strong coordination with OCHA, UNIFIL, UNRWA and others to address access constraints, adapt responses, and include preparedness measures for potential escalations. Ongoing advocacy to raise awareness and secure additional funding to meet growing needs.	Severe
Strategy & Context	Internal and cross-border population movement between Syria and Lebanon increases following the fall of the Assad regime and recent escalation of violence in Syria posing operational challenges for humanitarian agencies, requiring simultaneous efforts to support ongoing displaced and assist new arrivals fleeing instability.	Sustain active engagement with the GoL, the Disaster Risk Management unit, OCHA, UNDSS and the UK Office for Syria in addition to ongoing participation in HCT meetings to support preparedness planning.	Major
Strategy & Context	Increased anti-refugee and anti-UK rhetoric leads to restrictions on service delivery for refugees and inability of humanitarian partners to deliver services to vulnerable refugee communities and affects overall programme impact.	The UN engages with government, civil society, media, and communities to explain its mandate, promote humanitarian principles, and address concerns. Political advocacy is coordinated with partners to influence policy and rhetoric. Efforts are made to enhance public understanding of humanitarian work through media and events, while programme results are communicated to highlight positive impacts on both Lebanese and refugee populations.	Moderate
Strategy & Context	Recent changes at political level, including election of president and PM, and formation of new government cause delays and change in vision and priorities affecting UK policy and programming. A potential change in technical counterparts (advisors) in ministries causes changes in the approach to ongoing work. Key ministries allocated to LH affects UK ability to engage.	Continued engagement with technical counterparts to maintain strong relationships and ensure shared priorities Ongoing monitoring and adaptability to ensure programming responds effectively to the evolving political and operational context.	Moderate
Policy & Programme Delivery	Reduce donor funding, including because of US funding pause, leads to increase in overall vulnerability and impacts achievement of programme objectives.	Ensure partners have strong strategies to reach the most vulnerable and maintain regular, coordinated communication with donors on contextual changes. Act as an active member of key coordination bodies (Donor Working Group, HCT, Lebanon Donor Cash Forum) to promote donor collaboration, efficiency and reduced duplication. Highlight the impact of the US funding pause on humanitarian needs in Lebanon to inform internal decision-making and funding strategies.	Moderate
People	FCDO does not have adequate capacity to manage the programme due to staffing reductions and/or movement limitations, which limits our ability to monitor delivery, manage risk, and ensure value for money.	Ensure continuity plans in the event of staff drawdown or disruption due to crisis. / Request monitoring information from other donors. Engage with HQ discussions of development capability and workforce planning. Advocate for development capability in country due crisis mode. Pursue multiple options on advisory capacity including programme-funded surge support. Consider field visits within Beirut to minimise operational burden.	Moderate

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The activities delivered during the reporting period were governed through the following arrangements:
- LHF – MoU with OCHA
- Safe project and Flash Appeal – two MoUs with IOM
- Cash assistance for Syrian refugees and Lebanese – two Contribution Arrangements with WFP, drawing on the centrally agreed Framework Agreement between FCDO and WFP
- Social protection TA – MoU with ILO
- Makani and Preparedness – two Contribution Arrangements with UNICEF, drawing on the centrally agreed Framework Agreement between FCDO and UNICEF

Budget and spend for FY 24/25 is set out below. There was a minor overspend of £47,214, representing 0.08% of the total budget, well within the allowable 1% variance.
Component	Budget Allocation FY 24/25	Actual Spend FY 24/25
OCHA / Contribution to LHF	£4,500,000	£4,500,000
WFP / Cash contributions to Syrians	£25,000,000	£25,000,000
WFP / Cash contributions to Lebanese	£6,000,000	£6,000,000
ILO / Social Protection	£500,000	£500,000
IOM / Safe project	£1,000,000	£1,000,000
IOM / Flash Appeal project	£2,040,000	£2,040,000
UK-Med / EMT	£927,587	£927,587
UNICEF / Makani	£4,500,000	£4,500,000
UNICEF / Preparedness and Response	£11,420,000	£11,420,000
HSOT	£112,413	£159,627
Total	£56,000,000	£56,047,214

Delivery partners demonstrated strong performance against their agreed target and responsiveness to operational challenges. Narrative and financial reports were submitted on time and engagement through quarterly meetings and advisory boards enabled regular dialogue on delivery progress, risk mitigation and strategic alignment. Across the portfolio, partners demonstrated a commitment to gender equality and inclusion, with disaggregated data and inclusive approaches.

However, some challenges remain. Suggested improvements for some of the partners are as follows:
- OCHA/LHF: The LHF Advisory Board (AB) is designed to allow oversight on decision making and shaping allocation objectives and decisions. As it stands, the AB acts as more of an information sharing forum. Going forward, FCDO should work with other LHF donors and OCHA to consider how the governance function of the AB and ability to meaningfully influence strategies and decisions can be improved in line with the Humanitarian Reset.
- WFP: WFP should ensure that FCDO is consulted on any significant changes to the planned programme and ensure that any operational challenges are communicated in a timely and transparent manner. FCDO should also engage with central leads to push for more detail to be required in WFP’s financial reports During the reporting period, FCDO requested a specialised financial report (for a fee of $20,000); however, the level of detail provided did not offer significant added value beyond existing reports.
- UNICEF: Some challenges faced by UNICEF were only discovered by FCDO during field visits, rather than being communicated in a timely manner by the partner. Similar to WFP, UNICEF should proactively notify/consult FCDO on significant changes to the programme and contextual challenges. UNICEF’s reporting should also include explanations for variances between targets and results.
- ILO: ILO should work more collaboratively with its donors to ensure collective ownership, accountability and decision making. ILO could also consider how to better communicate its contribution to national social protection system strengthening to a wider audience including GoL.

The LHP team should also engage with central institutional leads to establish clear requirements for programme management where these are not covered in central Framework Agreements, e.g. in relation to the level of detail required for budgets and delivery chain maps.

At times FCDO requirements, processes and ways of working put additional pressure on partners e.g. through separate successive uplifts which created disproportionate programmatic demands. The addition of new activities and agreements also strained existing programme management and team capacity. Caps on the number of BEB staff in Beirut and rotational arrangements due to the security situation hindered the team’s collaboration by requiring extensive hybrid working and limited ability to engage meaningfully with GoL on response efforts, attend key external meetings and conduct monitoring visits.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Programme progress was reviewed through regular engagement with partners and quarterly or bi-annual reporting (depending on the agreement type and duration). Key milestones were initially reviewed against logframe targets; however, due to the conflict escalation, the rapid expansion of the programme, the evolving response and subsequent pressure on the team, updates to the logframe to reflect new targets and indicators were significantly delayed and, in some instances, inaccurate (this was particularly the case when the UNICEF preparedness grant was uplifted in December 2024).

While some monitoring visits were undertaken, including to collective shelters during the conflict escalation, FCDO’s ability to conduct regular field visits was negatively impacted by the conflict, changes to UK Travel Advice in Lebanon and the resulting BEB security posture. Overall monitoring was also impacted by the absence of an LHP M&E strategy. It is recommended that a strategy is developed as soon as possible to ensure adequate coverage of projects and locations so the programme team can gain critical insights into delivery on the ground and triangulate written reports from partners.

Evidence

No evaluation is planned for LHP overall and there have been no implications for the programme of developments in the broader evidence base underpinning the interventions. Following the ceasefire, lessons from the crisis response were captured by the HCT, including the need for increased preparedness efforts and an improved shelter strategy. As referenced under the narrative for Output 1, an evaluation of IOM’s protection programming for 2022-25 was carried out and the findings will inform Phase 2 of the Safe project. It is recommended that next year’s Annual Review captures all project-level studies and evaluations including those funded by other donors.

Learning

Key lessons identified through LHP over the past year have been outlined in the output sections and the summary section.
Date of last narrative financial report	OCHA LHF Annual Report 2024 – May 2025 / IOM Final narrative and financial report – July 2025 / WFP Final narrative and financial report – June 2025 / ILO Final narrative and financial report – May 2025 / UNICEF Final narrative and financial reports – June 2025	Date of last audited annual statement	All audit reports are shared at HQ level for UN partners.

Annex A: Theory of Change