## Annual Review

Title: Investments in Forests and Sustainable Land Use – Phase 2 (IFSLU2)
Programme Value £ (full life): Up to £500m		Review date: 14/12/2025
Programme Code: 301321	AMP start date: 14/12/2023	AMP end date: 31/12/2034

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Log frame

A. SUMMARY AND OVERVIEW

Description of programme
A new approach to land use needs to be at the centre of efforts to realise the Sustainable Development Goals (SDGs) and the Paris Agreement targets. Neither can be achieved without a shift in land use and food production to meet the needs of a growing population, reduce greenhouse gas emissions and protect the ecosystems and natural resources (fresh water, soil, biodiversity) which sustain life.
Investments in Forests and Sustainable Land Use Phase 2 (IFSLU2) seeks to mobilise private sector investment into forest protection and restoration, address deforestation associated with agricultural commodity production, scale up support to smallholder farmers and support jobs and strengthened livelihoods in poor rural communities. The programme builds on a successful first phase (£140m, 2015-24) which has provided proof-of-concept and an evidence base to inform the scaling-up of activities. Delivery contributes to the UK development policy goal of a world free from poverty on a liveable planet, working in partnership with business and civil society groups to mobilise investment that enhances smallholder livelihoods, drives green growth, protects and restores forests.
The programme business case sets out five components, with spend set out for the first five years (pending confirmation of Official Development Assistance (ODA) budget allocations to programmes following the 2026-29 Spending Review):
- Component 1: Business incubation and strengthened enabling conditions for investment (£101.5m): Delivered through a service contract to provide grant funding and technical assistance to take innovative and sustainable businesses from early stages of development to financial sustainability and commercially financed scale-up. The contract has been awarded to a consortium led by Palladium International Ltd.
- Component 2: Enhanced support for smallholder farmers (£45.5m): Delivered through grant funding and strategic partnerships, e.g. with IDH, Solidaridad and ISEAL, aimed at developing and implementing approaches to working efficiently with smallholder farmers at scale, to build resilience and engage this key group in efforts to halt and reverse deforestation.
- Component 3: Business and market development in the Congo Basin (£31.5m): Delivered through a service contract to build the enabling conditions, capabilities and structures required for business-led sustainable growth in Congo Basin countries. The contract has been awarded to a consortium led by Palladium International Ltd.
- Component 4: Policy support to catalyse transformational change and action at scale (£10.5m): Delivered through grant funding and strategic partnerships with the World Bank, World Economic Forum (WEF) and Centre for International Forestry Research (CIFOR-ICRAF), to build political momentum, scaling of action, collaboration, knowledge sharing and policy change through global and regional collaboration.
- Component 5: Monitoring, evaluation, learning and knowledge (£6m): Delivered through a service contract to provide independent monitoring and evaluation, supporting learning, adaptive management, programme strategy and a strengthened evidence base for interventions. The tender process for this contract has been paused pending confirmation of ODA budget allocations to programmes.
The scope of the programme and associated funding is now under review following a decision to reduce the UK’s ODA budget from 0.5% to 0.3% of GNI from FY26-27 onwards. A revised programme scope and logframe will be set out once reduced funding has been confirmed under the UK’s new ODA policy.
Summary supporting narrative for the overall score in this review
Two major contracts mobilised, transitioned into delivery and building portfolios of interventions
IFSLU2 was announced at COP28 in November 2023, with funding of up to £500m over a ten-year period. The focus of 2024 (the previous reporting year) was on procurement of contracts, negotiating and signing grant agreements, developing strategy and partnership ideas, mobilising partners, commencing early field activities and taking forward policy engagement and leadership around the aims of the programme.
Procurement of the two main contracts, to deliver Components 1 and 3, was completed in early 2025 (the current reporting year), followed by inception periods to establish the operations, strategies and governance arrangements. Both contracts are now in full delivery, building portfolios of interventions in line with programme strategies, and are on track to meet respective delivery milestones. Management of three grants to scale support to smallholders (Component 2) was handed over to the Component 1 supplier during the inception phase, helping to bring additional rigour to grant management.
Grants to scale support to smallholders achieving results and developing innovative scaling models
The Component 2 grants to support smallholder farmers delivered their first full year of results. The National Initiative for Sustainable Climate-Smart Oil Palm for Smallholders (NISCOPS) project trained over 31,000 farmers and workers across five palm oil producing countries, with particularly strong progress in Nigeria and Indonesia, whilst establishing government partnerships and private sector coalitions that will underpin future scaling. ISEAL expanded its Innovation Fund portfolio to 34 grants supporting 61 organisations with FCDO funding leveraging over £2.5m in match-funding pledges from the private sector and other sources. ISEAL has also consolidated the Living Income Community of Practice as the preeminent convenor on living income issues.
Efforts to scale-up public and private policy action re-established and broadened
A set of partnerships focused on scaling impact (Component 4) complements delivery on the ground through Components 1-3. These partnerships include mobilisation of action to tackle deforestation associated with agricultural commodity industries, engaging through the Tropical Forest Alliance (TFA), the Forests, Agricultural Commodity and Trade (FACT) Dialogue, and the Amsterdam Declarations Partnership (ADP); and mobilisation of finance into forest landscapes, engaging through PROGREEN, the World Bank’s principal programme for supporting governments to advance sustainable landscape management and the development of sustainable forest economies.
Engagement through the ADP has focused on sustaining government cooperation around demand-side policy measures to strengthen markets for deforestation-free agricultural commodities, at a time when concerns about costs and competitiveness are putting pressure on hard-won policy commitments. The FACT Dialogue marked the end of its initial five-year commitment period at COP30 in Brazil, following transition of the co-chair from Indonesia to Malaysia earlier in the year. An evaluation of the first five years highlighted the importance of dialogue and collaboration between producer and consumer countries in the context of current market pressures. This was affirmed through bilateral consultations with key members, highlighting a strong rationale to continue this cooperation beyond the initial five-year commitment period.
Engagement through PROGREEN has supported the establishment of a Liveable Landscape Academy (LLA), which will provide World Bank country teams and client countries with a knowledge platform to convene, share expertise and support a scaling of investments to prevent and reverse land degradation. The academy will launch in 2026, with an initial focus on West Africa and Southeast Asia, providing a basis for future collaboration and learning.
Major lessons and recommendations for the year ahead
Rapid progression into delivery of main contracts and the building of a shared strategy and vision
The inception period for Component 1 has run smoothly, drawing on experience, learning and continuity of key personnel in both FCDO and programme teams. This has facilitated rapid progress on strategy development, including a detailed focus on a revised theory of change and scaling pathways (a key differentiating factor in the transition from Phase 1 to Phase 2). This has also enabled a more rapid progression to the establishment of an initial portfolio, and a strong pipeline for future support.
This experience has also enabled and informed the inception of new operations in the Congo Basin region (Component 3). While Congo Basin operations follow a strikingly different approach to other regions reflecting lessons learned in the first phase, and are delivered by a new team, the inception period for this contract has supported strong progress, drawing on experience of business processes, theory of change, portfolio development and management. This has facilitated a rapid transition from set up and scoping through to the first stages of developing a portfolio.
Although Components 1 (business incubation) and 3 (market systems development in the Congo Basin) are under separate contracts and take different approach, it made sense to brand them under the umbrella of “Partnerships for Forests” (P4F) since this is already recognised among stakeholders and will help to crowd in private sector actors. The programme team and delivery partners should continue to foster join-up between Components on strategy, information-sharing, communications, field missions and stakeholder engagement. This will increase the efficiency of the IFSLU2 programme and help stakeholders to understand the programme as a whole and how best to interact with it.
Delivering on UK development priorities during a period of ODA constraints and policy evolution
There has been a major shift in the global ODA funding landscape in the last year, with significant impacts on delivery partners and programmes. The UK is modernising its approach to development, including by shifting from a donor to a partner and investor. IFSLU2 is well-placed to deliver in this new context, by unlocking private investment. It can also serve to provide technical expertise and confidence to corporates that have committed to addressing their exposure to deforestation and shifting to nature positive models. IFSLU2 can help businesses to maintain momentum in advance of new regulatory frameworks coming into effect in the EU and UK.
The rapid progress of the programme in the last year has taken place despite the context of severe ODA budget uncertainty due to delays in FCDO budget allocation for the 2026-29 Spending Review period. For instance, the procurement of Component 5 (Monitoring, evaluation, learning and knowledge) was paused. This uncertainty can also affect live contracts by delaying decision-making around recruitment and establishment of operations, if these might be at risk of restructuring in the future. It is nevertheless important to provide delivery partners with as much clarity as possible to enable implementation to continue in a no-regrets manner. Going forward the programme should be adjusted, using contract amendments as necessary, in line with forthcoming ODA budget allocations to provide clarity for delivery partners and drive good value for money. This will require the programme logical framework to be updated with revised targets and milestones agreed with partners once budgets are settled.
Building a programme that is more than the sum of its parts
The programme currently operates across multiple components, contracts and grants, each generating valuable insights. Each partner and grantee has its own monitoring, evaluation and learning (MEL) function, but there is limited systematic cross-fertilisation. Procurement of the fifth component – MEL and knowledge at the programme level – is paused until there is clarity on ODA budgets. In the coming year, once budgets are confirmed, the programme team and delivery partners should develop a programme-wide approach to learning and knowledge management. A deliberate approach to learning – with dedicated roles, structured processes and clear accountabilities – would help to ensure that lessons from one part of the programme inform others. This is particularly important given the programme’s theory of change, which depends on synergies between business incubation, smallholder support, policy engagement and market development.
Additionally, the programme team should seek to strengthen integration between programme delivery and policy engagement. IFSLU2’s impact depends not only on successful interventions through Components 1-3, but on how these connect with the public and private policy environment shaped through Component 4 and wider UK Government diplomatic engagement. Building on experience from Phase 1, the programme is designed to enable feedback loops where programme experience informs policy positions, and policy developments shape programme priorities. This includes ensuring that insights on sustainable commodity production from FACT Dialogue engagement, ADP work, and bilateral relationships with producer country governments are systematically fed into programme strategy, and that programme evidence strengthens the UK's credibility in policy forums. It also extends to emerging policy issues such as bioeconomy, brought to the fore by Brazil during its G20 and COP30 Presidencies, on which the programme has deep expertise and networks on which it can draw.
Recognising the success of IFSLU Phase 1, and given the importance of partnership and diplomatic engagement to achieve transformational change, together with the shift towards a new approach to development with closer post engagement with global programmes like IFSLU2, the UK embassy network is keen to collaborate with the renewed programme. Early examples of doing this effectively from across countries in which the programme is being delivered are starting to emerge. The programme should establish effective and efficient ways of working with the network to build and maintain support for the programme as a vehicle for delivering UK objectives in climate, forests and sustainable growth. This also applies to the FACT Dialogue which, although it is a multi-stakeholder initiative, has the potential to support UK partnership objectives around sustainable supply chains and smallholders.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

IFSLU2 aims to shift private sector incentives and practices and catalyse investment in forests and sustainable land use. The theory of change draws from the evidence of successful approaches applied to change private sector practices, and evidence and experience acquired in IFSLU1. New elements added in this second phase of the programme include a strengthened focus on scaling support to smallholder farmers and business and market development in ‘thin’ markets in the Congo Basin, taking into account lessons and addressing gaps identified in Phase 1.

Figure 1 provides a summary theory of change, showing how programme-funded activities through Components 1-4 are expected to lead to outputs, intermediate behavioural outcomes in four domains (demand-side measures, enabling conditions, supply-side support, and policy development & convening), systemic and equity outcomes, and transformational impacts.

Figure 1. Summary Theory of Change for IFSLU2
Changing business-as-usual practice in land use is challenging. The programme theory of change works to shift private sector incentives and practices through market-driven approaches to sustainable sourcing of forest products and agricultural commodities. Programme interventions generate shifts in demand-side market signals; improved enabling conditions for responsible and sustainable investment; better supply-side practices, and support and finance for investments (supply-side measures). These interventions across the full span of markets, supply chains and industries (from upstream to downstream) generate sufficient incentives to change behaviours and practices. Engagement to support scaling, replication and policy reform lead over time towards systemic and transformational change.

Experience of programme delivery over the past year – which has included development of global and regional strategies, wide-ranging consultations with stakeholders and partners across all programme regions, and research into the changing operating context for the programme – suggests that the theory of change remains valid. This conclusion is supported by early results, particularly in the parts of the programme (Components 2 and 4) which have been fully operational over the reporting year, while scoping and strategy development for Components 1 and 3 has brought greater clarity to the theory of change around scaling pathways and market systems development which will be further evidenced as the programme develops.

IFSLU2 will make a ‘significant’ contribution to gender equality in line with the International Development (Gender Equality) Act 2014. A Gender Equality and Social Inclusion (GESI) strategy has been developed to support this and a strengthened emphasis on inclusion of smallholders and marginalised groups. The GESI strategy sets three objectives:
1. Consistently ensuring projects do not unintentionally exclude women and marginalised people.
2. Identifying a subset of commercially viable projects which empower women and marginalised people.
3. Promoting investment in businesses which are aligned with 2X Challenge Criteria.
The 2X Criteria are a global industry standard used to identify investments that support gender equality. They are increasingly being adopted by investors, financial intermediaries and businesses. IFSLU1 opportunistically supported women-led businesses; the 2X Criteria will help the programme take a more structured and deliberate approach and thereby support the overall intended outcome of the programme to mobilise private investment.

Annual outcome assessment
IFSLU2 is on track to deliver the planned outputs (see Section C), and to contribute to expected outcomes and impact.

Justification to continue the programme (own merits and wider portfolio)
There is strong justification to continue the programme. COP30 in Brazil generated new momentum, and there is clear consensus that forests are central to tackling the climate and nature crisis. A commitment to develop a roadmap to halt deforestation in 2026 during the Brazilian COP presidency will bring new focus to these efforts. Within that, shifting private sector behaviours and practices remains the biggest – and most challenging – prize of all.

The UN Environment Programme (UNEP) estimates that annual private finance flows with a direct negative impact on nature are in the region of US$5 trillion. That compares to annual finance flows of US$200 billion into nature-positive practices. Shifting this imbalance, and drawing more private finance onto the positive side of the ledger, is urgent and essential. The Forest Finance Roadmap, published by the Forest and Climate Leaders Partnership (FCLP) at COP30, helps to draw this opportunity into sharper focus. It estimates that mobilising private investment into the forest bioeconomy could generate US$15 billion by 2030; and sustainable value chain finance in major agricultural commodity industries could generate a further US$36 billion by 2030.

Unlocking this potential requires a shift to a new economic model, which balances growth with forest protection, provides economic opportunity and delivers prosperity to the people who live in forest landscapes. IFSLU2 is the primary means through which the UK Government engages on this critical challenge. Phase 1 was set up in 2015 to demonstrate this potential, and Phase 2 is now drawing on this vast learning and experience to scale up action, providing the UK with a means to engage, demonstrate leadership and deliver results.

The value for money case is also strong, closely aligned with the shift in emphasis from donor to investor under the UK’s new policy framework for ODA, and a leading example of using ODA funding to catalyse private sector investment. Phase 1 mobilised private investment of £1.35 billion, at a ratio of £11 for every £1 of UK ODA. The Phase 2 emphasis on scaling impact, drawing on learning and evidence from Phase 1, has potential to achieve similar levels of value for money.

## C. DETAILED OUTPUT SCORING

As illustrated in the Theory of Change (Figure 1), the programme’s four output areas are delivered by separate components. The progress of each component in delivering its output is assessed below.

Output Title	Business incubation, pipeline development & business enabling conditions
Output number:		1	Output Score:	A
Impact weighting (%):		60	Weighting revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of partnerships supported.	Procurement of Technical Assistance supplier to provide business incubation services. / Mobilisation of contract and inception to establish Technical Assistance Facility and set global and regional strategies. / Initial pipeline of Business Incubation (BI) projects identified, screened and assessed for partnership support. / Initial pipeline of Business Incubator and Accelerator platforms identified, screened and assessed for partnership support.	Procurement completed and contract awarded. / Contract mobilised; 6-month inception phase completed and full delivery underway. / Regional project pipelines and portfolios* of BI projects being built and on track to achieve milestones. *The first BI project grants were approved towards the end of the reporting period / Regional project pipelines of incubator and accelerator projects being built and on track to achieve milestones.
1.2 ICF KPI 12 private finance leveraged		Engagement with Investors, Climate Funds and Impact Funds to build future potential investment pipeline. / Too early to report

Overview
This output is focused on supporting businesses with commercial potential to mobilise investment and deliver strong development, climate and nature benefits. Grant funding and technical assistance are used to develop market systems required for businesses to succeed, and to work in partnership with businesses through a managed process of incubation to mobilise investment and ensure financial sustainability.
The focus of the last 12 months has been on procurement of suppliers to undertake this work, the mobilisation of contracts, and their inception through establishment of regional teams and strategies across regions. Following inception, delivery teams have moved rapidly into implementation, building portfolios of projects aligned with their strategies. In parallel, climate events (e.g. London Climate Action Week, Africa Climate Week) and COP30 have been used to engage potential partners and investors.
Mobilisation
The reporting year saw the completion of a procurement exercise to identify an organisation or consortium capable of providing support to deliver Components 1 and 2, including support for business incubation and management of grants to support smallholder farmers.
Following submission of bids in October 2024 preferred bidders were selected and the contract commenced on 1st February 2025. The selected contractor, Palladium International, and its sub-contractors Systemiq and Efeca, bring a wealth of relevant expertise and experience, including from IFSLU Phase 1.
A six-month inception phase was conducted for operational set-up including recruiting and establishing expert local teams across five tropical forest regions, plus a global management and monitoring team based in the UK. These teams engaged extensively with stakeholders (including FCDO embassy networks), conducted in-depth research, and developed ambitious, context-specific strategies that reflect both the opportunities and challenges faced in each region and globally.
The inception phase produced several programme documents, controls, templates and tools including: updated Theory of Change, MEL and GESI strategies, results framework, grant management procedures, risk register, performance management dashboard and work plan. These provide a solid foundation on which to progress into delivery.
Reflecting the increased ambition of IFSLU2, strategy development resulted in four core scaling pathways that will be applied to support scaling and replication of successful models, interventions, or innovations to achieve greater reach, impact, and sustainability. These pathways are:
1. Build the ecosystem for regenerative and inclusive markets
2. Strengthen the policy environment
3. Scale access to finance and new revenue streams
4. Harness technology and data to drive scale.
One of the lessons from P4F Phase 1 (2015-2023) was the need for a deliberate approach to scaling impact for smallholders (the focus of Output 2). The need for market-connected, climate-resilient approaches that benefit smallholder farmers is also reflected across the regional strategies and operational plans of the business incubation TA facility (the means to deliver Output 1). This integrated approach ensures that smallholder considerations are not siloed but are embedded across the programme’s design, delivery and impact measurement.
Delivery
The contract moved into implementation in August 2025 under the external-facing title of Partnerships for Forests (P4F), which will help to re-engage stakeholders that were involved in P4F Phase 1. Regional teams have moved rapidly to mobilise the TA facility: identifying, screening and developing portfolios of projects for grant and technical assistance support. The early project pipeline is provided in Table 1, along with the main scaling pathway fostered by each.
Table 1. Early project pipeline (subject to final agreement)
Region	Project	Main scaling pathway
Latin America	Catalytic Capital for the Agricultural Transition in Brazil fund (CCAT)	Scale access to finance
Latin America	Beef on Track, Brazil	Build the ecosystem
West Africa	Agroforestry Finance Catalyst Initiative (AFCI) for increased lending to forest friendly businesses in WA	Scale access to finance
West Africa	S-Palm+ Smallholder Organic Oil Palm Production for Climate Smart Agriculture in Sierra Leone	Build the ecosystem
East Africa	Sustainable Forestry and Manufacturing (S-FORM) Facility	Scale access to finance
East Africa	Establishing Forested’s Ingredient Insetting Model	Build the ecosystem
Southeast Asia	Supporting Asia Climate Landscape Fund (ACLF) to scale	Build the ecosystem
Southeast Asia	KADIN Regenerative Forest Business Hub & Multi-Use Forestry Taskforce	Strengthen policy
Cross-cutting	Amsterdam Declarations Partnership (ADP)	Strengthen policy
Cross-cutting	UK Sustainable Commodities Initiative (UKSCI)	Strengthen policy

These projects range from initiatives that enhance support for smallholders – such as improving access to finance and technical assistance – to those that facilitate work with funds to unlock catalytic capital. This demonstrates a strong and productive start to delivery of programme activities.
Field visits were undertaken by the FCDO programme team to monitor progress and engage stakeholders during inception and early implementation including to Indonesia in April 2025 and Kenya in November 2025. Regular discussions have been established with relevant embassy teams and programmes, including Mobilising Finance for Forests, to ensure coordination and avoid duplication of effort.
Opportunities have been taken to leverage key stakeholder events including African Climate Week, London Climate Action Week and UNFCCC COP. The Latin America regional strategy was launched and discussed with relevant stakeholders attending COP30 in Belém, with two projects being announced for support. The global strategy was launched and discussed with stakeholders from corporate, investment and non-profit sectors at a well-attended event in London in November 2025, and the West Africa regional strategy was launched in Liberia in early December 2025.
The contract is judged to be on track to deliver its target milestones. This Annual Review does not provide a quantitative assessment of output results since much of this reporting year has been devoted to procurement, mobilisation and inception.
Lessons identified
Despite global political headwinds, the inception and early implementation phases of the contract have demonstrated that there is still a strong demand for forest partnerships that de-risk private investment and create shared value for stakeholders.
Lessons learned during P4F Phase 1, combined with stakeholder consultation, were used to develop robust regional strategies. These were used to stimulate lesson-sharing and collaboration on important themes. For instance, the Latin America team hosted a roundtable on land restoration that brought together strategic stakeholders to discuss the main barriers faced by the sector and collectively build pathways to transform the native forestry industry into a competitive driver of the Brazilian forestry economy. The Southeast Asia team and Efeca supported the successful delivery of a Nature Positive Trade Event, hosted by the Indonesian Embassy in London in collaboration with the British Chamber of Commerce. The event served as a platform to promote Indonesia’s sustainable commodities and strengthen UK market linkages. P4F’s GESI strategy was presented at a UNEP Land Use Finance Roundtable in Amsterdam, receiving positive feedback from global stakeholders.
Since the first phase of the programme there has been an expansion of incubators and accelerators, which is a positive trend. Therefore, in this second phase the programme has needed to adapt, with the strategy now including more activities to build a wider ecosystem of instruments and programmes to support forest positive investment. One approach is to provide technical assistance to incubators to help them learn from the programme (including lessons from the first phase of P4F). This ‘incubating incubators’ approach can have a catalytic effect in the sector, multiplying programme impact, but it also requires care to minimise layers of management costs and ensure good value for money. This will be monitored during delivery.
Recommendations
1. Provide regular updates to the FCDO embassy network to enable input from country offices, support stakeholder engagement, maximise the value for money from a more limited ODA budget, and ensure tailoring to political and economic contexts.
2. Seek opportunities to partner with other UK forest programmes, including Mobilising Finance for Forests (MFF); Forests, Governance, Markets & Climate (FGMC); UK Partnering for Accelerated Climate Transitions (UK PACT); and Accelerating Innovative Monitoring for Forests (AIM4Forests). This could include sharing information on project pipelines; developing a shared understanding of key topics (e.g. carbon markets for commodity supply chains); greater information sharing at a country or regional level, including through Posts; identifying barriers where the levers to support unblocking sit in another programme; and leveraging complementary skillsets (e.g. around innovative finance and technology).

Output Title	Smallholder support and capacity: Increased support and enhanced access to finance for smallholder farmers, to support a transition to sustainable practices
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of farmers supported (ICF TA KPI 2)	Number of farmers and workers (including processors) trained (NISCOPS)	31,094 (15,547 attributable to FCDO contributions)

Overview
Component 2 represents IFSLU2’s dedicated response to smallholder inclusion in agricultural commodity value chains, with Output 2 focused on scaling up support to smallholder farmers to enhance their livelihoods, build their resilience and engage them in efforts to protect and restore tropical forests.
In 2024, three grants were signed for two initiatives to establish the Component 2 portfolio, all of which have now completed their first full year of implementation. Component 2 grants are supporting the following initiatives:
- National Initiative for Sustainable Climate-Smart Oil Palm for Smallholders (NISCOPS), implemented jointly by IDH and Solidaridad and co-funded equally with the Netherlands, focuses on supply-side sectoral transformation of palm oil production across five producing countries (Indonesia, Malaysia, Ghana, Nigeria and Colombia), and demand-side market interventions in the key markets of India, Asia and Europe.
- ISEAL Alliance’s workstreams related to smallholder and cross-commodity sustainable supply chains through four workstreams: an Innovation Fund (co-funded with Switzerland/SECO), the Living Income Community of Practice, supporting smallholder-inclusive jurisdictional approaches via landscape practitioner networks, and technical assistance to support smallholder inclusion in company value chains.
Component 2 grants delivered their first full year of results in the current reporting period. NISCOPS trained over 31,000 farmers and workers across five palm oil producing countries and brought over 62,000 hectares under sustainable management. Government partnerships were established and private sector coalitions convened, including with major traders committing to deforestation-free supply chains in Indonesia, and six companies signing the India Sustainable Palm Oil Manifesto. Although progress was slower than expected, implementation began to accelerate in 2025 as government partnerships became operational, and substantive outputs are now materialising. The NISCOPS approach, with implementation set around cooperation agreements with partner governments, is different to the approach applied elsewhere across the programme, which is more explicitly focused on partnership with the private sector. Cooperation with government provides the NISCOPS intervention with a closer focus on policy change to enable scaling, with potential to learn from this and apply to other elements of the programme over time.
ISEAL expanded its Innovation Fund portfolio to 34 grants supporting 61 organisations, and consolidated the Living Income Community of Practice to become the preeminent global convenor on living income issues, growing to over 3,500 subscribers. Both initiatives also delivered notable technical outputs, including EUDR-compliant traceability platforms in Colombia and Indonesia, and revised Chain of Custody guidance that reduces logistical burdens for smallholder products.
Alongside delivery, Component 2 navigated a period of transition and uncertainty in 2025. As flagged in last year’s review, management of Component 2 grants transitioned from FCDO to Palladium under the Component 1 contract. This was completed smoothly, with new responsibility and reporting structures continuing to bed in. Relations between NISCOPS implementing partners have strengthened, with improved collaboration and joint planning. Budget pressures required consultations with grantees on the possibility of reducing funding envelopes, and IDH, Solidaridad and ISEAL have all responded constructively. Management of budget pressures has also required liaison with some UK posts, to manage relationships with partner governments and co-donors. The need for this liaison and relationship management will continue into 2026.
Mobilisation of future smallholder-focused work within Partnerships for Forests structures commenced but was paused pending clarity on the programme’s overall ODA settlement, with the aim of protecting operational grants to the maximum extent possible. Against this backdrop, going into 2026 the FCDO team is taking stock of Component 2’s strategic direction and identifying how to strengthen integration between policy engagement and programme delivery on smallholder issues, and how to establish systematic learning mechanisms between Component 2 grants and P4F investments.
NISCOPS Results and Progress
2024 Results
NISCOPS delivered its first full year of results in 2024 (the most recent figures available for the current reporting period). Programme-wide results for the calendar year included:
- 31,094 farmers and workers trained (25% of 2028 target of 126,784 people)
- 62,752 hectares of farmland brought under sustainable management practices (12% of 2028 target of 513,500 hectares)
- 16,270 hectares of forest under protection arrangements (3% of 2028 target of 496,546 hectares)
- 748 people with improved income/improved yield (0.6% of 2028 target of 121,725)
- 32% of people supported by the programme in 2024 were women (9,881 individuals)
Results from supply-side activities varied significantly. The most farmers were trained in Nigeria (14,232), followed by Indonesia (7,807), Malaysia (7,370), Colombia (1,527) and Ghana (158). Other highlights included:
- In Indonesia, NISCOPS convened major palm oil traders (including Wilmar, Musim Mas, Mars, Mondelez, Nestlé, Unilever, PepsiCo) who committed to work toward deforestation-free supply chains. IDH also supported the Ministry for Economic Affairs to develop a traceability system linking land registry, sales and tax data to support EUDR compliance. Solidaridad trained over 2,500 farmers, established 128 Training of Trainers facilitators, and secured three social forestry permits covering 7,547 hectares in Kalimantan.
- In Malaysia, the programme established governance structures with the Malaysian Palm Oil Board, launched a Deforestation Monitoring Taskforce and initiated a partnership to strengthen smallholder inclusion in the national sustainability standard with JAKOA (the government agency overseeing affairs of indigenous Orang Asli communities).
- In Nigeria, 49 Community-Based Forest Management Committees were established across four states and 276 community dialogues on sustainable practices were facilitated. The Okomu Smallholder Project commenced with 3,000 seedlings planted in High Conservation Value areas.
- In Ghana, Village Savings and Loan Associations were introduced with 158 livelihood applications received (67% from women). A bamboo cultivation pilot mobilised 414 farmers, and a collaboration was formed with mining company AngloGold Ashanti to restore degraded land for oil palm cultivation.
- In Colombia, the APSColombia (Sustainable Colombian Palm Oil Corporation) Digital Platform for EUDR compliance became fully operational.

Demand-side work generated several results. In India, IDH launched the India Sustainable Palm Oil Manifesto at the SUTRA Summit, signed by six major companies committing to scale responsibly sourced palm oil. In Europe, IDH and Solidaridad co-hosted side events on smallholder-inclusive sourcing at the Sustainable Palm Oil Dialogue (Brussels) and RSPO Roundtable (Bangkok). In Asia, IDH convened discussions with palm oil traders on EUDR solutions, sharing learnings with the Vietnamese coffee sector to inform national monitoring systems in Indonesia and Malaysia. There is now good potential to build collaboration between demand-side engagement in Asia and the UK Sustainable Commodities Initiative (UKSCI), which is the principal platform for engagement with the UK market for sustainable palm oil.

2025 Progress
Throughout 2025, NISCOPS accelerated implementation with the private sector as government partnerships became operational. In Indonesia, IDH finalised a €1.4 million co-funding agreement with two commodity companies (GAR and Mondelez) for farmer capacity building across Aceh and North Sumatra, training 6,000 additional farmers in Q3 alone and supporting 2,100 farmers toward certification readiness. In Colombia, the programme secured US$150,000 from &Green’s Technical Assistance Facility to design financing models for carbon capture under a sectoral Carbon Neutrality Roadmap, including mechanisms to bring smallholders into carbon schemes. In India, draft sustainability criteria for domestic palm oil were finalised and tested with industry, marking progress toward India’s first sector-wide sustainability framework. In Europe, Solidaridad published the Global Palm Oil Barometer with attention from approximately 50 media publications globally. Full results from 2025 will feature in the 2026 Annual Review, given the time-lag in the reporting cycle.

Comment on NISCOPS Results and Progress
Overall progress on output-level training targets was strong for the first year of full operation. Progress towards outcome level results was more mixed with reasonable performance on sustainable land management, minimal progress on forest protection, while better income results lagged significantly. Weaker progress towards these outcome-level results reflects both the early stage of the programme and delays in baseline data collection. Implementation was generally slower than anticipated in 2024, because delays in establishing government partnerships hampered progress, and staff recruitment gaps following the transition from Phase 1 to Phase 2 meant several country teams did not reach full capacity until mid-2024. Progress on output and outcome level results is expected to accelerate in the year ahead.

ISEAL Alliance: Results October 2024-September 2025

ISEAL performed well in delivering its mandate to identify, pilot and scale promising approaches for smallholder inclusion across its four workstreams.

- Innovation Fund: The Fund grew significantly with 22 new grants awarded, taking the total to 34 grants supporting 61 organisations. Two funding rounds were launched: Round 7 on future-proofing sustainability systems, and Round 8 on market mechanisms for transferring value to small-scale producers. Round 7 relaxed eligibility to allow non-ISEAL members to lead projects (provided an ISEAL member is a formal partner), doubling applications from 12 to 24.
- Living Income Community of Practice (LICOP): LICOP consolidated its position as the preeminent convenor of the living income agenda, growing to over 3,500 subscribers and delivering 26 events with approximately 1,000 participants. Technical outputs included guidance on gender equality and living income, and principles for aligning procurement with living income goals.
- Landscape Approaches: In collaboration with 19 organisations, ISEAL launched the Core Criteria for Mature Landscape Initiatives position paper to create a simple and consistent understanding of ‘landscape initiatives’. These criteria have since been adopted and embedded in a variety of landscape platforms (e.g. SourceUp and LandScale) and adopted by the Taskforce on Nature-related Financial Disclosures (TNFD) and the Science Based Targets Network.
- Technical Support: ISEAL published revised Chain of Custody guidance incorporating emerging models such as Controlled Blending and Controlled Mass Balance, which reduce logistical burdens for smallholder products.
Comment on ISEAL Results
ISEAL performed well in 2024, demonstrating particular strengths in managing and expanding the Innovation Fund’s reach, and convening LICOP. Indeed, the effectiveness and strategic importance of ISEAL’s work in these two areas was highlighted in an ISEAL/FCDO-commissioned independent midline assessment that surveyed the ISEAL membership. Since project start, £2,268,121 in FCDO contributions to the Innovation Fund have leveraged £2,241,359 in pledged funding from private sector and other sources, which is very promising. However, two areas of the Innovation Fund warrant monitoring and attention. Firstly, the conversion of pledged funding into actually committed funds has been weak, only 9.6% (£215,554) of pledges have materialised to date. Secondly, an independent mid-term evaluation commissioned by Switzerland (October 2025) found limited evidence of innovations being scaled, replicated or adapted beyond original grantees. Further attention on mainstreaming and cross-pollination will be required.
Design and Mobilisation of Remainder of Component 2
The degree to which it will be possible to implement Component 2 activities to the full extent envisioned in the business case will depend upon the confirmation of ODA budgets and the extent of cuts required. Planning for a range of scenarios is ongoing and the scale, shape and direction of future Component 2 activities will be further developed and mobilised in early 2026, with adjustment to logframe targets and projected results as required.
A further priority for next year will be developing integrated mechanisms for collaboration and learning between NISCOPS, ISEAL and Palladium. The existing Component 2 grants can be viewed as ‘learning assets’ offering value not only in results delivered directly, but in insights that can inform P4F activities.
Lessons identified
- Government partnerships are essential but take time to build. The legitimacy and sustainability of NISCOPS work depends on formal government partnership arrangements, which took longer to establish than anticipated. Once operational, these partnerships enable accelerated implementation, but country projects need to allow realistic timelines for government engagement.
- Private sector co-investment signals commercial viability. The €1.4 million co-funding agreement secured from GAR and Mondelez in Indonesia demonstrates that well-designed smallholder support programmes can attract commercial investment. Companies investing their own resources in this way suggests NISCOPs approaches have genuine business value. Future programming should monitor private sector co-investment as an indicator of sustainability and scalability potential.
- Scaling pathways for smallholder inclusion remain a collective challenge. Both NISCOPS and ISEAL generate promising approaches at project level, but mechanisms for translating these into broader uptake are so far underdeveloped. The value of supporting NISCOPS and ISEAL in tandem with P4F lies partly in pooling efforts towards the collective endeavour of advancing smallholder inclusion: testing approaches, learning what works, and sharing insights.
- Capture opportunities to enhance learning. The programme has an opportunity to enhance learning through development of strengthened mechanisms to share lessons from Component 2 grants to inform other programme components. Plans are in development to put this into practice in 2026.
Recommendations
1. Develop an integrated learning strategy for smallholder work across all components, through developing a strategy encompassing all programme components. This would help to maximise learning in relation to smallholders across the full scope of the programme, strengthening evidence and informing future work. The practicalities of implementing this should be developed in consultation with delivery partners to ensure buy-in and feasibility.
2. Articulate a realistic smallholder strategy for P4F. Work with Palladium to develop a clear strategic framework for smallholder work within P4F. This should: define what “smallholder-focused” means in practice for P4F; be realistic about the types of smallholders that a commercially-oriented programme can practically reach; reflect lessons and draw from wider expertise within FCDO; and use this analysis to inform future Component 2 design.
3. Monitor progress and engage strategically with ISEAL Innovation Fund. Firstly, monitor match funding conversion twice annually to track progress and assess whether the leverage model is functioning as intended. Secondly, encourage stronger mechanisms for disseminating and replicating innovations beyond original partners and across the P4F community of practice.
4. Strengthen working arrangements and alignment across Component 2 partners. Work to integrate Component 2 contributions into the emerging P4F community of practice, aligning the collective efforts of NISCOPS, ISEAL, P4F regional teams, and other partners around shared smallholder objectives.
5. Revisit and refine the smallholder elements of the IFSLU2 logframe. The current logframe indicators may not fully capture the breadth of results that Component 2 is generating, particularly around systemic outcomes such as government partnership development, private sector coalition-building, and the establishment of enabling infrastructure for smallholder inclusion. A review should assess whether additional indicators are needed to reflect these contributions, and whether targets require adjustment.

Output Title	Business and market development in ‘thin’ Congo Basin markets
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of partnerships supported.	Procurement of Technical Assistance supplier to provide market systems development and pre-incubation services in the Congo Basin. / Mobilisation of Congo Basin contract and inception to establish Technical Assistance Facility and set strategy. / Initial pipeline of market systems development and pre-incubation projects identified, screened and assessed for partnership support.	Procurement completed and contract awarded. / Contract mobilised; 9-month inception phase completed and full delivery underway. / Initial project pipeline under development. Work to develop project ideas began earlier than expected at the tail-end of inception.

Overview
The Congo Basin is the world’s second largest tropical rainforest, providing critical ecosystem services including acting as a major carbon sink, regulating global climate, and supporting unique biodiversity. It is also essential for the livelihoods, food security and cultural heritage of over 75 million people. Yet it remains one of the most underfunded and least studied forest regions compared to other major basins like the Amazon.
Phase 1 of IFSLU found that the main P4F approach – incubating forest-positive businesses – was effective in most tropical regions, but in the Congo Basin where markets are thinner, less developed and more fragmented, a key lesson highlighted that a different and more specialised approach was needed. Output 3 responds to this finding by strengthening market systems for sustainable, forest-linked value chains across the DRC, Republic of Congo, Cameroon and Gabon. The component aims to build the foundations of functioning markets for sustainable, private sector-led growth, through building private sector capacity and strengthening market systems. This includes improving the capacity of cooperatives, SMEs and other actors; enhancing connectivity across value chains; and addressing systemic constraints that prevent markets from operating effectively.
Delivery combines grant funding and technical assistance, while adopting a broad and responsive approach to intervention design. Lessons from inception confirm that success will require creativity and flexibility, while balancing risk across portfolios and permitting a higher degree of risk-taking and experimentation. This adaptive approach is essential given the complex operating environment, which includes conflict in the DRC, political instability following elections in Cameroon, and a complex political economy across the region.
The focus of the last 12 months has been on finalising procurement of suppliers to undertake this work, mobilisation of contracts, and completing a nine-month inception period, paving the way for delivery. The programme is now well positioned to move into implementation, with the key early priority being establishing an initial set of interventions.
Mobilisation
The aim of the procurement exercise was to identify an organisation or consortium capable of providing support to develop market systems and building capacity for private sector-led sustainable growth in the Congo Basin.
Following submission of bids in September 2024 a preferred bidder was selected and the contract commenced on 1st March 2025. The selected contractor, Palladium International, and its sub-contractors The Policy Practice, CrossBoundary Advisory, The Canopy Lab and TRIAS bring a wealth of regional expertise, experience and networks.
A nine-month inception phase was carried out to:
- Mobilise and onboard the core team and consortium and establish ways of working;
- Conduct in-depth research and analysis including through desk research and field scoping visits;
- Begin to build awareness of the aims of this new Output and build relationships with relevant stakeholders, including with FCDO posts;
- Develop an updated Theory of Change, a strategy, first year workplan, and approaches to GESI, MEL, communications, stakeholder engagement and a design for a Technical Assistance Facility;
- Set-up operational systems, tools and ways of working, and set up a regional presence in Cameroon and the DRC.
By the end of inception an initial set of geographic and thematic portfolios was identified to help focus delivery. These are: cocoa and coffee; palm oil; food security; bioeconomy innovations; community forestry enterprise; the DRC Green Corridor (Couloir Verte); and protected area buffer zones. Interventions within these portfolios all have identified potential to support jobs, livelihoods and growth through the development of a forest-friendly economy in the region. The inception phase has provided a solid foundation on which to progress into the delivery phase.
Delivery
The contract moved into implementation at the start of December 2025. The delivery partners accelerated a process to begin identifying and designing potential projects against priority portfolios at the tail end of inception. Work to continue developing the project pipeline continues at pace. This has resulted in a set of ideas screened and approved for further development into detailed concept notes (Table 2).
Table 2. Ideas approved for further development for early project pipeline
Country	Project	Thematic portfolio
DRC	Strengthening DOKAS as a Lead Aggregator for Sustainable Cocoa, Maize & Palm Oil in Tshopo Province	Cocoa & Coffee; Food Security; Palm Oil
DRC	Strengthening Cooperative-Exporter Partnerships in Tshopo	Cocoa & Coffee
DRC	Catalysing Financial Inclusion for Forest and Agricultural Enterprises in Equateur & Tshopo Provinces through a Green Agri-Microcredit Pilot	Cross-cutting
Cameroon	Strengthening Investment Readiness for Cooperatives in Cameroon	Cocoa & Coffee

These early project ideas include strengthening green market systems for cocoa in Tshopo (DRC) and Cameroon, and supporting financial inclusion and access in DRC by working with a local financial institution to design and pilot sustainability-linked microloans.
The contract is judged to be on track to deliver against milestones. This Annual Review does not provide a quantitative assessment of output results since this reporting year has almost entirely been devoted to procurement, mobilisation and inception.
Lessons identified
The inception and scoping phase confirmed what desk research had suggested: the Congo Basin presents a complex operating environment. Political economy dynamics are intricate and evolving, developmental needs remain vast, and major logistical constraints, such as poor infrastructure and limited connectivity, pose significant challenges to programme delivery. These realities underscore the importance of being realistic and well-informed about operational risks, while maintaining flexibility in planning and execution.
At the same time, scoping visits confirmed that the region offers considerable opportunities. There is growing political appetite for forest-positive initiatives, evidenced by commitments such as the Green Corridor (Couloir Vert) in DRC and Gabon’s policy intent to develop a green bioeconomy. Regional momentum is reinforced by international initiatives like the Belém Call to Action for the Congo Basin Forests and the launch of mechanisms such as the Tropical Forests Forever Facility (TFFF) and Canopy Trust at COP30. Beyond government actors, scoping missions revealed strong interest among civil society organisations, cooperatives, smallholder farmers, and businesses to engage in sustainable land-use models and supportive partnerships. This demand signals a favourable enabling environment for P4F interventions.
Crucially, the enormous diversity across the four countries in scope (DRC, Republic of Congo, Cameroon, and Gabon), and the dynamic nature of the region, marked by risks and opportunities, reinforces the need for adaptive programming and context specificity. This component will take a broad approach to intervention design, enabling flexibility in responding to opportunities. As a new output of the programme delivering in a complex operating environment, an approach will be taken that enables continued testing, learning, and iterating, underpinned by adaptive programming and an acute awareness of fluid political economy.
Finally, an important lesson from inception has been the challenge of communicating clearly about Output 1 and 3’s aims in the Congo Basin, both internally within FCDO and externally to stakeholders. We will need to continue to work on how we articulate the distinctions and complementarities to ensure clarity and coherence in messaging going forward.
Recommendations
1. Continue to foster join-up with the Business Incubation work (Output 1) on strategy, information-sharing, communications, field missions and stakeholder engagement. This will increase the efficiency of the programme and help stakeholders to understand the programme as a whole and how best to interact with it.
2. Use a common language and umbrella branding of Partnerships for Forests to refer to both business incubation (Output 1) and market systems development in the Congo Basin (Output 3). Tailor this messaging to the local audience, including the use of French where relevant.
3. Provide regular updates to the FCDO embassy network to enable input from posts, support stakeholder engagement, maximise the value for money from a more limited ODA budget, and ensure tailoring to political and economic contexts.
4. Continue coordination with other UK investments in the Congo Basin, such as Central African Forest Initiative (CAFI); Congo Basin Forest Action (CBFA) Programme; Forests, Governance, Markets & Climate (FGMC) and others. This will support complementarity, improved information sharing and understanding, and avoid duplication.

Output Title	Policy support for transformational change and action at scale
Output number:		4	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
4.1 Value and volume of agricultural commodities covered by sustainable sourcing and production policies; evidence of / implementation.	2025 Commitment Deadline for TFA Agriculture Sector Roadmap to 1.5 / Re-mobilise new phase of UKSCI under P4F	Progress on Ag Sector Roadmap was mixed with no major outputs at COP30 due to difficult politics around agribusiness in Brazil. / New phase of UKSCI re-mobilised
4.2 Number and impact of policy engagement platforms for / multistakeholder collaboration.	Transition managed from Phase 1 to Phase 2, procuring supplier, renewing funding to strategic partnerships and sustaining policy engagement. / Renewed support to the ADP under P4F	FACT Forum 2025 took place in Malaysia, focussing on smallholder support. / FACT events at COP30, and numerous reports and case studies to demonstrate progress. / Phase 4 grant support to TFA Secretariat committed. / ADP Multistakeholder Meeting in Berlin in 2025, hosted by three German ministries helping maintain the regulatory agenda around EUDR and focus beyond that on issues of traceability and smallholder inclusion.
4.3 Number and impact of policies, regulations, standards and / systems to enable sustainable investment.	Transition managed from Phase 1 to Phase 2, procuring supplier, renewing funding to strategic partnerships and sustaining policy engagement. / UKSCI members preparing for EUDR implementation this year despite uncertainty	World Bank PROGREEN call for proposals in preparation / issued for topic of Building Forest Economies. / New AIC Sustainable Commodities Standard for animal feed in the UK aligned with EUDR and UK Soy Manifesto / Renewed ADP Partnership through 2030, holding together a coalition to support deforestation free supply chains in Europe

Overview
This output is focused on policy engagement, partnerships, and initiatives to support scaling of impact and transformational change. It includes a focus on demand-side measures to build stronger markets for sustainably produced agricultural commodities, including:
- public policy reforms, such as due diligence measures; and
- private sector policy reforms, such as:
  - the implementation of sustainable sourcing commitments and practices;
  - enabling conditions such as policy reform and strengthened public-private collaboration;
  - improved business environment for investments in forests and sustainable land use;
  - enhanced capacity for sustainable business in low capacity and fragile regions with high forest cover;
  - and supply-side partnerships, such as collaboration with multilateral institutions, to scale-up and finance impact on the ground.
Key interventions in the portfolio currently include engagement through the UK Sustainable Commodities Initiative (UKSCI) and Amsterdam Declarations Partnership (ADP) to develop deeper markets for sustainably produced agricultural commodities; engagement through the FACT Dialogue and the Tropical Forest Alliance, respectively to facilitate deeper collaboration between producer and consumer governments, and to enable closer collaboration with the private sector; and a partnership with the World Bank aimed at scaling up finance and action through the multilateral system.
Delivery
UK Sustainable Commodities Initiative (UKSCI)
A new phase of UKSCI was launched in November 2025 under P4F, after a period of reduced activity due to limited funds. Despite the reduced budget, the platform hosted two Roundtable meetings, and has seen sustained engagement from across commodity sectors in the UK.
A new coffee working group has been formed, alongside progress in working groups on Oleochemicals, Embedded Soy, the Food Service Sector, and meetings on living income. Highlights include progress to develop an EU Deforestation Regulations (EUDR) aligned sustainable sourcing standard for animal feed in the UK, developed in collaboration between UKSCI and the Agricultural Industries Confederation. Also, business-to-business engagement between UK buyers and the Thai poultry sector (one of the biggest sources of processed chicken nuggets in the UK) to agree standards for the use of sustainable soy in Thai poultry feed.
All of this is in the context of impending EUDR enforcement, which drove significant engagement from members with operations linked to the EU or Northern Ireland. The progress towards compliance has been positive but members have also reflected that this has also been a distraction from the collaborative high ambition voluntary agenda. Subsequent delays to EUDR and UK Forest Risk Commodities (FRC) regulations have created challenging conditions for public-private engagement. Despite this, UKSCI has supported industry-led efforts to feed into policy processes through consultations and letters where possible.
Under the agreement for the new phase, a dedicated forum on Strategic Risks and Resilience will be established to help track increasing challenges with supply constraints, shifting sourcing regions, and increased prices for key commodities, helping to inform the next phase of collaboration under UKSCI, IFSLU2 and with UK Government given the increasingly complex environment.
Amsterdam Declarations Partnership
As of November 2025, P4F has mobilised funding for another two years of ADP. This is alongside financial commitments from other member states.
In January 2025, the UK handed over its chairing role to Germany to steer the group through the first half of 2025. In that period, members successfully signed the renewed ADP Partnership Statement through to 2030 and launched it at the Annual Stakeholder meeting in Berlin in June 2025. The renewed statement helps to focus the ADP on effective implementation of demand-side policies and helps to hold the partnership together at a time when many member countries are facing national political challenges in relation to sustainability policies.
The UK drafted the Partnership statement during its chairing period in 2024, and as a result the statement is well aligned with the strategic priorities and approach of IFSLU2, including key P4F scaling pathways such as support for better policies, a focus on enabling traceability and the data landscape, as well as smallholder inclusion.
Norway has chaired the ADP since July 2025 and has focused on mobilising investment into sustainable supply chains, as well as hosting valuable in country convenings in Indonesia and Brazil.
The ADP has also weathered the challenges of ODA cuts and EUDR delays, where having a grouping of governments has allowed for collaboration and flexibility around reduced funding for programmes (e.g. NISCOPS) and critical information sharing around EUDR developments.
Forests, Agricultural Commodity and Trade (FACT) Dialogue
The FACT Dialogue is an important intervention that contributes to Output 4. FACT brings together 28 of the largest producer and consumer countries of internationally traded agricultural commodities with the aim of protecting forests while promoting sustainable trade and development. FACT remains the only forum for cooperation between major producer and consumer countries on agricultural commodities. Different perspectives between producers and consumers mean that issues around commodity production and forest protection are often contested, and a greater degree of political consensus is required to enable collaboration and action to ensure sustainability.
FACT has continued to deliver against its Roadmap during this period, as it comes towards the end of the original timeframe. The incoming co-chair, Malaysia, has deeply engaged in the dialogue. This supported the delivery of the annual in-person FACT Forum in Malaysia, focussed on support for smallholders. Representatives from 19 FACT member countries attended, with the benefits of in-person interaction helping to reinvigorate the dialogue and demonstrate its potential to find common ground and enable collaboration.
Over the past year, the global landscape has shifted considerably, with new challenges and evolving political priorities. In this context, the FACT Dialogue has remained a steady and constructive space for shared purpose and coordinated action. Virtual thematic meetings have also been held, leading to the publication of several key reports on traceability and transparency, national assurance schemes and market recognition, as well as country case studies which demonstrate how members are translating the roadmap principles into domestic action. An independent review of the first phase of FACT was conducted, giving useful insights into the successes and challenges of the dialogue, which will help to influence the design of the next phase. The next challenge will be to take decisions around the future of FACT – with members confirming their desire to continue – the outputs of the dialogue, and opportunities for a more streamlined secretariat function.
Tropical Forest Alliance
The Tropical Forest Alliance (TFA) supports collaboration with the private sector in support of deforestation-free palm oil, soya and cattle industries. FCDO support is provided through a Delegated Cooperation Agreement with Norway, which serves as the lead donor on behalf of both the UK and the Netherlands. Norway in turn provides a grant to the World Economic Forum (WEF), which hosts the TFA secretariat.
The TFA is refocusing on delivery after a long period of change. Reporting covering the July 2024 – December 2024 period (the most recent available) notes limited progress with implementation and disclosure of deforestation-free policies by agricultural commodity companies in key segments of value chains, including traders and consumer goods companies. The challenges which companies are facing, and the role of the TFA in supporting their efforts, requires further attention. Alongside this challenging picture, there has been some success. This includes supporting COFCO International, a key agricultural commodity trader, to fulfil its first Brazil-China trade contract in deforestation-free soya; and strengthened engagement with the finance sector, notably through the Investor Policy Dialogue on Deforestation (IPDD). The IPDD now comprises 83 institutional investors from 21 countries, representing approximately US$11 trillion in assets, with TFA supporting members to engage with government authorities in key IPDD focus regions (Brazil, Indonesia, US, UK and EU) on frameworks and regulations to support the transition to deforestation and conversion-free commodity production.
PROGREEN
Engagement with the PROGREEN programme has facilitated new collaboration with the World Bank through its flagship Global Partnership for Sustainable and Resilient Landscapes. PROGREEN aims to scale up action and finance for sustainable landscapes. It is also a key vehicle for the delivery of the World Bank’s Global Challenge Program (GCP) on Forests for Development, Climate, and Biodiversity, which aims to support a sustainable forest economy in critical forest biomes. As such, it is closely aligned with the aims of IFSLU2 and provides an important avenue for collaboration under Output 4, which supports partnerships and collaboration to scale-up impact.
The UK’s £10m contribution to the fund is pooled with greater levels of finance from Germany and Sweden, but with the UK taking on a shared role with the co-donors in steering programme operations. UK finance accounts for a share of overall programme results. To date, PROGREEN programmes have enhanced conservation or management of more than 750,000 hectares of land; PROGREEN-informed operations have brought an additional 11.4 million hectares under improved management. Around 60,000 people have also gained enhanced resilience to climate risks through programme operations.
PROGREEN support has a considerable influence over World Bank and other sources of finance, with every US$1 of support informing US$68 of total investment. PROGREEN funding has informed US$14bn in IBRD and IDA funds, US$1.6bn in private capital, US$4bn in client funding and US$1bn in international climate and nature financing, including the Global Environment Facility and the Green Climate Fund. Targeting ensures that Sub-Saharan Africa receives the greatest share of PROGREEN support.
Specific developments since the UK joined PROGREEN include a new US$100m Call for Proposals for Type 1 programmes (grant finance aligned with the delivery of World Bank lending programmes to client countries) and a US$5m Call for Proposals for Type 2 interventions (analytical support and technical assistance to identify opportunities to strengthen the enabling conditions for a forest positive economy). Both calls for proposals were fully subscribed, strengthening and deepening the PROGREEN portfolio.
The Type 1 Call for Proposals was launched in early 2025, leading to the selection of 13 initiatives with a total financing commitment of approximately US$150m aligned with wider bank lending programmes, building on previous Type 2 activities, covering tropical forest landscapes in low-income countries, with preferencing for Sub-Saharan Africa. The Type 2 Call for Proposals – enabled by the first tranche of UK funding – was launched in December 2024 with a US$5m budget, aligned with a set of priorities that included alignment with GCP-Forests, the theme of building forest economies, and a focus on governance, finance, and jobs. The call for proposals led to the selection of 13 proposals in May, which are now underway. PROGREEN has also been extended to 2031, with the agreement of the three donors, aligning timelines more closely with the 10-year IFSLU2 commitment.
In addition to engagement in PROGREEN governance, FCDO has begun new collaboration with the World Bank focused on establishing a new Liveable Landscapes Academy (LLA) within the World Bank Group, with an additional £2.5m in funding channelled through PROGREEN to support the start-up of this work. The LLA will operate as a knowledge platform to share expertise, bring people together, provide learning opportunities that help scale investments to manage landscapes sustainably, and prevent and reverse land degradation.
While investments in landscapes yield a high return (some estimates suggest up to five times the initial investment, alongside significant job creation), there are major challenges to scaling, especially securing enough funding and managing the high costs of design and implementation. The LLA aims to support World Bank country teams and client country governments to overcome these challenges, focusing initially on West Africa and Southeast Asia. Plans are now being set out to launch the LLA in 2026.
Lessons identified
FACT highlights the potential to enhance impact through aligning policy engagement by UK officials and programme support delivered through technical partners. Over the reporting period, policy engagement has helped to bring Malaysia into the co-chair role. The producer country co-chair role is essential to maintain an approach based on partnership between producer and consumer countries. This leadership by governments in turn creates space for the secretariat to curate dialogue around challenging issues, building consensus around the path forward.
Experience with leading the FACT Dialogue since 2021 has provided valuable lessons, including on ways to sustain dialogue with limited opportunities for in-person interaction, between countries with vastly different circumstances, cultures and interests.
Sustaining the dialogue has been challenging, but fostering closer collaboration is essential to unlocking cooperation and action at the pace and scale required to halt deforestation. FACT provides a unique platform to work towards this with 28 governments. However, it is not intended to directly deliver actions and impact on the ground, which can make it challenging to sustain engagement of countries over time, measure outcomes and express impact in quantitative terms. The independent evaluation comes some way in addressing this, and the sustained effort is seeing a steady increase in active participation.
Partnership with the World Bank has created an opportunity for new collaboration with the potential to support scaling of action. The Bank operates with a scale of finance, diversity of instruments, global reach, depth of expertise, client relationship with key countries, and dialogue on policy reform to enable sustainable economic growth, all of which have potential to significantly aid the scale up of action. The World Bank’s Global Challenge Programme on Forests (GCP-F) sets out this aim of scaling action. However, it will be important to harness the full potential of this partnership by continuing to focus on collaborative approaches.
Recommendations
While considering the next phase of FACT, refine the key measures of success and streamline delivery around these.

1. Continue to maximise the return on UK investment by engaging actively with World Bank teams to support PROGREEN delivery of a successful launch of the Liveable Landscapes Academy, and ongoing collaboration around learning and scaling impact.
2. Align and combine demand-side efforts across programme partners. Demand-side work in IFSLU2 is currently distributed across NISCOPS (India, Europe, Asia regional), ISEAL (Living Income CoP, landscape networks), P4F, and supplemented by FCDO posts in key markets. Develop a coordinated approach that combines these efforts and ensures diplomatic opportunities are leveraged effectively. FCDO posts should be equipped as partners in these efforts.

D: VALUE FOR MONEY
Key cost drivers and performance
In the early years of the programme, Outcome level data to support assessment of value for money will not be available. However, the potential to secure value for money can be benchmarked against Outcome level results from Phase 1, which mobilised £1.35bn at a ratio of £11 of private investment for every £1 of public funds.
While Outcome level data are not available, a value for money framework based on the 5Es can help to assess performance and is used to guide programme delivery to ensure value for money. This framework comprises: Economy, measuring the costs of procuring inputs; Efficiency, measuring the conversion of these aggregate inputs into desired outputs; Effectiveness, measuring the rate at which outputs are transformed into desired outcomes and impacts; Cost-Effectiveness, measuring the impacts relative to the inputs; and Equity, measuring how fairly the benefits are distributed and the extent to which benefits reach poor and marginalised groups.
A focus on additionality further strengthens the value for money framework, with all partnerships under consideration for support reviewed against additionality criteria defined as the ‘net positive difference that is expected to result from a P4F supported partnership. The extent to which activities (and associated results) are larger in scale, at a higher quality, take place quicker, take place at a different location, or take place at all as a result of a P4F intervention’. Evidence to support additionality is documented for each partnership and broader analysis of these data used to help to improve the design and targeting of assistance more effectively.
Finally, a policy requiring match-funding of partnership activities ensures fair sharing of risk within partnership activities and enhanced value for money. No match funding data are as yet available to track progress, but a framework and business processes are in place to ensure this is tracked over time.
Economy
The main input costs in IFSLU2 are the specialist staffing required to partner effectively with businesses, governments, industry associations and non-government organisations, along with the core staffing, overheads and fees associated with overall programme management. Open competitive procurement processes were conducted for Components 1 and 3, with bids subject to thorough comparative evaluation against VfM criteria. Both resulted in the appointment of strong teams which have performed strongly in the first year of the contracts.
Operating policies, business processes, and frameworks to manage value for money have been set up during the inception periods for the Component 1 & 2 and Component 3 contracts. These will provide a basis for ensuring, tracking and understanding value for money performance of programme interventions over time. Policies include benchmarking of costs for local, national and international expertise, preferencing for local and national expertise, and sourcing policies to ensure competition to drive value for money where external expertise is required. Output-based contracts are being used to drive economy and effectiveness.
Funding packages for partners have been carefully reviewed and negotiated to reduce costs where possible. Innovative solutions to support multiple partnerships through addressing shared constraints are being developed to enhance efficiency (for example, developing metrics that can support the operations of multiple impact investment funds). Dialogue on partnership and co-funding has been stepped up, leading to some potential commitments of co-funding to support programme activities and enhance value for money.
In Component 2, IDH, Solidaridad and ISEAL continue to align with FCDO eligible cost guidance for accountable grants, with budgets commensurate with the activities being delivered, and rates of non-project attributable cost (i.e. overheads) in line with the grant agreements and their respective organisational structures and circumstances.
Efficiency
Contract procurement for Component 1 & 2 and Component 3 has resulted in the award of contracts to suppliers with strong technical expertise and programme management capabilities. The depth of these skills is evident in the successful completion of inception phases and rapid transition into programme delivery. Component 1 & 2 inception included recruitment of teams, development of management policies, business processes, grant management and risk management frameworks, alongside development of theories of change and results frameworks, the development and testing of regional strategies, identification of partnership opportunities and preparation of initial funding proposals.
Component 3 mirrors much of this, along with the additional challenges of drawing together and building a new delivery team, undertaking scoping in a new and challenging region, and the design of new approaches to supporting market systems development in that context.
Dialogue is ongoing with Component 2 and 4 grantees, focused on reducing budgets in line with anticipated cuts to the IFSLU2 budget following a decision to reduce the UK’s ODA budget to 0.3% of GNI. An important focus of that dialogue has been on how to maintain the integrity and viability of the interventions, and delivery of results, while operating with less funding. This is important to ensure the interventions continue to be justifiable on a value for money basis. The outcome of those discussions – resulting from constructive dialogue and collaborative responses from partners operating under challenging and uncertain circumstances – suggests that the value for money case for the interventions remains strong.
In respect to Component 2 grants to IDH, Solidaridad and ISEAL, determining output unit costs is challenging given the complexity of the programmes and their budget structures. In future years, the possibility of identifying some key output unit costs (e.g. per-farmer training cost across NISCOPS’ five operating regions) may be explored. Nevertheless, NISCOPS partners have made good progress on achieving outputs concerning farmer training (25% of the 2028 target was reached in 2024). Although programme delivery has been slower than anticipated (as discussed in Section C), and both implementing partners underspent on projected 2024 budgets by over 30%, delivery is expected to accelerate in the next reporting year as government partnerships become fully operational. Positive progress on the farmer training output indicates that when resources are deployed, NISCOPS partners are allocating them efficiently. ISEAL’s performance in managing the Innovation Fund is also notable, with 22 new grants allocated in 2024-25 and positive feedback on their performance received from ISEAL members (as noted in the midline assessment) and Swiss government stakeholders. This too provides an indication of efficient allocation of programme resources for delivery.
Effectiveness
Under Component 2 grants to IDH, Solidaridad and ISEAL, determining outcome unit costs is particularly challenging given the breadth of programme scope and the complexity of change in their operating contexts. Nevertheless, NISCOPS is beginning to realise outcome-related results that bode well for future years. To date, NISCOPS has brought 62,752 hectares of farmland under sustainable management practices and 16,270 hectares of forest into protection arrangements, representing 12% and 3% of their respective 2028 targets. Although outcome results for improved livelihoods are marginal at present (748 people benefitting from improved incomes/yields), this reflects methodological baselining challenges that should be resolved in the coming year. Early signals of effectiveness beyond these headline indicators include deforestation reductions in Aceh Tamiang district (where NISCOPS builds on a decade of landscape engagement prior to FCDO funding) and €1.4 million in private sector co-investment secured from GAR and Mondelez, suggesting that chosen approaches have commercial value. Solidaridad has also supported 2,800 farmers to meet EU market requirements on traceability, which should contribute to improved market access and livelihoods over time. ISEAL will begin reporting outcome-level results in 2026. In the meantime, £2,241,359 in FCDO contributions via the Innovation Fund have mobilised £2,241,359 in financial pledges from the private sector and other sources, though only 9.6% of these pledges have converted to actual commitments to date – a ratio that will require monitoring (and acting on) as grants mature.
Equity
The programme has taken a more targeted approach to addressing the challenges of smallholders, one of the most vulnerable stakeholder groups in large supply chains, building on lessons from IFSLU1. This includes a designated component of activities (Component 2) focused on delivering scaled up smallholder support. In addition, the programme has embedded a strong focus on GESI across the programme from Business Case design through to implementation. This includes dedicated GESI resource in both P4F contracts (Component 1 & 2 and Component 3). The P4F GESI strategy was presented at a UNEP Land Use Finance Roundtable in Amsterdam, receiving positive feedback from global stakeholders. Progress against the strategy will be reported in subsequent Annual Reviews.
In respect to NISCOPS, both IDH and Solidaridad collect gender-disaggregated output-level results concerning farmer training across the five production countries. In the 2024 results period, 32% of people supported by the programme were women (9,881 individuals). Meanwhile, in the NISCOPS Ghana project, 67% of livelihood applications through Village Savings and Loan Associations came from women, indicating that programme design is reaching women within smallholder populations. Age-disaggregated data are collected in some instances, but are not consistent enough to undertake meaningful analysis. ISEAL will begin reporting gender-disaggregated results data from October 2025 onwards.
Cost-effectiveness
An assessment of cost-effectiveness will be reported in future Annual Reviews, once outcomes have been recorded.
VfM performance compared to the original VfM proposition in the business case
It is too early to provide an assessment of overall VfM performance since key contracts have only been in implementation for a short period. Nevertheless, early indications – particularly from the smallholder scaling work (Component 2) – strongly suggest that the programme is delivering in line with the VfM proposition in the business case.
Assessment of continued value for money
The programme represents value for money based on the early evidence available.

E: RISK

Overview of risk management
Strong risk management systems are needed to manage risk within the programme, requiring a continuous focused on supporting innovation and the delivery of results while mitigating risk associated with the operating context and programme approach. Key factors to consider in risk management include the forest sector operating context and the programme approach to working with the private sector.
The operating context in the forest sector is challenging. Activities take place in remote regions, where weak governance, contested resources, poor infrastructure and challenging environmental conditions create a difficult operating environment, with enhanced risks around conflict and safeguarding in some circumstances. There are also programme specific political and reputational risks associated with supporting private sector-led innovation. Experience from Phase 1 demonstrates that these risks can be managed and mitigated. Lessons from Phase 1 have been applied to the set-up of risk management systems during mobilisation in the last year.
Table 3: FCDO risk framework and programme approach to risk
Strategy and Context - Receptive	Risk arising from pursuing diplomatic and development objectives which are undermined by a changing context, a lack of clarity or a weak evidence base. These risks undermine our delivery and impact.	The programme operates in line with the receptive stance, operating in a challenging context to deliver results for people, climate and nature. This includes operating in countries facing challenges from weak governance and political instability; and engaging to achieve impact on global challenges, such as mobilising action at scale to halt and reverse deforestation, where the evidence base is weak, to test and replicate strategies and solutions for impact.
Policy and Programme Delivery - Receptive	Risk arising from implementation of our core business of diplomacy and development, due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing, and/or operational support. These risks undermine our impact and influence.	The programme operates in line with the receptive stance, recognising that operations take place in a challenging context, and working with partners, beneficiaries and other stakeholders to identify and surmount challenges and risks to delivery through a constructive and solution-focused approach.
Public Service Delivery and Operations - Cautious	Risk arising from weaknesses in the delivery of consular services or the delivery of internal operations which support our core business and wider HMG, including security, legal, technology and information and property risks, impacting delivery, our people and British citizens.	N/A.
People - Cautious	Risk arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance.	N/A
Safeguarding – Cautious	Risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations, reputational damage and legal challenge.	The programme operates in line with the cautious stance, applying strong policies, measures and monitoring to minimise safeguarding risks in the implementation of the programme and delivery of support.
Financial and Fiduciary - Cautious	Risk arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak value for money, compliance and delivery failures and reputational damage.	The programme operates in line with the cautious stance, with zero tolerance for fraud, a strong focus on value for money in the implementation of activities, and a commitment to managing public money well to achieve outcomes.
Reputational - Cautious	Risk arising from political or adverse events, including delivery failures and ethical violations, damaging the FCDO’s reputation, within the organisation and/or externally, and/or the UK’s reputation.	The programme operates in line with the cautious stance, with a focus on managing and mitigating risks associated with programme delivery in partnership with the private sector, using due diligence, testing the additionality of public support, and monitoring results to mitigate risk and demonstrate the value of the approach.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partnerships
Component 1
Following completion of the procurement process a contraction for delivery of Component 1 was awarded to a consortium led by Palladium International, which brings together expertise in development programming, grant management, technical assistance, business incubation, public-private partnership building and demand-side policy facilitation. The consortium has a track record of working together effectively and the six-month inception period and early delivery demonstrated effective ways of working, including strategy development and cross-pollination between regional and global strategies (e.g. on scaling capital mobilisation). Some key decisions on office lets and staff resourcing have been paused to avoid locking in long-term decisions during a period of budget uncertainty. This demonstrates an ability to manage money and people responsibly, while retaining maximum flexibility. Financial and budget management and forecasting have been accurate and timely, within the thresholds established in the contract.
Component 2
Management of Component 2 grants transitioned from FCDO to Palladium under the Component 1 contract. This transition, flagged in last year’s review, has been completed smoothly. Palladium developed a responsibilities matrix clarifying roles between grantees, P4F, and FCDO, with a defined escalation process maintaining FCDO oversight for key decisions. First disbursements were processed following Q2 2025 reporting review, and P4F’s Southeast Asia Regional Manager attended the NISCOPS Annual General Meeting in Malaysia in October, supporting alignment between grants and the broader programme.
Coordination and collaboration between NISCOPS partners (IDH and Solidaridad) is working well, but both underspent on projected 2024 budgets by over 30%, and accurate forecasting of projected spend continued to be a challenge into 2025. Thanks to forecasting support provided by Palladium, forecasting accuracy is improving. Although challenging from a financial management perspective, it should be noted that this did not undermine VfM as necessary measures were put in place to ensure disbursements were not made in advance of need.
The grantees have responded constructively to significant funding pressures, and are working with the FCDO programme team to maintain momentum, drive results and ensure value for money with scaled-back funding.
Component 3
Following completion of the procurement process in early 2025, FCDO signed a contract with Palladium, leading a consortium of The Policy Practice, TRIAS, Canopy Lab, and CrossBoundary. This partnership brings together expertise in political economy analysis, local capacity building, market systems development, and investment facilitation, critical expertise for delivering Component 3 in the Congo Basin. Since contract signature, the consortium has mobilised teams, established governance and ways of working, and completed inception activities, including scoping missions across the DRC, Republic of Congo, Cameroon, and Gabon, and development of a strategy grounded in a Green Market Systems Development approach.
Commercial and financial performance is currently on track. Narrative reporting has been timely and of good quality, and good working relationships and ways of working have been developed by the core delivery team and FCDO. Efficient ways of working have also been built with Component 1, with joint field missions, quarterly strategy discussions and communications materials. This will drive synergies across the contracts and deliver stronger value for money.
Component 4
Component 4 is delivered through grants with the Centre for International Forestry Research – World Agroforestry Centre (CIFOR-ICRAF) (supporting the FACT Dialogue), the World Economic Forum (supporting the Tropical Forest Alliance) and a trust fund agreement with the World Bank (funding the PROGREEN programme). The partnerships with CIFOR and WEF are longstanding, with established governance supporting ongoing work. Independent evaluation highlighted challenges in the ways of working of the two organisations leading the FACT Dialogue secretariat. While a high level of input is needed to support the Secretariat, it has successfully delivered against many milestones and proved effective in country engagement and support. The work done during the last reporting period to clarify roles and responsibilities has helped to improve efficiency, but accuracy of forecasting remains a challenge.
The TFA is refocusing on delivery after a long period of change, working to address several significant challenges relating to both operations and grant management. This includes a loss of momentum and strategic focus in the transition from a previous phase of support, which has cast a long shadow across the current phase of operations; internal reorganisation; the identification of grant management issues requiring corrective action; long delays in recruiting new staff to fill key gaps in the TFA team; the temporary suspension of operations in China; and the loss of US State Department funding. These issues have now been addressed, providing scope for the TFA to refocus on delivery. The remaining 18 months on the grant will now be crucial in demonstrating results. An evaluation, which is due to be conducted in early 2026, will also provide important input for consideration of the future of this initiative.
Partnership with the World Bank through PROGREEN has enabled UK participation in broad programme governance, as well as more specific collaboration to develop the Liveable Landscapes Academy (LLA). Participation in broad programme governance provides access to learning, evidence and opportunities for collaboration, but with more limited influence over the wider programme strategy. Partnership to develop and launch the LLA offers an opportunity for more tailored cooperation on learning and scaling up impact. In both cases, it will be important to continue focusing on developing approaches to collaboration to harness the full potential of this partnership.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
Preparations for a tender to appoint an Independent Evaluation and Learning Manager have been paused due to ODA budget uncertainty resulting from the planned reduction in the UK’s ODA budget allocation. Depending on the outcome of the budget allocation exercise, the approach to evaluation and learning will need to be revised. This will be a key focus of 2026.
In the absence of a defined approach to independent evaluation, a strong approach to monitoring, evaluation and learning is being developed throughout the programme. Each component has its own MEL strategy, providing evidence and lessons learned to improve delivery. Monitoring visits have been undertaken to Southeast Asia, Central Africa and East Africa to oversee the early stages of programme delivery of the Component 1 & 2 and Component 3 contracts. It is clear from these regional visits that the delivery teams – drawn from different organisations – are able to work effectively under a ‘one team’ vision.
The contractor, Palladium, has taken over grant management of the Component 2 grants from FCDO and is providing a high-quality monitoring and support function to the grantees to help improve financial monitoring and forecasting as well as delivery of results. This allows the FCDO programme team to focus effort on overall programme monitoring and strategy.
Under Component 2, NISCOPS appointed a Scientific Assurance Partner in January 2025 to strengthen the scientific basis of the programme’s interventions. A supplier was also selected (KIT Royal Tropical Institute) to perform independent mid-term and end-term evaluations. ISEAL commissioned an independent midline assessment that identified that the Innovations Fund and Living Income workstreams were most influential and valued by the ISEAL membership, validating the strategic importance of these activities. The midline assessment also identified areas where ISEAL could strengthen its work, namely private sector and government engagement. These insights are informing budget and activity prioritisation in the year ahead.
Evidence
The current stage of the programme means that there has been limited opportunity to draw on evidence from activities. However, work is underway to gather evidence to inform future programme strategy and interventions. This has included wider scoping of opportunities and related evidence to inform strategy and portfolio development for Component 1 and Component 3 on topics such as forest restoration, challenges and opportunities relating to carbon market development in the Congo Basin; and deeper assessment of evidence relating to specific issues, such as assessing the potential of open-source data to contribute to cost-effective and accessible traceability systems, avoiding the costs and inefficiencies of operating multiple proprietary systems; and commissioning of a Rapid Evidence Assessment of Interventions to Support Smallholder Farmers, to inform strategy for addressing chronic inequality and poverty facing small farmers in agricultural commodity supply chains, which is a significant barrier to implementing action to curb deforestation.
A Discovery project commissioned by FCDO’s Frontier Tech Hub, completed by Proforest in May 2025 and made publicly available, has helped to inform programme strategy development around the use of Open data and technology to promote smallholder inclusion in commodity value chains, such as cocoa and palm oil, where there are risks of exclusion as markets shift to meet emerging due diligence requirements, such as the EU Deforestation Regulations (EUDR).
A Rapid Evidence Assessment into interventions designed to deter smallholder farmers from clearing forest to produce commodities or encourage sustainable agriculture practices was commissioned by the IFSLU programme team via the FCDO’s Evidence Fund. This assessment has informed strategic thinking about the future direction of Component 2. The final report (produced in April 2025) has been made publicly available and is also being refined and prepared for journal publication. This represents valuable use of published evidence to shape programme strategy.
Learning
Similarly, the current stage of the programme means that there are limited opportunities to support learning from programme activities. However, the approach to Phase 2 draws heavily on learning from Phase 1.
Under FACT, learning from Phase 1 delivery has informed management arrangements under the new grant. Moving the project into the IFSLU2 portfolio added value in encouraging the FACT Secretariat to prioritise the development of a Theory of Change and Evaluation Framework, which was included in the new grant and will inform the forthcoming independent evaluation of the programme. This evaluation will help FACT to reach a conclusion on the question of a next phase of FACT following its initial five-year commitment. The evaluation will also generate wider learnings on best practices for global policy dialogues and what it takes to sustain engagement in these sensitive but important collaboration platforms. Other MEL activities will include interviews and surveys with FACT member governments to collect both monitoring data but also wider evidence and case studies around policy action in line with the FACT Roadmap. New systems of quarterly senior project management meetings and a new financial reporting system have also helped to streamline and strengthen project monitoring.
ISEAL published three learning briefs synthesising insights from its Innovation Fund portfolio. These covered performance monitoring and reporting (identifying gaps in data integrity, secure sharing, and producer access to data); uptake and scaling (examining factors that enable or constrain replication of innovations beyond original partners); and climate action in sustainability systems (analysing barriers to market viability for climate-focused innovations). These briefs represent valuable honest learning about implementation challenges. Additionally, ISEAL produced three case studies that explored enabling smallholder market access, including approaches to stakeholder engagement and producer inclusion. While these learning outputs represent valuable knowledge products, mechanisms for systematically applying insights from Component 2 grants to inform P4F investment decisions and technical assistance design need to be developed. Establishing structured processes to translate ISEAL’s learning briefs and NISCOPS’s landscape experience into actionable guidance for P4F regional teams will be a priority for 2026.
As noted in earlier sections of the Annual Review, there is a need to learn across the programme to drive effective feedback between Components, generate evidence to inform adaptive management and activation of the scaling pathways conceptualised during the last year:
- Build the ecosystem for regenerative and inclusive markets
- Strengthen the policy environment
- Scale access to finance and new revenue streams
- Harness technology and data to drive scale
- Build smallholder farmer inclusive value chains.

Partner	Date of last narrative financial report	Date of last audited annual statement
ISEAL Alliance	30/10/2025	06/06/2025
IDH	31/10/2025	17/06/2025
Solidaridad	31/10/2025	30/06/2025
CIFOR-ICRAF	15/11/2025	24/09/2024
World Economic Forum	24/11/2025	24/11/2025
World Bank/PROGREEN	01/12/2024	30/06/2025