## Annual Review Template

Title: Peace and Stability Mozambique Programme (PSMP)
Programme Value £ (full life): up to £5m		Review date: 01/04/23 – 31/03/24
Programme Code: 301326	AMP start date: 23/11/21	AMP end date: 31/03/26

Summary of Programme Performance
Year	21/22	22/23	23/24	24/25	25/26
Overall Output Score	A	B	B
Risk Rating	Major	Moderate	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301326 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301326 Documents (fcdo.gov.uk)

Scoring

A. SUMMARY AND OVERVIEW

Description of programme

The Peace and Stability Mozambique Programme aims to promote peace and stability through initiatives to prevent the spread of violent extremism and foster peacebuilding in Cabo Delgado and northern Mozambique, and to consolidate the peace process in Central Mozambique. The programme has two components. Component 1 (which is the bulk of the programme (£4m of £4.9m) and the subject of this review aims to a) strengthen community resilience against violent extremist influence and narratives; b) promote provincial and local dialogue between public authorities, the private sector and citizens to increase trust and reduce tensions; c) support government-led mechanisms for conflict management and improved coordination with international partners. The programme also aims to influence other donors and public policies through effective pilot initiatives and monitoring, evaluation and learning. Component 2 concluded in March 2023 focussed on the conclusion of Demobilisation, Disarmament and Re-integration of former Renamo combatants and is therefore not covered in this review period.

Component 1 is delivered through a contract with TAG International and through a consortium involving Azul, Observatorio do Meio Rural and private security research consultants. Through research and dedicated engagement with communities they are building resilience to violent extremism through facilitated workshops, engaging local communities and security actors. Workshops work to build relationships based on trust fostering a culture of peace rather than violence to resolve conflict. A small grants mechanism is funding grassroots projects that are aimed at building peace and resilience within local communities. Research is building a common understanding of the conflict and how the international community and Government of Mozambique might work together to address the underlying drivers to support long-term peace for the region.

Summary supporting narrative for the overall score in this review

PSMP objectives remain aligned to the British High Commission (BHC) Mozambique’s Business Plan and northern Mozambique strategy and remains contextually relevant given the depth of fragility and poverty in Cabo Delgado. However, the annual review team has found that insufficient progress has been made over the reporting year towards outcomes in part due to weaknesses within the implementing consortia, including high staff turnover, as well as deterioration in the security context. In some areas the Programme is on track to achieve its outcomes but there is significant uncertainty that all targets will be met within the Programme timeframe.

Major lessons and recommendations for the year ahead:

Recommendation	Timing	Owner
Develop Programme Performance Improvement Plan for agreement at the PSMP Steering Committee. This should include an updated Delivery Plan, a stronger role for BHC’s new staff member in Pemba, more ambitious milestones for year 2, endline baselining, strengthening of grant management and resourcing and reviewing of Programme partner staffing (including potential for a greater footprint in-country).	Feb 2025	SRO
TAG to present to PSMP steering committee on a bi-annual basis to ensure alignment between strategy and programme objectives and agree forward looking government, international community engagement plan. This will include setting a programme of engagement with government and the international community (including through the soon to be established Cabo Delgado working group) to support greater co-ordination on peacebuilding, development and humanitarian actors working on Cabo Delgado and agreeing key messages.	March 2025	SRO
Scope use of third-party monitoring to ensure compliance and due diligence of grant mechanism.	March 2025	PM
HMG and PSMP should improve learning between grantees, through initiating lessons learn sessions across grantees and other UK investments to demonstrate what works and doesn’t, including sharing good project management practice in the context. These lessons to be documented and shared with HMG and other donors.	March 2025	TAG
Adopt more consistent wording to describe activities/outputs, aligned to those in the RF.	March 2025	TAG/SRO
Develop communications plan for how to best manage expectations of grantees given modest amount of funding available.	Jan 2025	TAG

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

At impact level the PSMP aims to reduce radicalisation and violence, sustain progress on reconciliation efforts, including through inclusive resolution of key issues of contestation, and reduce perceptions of exclusion and marginalisation.

There are three outcomes:

1. Drivers of conflict reduced increased group and community resilience and enhanced inter-community cohesion.
2. Community perceives improvement in responsiveness and behaviour of security forces & security actors better understand the value and importance of community engagement to achieving their objectives.
3. Greater alignment of agendas across those working to build peace and stability in Cabo Delgado, including the international community, private sector and Government of Mozambique, enhanced coherence of response, and greater synergy in application of funding ToC logic and assumptions remain broadly unchanged, despite slow progress in implementation. It could be made clearer that unless political levers can affect the political settlement in the North, only limited gains can be achieved at a local level.

The programme reported that the MREL Advisor ran two online workshops with the team in early April 2023 to review the Theory of Change (ToC) agreed at the end of Inception. The objective was to verify if the planned outcomes remain relevant and realistic and ensure the team has a common understanding of the direction of the programme. Some small edits were suggested.
[note] Component 1: The grants mechanism to support community programmes is the focus of Y2 so this was made more explicit in the Intermediate Outcome wording. Component 2: The term ‘police’ was replaced with the broader term ‘law enforcement’ in order to reflect the variety of stakeholders PSMP will likely work with; including, for example, forças locais. The C2 output wording was also updated to better reflect the research and experience gathering activities under this component. Component 3: Remains the same but the word ‘enhanced’ was added before ‘coordination’ in the component title to clarify that we are supporting coordination and not solely responsible for achieving it. It is noted that during year 2 of the programme Mozambique is due to hold elections and the security situation in the North is has become more challenging. This may require further review of the programme outcomes and impact metrics to refine their scope.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The Peace and Stability in Mozambique Programme (PSMP) started in May 2023, with the inception phase formally finalised in October 2023 – although in practice the review team heard that inception activities continued beyond this period. Much of the activity between October 2023 and March 2024 included further scoping rather than delivery. There were several problems including the management of downstream partners, which led to two partners pulling out. Following some course correction, TAG identified new downstream partners. However, these delays led to a longer than planned inception phase.

Overall, progress on outputs has been foundational and process related – which has not yet translated into significant progress towards outcomes. Progress appears to have been impeded by high turnover of key management positions within the programme and some disagreements between consortium members

At the time of writing the review, HMG and TAG have already taken course correction. New downstream partners have been recruited, with HMG conducting additional due diligence on quality assurance of the new partners. A workshop was held in September 2024 where HMG set renewed expectations for delivery, implementing lessons from earlier collaborations. All partners confirmed financial allocations were sufficient to deliver high quality outputs and that the balance of allocations per outcome was broadly correct. The work plan was reviewed to ensure improved delivery towards outcome 2 and the results framework has been amended to reflect more SMART and ambitious milestones.

Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio

Progress towards outcomes has been inadequate over the reporting period and needs to be accelerated, including with more stretching milestones put in place. Initial evidence suggests improvements have been made which justify the continuation of the Programme. More broadly, PSMP has the potential to provide important evidence about the nature of conflict in Cabo Delgado to support diplomatic and other programming efforts towards long term stability.

## C. DETAILED OUTPUT SCORING

Output Title	Community champion groups established in three selected districts and familiarised with GALS principles, methodology and tools (Component 1; Resilience)
Output number:		1	Output Score:	A
Impact weighting (%):		16.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1: Extent to which GALS adaptation methodology is adapted to and used in the context of peace and resilience	Baseline report and Implementation plan for how GALS will be adapted and implemented in the three selected districts of Cabo Delgado is produced.	Achieved: 105 community members were surveyed for baseline research (52 men, 53 women. 62 in MdP, 15 Mueda, 28 Montepuez) with age ranging 21-66. Baseline reports finalised and submitted in April 2024. Similarly, desk-based gender study and assessment was done. / The adaptation workshops further engaged a total of 121 participants, comprising of 47% women in dialogue and collaboration to identify key issues and develop solutions.
1.2: Number of champions in each district who are able to continue with GALS after the project (sustainability).	10 to 20 champions selected in Montepuez. - 50% male/female, balance of ethnicity and religion	Achieved. 30 champions are active in Montepuez. 16 male, 14 female.

Output Title	CDD set up necessary networks/infrastructure in the three implementation districts to facilitate Component 1 activities e.g. grant dispersal in Year 2 (Component 1; Empowerment)
Output number:		2	Output Score:	B
Impact weighting (%):		16.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1: Number of community officers contracted to work on PSMP	Baseline N/A / Target of 2 per district (total of 6). One man, one woman per district with different ethnic & religious backgrounds.	Achieved: A total of six community officers were hired, (two per district of either sex). Ethnicity, religion and sex were factors considered as part of conflict sensitivity. One man, one woman per district that jointly cover all three local languages (Macua, Makonde and Mwani).
2.2: Number of shared offices established.	Baseline N/A / Target: 1 in Mueda, 1 in MdP	Not achieved. One office established in Montepuez and the other districts not yet.

Output Title	Communications messaging/content produced and tested/piloted.
Output number:		3	Output Score:	B
Impact weighting (%):		16.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1: Number of content items tested in each of the three districts.	2 x sample content, supportive of PSMP objectives, developed and tested in each of the 3 districts and feedback/lessons captured.	Not achieved: ‘Partial’ testing was done, and content developed (though not all was tested due to quality issues). Lessons captured (see annual report).

Output Title	Influencing activities conducted to secure buy-in from key political and security actors. Establish the merit of creating community-led police liaison forums.
Output number:		4	Output Score:	B
Impact weighting (%):		16.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1: % of planned meetings conducted with key project stakeholders, with a positive outcome (i.e. they understand objectives of project and are willing to engage).	Meetings conducted with stakeholders from all 3 (i.e. 100%) of the key neighbouring countries: Rwanda, Tanzania, Botswana. Insights captured in C3 reports/briefings.	Achieved. 8 of 9 planned national level meetings in Mozambique conducted, as per C2 workplan, and insights captured in C3 reports/briefings. / Meetings conducted with stakeholders from all 3 (i.e. 100%) of the key neighbouring countries. Evidence and details provided in trip reports.
4.2: Comparative analysis with other African community policing experiences produced and lessons learned captured from international actors e.g. Rwandans, Tanzanians, SADC	Comparative analysis report.	Not achieved. The activity is planned for next financial year.

Output Title	Regular, high-quality research reports and analysis produced and disseminated.
Output number:		5	Output Score:	A
Impact weighting (%):		16.5	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
5.1: Number of policy briefs/working papers published	First policy brief published	Achieved. Two policy briefs drafted: . First brief published in December 2023 (ahead of schedule), second published in April 2024. / ‘Calls for denunciation and vigilance in a context of fragile State: reconstruction of public institutions and survival strategies for returned populations’ / ‘Weakening of the State, erosion of the social fabric and lack of prospects for resolving the conflict’
5.2: Number of conflict analysis/context updates and conflict flash reports	1 conflict update (flash reports have no target - only as needed)	Partially achieved. The SRO confirmed virtual meetings to diplomatic community have been held but not every month and no records were submitted.
5.3: Number of advocacy activities conducted e.g. briefings for national/regional/international actors, themed webinars, participation in symposia in Maputo, etc.	At least 3, targeting different national, provincial, international stakeholders	Achieved. Three webinars. advocacy activities conducted. / 1. OMR webinar 13th Feb. How is Cabo Delgado? What are the steps for peace? / 2. Institute of Security Studies (ISS) monthly closed webinars / 3. Event with Instituto Camoes Feb. 2024

Output Title	The project team benefit from opportunities to broaden their knowledge of GESI and peacebuilding topics and regular review on the incorporation of these topics in the project is conducted to facilitate improvements.
Output number:		6	Output Score:	C
Impact weighting (%):		16.5	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
6.1: % of (core) project team attending internal trainings	2 workshops held on GESI/PB topics with 75% attendance of core team.	Not achieved. One gender and peacebuilding workshop held for staff.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1.1 : The activities to deliver this output revolve around establishing peace champion groups in the three districts, Montepuez, Mocimboa da Praia (MdP) and Mueda including developing a baseline and an implementation plan to operationalize the Gender Action Learning System (GALS) methodology which contributes to peace and resilience. The purpose of the GALS Peace and Resilience approach is to support participants in developing a strong vision for change. Desk-based gender study and gender rapid assessment done to support the process.

The activity was on track and essentially offered a baseline against which milestones will be measured and hence on track. However, the baseline regarding perceptions around the GALS methodology was captured generically and no figures given. The awareness levels in the 3 districts differed with familiarity with the methodology mentioned in Montepuez and no familiarity in Mueda and MdP. Against a target of 10 to 20 champions to be re-integrated into PSMP, 30 champions were identified.

Output 2: Activity involved the setting up of necessary networks and infrastructure in the three implementation districts to facilitate output 1 activities. This included the recruitment of community officers in the three districts and establishment of offices. Although this target was met, this activity is an extension of inception phase activity.

Output 3: The inception report refers to two strands of messaging as part of communication strategy and a cross-cutting activity, namely 1) positive messaging designed to create awareness of, and engagement with PSMP and 2) counter narratives that directly and credibly undermine and provide alternatives to extremist messaging. The implementation plan outlines a robust process for the activity through strategy development, audience analysis, creative development and testing, dissemination network mapping, channel mapping, message development and testing and Year 2 comms planning.

However, the activity is poorly defined, lacking clarity on what messaging is being tested and to what end. The target audience should be clearer. No reports have been shared for Quarter 1 and 2 whilst there is limited information in the Quarter 3 and in the end of year report. Therefore, there was no evidence that this output was achieved.

Output 4: This activity was designed to facilitate the key project stakeholders in understanding the objectives of the project and to secure engagement. Activity included national level meetings in Mozambique and meetings with key stakeholders in neighbouring countries. Despite bureaucratic delays meetings were conducted and cross learning occurred as demonstrated through reporting, though the comparative analysis report was not produced.

Output 5: The activity for output 5 included high quality research reports and analysis including briefs, conflict analysis and context updates and advocacy activity at national, regional and international level.

Policy briefs were tailormade to inform and influence fostering dialogues between the relevant stakeholders in the sector and pursue several research lines. Research reports were shared with and well received by a wide range of stakeholders.

Output 6: This activity included internal training sessions for the programme implementation team including downstream partners. The target was met, through the delivery of one gender and peacebuilding workshop was held for staff. This output area would be better married with output 1. Staff training is a prerequisite to the GALS capacity building of community facilitators.
Lessons learned this year and recommendations for the year ahead:
- Effective midline or endline baselining needs to be undertaken to gauge change in the perceptions.
- Due to the raised levels of violence in Mocimboa da Praia (MdP) and Mueda, the programme team has had to adapt planning to ensure delivery could effectively manage the increased Health, Safety and Security (HSS) requirements demonstrating the need for flexibility and contingency planning. Lack of graduates to fill in the positions meant the project had to alter standards on recruitment, focusing more on experience rather than professional qualifications. This has not affected quality. Availability of rental space and high demand for the same have increased costs.
- There is a need to capture beyond numbers trained and have an outcome indicator that measures changes in attitudes, behaviour and practices because of the training.
General conclusions and recommendations on the outputs:

- There is inconsistency in activity/output descriptions. In the quarterly reports, references are made to “workstream” while in the annual report the same activity is captured as “components”. The quarterly reports should adopt the same terminology as reflected in the results framework.
- Activities in the Detailed Implementation Plan (DIP) are not coded hence difficult to follow what they are, and how it is linked to the RF.
- There is overlap of activities between Components 2 and 3 and to some extent Component 1. Though it is assumed that Component 3 activities inform the other two, there are activities in Component 3 that can essentially be ascribed to either 1 or 2. There is need to define the components/Outputs/Outcomes clearly in both the RF and other documents (reports, DIPs). Component 3 is expected to enhance coordination in conflict management across various sectors and yet it is largely research oriented.
- Communication is explained as a cross-cutting activity, and yet it is slotted in Output 2 in the results framework.
- Output 6, referred to as internal GESI, has not been populated in the RF in terms of progress. Unclear how GESI is mainstreamed into programming though it is assumed the GALS methodology is gender sensitive. The project team need to robustly integrate GESI in all activities and apply the GESI Markers. Marrying outputs 1 and 6 may be useful.
## D: VALUE FOR MONEY

The Peace and Stability Mozambique Programme (PSMP) Value for Money Framework (VFM) seeks to ensure that the programme’s design, delivery, management and evaluation maximises the impact of each taxpayer’s pound spent to deliver the programmes objectives.

The PSMP uses the four ‘E’ Value for Money Framework, which is the standard UK government approach to assessing value for money:

- Economy – buying inputs
- Efficiency – delivering outputs
- Effectiveness – achieving outcomes
- Equity – value to whom
The PSMP VFM is designed to answer the following Monitoring, Evaluation & Learning (MEL) questions against ‘E’:

- Economy – Are we buying inputs (staff, consultants, materials used to produce outputs) of appropriate quality, at the right price?
- Efficiency – How well are we converting inputs into outputs? (‘Spending well’)
- Effectiveness - How well are the outputs produced having the intended effect? (‘Spending wisely’)
- Equity - How fairly are the benefits distributed? To what extent have we reached marginalised groups? (‘Spending fairly’)
VFM performance compared to the original VFM proposition in the business case:

Outlined below are examples of how the Programme is seeking to achieve VfM across its various components. It is clear significant progress is required in year 2 for the Programme to be assessed as delivering the VfM proposition as envisaged in the original business case.

Economy: To ensure that purchases are made at the right price and quantity, the Programme team spent time reviewing multiple operational and logistics providers across the components and locations to ensure the best value for money options were selected. Through close maintenance of supplier relations, the Programme was able to secure stable prices across the year therefore solidifying unit costs. The PSMP team have worked closely with partners to understand what resources are needed to deliver planned activity and where possible, the team has grouped deployments across components to lower overall costs and to ensure that the quantity of resources such as car rental can be lowered. In some instances, to lower the cost of logistics, the PSMP team has leveraged partner’s pre-existing relationships with suppliers instead of forging new relationships where businesses may charge a premium. To further maintain the Programme economy, the team ensured that during the inception phase, research and meetings were based remotely where possible to cut unnecessary deployment costs. From April – October, PSMP invoiced 29.5% of the total budget for the year with operations and logistics costs accounting for 9.4% of total invoiced costs from the period, with the remaining 90.6% of invoiced costs accounting for staff time. This permitted over 70% of the budget to be available for the last five months of the FY when delivery commenced.

Efficiency: To ensure Programme efficiency, the Programme team has focused on working with local implementors in Mozambique. By strategically allocating tasks, e.g. combining trips for outcomes 1 and 3, the Programme has ensured efficient use of resources. Over the year, the Programme has reduced international deployments and enforced a greater emphasis on building the capacity of the in-country team with over 60% of staff salaries paid to local Mozambicans. The programmer’s communications expert sourced local partners to assist with the strategic communications component who were able to join the GALS team to capture key insights from the delivery whilst learning from the expert. This not only reduces costs but also helps to build Programme sustainability. The team has spent significant time evaluating delivery times to ensure Programme funds are being appropriately spent and that there will not be underspend, but this has also been in liaison with the BHCM to ensure money can be re-purposed where necessary.

Effectiveness: Following the inception period, the team decided to implement the GALS methodology and approach, which supported activities across the three components and works as a platform to further build community engagement for the duration of the Programme. During the inception phase, it was thought that the GALS team may only be able to identify 10-20 peace champions, which was targeted in the results framework, however the team were able to identify and train a total of 30 champions at no-extra cost. Though activities to support outcome 1 have been effective, there has been little progress towards outcomes 2 and 3. Progress has been process focused and an extension of inception phase especially in relation to output 2, delivering to outcome 1.

Equity: The Programme remains committed to ensuring that all activities reach potential recipients, irrespective of their background. The three adaptation workshops, held between January and March 2024, saw a total of 121 participants, with 47% female participation. Additionally, the four validation meetings that followed saw a total of 109 participants, including community leaders, government authorities and local forces, with 24% female participation. The team further ensured that provisions were made during Ramadan so that attendees of the GALS workshops were given breaks to pray and further those who were fasting could take their food home with them. Equally, TAG has monitored gender and conflict sensitivity throughout the Programme.

Assessment of whether the Programme continues to represent value for money
Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, there is evidence the programme should continue, albeit with significant improvements made across the programme (as outlined in the recommendations and those already underway since the review period).

E: RISK

Overview of risk management

The review team have established that risk is being managed and have seen examples of effective risk management processes and documentation.

Risk 1: Through year 1, the programme was confronted with a significant risk of diminished engagement with beneficiaries due to the programme partners restricted access to hard-to-reach communities and key stakeholders critical to the programme. Delays in the programme’s inception phase further inhibited stakeholder buy-in and traction.

Response: The programme has worked with the British High Commission Maputo (BHCM) to officially present the programme to the Government focal points in the Ministry of Defence, Ministry of Interior, Ministry of Justice and Agência de Desenvolvimento Integrado do Notre (ADIN), which are key to endorse the implementation of activities. Throughout quarter 4, the PSMP team ensured delivery was planned collaboratively with local leadership and employed effective feedback mechanisms to inform adjustments to activities. Further, the PSMP team kept the BHCM informed of any scenarios in which stakeholder management may need to be escalated, across quarter 3, weekly coordination calls permitted the rescheduling of a meeting with the Director for the Ministry of Foreign Affairs to reconcile misconceptions surrounding the programme. This will be taken forward into the next year of the programme.

Risk 2: Reported attacks in Cabo Delgado, particularly in Mocimboa da Praia and Macomia have meant it is unsafe to travel by road to these locations. Insurgents in the region are causing residents to flee, particularly after the killing of four civilians in Mocimboa de Praia district on January 5th, 2024, with Islamic State claiming responsibility for the attack. The instability poses a risk of attack particularly on road moves, meaning the programme must take necessary steps to protect deploying team members to reduce the threat to life.

Response: The programme has engaged with both local and international security experts to ensure the HSSP are regularly updated, and our security operating procedures are reflective of the risk situation. In cases where the team were previously going to travel to locations in Cabo Delgado by car, they have flown to mitigate the risk of attacks during road moves. The team is now sharing tracking information whilst deployed in fields and are provided with pre-deployment briefs ahead of their deployment.

Risk 3: The risk of border crossing from Mozambique to Tanzania may mean that team members face harsh treatment from the SADC mission and other local security actors, once the SADC mission withdraw.

Response: HSS lead to provide pre-deployment briefs, warning teams of the risk of travelling between the borders and the proper procedures to keep in mind and how to escalate risk. Team to use flights where possible to avoid having to cross border.

Risk 4: The increased cost in deploying teams to the field because of needing to implement heightened security measures has increased pressure on the budget. The programme has had to cautiously spend to ensure that the planned activity was not comprised by these escalated costs.

Response: Value for money measures were put in place to ensure the escalated costs were at the best possible price and grouped across components where possible.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial performance was on track by the end of the financial year, the implementer spent 99% of the allocated budget, £1,300,000.00.

However, BHC programme management colleagues commented that performance throughout the year was inconsistent, and variances were only reduced late in the financial year which may have resulted in a surge of activity later in the year, which has the potential to negatively affect quality of delivery. The following challenges were identified:

- Poor communication - there were changes in the consortium initially proposed on the contract. Part of the work was done in house by Torchlight which was initially allocated to the members of the consortium.
- Consortium members who withdrew from the programme were highly critical of ‘lack of financial transparency from TAG’.
- Insufficient information was provided about the formation of TAG International Development Ltd, this decision was shared after the changes were consolidated. Lack of communication about the creation of TAG led to delays with payments that could have been avoided if information had been shared earlier.
- TAG created more staffing positions mostly based in UK, often without discussing with the BHC first.
- Inconsistencies between amount on the Activity Based Budget (ABB) and the invoices were frequent throughout the year.

Quality and timeliness of narrative reporting and audited financial statements have been inconsistent and need to be improved.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The 23/24 Annual Review was undertaken by members of the UK- Integrated Security Fund East Africa team (Ben Fisher, Elly Imbyandumi, Mahamoud Haji). This involved a visit to Maputo and Pemba for meetings with a range of stakeholders. A wide range of perspectives was provided which has formed the basis for the review. This exercise was also useful for cross learning given that the ISF team manage the Mozambique – Tanzania ISF Borderlands project.

Monitoring: The PSMP implementing team admitted it had been challenging to gather primary feedback from communities where PSMP was implemented in year one due to access constraints (e.g. field work coincided with the rainy season) and because some were still in inception. However, the recruitment of community officers and a BHC officer who will be based in Cabo Delgado will support improved monitoring next year. In the meantime, photos of workshops and trainings and site reports have been submitted to the PSMP programme management team.

Evaluating: The MREL Advisor worked with the GALS team to ensure that the GALS fieldwork could also provide relevant information to baseline PSMP results framework indicators. The GALS reports produced at the end of year one provided information collected from potential beneficiaries that will inform the creation of realistic results framework indicators for year two and their baseline. This is of greatest relevance for indicators measuring the resilience of the communities and providing insights into what resilience means to different stakeholder groups. Furthermore, the learning from GALS activities has highlighted some areas where evidence gaps remain, and where we can target research activities under components two and three. For example, the GALS findings highlight the important role of local forces in certain districts, like Mueda, but it is not clear how these local forces could be incorporated into the police. GALS findings also indicate that PSMP could play a role in helping the police find their way and become a resource again in communities. In this regard component one and two activities can be mutually reinforcing

Research: The programme has an extensive research element, and research has been disseminated well to the wider international community. However, the programme would benefit from greater inclusion of the research and subsequent lessons into future programme development.

Learning: Authorisation to operate, as well as some degree of trust and awareness of the nature of the programme in these communities, is a necessary first step before deploying surveys or conducting interviews and focus groups with beneficiaries. However, the inclusion of the GALS methodology presented an opportunity to mitigate this challenge and has been a key achievement, helping to design planned programme activities for year two and complement, as well as validate, the research produced under component three. The team also gathered community input into the branding and logo design for PSMP. To ensure that cross-component learning and collaboration is effectively promoted, the MREL Advisor has set up a monthly cross-component call to protect space for these discussions and make sure learning is disseminated in a timely manner and not just collected at the end of each quarter.

The AR team recommends more interaction and sharing of learning between the implementing team and HMG. Teams need to find ways to ensure strategy development and implementation is based on evidence generated by the programme.

Date of last narrative financial report	N/A (first year of programme)	Date of last audited annual statement	N/A (to be completed by March 2025)