## Annual Review Template

Title: Peace and Stability in Mozambique Programme
Programme Value £ (full life): up to £5m		Review period: 01/04/2024-31/03/2025
Programme Code: 301326	AMP start date: 23/11/2021	AMP end date: 31/03/2026

Summary of Programme Performance
Year	21/22	22/23	23/24	24/25
Overall Output Score	A	B	B	A
Risk Rating	Major	Moderate	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301326 Documents
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006861.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
The Peace and Stability in Mozambique Programme (PSMP) has supported initiatives to prevent the spread of violent extremism and foster peacebuilding in Cabo Delgado/Northern Mozambique, as well as to implement the 2019 Maputo Peace Accords. In the review period (March-24/March-25), the sole focus of the programme was on the prevention of violent extremism/peacebuilding in Cabo Delgado/Northern Mozambique. Most of these efforts were implemented by a consortium led by TAG, which worked on four areas:
[note] TAG leads a consortium of: Observatorio do Meio Rural/OMR, which assists on research/analysis; Azul Foundation, which works at provincial/local level with communities and manages grants; and the African Policing Civilian Oversight Forum (APCOF), which leads the work with security/justice actors.
1. Strengthening community resilience against violent extremist influence through the establishment of community groups that deliver peace and development projects through a grant mechanism.
2. Supporting dialogue at provincial and local levels between public authorities, civil society, and community representatives.
3. Working with security and justice actors to promote community-centred approaches that improve accountability, human rights protections, and citizen trust.
4. Supporting mechanisms for conflict management and coordination with international partners, including through the production and dissemination of high-quality research and analysis.
Additionally, the programme provides technical assistance on corporate social responsibility to the private sector and on the prevention and combatting of violent extremism to the Mozambican Ministry of Defence, as well as funding a full-time country-based staff position in Cabo Delgado, who is managed directly by the British High Commission Maputo (BHCM).
In the review period, BHCM and programme partners adapted to a shifting operating environment. While some areas in Cabo Delgado saw improved access, the security situation remained volatile, with the increased use of Improvised Explosive Devices (IEDs) by insurgents marking a significant tactical shift, as well as markedly more expansive geographic reach and increased attacks on security forces. A major cyclone in early 2024 further disrupted access and impacted planned activities. National elections in late 2024 contributed to a tense political climate, delaying coordination with some government counterparts. In response, the programme adjusted timelines, rescheduled dialogues, and increased reliance on local actors to sustain delivery. Additionally, two PSMP consortium partners, CDD and ISS, were replaced by the Azul Foundation and the African Policing Civilian Oversight Forum (APCOF).
Summary supporting narrative for the overall score in this review
Based on our assessment of progress on three outputs and the trajectory towards the outcomes, the programme has scored an A. This is based on a score of A for output 1; B for output 2; and A for output 3. Additionally, TAG provided evidence of progress and results across a range of other metrics and indicators, which the programme team monitored in the review period. Finally, there is evidence that the programme is on track to contribute to outcome level changes as well as deliver value for money – further details below.
Major lessons and recommendations for the year ahead
RECOMMENDATION	TIMELINE	RESPONSIBLE(S)
RECOMMENDATION#1: Approve revised results framework. The new results framework will align BHCM’s and TAG’s documents, ensuring greater consistency on objectives and assessment of progress, as well as enabling more streamlined data collection.	Immediately	BHC Maputo
RECOMMENDATION#2: Improve timeliness of feedback and approvals. BHCM will prioritise faster and more predictable internal decision-making cycles.	Immediately	BHC Maputo
RECOMMENDATION#3: Advance central level engagement and structural reform. While the programme made strong gains at the local level, systemic change depends on national-level policy reform and political buy-in. Programme partners, alongside BHCM, should increase engagement with national government actors to advance inclusive governance and rights-based security sector reform, including pressing for the development of a national community policing framework.	By March/26	PSMP team / & BHC Maputo
RECOMMENDATION#4: Leverage donor platforms. Shrinking civic space and the erosion of civil society autonomy are emerging threats to peacebuilding. The programme, alongside BHCM, should use their influence in donor coordination fora to advocate for a protective regulatory environment for civil society organisations (CSOs).	Ongoing	BHC Maputo
RECOMMENDATION#5: Target geographic risk factors. With clear evidence of conflict dynamics expanding beyond Cabo Delgado, particularly into coastal Nampula and Niassa, BHCM should consider additional programming or policy engagement in these regions.	By March/26	BHC Maputo
RECOMMENDATION#6: Strengthen grants’ management and women’s participation. The Seeds for Peace grants delivered results but faced procedural and inclusion challenges. In Year 3, PSMP should continue refining grant systems to better support social transformation goals. New eligibility and financial control measures should be fully institutionalised.	By September/25	PSMP team
RECOMMENDATION#7: Strengthen communications and strategic use of evidence. Research conducted surfaced important insights into the evolving nature of conflict. These findings represent a strong opportunity to influence decision-making. In Year 3, the programme should take a more adaptive and intentional approach to how evidence is communicated and used.	Immediately	PSMP team
RECOMMENDATION#8: Continue strengthening TAG’s risk management and adaptive implementation capacity. TAG demonstrated an ability to adapt delivery in the face of compounding risks. In Year 3, TAG should build on this foundation by embedding risk mitigation and adaptive delivery deeper into its systems and support structures.	September/25	PSMP team

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
In the review period, the Theory of Change (ToC) largely held; however, Mozambique’s post-election context changed some of the assumptions. One of the original assumptions was that "(…) the situation in project intervention areas is not significantly affected by instability due to election cycles, political transitions, or other external factors (e.g., climate change, health crises) that are beyond the control of the project." This assumption no longer holds, as political dynamics in the post-election period significantly impacted local stability and project momentum.
In response, TAG changed some assumptions to their intervention. "(...)The programme maintains sufficient flexibility and adaptability to respond to evolving contextual factors, including security dynamics, political shifts, and environmental challenges." Additionally, it now explicitly acknowledges that "(…) project relationships and groundwork may be disrupted by increased national political instability," emphasizing the importance of adaptable, locally grounded approaches in complex settings.
As for programme impact and outcomes, at approval of the business case, the programme included an overall impact and two outcomes:
1. IMPACT: Improved peace and stability in Mozambique enabled by consolidation on peace process and inclusive resolution of key issues of contestation (power, resources, human rights violations) and perceptions of exclusion and marginalisation.
2. OUTCOME 1: Preventing further radicalisation and violence, fostering peacebuilding and increasing the resilience of communities to extremist influence in Northern Mozambique.
3. OUTCOME 2: Full implementation of the Maputo Peace Accords.
After the first year of implementation (2022), the programme largely concluded its support to the Maputo Peace Accords (outcome 2) and shifted attention to outcome 1. Meanwhile, in mid-2024, a business case addendum proposed a change to outcome 2, broadening its scope to respond to changing regional and global security dynamics. Outcome 2 was amended to:
‘Promote Mozambique’s role as peacemakers regionally and globally including through consolidating the peace process and supporting the full implementation of the Maputo Peace Accords and enhancing their role on the UN Security Council.’
This had no additional impact on the theory of change, nor specific indicators were added.
This addendum also recognised that existing delivery routes were restrictive and included an additional delivery mechanism enabling direct contracting and other procurement methods to allow for increased responsiveness. Activities approved within the business case addendum included a Deployable Civilian Expert to support to the Government of Mozambique/GoM in development and implementation of their Countering and Preventing Violent Extremism and Terrorism Strategy; and a country-based member of staff to be based in Cabo Delgado. These activities are supporting the achievement of outcome 1 – for detailed results, see table below:

Outcome 1	Indicators	Milestones / (March 2025)	Progress
Preventing further radicalisation and violence, fostering peacebuilding and increasing the resilience of communities to extremist influence in Northern Mozambique	Individual resilience: % of target groups that: / - reject values supportive of violence / - demonstrate an increased ability to bounce back/adapt / - have an increased social support network / - have a more positive vision of the future	60%	Exceeded: 75% / -Reject violence: 95% / -Ability to bounce back: 65% / -Social support network: 58% / -Positive vision of future: 82%
	% of community who perceive they are excluded or marginalised in some way	Decrease of 5% from baseline	Exceeded: Decrease of 21% (to 39%)
	% of target group who report improved confidence in local security actors / (% of target audience who express a positive change in attitude or beliefs towards security providers as a result of exposure to the communications messaging) (disaggregated by district)	N/A	BHCM did not collect data to measure this indicator. / TAG measured a similar indicator (in red), with the following result: / 52%
	% of target group that feel they have access to effective dispute resolution (i.e. somewhere to go when they have a problem)	N/A	Indicator not active anymore due to overlap with the Borderlands project – no data collected.
	GoM ability to manage conflict improves	GoM has plans in place to execute improvements	Achieved. Strategy and new Centre on Prevention and Countering of Violent Extremism have been approved/established.
	Private Sector shows improved engagement and understanding of conflict sensitivity	Mapping of CSR activities completed	Not achieved.
[note] See Annex 2, with details of the logframe and its indicators (MREL plan).

Over the past two years, TAG adapted its activities and approach, and its results framework was revised accordingly (Annex 1). TAG’s updated framework includes a more detailed structure, distinguishing three long-term outcomes and some intermediate outcomes:
1. Outcome 1: Reduced conflict narratives and incentives, increased group and community resilience and enhanced inter-community cohesion
2. Outcome 2: Community perceives improvement in law enforcement responsiveness and behaviour; law enforcement better understand the value and importance of community engagement to achieving their strategic objectives
3. Outcome 3: Greater knowledge of drivers and root causes of the conflict, and greater conflict sensitivity among donor projects in northern Mozambique.

For this annual review, we have used BHCM’s results framework – at impact, outcome and output level. For completeness, and where BHCM did not collect data, we have added info from TAG’s framework. This follows learning from last year’s annual review which highlighted some areas of misalignment in results frameworks.
Going forward, as per recommendations and BHCM’s revised results framework (Annex 3), we suggest a closer alignment between TAG’s and BHC’s results frameworks – while BHC’s framework will retain its two outcome statements, as approved in the business case and addendum, we will share most impact, outcome and output indicators.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to contribute to its outcomes and impact – though with important caveats. The situation in Cabo Delgado remains volatile, and attacks increased in 2025 – programme activities are niche and localised, and their impact is unlikely to be felt immediately, but over several years. The long-term, structural impact will depend on both TAG’s influencing work in the final year of programme implementation and BHCM’s engagement to support this process – including linking this work up to other bigger investments (e.g. WB and UN). Also, whereas the Demobilisation and Disarmament of former Renamo fighters has been completed, there remains questions on the sustainability of the implementation of the Maputo Peace Accords – particularly on reintegration and reconciliation efforts.
For the final year of implementation (2025/26), these are some of the key actions/activities:
1. The programme will deepen its investment in community-led change by strengthening the capacity of peace champions to independently replicate training, start local peace and development projects, and embed long-term sustainability. A sharper focus on follow-up systems will ensure workshops generate lasting transformation, moving from facilitation to embedding local practice.
2. On the ‘Seeds for Peace’ grants, the approach will evolve to focus on quality over quantity, targeting community-designed solutions to pressing issues such as local security and justice. By anchoring grants in joint diagnostics, the programme will promote collaboration and ensure initiatives directly address locally identified drivers of instability.
3. On influencing, the programme will sharpen its strategic influence with a clear evidence-sharing and policy engagement plan aligned with UK priorities. Key focus areas will include insurgency trends, inclusive reconstruction, and access to justice in conflict-affected zones. This work will draw on TAG’s detailed ‘Influencing and Stakeholder Engagement approach’ (Annex 5), whose implementation BHCM will support at political level and through linkages to the Democracy Deepening programme work on human rights.
4. On sustainability, the programme will finalise and publish its working papers, while exploring new partnerships to sustain research impact. The programme will also continue to push beyond local initiatives and engage with central government.
5. Sign an agreement with DCAF (Geneva Centre for Security Sector Governance), through which we will promote and disseminate conflict-sensitive and community liaison training to companies (including from the UK) working in Cabo Delgado. BHC’s new partnership with DCAF, which will come into force in late 2025, will increase companies’ resilience to the context and their ability to mitigate risks of exacerbating conflict through their work, a process which will contribute to conflict prevention and responsible business conduct.
6. Drive local engagement/ownership and sustainability through BHC’s Cabo Delgado liaison officer: BHC’s liaison officer in Cabo Delgado will both monitor TAG’s activities and support their delivery of their work – ensuring local ownership and sustainability.
7. Explore targeted areas of work/training with the security sector/police: There is scope for some additional training, particularly with the police, to kick-start discussions on good practices and respect for human rights. This will go in parallel to our work with the UN OHCHR through the Democracy Deepening programme (DD).
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme should continue – there have been several important results in the review period, and the work remains extremely relevant for BHC Mozambique’s portfolio. The situation in Cabo Delgado deteriorated in 2025, with an increase in attacks – which only adds to the importance of continuing efforts to prevent the spread of violence.
## C. DETAILED OUTPUT SCORING

Output Title	Increased local trust and resilience of groups and communities at risk of violent radicalisation
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress (March 2025)
1.1 Number of people who have been exposed to the adapted GALS peer-to-peer process	850	Exceeded: 1,945
1.2 Number of community initiatives in PSMP implementation areas that led to inter or intra community constructive dialogues	N/A	No data collected on this indicator. / However, 16 Seeds for Peace Grants have been funded up until this point.
1.3 Number of champions in each district who are able to continue with GALS after the project sustainably	30	Exceeded: 61
[note] GALS stands for Gender Action Learning System, and it is a tool/methodology for conflict prevention and resolution through the promotion of gender equality and empowerment of individuals and communities to address power imbalances and inequalities

Briefly describe the output’s activities and provide supporting narrative for the score.
In the review period, of the three indicators, two milestones were exceeded, and one was not measured.
Six GALS’ workshops were completed in the 3 target districts with over 1,945 people attending across them. Montepuez saw particularly high levels of attendance, while Mocímboa da Praia remains the most challenging district in terms of uptake. These individuals are actively continuing GALS dissemination within their communities. The programme continues to see the importance of a district-tailored approach: in Mueda, deeply rooted gender norms required additional focus on the topic, which led to more balanced participation. Trust-building in Mocímboa da Praia continues to be slower due to long-term conflict and displacement. Engagement is always highest in Montepuez, as the district has been previously exposed to GALS and there is a stronger local infrastructure.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Work under this output underwent changes in the review period. TAG monitored its impact through a revised set of outputs and indicators (for details, see annex 1), whereas BHCM did not manage to collect data on one of the indicators. Given these changes, and to improve the alignment between the results frameworks of BHCM and the programme’s implementing partner, BHCM will add the following output indicators for the final year of implementation:
Indicator(s)	Target (March/2026)
1.1. Number of champions in each district who are able to continue with GALS after the project (sustainability)	Another 30 in each district
1.2 Number of champions attending Training of Trainers workshops (disaggregated by district)	25 in each of the three districts for each round
1.3 Number of people who have been exposed to the adapted GALS peer-to-peer process (disaggregated by district)	225 (75 per district) for each round.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
In the review period, the programme made progress in responding to the lessons and recommendations identified in previous Annual Review. The programme strengthened in-country capacity by reducing its reliance on international staff and expanding the role of local actors.
The expansion of the Seeds for Peace grants further reinforced grassroots networks and provided a clear pathway for community-drive initiatives to transform from planning to implementation. The programme addressed earlier concerns about high operational costs and limited in-country presence by localising implementation through Azul.
Key lessons this year reaffirm the importance of deeply contextualised delivery. Success depended on building trust with communities and local authorities. However, challenges remain. Reintegration of demobilised youth is a critical gap, and shrinking civic space threatens the programme’s ability to sustain inclusive dialogue. While radio-based communications were effective in reinforcing community messaging, their reach remains limited to certain geographic and demographic groups, and a more comprehensive communications strategy is needed.
Looking ahead, PSMP aims to refine this digital approach, deepen its reintegration and civic space monitoring efforts, and embed a more systematic approach to sharing learning and influencing policy across partners.
Output Title	Improved accountability and responsiveness of security and justice sectors
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Extent to which community target group state they have seen an improvement in the security providers responsiveness and behaviour (highlight perceptions of women, minorities, IDPs etc and see perceptions are different for different security providers (local forces, police, etc.)	2 change stories detailing increase in responsiveness and behaviour of security providers	No specific data collected for this indicator. / However, 2 changes stories below highlight progress in building trust between security providers and community.
2.2 % of police target group (commanders and frontline officers) that state they believe it is important to engage positively with the community as part of their work / (TAG’s indicator: % of justice, protection and security actors that report they feel more responsible for solving community safety, security and law enforcement issues)	60%	No specific data collected for this indicator. / However, a comparable indicator that can be found at TAG's results framework (in red): / 52% of justice, protection and security actors reported they feel more responsible for solving community safety, security and law enforcement issues

Briefly describe the output’s activities and provide supporting narrative for the score.
Neither TAG nor BHC collected data for the current indicators in the results framework, but similar indicators showed progress. This was mostly due to miscommunication – TAG had a new set of indicators, and BHCM has not yet changed its results framework accordingly.
During the review period, the programme made meaningful progress in strengthening trust and engagement between communities and security providers in northern Mozambique. While the specific indicators under Output 2.1 and 2.2 were not measured, the programme continued to monitor progress through alternative measures and qualitative evidence.
Under Output 2.1, the original indicator aimed to assess whether community members perceived improvements in the responsiveness and behaviour of security providers. Although this indicator is no longer tracked, two compelling change stories illustrate how the programme has contributed to improved relationships and accountability.
Change Story 1:
In the review period, the programme contributed to a notable shift in how security and justice actors engage with communities in northern Mozambique. Previously, interactions between communities and security forces were marked by mistrust, limited dialogue, and little accountability. Recognising this gap, the programme introduced a series of district-level workshops grounded in human rights principles and participatory facilitation. Over 170 participants, including community members and representatives from the police (PRM), Police Rapid Response Unit (UIR), Armed Forces (FADM), and Força Local, came together in Montepuez, Mueda, and Mocímboa da Praia. Participants co-created shared standards of behaviour, emphasising dignity, responsiveness, and service to the community. These exchanges enabled security actors to listen directly to local concerns and reflect on their own practices. The process culminated in an inter-district workshop that brought together stakeholders across the three districts.
Change Story 2:
Workshops provided a unique space to openly discuss critical topics such as human rights, accountability, and cooperation, an opportunity that is rarely available elsewhere in Mozambique. These sessions began to break down silos and show early signs of fostering cooperation and initiating essential conversations among security actors. The impact varied across districts. In Mueda, where young people are often recruited into Força Local without adequate training, the workshops created a much-needed platform to reflect on the importance of upholding human rights, recognising what constitutes a crime, and discussing how security forces and communities can interact more effectively. In Mocímboa da Praia, a notable moment occurred when an army (FADM) head of ethics division made a public commitment to change his behaviour, and that of his colleagues, demonstrating openness to accountability. Some army members continued to engage in GALS workshops, and a visible shift in trust was observed.
Similarly, Output 2.2 originally measured the proportion of police officers who believed in the importance of engaging positively with communities. A comparable outcome-level measure, which was monitored by TAG, showed that 52% of justice, protection, and security actors now feel more responsible for addressing community safety and law enforcement issues. This suggests a growing sense of ownership and accountability among key actors.
Throughout Year 2, the programme delivered four district-level workshops, reaching 224 participants. These included representatives from the police, armed forces, and other protection actors. However, participation was inconsistent across districts. In Montepuez, police did not attend, and in Mueda, attendance from Rwandan forces was limited. Staff turnover and reassignments also posed challenges to sustained engagement.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Work under this output underwent changes in the review period. Given these changes, and to improve the alignment between the results frameworks of BHC and the programme’s implementing partner, BHCM will add two of TAG’s indicators for the final year of implementation:
Indicator(s)	Target (March/2026)
2.1 Number of security provider groups attending workshops	For each workshop: / Montepuez: 12 / Mueda: 9 / MdP: 12
% of target audience who express a positive change in attitude or beliefs towards security providers because of exposure to the communications messaging (disaggregated by district)	65%

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The programme made progress in response to last year’s recommendations on improving coordination with subnational institutions and strengthening formal recognition of its community engagement work. Over the review period, the programme found that establishing safe and inclusive fora played a critical role in building collaborative partnerships between communities and local authorities. The peer-to-peer structure of the GALS methodology enabled difficult conversations to emerge, including on corruption, gender-based violence, and human rights. However, the fragility of these gains became clear in the context of political volatility. One of the most important lessons was that institutional support, particularly at the provincial and national levels, is essential for sustaining progress and embedding participatory approaches into longer-term governance systems.
Looking ahead, the programme recognises that formal legitimacy must be secured before implementation can safely continue. Without integration into recognised structures such as provincial mandates, training curricula or official codes of conduct, both community facilitators and programme outcomes remain exposed and potentially undermined. To address this, the programme will focus on designing and implementing practical tools that directly respond to concerns raised by district and provincial stakeholders, particularly those affecting the relationship between communities and security providers. These tools will be developed in collaboration with local authorities to ensure institutional relevance and support. In parallel, the programme will work with the BHCM to secure high-level political endorsement, recognising that political and programme efforts must work together to strengthen legitimacy.
Output Title	Improved capacity for conflict management and stronger coordination mechanisms
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of advocacy activities conducted e.g. briefings for national/regional/international actors, themed webinars, participation in symposia in Maputo, etc.	2	Exceeded: 8 webinars, 2 conflict analyses/updates, one symposium in Pemba
3.2 Partners report improved understanding and context analysis supports their policy and programme approaches	90%	N/A: No specific data was collected for this indicator. / However, a comparable indicator that can be found at outcome level: 90% of stakeholders at PSMP events/briefings/lessons sharing that state the information they received is useful or has increased their knowledge
3.3 % of planned meetings conducted with GoM, with a positive outcome (i.e. they are willing to engage)	2	Achieved. At least two meetings with the Ministry of Justice and one with the Ministry of Interior.
3.4 GoM implements x-govt CT/CVE strategy	CT strategy published and communicated publicly	Achieved. CT strategy was approved and published.
3.5 No. of Private Sector CSR workshops	3	Partially achieved. 2 workshops held.
[note] For details of the strategy, see here: BR_56_I_SÉRIE_2025.indd.

Briefly describe the output’s activities and provide supporting narrative for the score.
In the review period, milestones were exceeded/achieved for three of the active indicators and partially achieved for one of them.
TAG delivered two webinars per quarter, two conflict analysis update sessions and one in-person symposium in Pemba. Across all these events, a total of 1080 participants attended. Generally, government authorities at the central level show the least engagement in conflict analysis updates, in contrast to donors, diplomats, and researchers.
While the new results framework no longer includes the indicator on improved understanding at the output level, feedback surveys conducted across our activities show that, on average, 90% of respondents report improved understanding. Collecting stakeholder responses has remained a consistent challenge with low response rates especially at the conflict analysis sessions.
On the back of BHCM’s long-term engagement with the Ministry of Defence, the GoM finalised and approved its National Strategy to Prevent and Combat Terrorism and Violent Extremism. BHCM supported the process through a Deployable Civilian Expert. The document was published in March/25, and it is the GoM’s first effort to structure its engagement on this area.
Also, on our engagement with the government, BHCM held several meetings with the GoM. With the Ministry of Justice, these discussions have paved the way for Mozambique’s membership to the Voluntary Principles of Security and Human Rights. With the Ministry of Interior, the meeting opened a channel for discussions on police training, with a focus on human rights – which the programme is seeking to pick up in its final year.
On our work with the private sector, BHCM, with the support of Peaceful Change, organised two workshops with private sector companies to discuss conflict sensitivity and corporate social responsibility. The workshops were organised in Pemba (March/24) and Maputo (March 2025). Altogether, 10 companies attended the discussions.
[note] Home | PCi
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Work under this output underwent changes in the review period. TAG monitored its impact through a revised set of outputs and indicators, whereas BHCM did not collect data on one of the indicators. Given these changes, and to improve the alignment between the results frameworks of BHC and the programme’s implementing partner, BHCM will add two of TAG’s indicators for the final year of implementation:
Indicator(s)	Target (March/2026)
3.1 Number of research products produced (PEAs, Conflict updates, policy briefs)	At least 8 research products.
% of stakeholders at PSMP events/briefings/lessons sharing that state the information they received is useful or has increased their knowledge	90%

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The programme addressed last year’s recommendations to strengthen its strategic positioning and clarify the role of research and coordination. This shift was reflected in the development of a more deliberate influencing strategy, tighter alignment with BHCM priorities, and stronger integration of research outputs into programme decision-making.
One of the most significant achievements was the dissemination of high-quality conflict analysis, which improved coherence across diplomatic, development, and humanitarian actors. PSMP’s research received highly positive feedback: over 90% of event participants found the content useful, and 80% reported they would directly apply it in their work. A March 2025 survey confirmed that all respondents who had attended earlier sessions had already used the information to inform programming or policy discussions.
The year’s success was a reminder of a key lesson: namely that credible, timely, and politically sensitive analysis, delivered through trusted relationships can meaningfully shape discourse and coordination, even in shrinking civic spaces. These interactions reflect a growing reputation for timely, context-specific insight, and show the value of PSMP’s positioning as a trusted, non-partisan actor.
Looking ahead, the programme will consolidate this momentum by delivering on its newly formalised ‘Stakeholder Influence and Engagement Plan’ (Annex 5) – as well as continuing to deliver tailored training to the government. This includes curating bi-monthly thematic learning events for donors, government, security actors, and civil society, focused on the programme’s tested approaches and practical tools. A strategic shift toward multichannel communications, including a new Facebook page, will complement in-person engagement by enhancing real-time visibility, expanding reach beyond radio, and positioning PSMP as a trusted source of grounded, context-specific insights. The programme will prioritise three influence themes: tracking the security situation, supporting inclusive return and reconstruction, and strengthening access to justice in marginalised communities. Additionally, BHCM will continue its niche, technical support to the Ministries of Justice, Interior and Defence.

## D: VALUE FOR MONEY (1 page)
Key cost drivers and performance
VfM performance compared to the original VfM proposition in the business case
In the review period, the programme made substantial progress in strengthening value for money across the four metrics: Economy, Efficiency, Effectiveness, and Equity. VfM was enhanced not only through financial controls and cost management but through demonstrable improvements in community-level outcomes, adaptive learning, and evidence-informed delivery.
Economy
The programme delivered cost savings without compromising quality or coverage. These measures addressed concerns from Year 1 around high operational costs, with overall unit costs in Year 2 reduced significantly.
Key efficiencies included:
- Localisation of delivery: TAG replaced Maputo-based NGO CDD with local partner Azul. This led to savings of £149,000 while maintaining coverage with fewer field officers.
- Smarter logistics: TAG’s vehicle hire and its travel costs were cut by nearly 50% through use of local suppliers and the UN Humanitarian Air Service, saving over £37,000 annually.
- Cost-conscious planning: TAG’s bundling of workshops and optimising deployments avoided unnecessary trips, saving an estimated £19,000 in logistics, which was reinvested into programme delivery.
Efficiency
Operational efficiency improved through better staffing structures and internal coordination:
- Greater localisation: 80% of TAG’s invoiced delivery days were delivered by Mozambican staff (up from 60% in Year 1), reducing international consultancy costs and improving ground presence.
- Lean consortium structure: With the exit of two partners, TAG streamlined roles and delegated field delivery to Azul, reducing bureaucracy and overlap.
- Collaborative delivery: Close coordination with the Borderlands programme avoided duplication and enhanced complementarity with other UK investments.
Effectiveness
Year 2 marked a shift from foundational setup to delivering tangible outcomes:
- Accelerated progress: Most of the outcome indicators are on track.
- Grants turning plans into action: 16 community-designed peace initiatives were funded under the Seeds for Peace mechanism, exceeding quality benchmarks. These targeted drivers of local conflict such as access to water, youth livelihoods, and local justice.
- Behavioural change and ownership: GALS participants reported improved family communication and conflict resolution, with 96% stating the programme had a lasting positive impact. Community “peace champions” became role models, fostering locally owned peacebuilding.
Equity
The programme embedded equity across its operations, with strong emphasis on gender and inclusion:
- Women’s leadership: 44% of approved grants were women-led, up from 33% of initial proposals. Tailored support helped women overcome confidence and literacy barriers.
- Inclusive participation: Activities were adapted to include youth, religious minorities, and remote communities. Cultural and linguistic adjustments (e.g. workshop scheduling during Ramadan, use of local languages) enhanced accessibility.
- Reaching the most marginalised: Mobile money enabled secure grant disbursements to recipients in remote or insecure areas, especially women without bank access. Additional support was provided for people with low literacy or disabilities.
Assessment of whether the programme continues to represent value for money
Based on progress in the review period, the programme continues to represent value for money and remains a strategically important investment within BHCM’s portfolio. The review period marked a significant shift from foundational activities toward tangible outcome delivery and early sustainability gains. By the final quarter, 91% of TAG’s milestones had been met or exceeded.
The launch of community-driven peacebuilding initiatives through the Seeds for Peace grants directly addressed prior concerns about the feasibility of outcome activities and their sustainability. Moreover, increased local delivery, smarter cost management, and better partner coordination have addressed operational inefficiencies identified in the Year 1 review.
Finally, the value of the programme extends beyond direct implementation. The programme is actively leveraging its two years of learning to inform and influence other actors in the field, contributing evidence-based insights that reflect our distinctive approach and experience. Given these achievements, Year 3 presents a critical opportunity to consolidate momentum, scale promising approaches (such as GALS and community-led grants), and further embed strategic influence through improved communications and research uptake.
E: RISK
Overview of risk management
The programme’s risk rating remained major – and within the programme’s and BHCM’s risk appetite. Our partners operate in a sensitive environment – external risks remain major, and with a downward trend, given increasing attacks and violence in Cabo Delgado. With this worsening of the security situation, TAG changed its approach to ensure the delivery of activities and the security of its staff. This meant, for example, fewer road trips and more workshops in Pemba. Through BHCM/TAG weekly catch-ups, risks and mitigating actions are discussed. And both BHCM and TAG keep regular engagement with provincial and local authorities to monitor the situation – both to mitigate risks but also to receive assurances from authorities that work can continue.
On fiduciary risks, TAG has improved its financial controls to avoid misuse of grants. Meanwhile, the programme improved its due diligence of grantees and is putting together a policy to inform the use of non-official receipts – which is common in the context of Cabo Delgado, particularly outside of Pemba. This should help prevent any further incident.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Financial Overview and Budget Distribution
During the review period, the programme disbursed £1,539,905 across its interventions. TAG, which accounted for over 97% of the total budget, managed its resources with financial discipline. Our spend on the programme-funded staff in Cabo Delgado and on the Deployable Civilian Expert (DCE) through Palladium showed deviations from planned budgets (table 1).
Table 1: Budget distribution by project
Project	Planned budget (£)	Actuals (£)	Distribution (%)
TAG	1,500,000.00	1,500,328.42	97.43
Programme Funded Staff position	39,013.69	32,331.31	2.10
Palladium	10,000.00	7,245.29	0.47
Total	1,549,013.69	1,539,905.02	100.00

The table below shows a comparison of planned and actual spending across Admin Costs, Programme Costs, and Grants.
Table 2: TAG planned and spending budget

Admin Costs increased due to strategic investments in local delivery, staffing, and coordination, reducing reliance on international consultants and enhancing field presence.
Programme Costs decreased, reflecting efficiency gains through smarter logistics, bundled activities, and streamlined partnerships. Despite lower expenditure, outcomes improved.
Grants enabled 16 community-led peace initiatives, exceeding benchmarks and enhancing effectiveness and equity. Grant funds were fully utilised in Year 2, directly contributing to community ownership, peacebuilding, and equity, addressing prior concerns about sustainability.
Overall, the close alignment between planned and actual spending across both years demonstrates good financial management. The programme transitioned from foundational setup to tangible delivery, with adaptive learning and community engagement at its core.
Forecast Accuracy and Compliance
Timely communication of forecast changes remains an area for improvement.
While TAG’s performance strengthened, some compliance issues persist. Notably, an audit requested in early 2024 for inclusion in the 2023–2024 annual review faced delays. Agreement was only recently reached, resulting in the audit covering both financial years 2024 and 2025.
Strategic Relationship Management
TAG scored 87% on the Strategic Relationship Management scorecard. Areas requiring further attention include:
- National-level engagement and influence.
- Sustainability strategy, with a focus on local ownership.
- Risk management, particularly in information sharing and contingency planning.
Fraud Mitigation Measures
The Grants Steering Committee implemented several improvements to their processes to mitigate risks:
- Transferred land ownership to the programme.
- Increased monitoring and post-disbursement check-ins.
- Enhanced beneficiary training on financial reporting.
- Shortened project phases to reduce exposure.
- Strengthened social accountability via the GALS peer-to-peer system.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
During the review period, monitoring and evaluation (M&E) activities were primarily conducted through partner reporting, supplemented by selective field monitoring and stakeholder engagement. Although BHCM staff had planned field visits to activity sites, deteriorating security conditions led to the postponement of these visits. However, BHCM personnel based in Cabo Delgado successfully monitored activities in Montepuez and provided positive feedback. Engagements with provincial government counterparts in Pemba also yielded insights into programme performance. Monitoring was further supported by TAG andthe external M&E supplier, whose weekly catch-up meetings and quarterly reports helped maintain oversight of operational challenges and strategic progress. TAG also led the refinement of output indicators to better reflect evolving programme priorities, such as the shift from general GALS workshops to a sustainability-focused Training of Trainers (ToT) model.
Evidence
Evidence collection during the review period was largely qualitative, with significant contributions from TAG’s monitoring reports and stakeholder feedback. The programme adapted its indicators to better align with contextual realities and strategic shifts, such as the introduction of ToT sessions and the removal of time-bound or less relevant measures.
Learning
The programme employed several learning mechanisms throughout the year, including quarterly workshops, stakeholder briefings, and peer-to-peer exchanges. These platforms facilitated the sharing of lessons, contextual insights, and practical tools among community members, security actors, and government representatives. Looking ahead, the programme aims to embed a more systematic approach to learning and influence. This includes bi-monthly thematic events, expanded digital communications, and continued technical support to government ministries.
Progress on recommendations from the previous AR
Since the programme scored two consecutive Bs in its annual reviews, BHCM moved the programme and its implementing partners into a ‘Performance Improvement Action Plan’. This plan was mostly completed – as per Annex 4. Additionally, there was progress across all other recommendations from the previous AR.
R#	Recommendation from previous AR (2023/4)	Progress
R#1	Develop Programme Performance Improvement Plan for agreement at the PSMP Steering Committee. This should include an updated Delivery Plan, a stronger role for BHC’s new staff member in Pemba, more ambitious milestones for year 2, endline baselining, strengthening of grant management and resourcing and review of programme partner staffing (including potential for a greater footprint in-country).	Mostly completed – see annex 4.
R#2	TAG to present to PSMP steering committee on a bi- annual basis to ensure alignment between strategy and programme objectives and agree forward looking government, international community engagement plan. This will include setting a programme of engagement with government and the international community (including through the soon to be established Cabo Delgado working group) to support greater co-ordination on peacebuilding, development and humanitarian actors working on Cabo Delgado and agreeing key messages.	Mostly completed – TAG is presenting to wider BHCM quarterly on lessons learned, and BHCM is inviting other partners to attend sessions. TAG also presented a ‘Stakeholder Engagement Plan’, which BHCM approved.
R#3	Scope use of third-party monitoring to ensure compliance and due diligence of grant mechanism.	Not completed.
R#4	HMG and PSMP should improve learning between grantees, through initiating lessons learn sessions across grantees and other UK investments to demonstrate what works and doesn’t, including sharing good project management practice in the context. These lessons to be documented and shared with HMG and other donors.	Not completed.
R#5	Adopt more consistent wording to describe activities/outputs, aligned to those in the RF	Completed with revised results framework.
R#6	Develop communications plan for how to best manage expectations of grantees given modest amount of funding available.	Done.

Date of last narrative financial report		Date of last audited annual statement