## Annual Review Template
Title: Animal and Plant Health Innovation and Evidence Delivery (APHID) Platform
Programme Value £ (full life): £37,000,000		Review date: 8th June 2025
Programme Code: 301328	AMP start date: 8th March 2023	AMP end date: 31st March 2028

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Programme Documents:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301328/documents

# SUMMARY AND OVERVIEW
What is One Health?
First, it is the concept that the health of humans, animals, plants, and the environment are inextricably linked and interdependent.
Second, it refers to the collaborative and sustained effort of multiple disciplines working together locally, nationally, regionally, and globally to attain optimal health for all living things and the ecosystems in which they co-exist.
Description of programme
Food systems, food security and human health are coming under increasing threat from existing and emerging animal and plant pests and diseases. This is due to climate change, trade, forest fragmentation, habitat destruction, agricultural expansion, concentrated livestock production, human penetration into wildlife habitats, and poor biosecurity. Taking a sector specific approach on its own will be insufficient to provide sustainable solutions. The UK is committed to supporting a One Health (OH) approach to tackling emerging threats and acknowledges the importance of research and innovation in animal and plant health.
The Animal and Plant Health Innovation and Evidence Delivery (APHID) Platform takes a OH approach to prevention, preparedness, and response to existing and emerging threats. It works with trusted partners and aims to integrate existing and new Investments within one delivery Platform. APHID supports an expanded and integrated portfolio of research and innovation to reduce the threat posed by animal and plant pests and diseases, contributing to food system resilience, food security and global health security in the face of climate change. A summary of Investments is provided in Annex 1. A dedicated Knowledge, Evidence and Learning Capability works to build synergies between individual Investments, identify new investment opportunities, and provide a responsive offer to FCDO on animal and plant health.
Summary supporting narrative for the overall score in this review
This Annual Review is the second for the APHID Platform and covers the period from 1st January to 31st December 2024. This was the first full year of APHID implementation and, as set out in this Review, not only have individual Investments delivered new evidence and impact, but also the more integrated approach to the portfolio Investments has resulted in some early successes. This Review also includes activities funded under Programme 300728: “Tackling global plant and animal health risks which threaten global food systems and health”, that are being integrated into APHID. During the year, work also continued to identify new Investment opportunities.
Results and Impact
- Development of a new vaccine for Foot and Mouth Disease has been completed by The Centre for Veterinary Vaccine Innovation and Manufacture (CVIM) with the project now transitioning fully to the private sector partner for commercialisation. Negotiations are ongoing for the transfer of the Rift Valley Fever Project to a second private sector partner. CVIM is also strengthening partnerships with UK research institutes and private companies.
- PlantwisePlus delivered plant health advice to over 23 million farmers during 2024. A randomized controlled trial (RCT) of active tomato farmers in Kenya showed that “time to act” alerts increased tomato yield and income, and reduced the frequency of pesticide use and associated costs. More details are provided in Annex 4. In Zambia, work is underway to identify possible predators for the tomato pinworm (Phthorimaea absoluta), a pest that has driven a sharp rise in insecticide use in tomato production.
- An independent evaluation of the reach and impact of disease alerts under the Wheat Disease Early Warning Advisory System (DEWAS) Programme, demonstrated that in 2024 over 600,000 farmers were reached with advisory information with at least two thirds of farmers reporting taking action after receiving the advisory.
- The Juno Evidence Alliance published their first Evidence Review, the State of the Field for Research on Agrifood Systems. The report was launched in July 2024 with a news story covered by 14 media outlets, with an estimated 140,000 views. The Juno team also piloted an approach to developing evidence synthesis at country level, integrating locally available data to deliver a report on crop breeding in Nepal.
- A Bibliometric Analysis of One Health Research covering research between 2010 and 2024 was completed, mapping research against the Action Tracks of the One Health Joint Plan of Action. An example of the analysis, which has generated considerable interest from members of the Quadripartite for One Health, is shown in Annex 6.
  [note] The Quadripartite for One Health aims to achieve together what no one sector can achieve alone, and it consists of four main agencies: the Food and Agriculture Organization of the United Nations (FAO), United Nations Environment Programme (UNEP), World Health Organization (WHO) and World Organisation for Animal Health (WOAH).
Synergies and relationships
A significant number of APHID Investments are co funded, and managed, in close partnership with the Gates Foundation. This relationship, with a significant agricultural research funder, strengthens technical oversight, manages innovation risks, and accelerates impact at scale. It also leverages significant funding to the UK science base, estimated at $340m. FCDO’s relationship with CABI, a significant delivery partner, and international membership organisation based in the UK, provides FCDO with access to their agriculture science expertise.
Delivering a more integrated portfolio of investments and strengthening relationships is a priority for APHID and there were notable successes during the year.
- FCDO and the Gates Foundation facilitated a closer working relationship between partners working on plant health systems in Africa. CABI and WAVE have complementary footprints in Africa, with CABI having a stronger presence in East and Southern Africa and WAVE being focused on West and Central Africa.
- The strength of WAVE’s work and relationships in West Africa has resulted in them being selected to lead the plant health component in the One Health cross government coordinating units in Côte d’Ivoire, Gabon and Sierra Leone. This is a significant achievement as plant health is under-represented in discussions on One Health.
- The One Health Hub UK (The Hub), hosted by CABI, has successfully raised the profile of FCDO’s support to One Health, building a strong working relationship with key organisations, including the Quadripartite for One Health, the One Health High Level Expert Panel (OHHLEP) and the PREZODE Initiative. They also worked with FCDO’s Nature Facility to develop a One Health Learning Journey for FCDO that will take place in January and February 2025.
  [note] The One Health High-Level Expert Panel (OHHLEP) provides scientific advice to the Quadripartite partners on One Health priority setting, policies and strategies.
  [note] PREventing ZOonotic Disease Emergence Initiative
- The Centre for Veterinary Vaccine Innovation and Manufacturing (CVIM) and the Global Alliance for Livestock Veterinary Medicines (GALVmed) have worked together to align their programmes to take new livestock vaccines from identification to commercialisation (see Figure 1 later in this Review),
- The platform approach taken by APHID has enabled FCDO to respond to emerging issues, such as avian influenza by leveraging existing UK expertise and partnerships through GALVmed. Their networks and track record of delivery will ensure that the new avian influence surveillance project is up and running rapidly.
This Review is scored “A – Programme met expectations”, with the Platform delivering against key milestones and targets for 2024.

Major lessons and recommendations for the year ahead
2024 was the first full year of implementation of APHID. The Platform Management Structures that have been put in place within FCDO have proved effective in terms of managing the Investments as a Portfolio, with quarterly meetings ensuring that all of those involved in the Investments are appraised of progress, risks are managed, and payments and forecasts are handled effectively. Good working relationships have also been established, or maintained, with key Delivery Partners.
The success in APHID programme management within FCDO has not been matched with success in stimulating more strategic discussions on future priorities or opportunities for synergies between Investments. This reflects a focus in 2024 on ensuring new Investments were launched successfully, with less time spent on Investments that were already up and running, or on identifying new opportunities or synergies.
During 2025, in addition to streamlining programme management, more formal “strategy” sessions should be held twice a year to review progress of the Portfolio as a whole.
Although reporting across individual APHID Investments has been brought into alignment with FCDO reporting deadlines, the results and impacts reported in this Annual Review are reported as discrete results from each Investment, as opposed to APHID Platform impacts.
In parallel with Recommendation 3, on refreshing the APHID Theory of Change, an APHID Platform Level Results Framework should be developed to enable reporting on the Platform as a whole, rather than as discrete Investments. While the diversity of Investments precludes a common logframe, a suite of high-level Outcome Level Indicators could be developed, some of which could be drawn, or adapted, from Investment level logframes. Each Investment would be expected to report against a minimum number of Indicators.
In the 2024 APHID Annual Review the following recommendation was made to deliver a more coherent and strategic approach to animal and health research that builds on discussions with key stakeholders, including other UK Government Departments.
Recommendation	Progress
During 2024, with the support of CABI through the Knowledge, Evidence and Learning Capability, the FCDO APHID Management Team should develop a more detailed stakeholder/audience map on One Health. This will include UK Government Departments, international organisations, research organisations and other organisations with an interest in One Health. This Map should then be used by both FCDO and CABI to identify key stakeholders, priorities for ongoing engagement, and opportunities for potential future collaboration.	The recommendation was completed in July 2024, as reported under Output 3 of this Review.

# THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
APHID’s primary impact will be increased agricultural productivity and efficiency in developing countries with reduced negative environmental impact, empowering women, better nourishing families, protecting people’s health and spurring economic growth. Secondary impact will be through reduced risk of pest and disease spread to the UK whilst strengthening the UK’s own emergency response and research capabilities. Climate change is having a significant impact on animal and plant pests and diseases and APHID will deliver new control options to help farmers adapt to these impacts.
The full Theory of Change, as set out in the APHID Business Case is shown in Annex 2, mapping the individual APHID Investments against each Output. Impact will be delivered through four outcomes associated with healthier crop and livestock production. These are:-
  - Rapid disease information sharing across and within sectors.
  - Sustainable pest and disease surveillance systems.
  - Prevention of emergence, early detection of, and timely response to, pests and diseases
  - Improved biosecurity and food safety along the value chain.
There is significant evidence to show that these Outputs set out in the Theory of Change are crucial to achieving the desired outcomes and impact.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
As outlined in this Review, APHID is on track to contribute to expected outcomes and impact. APHID Investments are delivering new knowledge, evidence, and innovation to tackle animal and plant pest and disease threats.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Research published in 2024 indicates the likely impact of a warmer and wetter climate on crop diseases, highlighting the importance and relevance of APHID’s work in this area to climate adaptation. Work on wheat estimates that a future climate is likely to increase the area suitable for wheat blast infection and reduce global wheat production by 69 million tons per year (13% decrease) by 2050. Brazilian researchers published the result of a new study which showed that plant diseases affecting Brazil’s most important crops are set to worsen as global temperatures rise.
[note] Pequeno, D. N., et al., (2024). Production vulnerability to wheat blast disease under climate change. Nature Climate Change, 14(2), 178-183. https://doi.org/10.1038/s41558-023-01902-2
[note] Angelotti, F., Hamada, E., & Bettiol, W. (2024). A Comprehensive Review of Climate Change and Plant Diseases in Brazil. Plants, 13(17), 2447. https://doi.org/10.3390/plants13172447
The APHID Platform remains highly relevant to FCDO’s priorities and is the flagship offer under Pillar 3 of the Gilbert Initiative, complementing work under the other four pillars. Health remains a priority for the UK Government, and APHID aligns with the UK’s support to the implementation of a One Health approach and Defra’s Action Plan on International Plant Health. It is also aligned with the UK government commitment to support developing countries to respond to the challenges and opportunities of climate change through International Climate Finance.
[note] The five Gilbert Initiative Pillars are: Climate resilient agriculture technologies, Pathways to scale, Tackling global pest and disease threats, Affordable, healthy diets, Resilience in fragile and conflict affected states.
The Theory of Change developed during the preparation of the APHID Business Case has provided an overall framework for Investments under the Programme. However, changes in the external context and new initiatives by other funders has resulted in the ToC become less useful as a tool to support the investment strategy and implementation of the programme.
During 2025, the FCDO Team should dedicate time to refreshing and updating the APHID ToC.

# DETAILED OUTPUT SCORING
Each APHID Investment is given an overall Red/Amber/Green Rating, as set out below. Each Investment has an agreed monitoring framework with clear milestones and deliverables. This approach is set out in more detail in the Monitoring, Evidence and Learning Section of this Review.
Investment on track with only minor variation from planned milestones.
Investment on track with moderate variation from planned milestones, with mitigation measures in place and agreed.
Investment off-track, mitigation options limited with risk of failure to deliver outputs.
No activities planned under APHID for the reporting year.

Output Title	Accelerated development and delivery of Vaccines, Therapeutics and Diagnostics, targeting major threats to livestock production and zoonotic diseases that can spread to humans.
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Investment	Progress (RAG rating)
Centre for Veterinary Vaccine Innovation and Manufacturing (CVIM) – co-funded with the Gates Foundation (GF)	Met Expectations: / All milestones for operations of CVIM were met. / The facility is fully staffed and operational, construction of new facilities is on track and governance and management systems are in place. / Vaccine Development is on-track. / Four vaccine development programmes are progressing well, with one being redesigned following poor technical performance of the vaccine. One new product has been handed over to private sector partner and one another is currently being transferred to partner.
Global Alliance for Livestock Veterinary Medicines (GALVmed)	Met Expectations: approval of a new phase of funding. / Negotiations for a new phase of funding to GALVmed were completed in 2024, with APHID funding commencing from January 2025. Progress will be reported in 2026.

Briefly describe the output’s activities and provide supporting narrative for the score.
Investments under this Output aim to accelerate the development and delivery of vaccines, therapeutics and diagnostics that target major threats to livestock production, and zoonotic diseases that can spread to humans. As set out in the APHD Business Case, in developing countries, where many people are dependent on livestock for their livelihoods, access to effective vaccines, therapeutics and diagnostics is very limited and for some diseases therapeutics and diagnostics simply don’t exist.
Two Investments are supported under this Output, with CVIM reporting under APHID since 2023, and GALVmed funding commencing in January 2025. CVIM has delivered against milestones and therefore this Output is therefore scored as A: Met Expectations.
The Centre for Veterinary Vaccine Innovation and Manufacture (CVIM)
In 2024, CVIM has continued to make good progress and have worked with GALVmed to align their programmes to deliver an end-to-end vaccine discovery, development and commercialisation programme, (Figure 1) drawing on GALVmed’s strong focus on commercialisation and scaling, and their network of private sector partnerships.
Figure 1: CVIM and GALVmed working together
Highlights of the past year include: -
CVIM capacity
- Good Laboratory Practice (GLP) facilities have been refurbished and equipped and are fully operational.
- The Good Manufacturing Practice (GMP) facility funded by UKRI has been designed and obtained planning permission. Significant savings have been identified during this process and the building is likely to come in below budget. Construction has started on schedule with completion expected by mid-2026.
Vaccine Development: Development pipelines have been established with commercial partners for recombinant DNA, protein sub-unit, and RNA vaccines testing important livestock and zoonotic diseases A summary of each pipeline is included in Annex 3. Good progress has been made in 2024:
- Foot-and-mouth disease: The project has now transitioned fully to the private sector partner, with CVIM providing support for in vivo protection studies for product registration.
- Rift Valley Fever: CVIM has now successfully completed the development of production processes with the African partner (MCI Morrocco). Detailed discussions are ongoing with MCI and GALVmed to initiate the transfer of vaccine technology for commercial production.
- Nanoparticle platform: Disease targets for this work are PPR and IB. Yeast strains expressing the nanoparticle-spike protein complexes have been generated. Work is underway to establish subunit production in bioreactors.
- Mareks Disease: The programme to develop low-cost Marek’s disease vaccine production that would be suitable for low-and-middle income countries has been terminated because of insufficient antigen yields. The work on this disease has switched to focus on Mareks Disease sub-unit vaccines.
- RNA Vaccines: A robotic high throughput RNA synthesis machine was installed and commissioned in 2024. CVIM is working with the Government Chemist, the UK Vaccine Catapult, and the RNA Centre of Excellence to onshore in the UK all elements of RNA vaccine production with strategic partners. This has the potential to provide the UK with an enhanced rapid response to emerging pandemics and livestock epizootics.
The CVIM Science Review Committee are currently evaluating new programmes submitted to CVIM for funding by the private sector. The SRC is determining the priority disease targets for new RNA vaccines. Studies to develop a Proof-of-Concept Blue Tongue RNA vaccine are underway.
The Global Alliance for Livestock Veterinary Medicines (GALVmed)
The UK-based GALVmed has become established as a global leader in catalysing the development of cheap and effective combination livestock vaccines, diagnostics and medicines. The previous GALVmed project will end in March 2025 with the estimates indicated that 38.7 million livestock deaths have been averted saving the sector approximately $359 million (2014 - 2023).
However, despite vaccines being highly effective in controlling animal disease, vaccines are not available for many livestock diseases, particularly those impact small holder livestock keepers in low- and middle-income countries. Therefore, during 2024 negotiations concluded for a new phase of funding to GALVmed, co-funded with the Gates Foundation. The new programme will run from 2025 to 2030 and will support vaccine R&D and distribution, targeting specific gaps in private investment, particularly small ruminant vaccines which are not a priority for private sector, the development of a new therapeutic drug and enhanced disease surveillance. The programme includes three projects which have specific targets:-
- VITAL 2: By 2030 small ruminant vaccine coverage rates will increase in Kenya (doubled), Tanzania (x8) and Nigeria (x20), reaching an additional 1.75m smallholder farmers.
- EDSAP: By 2028 the surveillance and management of Avian Influenza (AI) and other poultry diseases will be improved in Ethiopia, Tanzania and Nigeria through an enhanced level of near-real-time diagnosis and reporting,
- Tryps-3: By 2028 a new effective and safe drug to treat African Animal Trypanosomiasis will be registered for use and ready for commercialisation in two target countries.
The milestone and targets will be included in the APHID Log frame and reported in the 2026 Annual Review.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no major changes to this output during the past year, and no changes are planned as a result of this review.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
In the 2024 APHID Annual Review, the following recommendation was made:
Recommendation	Progress
FCDO should work with key stakeholders to identify new investment areas under this output, specifically around the potential for research and development on new diagnostics for livestock diseases in developing countries.	During 2024 discussions with The Global AMR Innovation Fund (GAMRIF), managed by the Department for Health Social Care (DHSC), and the Biotechnology and Biological Sciences Research Council (BBSRC) confirmed that both organisations are interested in supporting research on livestock diagnostics. However, resourcing constraints curtailed discussions.

The portfolio approach to investment in livestock vaccines, taken by both CVIM and GALVmed, mirrors the approach taken by the APHID Platform. This value of this approach has been demonstrated in 2024, with two vaccines transferred, or close to being transferred, to commercial partners, whilst slow progress on a third required a change in focus.
During 2025, building on the various relationships established through APHID, and using the information from the One Health bibliometrics (Output 3) and the Horizon Scanning work, FCDO should identify new priorities for work on livestock vaccines, therapeutics, and diagnostics.
by December 2025

Output Title	Improved, evidence-based Early Warning, Surveillance and Response Systems for animal and plant pest and disease threats, drawing on UK capability
Output number:		2	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	No

Investment	Progress (RAG rating)
Centre for Tropical Livestock Genetics and Health (CTLGH) – co-funded with Gates Foundation	Met Expectations: 1 output exceeding expectations, 21 outputs on track, 4 milestones yet to start / After a slow start in the first year of Phase 2, progress has accelerated in the second year, with CTLGH delivering improvements in poultry and cattle genetics.
Evidence-based approaches for the control of bovine tuberculosis in developing countries – co-funded with Gates Foundation	Met Expectations: All output milestones are on schedule and progressing well against the results tracker / Despite initial delays getting sub-contracts out in the first year, early setbacks have been overcome to position the project to complete the majority of trials as planned in the second year.
Nature based solutions innovation consortium for plant pests and diseases – delivered by CABI	Moderately did not meet expectations / Due to discussions with the Australian Centre for International Agricultural Research (ACIAR) who were interested in supporting the proposed Consortium, design and approval progressed more slowly than planned.
PlantwisePlus – delivered by CABI	Met Expectations: with 69 milestones met, 10 almost met and 3 not met / PlantwisePlus has made excellent progress during 2024, providing plant health advice to 4.3 million farmers and an awareness raising campaign in Kenya winning Silver in the Sustainability Category of the 2024 Data and Marketing Awards. Proactive engagement with FCDO and other funders has fostered productive working relationships including at country level.
West and Central African Virus Epidemiology (WAVE) – co-funded with Gates Foundation	Met Expectations: 2 milestones completed, 2 on track to be completed in 2025. / WAVE continues to make good technical progress, however risks remaining regarding the project’s sustainability of its work beyond the life of the project. WAVE are making good progress in implementing their sustainability plant. This will be the key focus for 20258.
Wheat Disease Early Warning Advisory System (DEWAS) – co-funded with Gates Foundation	Met: All milestones on track / Current progress has seen significant achievements, including the toolbox now capturing multiple diseases and more integrated data systems. The system is operational and has led to early detection of new pathogen races.
Zoonotic disease research and innovation with UK Research and Innovation (UKRI).	Moderately did not meet expectations / After generally slow progress in agreeing collaborative research on zoonotic disease, in late 2024 discussions moved forward much more rapidly, culminating in an agreement, in principle, for FCDO to cofund projects under UKRI’s Interdisciplinary research to tackle epidemic threats programme.

Briefly describe the output’s activities and provide supporting narrative for the score.
Under Output 2, APHID supports a range of Investments that draw on UK expertise and capability to deliver new knowledge, innovation and products that will support evidence-based early warning, surveillance and response systems for animal and plant pest and disease threats.
During 2024, one Investment, PlantwisePlus, was funded under APHID. Conversations were held on potential new Investments on nature-based solutions to tackle crops pests and diseases, wheat health, and zoonotic disease research. Additionally, for 2024, Investments funded under “Programme 300728: Tackling global plant and animal health risks which threaten global food systems and health” are reviewed here, as part of APHID’s integrated approach to investments in animal and plant health.
Whilst progress on the two new Investments identified in the APHID Business Case was slower than expected, this is balanced by the five active Investments delivering or exceeding against milestones. Therefore, this Output is scored as A: Met Expectations.
Centre for Tropical Livestock Genetics and Health (CTLGH)
CTLGH Phase II aims to contribute to increased animal productivity and income for small-scale producers with livestock in tropical conditions through new tools and technologies needed for effective dairy and poultry breeding platforms in Sub-Sharan Africa. During 2024 there has been strong collaboration with related farmer-facing projects and animal breeding networks. Key results include:
- Creation of a repository of biological samples of indigenous chicken breeds in Burkina Faso, Kenya, and Uganda. These breeds are adapted to local environmental conditions and disease pressures but are at risk of being lost due to the introduction of more productive, commercial breeds. Biobanking enables future breeding programmes to make use of the genetic diversity on indigenous breeds.
- Evaluating local chicken breeds across different environments is complex but published research by CTLGH has demonstrated that adaption of two modelling approaches for multi-environment performance analysis enables the evaluation of chicken breeds across different agroecological zones in Ethiopia.
  [note] Kebede, F. G., et al., (2024). Multi-environment performance analysis identifies more productive and widely adapted chicken breeds for smallholder farmers. Frontiers in Sustainable Food Systems, 8, 1441295. https://doi.org/10.3389/fsufs.2024.1441295
- Despite significant advancements in Next-Generation Sequencing, high-throughput technologies, and increasing affordability and accessibility, indigenous African cattle genetic data in global cattle genomic data resources is limited. Research conducted by CTLGH, and published in Nature, has reported the genome sequences of 555 cattle from nine countries. This data will support future breeding of cattle that are more productive, and resilient to disease pressures.
  [note] Tijjani, A., et al. (2024). Genomic Reference Resource for African Cattle: Genome Sequences and High-Density Array Variants. Scientific Data, 11(1), 801. https://doi.org/10.1038/s41597-024-03589-2
Evidence-based approaches for the control of bovine tuberculosis in developing countries
Bovine tuberculosis (bTB) is a chronic disease that limits livestock productivity and threatens human health and remains endemic in many lower income countries because test-and-slaughter control is not economically or culturally viable, and alternative control approaches do not exist. This project is conducting trials to assess the effectiveness of the Bacille Calmette-Guérin (BCG) vaccine, which has shown promise in previous trials. In the past year, the necessary approvals have been obtained and the trials are underway. Additionally, eight new peer-reviewed publications have been published, with a further eight in the pipeline.
Nature based solutions innovation consortium for plant pests and diseases
During 2024, FCDO worked with CABI to develop the proposal and work plan for this proposed new Investment, building on the experience and data generated by the PlantwisePlus Programme. The proposed innovation consortium will work with private companies, research organisations and national governments to speed up the development, and increase the use, of nature-based solutions to tackle crop pests and diseases that are effective and have less environmental impact that current chemical pesticides. There was significant interest in the innovation consortium from CABI Member Countries in Southeast Asia, including from the Australian Centre for International Agricultural Research (ACIAR). ACIAR were interested in co-funding the consortium prolonging the discussions around the proposal, with anticipated approval of funding in March 2025. This has delayed the start of work by CABI.
PlantwisePlus
PlantwisePlus works with partners at country level build their capacity to respond to threats to crop production from plant pests and disease in a changing climate. PlantwisePlus delivers activities under three impact pathways and aims to improve food security and the incomes and livelihoods of smallholder farmers through sustainable approaches to tackling plant pests and diseases. The programme provides science-based advice to farmers in 27 countries, supports countries to be better prepared to respond to pest and diseases and develops and tests new pest and disease control options. As a multi-donor programme, PlantwisePlus has significantly greater reach and impact than would be possible with a smaller programme funded solely by FCDO. Highlights from 2024 include:
[note] (i) pest preparedness, (ii) pesticide risk reduction and (iii) farmer advisory.
[note] PlantwisePlus funders: Directorate General for International Cooperation of the Netherlands (DGIS), the Swiss Agency for Development and Cooperation (SDC); the European Commission Directorate General for International Partnerships (INTPA); the UK Foreign, Commonwealth and Development Office (FCDO).
- PlantwisePlus delivered plant health advice to 4.3 million farmers during 2024, with close to 19 m benefitting from subsequent farmer-to-farmer sharing of information. This brings the cumulative total of farmer interactions to over 98 million since the launch of Plantwise, the predecessor to PlantwisePlus. Individual countries continue to strengthen their Plant Clinic Networks, with the Ministry of Agriculture and Livestock Development in Nepal approving a comprehensive document outlining guidelines for the nationwide operation of plant clinics.
- In Kenya, working in partnership with the Kenya Agricultural and Livestock Research Organization (KALRO), PlantwisePlus conducted a randomized controlled trial (RCT) of active tomato farmers across five counties in Kenya to evaluate the effectiveness of time-to-act pest alerts sent to farmers by text message. The study showed that the alerts increased tomato yield and income, and reduced the frequency of pesticide use and associated costs. More details are provided in Annex 4.
- Changes in how people access knowledge and information on all topics, including pest and disease control requires programmes such as PlantwisePlus to adapt and innovate to ensure key messages reach their target audience. Whilst the programme continues to support traditional approaches, including plant clinics, working with agriculture extension services, agro-dealers, and traditional media such as radio, they are testing and evaluating new approaches. For example:
    - A campaign run in in Nakuru County, Kenya, in partnership with the county government and the Behaviour Change and Communication Centre, received a Silver in the sustainability category of the 2024 Data and Marketing Awards. The “Ukulima True” campaign was developed “in-house” beating major commercial campaigns delivered by major agencies, and increased awareness amongst farmers, processors and the public on the correct use of pesticides, motivated and encouraged the adoption of safer and more sustainable practices by farmers and campaigned for improved linkages for markets for farm produce.
      [note] Meaning True Farming
    - A well-known Kenyan actress, who is also keen kitchen gardener with 760,000 followers on social media, shared her journey using the CABI Academy to learn more about crop pest diagnosis, pest management, and biological control, which led to hundreds of other people in Kenya visiting the CABI Academy.
- Over 600 agro-input dealers in Uganda underwent training using new content on pesticide risk reduction and many of those surveyed afterwards described how their behaviour is changing as a result, e.g., encouraging farmers to use Integrated Pest Management (IPM) approaches and lower-risk plant protection products where possible and avoiding repackaging pesticides due to the hazards this creates. Based on the positive feedback from the initial roll-out, the government of Uganda is now seeking PlantwisePlus support to update their entire agro-input dealer training course in 2025.
  [note] Integrated pest management is a sustainable approach to managing pests by combining biological, cultural, physical and chemical tools in a way that minimises economic, health and environmental risks.
Complementing PlantwisePlus’ work on supporting plant health systems to provide actionable advice to farmers and encourage the use of safer pest control options, work is also ongoing to identify, test, and scale up new pest control options to build on the success of the rapid control of the papaya mealybug using classical biological control in Kenya (reported last year). In Zambia, work is underway to identify possible predators for the tomato pinworm (Phthorimaea absoluta), a pest that has driven a sharp rise in insecticide use in tomato production. Assessments of five native parasitoids of the tomato pinworm revealed low parasitism rates, resulting in the decision to assess parasitoids from South America, its region of origin. The pest’s main parasitoid in South America, D. gelechiidivoris, has now been introduced in East Africa by the International Centre of Insect Physiology and Ecology (icipe), and CABI is considering its introduction in Zambia for 2025.
[note] Parasitoids are a group of insects whose larvae develop on or in the bodies off other insects, which they eventually kill.
CABI submits one PlantwisePlus Report to all donors which is available online. This report provides more details on the programme.
West and Central African Virus Epidemiology (WAVE)
In this final phase of funding to WAVE, the programme is focusing on two main areas of work:
- WAVE is working to advance the response plans of two pilot countries by developing and testing a Functional Rapid Responses to Plant Infectious Diseases (RAPID) prototype system. RAPID relies on dynamic models for epidemic spread and management developed in collaboration with the University of Cambridge.
- WAVE is also focusing on the future sustainability of the project beyond this phase of funding. A key milestone, building on work in the last year, will be the upcoming convening of key plant health partners in Abidjan in February 2025 that aims to review plant health activities in Central and West Africa, identify existing competencies and reach, and establish partnerships for a collaborative Plant Health Alliance in Central and West Africa.
- Based on WAVE’s contribution to community disease monitoring and reporting, as well as their laboratory capacity, which lead to the detection and molecular confirmation of the East African Cassava Mosaic Virus Uganda strain (EACMV-Ug) in Guinea and Sierra Leone in August 2023, WAVE have been selected to lead the plant health component in the One Health cross government coordinating units in Côte d’Ivoire, Gabon and Sierra Leone.
CABI and WAVE
In April 2024, FCDO and the Gates Foundation hosted a meeting in London, bringing together a number of partners working on plant health, including CABI, WAVE, Imperial College, and Defra. This has facilitated a closer working relationship between partners working on plant health systems in Africa. CABI and WAVE have complementary footprints in Africa, with CABI having a stronger presence in East and Southern Africa and WAVE being focused on West and Central Africa. Although FCDO and the Gates Foundation did not prescribe any specific outcome from the initial meeting it has led to a series of follow-up discussions. CABI and WAVE will cohost a regional plant health convening in February 2025, CABI intends to make use of WAVE’s laboratory facilities, and they are exploring the potential for submitting grant applications together.
Wheat Disease Early Warning Advisory System (DEWAS)
The DEWAS Team are making good progress towards delivering against milestones. Systems are being put in place, collaborations are being built, and surveillance is underway. Key highlights were:
- Delivery of disease alerts to farmers to raise awareness and enable action to be taken form the core of DEWAS’s work. 100 weekly alerts were generated during 2024, with accurate pre-season early warning of high wheat disease risks enabling farmers in Ethiopia to act.
- An independent evaluation of reach and impact of disease alerts, funded through FCDO’s Weather and Climate Information Services (WISER) Programme, demonstrated that in 2024 over 600,000 farmers were reached with advisory information in Bangladesh, Bhutan, and Nepal, including more than 120,000 women farmers and more than 220,000 marginalized farmers. A high proportion of farmers reported acting after receiving the advisory information - 98% in Bangladesh and 62% in Nepal. Significantly, in Nepal, provincial governments are now allocating resources to disease control.
Zoonotic disease research and innovation with UK Research and Innovation (UKRI).
During the design of the APHID Platform in 2023, and building on previous successful collaborations, FCDO’s Food and Agriculture Research and Global Health Research Teams initiated discussions with UK Research and Innovation (UKRI), specifically the Biotechnology and Biological Sciences Research Council (BBSRC) and Medical Research Council (MRC), to scope out the potential for a new collaborative research programme on zoonoses and One Health with UKRI.
After initial positive meetings early in 2024, progress towards agreeing a programme for applied multi country research to deliver new evidence and innovation to tackle existing and emerging zoonotic disease threats was much slower than hoped for. This was principally due to a lack of capacity from all parties, rather than a lack of interest in collaborating.
However, in late 2024, rapid progress was made culminating in agreement in principle for FCDO to cofund projects under UKRI’s call for proposals on “Interdisciplinary research to tackle epidemic threats”. FCDO’s contributions to the call text, including ODA eligibility requirements, were received positively. Discussions are ongoing, with the call being launched in late March 2025.
Proposed New Investments
During 2024, scoping work was conducted to identify potential new areas of work, particularly on plant health. This included a bibliometric analysis of current and emerging plant health challenges through Juno, and discussions with the Gates Foundation. One proposed new Investment has resulted from these discussions, building on previous work on wheat diseases, cofunded with the Gates Foundation. The Wheat Health Alliance would target fungal disease (rust, blast, and fusarium head blight) resistance, and link UK expertise in wheat with work at the International Maize and Wheat Improvement Center (CIMMYT). Working through the CIMMYT global wheat programme, the Alliance would have a focus on translational research and delivery of new wheat varieties in the field. As of December 2024, discussions were ongoing with potential cofunders of this work.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no major changes to this output during the past year. The main change as a result of this review will be work to update milestones/targets as appropriate across all Investments.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
In the 2024 APHID Annual Review, the following recommendation was made:
Recommendation	Progress
PlantwisePlus should engage with other organisations, such as the International Plant Protection Convention (IPPC) and FAO, working on plant health systems to share experience and expertise in this area to strengthen the programme’s approach and enable others to learn from CABI’s experience. This engagement may also identify areas for more formal collaboration on plant health systems.	Both CABI as an organisation, and PlantwisePlus as a specific programme, have engaged proactively with the International Plant Protection Convention (IPPC), and regional Plant Protection Organisations in Africa. PlantwisePlus is aligned with IPPC priorities and is also supporting work at regional level. CABI is also an implementing partner of the IPPC African Phytosanitary Programme (APP), which aims to provide advanced tools to prevent, detect, and manage significant plant pests and diseases. This partnership ensures more widespread adoption of PlantwisePlus tools, and APP support to African countries will build their capacity to use them.

2024 has demonstrated that despite working on similar issues, and often the same partners, Investments under APHID are not aware of each other’s work and capacity. CABI and WAVE have been working to strengthen plant health systems in Africa for many years but, until the introductions made by the Gates Foundation and FCDO, CABI and WAVE were unaware of each other’s capacity and experience. This validates the APHID approach of building a more strategic approach to Investments and brokering links between partners.
During 2025, APHID should continue to broker links between partners and track the progress/impact of this work.
The PlantwisePlus programme continues to deliver impact in multiple countries, with strong interest from key stakeholders at country-level. Implementation of activities across the three Impact Pathways varies between countries, contingent on their existing policies, institutional structures, and capacity. This is making the programme increasingly complex, both in terms of management and communicating results and impact. And, from a research perspective, it is more difficult to discern the research and evidence components of the programme, as compared to the broader development impact.
In partnership with the other funders of PlantwisePlus, FCDO should support CABI to streamline implementation of the programme, develop a simpler narrative about what the programme delivers, and strengthen the research and evidence components of the programme. This will include research on safer bioprotection products (biopesticides and biocontrol), understanding the barriers to adoption of safer products, and whether bundled service provision models are effective in increasing use of safer products.
by December 2025

Output Title	Enhanced Knowledge, Evidence and Learning to develop tools, knowledge and evidence that help FCDO and IDS priority countries prevent, identify, and respond to emerging animal and plant health threats.
Output number:		3	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Investment	Progress (RAG rating)
Global Burden of Crop Loss (CABI)	Met Expectations: with 9 of 11 milestones achieved. / Work has progressed well with modelling crop loss with a country case study underway. Cofunding from the Gates Foundation was agreed. The expanded scope that this will enable resulted in delaying some activities as they can now be more comprehensive.
Innovative Science Partnerships (CABI)	No activity was planned in 2024.
Juno Evidence Alliance (CABI)	Met Expectations: with 13 of 15 milestones achieved, and the 2 partially achieved / 2024 saw the successful completion of the proof-of-concept phase for Juno, and approval of a new phase of funding. / Six evidence reviews were completed and published, a Lesson Learned exercise reviewed the proof-of-concept phase, and proposed governance structures were agreed.
One Health Hub UK, hosted by CABI	Met Expectations: with 7 of 10 milestones achieved, and three partially achieved. / The One Health Hub UK has worked well with FCDO during 2024, delivering a number of evidence products and building relationships with key partners, both within the UK Government and internationally.
One Health Knowledge Nexus Initiative (FAO)	Moderately did not meet expectations: with 8 of 15 milestones achieved, principally due to delays in starting activities. / Funding for the One Health Knowledge Nexus was agreed in March 2024, but the start of activities was delayed to July. By the end of the year staffing was in place with the timetable of launch events for new Communities of Practice in place.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 has a strong focus on strengthening knowledge, evidence and learning on animal and plant health, One Health, and the broader agrifood system. Tackling the interrelated challenges both to and from the agrifood system requires the knowledge and evidence to be synthesized and shared with key stakeholders in developing countries and with FCDO.
Across the four Investments with planned activities during 2024, three have made good progress against agreed workplans and objectives, with the work of One Health Hub UK, exceeding expectations in some areas. Although the launch of activities under the One Health Knowledge Nexus Initiative was delayed to July, the groundwork laid by FAO before formal signature of the funding agreement enabled activities to commence quickly. Therefore, this Output is scored as A: Met Expectations.
Global Burden of Crop Loss (GBCL)
The Global Burden of Crop Loss Initiative aims to produce trusted metrics on the burden of crop loss across geographies and crops, enabling better informed action to protect crops from pests and diseases. A summary of the approach is provided in Annex 5.
In 2024, renewed funding from FCDO has enabled the Team to take forward multiple workstreams. Initial work has enabled estimates of global maize losses using a suite of advanced modelling approaches and drawing on a large dataset of over 230,000 global observations. These incorporate a comprehensive range of environmental factors (including climate and soil properties), socio-economic variables, and agronomic inputs such as fertilizer application and irrigation. Pilot work on a country-level case study for maize in Ghana has started.
The modelling work has been supported by the development of a Data Management and Access Plan (DMAP). This guides how data will be handled within GBCL, specifically data processing, data stewardship and management, data Infrastructure, licensing and permissions, data sharing, and data publishing. Work on future sustainability of GBCL is also underway.
Significantly, during 2024, discussions with the Gates Foundation resulted in CABI securing additional funding for GBCL. This will enable work to proceed more rapidly and cover more crops.
Juno Evidence Alliance
During 2024, FCDO supported the Juno proof-of-concept phase, and agreed a new phase of funding to Juno for 2024-2027. The proof-of-concept phase successfully tested the approach of using Artificial Intelligence (AI) I to deliver evidence reviews and generate insights from the analysis that is too costly and time consuming using traditional approaches.
Juno completed and published six evidence reviews in 2024, covering themes including One Health, crop breeding, gender, nature-based solutions and plant health. The first published review, the State of the Field (June 2024), introduced the new approach and evaluated 6.3 million records within agrifood systems and has been viewed 1005 times. The report was launched in July with a news story covered by 14 media outlets, with an estimated 140,000 views of the story combined. In addition, the report was highlighted in public speeches, one-to-one meetings and in-country engagements.
The Juno team also piloted an approach to developing evidence synthesis alongside key actors through a report on crop breeding in Nepal. In 2023 the Juno team hosted a stakeholder workshop in Nepal which identified seed systems and varieties as a key area of interest. Juno published the findings in November 2024. To compliment this review and support stakeholder engagement on this topic, in December the Juno team ran sessions in Nepal for 60 scientists at the National Agricultural Research Centre on evidence synthesis methods, to build national capacity in Nepal.
In April 2024 the Juno team produced a report on lessons learned from the proof-of-concept phase. Actions from this report were discussed with FCDO, and an approach for how these would be addressed in the new phase of funding was agreed by FCDO and Juno.
One Health Hub UK
The One Health Hub UK (The Hub) provides a dedicated Knowledge, Evidence and Learning function for the APHID programme to deliver a responsive offer to FCDO, support evidence synthesis, strengthen the use of the One Health Approach across the programme and build relationships with key organisations working on One Health. During 2024, The Hub have met with FCDO Advisers on a monthly basis to ensure alignment of activities with APHID objectives and broader One Health discussions within FCDO.
- The rapid Bibliometric Analysis of One Health Research that was conducted in 2023 to feed into the APHID Business Case was updated, and strengthened, to cover research between 2010 and 2024. It mapped research against the Action Tracks of the One Health Joint Plan of Action, with an example of the analysis provided in Annex 6. The analysis has generated considerable interest from members of the Quadripartite. Publication is planned in early 2025.
- The Hub Team have worked actively to engage key One Health stakeholders, including Quadripartite members, OHHLEP members, FAO One Health Teams, PREZODE, and the Secretariat for the International Research Consortium on Animal Health (SIRCAH). Through this work they have developed a One Health Stakeholder/Audience Map, enabling them to identify key audiences for One Health knowledge and evidence generated through APHID Investments.
- The Quadripartite and OHHLEP have indicated a strong interest in the evidence work being produced by The Hub, with representatives playing an active part in the Horizon Scanning work that kicked off in late 2024. Building on the One Health Bibliometrics, the One Health Horizon Scanning work is taking a consultative, and iterative process to identify One Health research priorities that need to be addressed in to tackle emerging threats to people, animals, plants and the environment. An initial online survey was launched in late 2024, with in-person workshops planned for March 2025.
- In the second half of the year, The Hub contributed to development of the FCDO One Health Learning Journey, commissioned through the Nature Facility. The additional expertise and capacity provided through The Hub, enabled Learning Journey to be more comprehensive, and ensured linkages with other FCDO funded work. The Learning Journey will be held in early 2025.
One Health Knowledge Nexus Initiative (OHKN)
The One Health Hub UK, hosted by CABI, has provided an excellent, responsive offer to FCDO on One Health, enabling the commissioning of new evidence products and engagement with a wider group of stakeholders. This offer is complemented by FCDO support to FAO’s One Health Knowledge Nexus (OHKN), which seeks to strengthen the implementation of the One Health Approach at country, regional and international levels by establishing Communities of Practice (CoPs) on key issues. The CoPs will provide a mechanism for practitioners, experts, policy makers, researchers, and implementers to learn from each other and share expertise. It will also provide a mechanism for the dissemination of the latest evidence on One Health implementation. The CoPs are facilitated by trained facilitators, will offer opportunities for engagement, including face-to-face and online, and link to quality training resources from the Quadripartite for One Health.
The OHKN is led by FAO, in partnership with the other members of the Quadripartite for One Health. Their extensive global networks provide an ideal route to tap into experience and expertise. For example, FAO is currently supporting 44 countries to strengthen their capacities to prevent, prepare and respond to future pandemic threats, including upstream prevention of zoonotic diseases and AMR.
Funding was agreed in March 2024, but the start of activities was delayed due to administrative issues. However, pilot funding provided by other donors enabled some activities to commence.
- A key evidence gap for One Health initiatives is evidence on the economic value or return on investment on for One Health. Pilot funding from the Gates Foundation supported the Return on Investment Community of Practice. With over 250 active members in 2024, the CoP has delivered a publication on the “Current evidence of the economic value of One Health initiatives”, and developed four e-learning modules that will be launched in 2025.
  [note] Auplish, A., et al., (2024). Current evidence of the economic value of One Health initiatives: A systematic literature review. One Health, 100755. https://doi.org/10.1016/j.onehlt.2024.100755.
- The nature of the OHKN, sharing knowledge and evidence, will require FAO to have a robust approach to assessing outcomes and impact. This was the focus of discussions during 2024, with work starting in December to refine the logframe indicators drawing on FAO’s Monitoring and Evaluation expertise. CoP membership data are collected and monitored, disaggregated by gender, age, institutional affiliation, and geographic location, with the data being used by CoP Coordinators to inform engagement strategies and ensure balanced engagement. Annex 7 provides examples of the analysis that can be carried out.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no major changes to this output during the past year. The main change as a result of this review will be work to update milestones/targets as appropriate across all Investments.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
In the 2024 APHID Annual Review, the following recommendations were made:
Recommendation	Progress
Considering the delays in negotiation new Investments, going forward the APHID Management Team needs to begin discussions much earlier for future Investments, dedicating more resource to ensure things move ahead more rapidly.	Work to identify new Investments moved forward in 2024, including for the Wheat Health Alliance. / Scoping work for new Investment in plant health was also completed.
Juno should conduct a formal “lessons learned” review in early 2024, to reflect on the proof-of-concept phase and identify areas where processes can be improved for future work with FCDO and other funders including GF.	This review was completed in February 2024, with changes to Juno processes being made as a result.

The work of the One Health Hub UK, and the One Health Knowledge Nexus has reinforced the need, identified in the APHID Business Case, for those working on One Health to have access to the latest knowledge and evidence they need to implement the approach in their work. There are multiple initiatives and programmes of relevance, but it is hard for busy practitioners to identify the most appropriate resources for their needs, and to learn from others in their country or regions. The Stakeholder Mapping conducted by the One Health Hub UK, and the One Health Toolkit collated by the Quadripartite, are the first steps towards more coherent and accessible information.
Working with the One Health Hub UK and One Health Knowledge Nexus Teams, building on the stakeholder mapping, and in partnership with other UK Government Departments with an interest in One Health, FCDO should identify opportunities to drive coherence of, and accessibility to, key evidence and knowledge on One Health.
by December 2025

# VALUE FOR MONEY
VfM performance compared to the original VfM proposition in the business case
As it can be challenging to assess the impact of research programmes, the Research and Evidence Directorate (RED) has developed the following VfM criteria, which APHID has adhered to:
- Picking the right problems. Tackling animal and plant pest and disease threats has a significant impact on health and food security, the environment and prosperity, and assessments of previous research in this area demonstrates strong VfM. Additionally, the 2021 FCDO Best Buys assessment assessed that investment in livestock vaccines and treatments were good value for money.
- Working through strong partnerships. APHID was designed and established as a platform programme in order to reduce management costs for FCDO, build effective research partnerships and increase the likelihood of transformational impact. By working with established and strategic partners such as CABI, FAO, the Pirbright Institute and the Gates Foundation, FCDO has been able to leverage significant expertise and funding and drive VfM outcomes.
- Always requiring good quality. As noted in section C of this report, partners funded under the APHID programme are already delivering research and development outcomes of the highest quality.
VfM Metrics
The total APHID budget is £37 million, with key cost drivers including staff costs, facilities, management and travel costs. APHID uses the following indicators to track the VfM for each investment: number of peer reviewed publications delivered in high impact journals; performance against milestones and targets; impact of research; reach of funded innovations. These indicators are considered in Section C of this report.
The table below assesses the VfM of each delivery partner during 2024 against the ‘5E’ framework:
Category	Delivery Partner	Performance Review
Economy / = minimising input costs	CABI	CABI has robust procurement policy and procedure that ensures that they obtain competitive rates for inputs. Staffing costs make up a significant proportion of costs, and CABI recruits both international and national staff, maintaining competitive salaries to attract staff with the right expertise. / In addition to delivery of APHID investments, CABI provides FCDO with advice and expertise on plant health.
	FAO	Staff costs are also a significant proportion of the OHKN programme expenditure. However, several senior FAO experts on animal and plant health contribute their time to the Nexus at no cost to FCDO through technical leadership and contributions to communities of practice (CoPs). The OHKN uses the FAO’s existing Virtual Learning Centre, which houses module-based courses with regional platforms, and represents another in-kind contribution to the programme in the form of software licenses, page maintenance and the established network of national training focal points and technical and e-learning expertise.
	Gates Foundation	The Gates Foundation manages the grant portfolio directly and does not charge any management fee or overhead to FCDO. This is a key component of this partnership’s VfM proposition. This is in addition to the significant monetary and in-kind contribution made by the Gates Foundation through their co-funding and direct management of the procurement process and handling of all grant management.
	The Pirbright Institute	CVIM’s Joint Oversight Committee, on which FCDO has a seat, receives financial reports quarterly that track the actuals spend to date against the budget. This helps keep a close oversight of costs and expenditure and enables scrutiny. / Significant savings have been identified during the design of the GMP facility at the Pirbright Institute, which is likely to result in the building work coming in below budget by the time construction is completed in 2026. / CVIM also draws core operational support from Pirbright under a Memorandum of Understanding, thus reducing the need for dedicated support for CVIM and making most appropriate use of resources (e.g. finance, HR, IT, Health and Safety etc.).
Efficiency / = maximising outputs in relationship to budget inputs	CABI	CABI is implementing a new business management system, CABI Connect, which will integrate with adjacent systems and improve the information CABI uses to manage projects and the organisation. This is a crucial step in improving planning, budgeting and resilience, and a critical part of ensuring efficiency, cost-effectiveness and VfM for FCDO.
	FAO	The OKHN builds on existing work that FAO has conducted on One Health, and four existing CoPs, supported by other donors. FAO works closely with the Quadripartite and this programme can build on the existing networks and insights of FAO and other Quadripartite organisations, which in turn will drive increased policy uptake.
	Gates Foundation	The partnership between FCDO and the Gates Foundation has become increasingly efficient, in part because the two funders have now been working together on research in the agriculture sector for a number of years. Co-funding arrangements have also enabled FCDO to leverage in-kind support from the Gates Foundation for the procurement and management of delivery partners for this portfolio. The establishment of the FCDO secondment significantly strengthened the partnership between the two funders and facilitated closer involvement from FCDO in this portfolio. An external review of the partnership is currently underway.
	The Pirbright Institute	CVIM is collaborating with GALVmed, who also receive funding under APHID, to align programmes. This will enable CVIM to capitalise on a wider network of partnerships for commercialisation and scaling. / FCDO support to CVIM also helps to leverage co-funding from the Gates Foundation, increasing overall investment into vaccine development.
Effectiveness / = ultimate impact on FCDO objectives relative to the inputs used	CABI	CABI has a strong track record of delivery impact at scale, and in 2024 the PlantwisePlus programme alone reached 23.2 million farmers. CABI also met or exceeded approximately 80% of organisational targets in 2024.
	FAO	FAO has deep expertise on One Health and close relationships with the Quadripartite and One Health High Level Expert Panel. Activities in 2024 have laid a strong foundation for the expansion of CoPs to address identified gaps in One Health knowledge and evidence.
	Gates Foundation	The partnership between FCDO and the Gates Foundation is on track to produce a stream of highly relevant agricultural technologies, scientific advances and evidence.
	The Pirbright Institute	CVIM has established development pipelines with commercial partners for recombinant DNA, protein sub-unit, and RNA vaccines testing important livestock and zoonotic diseases, which have shown strong progress in 2024.
Equity / = how fairly are the benefits distributed	CABI	CABI collects gender and age disaggregated data for all projects and programmes and has drafted strategic documents to support gender mainstreaming and gender-sensitive programming. Gender is a particular focus of the PlantwisePlus programme. For example, in Sri Lanka CABI has conducted a gender assessment which revealed that women’s limited access to information about pesticide risks and safety means that they face greater risks when storing or spraying pesticides. These results will inform future CABI activities in Sri Lanka, to ensure that women have equal access to pesticide information and alternatives. This approach has already yielded results in Pakistan, where targeted educational materials were developed, and women have been involved in advisory services, media campaigns, and policy discussions, and connected with women extension staff. Men from the same communities were offered sessions on gender inclusivity. More information on CABI’s gender work is provided in Annex 8.
	FAO	FAO has taken steps to ensure that CoPs adopt an inclusive approach. All CoP members are encouraged in user agreements to foster an environment in which the contributions of individuals from all backgrounds are valued regardless of educational background, age, culture, political views, religion, gender or sexual identity. / Efforts are also made to ensure balanced leadership within the CoPs by providing equal opportunities for both women and men to lead, facilitate discussions, and shape the community’s direction. / Among the CoPs supported by the project, two are coordinated by women and two by men. The coordinators represent countries across three different continents (Africa, Asia, and Europe) bringing a diversity of perspectives and experiences to the initiative. / CoP membership data are collected and monitored, disaggregated by gender, age, affiliation and geographic location. This disaggregated data is periodically analysed and shared with the CoP coordinators to inform engagement strategies. / Through the support of Gender Focal Points, FAO promotes gender mainstreaming in all FAO initiatives including One Health, particularly as gender equality is a foundational principle of the Quadripartite One Health Joint Plan of Action.
	Gates Foundation	Gendered dimensions of agriculture are addressed by multiple projects under the FCDO/Gates Foundation portfolio, with some particularly strong examples of integrating gendered considerations, including WAVE.
	The Pirbright Institute	CVIM’s work in 2024 has focused on the early stages of vaccine production. As such the equitable distribution of vaccines will be a focus of future years of the programme.
Overall Cost-effectiveness	CABI	CABI has a strong track record of delivering results for FCDO. Programmes such as PlantwisePlus have shown significant return on investment, and are funded by multiple donors, providing additional technical oversight of the programme and delivering economies of scale.
	FAO	FAO has already established new CoPs and produced some initial knowledge products in the reporting period. The project is building on joint efforts with other funding partners, alongside the in-kind contributions of multiple collaborators and partners.
	Gates Foundation	The FCDO/Gates Foundation programme represented strong value for money over the reporting period, with co-funding from the Gates Foundation, and a significant in-kind contribution through their direct handling of all the grants and procurement, on behalf of both funders. There is significant value for money in this type of collaboration between two of the major funders of research in agriculture. The overarching partnership with the Foundation leverages significant R&D resources into the UK.
	The Pirbright Institute	CVIM is staffed by a team of experienced personnel with a strong track record of supporting the development and deployment of vaccine technologies to combat neglected and emerging diseases of livestock. CVIM’s Scientific Strategy Board regularly reviews progress on vaccine development to ensure the quality of outputs.

Assessment of whether the programme continues to represent value for money
The Investments supported through APHID continue to represent good value for money. Performance of delivery partners has been strong, and partners have achieved the majority of milestones and targets. The programme remains highly relevant to FCDO’s priorities. Additionally, co-funding with the Gates Foundation leverages approximately three times more funding.

# RISK
Overview of risk management
The overall programme risk is moderate with all risks within FCDO’s risk appetite. In the context of climate change there is a need for agricultural research to deliver transformative solutions. As such, the portfolio contains a mix of investments, including higher-risk innovative programmes and support to evidence generation. APHID manages risks by working with trusted partners and integrating higher-risk investments within a broader programme of agricultural research and development to ensure strong overall returns.
The risk matrix on FCDO’s Aid Management Platform (AMP) has been updated over the course of 2024 and is included below. All risks are actively managed and reviewed by FCDO quarterly at a minimum. APHID delivery partners also have their own programme and organisational-level risk management tools and processes, and partners share updates on these risks in narrative reports and in regular meetings with FCDO. Partners also share audit reports on an annual basis with FCDO and no issues have been identified with the records shared. Further risk updates for each partner are included in Annex 9.
APHID Risk Register
Risk	Mitigation Strategy	Residual Risk	Risk trajectory
Strategy and Context
Public opinion in the target countries opposes specific technologies and products delivered.	Proposed partners have strong links into regional and national research organisations in target countries and are responsive to national demand, ensuring that demand is assessed and met. Although novel genetic technology is funded, it is only deployed where national policy supports this.	Minor	→
UK public opinion opposes international development funding and/or funding of international agricultural research.	This funding builds on previous partnerships which delivered excellent results. The programme will provide strong communications material to raise awareness of the importance of agricultural research, not only for developing countries, but also the UK national interest.	Minor	→
Exogenous shocks from political instability, conflict, climate change or other natural disasters have a negative impact on delivery or uptake of the research outputs.	The programme will work in multiple locations. This means that, while the risk of individual Investments being affected by exogenous shocks remains, the risk of this affecting the programme as a whole is minimal.	Minor	→
Policy and Programme Delivery
The proposed Knowledge, Evidence and Learning function fails to deliver anticipated synergies and learning.	FCDO will work closely with CABI to scope and design the function. Measures of effectiveness and impact will be agreed with a clear break point if things don’t go as planned.	Moderate	→
Knowledge and evidence generated by the programme does not impact policy or programmes.	Ensuring new knowledge and evidence is taken up entails some delivery risk as the pathway to impact through change in policy and practice is not linear and depends on engagement with diverse stakeholders. This is mitigated through early engagement with end-users and co-creation.	Moderate	→
One or more of APHID’s delivery partners faces significant financial pressures, is taken over by a competitor, or is forced to cease trading, resulting in an inability to deliver agreed objectives.	Although FCDO will maintain good working relationships with delivery partners, the landscape in which they operate is competitive and they cannot mitigate against all potential factors that would impact their ability to deliver. Maintaining strong relationships with existing partners, and identifying new partners, will limit the impact on the overall programme.	Minor	→
Developing vaccines carries an innovation risk, due to the complexities of identifying targets, testing vaccines, and scaling manufacturing.	This is mitigated through a portfolio approach; co-funding and working through proven partners.	Moderate	→
Safeguarding
A lack of sensitivity to gender in programme design limits the programme’s impact and potentially exacerbates inequalities for women and other marginalised groups.	Gender issues are firmly integrated into the programme, and FCDO will continue to monitor the performance and progress against gender targets, working with other investors.	Minor	→
Financial and Fiduciary
Financial mismanagement or fraud within the programme is not identified or the response is inadequate or ineffective.	As part of programme management and annual review processes, FCDO reviews audited accounts annually. In case of any mismanagement/fraud, FCDO procedures would be followed, and issues will be escalated.	Minor	→

Climate and Environment Risk
FCDO is required to assess climate and environment risk in Annual Reviews to align with the Paris Agreement on climate change. The risk of negative climate and environmental impacts from the APHID programme are low, as APHID has been designed to support the transition to sustainable food and agriculture systems.
For example, in 2024 our partner CABI has worked through the PlantwisePlus programme to promote climate-smart agriculture and promote nature-based solutions to restore landscapes. CABI has supported over 3 million smallholder farmers in 2024 with increased adaptive capacity to respond to climate change and reached over 5 million farmers with climate-smart options to respond to climate hazards. The PlantwisePlus programme has also strengthened climate-focused partnerships in 2024, co-organising a regional workshop on identifying climate reporting mechanisms under the Paris Agreement. This helped to identify activities under PlantwisePlus that align with the priorities outlined in countries’ Nationally Determined Contributions and National Adaptation Plans, ensuring targeted, government-backed support for farming communities facing increasing climate risks and variability.
At an organisational level, approaches to environmental impact assessment are documented as part of partner due diligence assessments.
Confirmation of compliance position
Area	Assessment
Legal compliance	FCDO ensures that each partner has an up-to-date due diligence assessment (DDA) on file, which provides a high level of confidence that partners are compliant with all relevant UK laws, regulations and guidance: / Due diligence assessments have been conducted for CVIM and GALVmed in 2024, with no major findings. / FCDO last conducted a due diligence assessment on CABI in 2016, and this was refreshed in 2019. A new DDA is currently being commissioned for CABI and will be completed by the end of 2025. The UK is also a member of CABI and has a seat on the board, so is well informed of CABI’s financial standing and organisational affairs. / The UK Representative in Rome is conducting a Central Assurance Assessment for FAO which will cover the due diligence requirements of this programme. / The Gates Foundation conducts due diligence assessments on downstream delivery partners before contracts are signed.
Branding	All delivery partners are complying with FCDO branding guidance, with UK International Development being referenced in publications and project/partner websites.
Gender Equality	The programme is compliant with the International Development (Gender Equality Act 2014). Research projects in the Gates portfolio aim to deliver new agricultural technologies and improve both men and women smallholders’ resilience to climate change, diseases, and pests. Gender issues are considered at the design stage of each grant. / CABI has developed an organisational Gender Strategy and reported gender disaggregated data for ICF KPIs and for farmers reached with plant health advice. / In 2024 and previous years CABI has conducted gender analyses in countries including Pakistan, Sri Lanka, and Uganda as part of the PlantwisePlus programme which have shown that women farmers often lack access to training, decision-making and protective measures against pesticide exposure. These assessments are then used to design programme activities that increase women’s access to information and resources.
IATI	FCDO has flagged gaps in IATI data to all partners and will follow up in 2025 ensure all data is published and correctly linked to FCDO funding.

Having flagged gaps in partner IATI data, FCDO should (re)share IATI guidance with partners, understand where issues remain, and link partners with FCDO IATI leads as necessary, to ensure full compliance going forward.

# PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
In 2024 FCDO partnered with CABI, CVIM, FAO, and the Gates Foundation under the APHID programme. While CABI, CVIM and FAO implement programmes directly, FCDO works with the Gates Foundation to co-fund downstream delivery partners, with the Gates Foundation directly managing all grantees, issuing grant agreements on behalf of both the Gates Foundation and FCDO, managing reporting and payment schedules, and sharing progress reports, financial reports and annual audited statements received from grantees with FCDO.
FCDO held regular meetings with all partners in 2024 to discuss project plans and progress, financial updates, and any risks. All delivery partners have performed well, and all narrative reports, financial reports and invoices have been received in a timely manner. Reporting indicates that each delivery partner is on track to achieve the agreed objectives. Annex 10 includes an assessment of each partner’s performance in 2024.
About changes to UK ODA
On 25 February 2025 the UK Prime Minister announced reductions in the UK’s Official Development Assistance (ODA) budget. This Annual Review covers the year to 31st December 2024 and therefore does not reflect the changes that will be made to the programme as a result of the reduction in ODA. At the time of drafting, work is ongoing to scale back ambition and targets under APHID.
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing ODA and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

# MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
Each APHID investment has its own results framework which is used to assess progress and impact. These results frameworks guide partner reporting and are assessed in Section C of this Review. Each results framework is designed to contribute to the outputs and outcomes in the wider APHID Theory of Change (Annex 2).
This Annual Review has been compiled from partner Annual Reports and Annual Review meetings, as well as discussions and documents shared by partners throughout the reporting period. The Review was led by the APHID Programme Responsible Owner, with support from a Programme Manager, other Lead Advisers and Senior Research Fellows with technical specialisms in animal and plant health. The Review has been quality assured by the Food and Agriculture Research Team Leader. FCDO’s approach to partner monitoring is included in Annex 10.Annex 10.
Evidence
Research published in 2024 has highlighted the importance and relevance of APHID’s work on tackling animal and plant pests and diseases. Climate change is impacting respiratory, waterborne and vector-borne diseases, including zoonoses. Work on wheat estimates that a future climate is likely to increase the area suitable for wheat blast infection and reduce global wheat production by 69 million tons per year (13% decrease) by 2050. And Brazilian researchers published the result of a new study which showed that plant diseases affecting Brazil’s most important crops are set to worsen as global temperatures rise.
[note] Pequeno, D. N., et al., (2024). Production vulnerability to wheat blast disease under climate change. Nature Climate Change, 14(2), 178-183. https://doi.org/10.1038/s41558-023-01902-2
[note] Angelotti, F., Hamada, E., & Bettiol, W. (2024). A Comprehensive Review of Climate Change and Plant Diseases in Brazil. Plants, 13(17), 2447. https://doi.org/10.3390/plants13172447
Learning
APHID has been designed to provide a responsive knowledge and learning offer to FCDO, and to inform a cross-sectoral One Health (OH) agenda. CABI and FAO investments in particular are focused on responsive evidence generation and knowledge sharing respectively. These investments have performed well in this first year of implementation, establishing and strengthening OH communities of practice and conducting relevant research to inform policy and programming. CABI, FAO, and other members of the Quadripartite for One Health have worked with the FCDO Nature Facility to develop a One Health Learning Journey for FCDO. This will take place in early 2025.
Report Status
Partner	Date of last narrative report	Date of last financial report	Date of last audited accounts
CABI	March 2025	March 2025	June 2025
FAO	March 2025	March 2025	January 2025
Gates Foundation	Gates Foundation Grantees each submit narrative and financial reports and audited accounts at different points during the year, depending on the reporting schedule in their grant agreement with the Gates Foundation. All Gates Foundation Grantee reports and audited accounts are up to date.
The Pirbright Institute	April 2025	April 2025	July 2025

Annex 1: Brief Description of each APHID Investment.
Investment	Summary	Geography/ Partner
Component 1
Centre for Veterinary Vaccine Innovation and Manufacture (CVIM)	Drawing on the world leading expertise at The Pirbright Institute, CVIM assess promising new technologies and manufactures vaccines for clinical trials and deployment, a critical barrier to rapid translation of technology into products that can be deployed in developing countries. This will accelerate the delivery of vaccines for livestock disease, prioritising diseases with disruptive potential for developing country agriculture and the UK and important zoonotic diseases including coronaviruses and influenzas. / CVIM aims to bridge a specific research and development gap, the limited access to GMP capacity to take candidate vaccines to market. CVIM is building GMP (Good Manufacturing Practice) capability at Pirbright and developing vaccines for use in clinical trials in partnership with private sector vaccines developers. / The centre will strengthen existing links to organisations working on human vaccine development to select products and disease targets. R&D pipelines have been identified, targeting high impact livestock diseases some of which have the potential to spillover to humans or pose a threat to the UK farming sector. These include RNA vaccines, recombinant DNA vaccines and Virus-like Particle (VLP) vaccines.	Global / BMGF, UKRI
Global Alliance for Livestock Veterinary Medicines (GALVmed)	With support from FCDO and BMGF, GALVmed has become established as a global leader in catalysing the development of cheap and effective combination livestock vaccines. GALVmed vaccines reach millions of farmers in developing countries. The organisation has a very successful track record of leveraging private sector investment by addressing barriers to product development. A new phase of funding to GALVmed (VITAL-2) will include: / Phased vaccine development programmes to develop two new vaccines, a) a new novel multivalent Rift Valley Fever Vaccine, a development programme will assess two novel candidates. B) a phased program to assess the viability of an existing novel sub-unit construct as a Haemorrhagic Septicaemia vaccine in Africa.3) on-going opportunity assessments of vaccine development projects with industry and academic partners. / Delivering private sector led vaccine supply chains. Supporting five commercial vaccine manufacturers expand their markets to service the ruminant vaccine market in three focus countries through investment in upstream vaccine manufacturing and supply, and downstream supply and demand creation. A third component will monitor progress. / Enabling the Vaccine Environment: work to build an enabling public policy environment for the development of commercial animal health markets. A) vaccine advocacy to create a conducive policy environment B) supporting the development of public-private partnerships 3) building effective industry associations	Global / BMGF
Component 2
Centre for Tropical Livestock Genetics and Health (CTLGH)	CTLGH is a global research alliance that aims to improve the health and productivity of livestock in the tropical regions of Africa and South-East Asia. FCDO co-funded the first phase from 2017 - 2022 with BMGF. The project is delivered by the University of Edinburgh (through the Roslin Institute), Scotland’s Rural College (SRUC) and the International Livestock Research Institute, and has hubs in Edinburgh, Nairobi, and Addis Ababa. / CTLGH harnesses advances in genetics, genomics, animal breeding and data science for livestock production systems in low- and middle-income countries (LMICs). The next phase will serve to support the delivery of CTLGH’s strategic plan to focus on the development of tools and innovations for resilient livestock smallholder systems over the next decade. In particular, the programme will develop technical solutions for genetic improvement by focusing on productivity, health resilience (endemic diseases) and adaptation (e.g., tolerance to heat and humidity). The anticipated outputs will be used to enhance health traits, adaptation, productivity, and emission intensity.	Sub-Saharan Africa / BMGF
Bovine TB research	Bovine tuberculosis (bTB) is a chronic disease that limits livestock productivity and threatens human health. bTB is well controlled in high-income countries through implementation of costly test and slaughter control programs. In contrast, bTB remains endemic in India, Ethiopia and many other developing countries because national control programs have not been implemented and test and slaughter control is not economically or culturally viable. Despite the substantial burden, there are no national bTB surveillance, control, or elimination programs in place, and a lack of clear policy guidelines for managing bTB. / A third phase of funding will build on the progress made in previous phases to accelerate the development and implementation of rational evidence-based approaches to control bTB in developing countries.	Ethiopia and India / BMGF
Nature based solutions innovation consortium for plant pests and diseases	With support from FCDO and other investors, CABI has established the BioProtection Portal to provide an open access resource that enables farmers and agricultural advisory services to correctly identify, source and apply registered nature-based solutions for agricultural pests, such as biocontrol and biopesticides. Development of the Portal has enabled CABI to build relationships with bioprotection manufacturers and regulatory authorities and build a network of organisations interested in expanding the availability of bioprotection products. / Drawing on this wealth of data and building on the commercial and regulatory opportunities that have been identified, CABI will lead a consortium to identify and research candidates for novel bioprotection products. The consortium would undertake early-stage discovery for novel products and identify existing products that, due to regulatory barriers or market sensitivities, are not available, focusing on the plant health challenges and product opportunities in the global South.	TBC / CABI
PlantwisePlus	PlantwisePlus is a global, multi-donor programme, that contributes to food security and improving the incomes and livelihoods of smallholder farmers through sustainable approaches to crop production that deliver safer and higher quality food in domestic markets. Working through a network of partners in developing countries, the programme delivers activities that deliver pest preparedness, pesticide risk reduction, and advice to farmers. The PlantwisePlus vision is to empower women and men smallholder farmers to confidently face evolving plant health threats, increase their incomes, improve food security and safety, and prevent biodiversity loss, through the promotion of sustainable crop production practices. PlantwisePlus builds on the successful, and impactful, Plantwise programme with the ambition to reach 75 million smallholder farmers in low- and lower-middle-income countries, providing them with access to the knowledge and skills they need to improve their agricultural production practices. This will be achieved by supporting countries to predict, prevent and prepare themselves for plant health threats in the face of a changing climate. And will ensure that farmers reduce their crop losses and produce more food using safer practices that safeguard human health and the environment. / PlantwisePlus has also developed a series of research questions to test the assumptions that are implicit within the programme, provide evidence on which to base future actions, understand whether the actions will achieve the expected changes, learn about unexpected consequences and provide evidence of what change has been achieved	Global with focus on Bangladesh, Ethiopia, Ghana, Kenya, Nepal, Pakistan, Uganda, Zambia, / CABI
WAVE (The Central and West African Virus Epidemiology) programme	A regional research initiative in Central and West Africa (CWA) which aims to / improve viral disease diagnostics and the management and control of cassava brown streak and cassava mosaic disease in the region. / raise awareness of, and train, cassava value chain actors (farmers, producers' associations, seed multipliers, agricultural advisors, policy makers and plant protection agents) on cassava diseases, their impact and on agricultural productivity and management best practices to prevent the diseases and their spread. / WAVE aims to catalyse sustainable protection and productivity of root and tuber crops in West and Central Africa through improved understanding and coordinated management of viral disease threats. Since 2015, WAVE has built strong partnerships with critical institutions and policy makers in 14 Central and West African countries, and has conducted research, gathered evidence and implemented pilot studies that are designed to trigger meaningful changes in existing national and regional plant disease management systems. / Building on the work since 2015, we will support a 24-month Bridge Period that will be focused on: / Developing a Functional Rapid Planning and Response (FRap) system with key partners. / Developing a clear, sustainable strategy that sets out WAVE’s role in the plant disease management ecosystem and wider relevant systems in sub-Saharan Africa. / Continuing research work and priority program activities across WAVE’s focus areas to ensure long-term readiness.	Benin, Burkina Faso, Cameroon, Côte d’Ivoire, DRC, Gabon, Ghana, Nigeria, Sierra Leone and Togo / BMGF
Wheat Disease Early Warning Advisory System (DEWAS)	Wheat DEWAS aims to provide an open and scalable system capable of preventing disease outbreaks from novel pathogen strains. The system builds on a prototype system developed by the research team to provide near-real-time model-based risk forecasts for governments, resulting in accurate, timely and actionable advice to farmers. As plant pathogens continue to evolve and threaten global food production, the system strengthens the capacity of countries to respond in a proactive manner to transboundary wheat diseases which will be sustainable over the long-term. The system focuses on responding to and containing the two major fungal pathogens of wheat known as rust and blast diseases. / The project is led by CIMMYT, and Cornell University’s College of Agriculture and Life Sciences. This project brings together research expertise from 23 research and academic organizations from sub-Saharan Africa, South Asia, Europe, the United States and Mexico.	Bangladesh, Bhutan, Ethiopia, India, Kenya, Nepal, Pakistan, Tanzania, Zambia, / BMGF
Targeted research with UKRI	FCDO’s Global Health and Food and Agriculture Research Teams have partnered with UK Research and Innovation (UKRI) on a number of programmes in the past ten years, notably the Zoonoses and Emerging Livestock Systems (ZELS) programme and the Joint Global Health Trials programme with the Medical Research Council. Initial discussions have been held with UKRI to scope out the potential for a new collaborative research programme on zoonoses and One Health. This would bring together the Global Health Research and Food and Agriculture Research Teams, working closely with policy leads, for applied multi country research to deliver new evidence and innovation to tackle existing and emerging zoonotic disease threats which have epidemic and pandemic potential, and impact vulnerable groups and women/girls, taking climate warming, changing land use and environmental degradation into account. / FCDO and UKRI are working to fund grants taking into consideration target geographies, diseases, shared technology platforms and potential for working with other UK Government Departments. Calls will be managed by the Medical Research Council (MRC).	TBC / UKRI
New plant/animal health work with BMGF	Building on the strong partnership with BMGF and plant and animal health research and innovation, FCDO will work with BMGF to identify new co-investment opportunities as part of our responsive offer to emerging and changing threats.	TBC / BMGF
Component 3
Global Burden of Crop Loss (GBCL)	GBCL supports global food security by providing robust estimates of crop losses to enable better informed action to protect crops and aims to produce trusted metrics on the burden of crop loss across geographies and crops. Through an initial focus on wheat and maize as pilot crops, GBCL has developed methods, engaged with stakeholders and built partnerships. A proof-of-concept provides global loss estimates to country-level for these crops, and work is underway on attribution and on country case studies for Kenya, Ghana, Zambia, and South Africa. / Over the next five years, full global estimates of the economic burden of crop loss will be produced for at least six crops including maize, wheat, rice, and soya, attributed to major biotic and abiotic causes. As part of this expansion and the requirement to collate different types of data from a wide range of sources, automated text extraction using natural language processing (NLP) or deep-learning language models such as GPT-4 will identify and collect evidence on reported pest impacts and their subnational-level distribution which are essential for underpinning assessment of the key pests contributing to the biggest share of overall global crop losses. GBCL will disseminate these estimates as a global public good, via a user-friendly interactive dashboard and a series of open access papers, accompanied with policy engagement activities in selected countries, will support uptake. Accessible and comprehensive estimates of the loss burden of strategically significant crops will provide a valuable resource to a range of stakeholders, allowing policy makers and programmers to better target finite resources, helping research funders identify critical gaps in the science base and enabling local and global researchers to better understand and communicate key plant health challenges to a wide audience.	Global / CABI
Juno Evidence Alliance	Juno is a new evidence alliance that supports evidence synthesis and decision-making in the symbiotic fields of agriculture, food systems and climate adaptation. This evidence coalition brings together researchers, policy makers, publishers, computer and data scientists, and evidence advocates from across fields and disciplines. It spans academic, intergovernmental bodies, and civil organisations in an effort to break down traditional boundaries between research production and use. Juno aims to deliver evidence reviews through: / Policy relevant work with donors and governments to prioritize evidence assessment needs. / Accelerated solutions, including normative and technical standards, as well as new services, platforms and systems for end users. / Standards driven science that expands the data sources used in evidence synthesis and applies Artificial Intelligence to speed up discovery and analysis. / Global network to deliver education & training, and champion the uptake & use of evidence in decision making.	Global with a focus on sub-Saharan Africa and South Asia / CABI
One Health Hub UK	Collaboration within and between different sectors is a core tenet of One Health. However, bringing together diverse groups of organisations and individuals and facilitating the sharing of evidence and knowledge to enable effective OH action requires dedicated resources and expertise. FAO’s OHKN will provide vital support to help organisations working in developing countries to collaborate and synergise effectively to build advocacy and political will and leverage investment for an evidence based OH approach, with a focus on driving change at country level. However, it is not structured to provide a responsive knowledge and learning offer to FCDO, or other UK Government Departments, on OH. There is also a need to support synergies, coherence and learning across the portfolio of investments proposed under the APHID. / The One Health Hub UK supports a dedicated Knowledge, Evidence and Learning function, managed by the UK-based, international research organisation CABI, to deliver a responsive offer, support evidence synthesis, and, over time, streamlined monitoring and evaluation and reporting across the Platform. This role will draw on CABI’s well established capability in managing research and innovation, its network of partnerships with UK and international science institutions, and its capabilities in knowledge management and capacity building.	Global / CABI
OHKN (through FAO)	The One Health Knowledge Nexus, pioneered by FAO and with the support of the Quadripartite (UNEP, WHO, and WOAH) and other partners, offers a space for One Health Communities of Practice (CoPs) that bring together stakeholders from governments, academia, NGOs, international organizations, and the private sector. By fostering knowledge exchange and collaboration on pressing issues such as emerging diseases and pests or antimicrobial resistance, the One Health Knowledge Nexus stimulates learning, generation of new information, and enhanced practice with the aim to inform One Health decision making and implementation, and improve the health of people, animals, plants, and the environment. The various CoPs are connected by a digital space designed for learning and careful facilitation that offer opportunities for engagement including face-to-face and online.	Global, with country focus / FAO
[note] Directorate General for International Cooperation of the Netherlands (DGIS), the Swiss Agency for Development and Cooperation (SDC); the European Commission Directorate General for International Partnerships (INTPA); the UK Foreign, Commonwealth and Development Office (FCDO). The Embassy of the Netherlands in Burundi provides exclusive and country-specific funding. The Ministry of Agriculture and Rural Affairs of the People’s Republic of China provides exclusive financial contributions for programme activities in China.

Annex 2: Theory of Change for the Animal and Plant Health Innovation and Evidence Delivery (APHID) Platform

Annex 3: Centre for Vaccine Innovation and Manufacturing Product Pipelines.
Foot-and-mouth disease, virus-like-particles
Background: Foot-and-mouth disease (FMD) infects cloven-hooved livestock and outbreaks impart severe financial impact through reduced productivity and restrictions on trade. This project supports an existing consortium (The Pirbright Institute; University of Oxford; University of Reading and private sector partners) to develop a pentavalent FMD vaccine for East Africa that is based on baculovirus expressed Virus Like Particles (VLP) with improved stability, productivity, and lower cost of goods. The project has now transitioned fully to the private sector partner with CVIM providing some support for in vivo protection studies for product registration.
Rift Valley Fever vaccines
Background: Rift Valley Fever (RVF) is a zoonotic disease affecting both humans and livestock. The causative agent, RVF virus, is transmitted between livestock by mosquitoes. A ChAdOx1-based vaccine has been developed at the University of Oxford; the objective of this project is to develop cost-effective manufacture of this ChAdOx RVF vaccine for livestock.
CVIM has now successfully completed the development of upstream bioreactor-based and downstream filtration processes (aside from final filtration step due to consumables lead times) which is aligned with production processes in the African commercial partner, an established veterinary vaccine producer. CVIM has also shown that significantly higher yields vaccine antigen can be achieved by using an alternative adenovirus vector, human adenovirus 5 (Ad5). CVIM is in the process of securing all the necessary licences to transfer this technology to the commercial partner and will continue this work with Ad5.
Nanoparticle platform
Background: This is a collaborative project with The Institute for Protein Design (IPD) at the University of Washington. It evaluates the production and immunogenicity of computationally designed two-component self-assembling nanoparticles that facilitate multivalent display of antigens. Key objectives are to develop a yeast expression platform based on suspension culture of the yeast Pichia pastoris, and to determine the levels of secreted nanoparticle-antigen subunit. The two target antigens for this project are the spike protein of avian infectious bronchitis virus (IBV) and the H protein of Peste des Petits Ruminants virus (PPRV), which cause infectious bronchitis (IB) in chickens and Peste des Petits Ruminants (PPR) in small ruminants, respectively.
Yeast strains expressing the nanoparticle-antigen subunit bearing the receptor binding domain (RBD) of the infectious bronchitis virus (IBV) Spike protein have been generated; this was achieved through screening a panel of 16 alternative secretion signals and evaluation in 3 different yeast strains. Work is underway to establish yeast growth and subunit production in bioreactors.
Marek’s disease vaccines
Background: Marek’s disease, a lymphoproliferative disease that causes tumours and immunosuppression, results in major losses to large- and small-scale poultry production globally. Herpesvirus of turkeys (HVT) is used as a live viral vaccine in chickens and turkeys. Current HVT vaccines are problematic – they are produced using cells isolated from embryonated eggs and because predominantly intracellular, necessitating an ultra-low temperature (liquid nitrogen) distribution chain.
This project had two initial objectives: (1) the development of a DF-1 suspension cell culture system to produce HVT, and (2) the generation of extracellular HVT through the deletion of target viral genes. These results show that although CVIM has successfully conducted planned R&D activities for the Marek’s Disease vaccine programme, the desired objectives were not obtained. CVIM has therefore re-focussed the project to evaluate the development of Marek’s disease subunit vaccines based on adenovirus and RNA platforms to try and achieve the primary goals of the programme, which is the development of a new vaccine for Mareks disease.
RNA vaccine platform
Background: Following a successful proof-of-concept immunogenicity study in sheep with a Peste des Petits Ruminants (PPR) vaccine, CVIM has expanded its work on RNA vaccines to fully evaluate their application in livestock. CVIM are developing a vaccine against bluetongue virus (BTV) because of the recent incursion of BTV into the UK and the poor efficacy of currently available vaccines. The BTV RNA vaccine is a test case for developing an emergency response vaccine to new and rapidly spreading viral outbreaks in the UK.

Annex 4: Impact of time-to-act pest alerts in Kenya.

Annex 5: Summary of the Global Burden of Crop Loss approach.

Annex 6: One Health Bibliometric Analysis example
This graphic shows the number (Panel A) and proportion (Panel B) of One Health publications related to each of the six Action Tracks of the One Health Joint Plan of Action, published between 2010-2024.
The share of publications across the action tracks has converged to balanced proportions between 20-30%, with Action Track 6 lagging in terms of numbers and proportions since 2017.

Annex 7: Examples of OHKN data analysis

Annex 8: CABI Gender work
In Pakistan, this approach led to the sensitization of over 200 farmers in Kyber Pakhtunkhwa province on lower-risk pesticide practices like the importance of personal protective equipment (PPE), and the risks associated with handling agrochemicals. Special emphasis was placed on women’s exposure, particularly through washing contaminated clothing and providing first aid to affected family members. PlantwisePlus also introduced gender-sensitive IPM strategies, ensuring equal access to information, training, and decision making. Recommendations included recognizing women as farm workers, increasing their awareness of pesticide risks, developing targeted educational materials, and involving them in advisory services, media campaigns, and policy discussions.
Gender technical working groups (GTWGs)
Across all programme activities, CABI recognizes the unique challenges associated with age and gender. Gender and youth experts provided input into plans, concept notes, reports, IPM guidelines and handbooks, communication materials, and mass communication campaigns to ensure that approaches and messages were gender sensitive and, in particular, empower women and youth to adopt lower-risk products and practices.
In response to recommendations from prior research, CABI has established a GTWG and Multi-Stakeholder Forum model that brings together key stakeholders – including government ministries, civil society organizations, international non-governmental organizations, universities, and private sector institutions – to address gender disparities in agriculture and ensure equitable access to agricultural extension support for women.
First launched in Pakistan and Ghana in 2022, GTWGs operate by fostering stakeholder collaboration on gender equity in agricultural extension. They develop a roadmap outlining key actions and responsibilities, bridging policy–practice gaps and strengthening commitments to gender equality. CABI’s regional gender coordinators facilitate training sessions on gender-sensitive strategies in agricultural projects. GTWGs also serve as platforms for discussing policy interventions, tracking gender-transformative actions, and addressing challenges. Through knowledge sharing and policy advocacy, GTWGs influence decision making and drive structural changes in national agricultural extension systems, promoting inclusive participation in agricultural and environmental development.
Sustainability and local ownership
Gender directorates and Ministries of Agriculture lead the GTWGs, ensuring local ownership and supporting long-term impact. A sustainability strategy, including an exit plan for CABI, is developed from the outset and periodically reviewed. As part of this plan, CABI provides capacity-building support and facilitates a gradual transition, with full handover expected after three to four years.
By embedding GTWGs within national frameworks, the initiative fosters accountability and long-term commitment to gender-inclusive agricultural policies. Following proven success in Pakistan and Ghana, this model will be scaled up to Zambia and Bangladesh in 2025.

Annex 9: Risks by Partner
Partner	Risk
CABI	CABI manages risk at various levels across the organisation. The Audit and Risk Committee at Board level, and the Executive Council (of Member Countries) sub-Committee on Finance and Risk, review the organisational risk register. Programme and project risks are also captured as part of project set-up and then reviewed throughout the project lifecycle. / The principal risk of relevance to CABI’s APHID Investments is potential reductions in donor funding, including to their flagship programme, PlantwisePlus. CABI aims to mitigate this risk by diversifying funding sources and making efficiency savings to ensure that existing income is used effectively. For example, in 2024 they obtained funding from a new funder, the Wolfson Foundation, to support relocation and upgrading of their laboratory facilities in the UK. / CABI has also flagged risks relating to a paucity of quality of data for research programmes such as the Global Burden of Crop Loss, as this impacts CABI’s ability to generate accurate estimates. CABI is mitigating this risk through the development of their own models, using field trial data.
FAO	Key risks that have been highlighted by FAO include delays in signing project agreements with partners including the Quadripartite, and associated delays in initiating activities. FAO is also concerned about limited commitment and interest from external stakeholders, particularly in communities of practice (CoPs). To mitigate against these risks, FAO plans to maintain a high level of engagement with the Quadripartite partners, including them in discussions about activities even before agreements are signed. FAO will also hold consultations on the needs identified by a core group to ensure that project activities are tailored accordingly.
Gates Foundation	For programmes co-funded with the Gates Foundation, in 2025 FCDO and GF will be monitoring for sustainability of interventions. For example, the WAVE programme has made a significant contribution to pest and disease monitoring and reporting, but the current model is reliant on donor funding. WAVE is currently exploring different options for institutional ownership.
The Pirbright Institute	The CVIM risk register is reviewed quarterly by the Joint Oversight Committee, on which FCDO has an observer seat. The risk register is then shared with the Board and Trustees. / Major risks highlighted in 2024 include risks of data loss; risk of inadequate monitoring and control of timely detection and rapid response to critical alarms and emergencies; and a failure to demonstrate financial stability and independence. Each of these risks is adequately managed by the risk owner and Director of Risk and Assurance, with oversight provided by senior management and the Joint Oversight Committee.

Annex 10: Monitoring and Partner Performance
Partner	FCDO monitoring approach and Partner Performance
CABI	CABI is a key delivery partner for APHID and has a strong track record of delivery for FCDO and other UK Government Departments. An FCDO representative attends CABI’s Board Meetings to review commercial and financial affairs and risk management. CABI and FCDO also hold regular meetings for each APHID Investment to assess progress and ensure that FCDO has the opportunity to review key programme outputs. Where the Gates Foundation has co-funded investments (GBCL) results frameworks have been agreed jointly with both donors, and update calls are held together. FCDO also attended the PlantwisePlus Donor Forum in May 2024, in order to receive a detailed update on programme activities and convene with other donors. / Organisationally, CABI performed strongly in 2024, as measured against their Medium-Term Strategy indicators. CABI met or exceeded 18 of their 23 active targets in 2024, and the five targets remaining were 80% met. Programme expenditure is on track. FCDO and CABI have discussed the need for more regular financial reporting for APHID investments, and in 2025 financial updates will be shared quarterly.
FAO	The FCDO programme team initially held monthly meetings with FAO, moving to quarterly once the programme was established. FCDO has held two in-person meetings with FAO during 2024 to finalise project design and build synergies with other APHID investments. / FAO have focused on foundational work in the first year of implementation, successfully recruiting the programme team, formalising partnerships with WHO and CIRAD, and establishing new One Health Communities of Practice. While programme spend in 2024 was lower than anticipated (584,851 USD against a budget of 2,086,600 USD), principally due to delays in signing the formal agreement, budgets and payment schedules have been adjusted and the rate of spend has increased over recent months as programme implementation has gained pace. / The UK Representative to Rome is leading on the refreshed Central Assurance Assessment for FAO that will document assurances in key commercial and financial areas. / FAO is currently finalising a full monitoring, evaluation and learning plan to capture programme impact. In 2025 the programme will start to report against outcome level indicators.
GALVmed	Performance not reviewed in this annual review as no activity was planned in 2024 under APHID.
Gates Foundation	For the Bovine Tb, CTLGH, DEWAS and WAVE investments, FCDO has channelled funds through the Gates Foundation to grantees. This funding arrangement is governed by the Gates Foundation/FCDO Collaboration Framework (2016-2026), and the Gates Foundation directly manages all grantees in the portfolio, including conducting due diligence assessments before agreements are signed. The grant agreements between the Gates Foundation and the grantees include FCDO’s core requirements – including, for example, the requirement for an annual audited statement. The Gates Foundation maintains regular contact with FCDO on grantee progress and emerging issues. Additionally, the FCDO seconded staff member to the Gates Foundation from March 2021 continues to coordinate and support the partnership building with frequent visits to both the Foundation and overseas to the jointly funded projects. / Throughout the reporting period, FCDO engaged closely with the Gates Foundation Programme Officers to track progress on the grants, particularly through the FCDO secondee role. Progress reports, financial reports and annual audited statements have been submitted on time (per the Gates Foundation reporting schedules) by all grantees during the reporting period. FCDO approval of grantees’ progress reports and their annual audited statement is required before payment is released.
The Pirbright Institute	Within the Pirbright Institute CVIM has its own governance structure and is scientifically independent. FCDO has an observer seat on the CVIM Joint Oversight Committee (JoC), which meets quarterly to discuss programmes, risk, and financial performance. Narrative and financial reports are produced for members in advance of these meetings. / Reports are also submitted to the Scientific Strategy Board (SSB), where FCDO and the Gates Foundation are observers. The SSB assesses technical progress and reports to the JoC. CVIM has a detailed results and milestone tracker and risk register which are stored on the Pirbright website along with all JoC and SSB meeting documents. These are reviewed each quarter by the JoC. / During the reporting period, financial reporting provided by Pirbright was timely and of a good standard, with any variance from forecasts within the acceptable range. Payments are made six-monthly; as of May 2025, just over 50% of FCDO’s commitment to CVIM has been paid.
UKRI	Performance not reviewed in this annual review as no activity was planned in 2024 under APHID.