Programme Completion Review

Title: FP2030 - The Global Family Planning Partnership
Final Programme Spend £ (full life): £6,000,000	Review Date:
Programme Code: [AMP ID#]	Start Date: 4/1/2022	End Date: 31/3/2025

Summary of Programme Performance

Year	2022	2023	2024
Programme Score	B	A+	A
Residual Risk Exposure Rating	Minor	Minor	Major

DevTracker Link to Business Case (and any addendum):
DevTracker Links to all logframes used during programme lifetime:

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]

Over the course of this 3-year programme, FP2030 has shown strong dedication to their mandate -of advocacy, data and accountability on family planning. Building on its transition from FP2020, the partnership has secured 219 commitments from governments and non-state actors, to reinforce the global momentum for voluntary, rights-based family planning.

To bolster their agenda and further facilitate country-ownership of family planning and the partnership, FP2030 decentralised their governance structures into 5 regional hubs (North, West and Central Africa; East and Southern Africa; Asia Pacific; Latin America and Caribbean; and North America and Europe). The transition was challenging for FP2030 with the contracting of new hub hosts, onboarding staff and operationalisation of 4 new locations globally taking longer than expected. Furthermore, the time and resource cost of managing a decentralised network even after establishment remain high with 2-year re-contracting cycles for hubs, ensuring alignment of human resource policies across hubs, and financial management across a more complicated structure. The regional hub structure has however brought potential efficiencies and strengthened the partnership too. This regionalisation has brought decision-making closer to country governments, strengthened local leadership, and enabled more tailored support and accountability.

Since 2021, FP2030 has secured a total of 219 family planning commitments (49 from country governments, 5 donor commitments and 165 from other non-government actors including the private sector and donors). They also achieved 43 advocacy wins – 15 that improved family planning programs and policies; 13 that mobilised funding for FP; 6 that enhanced government accountability; and 9 that elevated the profile of FP at global, regional, and national levels. Using commitments as a rallying point and anchor for tailored advocacy and accountability efforts, FP2030 contributed to the mobilisation of political will from government decision makers and brokered support from civil society partners to help governments implement their commitments.

FP2030 managed to secure fewer donor commitments than initially predicted. However, given the challenges around ODA in 2025, it feels right to prioritise commitments from country governments and non-government actors.

Also, during this period, FP2030 has been a leader in family planning data. They have worked to improve the indicators used to measure family planning, including developing new indicators around women’s choice in family planning use; developing a youth and adolescent dashboard; and convening experts to elevate underrepresented country voices and priorities for family planning measurement.

In its evolution to FP2030, the organisation has fully transitioned to a decentralised operating model and deepened its focus on inclusion by strengthening country-led advocacy for rights-based family planning and ensuring that youth, persons with disabilities, and other marginalized groups have a seat at the table in shaping national strategies and priorities, and central role in leading advocacy.

More broadly, this period was marked by positive trends in contraceptive access, choice, and use. As of 2024, there are nearly 100 million more contraceptive users in low and lower-middle income countries than there were in 2012 when FP2020 first began.

FP2030 has also faced challenges in keeping their operating model relevant to an ever-changing world. They have had to justify their narrow focus on family planning as the sector shifted towards focusing more comprehensively at SRHR or the more difficult to achieve elements of it. They have also struggled to ensure that all countries report on their family planning commitments through self-reports, a key accountability tool to show that the commitment making process actually leads to impact.

FP2030 find themselves now in a much more difficult context than 2020. FP2030 will need to maintain their dedication to inclusive, rights-based, and country-led family planning within the new ODA reality. It is more important than ever to continue articulating their contribution and value add to the sector through their focus on family planning specifically and their regionalised approach to advocacy

Furthermore, FP2030 will need to adapt its strategies to respond to the demographic shifts across the world which potentially threaten rights-based family planning access. FP2030 have already shown some engagement with this. They were invited by the Pakistan government to provide technical expertise at the National Population Conference in July 2023, to provide advice on rights-based family planning in a context of stagnating population in the country.

FP2030 have embarked on a process to restructure and reprioritise their work to respond both to the new financial, political and social developments in 2025 and beyond, and to respond to direct funding challenges for their organisation as a result of reduced ODA.

Major lessons learned, evidence generated and recommendations [1/2 page]
- Regional Leadership: Over the past three years, FP2030 has navigated a rapidly evolving global context for Family Planning. A major lesson learned is the critical importance of decentralizing ownership and investing in regional leadership. Their transition to a distributed support network, with regional hubs in Africa, Asia, and Latin America, has enabled more context-specific engagement, greater political responsiveness, and stronger accountability to country commitments. FP2030 partner feedback and commitment tracking shows that regional-proximity fosters more sustained momentum toward national family planning goals, even in fragile or contested political environments. Additionally, we’ve learned that sustained progress requires embedding family planning within broader health, gender, and development agendas to protect it from political volatility.
- Accountability: FP2030 would benefit from a greater push on family planning commitment self-report returns and other methods of assessing progress against commitments. It should be recognised that governments are responsible for reporting on their commitment, and too stringent reporting requirements could lead to fewer commitments. By not reporting on a commitment, it throws into doubt whether the commitment still holds. Without reporting, it is not clear if commitment making is an effective method that really does lead to progress on rights based family planning, questioning the whole model.
- Family Planning vs comprehensive SRHR: FP2020 was created to specifically advance family planning, in contexts where a fully comprehensive SRHR offer was difficult (or opposed by the government). Many countries still cannot meet the modern contraceptive needs of their populations and there is an argument for advancing rights-based family planning as the most basic (yet effective) SRHR service in these geographies. Over the course of the programme, there have also been some challenges for this approach – the sector has moved to financing SRHR more comprehensively and arguments have been made for family planning to be financed by domestic governments rather than aid. With the fast changing ODA/Aid context, FP2030 must articulate their value add as an organisation focusing specifically on family planning.
- Pivoting to respond to the new ODA realities: FP2030 find themselves in a challenging context at the end of this programme period in 2025 with global reduction in ODA, greater opposition to sexual and reproductive health and rights, and a continually growing need for access to family planning. FP2030 will need to show that they can pivot from operating in a donor-financed and dependent sector and to use their new structures to better mobilise funding from government domestic resources, non-government partners and non-traditional actors. They are still too focused on donor financing for the sector.
- Protecting Rights Based Approach: It is clear from the FP2030 programme results that different countries are at different points in their journey towards providing rights based family planning. FP2030 has always pursued a mix of a pragmatic and aspirational approach to their work, recognising commitments that may not be fully inclusive yet but are on the right trajectory to ensuring people have access to critical FP services. With a growing opposition to SRHR and FP and demographic changes leading to more natalist policies in some countries, FP2030 must remain dedicated to the rights focus of their work. They also need to provide more central analysis on commitments to ensure they aren’t inadvertently endorsing commitments which showcase a rollback from previous commitments, or are harmful to their agenda.
- Youth and Adolescents: FP2030 have put significant effort into engaging youth and adolescents in their governance structures and advocacy work. This is incredibly welcome and should continue. One suggestion would be to explore, potentially with other partners in this field, whether the commitments are having the desired impact on SRHR access for young people.
- Data: FP2030’s data stream has been commended by partners in the sector. However, the cuts to the health data infrastructure will require FP2030 to consider seriously how they can continue to successfully contribute to advancements in this area.
- Programmatic Lessons: The key programmatic lessons to highlight is around the challenges in designing and updating a meaningful and fair results framework/logframe for this programme. The logframe for the programme was updated yearly to reflect the programme realities and following a period of learning since programme design. The latest iteration of the logframe was in 2024 with the aim to a) ensure the logframe was ambitious enough b) adequately captured delivery successes after 2 years of operational transition c) articulated FP2030 specific contribution to global advocacy on rights-based family planning and d) did not hold FP2030 to account for deliverables not in their power. Whilst the FCDO and FP2030 were happy with the new logframe, it is evident in some areas of this PCR that the milestone setting was not accurate or ambitious enough. This is always a challenge for advocacy programmes. Some scores have therefore been adjusted to both recognise FP2030s achievements and provide a balanced assessment of progress against indicators. Therefore to calibrate scores in this PCR, indicators which greatly exceeded targets with a strong indication that the indicator was low ambition were classified as met (rather than exceeded).

How this report was conducted [1 paragraph]
This report was developed through a consultative process drawing on inputs from FP2030’s global support team and all four regional hubs to ensure a comprehensive and context-specific perspective. Evidence sources included internal progress tracking data, regional and country-level commitment updates, partner feedback, and documentation from technical convenings and working groups held over the past year. The process was informed by FP2030’s monitoring framework and aligned with our Theory of Change, allowing for a structured analysis of progress, challenges, and emerging trends across regions. Regional hub teams played a central role in identifying priority themes and validating key lessons and recommendations, ensuring the report reflects both global oversight and local realities.

Actions following approval of this report [1-2 paragraphs]
All payments have now been made to FP2030, and there are no assets to return or dispose of. Whilst the programme is closing, FCDO will continue engage in FP2030 meetings to remain coordinated with key SRHR and family planning partners. Following the budget allocation process after the 3-year spending review, FCDO will consider its future funding to FP2030. This decision will follow a strategic portfolio level review in line with HMG priorities for the next 3 years, and will integrate existing analysis within the SRHR team on investments on global advocacy.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£6,000,000	£6,000,000
Timeframe	31/03/2022 – 31/03/2025	31/03/2022 – 31/03/2025
Outcomes	Outcome 1.1 - Increased ability of countries to provide rights-based family planning services equitably and sustainably through commitments to family planning and implementation of the High Impact Practices. / Baseline – 0 / Final Milestone Target - 6 country commitments, 4 CIPs	Moderately Not Met / Outcome 1.1 Percent of country commitments and costed-implementation plans that integrate HIPs, and other HIP’s evidence-based resources for country priority setting / Final Milestone Target - 90% country commitments; 90% CIPs / Achieved – 100% country commitments, NA on Costed Implementation Plans (Explained under the outcomes detail further down)
	Outcome 2.2 - Number of documented favorable multisectoral partnerships indicating greater resources for family planning, or fiscal policy change or traceable increased financial expenditure towards family planning, including creation of budget lines, inclusion of FP in health insurance coverage or other UHC schemes, new donor or private sector funding initiatives, workplace coverage of FP, co-funding/matched funding arrangements and others. / Baseline – 0 / Final Milestone Target - 10	Met / Outcome 2.1 Number of documented favourable multisectoral partnerships indicating greater resources for family planning, or fiscal policy change or traceable increased financial expenditure towards family planning, including creation of budget lines, inclusion of FP in health insurance coverage or other UHC schemes, new donor or private sector funding initiatives, workplace coverage of FP, co-funding/matched funding arrangements and others. / Final Milestone Target - 10 / Achieved – 43

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]
- FP2030 has been effective in cultivating, growing, and sustaining support for family planning at the global, regional, and country levels, and has accelerated government commitment making to family planning. In the 4 years of the programme (2021-2025), FP2030 secured 49 government FP2030 commitments, all of which included family planning high-impact practices. Compared to FP2020, when 48 country commitments were secured over the course of 8 years, FP2030 has demonstrated accelerated progress in securing family planning commitments.
- Through its global partnership, FP2030 has put significant energy into family planning advocacy, recording 43 notable instances of advocacy successes. This includes 15 policy changes and13 budgetary , 9 visibility, and 6 accountability wins (see below for examples). Investments in FP2030 enabled us to act as change catalysts/accelerators, advocate, and provide or broker technical assistance to governments in implementing their family planning commitments.
- FP2030 plays a valuable role as a convener and broker in the family planning ecosystem, facilitating collaboration between government, civil society, and private sector to enable countries to implement rights-based family planning programs. In addition to country commitments, FP2030 galvanized 170 more commitments from civil society and other non-governmental actors (including donors) to support governments to actualize their commitments.
- In low and lower-middle income countries, modern contraceptive use indicators show positive trends and continued progress. Since 2012 (when the FP2020 partnership began), the number of women in low and lower-middle income countries currently using a modern method of contraception rose by 97.5 million (35%), from 282.5 million that were using a method in 2012 to more than 380 million in 2024.
- The global family planning movement is at a major crossroads. In 2025, the sector has seen the US withdrawal of International Aid funding, and as a result, also the loss of technical knowledge, expertise, implementing partners, vital data and health infrastructure.
- Given the current strained funding environment and growing anti-rights movement, leadership and support for family planning is now more important than ever. It is critical to enable partners to hold the line for family planning and continue to push for SRHR in the face of mounting opposition.
- FP2030 could play an important role, especially with the launch of their Made Possible by Family Planning campaign this year, to coalesce the family planning community, elevate family planning on global, regional, and national agendas and ensure family planning is integrated within broader development agendas and is not deprioritized by governments, donors, and other important actors.
- Furthermore, as Sexual and Reproductive Health and Rights, continues to be controversial as a comprehensive package, FP2030 could play an important role in ensuring minimum access to rights-based family planning, or serving as a platform to keep channels of communication open with middle-ground and oppositional actors.

Significant changes and unexpected outcomes:
In January 2025, the Mexico City Policy was reinstated (as expected), resuming the previously expanded version of the policy that was adopted in the Trump administration’s first term. A freeze on foreign aid was first put in place, followed by the unexpected dismantling of USAID, which ended USAID-funded activities affecting. The impact is severe as more than three-quarters (289 million) of the 380 million modern contraceptive users in low and lower-middle income countries reside in a USAID investment country. With the loss of USAID funding, these women and girls are at significant risk of interrupted or discontinued access to family planning services and commodities. This not only curtails global progress but also threatens to reverse years' worth of gains in the family planning movement. The termination of USAID funding forced many key family planning implementing partners (previously USAID funded) to shut down their operations and make large scale reductions in force (RIF). That, coupled with the RIFs within USAID itself, has meant a huge loss in technical expertise and institutional knowledge for the family planning community, with immediate and long-term consequences.

The U.S. government also formally rejoined the Geneva Consensus Declaration, an anti-comprehensive SRHR political statement which now has 40 signatories. Sixteen of these are also FP2030 commitment-making countries. In contrast to a country signing the GCD, FP2030 commitments are generated through a collaborative, country-led process with sign off usually by a Minister (often Minister of Health) and followed by a public launch. While the GCD is not a formal, legally binding agreement and it’s unclear whether or how the signatories will operationalise it, it does underscore the fractured leadership and support for family planning within many of the commitment-making governments. FP2030 regional hubs will continue to engage commitment makers to monitor progress, as well as the impact on FP from actions on the GCD. Through our annual data and measurement work producing data on key family planning indicators and advocacy and accountability efforts at the global level, FP2030 will also reinforce government accountability to their family planning commitments.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

Impact Indicator	Starting Target	Final Logframe Target	Final Result Achieved
1. Trends indicate that in a growing number of countries, total contraceptive users, contraceptive prevalence, and demand satisfied show an advancement in the availability and use of modern methods of contraception.	Baseline: N/A	Positive country trends in contraceptive users, contraceptive prevalence, and demand satisfied	As of July 2024, more than 380 million women in low and lower-middle income countries are currently using a modern method of contraception, 97.5 million more than the 282.5 million that were using a method in 2012 when the FP2020 partnership began. In 26 countries, the number of users of modern contraception has doubled since 2012. / The modern contraceptive prevalence (MCP) has increased from 31.6% to 34.8% among all women and from 43.5% to 48.8% among married women over the same period. The increase has been most rapid in Sub-Saharan Africa where MCP among married women (from 19.7% to 29.1%). There has also been substantial progress among countries with the lowest MCP. In 2012, there were 13 countries with MCP below 10% among all women; now in 2024, only three countries remain in this category of very low modern contraceptive prevalence (Chad, Somalia, and South Sudan). / As of 2024, only 19 countries had surpassed the proposed 2030 benchmark for demand satisfied of 75% among all women (note that in 2012, 13 countries had already surpassed this benchmark). Between 2012 and 2024, levels of demand satisfied either increased (Latin America & Caribbean, Sub-Saharan Africa, and Middle East & North Africa) or remained steady (Europe and Asia) in all regions.
2. Trends indicate that in a growing number of countries a wide range of short-term, long-acting, permanent, coitally dependent, and on-demand (EC) methods are available, supported with sufficient counselling, and are in use by women and their partners.	N/A	Positive country trends in method availability, method counselling, and method mix	There have been positive trends in access to multiple methods of contraceptives. / In terms of method mix, we continue to see a shift from short-acting methods to long-acting reversible contraceptives. In particular, the shift in methods is characterized by the expanded availability and use of implants. In 2012, implants were the most commonly used method in only one country (Burkina Faso), while as of 2024, implants are the most common method in 13 countries and the second most common method in 15 countries.
3. Trends indicate increases in total financing for family planning – disaggregated by donor source and by country domestic expenditure	N/A	Positive trends in global and country financing for family planning	Positive trends were noted in global donor financing for FP (between 2022 and 2023) and country financing (between 2021 and 2022, the most recent data point available) for the majority of reporting countries. / Donor government bilateral funding for family planning rose from $1.27 billion in 2022 to $1.47 billion in 2023, bringing it back to 2021 funding levels. Between 2012 and 2023, donor funding fluctuated but remained relatively stagnant, with variances (in either direction) ranging from 0.6% to 13%. The largest increase (13%) in donor funding occurred in 2017 and funding levels peaked in 2019 (at $1.58 billion). / The 5 largest donors in 2023 were the U.S., whose funding accounted for 40% of the total global donations, followed by the Netherlands (17%), the U.K. (14%), Sweden (9%), and Canada (8%). / Analysis of available government expenditure in 2022 showed that 58% (or 26) of the 45 reporting countries had an increase in government expenditure on family planning compared to their 2021 spending.

Outcome Indicator	Starting Target	Final Logframe Target	Final Result Achieved
1.1 Percent of country commitments and costed-implementation plans that integrate High Impact Practices (HIP), and other HIP’s evidence-based resources for country priority setting	Baseline: N/A	90% country commitments; 90% CIPs	Moderately not met / 100% country commitments – Costed Implementation Plans (CIPs) (Not available, and therefore not met)

Outcome Indicator	Starting Target	Final Logframe Target	Final Result Achieved
2.1 Number of advocacy wins (instances of policy, funding, and/or program changes) as a result of advocacy efforts of civil society partners supported by FP2030, including but not limited to the adoption of new policies, new or increased financing in support family planning, or integration of new HIPs into FP programs and health system interventions.	0	5	Met / 43 total advocacy wins (15 policy, 13 budget, 9 visibility, and 6 accountability wins)

FP2030’s theory of change shows that: generating strong, sustained leadership and support for family planning through public FP2030 commitments that have accountability mechanisms embedded; supporting the scale up of proven High Impact Practices; and generating data to enable evidence-based decision making, the policy, funding, and accountability environments in countries will improve, enabling greater and more equitable access to rights-based family planning.

Outcome 1.1: FP2030 successfully worked with 49 government commitment-makers to integrate high impact practices into family planning commitments. However, FP2030 did not receive sufficient data on countries’ family planning costed implementation plans and therefore could not report against the second part of this outcome. This is a major failing given what we know about commitment making. Countries are responsible for sharing their progress against their CIPs and the systematic tracking of this indicator was discontinued when the Global HIPs Secretariat significantly downsized and reduced their capacity.

Outcome 2.1: Since the start of FP2030, the partnership has successfully galvanized family planning commitments from 49 countries and 170 non-government actors, with all country commitments integrating 1 or more HIPs (thanks to advocacy and technical support from regional hubs, the global HIPs Secretariat, and other FP2030 partners). During this time, FP2030 also achieved 43 advocacy wins (at the regional, national, and subnational levels) that elevated the profile and prioritization of FP, mobilised financial resources, improved programs and policies, and enhanced government accountability on country commitments. Because of the ways in which FP2030 effects change—by elevating the visibility of FP and promoting its recognition as a ‘best buy’ for development, galvanizing political support and leadership in the form of public FP2030 commitments, convening partners to support development and implementation of an action plan for the country commitments, and ensuring accountability mechanisms are in place (including ongoing engagement by the regional hubs to monitor/review progress)—progress is measured through incremental changes, not just in policy and budget domains, but also in visibility (e.g., increased leadership or political will) and accountability. Examples of the broad range of achievements are below.

In line with the FP2030 theory of change, indicators of voluntary contraceptive use (such as contraceptive prevalence, number of users, and demand satisfied), access to a range of methods, and total financing for family planning all showed positive trends, demonstrating progress in the provision, funding, access, and use of FP.

In early 2023, FP2030 began a strategy refresh process to update the organisation strategy and theory of change in line with the new decentralised support network structure. The FP2030 strategy and TOC was shared and approved by the Governing Board in May 2024.

Example wins:
Policy achievements:
- In June 2024, Ministers of Health in the East, Central, and Southern Africa Health Community (ECSA-HC) adopted policy resolutions that integrate adolescent and youth sexual and reproductive health in emergency preparedness plans and knowledge management systems. The resolutions called for two major actions: 1) integrating adolescent and youth SRHR into national emergency preparedness and response plans to ensure service continuity during crises; and 2) establishing robust knowledge management systems to accelerate implementation of SRHR policies for young people. These resolutions were submitted jointly by FP2030, USAID-Knowledge Success, USAID-Kenya and East Africa Office, Partners for Population and Development-Africa Regional Office (PPD-ARO), ENNASSO, Nutrition International, and the ECSA Health Conference Secretariat. FP2030 advocated with partners and civil society to ensure recommendations were reflected in the final ministerial commitments. This signals a growing political will to include the needs of adolescents and youth in broader health and preparedness policies.
- Pakistan's Ministry of National Health Services, Regulations, and Coordination announced in January 2025 that the Government would revise its National Action Plan (2025–2030) to integrate family planning and reproductive health services at all levels of care. FP2030 contributed to reviewing the Council of Common Interest (CCI) recommendations in July 2023. FP2030 was a technical partner of the National Population Conference in July 2023 which led to the revision of the National Health and Population Policy. The Asia Pacific hub provided regular technical assistance to Pakistan through one-to-one calls focusing on advocacy, through regional focal points workshop and south-south learning workshops. This change represents a key step toward enhancing the health system's responsiveness and equity.
Budget achievements:
- In December 2024, the Federal Ministry of Health in Nigeria released $4 million from the 2024 fiscal year budget to UNFPA for the procurement of contraceptives. In partnership with local civil society organizations, FP2030's North, West and Central Africa Hub trained advocates on SMART Advocacy and helped establish a Task Team to develop a targeted advocacy strategy aimed at increasing government funding for contraceptives. To help make the case to the Government of Nigeria, FP2030 ensured that the voices of local civil society were amplified. This release of funding is a significant marker of progress in a context where delays and underfunding have historically undermined service delivery.
- FP2030 advocacy efforts contributed to the integration of High Impact Practices (HIPs) into the 2024-2028 Family Planning Costed Implementation Plan by the Disease Prevention and Control Bureau (DPCB) of the Department of Health (DOH) in the Philippines, backed by P873,000,000 (approximately US$ 15 million) in funding.
Accountability achievements:
- Advocacy efforts by FP2030’s Asia Pacific hub led to the introduction of the Motion Tracker in Kyrgyzstan, where the hub partnered with Indonesian focal points to provide training and guidance. The Motion Tracker mechanism creates a foundation for sustained engagement among partners in country.
- In October 2024, the Ghana Health Service officially launched its FP CIP 2024-2030, with technical support from FP2030’s North, West and Central Africa hub. Following the launch, the hub partnered with Pathfinder International to host a two-day workshop focused on clarifying stakeholder roles in CIP implementation, reinforcing ownership, and emphasizing the need for accountability. As a result, the FP CIP Task Team developed a set of accountability activities, which were formally integrated into its annual work plan, setting a clear path forward for implementation and monitoring.
Visibility achievements:
- FP2030’s advocacy resulted in Kenya’s Permanent Secretary for Health declaring himself a champion for family planning and committing to address program bottlenecks and improve FP services.
- In September 2024, Angola’s Minister of Health formally endorsed the country’s FP2030 Commitments, marking a significant step forward in strengthening family planning efforts. This milestone was achieved through sustained advocacy and collaboration led by FP2030’s East and Southern Africa hub, in partnership with USAID-Angola, UNFPA-Angola, and other key FP2030 representatives in Angola. Since 2021, the East and Southern Africa hub has been providing technical support to shape these commitments.

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title	Robust (quality, rights-based and evidence-informed) commitments mobilised with implementation through accountability accelerated at all levels.
Output Score	A
Impact weighting (%)	20%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
1.1 Number of commitments generated by country governments, donors, private sector, and other non-governmental stakeholders that support the services, financing, technical assistance, data, and advocacy and accountability needed for countries and other stakeholders to implement their commitments and achieve their commitment objectives.		210 (57 country, 18 donors and multilaterals, 135 other stakeholders)	190 commitment makers (52 country governments, 13 donor commitments, 125 other stakeholders)	Met / 219 commitment makers / (49 country governments, 5 donor, and 165 non-government actors)
1.2 Number of commitment-making countries making progress and on track or ahead of their policy, financing, and service delivery goals for contraception, method expansion, reaching specific populations and geographies, and other commitment objectives.		30 out of 52 countries (58%)	25 out of 45 countries (56%)	Met / 26 out of 42 countries (62%)
1.3 Percent of donor, civil society, private sector, and other commitment-makers who indicate through annual self-reports that they are making progress and are on track to achieve the goals in their FP2030 commitments.		110 out of 153	71% of NGA self-reports asked to be submitted	Moderately not met / 55% of non-Government Actors that were asked to submit a self-report did so and indicated progress towards achieving their FP2030 commitments. / 36 of the 60 NGA’s asked to report did so, making the response rate 65%. However, the majority (33 NGAs or 92%) of respondents reported making progress on their commitments.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
Output 1.1: FP2030 made better than expected progress on its target and steadily increased the number of FP2030 commitment makers, generating in total 219 commitments from country governments and non-governmental stakeholders. This includes 49 commitments from country governments (20 in the East and Southern Africa region, 18 in North, West and Central Africa, 10 in Asia Pacific, and 1 in Latin America and Caribbean). Forty-four (90%) of these countries are repeat commitment makers, and five (Botswana, Comoros, Fiji, Honduras, and Namibia) are first-time commitment makers., FP2030 also mobilised a total of 170 commitments from NGAs, 142 of which are still currently active and driving progress in 39 different countries. The Latin America and Caribbean region saw the greatest number of non-government commitments.

FP2030 fell somewhat shy of its target for donor commitments. The period since 2020 saw a number of donors’ budgets fluctuate, including the FCDO. This meant fewer donor commitments than predicted. However, given the challenges around ODA in 2025, it feels right to prioritise commitments from country governments and non-government actors.

Output 1.2: Of the 49 countries that made FP2030 commitments, 42 countries officially launched their commitments by the end of this programme period.

FP2030 requested 2023 self-reports from 24 countries that had at least 12 months to implement their commitments. Of the 24 requested, 18 (75%) commitment-making countries submitted self-reports. Thirteen countries (72% of the 18 respondents, or 54% of countries for which self-reports were requested) indicated that they are on track or ahead of their policy, financing, and service delivery goals for contraception, method expansion, reaching specific populations and geographies, and other commitment objectives.

In addition to the 13 countries reporting progress in their self-reports, another 13 commitment-making countries also documented progress based on regional hubs’ assessment from other sources outside of self-reports, such as quarterly review meetings and communication with focal points. Progress reported by government commitment makers included implementation of Adolescent-Youth friendly services at health facilities in Ethiopia, development of an electronic data collection tool to monitor FP consumption at the pharmacy level in Kenya, introduction of new methods (hormonal IUD and DMPA-SC) in Rwanda, and advancement of Post Partum Family Planning and hormonal IUD policies in Ghana, to name a few.

Note: Targets for indicator 1.2 were based on projections of the number of commitment makers at different time points, but it did not take into account the fact that the number of countries that would be asked to self-report in a given year depends on when the country made its commitment (whether their commitment has been in place for at least a year). As such, not all commitment makers would be asked to submit self-reports, and for those not completing self-reports, we have limited means of ascertaining their progress, given current resources.

Output 1.3: Of the 60 non-government commitment makers asked to submit self-reports, 36 or 60% responded and of those, 92% indicated they are making progress on their commitments. While the response rate was disappointing, it was good to see that good progress was being made in the responses FP2030 did receive.

Given the voluntary nature of self-reports, the low self-reporting rates were not completely surprising but it is concerning. Despite this, we know from government self-reports that civil society partners play a critical role in driving implementation of government family planning commitments, as well as tracking and validating data to monitor progress. While NGA commitment makers may not be submitting their own self-reports, many of them carry out their family planning commitments and actively engaging with governments in the country self-reporting process. FP2030 planned to conduct an in-depth analysis of NGA self-reports to better understand the impacts, opportunities, and challenges facing NGA commitment makers. However, the analysis was funded by USAID, and the termination of their award required that to be discontinued.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Tailored approaches and country alignment. Through initial country engagements, FP2030 learned that tailored messaging and approaches to garnering support for family planning was key. Sociodemographic differences across regions called for tailored messaging (and evidence) to ensure FP2030’s outreach resonated with country leaders and the priorities of their country. For example, mobilizing action to advance family planning in low-fertility settings (such as the Asia Pacific region) required a different script and different framing as to why family planning is vital. Understanding country priorities and positioning family planning within those policy frameworks helped facilitate country buy-in in commitment making and ensured family planning commitments were responsive to the unique needs and context of each country. The development of the regional hubs and support network was an important part of this approach.
Importance of relationship and partnership building. Establishing relationships and building rapport with government and non-governmental partners are cornerstone to our commitment making and self-reporting/accountability processes. FP2030 learned that cultivating relationships, engaging new country commitment makers, and providing consultative and technical support during the drafting and launching of the commitments are time- and resource-intensive activities. Especially for the more recently established regional hubs (LAC and AP), partnership building was crucial in laying down the foundation for future commitments and thus a key priority for the hubs.

- Challenges in self-reporting. Self-reports are an important mechanism for holding government commitment makers to account, however it can be a time-consuming, burdensome activity for government partners, as it requires them to gather inputs from a variety of stakeholders and (ideally) also consult and validate the data with civil society partners, which could delay or even prevent countries from self-reporting. An efficient way of completing self-reports is for governments, implementing partners, advocates, and other civil society partners to come together for a dedicated session/workshop to review progress, aggregate data, and validate the results. However, such convening can be difficult to coordinate and costly to organize. In the past, USAID-funded implementing partners often supported the self-reporting process. Now, in the post-USAID era, alternative sources of support for this would need to be identified. Additionally, there needs to be a stronger incentive for countries to self-report. Considering governments do not receive any direct funding from FP2030, and self-reports are purely voluntary, countries need to see a clear value in self-reporting (beyond demonstrating accountability). From regional hubs’ consultations with government partners, we know that governments want to see some form of feedback from the self-reports that would be useful to them, such as insights/learnings from other countries implementing similar interventions. Hence, to boost rates of government self-reporting, for the 2024 self-reports, FP2030 have revised the template to not only streamline and simplify the report but also enable them to facilitate south-to-south learning among countries that are self-reporting.
- Despite the challenges in self-reporting, they are crucial in determining whether countries have made progress against their commitment, and to show that the advocacy and accountability of FP2030 works. FP2030 should consider how to improv reporting rates even further.
- With the right resources and with the support of other partners, FP2030 could also centrally monitor progress against the commitments and provide an expert lens to determine whether reported progress fully integrates a right based approach and to use multiple data sources to establish progress on family planning commitments. FP2030 could also work with donor/partner country offices to align data where SRHR and family planning programmes exists, to establish progress against commitments. However, with a relatively lean secretariat and reduced funding, this currently might be too big an ask of them.

Output Number and Title	Increased use of data and evidence to advance FP2030 goals, including for planning, decision-making, advocacy and accountability and prioritization of HIPs with a focus on equity.
Output Score	A
Impact weighting (%)	15%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
2.1 Number of (cumulative) data/analytic products and FP2030 focal point workshops intentionally designed to integrate data use for prioritization, progress monitoring, and decision making		Number of instances of that family planning data are used annually by countries and partners to assess progress toward commitments and prioritization and implementation of HIPs / 18	10	Met / 52
2.2 Number of (cumulative) improvements in family planning metrics and measurement as a result of the efforts of FP2030 and the Performance Monitoring and Evidence Working Group		Number of improvements in family planning metrics and measurement as a result of the efforts of FP2030 and the Performance Monitoring and Evidence Working Group. / 20	10	Met / 10

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
Output 2.1: FP2030 show has shown good evidence of producing useful analytical and data products for use by governments and stakeholders. FP2030 generated a total of 52 communication/analytical products and workshops designed to integrate data use for prioritization, progress monitoring, and decision making. This includes 16 country analyses and post-partum family planning/post abortion family planning briefs, 19 private sector briefs, 1 publication on post-partum family planning, 1 publication on Emergency Contraceptive Pills in Pakistan, 7 regional workshops, and 8 documented examples of commitment-making countries using data-driven tools/mechanisms to monitor and review progress.

Country self-reports highlighted the use of tools such as the Motion Tracker, Track20 Family Planning Estimation Tool (FPET), data dashboards, and more in Benin, Burkina Faso, Guinea, Kenya, Madagascar, Tanzania, Togo, and Uganda. FP20320’s Data and Measurement team also launched an interactive data dashboard featuring data visualizations for the 20+ annually reported indicators for 85 low- and lower-middle-income countries and/or FP2030 commitment makers, to enhance data availability and utility for various audiences.

In addition to generating data and synthesizing evidence, other examples of FP2030’s work to strengthen data-driven decision making at the country level include:
- In the East and Southern Africa region, FP2030 began the practice of conducting Demographic Health Survey (DHS) deep dives whenever a new DHS is released. A deep dive on Mozambique’s 2022–2023 DHS, which was released during this reporting period yielded learnings on inadequate financing of family planning services which became the focus for a subsequent SMART Advocacy training.
- The Asia Pacific hub intentionally embedded Track20 in India’s focal point structure and fostered close collaboration between key national and regional stakeholders to help facilitate evidence-based decision making. During the last project year, Track20 and the Ministry of Health and Family Welfare gathered over 100 stakeholders (including donors, CSOs, and state representatives) for a two-day national consensus meeting in India to review FP2030 core indicators, with a focus on high-need states and scaling up FP services, particularly around the Mission Parivar Vikas, social and behavioural change activities, supply chain improvements, and adolescent health services.

Over the course of the grant, the original indicator was updated to first become a cumulative metric, and then further revised to “number of data/analytic products and FP2030 focal point workshops intentionally designed to integrate data use for prioritization, progress monitoring, and decision making”. This revision was intended to add specificity to better reflect the ways in which FP2030 contributes to increased use of data and evidence to advance family planning goals. FP2030 have indicated that they were able to deliver more than expected in part due to the increased demand and support for HIPs and HIPs-related data, as well as the amplification of this work at the regional and country levels following FP2030’s transition to a regional hub model. They have indicated that closer engagements with countries allowed regional hubs to better respond to their data needs.
However, exceeding milestone targets by such a high figure might suggest some weakness in our attempts to better balance ambition and fairness in the logframe in 2024. This should not detract from their achievements in this area and has not negatively impacted their score for this output.

Output 2.2: FP2030 met its target for improvements in family planning metrics and measurements.
Key data improvements and measurement advances over the grant period included:
- A review and update of three indicators reported on in the annual measurement report: (1) Family planning information, (2) discontinuation and switching contraceptive methods, and (3) source of method
- Improvement to the reporting of the family planning decision-making indicator. Previously, the indicator combined the percentage of women who decided to use family planning alone and those who decided jointly with their husbands/partners into a single category. Starting with FP2030’s 2023 data file, the indicator will now disaggregate this category so that FP2030 can gain better visibility into those women who report making the decision themselves.
- Formation of a working group dedicated to reassessing contraceptive measures with a reproductive justice perspective – the International Union for the Scientific Study of Population (IUSSP) Scientific panel, which held a series of webinars on the history of demand-side indicators and new ways to redefine demand
- New annual data on FP finance on FP2030’s newly launched interactive data dashboard. In 2023, FP2030 and Track20 published trends in domestic expenditures for all available countries for the first time. The data also provides an in-depth examination of different expenditure components that make up total domestic expenditures (e.g., personnel, capital costs, commodity procurement, etc.).
- New functionality on the FP2030 data dashboard allowing for regional data comparisons, new comparisons of countries within regions, and comparisons of A/Y data across multiple countries.
- Convening of experts to elevate historically underrepresented country voices, perspectives, and priorities for the Family Planning Measurement Advancement Convening Series (FP MACS), which held its first meeting in Nairobi, Kenya in June 2024 and brought together 48 participants representing 20+ countries across the four FP2030 regions.
- Recommendation to include a time dimension for the intent-to-use indicator in the next iteration of core DHS questionnaires
- Launch of the first Regional Data Observatory by FP2030’s LAC hub and Profamilia, featuring data on 13 family planning indicators from 17 LAC countries

FP2030’s Performance Monitoring and Evidence (PME) Working Group also remains active, with smaller task teams focused on different measurement issues/priorities (e.g., challenges related to post-partum family planning/post abortion family planning, FP finance tracking, and stockouts).

This indicator was initially amended to record data and metrics improvements cumulatively. In 2023, the final milestone target was also reviewed and reduced (from 20 to 10) to reflect the more detailed work that goes into developing new sector metrics over a relatively short period of time (3 year programme lifetime).

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
- From past workshops led by FP2030 regional hubs, we know there is a growing demand among health practitioners and program managers for practical, context-specific guidance. Workshop participants consistently emphasize the value of implementation case studies and structured learning exchanges to translate global guidance into actionable strategies at the country level. These formats enable peer-to-peer learning, foster the adaptation of HIPs to local realities, and build momentum for scaling. The success of the Nepal HIPs workshop demonstrated the effectiveness of action-oriented, locally relevant learning in bolstering country-level commitment. To support South-to-South learning where countries can share relevant evidence with others in similar contexts, we incorporated questions in the revision of FP2030’s country 2024 self-reporting template to help identify opportunities for cross-country learning as it relates to HIPs measurement and implementation science.
- In the past, FP2030 have also adapted the format of the PME Working Group meeting to enable smaller task teams that can delve deeper into their focus area/topic. These task teams welcome members from a broader measurement community that is not limited to existing working group members. For example, FP2030 used the PME Working Group to host larger group discussions on family planning measurement advancement, such as the FP MACS convening in Nairobi. Then in 2025 when USAID funding terminations brought upheaval to the family planning space, the PME Working Group was leveraged to convene key partners to re-strategize measurement advancement efforts in the new and still evolving post-USAID funding environment.

Output Number and Title	Stronger, more coordinated and integrated advocacy supports an enabling environment for achieving FP2030 goals.
Output Score	A
Impact weighting (%)	15%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
3.1 Instances of policy and/or program changes as a result of advocacy efforts of FP2030 and civil society partners, including integration of new HIPs into FP programs and health system interventions, adoption of new policies, or new or increased financing in support of expansion of HIPs.		30	Discontinued	Discontinued – this indicator was reviewed after the 2024 Annual Review and it was determined that it belonged more at an outcome level than output. 3.3 was instead added
3.2 Number of instances that FP2030’s advocacy efforts contributed to increased support for and implementation of improved FP policies and programs, including uptake of HIPs, by FP2030 commitment-makers		Evidence that FP2030 support network and regional hubs advocacy efforts contributed to increased support for and implementation of HIPs by FP2030 commitment-makers / 25	Discontinued	Discontinued – This indicator was determined to be more at the outcome level and therefore it was removed after outcome 2.1 was reworded to integrate this. The new indicator 3.4 below tries to bring out more, FP2030’s contribution to FP progress through advocacy.
3.3 Number of youth leaders supported by FP2030 to implement local advocacy and accountability activities		New to 2024	40	Met / 112
(New) 3.4 Number of global policy processes or platforms leveraged or created by FP2030 to advocate for prioritization and increased investment in SRHR/FP as a core part of a broader development agenda		New to 2024	6	Met / 14

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
Outputs 3.1 and 3.2 were discontinued. Reasons are given in the results box above but to summarise, these indicators were changed to specifically bring our FP2030’s contribution to youth empowerment and global advocacy – shifting the metric away from a focus on country achievements only, to showcasing FP2030’s value add. However it did mean it is hard to know the impact of these activities and whether they were the right activities.

Output 3.3: FP2030 supported 112 youth leaders to implement local advocacy and accountability activities, exceeding the logframe target. FP2030’s ongoing engagement with youth and investment in youth leadership in the SRHR space resulted in the following:
- Thirty-two youth focal points (YFP) from 11 commitment-making countries in the East and Southern Africa region and 10 countries in the North, West and Central Africa region developed AYSRHR advocacy objectives for their respective countries following FP2030’s dedicated SMART Advocacy training for YFPs in April 2024 in Ghana. Subsequently, the East and Southern Africa hub worked with the YFPs to create a combined regional advocacy agenda for AYSRHR.
- YFPs organized and engaged in a range of activities to socialize the new FP2030 Adolescent-Youth strategy throughout the 21 countries in North, West, and Central Africa. Activities included the development of national programs, health sector policies, strategies, and/or advocacy plans (Burundi, Côte d’Ivoire, Gambia, Mali); community mobilization and demonstration (CAR, Ghana); peer educator training (Liberia); school sensitization on comprehensive sexual education (Madagascar); in-person and digital SRHR campaigns (DRC, Ghana, Niger); media engagement (Benin); and the formation of technical working groups (Burkina Faso).
- FP2030 continued to curate and disseminate knowledge on AYSRHR and create intentional spaces for discussion of important AYSRHR matters and an exchange of knowledge. The North, West and Central Africa hub, for instance, co-hosted three AYSRHR-focused webinars: one that facilitated intergenerational discussion on the active roles of young people and governments in promoting SRHR in West and Central Africa; another on teenage pregnancies in Africa; and a third on contraceptive (dis)continuation among adolescent girls in Kenya and Nigeria.
- The Asia Pacific hub recruited eight YFPs who developed national work plans aligned with FP2030 commitments, emphasizing such issues as comprehensive sex education and adolescent pregnancy prevention.
- To bring out young voices and encourage the active participation of youth in the family planning movement, the Latin America and Caribbean regional hub held its first regional art contest on topics related to family planning alongside the launch of the Adolescent-Youth Strategy for LAC. At the same time, the hub further invested in strengthening the capacity of young people by bolstering their training in global mechanisms for tracking health and SRHR commitments and assembling a virtual advocacy school, which delivered weekly seminars to 26 adolescents and young people across 15 countries to prepare for their participation at the 5th Regional Conference on Population and Development in Colombia in July 2024.
Output 3.4: FP2030 met the target for this indicator by leveraging or creating 14 global policy processes or platforms to advocate for SRHR/FP investments and prioritization. Some key highlights include:
- 10-Year Review of the Addis Ababa Declaration on Population and Development, (AADPD@10 Review Meeting), Lusaka, Nov 2023. Through this event, youth were empowered with digital skills, ensuring internet access, addressing leadership underrepresentation, and promoting inclusive SRH services without stigma, especially for marginalized and conflict-affected populations.
- 7th Asian and Pacific Population Conference (APPC), Bangkok, Nov 2023. FP2030 co-hosted three side events and a high-level networking event, that facilitated cross-regional sharing among countries in the region facing similar challenges due to demographic shifts and examined the impacts of climate change, migration, and humanitarian crises on reproductive rights of vulnerable women.
- ICPD30 Global Dialogue on Demographic Diversity and Sustainable Development (hosted by the Governments of Bangladesh, Bulgaria and Japan, together with UNFPA), Dhaka, May 2024. The dialogue highlighted family planning amid population growth efforts and its rights-based implications. FP2030 Asia Pacific Hub will develop investment cases, collaborate with UNFPA, engage policymakers, and advocate for rights-based family planning in low-fertility settings.
- Climate Chaos, SRHR Crisis: Weaving a Web of Strength, Solutions and Solidarity during the Summit of the Future in New York, USA, Sept 2024. The side event highlighted youth networks' role in policy change, multilateral cooperation in SRHR and climate crises, and equity in governance. A Pakistani youth platform was established to unite and amplify young leaders' voices.
This new Indicator was added after Indicator 3.2 was discontinued in an effort to streamline similar/redundant indicators. Prior to that, the indicator was changed from the original indicator “evidence that FP2030 support network and regional hubs advocacy efforts contributed to increased support for and implementation of HIPs by FP2030 commitment makers”. In retrospective it was too low ambition so is scored as met not exceeded.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
- Again, whilst it is clear that FP2030 has prioritised youth engagement, and achieved a lot in this space, the logframe indicator should have been more ambitious to reflect the impact of the work FP2030 has been putting into this area over the last 3 years.
- FP2030 have become better at highlighting their contribution and value add to sector progress through advocacy and technical advice. Their engagement in these global processes show the value of their expertise by governments across the world.
Output Number and Title	Strengthened use of accountability tools to assess progress and meet FP2030 goals.
Output Score	A+
Impact weighting (%)	10%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
4.1 Number of countries implementing accountability plans and using accountability tools and mechanisms annually, including # of CSO led accountability efforts tracking country-commitment progress		35	25	Exceeded / 38
4.2 Percent of commitment-makers submitting self-reports		80% (countries); 70% NGA	70% (countries); 60% (NGAs)	Met / 71% (countries); / 63% ((NGAs)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
Output 4.1: With accountability well integrated in FP2030’s commitment-making and self-reporting processes, as well as its ongoing country engagement, a growing number (38) of countries are implementing accountability plans and using accountability tools and mechanisms annually. For many countries, an accountability mechanism is defined and embedded in their commitments from the outset. This can take the form of country self-reports, which is a collaborative process with civil society stakeholders to take stock of progress, or other accountability tools, such as Motion Tracker, The Common Framework (for budget accountability), scorecards, and dashboards. Key highlights on country accountability efforts include:
In 2024, FP2030 focused on establishing interministerial platforms in Malawi, Nigeria, Sierra Leone, and Tanzania as a strategic priority. These platforms aim to drive coordinated national efforts to advance family planning through comprehensive strategy development and resource mobilization and represent a critical step toward ultimately establishing a presidential task force in Africa.
- In July 2024, FP2030’s North, West and Central Africa regional hub launched a coordination and accountability mechanism for Central African countries under FP2030. Establishing a regional mechanism with regular communication, coordinated action plans, and shared resources will allow resource optimization, build accountability with structured progress tracking, promote youth engagement in decision making, and facilitate unified advocacy for policy reforms.
- In Ethiopia, FP2030 partner Consortium of Reproductive Health Associations led efforts to establish a media community of practice that fosters dialogue on the country’s FP2030 commitment and accountability, using the Motion Tracker.
- In Nigeria, the Association for the Advancement of Family Planning organized the FP2030 Stakeholders Accountability Meeting to discuss progress, challenges, and lessons learned in advancing family planning. AAFP is collaborating with other civil society organizations and government stakeholders to drive key recommendations from the meeting into action.
- The Health Development Initiative (HDI) in Rwanda took an innovative approach by training youth to engage in FP2030 accountability efforts. This initiative enabled young advocates to participate in key technical working meetings, where they effectively articulate priorities for adolescent and youth sexual and reproductive health and rights (AYSRHR).
In addition to the country-led accountability plans mentioned above, annual accountability processes were completed by FP2030 for 85 countries, including the release of annual family planning measurement data.
Output 4.2: Another key measure of accountability is the rate of self-reporting among FP2030 commitment makers, and that target was met for both government and non-governmental commitment makers. Each year, FP2030 asks commitment makers who have had their commitments in place for a year or more to submit self-reports on progress on their commitments in the year prior. Recognizing that commitment implementation takes time, self-reports were only requested of commitment makers who have had sufficient time to plan and implement their commitments. In 2023 when commitment makers were asked to self-report on their 2022 progress, 79% of governments and 60% of non-government actors that were asked to submit self-reports actually submitted reports. The following year (2024), self-reporting rates on 2023 progress were in a similar range (71% for governments and 63% for NGAs). Whilst self-reporting rates should be higher, it is positive to see countries who do report are making progress against their commitments.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
- FP2030 regional hubs acknowledged the difficulty in getting countries to submit self-reports. FP2030 focal points are collaborating partners whose primary role rests within separate organizations to FP2030. As such, competing priorities have limited their availability to support the self-reporting process.
- FP2030 revised its 2024 country self-report template to make it easier and less time-consuming to complete, eliminating non-essential questions that could be ascertained through other means and adding questions that could generate useful insights/learnings which would enable countries to learn from each other. FP2030 has acted on feedback received from NGA commitment makers, who expressed a desire for more opportunities to share best practices, lessons learned, and challenges. In response, FP2030 is incorporating additional opportunities in its 2024/25 work plan to include NGAs in webinars and events, while also highlighting their contributions on social media and in newsletters.
- Other note-worthy findings from the recent NGA self-reports are:
- Participation in regional discussions (such as ICPD30), and cross-regional exchanges (on faith and family planning, for instance) helped NGAs identify specific opportunities for advancing FP and facilitated the development of targeted advocacy objectives.
- There has been notable increase in collaboration between youth-led organizations and their civil society counterparts, providing a stronger platform for young people to participate in policy and program discussions.
Innovative approaches have emerged, with NGAs using podcasts and social media to showcase the benefits of engaging young people in improving family planning programming.
Lastly, with all four regional hubs now fully staffed, FP2030 has revised its approach to foster greater engagement with non-government commitment makers. Regional hubs are now tasked with building relationships with civil society, the private sector, and other nongovernment actors in their regions. Meanwhile, the global team manages NGA commitment makers in the North America and Europe region and synthesizes key themes, opportunities, and gaps from all NGA commitment makers. This enhanced engagement over the last project year resulted in an exponential growth in the number of new NGAs expressing interest in making FP2030 commitments FP2030 regional hubs are actively working to finalize and launch these commitments. This momentum will be built into the Made Possible by FP campaign, ensuring wider reach of the FP message and buy-in from both traditional and nontraditional constituencies.

Output Number and Title	An expanded, more inclusive and ever more visible rights-based family planning movement with a broad base of support.
Output Score	A+
Impact weighting (%)	20%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
5.1 Evidence of increased and meaningful youth engagement in the partnership, including youth commitments, youth participation in FP2030 governance bodies, and meaningful youth engagement in global, regional, and country decision-making	Number of examples indicating diversified participation in FP2030 governance (board, leadership, and staff) in-person and virtual convenings, non-governmental actor commitments, and participation in other communications platforms including social media, video, media stories, and other products. / 5	17 / Governing bodies: 4 / Youth commitments: 3 / Youth engagement: 10	Exceeded / 36 / Governing bodies: 4 / Youth commitments: 19 / Youth engagement: 13
5.2 Number of forums/meetings facilitated by FP2030 (through the DEG) for information sharing and coordination among donors	Number of wins indicating increased donor coordination and new donor participation in family planning through the FP2030 Donor Engagement Group’s platform for collaboration and new donor commitments. / 8	4	Met / 4
5.3 Number of new and non-traditional partners and champions indicating broader support for family planning	Number of wins indicating broader support for family planning from commitments, funding, public statements of support for FP in the media and communications platforms, and other forms of partnerships by new and non-traditional partners and champions. / 5 new/non-traditional partner commitments or partnerships, 5 public statements of support	10	Exceeded / 18

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
Output 5.1: FP2030 has made strong progress in increasing meaningful youth engagement in the partnership. FP2030 demonstrated 36 examples of youth playing an integral role in FP2030’s governance; commitment making; advocacy coalition building; and leadership within global, regional, and country decision-making platforms. FP2030’s ongoing engagement with youth and investment in youth leadership in the SRHR space has resulted in the following:
- Thirty-two youth focal points (YFPs) from 21 countries developed AYSRHR advocacy objectives after FP2030’s SMART Advocacy training in Ghana. The East and Southern Africa hub then collaborated with them to create a unified regional advocacy agenda for AYSRHR.
- The East and Southern Africa hub supported Adolescent-Youth advocacy in Zimbabwe, Uganda, and South Sudan through youth-led events on health, advocacy, and climate change. FP2030 also funded a Ugandan conference uniting youth-led organizations, including marginalized groups.
- YFPs promoted FP2030's Adolescent-Youth strategy across the North, West and Central Africa region through policy development, advocacy, community mobilization, peer training, school sensitization, SRHR campaigns, media engagement, and technical working groups to enhance youth-focused reproductive health initiatives.
- FP2030 helped lift youth voices by supporting youth representatives from India, Indonesia, and Nepal to voice their SRHR and climate justice perspectives at regional and global platforms, including the Asia-Pacific Forum on Sustainable Development and ICPD30 Global Youth Dialogue.
- To bring out young voices and encourage the active participation of youth in the family planning movement, the Latin America and the Caribbean (LAC) regional hub held its first regional art contest on topics related to family planning alongside the launch of the Adolescent-Youth Strategy for LAC.
- Amplification of the voices of youth leaders in regional meetings: in October 2023, FP2030 funded three youth focal points to participate in the North, West and Central Africa regional Interfaith workshop in Abidjan. This offered youth partners the opportunity to share their experiences with the key actors of the faith community in the region.
- Across the various regions, FP2030 took steps to ensure that new youth focal points joining the team come from least represented groups (youth with disability, youth living in non-urban settings.)
- During World Contraception Day 2023, FP2030 engaged three youth leaders from Asia/Africa to participate in a high panel discussion with senior executive members on the evolution of contraceptive methods for young people.
Output 5.2: FP2030 continues to fulfil its role as convener of the Donor Engagement Group, holding four quarterly meetings each year to facilitate information sharing and coordination among donors, in accordance with the DEG’s objectives. The DEG platform was used by donors to discuss potential and actual risks to FP funding based on political/administration changes in donor countries, monitor important signals or patterns in key family planning indicators at the global level, and coordinate on cross-donor priorities and opportunities (e.g., Made Possible campaign, UNGA).
Output 5.2: FP2030 exceeded its target to expand and diversify the family planning movement. This was achieved through FP2030’s deliberate efforts to resource and elevate local leadership to address local FP issues through the Partnership Fund and cross-sectoral outreach to rally support for FP integration and funding (e.g., climate, education, and finance). Beyond formal FP2030 commitments, there have been many statements of support for family planning through public platforms, with many coming from new or nontraditional partners in the family planning sector. For example:
1. Private sector: These 7 specific actions will help improve reproductive health – written by Chris Purdy, CEO of DKT International, and Dr. Samukeliso Dube, Executive Director of FP2030, published in Devex.
2. Women Deliver side event: Several speakers highlighted their public support for family planning at the FP2030 Women Deliver side event, notably including Diana Rodríguez Franco, Secretary of Women’s Affairs in Bogota, Colombia.
3. UN General Assembly 78: Several speakers highlighted their support – and the urgent need for action on – universal family planning. Most notably, Dr. Benjamin Djoudalbaye, from Africa CDC spoke about how FP2030 can position investments in family planning within the new public health order for Africa as a key tool for achieving the vision for the ‘Africa FP2030 Want.”

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Regional conferences, such as The Africa Health Agenda International Conference, Intercontinental Youth Summit on Climate Change, MENA Region Adolescents’ Wellness Conference, and the Asia Pacific Forum on Sustainable Development (APFSD), among others, have been valuable opportunities to not only elevate the prioritization of FP and engage high-level political leaders, but also to cultivate new partnerships and meaningfully engage youth in policy dialogue. These events opened doors for identifying new partners (such as youth-led organizations and initiatives), engaging new champions for family planning, and increasing the visibility of FP2030 and country commitments writ large. By hosting plenaries, side events, and speaker sessions, FP2030 can position family planning as a critical investment, fostering partnerships, advocacy, and increased political commitment in the region. FP2030 will also leverage these types of convenings to galvanize momentum for the Made Possible by Family Planning campaign.

Going forward, FP2030 plans to accelerate the implementation of its strategy to advance adolescent and youth sexual and reproductive health and rights through the promotion of high-impact service delivery models tailored to the needs of adolescents and youth, advocacy efforts to ensure Adolescent-Youth active participation in decision making, dissemination of disaggregated data to inform policy and programming, and forging alliance with youth movements. In response to the declining political buy-in for family planning, especially among adolescents and young people in Uganda, the East and Southern Africa hub has the opportunity to develop a collaboration with local faith-based partners to revitalize political support for youth family planning. Planned activities include developing targeted advocacy campaigns to engage policymakers and community leaders and fostering greater youth involvement in reproductive health initiatives.

Output Number and Title	Transition to the new governance structure and Support Network hub architecture to optimize FP2030's core functions for enhanced impact
Output Score	A
Impact weighting (%)	20%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
6.1 FP2030 Regional Hub Host organizations selected and contracted		5 Hub hosts selected and maintained	FP2030 Hub host organizations contracts maintained	FP2030 Hub host organizations contracts maintained
6.2 FP2030 Regional Hubs’ staffing plans finalized and recruitment underway		Regional hubs lead annual workplan development	FP2030 Regional Hubs recruitment and staffing plan operationalised	FP2030 Regional Hubs recruitment and staffing plans operationalised for all 4 regional hubs
6.3 Number of FP2030 Regional Hubs making progress on their annual work plans		FP2030 Regional Hub staff onboarding plans developed and implemented, including Hub staff onboarding to knowledge management platforms and workplan development / Regional hubs lead annual workplan development	4	4
6.4 Number of committees (including the Governing Board) meeting all of its mandated procedural objectives* each year		FP2030’s Governing Board and Governing Board Committees established and operational / 2 Board meetings per year; 1 Committee meeting per year (per committee)	4 total (1 Board and 3 committees)	4 (1 Board and 3 committees)
6.5 FP2030's restructure to a Global Technical Support and Strategy Office completed (merging the NAE Hub with the Executive Directorate team)		New to 2024	Restructure completed	Restructure completed
6.6 Number of new partnerships cultivated by Regional Hubs to advance FP2030 goals		New 2024	12	Met / 170 (121 from LAC hub, 18 from NWCA, 17 from AP, and 14 from East and Southern Africa,)
6.7 Number of internal systems improved or enhanced (e.g., financial management, project management, fundraising, etc.)		New 2024	6	Exceeded / 11 / 6 systems within regional hubs and 5 global systems improved

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]
FP2030 has successfully transitioned to its new governance structure and operationalised its new decentralised operating model and Support Network regional hub architect, meeting all targets under output 6. Five FP2030 regional hub host organizations were selected and contracted; FP2030 recruitment, staffing, and onboarding plans were operationalised for all four regional hubs; and all hubs have developed, implemented, and achieved progress on their annual workplans. FP2030 continue to learn, adapt, and evolve the decentralised model of the FP2030 Support Network.

As FP2030 progressed in its transition to a regional hub structure, their milestones also evolved. For instance, output indicators 6.3 and 6.4 shifted from measuring the development/establishment of regional hub staff onboarding plans, work plans, Governing Board, and Governing Board Committees to measuring their functionality and effectiveness (e.g., progress on work plans developed, Board and committees meeting their mandated objectives).

After meeting key transition milestones, FP2030 worked to optimise the operating model, which included restructuring the global team, empowering regional hubs to take on a bigger role in cultivating partnerships at the country and regional levels, and improving internal systems that would facilitate smoother cross-hub functions and collaborations (hence the addition of output indicators 6,5, 6.6, and 6.7, respectively).

The transition for FP2030 was challenging. It took longer than planned to contract new hub hosts and operationalise each regional office. Post –transition there were ongoing issues around the alignment of policies around human resource, and with staff turnover. That being said, FP2030 has managed many of these challenges associated with a significant upheaval of the organisations governance and operations. As they worked on their culture and learning, they were able to identify and overcome gaps, bottlenecks, and opportunities in their structure and processes. Over the past year, the Support Network has taken steps to optimize their structure for efficiency, allowing for acceleration of the strategy to lead to more impact, and importantly to deal with the financial challenges the sector and FP2030 face.

Operational excellence and efficiency
- The FP2030 Executive Director has provided suitable autonomy for decision making with regard to programme direction and budgeting, guided by the FP2030 Strategy and other agreed-upon priorities.
- The FP2030 Support Network has been intentional in promoting cross-hub coordination and joint activity implementation, and this has enhanced collaboration within the network. For instance, the North, West and Central Africa and East and Southern Africa hubs jointly conducted the SMART Advocacy training for youth focal points in Ghana to strengthen young leaders’ capacity in family planning advocacy.
- The FP2030 Support Network refined the country engagement portfolio and has now established monthly cross-hub coordination meetings, which are led by each individual hub every month. The meetings are strategic and focus on different areas identified by hubs.
- Through quarterly meetings with country focal points, the Asia Pacific hub has created a structured platform for tracking FP2030 commitments, sharing best practices, and addressing technical needs, ensuring that support is timely and relevant to each country’s context. This model has enabled the hub to swiftly address emerging challenges and provide tailored support that aligns with local priorities.
Indicator 6.4. Governance
- FP2030 held a productive in-person meeting in London in May 2024. Gathering in person allowed for robust discussions, problem solving, and brainstorming
- New members of the Governing Board have been announced at the end of 2024 and new Adolescent-Youth members are being onboarded.
Indicator 6.6. Partnerships cultivated by regional hubs
- Across the ESA, NWCA, AP, and LAC regions, FP2030 regional hubs cultivated over 100 partnerships. This was largely driven by the successful activation of civil society partners in the LAC region. As a new engagement region for FP2030, the LAC hub made deliberate and strategic efforts to connect with other stakeholders, build rapport, and forge new partnerships. Key initiatives contributing to the LAC hub’s exponential growth of partners included the LAC Partnership Fund, which sparked widespread interest and facilitated new engagements; regional contests targeting youth and adolescents; increased engagement at regional and global events; and the hub’s strong and diverse communication tactics. The LAC hub positioned itself in the region as a unifying agent by engaging diverse audiences and fostering new partnerships. Its vibrant social media presence, through social media campaigns, podcasts, and collaboration with other international campaigns and issue areas, certainly played a supporting role. In the ESA, NWCA, and AP regions (where FP2020 previously worked), after the establishment of regional hubs, hubs took on the role of facilitating and managing partner relationships (49 in total across the 3 regions), roughly 41% of which were new partnerships established by the regional hubs. With FP2030’s new regional hub model, we set a conservative target for indicator 6.6, which was added in the last year of the project, with the understanding that we would review the first year of data and adjust future targets accordingly. If FP2030’s grant were to continue, future trend data would help inform target setting for subsequent project years and enable us to make more accurate projections going forward.
- This indicator target was sadly significantly lower than the achieved score - (target 12, achieved 112). It has therefore been marked as ‘met’ rather than achieving given the discrepancy in target setting.
Indicator 6.7. Operations
FP2030 improved/enhanced 5 global systems (for MEL, Partnership Fund grants management, Partnership Fund proposal score cards, fundraising, project management) and 6 systems across the regional hubs.
On knowledge management, they've encountered technical challenges with operationalizing a network-wide KM platform (due to the 5 hubs having 5 different sets of IT systems and firewalls), and are currently re-assessing to optimize it this year. As they have grown their pool of funding, they have had to invest in both proposal and grant management capabilities.
- The Executive Directorate has built a calendar of key donor engagements. This includes all-funder reports, payment requests, deliverables, deep dives, and key touchpoints. This supports timely grant management as well as transparency with the full FP2030 team.
- They have instituted regular technical deep dives with FP2030 funders to provide an opportunity to learn more about our work, test our approach, ask questions, and provide feedback in real time.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
1. Cross-hub collaboration encouraged support, learning, and the sharing of best practices.
2. The efficiency of systems in the host hub was crucial for the success of hub operations. Amref has undergone changes in its HR department that were very necessary, especially for hosted entities, to provide more timely and effective support concerning staff recruitment, onboarding, evaluation, and the dissemination of relevant HR policies.
3. The hub’s decentralised approach has proven more responsive to local needs around advocacy and commitment making. A decentralised structure, while useful and nimble, also comes with layered costs as it loses the benefits of a centralized financial and reporting system. To maintain cohesive operations across FP2030, they are finding a greater need for coordination across the different regional hubs and functional units. A decentralised operating structure but centralized reporting system calls for a higher level of effort to centralize knowledge management, coordinate information gathering, aggregate and synthesize data, and generate learnings across the entire FP2030 portfolio and partnership.

FP2030 will continue to fine-tune, streamline, and standardize MEL data collection and reporting across the global support network in the year ahead. This includes more collaborative processes across functional teams and regional hubs during strategic planning, budgeting, and portfolio reviews, as well as joint implementation of select activities. Across regional hubs and technical teams, FP2030 will convene working groups focused on knowledge management, learning, and self-reporting. As more countries continue to make FP2030 commitments, sustaining engagement through the self-reporting process is critical to ensure ongoing progress and accountability. Recognizing that self-reports are completely voluntary and require much coordination to complete, FP2030 will work with countries to refine self-reports to increase its relevance and utility not just for global accountability monitoring, but also for governments and their work. By simplifying and tailoring to the needs of those contributing to and using self-reports, we hope to further increase rates of self-reporting among commitment makers in the future.
D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case
Family planning is one of the most cost-effective interventions and a development ‘best buy’. As the only partnership dedicated to family planning, FP2030 aims to play a direct catalytic role in advancing family planning goals at national and global levels, which in turn, is expected to translate to long term gains on rights based family planning access.

Economy: A core focus of FP2030’s growth over the past three years had been the establishment of consistent financial and administrative policies across all hubs. Each Hub Host institution is required to implement standardized salary bands and compensation policies for their FP2030 teams, with built-in mechanisms to ensure equity and fairness in pay. These policies have laid the foundation for harmonized financial practices across the decentralised structure. However it has been difficult.

For teams and consultants employed through UNF (covering the North America & Europe Hub and the Executive Directorate), compensation remains aligned with UNF’s established salary scales and consultant rate structures. In 2023, several consultancy contracts in this hub were extended to provide continued technical support and institutional knowledge transfer to new regional teams. These consultancy costs are expected to decrease in 2024 as responsibility shifts fully to Regional Hubs, in line with the localized, decentralised model.
FP2030 has embedded cost discipline and financial oversight into its governance model through a centralized, three-person Fiduciary team within the Executive Directorate. This team is responsible for ensuring robust financial management and compliance across all hubs. FCDO continues to play an active role in financial governance through its participation in the FP2030 Finance Committee, Governing Board, and other oversight structures.

However, FP2030 still faces challenges on collating and aligning financial reporting across the support network, through 5 regional hubs. They also have faced some difficulty in responding FCDO financial reporting in a timely manner, across the programme lifetime. This as partly been due to staff turnover.

Efficiencies:
FP2030’s transition to a decentralised support network has significantly improved operational efficiency by shifting programmatic leadership and implementation to Regional Hubs and in-country teams. This model ensures that programming is closer to the context, enabling faster decision-making, more relevant technical support, and stronger local ownership of outcomes. By empowering Regional Hubs to lead country engagement, manage partnerships, and support commitment-making and accountability efforts, the North America & Europe Hub—home to the Executive Directorate—has been able to realign its focus toward high-value, system-wide functions. These include oversight of core operations, impact reporting, and the development of FP2030’s global Monitoring, Evaluation, and Learning (MEL) strategy.

This structure has also enabled the North America-based teams to lead on cross-cutting priorities such as data and measurement, global advocacy, and strategic thought leadership. Centralizing these functions has created greater coherence across regions, while reducing duplication of effort and ensuring consistent alignment with the partnership’s global goals.

The decentralised model has led to efficiencies in operations – staff operating in the same time zones as counterparts, offices nearer to partner governments, and more opportunity for accurate regional insight and reporting. However, logistically it has also brought challenges including on aligning staff terms and conditions, it has increased management time spent operational issues like recruitment and retention, and the new structure is currently leading to high overhead expenses for the hub hosting structure.

Equity: FP2030 has been committed to ensuring that adolescents and youth are empowered to make informed decisions about their sexual and reproductive health, supported by a responsive and inclusive ecosystem that centres their needs and rights. Regional hubs have also been intentional about engaging and elevating voices of vulnerable/marginalized groups, like young people with disabilities, to ensure rights and equity are not left behind in our pursuit for greater SRH access. Through innovative service delivery models, data-driven approaches, policy advocacy, youth leadership, and strategic partnerships, FP2030 seeks to increase equity in reproductive autonomy, whether it is through delayed first births, reduction in unintended pregnancies and unmet need, or enhanced overall well-being of young people globally.

As part of this commitment, FP2030 launched an Adolescent and Youth Strategy, publicly outlining the priorities and principles guiding our work with and for young people. To date, they have secured 19 youth-led family planning commitments and established a Centre of Excellence for Adolescents and Youth to drive learning, innovation, and best practices across the partnership. Youth leadership is embedded in our governance: FP2030 has reserved two seats on the Governing Board for youth representatives, and over the lifetime of this award, a total of six young leaders have served in these roles, bringing critical perspectives to strategic decision-making.

FP2030 have made significant progress in youth involvement. They will need to show the impact of these efforts and ensure that their work more broadly on family planning has led to progress specifically on the ‘rights-based’ agenda. They can do this through more central analysis on the commitments and progress against them, partially through better self-reporting.

Effectiveness: With all five Regional Hubs now fully operational, the organization is advancing a coordinated Monitoring, Evaluation, and Learning (MEL) agenda. Each hub has a dedicated MEL counterpart, ensuring regional ownership of data collection, performance tracking, and learning. This decentralised MEL structure is supported by a new Director of MEL, who is leading the development of a comprehensive strategy to align metrics, strengthen institutional learning, and drive accountability across the entire partnership.

The reasoning for the regional transition is strong, and there is already evidence of better regional reporting and advocacy from the new operating model. Time will tell the impact on the rights based family planning agenda.

E: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]
There are a number of risks that FP2030 has successfully managed over the programme lifetime.
- The significant operational risks caused by an overhaul of their governance structures to become more decentralised. This required host arrangements for 5 regional hubs, onboarding new staff, harmonising systems, and building new local partnerships. Whilst this caused a lot of challenges around recruitment, retention and contracting, FP2030 have managed this risk to the best of their ability. However, it is possible that the need to work through a number of different regional hosts limits their agility as they pivot to meet the current context. It may also, in some contexts, offer opportunities.
- Secondly, as a country-led organisation dedicated to rights-based family planning, there has always been a risk around entrenching more traditional practices around family planning which aren’t completely rights based or inclusive. FP2030 have been an outspoken champion for SRHR and rights-based FP while pragmatically recognising that some countries, contexts and people will need to progress through different pathways that don’t immediate offer a full comprehensive package. However, FP2030 will need to continue to ensure that they do not lose focus on the rights-based approach even when taking a pragmatic approach and especially in the context of growing opposition.
- Finally, the biggest risk to FP2030 and their work has been financing. USAID’s demise has left a significant gap in FP and SRHR financing, and combined with reduction ODA from other donors (including the UK) and combined with a growing opposition to gender equality and SRHR, the risk to the sector is huge. FP2030 have also been directly affected financially, with the US pulling out and UK future funding uncertain.

Risk	Description	Risk	Mitigation Strategy	Likelihood	Impact	Residual Risk
C0	Global challenges, including pressures on the global economy, result in weakened political and financial commitment to FP at all levels and together limit/stop engagement with the FP2030 partnership.	Strategy & Context	In delivering its vision/mandate, FP2030 will advocate nationally and globally to ensure commitments to Family Planning are made and delivered. FP2030 will continue to leverage the influence, expertise, and relationships of its Champions, Governing Board members, and commitment makers. The new support network should improve regional presence and capacity to advocate on behalf of family planning investments. The US withdrawal from Aid and potentially other Donor's reductions in ODA will likely have severe impacts on the family planning sector. / Over the long term, FP2030 can support countries to recover from the sudden funding cuts from donors to help establish more sustainable SRHR financing systems.	Almost Certain	Major	Severe
C1	The rise of political/economic/climate instability in FP2030 countries limits capacity of governments to implement commitments.	Strategy & Context	The structure of the FP2030 Support Network itself is a critical mitigator of risks especially as it works to make commitments more robust, accountability more visible and measurable, partnerships stronger, and civil society and youth partners centrally positioned to support the implementation of commitments.	Likely	Moderate	Moderate
C13	FP2030 fails to ensure its efforts are grounded in rights and in reaching the poorest and those hardest to reach.	Strategy & Context	FP2030's strategy refresh process is grounded in rights-based FP. Implementation of FP2030's gender strategy will support more inclusive and gender transformative FP programming, grounded in rights. As a country led partnership, the growing pressures on gender equity and rights globally could directly impact appetite for rights-based family planning appetite at the country level.	Likely	Moderate	Moderate
C2	Failure to integrate within the global health and development agendas resulting from narrow FP remit.	Strategy & Context	The new more inclusive and country-owned FP2030 structure will enable increased support for FP and integration into wider movements and agendas. FP2030 also has a strong track record in making links with wider agendas and initiatives and intends to strengthen this further.	Unlikely	Minor	Minor
D14	FP2030's devolved operational structure makes it hard to work effectively and efficiently.	Policy & Programme Delivery	FP2030's Executive Director engages regularly with Hub managing directors and finance leads to stay on top of and respond to operational challenges. The new Monitoring and Evaluation Director has instigated a programme of operational delivery monitoring, and will work to share knowledge on efficient collaboration across the hubs and network. FP2030 will begin holding all staff meetings to ensure uniform delivery of the organisation's strategy and objectives. key challenges to watch include indirect costs from regional hub hosts (on top of UNF costs) and trying to manage uniformity of staff contracts across 5 different hub employment processes.	Possible	Moderate	Moderate
D15	FP2030's regionalization approach is fully implemented but does not have the desired impact on family planning progress	Policy & Programme Delivery	The FP2030 data team, the advocacy, accountability and partnership's team and the Regional Hubs will work closely together on monitoring of global and country progress in family planning and progress on achieving FP commitments to identify whether FP2030's efforts are helping to bend the curve over time. This will also be an area of ongoing attention for FP2030 Senior Leadership and the Governing Board's Program and Strategy Committee.	Unlikely	Major	Moderate
D3	Failure to secure a committed and sustained base of funders to fund the Support Network at or above its required core funding levels.	Policy & Programme Delivery	Mitigated through proactive resource mobilization work through the Finance & Audit Committee, Donor Engagement Group, and UNF's and FP2030's established relationships, as well as through the addition of a new Business Development position on the FP2030 team. The FP2030 continue to seek more investments to continue activities to 2030. The US exit from Aid, UK ODA reductions and the wider ODA challenges has made this risk more pronounced. FP2030 has begun a restructuring process to mitigate these significant challenges to funding.	Highly Likely	Moderate	Major
D4	Transition to new more complex decentralised model and governance structures cause operational delays/challenges	Policy & Programme Delivery	Clearly established decision-making bodies and lines of authority, proactive communication, and an ongoing commitment to adapt as the needs of the Support Network evolve should help to meet this challenge. Knowledge management tools, systems, resources, and procedures for effective information sharing are also under development. The Executive Directorate will work with regional hub staff to transfer ownership of work, knowledge, and skills, and build capacity across the support network.	Unlikely	Moderate	Minor
D5	Loss of knowledge and critical learnings accrued under FP2020.	Policy & Programme Delivery	FP2030's ongoing work to ensure inclusive processes, good governance procedures, and comprehensive documentation of lessons learned, and the ongoing work of the FP2030 team to ensure knowledge management systems are in place and that information is shared and relationships transferred successfully will mitigate this risk.	Unlikely	Minor	Minor
F10	Financial risk from weak hub host institutions.	Financial & Fiduciary	As fiduciary host, UNF developed and supports the implementation of financial best practices and rigorous internal controls across the Support Network, thereby centralising and standardising overall financial reporting to donors from all regional hubs. Hub hosts maintain overall responsibility over their finances but provide quarterly programmatic and financial reporting to FP2030 and UNF for accountability from the centre.	Unlikely	Moderate	Minor
F11	Procurement related risks.	Financial & Fiduciary	Each hub is responsible for its own procurement processes, which are reviewed at hub selection phase. The executive director monitors procurement issues at hubs to resolve them with the hub directors.	Unlikely	Minor	Minor
F9	Financial risk such as fraud, mismanagement of funds or poor value for money.	Financial & Fiduciary	Each hub is responsible for maintaining its own fiduciary and financial compliance under the processes of the host. FP2030 selected hub hosts which have strong financial rules and regulations. FP2030's Finance & Audit Committee monitors audits and any fraud or other concerns raised about FP2030 host entities or downstream partners.	Unlikely	Minor	Minor
P7	Staff turnover and risks in transition of knowledge/relationships.	People	FP2030 leadership team have maintained an ongoing focus on appropriately incentivising staff retention to maintain continuity of key relationships at the country, regional, and global levels during this period of transition, and allow current FP2030 staff to complete the handover process to new regional hub staff. In some cases, consultant support maintains knowledge and relationships until a full transition is complete.	Unlikely	Minor	Minor
R12	The UK receives criticism for funding a programme that advocates for FP but does not itself demonstrate/renew FP2030 commitment.	Reputational	The .UK has long been a champion for SRHR and committed to women and girls’ health agenda. / With ODA reductions from 0.5% GNI to 0.3%, there remains a risk that FCDO will not be able to commit to FP/SRHR to the same level it has done before, at least financially. / This being said, regardless of funding, we expect some level of policy and technical expertise on SRHR to continue.	likely	Moderate	Moderate
S8	FP2030 partners have insufficient safeguarding culture, policies and actions, which facilitates safeguarding breaches or fails to respond to incidents.	Safeguarding	FP2030 has selected Hub Hosts with strong internal controls and policies, and which have a track record of attention and care taken to safeguarding and related concerns. FP2030 staff adhere to UNF's policy and due diligence and monitoring of sub-grantees, including proactive engagement to embedding a culture focused on preventing and responding to safeguarding issues. In the event of any potential safeguarding issue the Finance & Audit Committee will be responsible for notifying donors swiftly and early on, as appropriate, so their investigative systems can be mobilized to support the investigation as well. Hub hosts have a duty to inform the FP2030 finance and audit committee, who will in turn inform FCDO of any safeguarding concerns. Hub policies on safeguarding are reviewed thoroughly before being awarded the host contract by FP2030.	Unlikely	Major	Moderate

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]
- FP2030 have delivered well against the programme results framework and complied with all FCDO requirements.
- The FP2030 have been approachable and supportive across the programme lifespan – FCDO and FP2030 met on a monthly basis to discuss programme delivery and wider coordination on the FP/SRHR agenda.
- FCDO and FP2030 worked each year to update the results framework for the programme, to ensure it captured FP2030’s contribution to the sector and ensure the right level of ambition.
- There were at times some challenges around financial reporting. This was largely due to staff turnover and the complicated nature of FCDO reporting requirements. However, FCDO always eventually received the reporting necessary. With the role of Finance Director and Chief of staff now filled, we expect these issue to improve.
- FP2030 has faced wider financial challenges with USAID dropping funding and other government donors being slow to – or not - renewing funding (including the UK). They are responding to these challenges in a measured way, adjusting operational structures and workplans.

Programme-level approach to monitoring and evaluation [1/2 page]
The programme has been monitored with regular (monthly) meetings between FCDO and FP2030 teams. In November 2023, the programme team also visited the East and South Africa Hub to understand how the transition had progressed to the regional structure.

FP2030 have updated their Monitoring and Evaluation processes over the 3 years.

During the first half of this grant, FP2030 was in the process of building its institutional MEL capacity, starting with the recruitment of a MEL Director, who started in the first quarter of 2024. At that point, FP2030 began piloting new systems and processes for collecting MEL data across the partnership and continue to iterate on them as we’ve had more opportunities for application, reflection, and learning. The vision for MEL, like FP2030’s overall decentralised operating model, was for it to be locally led and implemented, with support from the global technical support team. FP2030 aimed to strike a balance between providing key inputs for donors’ strategic monitoring and oversight and keeping a lean results framework so regional hubs and partners are not overly burdened with administrative reporting. In 2024, FP2030 harmonized their results framework indicators across our multiple donors, which helped us gain efficiencies in our donor reporting. Rolling out new MEL tools and processes completely virtually proved challenging however, as change management and a cultural shift to systematic documentation and learning typically require significant upfront investment in relationship and systems building – through field visits, regular partner meetings, review meetings, and beneficiary engagement. These were all planned activities in 2025 that were disrupted by the upending of USAID funding and the programmatic pivots that followed.

To continue refining their MEL approach and optimize internal processes, they have established an internal MEL/KM Council (with existing staff that have been designated the MEL focal point for their regional hub) to plan, coordinate, and operationalise MEL activities across the regional hubs and global portfolios. In the year ahead, FP2030 will map out the resource requirements to meet our learning needs and fulfil donor MEL obligations and develop a plan to better resource MEL across the partnership. Reflecting on their experience implementing MEL under FP2030’s new decentralised model over the past year will enable them to learn and adapt the MEL structure accordingly.

Date of last narrative financial report	May 14, 2025	Date of last audited annual statement	March 31, 2025