Title: Humanitarian Assistance and Resilience Programme (HARP)
Programme Value £ (full life): £191.9m		Review date: November 2025
Programme Code: 301362	AMP start date: 26/09/2022	AMP end date: / 30/09/2027

Summary of Programme Performance
Year	2022/23	2023/24	2024/25
Overall Output Score	A	A	A+
Risk Rating	Severe/Eager	Severe/Eager	Severe/Eager

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0001348.odt
DevTracker Link to Business Case Addendum:	https://iati.fcdo.gov.uk/iati_documents/D0006690.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006160.xlsx

List of Acronyms – see end

A. SUMMARY AND OVERVIEW

The Humanitarian Assistance and Resilience Programme (HARP) delivers the Foreign, Commonwealth and Development Office (FCDO) bilateral humanitarian support to Nigeria. With a total approved budget of £191.9 million running until September 2027, the programme aims to reduce mortality, alleviate suffering, and increase resilience among people facing the most severe humanitarian needs. The intervention focuses on three core pillars: food security, nutrition, and protection. It is delivered through a mixed portfolio of UN agencies, the Red Cross movement, and international Non-Governmental Organisations (NGOs) as well as the Nigeria Humanitarian Fund (NHF), a pooled funding mechanism. The programme provides life-saving assistance to civilians affected by conflict and displacement, particularly women and girls, while simultaneously supporting humanitarian access and maintaining a rapid response mechanism for sudden-onset emergencies.

Originally focused on the North East states of Borno, Adamawa, and Yobe (BAY States), where a decade-long non-international armed conflict continues to drive displacement, HARP secured a costed extension in 2025. This pivot expanded the programme’s geographical footprint to the North West states of Sokoto, Zamfara, and Katsina to respond to the escalating banditry and violence in the region. This expansion marks a strategic shift in the programme’s logic, moving beyond purely life-saving aid toward integrated resilience interventions designed to address chronic vulnerability and reduce the humanitarian caseload in alignment with the Nigeria Country Business Plan.

Since the last review, the operating context has deteriorated, driven by a convergence of conflict, economic instability, environmental shocks and funding uncertainty. In the North East, the crisis remains severe: the 2025 Humanitarian Needs and Response Plan (HRP) identified 7.8 million people in need of urgent assistance across the BAY states, a figure driven by protracted displacement and limited access to basic services. Civilians remain concentrated in garrison towns, facing persistent threats from non-state armed groups, including abductions and the proliferation of improvised explosive devices. Simultaneously, insecurity in the North West has become more challenging, with widespread banditry creating displacement outside the traditional HARP coverage area amid alarming malnutrition indicators.

Food insecurity has deepened across both regions. The Cadre Harmonisé (CH) analysis for the 2024 lean season (June–August) projected that 31.8 million people nationally were facing Crisis (Phase 3) or Emergency (Phase 4) food insecurity, with the situation in the North East and North West particularly critical due to limited humanitarian access and high food prices. This was compounded by severe macroeconomic instability. Data from the National Bureau of Statistics (NBS) indicates that headline inflation peaked at 34.19% in June 2024, with food price inflation exceeding 40%. This hyper-inflationary environment has significantly eroded the purchasing power of cash transfers and increased the cost of delivering aid. The poorest were impacted most by high fuel and food prices.

Environmental shocks further exacerbated these vulnerabilities, most notably the collapse of the Alau Dam outside Maiduguri in September 2024, which displaced over 400,000 individuals in Borno State and disrupted humanitarian supply chains. Recent national data underscores the depth of the health crisis; the 2024 Demographic and Health Survey (DHS) revealed a regression in key health indicators, with childhood vaccination rates declining and exclusive breastfeeding rates remaining critically low across northern Nigeria. Despite marginal progress in maternal health, access to basic services in conflict-affected areas continues to shrink.

The scale of violence has intensified in 2025, with at least 2,266 people killed by NSAGs in the first half of the year, a significant rise compared to around 1,083 fatalities during the same period in 2024 and already surpassing the 2,194 recorded over the whole of 2024 (ACAPS, 2025). Over 2000 GBV incidents were reported in the NE between Jan–Jun 2025, a 5% increase from 2024.

Against this backdrop, the broader funding landscape has constricted. The North East Humanitarian Needs and Response Plan (HNRP) remains significantly underfunded, and key donors have reduced allocations, forcing difficult prioritisation decisions. The UK has remained committed to principled humanitarian support in an increasingly volatile environment, worked with partners to achieve greater efficiencies to maximise impact for beneficiaries, increased funding where possible and expanded into the North West with a set of strategically focused interventions.

Summary supporting narrative for the overall score in this review

HARP has made significant progress this year and output-level results have been positive. The programme overall scores an A+, driven by excellent results in malnutrition services, both in treatment and prevention. Despite contextual challenges discussed above, partners have remained adaptable, reactive to challenges and persistent in providing support to the most vulnerable people across large areas of North East and North West Nigeria in often difficult circumstances. Programme management has been resourced at a sufficient level to manage a complex set of partnerships and proven agile and adaptable in responding to shocks and making best use of available UK resources.

Key results to date include:
- Treatment of 260,348 children under five for severe malnutrition, with a 98.6% cure rate
- Provision of lifesaving food assistance to more than 400,000 people
- Support to 26,352 vulnerable women with cash to support survival and nutrition
- Enabling of 7,729 aid worker journeys by air to reach their duty stations.

Some other important results are that HARP’s low-cost interventions being delivered to achieve high preventative impact has also helped in reaching 4.9 million children with vitamin A supplementation and reaching over 1.3 million people through OCHA’s humanitarian pooled fund mechanism.

Major lessons and recommendations for the year ahead

The final year of HARP delivery (to March 2027) should focus on consolidation, not reinvention. The programme’s core structure and focus on food insecurity, malnutrition and protection remains relevant and contributes to addressing humanitarian need in Nigeria. No major design changes are recommended but the programme should continue to advance ways of working which reduce needs and dependency, promote resilience and encourage sustainability. Cogent decision making and effective planning will be possible when HARP’s final year budget is confirmed.

FCDO should prioritise documenting lessons and building the evidence base to inform the next business case and future humanitarian and resilience programming in the context of a protracted crisis. This includes assessing the future potential of pooled funding, locally-led, and area-based approaches, and identifying where pivots may be needed considering the global humanitarian reset and ministerial priorities. Where possible these pivots should begin in the final year of HARP. Scoping work for future direction should be completed by Q2 of 2026 to inform design decisions and provide sufficient time for procurement of services for any successor programming.

Programme management for HARP itself should also shift towards closure planning. This includes ensuring appropriate financial close-out, clear documentation of results and lessons, and realistic transition planning with partners. FCDO should work with partners to agree exit strategies where applicable and ensure that any handover to government or other actors is feasible and clearly communicated.

Looking ahead, FCDO should collaborate with other donors and the Government of Nigeria to shape a successor programme that pivots to resilience, is locally led, and better aligned with state systems. This includes exploring all available options for joint funding and stronger links between humanitarian and development investments. Further data on developing strategies such as Anticipatory Action, increased work on cash, and the effectiveness of livelihoods programming should be obtained to ensure that future programming and strategy is realistic and has a strong evidence base. Research pieces on specific policy and delivery issues have been commissioned through both the Third Party Monitoring contract and the FCDO Nigeria PMEL programme. Core humanitarian response capacity should be maintained to enable delivery of lifesaving assistance in a challenging security context which has major impact on civilians and may deteriorate in future.

Specific recommendations against each output are detailed in section C and will be tracked and delivered in the final year of HARP.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The programme’s theory of change remains valid and centred on reducing humanitarian need in Nigeria by supporting timely, principled assistance and enabling a shift towards recovery. It assumes that sustained support to vulnerable populations, delivered through capable partners and coordinated with government, will improve access to essential services, reduce reliance on emergency aid, and strengthen local capacity. The programme also aims to support a more coherent approach across humanitarian and development actors, with a view to long-term solutions.

The Business Case Addendum, approved in January 2025 confirmed that the core logic of the programme remains effective but also recognised the need to adapt delivery in response to changing needs and funding constraints. The agreement by Ministers to expand the programme into North West Nigeria reflected a shift in scope, underpinned by evidence of rising needs and limited coverage in the North West.

The donor landscape shifted significantly in early 2025, with funding reductions and the ‘humanitarian reset’ affecting the prioritisation of humanitarian assistance in Nigeria. Impacts of these shifts will likely be felt into the last two years of HARP. At present, UK funding has been consistently at or near planned levels and the programme remains on track to meet its core objectives. However, the funding context now requires more active management of trade-offs and risks.

Overall progress against the theory of change is increasingly challenged by deepening food insecurity and rising rates of malnutrition, in both North East and North West Nigeria, given food price rises and other contextual drivers. These trends are driven by displacement, insecurity, and economic pressures, and are outpacing the scale of response making it challenging to discern progress in the face of rising pressures. This is likely to make it more challenging to reduce reliance on emergency aid or shift towards recovery in the most affected areas, particularly where farming livelihoods are limited or impossible to achieve safely.

Access also remains severely challenging. The programme assumed that humanitarian access would improve and that local actors would be able to take on greater delivery roles. In practice, access remains severely constrained in much of the North East with civilians in most need confined in large parts to garrison towns. Camp closures are being pursued by State governments, in some cases moving civilians out of the reach of humanitarians. Local capacity is uneven. The shift to the North West has exposed further gaps in coordination and delivery, particularly in the absence of a formal humanitarian architecture.

No changes have been made to the outcome or impact indicators that would require reapproval. The programme continues to track progress against its original objectives, with adjustments made through delivery rather than redesign. The final year of HARP should pursue the original Theory of Change given that humanitarian needs remain as high or higher than at design, and the short duration remaining in the programme.

Gender Equality, Disability, and Social Inclusion (GEDSI) has been systematically integrated across humanitarian programming under HARP. Interventions prioritised women’s leadership, inclusive decision-making, and protection services, while embedding disability-sensitive approaches in health, WASH, and livelihood activities. Women-led organisations and community structures were strengthened through capacity-building and financial inclusion initiatives, complemented by targeted GBV prevention and response, psychosocial support, and vocational training. Disability inclusion was advanced through assistive devices, accessible facilities, and tailored livelihood support. These efforts demonstrate progress toward equitable access and empowerment despite resource constraints.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme remains broadly on track to deliver its intended outputs, with some progress towards outcomes and has produced some impressive results. However, the link between outputs and longer-term impact is increasingly under pressure as drivers of need remain significantly unaddressed. Security and violence remain the dominant constraints for civilian resilience in the face of protracted crisis and humanitarian needs and numbers of displaced people remain high. Attacks by non-state armed groups in the North East and banditry in the North West continue to drive civilian harm and limit livelihoods opportunities. Farmers face extortion and violence, and humanitarian access is frequently delayed, movements cancelled or partners need to evacuate staff. Funding volatility reduced the overall humanitarian footprint and created uncertainty. The negative impacts of Nigeria’s economic reform on the poorest, including high food prices, continued to drive poor food insecurity and worsening malnutrition indicators.

National NGO capacity has improved significantly but remains uneven. Many now meet NHF eligibility criteria and deliver high-quality programming. Monitoring, audits, and reporting have strengthened governance and financial management. Some progress has been made on resilience programming and an increasing focus on prevention of need in recent months which will be more fully reported in the next annual review.

Beneficiary feedback mechanisms are in place and generally effective. However, recent assessments suggest some participants feel pressured to provide positive feedback, and marginalised groups face barriers to engagement. Workshops targeting people with disabilities and other excluded groups are helping to address this.

Planned actions for the year ahead include:
- Maintain life-saving assistance in food, nutrition, and protection, with continued focus on the most vulnerable in the North East and North West.
- Explore the feasibility of scaling locally-led resilience activities, including vocational training, dry season farming, and livelihoods support, to reduce reliance on traditional aid mechanisms and drive down the humanitarian caseload.
- Sustain protection programming, particularly for women and girls at heightened risk of violence.
- Retain flexibility to respond to spikes in need or deterioration in the humanitarian context.
- Document HARP’s lessons to inform successor programming, including options for hybrid humanitarian-resilience approaches, efficient cash delivery, locally-led models, and assessing system capacity for anticipatory action and early warning systems.
- Revise the existing log frame.
- Consult widely with government, beneficiaries and partners to design a successor programme to HARP
- Assess the practicality and evidence of using locally produced food to address moderate acute malnutrition, and work with food security and nutrition partners to consider how future UK support should be balanced across emergency and prevention approaches without compromising access to life-saving care.
The programme should continue. Humanitarian needs in Nigeria remain acute, with little sign of improvement given the nature of the protracted crisis caused by the non-international armed conflict. Malnutrition is widespread and deeply entrenched, and violence against civilians is persistent. The recent contraction in global humanitarian funding has already led to reduced coverage, and further cuts risk leaving large populations without support. A sudden end to UK funding would create a cliff edge, undermine progress and leave gaps that others are unlikely to fill. A successor programme will be needed to address this longer term and to maintain UK influence and delivery. HARP remains aligned with the UK’s humanitarian priorities and is well placed to adapt and pivot to new approaches. It can support locally led action, scale up cash and anticipatory action, and contribute to a more coherent and cost-effective response. The programme continues to represent good value for money given the difficult operating environment and remains central to FCDO’s goals in Nigeria.

## C. DETAILED OUTPUT SCORING

Output Title	The delivery of more predictable and impactful food assistance in NE Nigeria
Output number:		1	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of people receiving food assistance broken down by type of transfer	400,000	Overall output total: 482,178 (A+) / Total achieved (World Food Programme - WFP): 402,706 / 2024: WFP Overall reached 1,829,991 people with food assistance. FCDO contributed 6% of the total SO1 expenditure and a figure of 109,799 is therefore used for the FCDO attribution for indicator 1.1 in 2024. Combined with WFP results previously reported for the earlier years of HARP, this totals 402,706 FCDO’s support was 80% cash-based transfers (vouchers) and 20% in-kind. / Previous years’ total reported (WFP): 292,907 / Total Achieved (International Committee of the Red Cross - ICRC): 79,472 / In 2024, the ICRC reached 78,370 people with food assistance (FCDO contributed 7% of the appeal last year) FCDO has reached 5,486 in 2024 through its contribution. / Previous years’ totals reported (ICRC): 73,986
Percentage of people receiving CBT, including percentage of WFP CBT provided as MPCA	n/a	Not Scored - During 2024 WFP did not provide cash but only value vouchers (cash-based figures reported above)
Number of households reached by HARP covered by the government cash transfers (National Social Registry)	n/a	In line with the recommendation from the previous annual review, this indicator will no longer be tracked[1]
Number of women in selected households receiving gender-sensitive cash/voucher assistance	20,000	Overall total: 26,352 (A+) / Total achieved this year (UNICEF): 12,671 / Previous years’ total reported (UNICEF): 4,789 / Total achieved this year (CARE): 8003 / Previous years’ total reported (CARE): 889
[1] Following changes at the Ministry of Humanitarian Affairs last year including suspension of cash safety net programming and changes in personnel, it was no longer possible to track this indicator

Food assistance in North East Nigeria was delivered through a mix of in-kind distributions, cash transfers and vouchers, the majority in efficient cash-based transfers. WFP focused on reaching displaced people, returnees and host communities in crisis-affected areas. Targeting was based on vulnerability assessments and prioritised locations with the highest food insecurity. WFP used Cadre Harmonisé (food insecurity analysis) data and sector coordination to adjust its reach in line with overall available funding throughout the year. ICRC supported food consumption and income generation for conflict-affected communities. Activities included supplementary feeding, livestock vaccination, seed distribution and cash-for-work. These were aimed at meeting immediate needs and helping people recover, especially in areas hit by flooding and displacement. The Nigeria Humanitarian Fund also supported food assistance. NHF-funded projects included multi-purpose cash transfers and nutrition support, often delivered in coordination with CERF and in multisectoral projects. These helped fill gaps in priority areas and supported local delivery. Nearly half of NHF funding went to national NGOs.

Addressing food insecurity faced serious challenges as identified in the original business case. The lean season coincided with the negative impact of economic reform on the poorest through inflation, with market volatility and repeated shocks. Dangerous flooding in Borno damaged infrastructure and restricted access following a dam collapse. Insecurity continued to limit movement in parts of Borno and Yobe. Inflation and exchange rate reforms affected procurement and forced changes to food basket composition. Fuel costs and supply chain delays added further pressure. Despite constraints, the output remains on track. Partners adapted delivery models, scaled up emergency feeding and maintained operations in priority areas whilst downscaling in others. Challenges remain in providing people adequate support via vouchers in an inflationary environment, with transfer values being revised upwards several times in-year. Coordination through the Food Security Sector helped manage gaps. However, limited improvements in the overall food insecurity and malnutrition situation continue to undermine significant positive progress, particularly where displacement is entrenched and livelihoods are limited.

There were no changes to the output indicator during the year, but delivery was adapted in response to worsening conditions and a more constrained funding environment. In the overall food security sector, partners adjusted targeting to reflect updated Cadre Harmonisé analysis and reduced overall funding availability and prioritised LGAs with the highest food insecurity. WFP scaled up emergency feeding in flood-affected areas and adjusted transfer values to account for inflation, as well as conducting a verification exercise to ensure beneficiary lists were up to date. ICRC expanded its food and income support activities beyond planned levels. These changes were operational rather than strategic. As noted elsewhere in this report, the broader humanitarian funding landscape has shifted. This has increased uncertainty and programming timelines and reduced available funding and subsequent scale of response overall. Future targets will depend on funding availability and a full review of the logframe will need to take place.

Recommendations from the previous review for this output focused on indicator design, financial forecasting, procurement coordination, and alignment with national systems. Progress was uneven. WFP adapted delivery modalities and transfer values in response to inflation and funding volatility, and FCDO agreed new resilience programming in the northwest. Some support was provided to the National Cash and Voucher Policy. HARP indicator revisions and standardised forecasting procedures were not formally followed up due to lack of capacity and will be addressed as a priority as reflected in the recommendations and priority actions for the final year of HARP.

Key lessons for this output include the vulnerability of delivery to external policy shifts (such as a Government of Nigeria directive halting WFP’s local procurement which disrupted supply chains). Planning and forecasting across the sector were constrained by financial uncertainties and late budget confirmations, including from FCDO. The importance of predictable, multi-year funding was again highlighted (although not new in humanitarian contexts) and remains relevant for future resilience-focused work. Community engagement remained strong, and locally produced nutrition solutions showed promise but require further evidence.

Recommendation for output 1: Assess feasibility of utilisation of locally produced food to address Moderate Acute Malnutrition (Q3 2026) alongside a considered position developed in collaboration with food security partners on how to divide future UK support between emergency food assistance, nutrition and resilience work (Q1 2026).
Output Title	Improve nutrition outcomes in children, adolescents and women in Northeast Nigeria through a gender transformative, inclusive, multi-sectoral response
Output number:		2	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Monthly average number of children 0 to 59 months screened for acute malnutrition across the NE and number newly admitted at OTP/SC for SAM treatment -outpatient and inpatient (Gender disaggregated)	700,000 / 76,074	679,780 children were screened monthly (A) / 260,348* children were treated for severe acute malnutrition (A++) / *This is a cumulative figure
Proportion of severely malnourished children <5 years recovered, defaulted and died	Recovery rate: >75% / Default rate: <15% / Death rate: <5%	Recovery: 98.6% (up from 97.7 in previous report) / Default: 0.9% (down from 1.3% in previous report) / Death: 0.1% (down from 0.4% in previous report) / All score A+
Percentage of children being admitted at OTP/SC as self referral by caregivers/ mothers trained in MUAC screening	UNICEF: 40%	26% (B) (down from 33% in previous report)
Number of vulnerable people (including families with SAM children, adolescent girls and PLW) in communities and IDP camps gaining access to climate-resilient, gender- and disability-sensitive WASH services and supplies to ensure optimal dietary practices	UNICEF: 150,000	138,288 (B)
Number of HCFs (w/CMAM and/or OTP centres) in target areas provided with access to gender- and disability-sensitive WASH services	UNICEF: 25	49 (A++)

This output aims to improve nutrition for children, adolescents and women in North East Nigeria. Activities included screening, treatment, counselling, and support for better diets and hygiene. UNICEF remains a high performing partner and has met or exceeded most targets, most notably the number of children treated for severe acute malnutrition.

Between October 2022 and March 2025, partners screened an average of 692,287 children under five each month. A total of 260,348 children were treated for severe acute malnutrition, with recovery rates of 98.6 per cent and very low default and death rates. These figures suggest high programme quality, although data on relapse after treatment remain limited. Targets should have been more ambitious for treatment, but this figure represents a significant step up from the 51,000 treated as reported in last year’s annual review.

Preventive work also made significant progress. Nearly five million children received vitamin A, and over 278,000 pregnant and breastfeeding women received iron and folic acid. Nutrition supplements reached more than 200,000 children, and 267,917 caregivers were reached with advice on feeding and hygiene. 579,754 children have received a first dose of measles vaccine. Around 6,000 support groups were active. WASH services reached over 100,000 people, helping reduce illness and improve hygiene.

Most output targets were met or exceeded. However, malnutrition rose in Borno in 2024, as underlying drivers have either not improved or deteriorated, making it challenging to demonstrate impact at outcome level. UNICEF has also supported the training of over 300,000 caregivers to screen children for malnutrition at home, which contributed to early detection and timely referrals albeit at a lower rate than previously, highlighting how challenging it can be when long gaps between training of caregivers are experienced. The output remains on track, with strong delivery against targets despite operational constraints. The score reflects both the scale of delivery, above planned volumes, and the programme’s ability to adapt to shocks.

The output underwent several operational adjustments in response to rising caseloads, funding uncertainty, and a shift in delivery models. UNICEF scaled up stabilisation centre beds for the sickest children, highlighting the lifesaving nature of this output. UNICEF and the Government of Nigeria introduced simplified treatment protocols to manage increased patient numbers more efficiently within constrained resources. In the face of funding challenges, many partners reduced staffing and restructured. There was also a shift towards greater government ownership, with most outpatient treatment sites now run by state staff. Preventive programming expanded, including caregiver-led screening and support groups. No changes to targets or indicators are proposed at this stage, but milestone targets may be considered in the next review to reflect progress in government uptake and preventive coverage, particularly when broader sector capacities are taken into account and coverage assessed.

No specific recommendations were made in the previous annual review for this output. This year’s activities highlighted several practical lessons. Training mothers to check for signs of malnutrition at home helped more children get treatment early. Digital birth registration improved coverage and reduced delays. Deploying midwives to isolated communities strengthened maternal health services. Nutrition support worked best when combined with cash assistance and hygiene promotion. These lessons show the value of joined-up planning and locally-led delivery. FCDO should encourage UNICEF to continue to test and document the cost-effectiveness of simplified treatment protocols, expand links between health services and civil registration, and improve data systems to support faster adaptation when conditions change.

- Recommendation for output 2: FCDO should assess whether the current balance between treatment and prevention of malnutrition is appropriate and agree a clear strategy with UNICEF to ensure that prevention is scaled without undermining access to life-saving care. Q1 2026
- Recommendation for output 2: FCDO and UNICEF should explore rates of relapse of malnutrition in children leaving treatment and consider evidence-based programming to reduce the likelihood of children requiring repeated support. Q2-Q3 2026

Output Title	Protecting people from harm and strengthening humanitarian access.
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of individuals accessing awareness raising and community-based protection mechanisms in target LGAs	CARE: 80,000	Overall output total: 125,480 (A+) / Total achieved this year (CARE): 103,850 / Previous years’ total reported (CARE): 21,630
3.2 Number of women and girls targeted/reached with comprehensive GBV case management, psychosocial support, and referral for other specialized services including nutrition, legal, security and justice services and mechanisms (age disaggregated)	Total: 625 / CARE: 125 / OCHA: 300 / ICRC: 200	Overall output total: 6,722: 1190 (CARE) + 4,707 (NHF) + 825 (ICRC) (A+) / Total achieved this year (CARE): 1,022 / Previous years’ total reported (CARE): 168 / Total achieved this year (OCHA/NHF):2,497Previous years’ total reported (OCHA/NHF): 2,210 / OCHA: In 2024, the UK contributed US $3.2m (16.6%) of overall US$19.3m allocated that reached 15,045 people with GBV case management and specialised services, therefore FCDO attribution is 2,497 people. / Total achieved this year (ICRC): 209 / Previous years’ total reported (ICRC): 616 / In 2024, ICRC supported 4098 people with mental health support service, the UK contributed 7.1% to the ICRC budget therefore reached 209 people.
3.3 Number of individuals trained to support inclusive & safe protection services, awareness raising and drive social changes (paralegals, project staff, community structures, men and boys and health providers).	CARE: 690	Overall output total: 675 (A) / Total achieved this year: 220 / Previous years’ total reported: 455
3.4 Number of passenger journeys funded by FCDO and as a proportion of total journeys	5,500	Overall output total: 7,729 (A+) / From August 2024 to July 2025, UNHAS transported 24,338 passengers. The UK contributed 15% of UNHAS Nigeria’s total budget, therefore contributed to transporting 3,639 humanitarian actors. / Previous years’ total reported: 4,090
3.5 Number of organisations in NE Nigeria supported by INSO with safety coordination, training and advisory services	75	At least 114 organisations have been supported by INSO in the last year[2].
[2] INSO increased its reach to 114 organisations in this reporting year. However, due to registration and regulatory challenges was obliged to stop operations in May 2025. Discussions with the partner on viability of future operations remain ongoing.

This output focused on reducing protection risks for vulnerable populations and enabling humanitarian access in conflict-affected areas. Partners delivered a wide range of activities, including GBV case management, psychosocial support, legal aid, and community-based protection mechanisms. For this period under review, HARP reached 103,850 individuals with awareness-raising on GBV/SRH services including through community-based structures. 3,708 SGBV cases were successfully managed and supported with specialised services, significantly exceeding target. Women’s leadership was strengthened through 30 Women Lead in Emergencies groups, with 600 members actively promoting GBV and SRH awareness. Legal access improved through establishment of six gender desks in police stations, while community engagement was reinforced by safety audits and advocacy workshops.

The Nigeria Humanitarian Fund (NHF – country based pooled fund) enhanced protection for vulnerable groups in the BAY states amid conflict, floods, and displacement. It allocated $1.2 million for gender-based violence (GBV) prevention and response, supporting case management, psychosocial care, safety audits, dignity kits and livelihoods for survivors. Women-led organizations received funding and capacity-building to strengthen leadership, while vocational and economic programs helped women and girls recover. Disability inclusion was prioritized with $281,800 for assistive devices, adapted WASH facilities, and digital learning centres for women and girls with disabilities. Safe spaces and tailored skills training promoted independence and protection. NHF also mainstreamed protection across all projects and reinforced safeguards against sexual exploitation and abuse, affirming its commitment to dignity, equality, and resilience for women, girls, and persons with disabilities in crisis-affected communities.

FCDO support to UNHAS enabled humanitarian actors to maintain helicopter access to hard-to-reach areas in Northeast Nigeria despite insecurity and severe flooding. During this period, UNHAS extended no-cost cargo flights during emergencies, and revised cost recovery fees to ease humanitarian access to deep field locations. However, funding gaps and delayed contributions posed operational challenges, requiring intensified advocacy to sustain services and necessitating several changes to flight schedules in line with available resources. FCDO remained a member of the UNHAS steering committee.

No changes made to this output except the rising caseload as a result of the September flooding in Borno that resulted in mass displacement and exacerbated needs across some project locations, followed by funding cuts in the sector. During this review period, following the HARP BC amendment to include the NW, new AGA partners[3] were onboarded through a competitive commercial process for the protection and TPM activities, with an additional partner to carry out protection monitoring activities to complement and strengthen the HARP protection response. New partner activities will be reported in the next review period.
[3] Danish Refugee Council and Premiere Urgence Internationale

Recommendation for output 3: HARP should continue to monitor and support protection sector capacity and transition process as part of the humanitarian reset. FCDO should also continue to assess functionality of protection monitoring systems and GBV services, supporting where possible to ensure accurate and timely understanding of risks for women and other vulnerable groups and build local capacity for protection activities and position local actors to take lead in implementing protection activities in the last year of HARP.

Output Title	HARP cultivates a more localised response in NE Nigeria that is informed by learning and fully responsive to spikes in need
Output number:		4	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Proportion of annual HARP spend (including FCDO contribution to NHF) directed to local CSOs/NGOs	35%	Scored as A+ overall, with variances per partner as below: / NHF: 47% (previously 54%) - 53LNGOs (23 WLO) / CARE: 49.9% (previously 31%) - 2 LNGOs / UNICEF: 27% (previously (21%) - 4 LNGOs / Clear Global: 28.14% (previously 45%) - 1LNGO / WFP worked with 15 local NGOs during 2024
4.2 Number/frequency of independent Third-Party programme monitoring and verification visits undertaken	4	6 (2 Risk Monitoring + 3 LTV + 1 SPSS = 6 major verification exercises)
4.3 Number of partners reporting improvements in: a) programme design and delivery; b) adherence to best practise and c) fundraising as a direct result of Third Party Monitoring and verification visits		See narrative below for qualitative information for this indicator.

HARP continues to provide a more localised response informed by learning. Direct partners have increasingly provided implementation via local partners (at least 75 local partners this year), which has helped to provide capacity and increasingly move international partners to a supportive role. The proportion of spend for this review period ranges between 27% and 49% for selected partners as above. These partners surpass targets although more work is needed to assess multilateral partner trajectory. Whilst the proportion of NHF funding supporting local partners dropped slightly compared to 2023 results to 47% from 54%, the NHF did expend more effort to allocate specific envelopes for local partners focused on disability and Women Led Organisations.

HARP Third Party Monitoring (TPM) activities were fully launched during this period with 6 monitoring and verification visits carried out across programme locations. As a direct result of TPM and verification visits, all three implementing partners CARE, UNICEF, and WFP reported tangible improvements in programme design and delivery, adherence to best practices, and overall accountability. TPM findings informed adjustments to targeting and distribution schedules, strengthened risk mitigation strategies, and improved the accessibility and functionality of Complaints and Feedback Mechanisms (CFMs). Partners integrated gender sensitive and inclusive approaches, such as language translation and engagement of marginalized groups, following recommendations from AAP assessments and CFM workshops. While fundraising impact was not formally tracked, IPs indicated that TPM outputs such as risk matrices, dashboards, and AAP reports enhanced donor confidence and were referenced in proposals and strategic discussions, demonstrating the value of evidence-based monitoring in shaping more responsive and compliant humanitarian interventions.

No changes made to this output during the past year. However, there will need to be a review of the indicator and milestones for next year due to the change in partner and adjustment in activities under this output.
## D: VALUE FOR MONEY

In a context of hyper-inflation peaking at over 34% and a contraction in donor funding, FCDO funding provided stability and agility in an uncertain humanitarian environment. The programme’s approach to economy ranged from cost-containment to market management. To counter the erosion of purchasing power caused by Naira depreciation, FCDO encouraged partners to prioritise local procurement. CARE and NHF-funded projects sourced hygiene kits, food items and medical supplies from nearby markets, reducing transport costs and supporting local economies.

FCDO also leveraged its CDEL investments through the BRINNS programme to stockpile locally manufactured commodities, particularly Ready-to-Use Therapeutic Food (RUTF), cutting transport costs. Cash-Based Transfers (CBT) formed a significant share of the portfolio, representing more than 70% of food assistance and an increasing proportion of nutrition top-up support for caregivers of children under two and of GBV programming. Despite inflationary pressure requiring frequent upward revisions of the Minimum Expenditure Basket (MEB), the programme maintained this pro-cash posture with UK funding.

Efficiency was driven by consolidation of the delivery architecture. The Nigeria Humanitarian Fund (NHF) moved away from fragmented allocation models, streamlining funding to fewer partners with stricter geographical targeting. This reduced administrative friction and duplication, ensuring resources focused on delivery rather than overheads. Data was used as a driver of efficiency: Third-Party Monitoring (TPM) was integrated upstream, using pre-survey assessments and real-time data cleaning to catch targeting errors before resources were committed. Logistics were optimised through shared services and continued support to enabling services such as UNHAS. Solarisation of deep-field humanitarian hubs through CDEL reduced running costs and contributed to a 27% reduction in annual operational costs in 2025 compared to the previous year. Efficiency was also supported by a growing focus on prevention of malnutrition, a cheaper intervention than treatment.

Effectiveness was demonstrated by adaptability and reach. The programme consistently met logframe targets, achieving 100% of measured outputs and reaching over 1.3 million people through NHF interventions alone. Low-cost interventions with high preventative impact included reaching 4.9 million children with vitamin A and providing 579,754 measles vaccinations since inception. The programme also pivoted to respond to sudden-onset emergencies such as the Alau Dam collapse, displacement and acute watery diarrhoea outbreaks, demonstrating strong operational agility. Delivery continued even in inaccessible garrison towns, supported by continuous beneficiary feedback loops verified by TPM to ensure relevance.

Equity was embedded as a sustainability strategy and an early pivot toward the humanitarian reset. The programme advanced localisation by supporting NHF’s Country-Based Pooled Fund to allocate 47% of its annual funding to local actors, exceeding Grand Bargain targets. UNICEF ensured that 58% of its downstream delivery partners were local NGOs, including three women-led organisations. All protection work in Adamawa and Yobe States was delivered by local actors such as EYN and Neem Foundation, together accounting for more than 40% of protection grant expenditure. WFP also strengthened localisation by partnering with 15 local NGOs and 14 international NGOs. Inclusion of women and persons with disabilities was implemented through protection partners who ensured representation in decision-making spaces. Nutrition feedback showed 55.3% from women and adolescent girls and 1.7% from people with disabilities. WFP assessed and prioritised persons with disabilities for food assistance.

Women and children remained the major focus of HARP. People with disabilities were prioritised, with all physical infrastructure supported by the programme designed to be disability-friendly. TPM conducted PWD-focused AAP sessions to ensure that FCDO prioritised the voices of the most vulnerable.

As funding for the humanitarian response in Nigeria continues to decline into 2026, enabling services such as security, humanitarian hubs and helicopter access will face increased scrutiny. These services are costly but essential. The areas with the greatest humanitarian need are often the hardest to reach. Enabling services are not a luxury; they are a prerequisite for delivering assistance to those most at risk. Difficult financing decisions will be required, but any assessment of value for money must reflect the shift toward high-risk, high-cost locations. Reducing or removing enabling services could prevent partners from reaching the most vulnerable. These services should be viewed as necessary investments, not optional overheads.

E: RISK

HARP maintained an Eager risk appetite for Strategy and Delivery, a necessary posture to sustain life-saving operations within the volatile security theatres of the North East and the emerging frontiers of the North West. This was balanced against a Cautious appetite for Financial and Fiduciary risks. The operating environment was dominated by triple pressures: kinetic insecurity from armed group activity and government countermeasures restricting access, bureaucratic impediments and severe macroeconomic instability where inflation and currency volatility actively impacted programme value and planning. Despite these deteriorating external conditions, the residual fiduciary risk remains within the Cautious appetite, a stability driven by the introduction of closer financial oversight through regular partner check-ins, the amendment of reporting templates to enforce transparency in downstream partnerships and enhanced Third-Party Monitoring (TPM) protocols that are already yielding results in newer partnerships outside this reporting period.

The strategic expansion to the North West has shifted HARP’s risk profile. Unlike the North East, this region lacks a formal humanitarian coordination architecture, necessitating a heavy reliance on local partner capacity which carries inherent delivery risks. We are mitigating this through a ‘localisation first’ approach, anchored by prioritising partnerships with local NGOs, integrated nutrition and protection programming, rigorous capacity building and scenario planning for shocks, including flooding.

Safeguarding risks persisted, driven by power imbalances and harmful coping strategies. We held a Receptive appetite here to proactively encourage transparency, countering power imbalances through strengthened partner policies, survivor-centred reporting mechanisms and regular/periodic SEAH training. Gender equality assumptions in the business case remain valid; monitoring through TPM and partner reporting shows no material negative impact, though women and girls remain disproportionately vulnerable. As overall humanitarian support declines, reports of negative coping mechanisms including transactional sex have been growing, a contextual risk that is likely to increase.

Assurance testing during the period provided clear evidence that these controls are functioning effectively to identify and neutralise threats. For instance, a targeted audit spot-check by the programme’s audit partner, PKF, identified instances of fund co-mingling by downstream local partners; this detection allowed the programme team to intervene immediately, strengthening partner systems to maintain distinct funding lines and preventing future loss. Similarly, TPM mechanisms proved their worth by identifying isolated instances where beneficiaries were being tasked by local leaders to remit a portion of cash received under protection activities. Rather than treating this as a systemic failure, the programme used the signal to trigger an immediate deepening of community engagement and legitimacy work, successfully building broad-based accountability within the cash transfer process to halt the practice in implementation locations.

Due diligence assessments were initiated and refreshed where required, and progress on recommendations has reduced residual risk FCDO holds with most partners. Annual audits and TPM monitoring visits provided assurance on fiduciary controls, though aid diversion and fraud remain inherent risks in cash and commodity distribution. These systems successfully identified isolated issues without revealing systemic failures. Broader assurance is evidenced by the successful closure of major audit findings, including the resolution of spot-check issues that allowed for the lifting of a short-term partner suspension during the period. The team has also been actively collaborating with UN partners on addressing key audit findings including with WFP to develop a country risk appetite statement and risk register focused on cash-based transfers and with UNICEF on tackling the theft of nutrition supplies in government-managed storage facilities identified by TPM and the audit finding on deepening the capacity of UNICEF staff and partners on SEAH and strengthening UNICEF's fraud risk assessment.

Equality and safeguarding indicators were monitored through partner reporting and TPM, with no evidence of adverse impacts on protected groups. Flexible funding and scenario planning are in place to respond to shocks such as flooding or disease outbreaks, supported by integrated Health-WASH-Nutrition programming.

The programme largely delivered within appetite, though pressure points in access, safeguarding, and financial oversight require continued mitigation. Risk registers and AMP have been updated, and escalation protocols remain active. No change to overall appetite is proposed, but vigilance is required on fiduciary and safeguarding risks as localisation deepens and amid overall funding uncertainty. To mitigate these emergent risks, the programme has introduced additional control layers, including funding ecosystem capacity building through PLRCAP and broadening research to build on evidence-based local models using both the TPM research component and the office’s PMEL programme. Importantly, FCDO has instituted a protocol to engage directly with local downstream partners to verify that capacity strengthening actions agreed in the Due Diligence Assessments of direct partners are effectively cascading down to the frontline, and ensuring they participate in partner capacity sessions. To counter SEAH risks in these new operational areas, the programme has supported the appointment of specific SEAH focal points in all downstream partner offices and is currently refreshing the safeguarding programme deep-dive to explicitly include local partners in its scope.

HARP’s risk management approach remains robust and adaptive, ensuring alignment with FCDO standards while responding to evolving humanitarian needs. Continued investment in partner capacity, safeguarding systems, and flexible funding will be critical to maintaining delivery within appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Most partnerships from the previous year were maintained. Key changes included the closure of two grants with CARE and CLEAR Global in March 2025 and the selection of new protection partners[4], the expansion of FCDO’s partnership with WFP and UNICEF to new projects focused on resilience in the North West and the shift towards fully implementing the new WFP-FCDO framework arrangement.
[4] Danish Refugee Council and Premiere Urgence Internationale

The period under review was characterised by a significant divergence in partner performance, marked by high-quality delivery from multilateral partners in contrast with some operational and fiduciary challenges within the Accountable Grant agreements, including on rates of programme spend and speed of implementation. The latter was partly caused by decisions to onboard new partners as mentioned above. Regulatory and registration challenges experienced by INSO in the later part of the reporting period increased operational risk for INGO partners due to the loss of security advice and training, which is likely to impact risk management in future. However, their previous reporting framework had provided a clear and detailed view of operations across Nigeria, which was valuable for informing FCDO’s overall risk appetite and planning. This level of insight is now missing and will be difficult to replace. While no standalone partner capacity building sessions were held in this period, regular review meetings with partners were useful to share useful information to strengthen partner delivery and FCDO expectations on risk and safeguarding.

Overall, HARP witnessed a substantial improvement in both the quality and timeliness of partner reporting as the programme matured. UNICEF demonstrated high performance in this regard, consistently submitting timely reports that met and often exceeded high internal quality standards. The reporting provided by other UN and multilateral agencies did not require bespoke templates but remained timely and of high quality. These annual reports provided clear, robust evidence of strong performance across their agreements, allowing the programme team to maintain effective oversight of large-scale humanitarian deliverables. All partners remained willing and available for frequent discussions on context and the operating environment with staff across the High Commission in Abuja within the existing humanitarian architecture, alongside other donors and bilaterally which helped to triangulate information and monitor performance.

Reporting performance among grant-funded partners was more mixed. While reporting timeliness improved, some submissions lacked sufficient analysis, particularly on Value for Money, gender equality and in drawing clear conclusions about the impact of activities on programme outcomes. In one case, internal governance issues within consortium structures affected cohesion and reporting quality, leading to early closure of projects and onboarding of new monitoring partners. External shocks such as flooding and loss of hosting privileges disrupted delivery and required rapid realignment of resources. These challenges highlighted the need for stronger contingency planning and clearer communication of approval processes to avoid administrative friction.

Financial oversight was strengthened through rigorous independent audits and spot checks, the results of which demonstrated that the controls in place are effective in identifying and addressing risks (examples below). Managing these processes required sustained engagement from the programme team, including detailed follow-up with partners to resolve issues. This level of interaction reflects the complexity of the portfolio and the amount of management effort required.

Some audits revealed serious weaknesses in financial controls. A whistleblower report triggered a spot check on one partner, which uncovered poor tax compliance, weak accounting for staff costs, and commingling of donor funds. These findings led to a two-month suspension while a rectification plan was implemented. FCDO worked closely with the partner to strengthen controls and staff capacity before lifting the suspension. Cash-based interventions also faced risks. Third-party monitoring flagged problems with one cash distribution activity, including failures in beneficiary verification and confirmed cases of aid diversion. These risks prompted suspension of cash activities while verification protocols, staff training and community engagement were improved. No other notable fraud cases were reported during the period although the operating environment remained challenging.

Broader financial management varied. Some NGO partners maintained low variances between forecasts and actual spend, despite the issues noted above. Quality of other spending forecasts and reporting was distinctly poorer, with persistent underspend and delays in reporting. Optimism bias in forecasting and abrupt changes to project components, such as the closure of PLRCAP[5] and flooding in Maiduguri, created further misalignment. For one partner, delays in submitting final financial reports led to overbudgeting for closure activities, with some costs later ruled ineligible as appropriate permissions were not granted ahead of spend. Despite these challenges, asset management remained strong. The asset registers for active partners were regularly reviewed and verified through audit.
[5] A capacity building project for local partners

In the next reporting period, FCDO is aiming to improve its effectiveness by documenting partner meetings more systematically and sharing insights across teams to enhance coherence and learning. Insights provided by independent auditors PKF provided valuable insight and clear recommendations for corrective actions and such external support should be retained in future programming.

By March 2026, the HARP Programme had spent a total of £100.9m of its £150m envelope (expanded to £191.9m by the 2-year cost extension), with £33.45m spent just within the FY 24/25 across partners as follows:

Component Code	Delivery Partner	Programming delivered/location	Funding spent
301362-102	The World Food Programme (WFP)	Food assistance – Borno, Adamawa and Yobe States	£7,862,500.00
301362-103	The United Nations Children's Fund (UNICEF)	Multisectoral, Integrated Nutrition – Borno & Yobe States	£12,000,000.00
301362-104	The International Committee of the Red Cross (ICRC)	Multisectoral Humanitarian Assistance - Borno, Adamawa and Yobe States	£3,506,811.72
301362-105	The United Nations Humanitarian Air Service (UNHAS)	Humanitarian Air Service – FCT, Borno and Adamawa States	£3,487,500.00
301362-106	International NGO Safety Organisation (INSO)	Humanitarian Access and Aid Worker Safety – Borno, Adamawa, Yobe, Katsina, Zamfara and Sokoto States	£430,404.00
301362-107	The United Nations Office for the Coordination of Humanitarian Affairs (OCHA)	Multisectoral Humanitarian Assistance through the NHF - Borno, Adamawa and Yobe States	£3,000,000.00
301362-108	CARE International	GBV Prevention/Protection - Borno, Adamawa and Yobe States	£1,998,573.36
301362-109	Clear Global	Third Party Monitoring - Borno, Adamawa and Yobe States	£1,056,843.00
301362-110	HSOT -Palladium	Cash TA - FCT	£107,367.92
301362-401	PKF International Audit Services Limited	Audit Services - Borno, Adamawa and Yobe States	Post-payment

Commercial Performance, Compliance, and Strategic Alignment

The HSOT[6] contract was used to maintain the Cash-focused Humanitarian Adviser role until November 2024. Beyond this, activity was limited, but the contract remains central to future plans. In line with the Humanitarian Reset, the programme intends to use HSOT to deploy a Humanitarian Reset Coordinator to support OCHA, ensuring commercial assets contribute to system-wide changes.
[6] Humanitarian and Stabilisation Operations Team

The programme was audited by FCDO Internal Audit and Investigations in late 2024. Controls and partnerships were assessed as adequate, with recommendations on the Value for Money framework and risk register consolidation. These have been implemented, supported by a Risk Clinic and a revised Risk Appetite Statement.

Partners complied with the Gender Equality Duty, delivering targeted programming on gender-based violence and food and cash assistance. Women were visible in implementation roles, and partnerships with women-led organisations were prioritised. Internal governance stabilised during the period. Senior roles were fully staffed, and compliance training completed. Some administrative changes occurred, but leadership remained consistent. The transition of IATI reporting to the Aid Management Platform created a learning curve but improved transparency compliance.

The programme secured a costed extension to September 2027, increasing the budget from £150 million to £191.9 million and expanding coverage to North West states. By the end of 2024/25, spend reached £100.9 million, meeting HARP’s ODA target.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

FCDO teams were able to visit North East Nigeria on multiple occasions in the last year. Visits for programme monitoring are constrained by security management requirements but allow occasional face-to-face discussions with partners and beneficiaries. Partners were generally able to provide monitoring with separate teams of their own activities and those of sub-partners in the delivery chain.

Third-party monitoring was delivered through a consortium using both qualitative and quantitative methods. Risk monitoring and light-touch verification exercises were conducted in Borno and Yobe, involving focus group discussions and structured surveys with beneficiaries. These assessments highlighted issues such as overcrowding at distribution sites, delays in aid delivery, and household tensions. Findings informed changes to distribution planning, logistics, and community sensitisation.

The NHF exceeded its monitoring targets, conducting 103% of planned project monitoring and 113% of financial spot checks. External audits covered 81 NGO projects, with 83% showing no major findings. However, some national NGOs reported non-compliance and internal control weaknesses, which are being addressed through follow-up and capacity-building. Beneficiary feedback was actively collected through help desks, hotlines and community meetings.

No programme-wide formal evaluation was conducted during the review period but monitoring and surveillance activities provided sufficient evidence to assess performance.

Evidence

Several major assessments informed programming decisions during the year. Recently published reporting from the Cadre Harmonisé food insecurity analysis projected that 34.8m people in Nigeria face crisis or worse levels of food insecurity during the year. Nutrition partners conducted SMART+ surveys across the BAY states, identifying geographic hotspots of acute malnutrition. The Nutrition and Food Security Surveillance (NFSS) provided disaggregated data on household vulnerability and nutrition outcomes, while sentinel surveillance systems in Borno and Yobe offered early warning on health and nutrition trends.

In addition to partner-led studies, HARP draws on a wider body of humanitarian analysis to inform programming. This includes regular data on displacement, protection analysis and from health interventions. While not funded directly by HARP, these sources contribute to a continuously improving understanding of the humanitarian context and form an important part of FCDO’s engagement with both partners that we fund directly under HARP and the broader humanitarian community.

Learning

Learning was captured through third-party monitoring, surveillance, partner reporting, and structured review meetings, including for this review. Partners were encouraged to share learning and common issues in programme-wide meetings. The TPM partners provided regular analysis, while partners contributed lessons through coordination platforms and operational reviews. The pilot AAP training for marginalised groups in the NE exemplifies adaptive learning within HARP. By dedicating sessions exclusively to people with disabilities and other overlooked populations, the activity addressed systemic barriers to participation and accountability.

Lessons included the need for tailored logistics, language accessibility, and home-based outreach for the most isolated individuals. Follow-up visits reinforced learning and provided audio and translated materials, closing gaps in information access. This initiative contributes to HARP’s learning agenda by demonstrating that inclusive design and persistent engagement can transform accountability practices, strengthen trust, and improve programme relevance. It offers actionable insights for scaling AAP approaches that prioritise equity and dignity in humanitarian response.

Over the past year, learning has been driven by implementation experience, coordination platforms, and targeted assessments. National NGOs highlighted the value of learning by doing, with direct delivery helping to build capacity more effectively than formal training alone. Coordination platforms such as the Rapid Response Mechanism and NHF structures helped facilitate lesson-sharing.

Several lessons emerged across the programme:
- Locally led delivery is more cost-effective and trusted by communities, but sustainability depends on predictable funding and structured handovers.
- Multi-year funding is essential for resilience programming to deliver meaningful results.
- Coordination remains uneven, with NHF structures working well but wider strategic alignment with government actors still limited.
- Health and nutrition services are increasingly run by government staff, but technical gaps persist in stabilisation centres and surveillance systems and there are few solutions to staffing gaps bridged by incentive payments by international partners.
- Data systems need decentralisation and harmonisation, and the loss of centralised coordination bodies risks skewing programming toward better-resourced areas.
- Forced returns and premature resettlement have undermined protection outcomes, and durable solutions will require area-based approaches and long-term investment.
Looking ahead, the programme will focus on strengthening the evidence base for locally led resilience interventions, support the UN-led humanitarian architecture in assessing future engagement strategies for transition planning with government actors, and supporting structured handovers of enabling functions. There is a need to expand adaptive programming to respond to shifting needs and security dynamics, while ensuring national NGOs have more predictable funding and direct access to pooled resources. Learning aims for the coming year include assessing system-level capacities for anticipatory action, deepening understanding of what works in livelihoods programming in North East Nigeria, and improving coherence in nutrition commodity pipelines. Lessons will be documented and used to inform successor programming and strategic planning.

Date of last narrative financial report	WFP: March 2025 / UNICEF: September 2025 / ICRC: March 2025 / OCHA: April 2025 / CARE: June 2025 / INSO: July 2025 / CLEAR Global: June 2025	Date of last audited annual statement	WFP: March 2024 / UNICEF: December 2024 / ICRC: March 2025 / OCHA: March 2024 / CARE: November 2025 / INSO: August 2025 / CLEAR Global: November 2025

List of Acronyms
- AAP – Accountability to Affected Populations
- AGA – Accountable Grant Agreement
- AMP – Aid Management Platform
- AR – Annual Review
- BAY - Borno, Adamawa, and Yobe
- BC – Business Case
- BEmONC – Basic Emergency Obstetrics and Newborn Care
- BRINNS – Building Resilient Infrastructure for Nutrition and Nutrition Security
- CBT – Cash-Based Transfers
- CDEL – Capital Departmental Expenditure Limit
- CERF – Central Emergency Response Fund
- CFM – Complaints and Feedback Mechanism
- CH – Cadre Harmonisé
- CMAM – Community-based Management of Acute Malnutrition
- CMR – Clinical Management of Rape
- DHS - Demographic and Health Survey
- DRC – Danish Refugee Council
- EYN – Ekklesiyar Yan'uwa a Nigeria (Church of the Brethren in Nigeria)
- FCDO – Foreign, Commonwealth & Development Office
- FP – Family Planning
- GBV – Gender-Based Violence
- GEDSI – Gender Equality, Disability and Social Inclusion
- GESI – Gender Equality and Social Inclusion
- HARP – Humanitarian Assistance and Resilience Programme
- HCF – Health Care Facility
- HSOT – The Humanitarian and Stabilisation Operations Team
- HRP – Humanitarian Response Plan
- IAID – Internal Audit and Investigations Department
- IATI – International Aid Transparency Initiative
- ICRC – International Committee of the Red Cross
- IDP – Internally Displaced Person
- INGO – International Non-Governmental Organisation
- INSO – International NGO Safety Organisation
- IPC – Infection Prevention and Control
- LGAs – Local Government Areas
- MAM – Moderate Acute Malnutrition
- MEB – Minimum Expenditure Basket
- MOU – Memorandum of Understanding
- MPCA – Multi-Purpose Cash Assistance
- MUAC – Mid-Upper Arm Circumference
- NBS – National Bureau of Statistics
- NE – North East
- NFSS – Nutrition and Food Security Surveillance
- NGO – Non-Governmental Organisation
- NHF – Nigeria Humanitarian Fund
- NIAC – Non-International Armed Conflict
- NSAG – Non-State Armed Groups
- NW – North West
- OCHA – Office for the Coordination of Humanitarian Affairs
- ODA – Official Development Assistance
- ORP – Oral Rehydration Point
- OTP – Outpatient Therapeutic Programme
- PLRCAP – Promoting Local Response Capacity and Partnership
- PLW – Pregnant and Lactating Women
- PMEL – Portfolio Monitoring, Evaluation, and Learning Programme
- PRO – Programme Responsible Officer
- PUI – Première Urgence Internationale
- QRMs – Quarterly Review Meetings
- RUSF – Ready-to-use Supplementary Food
- RUTF – Ready-to-use Therapeutic Food
- SAM – Severe Acute Malnutrition
- SC – Stabilisation Centre
- SEAH – Sexual Exploitation, Abuse and Harassment
- SGBV – Sexual and Gender-Based Violence
- SMART+ – Standardised Monitoring and Assessment of Relief and Transitions (enhanced version)
- SRH – Sexual and Reproductive Health
- SRHR – Sexual and Reproductive Health and Rights
- SRO – Senior Responsible Officer
- TA – Technical Assistance
- TPM – Third Party Monitoring
- UN – United Nations
- UNHAS – United Nations Humanitarian Air Service
- UNICEF – United Nations Children’s Fund
- VfM – Value for Money
- WASH – Water, Sanitation and Hygiene
- WFP – World Food Programme
- WLO – Women-Led Organisations