## Guidance
Guidance
Partners should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are supported by a robust analysis including a risk matrix. - https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/253815/risk-management-guidance.pdf

## 2022-23
ORGANISATION NAME | Humanitarian and Resilience Programme (2022-2025) First year LF (2022/23) |  |  |  | 1st October 2022 to 30th September 2023
PROJECT NAME
IMPACT | Impact Indicator 1 | Partner driving result | Status | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Reduced morbidity and mortality for people with the most severe humanitarian needs in North east Nigeria | Prevalence of severe food insecurity: Percentage of Surveyed Population in the BAY states in IPC 4 and 5 | WFP | Target | 6.7% | 6% | 6% | 5%
|  |  | Achieved |  | TBC
Source & Means of verification
Baseline (2022) - Cadre Harmonise; Future measures Oct/Nov CH annually
| Impact Indicator 2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Prevalence (%) of global acute malnutrition in Children under 5 years in the BAY states | UNICEF | Target | 11.8% (Borno) 14.1% (Yobe) | 10%(Borno); 10% (Yobe) | 8.5% (Borno) 9.0% (Yobe) | 8.0% (Borno) 8.5% (Yobe)
|  |  | Achieved |  | 9.4%(Borno); 9.4% (Yobe)
Source & Means of verification
Baseline (2022) - NFSS Global Acute Malnutrition Report; Future measures - UNICEF MINA LF Outcome Indicator 3
| Impact Indicator 3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of persons/target population in the target LGAs of the BAY states (disaggregated by age and gender) reporting an improved feeling of safety, reduced vulnerability and improved inclusion in decision-making | CARE | Target | 0% | 0% | 40% | 60%
|  |  | Achieved |  | Project in mobilisation
Source & Means of verification
CARE Impact Indicator 1 - Households (HH) survey through Baseline, Midline and Endline
OUTCOME 1 | Outcome Indicator 1.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions & Risks
People with severe humanitarian needs in the BAY states have increased food security and improved nutritional status | Proportion of infants 0–5 months of age who are fed exclusively with breast milk in the BAY states | UNICEF | Planned | 49% (Borno) 44.4% (Yobe) | 50% (Borno) 45% (Yobe) | 55% (Borno) 47% (Yobe) | 60% (Borno) 50% (Yobe) | a. No rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. b. UNICEF and WFP, alongside downstream partners maintain strong capacity to deliver and license to operate without major delivery or operational disruptions c. Continued funding support and quality delivery by other sector actors and government support maintained. d. Adoption of behaviors remains accepted, appropriate and affordable. e. Humanitarian actors at state and federal level are supportive of the programme and are actively engaged. f. Enabling environment is conducive for partners to be able to conduct activities without constraints such as bureaucratic impediments preventing implementation of activities.
|  |  | Achieved |  | 44.6% (Borno) 38.4% (Yobe)
Source & Means of verification
Baseline from UNICEF MINA Outcome Indicator 1; Future measures from UNICEF MINA Outcome Indicator 1
| Outcome Indicator 1.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of children 6–23 months of age who receive a minimum dietary diversity in the BAY states | UNICEF | Planned | 15.6% (Borno) 17.3% (Yobe) | 16% (Borno) 18% (Yobe) | 20% (Borno) 20% (Yobe) | 25% (Borno) 25% (Yobe)
|  |  | Achieved |  | 6.6% (Borno) 6.2% (Yobe)
Source & Means of verification
Baseline from UNICEF MINA Outcome Indicator 2; Future measures from UNICEF MINA Outcome Indicator 2
Risk Rating | Outcome Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Eager | Percentage of households with acceptable food consumption score in the BAY states | WFP | Planned | 51.1% | >50% | >60 | >65
|  |  | Achieved |  | 37%
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Outcome 1 Indicator 2
Impact weighting | Outcome Indicator 1.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
60% | Percentage of households not using livelihood based coping strategies | WFP | Planned | 40.5% | ≥50 | >60% | >75%
|  |  | Achieved |  | 30.5
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Outcome 1 Indicator 4
| Outcome Indicator 1.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of beneficiaries receiving food and/or cash benefits who are women | WFP | Planned | 59.7% | 59.7% | 57% | 59%
|  |  | Achieved |  | 59.69%
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Output Indicator 1
OUTCOME 2 | Outcome Indicator 2.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions & Risks
Vulnerable people in the BAY states with the most severe humanitarian needs are protected from harm and are reached with sustained humanitarian access. | Percentage of beneficiaries (disaggregated by sex, age, and disability) aware of their rights/ high-quality, survivor-centred inclusive protection services (Gender Based Violence (GBV) mangement -including access to justice, and Sexual and Reproductive Health (SRH)) available in their community and report knowing how to access them. | CARE | Planned | TBD on baseline report | TBC | TBC | TBC | a. No rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. b. Implementing Partners, alongside downstream partners maintain strong capacity to deliver and license to operate without major delivery or operational disruptions c. Continued funding support and quality delivery by other sector actors and government support maintained. d. Actors will coordinate and provide required services for survivors. The government will support intervention and provide complementary services. e. Humanitarian actors at state and federal level are supportive of the programme and are actively engaged f. Enabling environment is conducive for partners to be able to conduct activities without constraints such as bureaucratic impediments preventing implementation of activities.
|  |  | Achieved |  | N/A
Source & Means of verification
CARE Project surveys: coping strategies index. Data disaggregated by HH with people living with disabilities; Future measures - CARE Impact Indicator 2
| Outcome Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of supported women-led groups/collectives actively partcipating in humanitarian action and sustainable resilience building. | CARE UNICEF OCHA | Planned | 0 | UNICEF: 5,000 CARE: 0 OCHA: 0 Total: 5,000 | UNICEF: 10,000 CARE: 50 | UNICEF: 15,000 CARE: 50
|  |  | Achieved |  | UNICEF: 4,197 CARE: 0 OCHA: 30 Total = 4,227
Source & Means of verification
Future measures - CARE Outcome Indicator 2.1 and UNICEF Output Indicator 2.1, OCHA indicator TBC, Output Indicator 2.1. OCHA - 0 (new partners to be onboarded)
Outcome Indicator 2.3
| Proportion of UNHAS User Community satisfied with UNHAS' overall service on the annual Provision of Access Satisfaction Survey (PASS) | UNHAS | Planned | 91.58% | >65% | >70% | >70% | Security risks remain signifanct but no rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. Vulnerable and targeted populations remain accessible only through the UNHAS; INSO continues to enjoy license to operate from security agencies (I)NGOs continue to be allowed to operate in the BAY states Donor funding is received from other donors to maintain budgets UK interest in the North East, Nigeria and the humanitarian response remains strong and signifant
|  |  | Achieved |  | 97%
Source & Means of verification
WFP ACR 2022
| Outcome Indicator 2.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of supported organisations that strongly agree with the statement – “INSO Nigeria services are relevant and useful and improve my NGOs understanding of security environment" | INSO | Planned | 74% | >75% | >75% | >80%
|  |  | Achieved |  | TBC
Source & Means of verification
Baseline - 2022 INSO Partners Satisfaction Survey; Future measures - Annual INSO Partners Satisfaction Survey
Risk Rating | Outcome Indicator 2.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Receptive | .Number of people in need assisted through CBPF funding | OCHA | Planned | N/A | 250000
Impact Weighting |  |  | Achieved |  | 1500000
40% |  |  |  | Source & Means of verification
NHF report
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  |  | 0 | 0 | 0 | 100%
OUTPUT 1 | Output Indicator 1.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Improvement in vulnerable people’s access to adequate food, and cash assistance in reducing prevalence of poor food and nutritional outcomes in the BAY states. | Number of people who received in-kind food assistance | WFP ICRC | Planned | 336019 | WFP: 82,063 ICRC: 0 | 300000 | 400000 | Limited political and military interference in partners activities The targeted sites for this action will remain accessible throughout the delivery period. Complementary services and items such as healthcare, protection is provided by other actors. Cash transfer beneficiaries know optimal use of the fund for their households. Cash transfers do not worsen inflation. Regulatory controls on ATF, AML and IFF are fully adhered to and risks properly mitigated.
|  |  | Achieved |  | WFP: 80,280 ICRC: 25,103 Total:
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of people who received cash/cash-based assistance | WFP ICRC | Planned | 304021 | WFP: 140,738 ICRC: 0 | 150000 | 180000
|  |  | Achieved |  | WFP: 101,294 ICRC: 38,833 Total:
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of cash assistance delivered as direct cash transfers | WFP | Planned | 0% | 5% | 7% | 10%
|  |  | Achieved |  | 2.5%
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of households reached by HARP covered by the government cash transfers (National Social Registry) | WFP UNICEF | Planned | n/a | 5000 | 10000 | 30000
|  |  | Achieved |  | In prep
Source & Means of verification
UNICEF MINA Output Indicator 1.2 (Baseline and future measures) - WFP numbers to be added (simple summation approach)
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
25% | Number of women in selected households receiving gender-sensitive cash/voucher assistance | WFP CARE UNICEF | Planned | UNICEF: 0 CARE: 0 | UNICEF: 5,000 CARE: 200 | UNICEF: 10,000 CARE: 500 | UNICEF: 20,000 CARE: 500 | Eager
|  |  | Achieved |  | In prep
Source & Means of verification
UNICEF MINA Output Indicator 1.1 (Baseline and future measures) + CARE Output Indicator 1.3 (Baseline and future measures) - WFP numbers to be added (simple summation approach)
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
OUTPUT 2 | Output Indicator 2.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Improve nutrition outcomes in children, adolescents and women in Northeast Nigeria through a gender transformative, inclusive, multi-sectoral response. | Monthly average number of Children 0 to 59 months screened for acute malnutrition across the North East | UNICEF | Planned | 600000 | 600000 | 700000 | 700000 | Supply of nutrition commodities are secured and such devliery is at quality, within cost and on time. Service providers are available to provide quality care, counselling and training services when due. Beneficiaries/communities are open to positive social behaviour change to improve nutritional outcomes. Communities and local leaders support the project and actively participate in project activities. PLW have self-efficacy to support interventions and personally practice better behaviours for improved nutritional ooutcomes. State governments provide adequate support to treatment centres and campaigns in a timely manner and releases funds for operational costs promptly. Cash transfer beneficiaries know optimal use of the fund for their households and it does not worsen GBV incidents. Availability of WASH materials to provide services sustainably. Medical supplies chain remains significantly operational through delivery period, Community motivated to own, use and maintain WAS and Health Facilities. State governments provide adequate support to treatment centres and campaigns in a timely manner and releases funds for operational costs promptly. Service providers are available to provide quality care and support services when due. Communities and local leaders support the project and actively participate in project activities. Communities are willing to take ownership of the development process and will commit resources to its sustainability Beneficiaries/communities are open to positive social behaviour change to improve nutritional outcomes. The targeted sites remain accessible throughout the delivery period.
|  |  | Achieved |  | 740,518 (407,285 girls and 333,233 boys)
Source & Means of verification
UNICEF MINA Output Indicator 3.4 (Baseline and future measures)
| Output Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of new SAM admissions (outpatient and inpatient) admitted for treatment (gender disaggregated). | UNICEF | Planned | 0 | TBC | 45000 | 73074
|  |  | Achieved |  | 26,000 Children identified with SAM were referred to OTPs and treated with nutrition commodities procured with funds from a previous FCDO grant (ACA-RUTF
Source & Means of verification
UNICEF MINA Output Indicator 3.5 (Baseline and future measures)
| Output Indicator 2.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of severely malnourished children <5 years recovered, defaulted and died | UNICEF | Planned | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5%
|  |  | Achieved |  | Not reported on
Source & Means of verification
UNICEF MINA Output Indicator 3.6 (Baseline and future measures)
| Output Indicator 2.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of children being admitted at OTP/SC as self referral by caregivers/ mothers trained in MUAC screening | UNICEF | Planned | 20% | 25% | 30% | 40%
|  |  | Achieved |  | 24.5%
Source & Means of verification
UNICEF MINA Output Indicator 3.3b (Baseline and future measures)
| Output Indicator 2.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of pregnant and lactating women (PLW) and their partners who receive counselling and behaviour change messaging about healthy diets and practices and GBV. | UNICEF | Planned | 0 | 50000 | 100000 | 250000
|  |  | Achieved |  | 48458
Source & Means of verification
UNICEF MINA Output Indicator 2.2 (Baseline and future measures)
| Output Indicator 2.6 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women who attended at least 4 ANC visits by age. | UNICEF | Planned | 205573 | 102787 | 250000 | 380000
|  |  | Achieved |  | 64064
Source & Means of verification
UNICEF MINA Output Indicator 3.9 (Baseline and future measures)
| Output Indicator 2.7 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 6 to 59 months who received Vitamin A supplementation. | UNICEF | Planned | 1500000 | 1500000 | 3000000 | 4500000
|  |  | Achieved |  | 1438993
Source & Means of verification
UNICEF MINA Output Indicator 3.1 (Baseline and future measures)
| Output Indicator 2.8 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 6 -24 months receiving micronutrient powders. | UNICEF |  | N/A | UNICEF: Procurement initiated but delayed due to global shortage.
In prep
Source & Means of verification
| Output Indicator 2.9 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children, adolescents and caregivers reached with comprehensive focus mental health and psychosocial support services including life skills education and positive parenting (gender and age disaggregated) | UNICEF | Planned | 345153 | 75000 | 200000 | 250000
|  |  | Achieved |  | 50000
Source & Means of verification
UNICEF MINA Output Indicator 3.12 (Baseline and future measures)
| Output Indicator 2.10 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of vulnerable people (including families with SAM children, adolescent girls and PLW) in communities and IDP camps gaining access to climate-resilient, gender- and disability-sensitive WASH services and supplies to ensure optimal dietary practices | UNICEF | Planned | 0 | 37500 | 112500 | 150000
|  |  | Achieved |  | 14500
Source & Means of verification
UNICEF MINA Output Indicator 2.3 (Baseline and future measures)
| Output Indicator 2.11 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of ODF certified communities | UNICEF | Planned | 0 | 0 | 100 | 120
|  |  | Achieved |  | In prep
Source & Means of verification
UNICEF MINA Output Indicator 2.4 (Baseline and future measures)
| Output Indicator 2.12 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of HCFs (w/CMAM and/or OTP centers) in target areas provided with access to gender- and disability-sensitive WASH services | UNICEF | Planned | 0 | 5 | 15 | 25
|  |  | Achieved |  | In prep
Source & Means of verification
UNICEF MINA Output Indicator 3.17 (Baseline and future measures)
IMPACT WEIGHTING (%) | Output Indicator 2.13 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
35% | [Nothing]
Receptive
Source & Means of verification
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  |  | 0 | 0 |  | 100%
OUTPUT 3 | Output Indicator 3.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Protecting people from harm and strengthening humanitarian access. | Number of individuals accessing awareness raising and community based protection mechanisms in the targeted LGAs of the BAY states (by age and gender) | CARE OCHA ICRC | Planned | 0 | 50000 | 70000 | 80000 | Limited political and military interference in partners activities. The targeted sites for this action will remain accessible throughout the delivery period. Legal and civil documentation processes are not bogged down by bureaucratic challenges. Participation of women in the program is encouraged through community sensitization of men. Strong rapport with the key community leaders and government stakeholders built for strong coordination and timely support. Services provided are able to meaningfully support individuals and enble confidentiality for increased uptake. Women and girls’ groups are already established and or will be open to establish a group to work on women’s participation/leadership in decision-making spaces The absence of reliable commercial air operators to service currently inaccessible areas continues. Demand from the humanitarian community for enabling services remains strong. Limited political and military interference in partners activities. The targeted sites for this action will remain accessible throughout the delivery period.
|  |  | Achieved |  | 49963
Source & Means of verification
Baseline and future measures CARE Output Indicator 1.2. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women and girls targeted/reached with comprehensive GBV case management, psychosocial support, and referral for other specialized services including nutrition, legal, security and justice services and mechanisms(age disaggregated) | CARE OCHA ICRC | Planned | 0 | 75
|  |  | Achieved |  | 551
Source & Means of verification
Baseline and future measures CARE Output Indicator 1.1. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of beneficiaries who can identify and act upon protection concerns | CARE ICRC | Planned | 0 | 150 | 300 | 300
|  |  | Achieved |  | In prep
Source & Means of verification
Baseline and future measures CARE Outcome Indicator 2.3. ICRC Indicators TBC. (Simple summation approach)
| Output Indicator 3.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of Gynaelogical/obstetric admissions | ICRC | Planned | N/A | 0 | 10 | 10
|  |  | Achieved |  | 1243
Source & Means of verification
ICRC annual report
| Output Indicator 3.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of missing persons tracing cases still being handled at the end of the reporting period (W&G) | ICRC | Planned | N/A | N/A | 10 | 10
|  |  | Achieved |  | In prep
Source & Means of verification
ICRC annual report
| Output Indicator 3.6 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of unaccompanied minors/separated children cases being supported (girls figure available) | ICRC | Planned | N/A | N/A | 10 | 10
|  |  | Achieved |  | 15
Source & Means of verification
ICRC annual report
| Output Indicator 3.7 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women and girls detainees visited | ICRC | Planned | 0 | N/A | 10 | 10
|  |  | Achieved |  | 1186
Source & Means of verification
ICRC annual report
| Output Indicator 3.8 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of womens' groups trained to meaningfully influence decision makers or local authorities or traditional leaders at LGAs relevant with GBV and SRH rights and services. | CARE | Planned | 0 | 0 | 10 | 10
|  |  | Achieved |  | In prep
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.9 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of individuals trained to support inclusive & safe protection services, awareness raising and drive social changes (paralegals, project staff, community structures, men and boys and health providers). | CARE | Planned | 0 | 0 | 690 | 690
|  |  | Achieved |  | In prep
Source & Means of verification
Baseline and future measures CARE LF - Summation of Output indicator 1.4, Output indicator 1.2.1, Output indicator 2.1.1 and Output Indicator 2.1.2
| Output Indicator 3.10 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of passengers transported by UNHAS (fixed and rotary wings) supported by FCDO funding | UNHAS | Planned | 3791 | 3791 | 5000 | 5500
|  |  | Achieved |  | 2887
Source & Means of verification
Baseline - Dec 2022 UNHAS steering committee report; future measures - WFP Annual ACR (as proportion of contributions to NE results), Activity 9, Output 15
| Output Indicator 3.11 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Size in MT of commodities transported by UNHAS supported by FCDO funding | UNHAS | Planned | 13.24 | 13 | 15 | 17
|  |  | Achieved |  | 11.2
Source & Means of verification
Baseline - Dec 2022 UNHAS steering committee report; future measures - WFP Annual ACR (as proportion of contributions to NE results) Activity 9, Output 15
| Output Indicator 3.12 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of passsenger bookings successfully fulfilled/served | UNHAS | Planned | 80% | 80% | 85% | 90%
|  |  | Achieved |  | 88%
Source & Means of verification
Future measures - WFP Annual ACR (as proportion of contributions to NE results), Activity 9, Output 15
| Output Indicator 3.13 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of organisations in N/East Nigeria supported by INSO with safety coordination, training and advisory services | INSO | Planned | 70 | 71 | 73 | 75
|  |  | Achieved |  | 111
Source & Means of verification
INSO annual reports
| Output Indicator 3.14 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of supported organisation who received basic and/or advanced security management trainings delivered by INSO during the year. | INSO | Planned | N.a | 95% | 95% | 100%
|  |  | Achieved |  | 105%
Source & Means of verification
INSO annual reports
IMPACT WEIGHTING (%) | Output Indicator 3.15 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
30% | Proportion of notified incidents and quarterly security analysis that INSO was able to successfully send flash SMS and emails/reports on to NGO partners. | INSO | Planned | N.a | 95% | 95% | 100% | Receptive
|  |  | Achieved |  | 105%
Source & Means of verification
INSO annual reports
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Planned
Achieved
Source & Means of verification
| Output Indicator 6.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Planned
Achieved
Source & Means of verification
IMPACT WEIGHTING (%) | Output Indicator 6.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Planned
Achieved
|  |  | Source & Means of verification |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4.1 | Output Indicator 4.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Deliver multi-sector emergency response to address dynamic and unpredictable needs in the North-East | Proportion of annual HARP spend directed to local CSOs/NGOs to effectively contribute to humanitarian planning and response in Nigeria | WFP, UNICEF, OCHA, CARE and Clear Global | Planned | Baseline year for reporting | Baseline year for reporting | 25% | 35% | UK political will and reputational capital to continue engaging in the N/East to deliver basic services and (re)build infrastructure in the longer term remains adequate. There is opportunity for meaningful UK engagement with partners and state actors who have capacity to deliver. Partners are supportive of the multisector localisation and inclusive agenda.
|  |  | Achieved |  | N/A
Source(s) of verification
All partner reporting
| Output Indicator 4.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of HARP partners with functional and verified CFM | WFP, UNICEF, ICRC, and OCHA | Achieved | 2 | 4 | 4 | 4
3
Source(s) of verification
All partner reporting
| Output Indicator 4.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| The NHF Advisory Board has a manageable size and a balanced representation of Country-Based Pooled Funds (CBPF) stakeholders. | OCHA | Planned | 9 | 9 | 10 | 10
|  |  | Achieved |  | 10
Source(s) of verification
OCHA NHF annual reporting
| Output Indicator 4.4 |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Is CBPF funding allocated to the best-positioned actors, leveraging the diversity and comparative advantage of eligible organizations? | OCHA | Achieved | N/A | Yes | Yes | Yes
Yes
Source(s) of verification
OCHA NHF annual reporting
| Output Indicator 4.5 |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| CBPFs allocation processes have an appropriate duration | OCHA | Achieved | N/A | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average. | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average. | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average.
Standard Allocation projects were processed (from the submission deadline to HC signature) within 30 days on average
Source(s) of verification
OCHA NHF annual reporting
IMPACT WEIGHTING (%) | Output Indicator 4.6 |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
| CBPFs have a significant funding level to support the delivery of the HRPs | OCHA | Achieved | N/A | 15% of HRP funding received through the CBPF | 15% of HRP funding received through the CBPF | 15% of HRP funding received through the CBPF | Receptive
4.1% of HRP contribution to received through the CBPF
Source(s) of verification
OCHA NHF annual reporting
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)

## 2023-24
ORGANISATION NAME | Humanitarian and Resilience Programme (2022-2025) Second Year LF (2023-2024) |  |  |  | 1st October 2023 to 30th September 2024
PROJECT NAME
IMPACT | Impact Indicator 1 | Partner driving result | Status | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Reduced morbidity and mortality, improved protection and strengthened resilience for people with the most severe humanitarian needs in NE Nigeria | Percentage of population in NE Nigeria in IPC 4 and 5 | WFP | Target | 6.7% | 6% | 6% | 5%
|  |  | Achieved |  | TBC | 1.2%
Source & Means of verification
Baseline (2022) - Cadre Harmonise; Future measures Oct/Nov CH annually
| Impact Indicator 2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Prevalence (%) of global acute malnutrition in children under 5 years in NE Nigeria | UNICEF | Target | 11.8% (Borno) 14.1% (Yobe) | 10%(Borno); 10% (Yobe) | 8.5% (Borno) 9.0% (Yobe) | 8.0% (Borno) 8.5% (Yobe)
|  |  | Achieved |  | 9.4%(Borno); 9.4% (Yobe) | 10.2% (Borno) 8.0% (Yobe)
Source & Means of verification
Baseline (2022) - NFSS Global Acute Malnutrition Report; Future measures - UNICEF MINA LF Outcome Indicator 3
| Impact Indicator 3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Increase in the number of women and girls able to access appropriate assistance and services | CARE | Target | 0% | 0% | 40% | 60%
|  |  | Achieved |  | Project in mobilisation | 47%
Source & Means of verification
CARE Impact Indicator 1 - Households (HH) survey through Baseline, Midline and Endline
OUTCOME 1 | Outcome Indicator 1.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions & Risks
Improved food security and nutritional status for the most vulnerable in NE Nigeria | Proportion of children 6–23 months of age who receive a minimum dietary diversity in the BAY states | UNICEF | Planned | 49% (Borno) 44.4% (Yobe) | 50% (Borno) 45% (Yobe) | 20% (Borno) 20% (Yobe) | 60% (Borno) 50% (Yobe) | a. No rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. b. UNICEF and WFP, alongside downstream partners maintain strong capacity to deliver and license to operate without major delivery or operational disruptions c. Continued funding support and quality delivery by other sector actors and government support maintained. d. Adoption of behaviors remains accepted, appropriate and affordable. e. Humanitarian actors at state and federal level are supportive of the programme and are actively engaged. f. Enabling environment is conducive for partners to be able to conduct activities without constraints such as bureaucratic impediments preventing implementation of activities.
|  |  | Achieved |  | 44.6% (Borno) 38.4% (Yobe) | 23% (Borno); 32.6% (Yobe)
Source & Means of verification
Baseline from UNICEF MINA Outcome Indicator 1; Future measures from UNICEF MINA Outcome Indicator 1 Outcome Indicator 2
Risk Rating | Outcome Indicator 1.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Eager | Percentage of households with acceptable food consumption and household hunger scores in the BAY states | WFP | Planned | 51.1% | >50% | >60 | >65
|  |  | Achieved |  | 37% | 36.4% (29.2 F and 38.5 M)
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Outcome 1 Indicator 2
Impact weighting | Outcome Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
60% | Percentage of households using livelihood based coping strategies leading to a reduction in the number of households receiving in-kind/CBT assistance | WFP | Planned | 40.5% | ≥50 | >60% | >75%
|  |  | Achieved |  | 30.5
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Outcome 1 Indicator 4
| Outcome Indicator 1.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of beneficiaries receiving food and/or cash benefits who are women | WFP | Planned | 59.7% | 59.7% | 57% | 59%
|  |  | Achieved |  | 59.69%
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Output Indicator 1
OUTCOME 2 | Outcome Indicator 2.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions & Risks
Increased protection of target comunities across the NE benefiting from predictable, localised and multisectoral humanitarian assistance | Percentage of beneficiaries (disaggregated by sex, age, and disability) aware of their rights/ high-quality, survivor-centred inclusive protection services (Gender Based Violence (GBV) mangement -including access to justice, and Sexual and Reproductive Health (SRH)) available in their community and report knowing how to access them. | CARE | Planned | TBD on baseline report | 17,6% | 18,25% | 55% | a. No rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. b. Implementing Partners, alongside downstream partners maintain strong capacity to deliver and license to operate without major delivery or operational disruptions c. Continued funding support and quality delivery by other sector actors and government support maintained. d. Actors will coordinate and provide required services for survivors. The government will support intervention and provide complementary services. e. Humanitarian actors at state and federal level are supportive of the programme and are actively engaged f. Enabling environment is conducive for partners to be able to conduct activities without constraints such as bureaucratic impediments preventing implementation of activities.
|  |  | Achieved |  | N/A | Mid line evalution in october 2024
Source & Means of verification
CARE Project surveys: coping strategies index. Data disaggregated by HH with people living with disabilities; Future measures - CARE Impact Indicator 2
| Outcome Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of supported women-led groups/collectives actively partcipating in humanitarian action and sustainable resilience building. | CARE UNICEF OCHA | Planned | 0 | UNICEF: 5,000 CARE: 0 OCHA: 0 Total: 5,000 | UNICEF: 10,000 CARE: 50 | UNICEF: 15,000 CARE: 50
|  |  | Achieved |  | UNICEF: 4,197 CARE: 0 OCHA: 30 Total = 4,227 | UNICEF: 6,025 CARE: 10
Source & Means of verification
Future measures - CARE Outcome Indicator 2.1 and UNICEF Output Indicator 2.1, OCHA indicator TBC, Output Indicator 2.1. OCHA - 0 (new partners to be onboarded)
Risk Rating | Outcome Indicator 2.3
Receptive | Number of LGAs HARP partners are active in as a proportion of the LGAs targeted by the HRP | UNHAS | Planned | 91.58% | >65% | >70% | >70% | Security risks remain signifanct but no rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. Vulnerable and targeted populations remain accessible only through the UNHAS; INSO continues to enjoy license to operate from security agencies (I)NGOs continue to be allowed to operate in the BAY states Donor funding is received from other donors to maintain budgets UK interest in the North East, Nigeria and the humanitarian response remains strong and signifant
Impact Weighting |  |  | Achieved |  | 97%
40% |  |  |  | Source & Means of verification
WFP ACR 2022
| Outcome Indicator 2.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of supported organisations that strongly agree with the statement – “INSO Nigeria services are relevant and useful and improve my NGOs understanding of security environment" | INSO | Planned | 74% | >75% | >75% | >80%
|  |  | Achieved |  | TBC
Source & Means of verification
Baseline - 2022 INSO Partners Satisfaction Survey; Future measures - Annual INSO Partners Satisfaction Survey
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  |  | 0 | 0 | 0 | 100%
OUTPUT 1 | Output Indicator 1.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 (cumulative ) | Target (date) - Sept 2025 | Assumptions and Risks
The delivery of more predictable and impactful food assistance in NE Nigeria | Number of people receiving food assistance broken down by type of transfer | WFP ICRC | Planned | 336019 | WFP: 82,063 ICRC: 0 | WFP: 300,000 ICRC: 18,000 | 400000 | Limited political and military interference in partners activities The targeted sites for this action will remain accessible throughout the delivery period. Complementary services and items such as healthcare, protection is provided by other actors. Cash transfer beneficiaries know optimal use of the fund for their households. Cash transfers do not worsen inflation. Regulatory controls on ATF, AML and IFF are fully adhered to and risks properly mitigated.
|  |  | Achieved |  | WFP: 80,280 ICRC: 25,103 | WFP: Tot. 292,907 from 111,333 (2023) + 80,280 (2022) + 101,294 (2022) ICRC: Tot. 35,153 from 10,050 (2023) + 25,103 (2022) + 38,833 (2022)
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number Percentage of people receiving CBT, including percentage of WFP CBT provided as MPCA | WFP ICRC | Planned | 304021 | WFP: 140,738 ICRC: 0 | WFP: 150,000 ICRC: | 180000
|  |  | Achieved |  | WFP: 101,294 ICRC: 38,833 | WFP did not provide cash as modality of CBT only value vouchers.
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of cash assistance delivered as direct cash transfers | WFP | Planned | 0% | 5% | 7% | 10%
|  |  | Achieved |  | 2.5%
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of households reached by HARP covered by the government cash transfers (National Social Registry) | WFP UNICEF | Planned | n/a | 5000 | WFP: 10000 UNICEF: 3000 | 30000
|  |  | Achieved |  | In prep | UNICEF: 4000
Source & Means of verification
UNICEF MINA Output Indicator 1.2 (Baseline and future measures) - WFP numbers to be added (simple summation approach)
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 (cumulative) | Target (date) - Sept 2025 | RISK RATING
25% | Number of women in selected households receiving gender-sensitive cash/voucher assistance | WFP CARE UNICEF | Planned | UNICEF: 0 CARE: 0 | UNICEF: 5,000 CARE: 200 | UNICEF: 10,000 CARE: 500 | UNICEF: 20,000 CARE: 500 | Eager
|  |  | Achieved |  | In prep | UNICEF: 14,789 CARE: 889
Source & Means of verification
UNICEF MINA Output Indicator 1.1 (Baseline and future measures) + CARE Output Indicator 1.3 (Baseline and future measures) - WFP numbers to be added (simple summation approach)
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
OUTPUT 2 | Output Indicator 2.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Improve nutrition outcomes in children, adolescents and women in Northeast Nigeria through a gender transformative, inclusive, multi-sectoral response | Monthly average number of children 0 to 59 months screened for acute malnutrition across the NE and number newly admitted at OTP/SC for SAM treatment -outpatient and inpatient (Gender disaggregated) | UNICEF | Planned | 600000 | 600000 | 700000 | 700000 | Supply of nutrition commodities are secured and such devliery is at quality, within cost and on time. Service providers are available to provide quality care, counselling and training services when due. Beneficiaries/communities are open to positive social behaviour change to improve nutritional outcomes. Communities and local leaders support the project and actively participate in project activities. PLW have self-efficacy to support interventions and personally practice better behaviours for improved nutritional ooutcomes. State governments provide adequate support to treatment centres and campaigns in a timely manner and releases funds for operational costs promptly. Cash transfer beneficiaries know optimal use of the fund for their households and it does not worsen GBV incidents. Availability of WASH materials to provide services sustainably. Medical supplies chain remains significantly operational through delivery period, Community motivated to own, use and maintain WAS and Health Facilities. State governments provide adequate support to treatment centres and campaigns in a timely manner and releases funds for operational costs promptly. Service providers are available to provide quality care and support services when due. Communities and local leaders support the project and actively participate in project activities. Communities are willing to take ownership of the development process and will commit resources to its sustainability Beneficiaries/communities are open to positive social behaviour change to improve nutritional outcomes. The targeted sites remain accessible throughout the delivery period.
|  |  | Achieved |  | 740,518 (407,285 girls and 333,233 boys) | 656,564 children (94%) (boys: 302,019 and girls: 354,545)
Source & Means of verification
UNICEF MINA Output Indicator 3.4 (Baseline and future measures)
| Output Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 0 to 59 months being newly admitted at OTP/SC for SAM treatment -outpatient and inpatient. (gender disaggregated). | UNICEF | Planned | 0 | TBC | 45000 | 73074
|  |  | Achieved |  | 26,000 Children identified with SAM were referred to OTPs and treated with nutrition commodities procured with funds from a previous FCDO grant (ACA-RUTF
Source & Means of verification
UNICEF MINA Output Indicator 3.5 (Baseline and future measures)
| Output Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of severely malnourished children <5 years recovered, defaulted and died | UNICEF | Planned | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5%
|  |  | Achieved |  | Not reported on | Recovery rate: 97.7% Default rate: 1.3% Death rate: 0.4%
Source & Means of verification
UNICEF MINA Output Indicator 3.6 (Baseline and future measures)
| Output Indicator 2.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of children being admitted at OTP/SC as self referral by caregivers/ mothers trained in MUAC screening | UNICEF | Planned | 20% | 25% | 30% | 40%
|  |  | Achieved |  | 24.5% | 33%
Source & Means of verification
UNICEF MINA Output Indicator 3.3b (Baseline and future measures)
| Output Indicator 2.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of pregnant and lactating women (PLW) and their partners who receive counselling and behaviour change messaging about healthy diets and practices and GBV. | UNICEF | Planned | 0 | 50000 | 100000 | 250000
|  |  | Achieved |  | 48458
Source & Means of verification
UNICEF MINA Output Indicator 2.2 (Baseline and future measures)
| Output Indicator 2.6 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women who attended at least 4 ANC visits by age. | UNICEF | Planned | 205573 | 102787 | 250000 | 380000
|  |  | Achieved |  | 64064
Source & Means of verification
UNICEF MINA Output Indicator 3.9 (Baseline and future measures)
| Output Indicator 2.7 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 6 to 59 months who received Vitamin A supplementation. | UNICEF | Planned | 1500000 | 1500000 | 3000000 | 4500000
|  |  | Achieved |  | 1438993
Source & Means of verification
UNICEF MINA Output Indicator 3.1 (Baseline and future measures)
| Output Indicator 2.8 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 6 -24 months receiving micronutrient powders. | UNICEF |  | N/A | UNICEF: Procurement initiated but delayed due to global shortage.
In prep
Source & Means of verification
| Output Indicator 2.9 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children, adolescents and caregivers reached with comprehensive focus mental health and psychosocial support services including life skills education and positive parenting (gender and age disaggregated) | UNICEF | Planned | 345153 | 75000 | 200000 | 250000
|  |  | Achieved |  | 50000
Source & Means of verification
UNICEF MINA Output Indicator 3.12 (Baseline and future measures)
| Output Indicator 2.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 (cumulative) | Target (date) - Sept 2025
| Number of vulnerable people (including families with SAM children, adolescent girls and PLW) in communities and IDP camps gaining access to climate-resilient, gender- and disability-sensitive WASH services and supplies to ensure optimal dietary practices | UNICEF | Planned | 0 | 37500 | 112500 | 150000
|  |  | Achieved |  | 14500 | 59,720 + 14,500
Source & Means of verification
UNICEF MINA Output Indicator 2.3 (Baseline and future measures)
| Output Indicator 2.11 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of ODF certified communities | UNICEF | Planned | 0 | 0 | 100 | 120
|  |  | Achieved |  | In prep
Source & Means of verification
UNICEF MINA Output Indicator 2.4 (Baseline and future measures)
| Output Indicator 2.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of HCFs (w/CMAM and/or OTP centers) in target areas provided with access to gender- and disability-sensitive WASH services | UNICEF | Planned | 0 | 5 | 15 | 25
|  |  | Achieved |  | In prep | 15
Source & Means of verification
UNICEF MINA Output Indicator 3.17 (Baseline and future measures)
IMPACT WEIGHTING (%) |  |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
35%
Receptive
Source & Means of verification
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  |  | 0 | 0 |  | 100%
OUTPUT 3 | Output Indicator 3.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Protecting people from harm and strengthening humanitarian access. | Number of individuals accessing awareness raising and community based protection mechanisms in target LGAs (by age and gender) | CARE OCHA ICRC | Planned | 0 | 50000 | CARE: 20000 OCHA: ICRC: | 80000 | Limited political and military interference in partners activities. The targeted sites for this action will remain accessible throughout the delivery period. Legal and civil documentation processes are not bogged down by bureaucratic challenges. Participation of women in the program is encouraged through community sensitization of men. Strong rapport with the key community leaders and government stakeholders built for strong coordination and timely support. Services provided are able to meaningfully support individuals and enble confidentiality for increased uptake. Women and girls’ groups are already established and or will be open to establish a group to work on women’s participation/leadership in decision-making spaces The absence of reliable commercial air operators to service currently inaccessible areas continues. Demand from the humanitarian community for enabling services remains strong. Limited political and military interference in partners activities. The targeted sites for this action will remain accessible throughout the delivery period.
|  |  | Achieved |  | 49963 | CARE: 21,630
Source & Means of verification
Baseline and future measures CARE Output Indicator 1.2. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women and girls targeted/reached with comprehensive GBV case management, psychosocial support, and referral for other specialized services including nutrition, legal, security and justice services and mechanisms (age disaggregated) | CARE OCHA ICRC | Planned | 0 | 75 | CARE: 125 OCHA: 300 ICRC: 200
|  |  | Achieved |  | 551 | CARE: 168 OCHA: 2,210 ICRC: 616
Source & Means of verification
Baseline and future measures CARE Output Indicator 1.1. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of beneficiaries who can identify and act upon protection concerns I'm not sure what this means and how efectively it can be measured! | CARE OCHA ICRC | Planned | 0 | 150 | 300 | 300
Achieved
Source & Means of verification
Baseline and future measures CARE Outcome Indicator 2.3. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of Gynaelogical/obstetric admissions | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of missing persons tracing cases still being handled at the end of the reporting period (W&G) | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.6 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of unaccompanied minors/separated children cases being supported (girls figure available) | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.7 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women and girls detainees visited | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.8 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of womens' groups trained to meaningfully influence decision makers or local authorities or traditional leaders at LGAs relevant with GBV and SRH rights and services.This is broadly similar to inidcator 3,.2 | CARE | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of individuals trained to support inclusive & safe protection services, awareness raising and drive social changes (paralegals, project staff, community structures, men and boys and health providers). | CARE | Planned | 0 | 450 | 690 | 690
|  |  | Achieved |  |  | 455
Source & Means of verification
Baseline and future measures CARE LF - Summation of Output indicator 1.4, Output indicator 1.2.1, Output indicator 2.1.1 and Output Indicator 2.1.2
| Output Indicator 3.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of passenger journeys funded by FCDO and as a proportion of total journeys | UNHAS | Planned | 3791 | 3791 | 5000 | 5500
|  |  | Achieved |  | 2887 | 4090
Source & Means of verification
Baseline - Dec 2022 UNHAS steering committee report; future measures - WFP Annual ACR (as proportion of contributions to NE results), Activity 9, Output 15
| Output Indicator 3.11 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Size in MT of commodities transported by UNHAS supported by FCDO funding | UNHAS | Planned | 13.24 | 13 | 15 | 17
|  |  | Achieved |  | 11.2
Source & Means of verification
Baseline - Dec 2022 UNHAS steering committee report; future measures - WFP Annual ACR (as proportion of contributions to NE results) Activity 9, Output 15
| Output Indicator 3.12 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of passsenger bookings successfully fulfilled/served | UNHAS | Planned | 80% | 80% | 85% | 90%
|  |  | Achieved |  | 88%
Source & Means of verification
Future measures - WFP Annual ACR (as proportion of contributions to NE results), Activity 9, Output 15
| Output Indicator 3.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of organisations in NE Nigeria supported by INSO with safety coordination, training and advisory services | INSO | Planned | 70 | 71 | 73 | 75
|  |  | Achieved |  | 111 | 111
Source & Means of verification
INSO annual reports
IMPACT WEIGHTING (%) |  |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
30% | Proportion of supported organisation who received basic and/or advanced security management trainings delivered by INSO during the year. Number of organisations and participants receiving INSO training | INSO | Planned | N.a | 95% | 95% | 100% | Receptive
Achieved
Source & Means of verification
INSO annual reports
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Planned
Achieved
Source & Means of verification
| Output Indicator 6.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Planned
Achieved
Source & Means of verification
IMPACT WEIGHTING (%) | Output Indicator 6.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Planned
Achieved
|  |  | Source & Means of verification |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4.1 | Output Indicator 4.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
HARP cultivates a more localised response in NE Nigeria that is informed by learning and fully responsive to spikes in need | Proportion of annual HARP spend (including FCDO contribution to NHF) directed to local CSOs/NGOs | WFP, UNICEF, OCHA, CARE and Clear Global | Planned | Baseline year for reporting | Baseline year for reporting | 25% | 35% | UK political will and reputational capital to continue engaging in the N/East to deliver basic services and (re)build infrastructure in the longer term remains adequate. There is opportunity for meaningful UK engagement with partners and state actors who have capacity to deliver. Partners are supportive of the multisector localisation and inclusive agenda.
|  |  | Achieved |  | N/A | 30%
Source(s) of verification
All partner reporting
| Output Indicator 4.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number/frequency of independent third party programme monitoring and verification visits undertaken | CG | Achieved | 2 | 4 | 4 | 4
[5 empty] | 3 | NA
Source(s) of verification
All partner reporting
| Output Indicator 4.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of partners reporting improvements in: a) programme design and delivery; b) adherence to best practise and c) fundraising as a direct result of Third Party monitoring and verification visits | CG | Planned | 9
Achieved
Source(s) of verification
OCHA NHF annual reporting
| Output Indicator 4.5 |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| CBPFs allocation processes have an appropriate duration | OCHA | Achieved | N/A | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average. | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average. | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average.
Standard Allocation projects were processed (from the submission deadline to HC signature) within 30 days on average
Source(s) of verification
OCHA NHF annual reporting
IMPACT WEIGHTING (%) |  |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
| CBPFs have a significant funding level to support the delivery of the HRPs | OCHA | Achieved | N/A | 15% of HRP funding received through the CBPF | 15% of HRP funding received through the CBPF | 15% of HRP funding received through the CBPF | Receptive
4.1% of HRP contribution to received through the CBPF
Source(s) of verification
OCHA NHF annual reporting
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)

## 2024-25
ORGANISATION NAME | Humanitarian and Resilience Programme (2022-2027) Third Year LF (2023-2024) |  |  |  | 1st October 2024 to 30th September 2025
PROJECT NAME
IMPACT | Impact Indicator 1 | Partner driving result | Status | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Reduced morbidity and mortality, improved protection and strengthened resilience for people with the most severe humanitarian needs in NE Nigeria | Percentage of population in NE Nigeria in IPC 4 and 5 | WFP | Target | 6.7% | 6% | 6% | 5%
|  |  | Achieved |  | TBC | 1.2% | 3.36%
Source & Means of verification
Baseline (2022) - Cadre Harmonise; Future measures Oct/Nov CH annually
| Impact Indicator 2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Prevalence (%) of global acute malnutrition in children under 5 years in NE Nigeria | UNICEF | Target | 11.8% (Borno) 14.1% (Yobe) | 10%(Borno); 10% (Yobe) | 8.5% (Borno) 9.0% (Yobe) | 8.0% (Borno) 8.5% (Yobe)
|  |  | Achieved |  | 9.4%(Borno); 9.4% (Yobe) | 10.2% (Borno) 8.0% (Yobe) | 15.7% (Borno) 11.9% (Yobe)
Source & Means of verification
Baseline (2022) - NFSS Global Acute Malnutrition Report; Future measures - UNICEF MINA LF Outcome Indicator 3
| Impact Indicator 3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - April 2025
| Increase in the number of women and girls able to access appropriate assistance and services | CARE | Target | 0% | 0% | 40% | 60%
|  |  | Achieved |  | Project in mobilisation | 47% | 96%
Source & Means of verification
CARE Impact Indicator 1 - Households (HH) survey through Baseline, Midline and Endline
OUTCOME 1 | Outcome Indicator 1.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions & Risks
Improved food security and nutritional status for the most vulnerable in NE Nigeria | Proportion of children 6–23 months of age who receive a minimum dietary diversity in the BAY states | UNICEF | Planned | 49% (Borno) 44.4% (Yobe) | 50% (Borno) 45% (Yobe) | 20% (Borno) 20% (Yobe) | 60% (Borno) 50% (Yobe) | a. No rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. b. UNICEF and WFP, alongside downstream partners maintain strong capacity to deliver and license to operate without major delivery or operational disruptions c. Continued funding support and quality delivery by other sector actors and government support maintained. d. Adoption of behaviors remains accepted, appropriate and affordable. e. Humanitarian actors at state and federal level are supportive of the programme and are actively engaged. f. Enabling environment is conducive for partners to be able to conduct activities without constraints such as bureaucratic impediments preventing implementation of activities.
|  |  | Achieved |  | 44.6% (Borno) 38.4% (Yobe) | 23% (Borno); 32.6% (Yobe) | 41.9% (Borno) 51% (Yobe)
Source & Means of verification
Baseline from UNICEF MINA Outcome Indicator 1; Future measures from UNICEF MINA Outcome Indicator 2
Risk Rating | Outcome Indicator 1.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Eager | Percentage of households with acceptable food consumption and household hunger scores in the BAY states | WFP | Planned | 51.1% | >50% | >60 | >65
|  |  | Achieved |  | 37% | 36.4% (29.2 F and 38.5 M) | 17.8% (18.85 F and 17.33 M)
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Outcome 1 Indicator 2
Impact weighting | Outcome Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
60% | Percentage of households using livelihood based coping strategies leading to a reduction in the number of households receiving in-kind/CBT assistance | WFP | Planned | 40.5% | ≥50 | >60% | >75%
|  |  | Achieved |  | 30.5 | Follow-up | 22.21%
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Outcome 1 Indicator 4
| Outcome Indicator 1.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of beneficiaries receiving food and/or cash benefits who are women | WFP | Planned | 59.7% | 59.7% | 57% | 59%
|  |  | Achieved |  | 59.69%
Source & Means of verification
Baseline from WFP ACR 2022; Future measures from WFP Annual Country Report - Output Indicator 1
OUTCOME 2 | Outcome Indicator 2.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions & Risks
Increased protection of target comunities across the NE benefiting from predictable, localised and multisectoral humanitarian assistance | Percentage of beneficiaries (disaggregated by sex, age, and disability) aware of their rights/ high-quality, survivor-centred inclusive protection services (Gender Based Violence (GBV) mangement -including access to justice, and Sexual and Reproductive Health (SRH)) available in their community and report knowing how to access them. | CARE | Planned | TBD on baseline report | 17,6% | 18,25% | 55% | a. No rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. b. Implementing Partners, alongside downstream partners maintain strong capacity to deliver and license to operate without major delivery or operational disruptions c. Continued funding support and quality delivery by other sector actors and government support maintained. d. Actors will coordinate and provide required services for survivors. The government will support intervention and provide complementary services. e. Humanitarian actors at state and federal level are supportive of the programme and are actively engaged f. Enabling environment is conducive for partners to be able to conduct activities without constraints such as bureaucratic impediments preventing implementation of activities.
|  |  | Achieved |  | N/A | Mid line evalution in october 2024 | 82%
Source & Means of verification
CARE Project surveys: coping strategies index. Data disaggregated by HH with people living with disabilities; Future measures - CARE Impact Indicator 2
| Outcome Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of supported women-led groups/collectives actively partcipating in humanitarian action and sustainable resilience building. | CARE UNICEF | Planned | 0 | UNICEF: 5,000 CARE: 0 OCHA: 0 Total: 5,000 | UNICEF: 10,000 CARE: 50 | UNICEF: 15,000 CARE: 50
|  |  | Achieved |  | UNICEF: 4,197 CARE: 0 OCHA: 30 Total = 4,227 | UNICEF: 6,025 CARE: 10 | UNICEF: 5,960 CARE: 30
Source & Means of verification
Future measures - CARE Outcome Indicator 2.3 and UNICEF Output Indicator 2.1
Risk Rating | Outcome Indicator 2.3
Receptive | Number of LGAs HARP partners are active in as a proportion of the LGAs targeted by the HRP | UNHAS | Planned | 91.58% | >65% | >70% | >70% | Security risks remain signifanct but no rapid worsening of the conflict or onset of major disaster or disease outbreaks to cause significant situational deterioration. Vulnerable and targeted populations remain accessible only through the UNHAS; INSO continues to enjoy license to operate from security agencies (I)NGOs continue to be allowed to operate in the BAY states Donor funding is received from other donors to maintain budgets UK interest in the North East, Nigeria and the humanitarian response remains strong and signifant
Impact Weighting |  |  | Achieved |  | 97% | N/A | N/A
40% |  |  |  | Source & Means of verification
WFP ACR 2022
| Outcome Indicator 2.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of supported organisations that strongly agree with the statement – “INSO Nigeria services are relevant and useful and improve my NGOs understanding of security environment" | INSO | Planned | 74% | >75% | >75% | >80%
|  |  | Achieved |  | TBC
Source & Means of verification
Baseline - 2022 INSO Partners Satisfaction Survey; Future measures - Annual INSO Partners Satisfaction Survey
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  |  | 0 | 0 | 0 | 100%
OUTPUT 1 | Output Indicator 1.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 (cumulative ) | Target (date) - Sept 2025 | Assumptions and Risks
The delivery of more predictable and impactful food assistance in NE Nigeria | Number of people receiving food assistance broken down by type of transfer | WFP ICRC | Planned | 336019 | WFP: 82,063 ICRC: 0 | WFP: 300,000 ICRC: 18,000 | 400000 | Limited political and military interference in partners activities The targeted sites for this action will remain accessible throughout the delivery period. Complementary services and items such as healthcare, protection is provided by other actors. Cash transfer beneficiaries know optimal use of the fund for their households. Cash transfers do not worsen inflation. Regulatory controls on ATF, AML and IFF are fully adhered to and risks properly mitigated.
|  |  | Achieved |  | WFP: 80,280 ICRC: 25,103 | WFP: Tot. 292,907 from 111,333 (2023) + 80,280 (2022) + 101,294 (2022) ICRC: Tot. 35,153 from 10,050 (2023) + 25,103 (2022) + 38,833 (2022) | WFP: Tot. 402,706 from 109,799 (2024) + 111,333 (2023) + 80,280 (2022) + 101,294 (2022) ICRC: Tot. 79,472 from 5,486 (2024) + 10,050 (2023) + 25,103 (2022) + 38,833 (2022)
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number Percentage of people receiving CBT, including percentage of WFP CBT provided as MPCA | WFP ICRC | Planned | 304021 | WFP: 140,738 ICRC: 0 | WFP: 150,000 ICRC: | 180000
|  |  | Achieved |  | WFP: 101,294 ICRC: 38,833 | WFP did not provide cash as modality of CBT only value vouchers. | WFP did not provide cash as modality of CBT only value vouchers.
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of cash assistance delivered as direct cash transfers | WFP | Planned | 0% | 5% | 7% | 10%
|  |  | Achieved |  | 2.5%
Source & Means of verification
Baseline - ACA PCR; Future measures - WFP Annual ACR reports (as proportion of contributions to NE results) - ICRC Annual Reports
| Output Indicator 1.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of households reached by HARP covered by the government cash transfers (National Social Registry) | WFP UNICEF | Planned | n/a | 5000 | WFP: 10000 UNICEF: 3000 | 30000
|  |  | Achieved |  | In prep | UNICEF: 4000 | In line with the recommendation from the previous annual review, this indicator will no longer be tracked
Source & Means of verification
UNICEF MINA Output Indicator 1.2 (Baseline and future measures) - WFP numbers to be added (simple summation approach)
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 (cumulative) | Target (date) - Sept 2025 | RISK RATING
25% | Number of women in selected households receiving gender-sensitive cash/voucher assistance | WFP CARE UNICEF | Planned | UNICEF: 0 CARE: 0 | UNICEF: 5,000 CARE: 200 | UNICEF: 10,000 CARE: 500 | UNICEF: 20,000 CARE: 500 | Eager
|  |  | Achieved |  | In prep | UNICEF: 14,789 CARE: 889 | UNICEF: 17,460 CARE: 8,892
Source & Means of verification
UNICEF MINA Output Indicator 1.1 (Baseline and future measures) + CARE Output Indicator 1.3 (Baseline and future measures) - WFP numbers to be added (simple summation approach)
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
OUTPUT 2 | Output Indicator 2.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Improve nutrition outcomes in children, adolescents and women in Northeast Nigeria through a gender transformative, inclusive, multi-sectoral response | Monthly average number of children 0 to 59 months screened for acute malnutrition across the NE and number newly admitted at OTP/SC for SAM treatment -outpatient and inpatient (Gender disaggregated) | UNICEF | Planned | 600000 | 600000 | 700000 | 700000 | Supply of nutrition commodities are secured and such devliery is at quality, within cost and on time. Service providers are available to provide quality care, counselling and training services when due. Beneficiaries/communities are open to positive social behaviour change to improve nutritional outcomes. Communities and local leaders support the project and actively participate in project activities. PLW have self-efficacy to support interventions and personally practice better behaviours for improved nutritional ooutcomes. State governments provide adequate support to treatment centres and campaigns in a timely manner and releases funds for operational costs promptly. Cash transfer beneficiaries know optimal use of the fund for their households and it does not worsen GBV incidents. Availability of WASH materials to provide services sustainably. Medical supplies chain remains significantly operational through delivery period, Community motivated to own, use and maintain WAS and Health Facilities. State governments provide adequate support to treatment centres and campaigns in a timely manner and releases funds for operational costs promptly. Service providers are available to provide quality care and support services when due. Communities and local leaders support the project and actively participate in project activities. Communities are willing to take ownership of the development process and will commit resources to its sustainability Beneficiaries/communities are open to positive social behaviour change to improve nutritional outcomes. The targeted sites remain accessible throughout the delivery period.
|  |  | Achieved |  | 740,518 (407,285 girls and 333,233 boys) | 656,564 children (94%) (boys: 302,019 and girls: 354,545) | 679,780 children were screened monthly 260,348 children were treated for severe acute malnutrition
Source & Means of verification
UNICEF MINA Output Indicator 3.4 (Baseline and future measures)
| Output Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 0 to 59 months being newly admitted at OTP/SC for SAM treatment -outpatient and inpatient. (gender disaggregated). | UNICEF | Planned | 0 | TBC | 45000 | 73074
|  |  | Achieved |  | 26,000 Children identified with SAM were referred to OTPs and treated with nutrition commodities procured with funds from a previous FCDO grant (ACA-RUTF
Source & Means of verification
UNICEF MINA Output Indicator 3.5 (Baseline and future measures)
| Output Indicator 2.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of severely malnourished children <5 years recovered, defaulted and died | UNICEF | Planned | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5% | Recovery rate: >75% Default rate: <15% Death rate: <5%
|  |  | Achieved |  | Not reported on | Recovery rate: 97.7% Default rate: 1.3% Death rate: 0.4% | Recovery rate: 98.6% Default rate: 0.9% Death rate: 0.1%
Source & Means of verification
UNICEF MINA Output Indicator 3.6 (Baseline and future measures)
| Output Indicator 2.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Percentage of children being admitted at OTP/SC as self referral by caregivers/ mothers trained in MUAC screening | UNICEF | Planned | 20% | 25% | 30% | 40%
|  |  | Achieved |  | 24.5% | 33% | 26%
Source & Means of verification
UNICEF MINA Output Indicator 3.3b (Baseline and future measures)
| Output Indicator 2.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of pregnant and lactating women (PLW) and their partners who receive counselling and behaviour change messaging about healthy diets and practices and GBV. | UNICEF | Planned | 0 | 50000 | 100000 | 250000
|  |  | Achieved |  | 48458
Source & Means of verification
UNICEF MINA Output Indicator 2.2 (Baseline and future measures)
| Output Indicator 2.6 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women who attended at least 4 ANC visits by age. | UNICEF | Planned | 205573 | 102787 | 250000 | 380000
|  |  | Achieved |  | 64064
Source & Means of verification
UNICEF MINA Output Indicator 3.9 (Baseline and future measures)
| Output Indicator 2.7 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 6 to 59 months who received Vitamin A supplementation. | UNICEF | Planned | 1500000 | 1500000 | 3000000 | 4500000
|  |  | Achieved |  | 1438993
Source & Means of verification
UNICEF MINA Output Indicator 3.1 (Baseline and future measures)
| Output Indicator 2.8 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children 6 -24 months receiving micronutrient powders. | UNICEF |  | N/A | UNICEF: Procurement initiated but delayed due to global shortage.
In prep
Source & Means of verification
| Output Indicator 2.9 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of children, adolescents and caregivers reached with comprehensive focus mental health and psychosocial support services including life skills education and positive parenting (gender and age disaggregated) | UNICEF | Planned | 345153 | 75000 | 200000 | 250000
|  |  | Achieved |  | 50000
Source & Means of verification
UNICEF MINA Output Indicator 3.12 (Baseline and future measures)
| Output Indicator 2.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 (cumulative) | Target (date) - Sept 2025
| Number of vulnerable people (including families with SAM children, adolescent girls and PLW) in communities and IDP camps gaining access to climate-resilient, gender- and disability-sensitive WASH services and supplies to ensure optimal dietary practices | UNICEF | Planned | 0 | 37500 | 112500 | 150000
|  |  | Achieved |  | 14500 | 59,720 + 14,500 | 138288
Source & Means of verification
UNICEF MINA Output Indicator 2.3 (Baseline and future measures)
| Output Indicator 2.11 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of ODF certified communities | UNICEF | Planned | 0 | 0 | 100 | 120
|  |  | Achieved |  | In prep
Source & Means of verification
UNICEF MINA Output Indicator 2.4 (Baseline and future measures)
| Output Indicator 2.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of HCFs (w/CMAM and/or OTP centers) in target areas provided with access to gender- and disability-sensitive WASH services | UNICEF | Planned | 0 | 5 | 15 | 25
|  |  | Achieved |  | In prep | 15 | 49
Source & Means of verification
UNICEF MINA Output Indicator 3.17 (Baseline and future measures)
IMPACT WEIGHTING (%) |  |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
35%
Receptive
Source & Means of verification
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
|  |  |  | 0 | 0 |  | 100%
OUTPUT 3 | Output Indicator 3.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Protecting people from harm and strengthening humanitarian access. | Number of individuals accessing awareness raising and community based protection mechanisms in target LGAs (by age and gender) | CARE OCHA ICRC | Planned | 0 | 50000 | CARE: 20000 OCHA: ICRC: | 80000 | Limited political and military interference in partners activities. The targeted sites for this action will remain accessible throughout the delivery period. Legal and civil documentation processes are not bogged down by bureaucratic challenges. Participation of women in the program is encouraged through community sensitization of men. Strong rapport with the key community leaders and government stakeholders built for strong coordination and timely support. Services provided are able to meaningfully support individuals and enble confidentiality for increased uptake. Women and girls’ groups are already established and or will be open to establish a group to work on women’s participation/leadership in decision-making spaces The absence of reliable commercial air operators to service currently inaccessible areas continues. Demand from the humanitarian community for enabling services remains strong. Limited political and military interference in partners activities. The targeted sites for this action will remain accessible throughout the delivery period.
|  |  | Achieved |  | 49963 | CARE: 21,630 | CARE: 125,480
Source & Means of verification
Baseline and future measures CARE Output Indicator 1.2. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women and girls targeted/reached with comprehensive GBV case management, psychosocial support, and referral for other specialized services including nutrition, legal, security and justice services and mechanisms (age disaggregated) | CARE OCHA ICRC | Planned | 0 | 75 | CARE: 125 OCHA: 300 ICRC: 200 | CARE: 125 OCHA: 300 ICRC: 200
|  |  | Achieved |  | 551 | CARE: 168 OCHA: 2,210 ICRC: 616 | CARE: 1,190 OCHA: XXX ICRC: 825
Source & Means of verification
Baseline and future measures CARE Output Indicator 1.1. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of beneficiaries who can identify and act upon protection concerns I'm not sure what this means and how efectively it can be measured! | CARE OCHA ICRC | Planned | 0 | 150 | 300 | 300
Achieved
Source & Means of verification
Baseline and future measures CARE Outcome Indicator 2.3. ICRC and OCHA Indicators TBC. (Simple summation approach)
| Output Indicator 3.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of Gynaelogical/obstetric admissions | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of missing persons tracing cases still being handled at the end of the reporting period (W&G) | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.6 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of unaccompanied minors/separated children cases being supported (girls figure available) | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.7 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of women and girls detainees visited | ICRC | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.8 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of womens' groups trained to meaningfully influence decision makers or local authorities or traditional leaders at LGAs relevant with GBV and SRH rights and services.This is broadly similar to inidcator 3,.2 | CARE | Planned | 0 | 5 | 10 | 10
Achieved
Source & Means of verification
Baseline and future measures CARE Output Indicator 2.2.1
| Output Indicator 3.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of individuals trained to support inclusive & safe protection services, awareness raising and drive social changes (paralegals, project staff, community structures, men and boys and health providers). | CARE | Planned | 0 | 450 | 690 | 690
|  |  | Achieved |  |  | 455 | 675
Source & Means of verification
Baseline and future measures CARE LF - Summation of Output indicator 1.4, Output indicator 1.2.1, Output indicator 2.1.1 and Output Indicator 2.1.2
| Output Indicator 3.4 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of passenger journeys funded by FCDO and as a proportion of total journeys | UNHAS | Planned | 3791 | 3791 | 5000 | 5500
|  |  | Achieved |  | 2887 | 4090 | 7729
Source & Means of verification
Baseline - Dec 2022 UNHAS steering committee report; future measures - WFP Annual ACR (as proportion of contributions to NE results), Activity 9, Output 15
| Output Indicator 3.11 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Size in MT of commodities transported by UNHAS supported by FCDO funding | UNHAS | Planned | 13.24 | 13 | 15 | 17
|  |  | Achieved |  | 11.2
Source & Means of verification
Baseline - Dec 2022 UNHAS steering committee report; future measures - WFP Annual ACR (as proportion of contributions to NE results) Activity 9, Output 15
| Output Indicator 3.12 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Proportion of passsenger bookings successfully fulfilled/served | UNHAS | Planned | 80% | 80% | 85% | 90%
|  |  | Achieved |  | 88%
Source & Means of verification
Future measures - WFP Annual ACR (as proportion of contributions to NE results), Activity 9, Output 15
| Output Indicator 3.5 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of organisations in NE Nigeria supported by INSO with safety coordination, training and advisory services | INSO | Planned | 70 | 71 | 73 | 75
|  |  | Achieved |  | 111 | 111 | 114
Source & Means of verification
INSO annual reports
IMPACT WEIGHTING (%) |  |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
30% | Proportion of supported organisation who received basic and/or advanced security management trainings delivered by INSO during the year. Number of organisations and participants receiving INSO training | INSO | Planned | N.a | 95% | 95% | 100% | Receptive
Achieved
Source & Means of verification
INSO annual reports
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
Planned
Achieved
Source & Means of verification
| Output Indicator 6.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Planned
Achieved
Source & Means of verification
IMPACT WEIGHTING (%) | Output Indicator 6.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
Planned
Achieved
|  |  | Source & Means of verification |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4.1 | Output Indicator 4.1 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | Assumptions and Risks
HARP cultivates a more localised response in NE Nigeria that is informed by learning and fully responsive to spikes in need | Proportion of annual HARP spend (including FCDO contribution to NHF) directed to local CSOs/NGOs | WFP, UNICEF, OCHA, CARE and Clear Global | Planned | Baseline year for reporting | Baseline year for reporting | 25% | 35% | UK political will and reputational capital to continue engaging in the N/East to deliver basic services and (re)build infrastructure in the longer term remains adequate. There is opportunity for meaningful UK engagement with partners and state actors who have capacity to deliver. Partners are supportive of the multisector localisation and inclusive agenda.
|  |  | Achieved |  | N/A | 30% | 38%
Source(s) of verification
All partner reporting
| Output Indicator 4.2 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number/frequency of independent third party programme monitoring and verification visits undertaken | CG | Achieved | 2 | 4 | 4 | 4
[5 empty] | 3 | NA | 6
Source(s) of verification
All partner reporting
| Output Indicator 4.3 |  |  | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| Number of partners reporting improvements in: a) programme design and delivery; b) adherence to best practise and c) fundraising as a direct result of Third Party monitoring and verification visits | CG | Planned | 9
Achieved
Source(s) of verification
OCHA NHF annual reporting
| Output Indicator 4.5 |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025
| CBPFs allocation processes have an appropriate duration | OCHA | Achieved | N/A | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average. | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average. | Standard Allocation projects are processed (from the submission deadline to the HC signature) within 30 days on average.
Standard Allocation projects were processed (from the submission deadline to HC signature) within 30 days on average
Source(s) of verification
OCHA NHF annual reporting
IMPACT WEIGHTING (%) |  |  | Planned | Baseline (2022) | Milestone 1 - Sept 2023 | Milestone 2 - Sept 2024 | Target (date) - Sept 2025 | RISK RATING
| CBPFs have a significant funding level to support the delivery of the HRPs | OCHA | Achieved | N/A | 15% of HRP funding received through the CBPF | 15% of HRP funding received through the CBPF | 15% of HRP funding received through the CBPF | Receptive
4.1% of HRP contribution to received through the CBPF
Source(s) of verification
OCHA NHF annual reporting
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)