Programme Completion Review

Title: Building Resilience in Nigeria’s Nutrition Stockpile (BRINNS) Programme
Final Programme Spend £ (full life): £10,805,960	Review Date:	June 2025
Programme Code: 400130	Start Date: 15 January 2024	End Date: 31 March 2025

Summary of Programme Performance

Year	2024/2025
Programme Score	A+
Residual Risk Exposure Rating	SEVERE (Eager)

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/D0004867.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0006177.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The Building Resilience in Nigeria’s Nutrition Stockpile (BRINNS) programme was a short-term, capital-funded intervention to strengthen Nigeria’s nutrition supply chain. It ran from January 2024 to March 2025 with a final budget of £10.8 million and was delivered by UNICEF under a single-partner model.

BRINNS aimed to reduce gaps in the availability of Ready-to-Use Therapeutic Food (RUTF) by establishing a national stockpile. RUTF is a high-energy, nutrient-rich paste used to treat children with severe acute malnutrition. The programme focused on supply chain resilience rather than direct service delivery, complementing existing humanitarian programmes. Over 247,000 cartons of RUTF were procured and pre-positioned across four sites, exceeding the original target. This helped smooth supply across the year and enabled rapid deployment to areas of greatest need.

The programme also upgraded three government-owned warehouses in Kaduna, Sokoto and Zamfara. These were equipped with racking systems, solar power and handling equipment to improve storage and last-mile delivery. A standard operating procedure was developed to guide stock management, activation and replenishment.

Five activations were carried out in response to emergencies in six northern states. Nearly 300,000 cartons of RUTF were distributed, helping to maintain continuity of treatment for children with severe acute malnutrition.

BRINNS supported the UK’s commitment to end preventable deaths by 2030. It aligned with FCDO’s humanitarian strategy by prioritising the most vulnerable, protecting at-risk populations and preventing malnutrition. All RUTF was sourced from certified Nigerian manufacturers, supporting local industry and reducing delivery times.

Although BRINNS did not involve direct contact with beneficiaries, it played a vital role in sustaining life-saving nutrition services. It demonstrated the value of capital investment in humanitarian supply chains and offers a model for future emergency preparedness and supply chain improvement in Nigeria and beyond.

Major lessons learned, evidence generated and recommendations

BRINNS demonstrated that capital investment in humanitarian supply chains can deliver rapid, cost-effective results in fragile contexts. The programme confirmed that pre-positioned stockpiles of Ready-to-Use Therapeutic Food (RUTF) significantly reduce lead times and prevent stock ruptures. Five activations were completed during the year, and no stock-outs were reported in the targeted humanitarian states. This ensured continuity of life-saving nutrition services for children with severe acute malnutrition.

A key lesson was the value of a clear and jointly developed standard operating procedure (SOP). This ensured consistent management of the stockpile, including activation and replenishment. The SOP was co-designed by UNICEF’s programme, logistics and finance teams, and proved essential to operational efficiency.

Flexibility in delivery was also critical. The programme adapted to changes in infrastructure availability, including the reallocation of warehouse upgrades from Maiduguri to Sokoto and Zamfara mainly due to changes in host government provision of specific buildings. These adaptations were agreed with FCDO and improved geographic coverage and operational reach, although they did contribute to some delays in finalising warehouse upgrade plans. A further recommendation is this area would be to ensure that the full scope of infrastructure works is clearly defined at the outset, ensuring FCDO’s ability to scrutinise delivery risks early on. Future programmes should ensure that infrastructure components are fully scoped and costed before mobilisation, with clear milestones and contingency plans in place.

Reporting systems worked well and were light touch given the short duration and narrowly defined scope of the programme. Frequent, short updates provided to the FCDO team were of high value and ensured close monitoring without an undue burden of narrative reporting on the partner. Early discussions on allowable costs for capital funding and guidance provided by the FCDO team on treatment of issues such as asset creation, budgeting, management and monitoring approaches helped to clarify the nature of the funding and how it differs from resource funding.

The programme also highlighted the importance of strong local procurement. All RUTF was sourced from certified Nigerian manufacturers, reducing costs, improving delivery times, and supporting local capacity. Any similar programmes would benefit from fully exploiting local procurement opportunities, avoiding international importation which may make delivery timeframes uncertain.

Future programmes could consider embedding capital investment in supply chain resilience as a core component of humanitarian response. Stockpiling should be linked to clear governance mechanisms and replenishment strategies. FCDO should continue to advocate for government co-financing through the Child Nutrition Fund to sustain these gains. An open question remains on whether a separate CDEL programme such as BRINNS is more effective than combining capital funding into existing programmes such as those delivering humanitarian support with more typical resource (RDEL) funding. BRINNS usefully advanced independently of other programmes and at pace, with momentum generated by its short-term nature, but this did put pressure on delivery in areas which were new for both FCDO and UNICEF.

Possible next steps to develop and disseminate learning and recommendations internally include: participation in the PMEL synthesis review of all CDEL programmes within FCDO Nigeria; presentation of BRINNS’ results in FCDO Nigeria’s programme delivery Board; presentation to the humanitarian cadre. Further discussion will take place with UNICEF to document lessons learned and assess whether a programme such as BRINNS could be appropriate in other contexts. It may be possible to assist UNICEF in developing materials to propose adaptations to similar programmes based on the experience in Nigeria. There may be opportunities to assess effective strategies to further prolong the sustainability of the stockpile by discussing modes of handover to government in future.

This review is kept short by intent due to the short-term nature of the programme and the fact that it delivered on capital (CDEL) funding. The programme did not directly interact with beneficiaries or those in humanitarian need but worked on underlying supply chain issues affecting the efficiency and effectiveness of the humanitarian response in Nigeria. The review draws on regular programme monitoring experience, reporting from UNICEF and the programme team’s overall assessment of the success of BRINNS.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£9,945,000	£10,805,960
Timeframe	January 2024 – March 2025	As expected
Outcomes	The concept note suggested: / This programme proposes to create up to a three-month strategic stockpile of RUTF which will allow: / A stabilised supply chain / Increased prepositioning and fewer stock-outs / Rapid delivery, reduced transport and logistics costs / Increased confidence in supply allowing more ambitious nutrition treatment targets.	The logframe’s outcome level statement was finalised as: / By 2025, malnutrition is addressed by prepositioning life-saving nutrition commodities (RUTF) to ensure no break in the UNICEF managed pipeline by establishing a stockpile asset of RUTF

The BRINNS programme achieved its intended outcome of improving the efficiency and reliability of Nigeria’s nutrition supply chain. It was designed as a capital investment to establish a strategic stockpile of Ready-to-Use Therapeutic Food (RUTF), with the aim of reducing stock-outs, smoothing procurement cycles, and enabling faster response to emergencies. The programme was not intended to deliver direct treatment services, but to strengthen the enabling environment for nutrition programming.

By the end of the programme, 247,157 cartons of RUTF had been procured, exceeding the target of 240,000. Five activations were carried out in response to emergency triggers, releasing 298,000 cartons to partners across six high-burden states. These activations were guided by a new Standard Operating Procedure (SOP), developed and institutionalised during the programme. Three warehouses were upgraded, against a target of two, improving national storage capacity and enabling pre-positioning closer to areas of need. The programme fell slightly short of its outcome indicator, with 87 per cent of the four-month stockpile established. This was due to delays in warehouse readiness and replenishment funding.

The programme has laid a strong foundation for sustainability. Local procurement through long-term agreements with Nigerian manufacturers reduced lead times and costs, while also supporting domestic production capacity. The SOP and governance structure for stockpile activation are now embedded in UNICEF’s systems. However, sustainability will depend on continued donor support and increased domestic financing, particularly through the Child Nutrition Fund.

BRINNS delivered good value for money with local procurement in Nigeria supporting the Nigerian manufacturing base, and delivering shortened lead times to as little as two weeks. In addition, the programme was able to leverage incoming supplies procured by other partners for the nutrition pipeline, benefitting the humanitarian response beyond UK support. A major efficiency achievement was to reduce procurement lead times from three months to as little as two weeks. UNICEF’s flexible delivery model allowed the programme to absorb additional funding within the year, responding to both operational capacity and the growing burden of malnutrition. All output targets were met or exceeded.

The programme adapted well to contextual challenges, including flooding, disease outbreaks, and changes in government leadership. Delays in warehouse upgrades were mitigated through revised timelines and reallocation of resources. One lesson is the need for clearer infrastructure planning at the outset. UNICEF’s mid-programme changes to warehouse locations reduced FCDO’s ability to scrutinise delivery risks and contributed to delays.

Overall, BRINNS delivered strong results within budget and timeframe, and demonstrated the value of capital investment in humanitarian supply chain resilience.

The BRINNS programme was designed to address chronic supply chain bottlenecks affecting the treatment of severe acute malnutrition (SAM) in Nigeria. The theory of change was based on the premise that a capital investment in a national stockpile of Ready-to-Use Therapeutic Food (RUTF) would reduce stock-outs, shorten procurement lead times, and enable a faster and more predictable response to emergencies. This would help stabilise the nutrition pipeline and support the continuity of life-saving services.

The programme assumed that local manufacturers could meet demand, that pre-positioned stock would be accessible when needed, and that government and donor systems would be able to sustain the stockpile once established. These assumptions were broadly valid. However, the programme was implemented in a context of rising need. The national SAM burden increased from 2.6 million in 2023 to 3.5 million in 2024. This placed additional pressure on the RUTF pipeline and tested the programme’s capacity. The logic of the programme held, but the scale of demand highlighted the need for greater flexibility and sustained investment.

The results framework remained unchanged. The outcome indicator focused on the establishment of a four-month national stockpile. By March 2025, 87 per cent of this target had been achieved. This was due to delays in warehouse readiness and replenishment funding, particularly in the North-West. All output targets were met or exceeded. These included procurement of 247,157 cartons of RUTF (target: 240,000), five activations (target: four), and three warehouse upgrades (target: two).

The programme was designed to be adaptive. UNICEF and FCDO held regular check-ins to review progress and agree changes. When the Maiduguri warehouse was reclaimed by the state government, UNICEF pivoted to upgrade facilities in Sokoto and Zamfara. These changes were agreed with FCDO and improved geographic coverage. The SOP for stockpile management was developed collaboratively and proved critical to operational success.

The programme score of A+ reflects strong delivery against outputs and a credible contribution to the intended outcome. The experience of BRINNS reinforces the case for capital investment in humanitarian supply chains, particularly in high-risk, high-need settings.

## C: Detailed Output Assessment

Output Number and Title	Procure nutrition commodities to establish the national stockpile asset
Output Score	A+
Impact weighting (%)	25%		Impact weighting revised since last AR?	n/a

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Number of cartons of RUTF procured		170,000	240,000	247,157

Output 1 delivered the procurement of 247,157 cartons of Ready-to-Use Therapeutic Food (RUTF), exceeding the end-of-programme target of 240,000. All commodities were sourced from certified Nigerian manufacturers under long-term agreements. Procurement was phased to align with warehousing capacity and anticipated activation needs. Progress was monitored through UNICEF procurement reports and regular FCDO engagement. Despite inflation and rising demand, the output was delivered in full and on time. The score of A+ reflects strong performance against target and effective delivery in a challenging operating environment.

Lessons learned through this output, and recommendations for future programming

The procurement of RUTF from local manufacturers proved effective. It reduced lead times and allowed for timely delivery to warehouses. UNICEF’s long-term agreements with suppliers helped secure better prices and ensured quality. This approach also supported local industry and reduced reliance on international supply chains.

BRINNS benefitted from earlier investments in RUTF manufacturing in Nigeria, including with extensive capacity building and quality advice from UNICEF and UK investments via the Manufacturing Africa programme and other nutrition programmes which supported a transition from international to local procurement. A key lesson seen during BRINNS was the value of early engagement with manufacturers. By sharing forecasts and timelines, UNICEF enabled suppliers to plan ahead and pre-position raw materials. This helped avoid delays. Future programmes should continue this practice and consider formalising quarterly planning meetings with suppliers. It is also recommended to maintain flexibility in warehouse selection, as seen in the shift from Bauchi to Kaduna, to adapt to operational realities.

Output Number and Title		Activate stockpile asset using established SOP
Output Score		A+
Impact weighting (%)		25%	Impact weighting revised since last AR?	n/a

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Number of stockpile activations per quarter	4 activations per year		4 activations per year	5 activations

Lessons learned through this output, and recommendations for future programming

Considering the very short timeframe of the programme, including time needed for design and initial procurement, the rhythm and number of activations of the stockpile was highly successful with the first already completed in July 2024. UNICEF made systematic efforts to ensure that the system was clearly defined and responsive. The use of a standard operating procedure helped ensure that activations were timely and well-managed. Five activations were carried out, exceeding the target of four.

A key lesson was the importance of clear governance. The process for requesting and approving activations was well-defined, with roles clearly assigned. This helped avoid delays. For future programmes, it is recommended to maintain this structure and ensure that all partners are trained on the SOP. It may also be helpful to review the SOP annually to reflect any changes in context or lessons from use. The management of the stockpile took into account the high and growing needs for malnutrition treatment in Nigeria, including the risks identified in the business case that the demand on the stockpile would make its longer-term existence difficult to sustain. It is notable that even after the formal closure of the programme, UNICEF is still operating the stockpile in line with existing protocols, demonstrating its sustainability.

BRINNS was able to release stock in advance of confirmed replenishments, based on strong indications of incoming support from other humanitarian donors, harnessing resources beyond the UK’s initial investment in BRINNS, multiplying the stockpile’s effectiveness and benefitting the humanitarian response more widely.

Output Number and Title		RUTF released to respond to triggers
Output Score		A+
Impact weighting (%)		25%	Impact weighting revised since last AR?	n/a

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Quantity of RUTF released	n/a this was a newly added output in the final logframe		198,000	298,000 cartons – which was always less than the 80% mentioned below

Lessons learned through this output, and recommendations for future programming

This output was tracked to ensure that stock was not released in its entirety from the stockpile. The aim was that the maximum amount of stock released should be less than 80% of the warehouse stock at any one time. The amount of RUTF released exceeds the quantity procured with FCDO funding alone, due to replenishment from other partners, indicating successful management of the stock.

Output Number and Title		Existing warehouses upgraded
Output Score		A+
Impact weighting (%)		25%	Impact weighting revised since last AR?	n/a

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Warehouse Capacity Upgraded	2		2	3

Lessons learned through this output, and recommendations for future programming

The warehouse upgrades were delivered, though not without challenge. Flexibility was key: one site was changed due to government reprioritisation, and two others were completed using a mix of FCDO and other funds. Delays in procurement and shipping of equipment, such as racking and forklifts, slowed progress. Future programmes should allow for early engagement with state authorities and suppliers, and build in time for import delays. Where possible, sourcing equipment locally would reduce risk and improve delivery speed.

D: Value for Money

The programme performed well in Value for Money terms. As well as being rapidly mobilised, the stockpile is still in good health after the formal end date of the programme, and still releasing from the stockpile in the midst of Nigeria’s 2025 lean season.

Economy: All RUTF was procured from local manufacturers, as planned. This avoided international freight costs and supported Nigeria’s production base and jobs. Local procurement avoided an estimate of USD $10 per carton in purchase and international freight costs, before costs of transport within Nigeria by road were taken into account. Prices remained stable, and long-term agreements helped manage risk.

Efficiency: Procurement lead times were reduced from three months to as little as two weeks, enabling faster emergency response and avoiding costly last-minute transport. The SOP streamlined logistics and ensured timely stock release. UNICEF’s flexible delivery model allowed the programme to absorb additional funding within the year, responding to both operational capacity and the growing burden of malnutrition.
Effectiveness: All output targets were met or exceeded. The stockpile was established, activated five times, and used to release nearly 300,000 cartons of RUTF. Three warehouses were upgraded instead of two. These results strengthened the resilience of the nutrition supply system and improved emergency response.
Equity: The programme focused on the North-East and North-West, where needs are highest. However, stock-outs in the North-West show that gaps remain, especially where routine pipelines are weak. UNICEF data shows girls made up 54% of admissions, and disability inclusion was mainstreamed.
Cost-effectiveness: The stockpile helped avoid delays and reduced the need for inpatient care. The original theory of change held true. The programme was able to absorb £860,960 in additional funding during its short lifespan, ensuring that UK CDEL funds were maximised to support the lifesaving malnutrition supply chain.
E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The programme operated in a high-risk environment, consistent with the original risk appetite. The overall risk rating was severe, reflecting the volatile context in northern Nigeria and the fiduciary risks associated with humanitarian delivery. The programme was also novel and a learning experience for both UNICEF and FCDO. Despite this, and despite challenges in insecurity, flooding and changes in the international funding landscape, the programme was delivered without major incident.

The main contextual risks were insecurity, displacement, and disruption to supply chains. These were managed through flexible delivery arrangements, regular engagement with state authorities, and the use of multiple warehouse locations. The decision to procure RUTF locally reduced exposure to international shipping delays and customs issues. Some of the lessons learned around the feasibility of infrastructure works and warehouse improvements in very short timeframes include that early planning and infrastructure considerations should be integrated from the early stages of implementation. This proactive approach helps to avoid disruptions caused by sourcing and logistics delays.

Managing a large grant of capital funding was challenging in the context of delivery of other large programmes but facilitated by frequent and informal conversations between the FCDO programme team and the partner, by frequent consultation with FCDO’s internal delivery and strategy unit in Nigeria and by setting down expectations clearly in informal guidance on how management of capital funding differed from the typical humanitarian and development funds that UNICEF was more accustomed to receiving in such settings. UNICEF drew in expertise and various teams appropriately, ensuring a team effort between nutrition, logistics and field teams and benefitted from working on CDEL funding with other FCDO Nigeria teams.

The programme remained within risk appetite throughout. There were no formal amendments or early closure. The upgraded warehouses have been handed over to state governments, who have committed to staffing and maintenance. UNICEF is working with partners to sustain the stockpile and explore further solarisation. These steps support a responsible exit and improve long-term resilience.

Sources include UNICEF’s final report, internal FCDO risk registers, and partner due diligence records.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

The programme had an approved core budget of £7 million, with an additional headroom of up to £5 million, making a total potential budget of £12 million. Following budget confirmation in March 2024, an agreement of £9.94 million was signed with UNICEF, with a further uplift of £860,000 in the third quarter of the 2024/25 financial year. UNICEF was able to fully expend 100% of the total funding (£10,805,960) as at programme closure, with 87% (£9,459,350.13) of the project value expended on the purchase of supplies and commodities. In addition, of a targeted 240,000 cartons of RUTF envisaged at design, UNICEF has been able to successfully order 247,157 cartons of RUTF, representing an overperformance. Disbursements were in three tranches – each made following confirmation of full or substantial utilisation of funds. During implementation, UNICEF remained a very responsive partner, providing information or meeting availability as needed.

A rigorous monitoring approach, which was agreed with the partner, was embedded throughout the programme. At the design stage, a standard operating procedures document specifically for the procurement, supply management and replenishment of the stockpile was developed by UNICEF and agreed with FCDO. Furthermore, considering the innovative nature of the programme, UNICEF were asked to and successfully provided regular in-person updates and slides to explain progress, on a much more frequent basis than other RDEL-funded programmes. These check-ins enabled FCDO and UNICEF to review progress, discuss risks, and agree on adaptations. These meetings were used to track delivery against the logframe and inform funding decisions. Conversations around BRINNS were also situated within the FCDO’s existing knowledge and understanding of the malnutrition pipeline, informed by UNICEF and other malnutrition partners who were able to provide informal views on the health of the supply chain. The monitoring approach was proportionate and effective for a short-duration programme.

Date of last narrative financial report	1 July 2025	Date of last audited annual statement	2023