## Annual Review Template

Title: Mozambique Humanitarian Response Plan
Programme Value £ (full life): £38.74m		Review date: 14/12/2025
Programme Code: 301363	AMP start date: 25/02/2022	AMP end date: 31/05/2027

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301363 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301363 Documents (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW

Description of programme

The Mozambique Humanitarian Response Programme (MHRP), launched in May 2022, is designed to provide lifesaving assistance to people affected by conflict and climate-related disasters, while also strengthening humanitarian systems for more effective and timely responses. The programme is structured around four multi-year partnerships and one technical assistance component. Delivery partners include the International Organization for Migration (IOM) for shelter and health, the World Food Programme (WFP) for food security and anticipatory action, the Norwegian Refugee Council (NRC) for protection and legal identity, and the International NGO Safety Organisation (INSO) for access and security coordination. The programme is underpinned by flexible funding, allowing partners to scale up rapidly in response to emergencies and invest in preparedness.

This report covers April 2024 to March 2025, a period during which the country experienced a sharp escalation in conflict and displacement in the north and three intense cyclones struck within just two months, causing widespread destruction and humanitarian need. Over one million people in conflict-affected areas remained reliant on humanitarian assistance, with limited access to basic services and livelihoods. The scale and overlap of these crises placed immense pressure on humanitarian actors, further compounded by a temporary national shutdown due to post election violence. In response to the growing needs, particularly related to cyclones, the UK provided a £5 million uplift to the programme to support the cyclone response and increased displacement.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme has scored an ‘A+’ based on excellent partner performance, flexibility, and strong prioritization of response despite the difficult operating environment. All partners remained responsive, rapidly adapting to the evolving context and the MEAL platform made operational. The cyclone response was delivered at the same time as a major increase in conflict-related needs, with partners absorbing the £5 million uplift at speed—even during the post-election political violence which saw the risk of politicization of aid.

However, these achievements must be viewed against a deteriorating backdrop. Global aid cuts, the humanitarian reset, coordination challenges, and worsening conflict have constrained improvements in coverage and quality. While UK support enabled some localized gains—such as anticipatory action protocols and pooled funds—the overall trajectory of the humanitarian response remains precarious. System-wide effectiveness is not improving at the same pace as programme-level delivery, and gains are fragile without sustained investment and access.

The year also saw the successful launch of two new pooled funding mechanisms focused on localizing responses. As the founding donor to both, the UK played a catalytic role in getting them off the ground and attracting other donors, helping to shift more resources and decision-making power to local actors. Though both have been operational for less than half of the review period, they are showing solid progress.

The programme also made important progress on anticipatory action, particularly through WFP’s work to integrate anticipatory action protocols with government-led social protection. This approach proved valuable in responding to both drought and cyclones, allowing for faster and more targeted assistance. However, applying similar models in conflict settings was challenging due to GoM concerns over risk of diversion of aid. Partners continue to advocate for more cash assistance in conflict areas. The ability of key partners to pivot quickly and maintain delivery under pressure highlights the strength of the programme’s design and the importance of flexible, well-managed funding.

Some highlights on results include:
- People reached: 427,437 people reached with humanitarian assistance against target of 400,000.
- Prioritization: Based on vulnerability-based targeting (VBT) lists in priority districts, 80% of households assessed as most vulnerable received multisectoral assistance, exceeding the 60% target
- Localisation: 24 national NGOs supported via pooled funds (OCHA & IOM) through 22 projects
- Protection: 20,000+ birth certificates/IDs issued; 67% beneficiaries accessed essential services; 6,920 people received psychosocial support.
- Security: 94% of NGOs reported improved safety planning; 129 staff trained, majority from local organisations.
- Enabling environment; Anticipatory action protocols were embedded in Mozambique’s national emergency plan, enabling faster cyclone response and proving the model works.

Major lessons and recommendations for the year ahead

1. Improved accountability systems
  1. All partners’ beneficiary feedback mechanisms should undergo a comprehensive review in the coming year to assess how feedback is influencing programme adaptations. The BHC Maputo Humanitarian Team should consolidate findings across partners to identify trends and ensure that corrective actions are documented and implemented, particularly in light of gaps highlighted by third-party monitoring of IOM interventions.
2. Transition of anticipatory action to Social Protection
  1. The anticipatory action component currently managed by WFP should be fully transitioned to the BHC Social Protection programme by the end of 2025 to ensure sustainability and integration with national systems. This transition will require clear timelines, coordination with government stakeholders, and alignment of protocols to maintain continuity of early warning and response mechanisms.
3. Strengthen coordination between pooled funds and security services
  1. Coordination between OCHA and IOM pooled funds should be formalized and linked more closely to cluster systems to improve complementarity and efficiency. Additionally, stronger collaboration with INSO is needed to integrate security considerations into pooled fund operations, ensuring safe and timely delivery in high-risk areas.
4. Enhance disability inclusion in monitoring and programming
  1. The programme should apply a disability inclusion marker in the next reporting cycle, with MEAL partner integrating disability-specific indicators and barriers analysis.
  2. The BHC team should request the MEAL partner to prioritize disability inclusion in its monitoring framework, with a specific focus on identifying access barriers and service gaps for persons with disabilities. This review should inform partner-level adaptations and ensure that inclusion commitments are consistently met across all interventions.
5. Logframe review to strengthen effectiveness indicators
  1. Next year’s logframe review should incorporate indicators that measure the speed, effectiveness, and complementarity of pooled funds and the MEAL component. These additions will provide a clearer picture of how localization and monitoring systems contribute to overall programme performance and value for money.
6. Fraud and safeguarding:
  1. Strengthen fraud and safeguarding reporting by introducing a joint donor review mechanism for pooled funds and requiring partners to submit consolidated case data quarterly.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

While the programme remains broadly on track against its own objectives, the wider humanitarian response in Mozambique—and globally—is not improving. Funding cuts, the humanitarian architecture reset, coordination challenges, and worsening conflict have eroded system-wide effectiveness and coverage. These factors constrain improvements in coverage and quality, meaning that gains achieved through MHRP are fragile and risk reversal without sustained investment and access. Progress towards outcomes should therefore be interpreted cautiously given the deteriorating operating environment and systemic constraints.
These trends pre-date the review period but intensified during it, leaving the overall trajectory precarious.

Within this deteriorating environment, MHRP has delivered against a narrower but critical criterion: providing lifesaving assistance to the most vulnerable and enabling rapid scale-up during overlapping crises. The programme’s flexibility, anticipatory action work, and pooled funding mechanisms allowed partners to respond quickly and maintain delivery despite insecurity, political volatility, and shrinking humanitarian space. These gains are significant but fragile, and should not be interpreted as evidence of systemic improvement.

The programme aims to achieve two Outcomes:
- Increased effectiveness of humanitarian response
- Improved quality and coverage of priority needs
These are delivered through four interlinked Outputs:
- Improved operating environment for safer, more effective delivery
- Prioritised assistance for the most vulnerable
- Improved coordination and leadership for system-wide efficiency
- Rapid and effective emergency response during crises

The Mozambique Humanitarian Response Programme (MHRP) is guided by a Theory of Change that recognises the importance of flexible, timely, and well-coordinated humanitarian funding. When combined with efforts to strengthen national systems, this enables more effective and equitable assistance for people affected by conflict and climate-related crises. The intended impact is to reduce suffering for conflict- and disaster-affected communities in Mozambique.
The programme aims to achieve two Outcomes:
1. Increased effectiveness of humanitarian response
2. Improved quality and coverage of priority needs

These are delivered through four interlinked Outputs:
1. Improved operating environment for safer, more effective delivery (supports Outcome 1)
2. Prioritised assistance for the most vulnerable (supports Outcome 2)
3. Improved coordination and leadership for system-wide efficiency (supports both Outcomes)
4. Rapid and effective emergency response during crises (supports both Outcomes)
Since inception in 2022, the Theory of Change and outcome/impact indicators have not changed, but the context has evolved significantly. The programme has adapted to four funding uplifts and two formal addendums, shifting from a focus on enabling the humanitarian environment to include substantial direct delivery and system-strengthening measures.

The MHRP’s monitoring and learning approach is grounded in the ‘Leave No One Behind’ principle, with data disaggregated by sex, age, disability, and geography wherever possible. Access restrictions and budget reallocations delayed the dedicated MEAL component during the review period, though third-party monitoring began later and informed some findings.

Despite these constraints, the team adapted quickly to emerging needs. For example, market assessments informed scale-up of cash transfers in cyclone-affected districts. The team also strengthened anticipatory action – one of the programme’s most notable successes this year – by supporting protocols and frameworks for early response, harmonised with the Social Protection programme (SSPP2). This alignment ensured consistency on triggers, targeting, and delivery systems. FCDO drove success on both fronts, including through policy engagement with government to embed anticipatory measures into national systems and improve early warning linkages. These efforts have positioned anticipatory action as a predictable and coordinated part of Mozambique’s disaster response architecture.

Due to funding delays, the first third-party monitoring was only completed just as this Annual Review was being completed, and provided an initial review of IOM interventions giving a good degree of confidence on the effectiveness of this component. For other components, the team relied on close engagement with partners and local actors, combined with real-time context analysis, to guide decisions. This supported timely adaptations, and early evidence suggests progress on gender and inclusion commitments, though challenges remain in conflict settings where access is limited.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme remains on track to deliver its intended Outcomes—more effective humanitarian response and improved coverage of priority needs, despite working in a very constrained operating space with reduced funding in Mozambique overall. It has helped strengthened government systems, expanded anticipatory action frameworks, and ensured timely support for the most vulnerable. Progress has been particularly strong in scaling up to multiple, overlapping crises: following Cyclone Chido, which struck conflict-affected areas, the UK was among the first donors to channel funding through a rapid central uplift, enabling life-saving assistance within days.

Localisation has also advanced significantly. Two new pooled funds—OCHA and IOM—came online this year, both making good strides in supporting local organisations. Feedback from local actors during consultations highlights that these funds are critical for improving access and building organisational capacity, particularly in security management and compliance. While more work is needed, there is strong consensus that pooled funding is the most effective route to strengthen local leadership. The UK was a founding donor for both funds, and the priority now is to bring in additional donors to ensure sustainability and scale.

Monitoring Direct engagement with beneficiaries was not possible during this review, as the programme targets the most vulnerable populations in areas that remain largely inaccessible due to conflict and insecurity. Monitoring of beneficiary feedback mechanisms (BFMs) has therefore been challenging. Third-party monitors deployed just before this review found BFMs generally functioning but highlighted the need to strengthen feedback loops and make clearer how programmes adapt based on feedback, particularly for IOM-led interventions. Addressing this gap will be a key focus in the coming year. This will see strengthened third-party monitoring and joint visits with IOM and co-donor Ireland, now that the pooled fund is fully operational. The focus will be on improving feedback loops within BFMs and documenting how programmes adapt based on community input, while continuing to advance localisation through IOM-led capacity-building for local partners.

Planned actions include harmonising anticipatory action protocols with social protection systems, supporting government adoption of early warning triggers, and expanding local capacity through INSO-led training for organisations funded via OCHA and IOM rapid response mechanisms. Humanitarian programming will continue having an equal focus on direct delivery and on enabling systems that absorb shocks and respond faster but also ensure more effectiveness. The partnership with WFP will conclude over the coming six-twelve months as objectives on vulnerability targeting have been met, freeing resources to scale multisectoral cash assistance through social protection frameworks. Through the component on issuance of birth certificates and national IDs under Norwegian Refugee Council, there will be continued investment in government-led protection systems and local registration will remain central to sustainability and stronger national leadership. Further, through IOM, there will be continued assistance to the local authorities around disaster-risk reduction in camp management and coordination, as part of the larger sustainability efforts.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The MHRP should continue as it fills a critical gap in delivering lifesaving humanitarian assistance in Mozambique and represents good value for money, with strong results despite a rapidly deteriorating context. Needs and vulnerability are growing due to three major cyclones in the past year and worsening conflict in Cabo Delgado, while access is shrinking and protection risks are rising. At the same time, funding is declining, forcing the humanitarian system to do more with less. In this environment, the programme’s flexibility has been essential—enabling rapid, effective response to overlapping disasters while also supporting systems strengthening in coordination, localisation, security analysis, and protection. MHRP contributes directly to Country Business Plan objectives on climate resilience and conflict and stability, and its ability to combine lifesaving delivery with preparedness and institutional support makes it uniquely valuable. To ensure strategic alignment, the WFP relationship should transition to the Social Protection programme in the coming year, allowing MHRP to sharpen its focus on rapid response, prepositioning, and protection—where its comparative advantage lies and where Mozambique and the British High Commission most need agility.

## C. DETAILED OUTPUT SCORING

Output Title	Humanitarian assistance is prioritized for those most in need and affected by conflict and climate disasters
Output number:		1	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of people reached with humanitarian assistance through FCDO funds	400,000	427,437
1.2 Yr 2 & 3: % of those assessed as most vulnerable targeted for appropriate assistance	60%	80%
1.3 % of those from host community also receiving humanitarian assistance either following a disaster or in conflict-affected areas	20%	Av. 28%
1.4 Number of tools developed or reviewed to strengthen national capacities for forecast-based anticipatory action (only reporting quantitively at end of project)	6	Ongoing
1.5 MHRP has assurances of good progress based on establishing a MEAL component	Supplier Identified	Done

Briefly describe the output’s activities and provide supporting narrative for the score.

- Output 1.1:
  - The programme has reached over 400,000[1] people across Mozambique. Camp coordination and management activities have supported more than 150,000 people in displacement sites including 62,000 people affected by cyclones. IOM’s Rapid Response Fund (RRF) reached more than 15,000 people in the first few months of delivery, with OCHA pooled fund supporting up to 80,000.[2]
    [1] Note that there is a risk of double counting and these may not represent unique individuals
    [2] Note that all results are attributed based on the percentage of UK funds and number of other donors for both pooled funds.
- Output 1.2:
  - Vulnerability-based targeting (VBT) advanced in priority districts but is not yet fully rolled out. Muidumbe and Nangade finalized lists, while Macomia and Quissanga face delays due to insecurity; Mocímboa da Praia lists were rejected by local authorities resulting in assistance being suspended. Despite these challenges, 80% of those assessed as most vulnerable received aid, exceeding the 60% target.
- Output 1.3:
  - Host communities are increasingly included in vulnerability mapping and targeting, but assistance remains inconsistent. While overall coverage averaged 28%, surpassing the 20% target, many host communities in districts without VBT still receive little or no aid.
- Output 1.4:
  - Six key tools were developed or reviewed, including cyclone and flood triggers, SOPs for anticipatory actions, a national simulation framework, district-level Anticipatory Action Plans, and expanded drought plans. These tools are now integrated into national systems, with SOPs endorsed and operational testing completed.
- Output 1.5:
  - This is new output for the year. Supplier for delivery of the MEAL component was identified through a central-managed Framework Agreement.
Two pooled funds – the OCHA Pooled Fund and IOM’s Rapid Response Fund – enabled rapid scale-up and localization, supporting 24 national NGOs through 22 projects despite operating for less than half the period covered by this review. OCHA launched one Standard and one ‘Reserve’ allocation, responding to ongoing conflict and to the three cyclones. The RRF has also responded to both conflict and climate disasters though focus is more on local capacity building alongside short-term assistance. Both funds were just operation not long before the cyclone season hit, proving critical for timely delivery despite access challenges. The RRF faced some financial delays after US funding withdrawal but is now on track, funding 11 local organizations.

A dedicated MEAL component signed at year-end will strengthen monitoring and accountability across all pooled fund projects. This includes third-party monitoring in hard-to-reach areas, standardized reporting tools for partners, and a new analytical framework to track impact against strategic objectives. The first independent review has already been completed, providing baseline insights to improve targeting and delivery in the next cycle.

FDCO support also strengthened Mozambique’s early warning systems and enabled the first anticipatory action for three cyclones, triggering pre-positioning and community preparedness that reduced losses and proved the model works. Success was driven by WFP’s technical and delivery support, leading to official guidelines now embedded in the national emergency plan. A major simulation trained teams for faster response, and much of this work will transition to the social protection programme to ensure sustainability. In addition, six key tools for anticipatory action were developed or reviewed—including cyclone and flood triggers, SOPs, district-level plans, and expanded drought plans—now integrated into national systems.

Despite sustained WFP engagement, vulnerability-based targeting (VBT) in Cabo Delgado remains uneven and politically sensitive. Lists are finalized and in use in Muidumbe, completed but pending approval in Nangade, while data collection in Macomia and Quissanga is delayed due to insecurity. In Mocímboa da Praia, authorities rejected verified lists after repeated consultations, leading to suspension of assistance and the district’s removal from HRP priorities. These disputes reflect growing concerns over control and bias, signalling an increased risk of aid politicization. To mitigate this, WFP uses SCOPE, its digital beneficiary management system, to register and verify households, reducing manipulation of lists and ensuring transparency. Combined with community feedback mechanisms and conflict-sensitive engagement, these measures aim to safeguard impartiality, but resistance continues to delay distributions and erode trust.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The milestone for Output 1.1 changed significantly during the year with a £5m uplift, which increased the target from 250,000 to 400,000 people to be reach. With the identification of a delivery partner for the MEAL component, Output 1.5 was added.

For the coming year, the Outputs will be reviewed to overall better reflect effectiveness of both pooled funds around speed of funding and contribution to the localisation agenda.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

From last year:
WFP: Prioritize the establishment and rollout of anticipatory action (AA) mechanisms in conflict settings, ensuring protocols are agreed and implemented in the next period. Completion: Progress remains slow, largely due to government reluctance on cash in conflict areas rather than WFP’s performance.
For this year:
- OCHA: Consider speeding up disbursements and simplifying reporting requirements. Some organizations noted that the time between trigger and disbursement could be faster; this will be tracked as a key effectiveness indicator in the next Annual Report.
- IOM/OCHA: Formalize coordination between funds and partners, including better mapping to improve complementarity.
- FCDO Humanitarian Team: shift outputs to capture progress on localisation through pooled funds, along with speed and ease of response.

Output Title	Humanitarian and development organisations in Mozambique have access to timely, reliable, and high-quality safety services that help them plan, operate, and deliver aid more safely.
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
% of NGO respondents agree that INSO services help them plan, operate, and deliver aid more safely.	80%	Exceeded / 94%
Number of INGO staff receiving regular trainings and support on security and access	60	Exceeded / 129 (now includes staff of NNGOs as well)

Briefly describe the output’s activities and provide supporting narrative for the score.

- Output 2.1:
  - INSO conducted a satisfaction survey in June 2024, which showed that 94% of respondents agreed that INSO’s alerts and reports were well-timed and supported their operational decision-making. Flash Alerts were the most cited service influencing operational decisions, with 36% of respondents reporting they altered or rescheduled activities based on INSO alerts. One INGO noted that INSO’s analysis enabled safe movement between field offices during heightened insecurity.
- Output 2.2:
  - INSO delivered 29 training sessions during the year, reaching 249 participants. Over 85% were national staff and 37–46% were women. Trainings covered essential security, crisis management, travel safety, and humanitarian negotiations, with all sessions rated “Excellent” or “Very Good” by participants.
INSO Mozambique expanded its operational footprint by launching services in Nampula province, following formal registration in May 2024. Roundtables began in November and were scaled up in response to security volatility.

Overall partner registration grew from 80 to 96 NGOs, with local NGOs now representing 25% of the total. INSO supported this inclusion through bilingual engagement, targeted outreach, and collaboration with donors like UNFPA to encourage LNGO participation in trainings and advisory services.

The year was marked by significant challenges, including post-election unrest, cyclones, and a major funding gap following the termination of USAID/BHA support. INSO responded with adaptive measures—nationalizing key roles, reducing non-essential travel, and shifting reporting formats—to maintain core services and ensure continuity for humanitarian partners operating in volatile environments.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to the Output indicators or targets.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Last Year:
INSO: Should consider how to integrate more local organizations into its training and support outputs, including targeted security assessments in active conflict areas to empower local organizations
Completion: Achieved with larger majority of trainings and support now for local orgs
This year:
No new recommendations for the next Annual Report.

Output Title	People have access to timely lifesaving response following displacement from conflict and from climate disasters
Output number:		3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of households benefitting from the construction/upgrade of housing solutions.	130	Exceeded / 300
3.2 # of shelter kits procured and disbursed as prepositioning to disaster	4000	Exceeded / 5,500 (inc. 4,200 prepositioned)
3.3. Number of displacement/settlement sites benefiting from improved camp management and coordination	15	Exceeded / 21
3.4 # of people benefiting from new water points or benefitted of rehabilitation of existing water supply infrastructures	5,000	Met / c. 6,000
3.5 # of people benefiting from basic services (health, education) in emergencies	40,000	Met / 40,000

Briefly describe the output’s activities and provide supporting narrative for the score.]

- Indicator 3.1
  - For housing support, the initial milestone of 130 households was revised upward. By the end of the period, 632 households had received shelter assistance, of which 300 were upgraded shelters. This included new construction in Ibo, upgrades in Metuge, and early recovery support in Meluco. In Ancuabe, 158 roofs were repaired and 156 homes received additional improvements such as plastering, bringing the total number of upgraded homes to 300.
- Indicator 3.2.
  - On disaster preparedness 4,031 shelter kits were procured and distributed through the Shelter Common Pipeline, meeting the revised target. These kits reached 2,410 vulnerable households across six districts, supporting communities ahead of the rainy and cyclone season as well as 2,000 kits procured from the uplift following the cyclones of Dec. 2024. Shelter kits reached an estimated 48,000 people affected by cyclones.
- Indicator 3.3.
  - 21 displacement and accommodation sites benefited from improved camp management and coordination, including site upgrades, static management, and community engagement structures. These efforts strengthened service delivery and accountability mechanisms, ensuring safer and more dignified living conditions for displaced populations.
- Indicator 3.4.
  - Water access improved through the rehabilitation or initiation of six boreholes in Niassa, Metuge, and Nampula. While the infrastructure targets were met, final beneficiary numbers are still being compiled by the WASH team.
- Indicator 3.5
  - Approximately 40,000 people accessed basic services in emergency settings. This included over 22,000 health consultations delivered through mobile and static clinics, mental health and psychosocial support for more than 3,000 individuals, and hygiene promotion activities reaching nearly 3,500 people. CCCM teams also worked with local authorities to relocate displaced families from schools, allowing education services to resume.
This Output has scored an A+. All output targets were met, and many were scaled up during the reporting year to respond to growing needs, along with a funding uplift[3]. These results were delivered in an exceptionally difficult year, marked by a sharp increase in conflict, three cyclones, and episodes of political violence that disrupted access and operations. Despite these challenges, the partners have delivered and adapted quickly to shifting conditions.
[3] In December 2024, an additional £5m was granted to both OCHA and to IOM to respond to new needs from the cyclones and with additional conflict-related displacement.

IOM demonstrated strong adaptability in using CDEL funds to meet urgent and longer-term needs. This funding enabled sustainable shelter upgrades for 185 houses and support to 500 vulnerable households, while also advancing durable housing construction at Corrane and community infrastructure such as health facilities and centres. In parallel, CDEL resources also supported borehole installation and permanent latrines to improve WASH access, and contributed to area-based planning for returns and relocation, laying the groundwork for permanent structures and climate-resilient settlements. This has been critical during a year when longer-term needs including in returns area are competing with new lifesaving needs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the past year, this Output was adjusted to respond to increased displacement and emerging needs, particularly following conflict-related events in Chiure and Macomia. Targets for shelter support, camp management, and water infrastructure were revised upward, and resources were reallocated to expand coverage. As a result of this review, planned changes include completing shelter repairs in Marrucane, initiating new rehabilitation in Corrane, and continuing the transition of site management to local authorities, with a stronger focus on preparedness for climate-related emergencies.

With the addition of OCHA and IOM pooled funds, these Outputs will be revised to reflect the breadth of interventions that are being carried out now by local actors, to ensure that percentage of those reached through local organisations is reflected

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last Year:
- Improve coordination with INGD, especially at early disaster stages at district level and capacity building
  - Response: Coordination strengthened through joint verification and registration, but more direct capacity-building of INGD needed.

- Revise indicators to reflect expanded support to return areas and shelter construction.
  Response: A full review of outputs and the logframe is scheduled for the next reporting cycle to reflect new focus areas on sustainability of shelter models
- Plan prepositioning of shelter stocks well ahead of cyclone season for better VfM and resilience.
  Response: FCDO successfully prepositioned supplies for over 5,000 households this period and aims to increase coverage in the coming year.
Next Year:
BHC Maputo Humanitarian Team: With the addition of OCHA and IOM pooled funds, these Outputs will be revised to reflect the breadth of interventions that are being carried out now by local actors.

Output Title	Protection is placed at top of humanitarian response agenda, with specific focus on inclusion of all programming
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
4.1 % of beneficiaries who report accessing administrative, educational, financial and other public and private services as a result of legal support services and provision of new birth certificates	60%	Partially exceeded / 67%
4.2 # of individuals supported with focused MHPSS services	7,000	Almost Met / 6,920
4.3 Protection interventions and innovations included by all partners to ensure inclusion and PSEA. (Qualitative summary of new interventions each year)	Qualitative only	Community-based protection interventions scaled up (training of local judges, reactivation of courts)
4.4 % of overall assistance reaching people living with disability targeted with appropriate support	8%	Almost met / c. 6%

Briefly describe the output’s activities and provide supporting narrative for the score.]

Over the past year, NRC has adapted its approach in Cabo Delgado to respond to growing protection needs and a rapidly shifting context. In addition to expanding legal assistance and documentation services, NRC began supporting local registry offices—such as in Nangade—to strengthen civil registration systems and promote sustainability. The team also scaled up door-to-door legal awareness and initiated plans for radio messaging to reach underserved communities. Outcome monitoring was expanded to assess impact on dignity, access, and satisfaction, while community-based justice was deepened through the reactivation of 59 courts and training of 98 judges. These shifts reflect NRC’s commitment to locally driven, inclusive protection that restores rights and reinforces resilience.

- Output 4.1:
  - NRC supported over 20,000 people with birth certificates, ID cards, and legal counselling. Services were delivered in high-need areas like Pemba, Mueda, and Muidumbe, with a strong focus on women (60% of beneficiaries). Of those receiving documentation, 67% reported accessing administrative, educational, financial, and other public or private services as a direct result of NRC’s legal support and provision of birth certificates, according to Post-Distribution Monitoring (PDM) data. These services included school enrolment for children, access to health facilities, opening bank accounts, and obtaining social protection benefits.
  - Following Cyclone Chido, NRC swiftly adapted its legal assistance to support documentation recovery and counselling for those affected, reaching over 3,000 individuals during the emergency period and integrating this response with other core competencies to help restore access to services and legal identity.
- Output 4.2:
  - During the period, IOM reached 6,920 people through awareness and mobile brigades, provided Psychological First Aid to 2,720 individuals, and delivered counselling and socio-relational activities to over 1,800 people Following Cyclone Chido, 339 people received tailored counselling and 2,720 were reached with Psychological First Aid.
  - Mobile brigades and community-based sessions expanded access to remote areas, while an impact assessment showed that 82.5% of beneficiaries reported improved wellbeing and nearly 100% expressed satisfaction. The integration of MHPSS into emergency response and the use of socio-relational activities marked a significant step forward in reaching vulnerable populations with timely, culturally appropriate support.
- Output 4.3:
  - NRC strengthened community-based protection by training 98 community judges and reactivating 59 courts across Cabo Delgado. These courts resolved nearly 950 cases, mostly related to informal unions and land disputes, offering accessible justice and reducing tensions in displacement-affected areas. Training included gender-sensitive dispute resolution, inheritance law, and PSEA principles, ensuring that protection risks were addressed through inclusive legal mechanisms.
- Output 4.4:
  - Persons with disabilities were prioritized as a key vulnerability criterion in shelter and site interventions, with inclusive committees established and consultations informing safe, accessible latrine placement. Across CCCM, WASH, and cyclone response activities, 1,858 persons with disabilities were reached, including through hygiene campaigns and disability-sensitive infrastructure design. Additional disaggregated data from other partners, including pooled fund projects, is still being compiled and will be needed to provide a full picture of inclusion and service access.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output Indicator 4.4 was added to the logframe this year, to reflect the need to increase focus on disability and inclusion.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Next Year:
IOM: MHPSS programming should prioritize reaching the most vulnerable by expanding coverage in conflict-affected and hard-to-access areas. This includes strengthening local referral networks and deploying mobile brigades more strategically to ensure equitable access to psychosocial support.
BHC Maputo Humanitarian Team should require pooled fund partners to report disability-disaggregated data and evidence of inclusive design in all proposals and reports. At least one monitoring visit should specifically assess accessibility and consult Organisations of Persons with Disabilities.

## D: VALUE FOR MONEY

Key cost drivers and performance
Between April 2024 and March 2025, FCDO disbursed a total of £14.1 million. The key cost drivers were localization pooled funds, which accounted for 28% of the budget (£3.9 million), providing training and grants to local NGOs to respond to conflict in Cabo Delgado and natural disasters. Shelter/NFIs represented 16% (£2.3 million) and provision basic services also accounted for 16% (£2.3 million). This included provision of shelter materials and non-food items to people affected by conflict and cyclone Chido. Staff costs represented 12% (£1.7 million), covering essential personnel and technical support, while technical assistance on Anticipatory Actions, Nutrition and other sectors accounted for 10% (£1.4 million) followed by infrastructure investment representing 8% (£1.1 million).

VfM performance compared to the original VfM proposition in the business case
Economy
The data indicates that IOM is demonstrating improving economic value for money. The staff costs of IOM in 2024 alone showed a decrease from the initial 34% from the original MOU budget to 23% at the end of the 2024 financial year. This was justified by the economies of scale as we toped up £6.7 million this financial year. However, Shelter/NFIs kits showed an increase in costs moving from the £65 in the previous year to £104 per household. This was mainly due to the kits for the response to cyclone Chido having included additional items such as solar lamps and kitchen sets compared to kits distributed last year. This continue to be value for money compared to the cost of FCDO centrally procured kits that cost £114.

Efficiency and Effectiveness
The programme is demonstrating efficiency through its localization pooled fund components by enabling delivery at lower costs in areas where international NGOs and UN agencies have limited access. The IOM Rapid Response Fund for Localization provided grants to 11 local NGOs delivering services to people affected by conflict and disasters in Cabo Delgado, Nampula, Zambezia, and Sofala. Similarly, the OCHA Country-Based Pooled Fund supported more than 11 local NGOs through reserve and standard allocations. Although overall spending by both funds has been slow, they have made significant progress in capacity building and due diligence, enabling local NGOs to qualify for funding within these pooled mechanisms and from other donors. This approach is bringing local NGOs into coordination structures and strengthening their role in service delivery at the community level.

The programme is demonstrating efficiency through its localization pooled fund components by enabling delivery at lower costs in areas where international NGOs and UN agencies have limited access. The IOM Rapid Response Fund for Localization provided grants to 11 local NGOs delivering services to people affected by conflict and disasters in Cabo Delgado, Nampula, Zambezia, and Sofala. Similarly, the OCHA Country-Based Pooled Fund supported more than 11 local NGOs through reserve and standard allocations. Although overall spending by both funds has been slow, they have made significant progress in capacity building and due diligence, enabling local NGOs to qualify for funding within these pooled mechanisms and from other donors. This approach is bringing local NGOs into coordination structures and strengthening their role in service delivery at the community level.
In addition, FCDO funding to NRC and IOM to improve research and innovation on shelter is bringing efficiency into the shelter response. The NRC component on research on shelter, jointly with local universities, is ongoing and bringing new options for shelter using local materials. These options will not only lower the price per shelter unit but transfer knowledge to communities and be climate friendly compared to the use of plastic sheets and other materials. This intervention is at earlier stages but is expected to contribute to efficiency of the programme and humanitarian community response to natural disasters.

On equity, the programme provided lifesaving assistance to people affected by conflict in Cabo Delgado and natural disasters like Chido in the assessed period. The assistance was specially directed to vulnerable populations like people with disability, women, elder and children. The people living with disability targeted this year is around 6% as mentioned in the indicator 4.4. Our support to WFP has a component on vulnerability targeting to ensure that the programme and other humanitarian response can target the most vulnerable without discrimination. OCHA Pooled fund and IOM Rapid Response Fund is another mechanism to ensure that funds reach to the last mile beneficiaries.

 Assessment of whether the programme continues to represent value for money
The programme continues to represent value for money as people start to return to the northern districts of Cabo Delgado and insecurity worsens. The programme will continue to support IDPs especially through IOM Multisector support. The vulnerability to climate shocks remains a big challenge for IDPs in Cabo Delgado and other areas in Mozambique. The funding of both OCHA Country Based Pooled Fund and IOM Rapid Response Fund for localization continues to be essential to ensure the response of the most in need in areas that are difficult to access.

E: RISK

Overview of risk management
The overall risk rating for the programme remained high over the last year yet within the BHC’s risk appetite.
Insecurity worsened in the northern province of Cabo Delgado due to conflict in the past year. This remained one of the major risks limiting access to beneficiaries with conflict affecting the northern districts of Nampula provinces and neighbouring Niassa as well. The attacks led to the suspension of humanitarian activities and movement restrictions in some areas with some humanitarian partners suspending much of its life-saving aid operations in Macomia, Nangade, Quissanga, Mueda, Muidumbe and Mocimboa da Praia districts. To mitigate the situation, FCDO continued to fund INSO as the main source of security advice for humanitarian partners especially international and national NGOs. Mozambique Armed Forces also carried out escorts in main roads heading to the northern districts, from Ancuabe up to Mocimboa da Praia with NGOs using the service mostly.

The risk of post presidential election violence materialized and impacted moderately on project implementation for some partners. While output targets have been met operations have slowed down in some areas and major community mobilization and infrastructure works have been temporarily de-prioritized to ensure security of staff and communities as well as impartiality of targeting.

The financial sustainability risk of implementing partners not being able to secure the total funding necessary to implement and sustain its operation in Mozambique materialised with US funds cuts. This risk impacted on INSO and IOM with bigger contributions from the US. FCDO budget uplift approved in 2024 mitigated some of the risks for both INSO and IOM as well as bringing forward funds from INSO agreement outer years while IOM received a budget top-up for multi-sector components and response to cyclone.

All partners Due Diligence are up to date and some are due to be refreshed in early 2026. WFP and NRC DDA will be refreshed in April and May 2026 while INSO will be refreshed in November 2026. The remaining DDA for IOM and OCHA are due to be refreshed in 2027.

Current level of fiduciary risk and direction of travel since last ASP	Worsening
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable
Is a full FRA update required?	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The overall performance of delivery of the IOM Multi Sector Project has been good despite some delays caused by changes to IOM financial systems and procurement. This was reported in the first meeting review of 2025 financial year and mitigation measures agreed. IOM’s report was submitted on time and a review meeting carried out jointly with the implementing partner. Two amendment letters were signed in 2024. The first amendment letter was to increase £3.2 million as part of the office budget uplift and change the MOU end date to 31st March 2027. The second amendment letter was signed to increase £3.5 million to respond to Cyclone Chido. All funds increase in both Amendment letters were disbursed and spent by 31st March 2025.
The WFP Contribution Arrangement performance of delivery has been good. The report was submitted on time and a review meeting carried out jointly with the implementing partner. One amendment letter was signed in 2024 to increase £3.3 million as part of the office budget uplift and change the MOU end date to 31st March 2027. During last financial year, FCDO disbursed £1.4 million that were disbursed and spent by 31st March 2025.
The performance of delivery of INSO Accountable Grant has been good. The quarterly reports were submitted on time and a review meeting carried out jointly with the implementing partner quarterly. One amendment letter was signed in 2024 to increase £0.9 million as part of the office budget uplift and change the MOU end date to 31st March 2027. During last financial year, FCDO disbursed £525,000 that were disbursed and spent by 31st March 2025. INSO faced financial sustainability that required FCDO to increase £125,000 in the initial annual budget allocation to cover INSO needs. This issue was reported in the risk section.
The NRC Accountable Grant has been good. The quarterly reports were submitted on time and a review meeting carried out jointly with the implementing partner quarterly. One amendment letter was signed in 2024 to increase £1.7 million as part of the office budget uplift and change the MOU end date to 31st March 2027. During last financial year, FCDO disbursed £711,205 that were disbursed and spent by 31st March 2025.
A new MOU with IOM was signed to implement the Rapid Response Fund for Localization in November 2024 in a total of £2.7 million. During last financial year, FCDO disbursed £1.2 million that were disbursed and spent by 31st March 2025. All compliance requirements were followed using the due diligence from the IOM Multi Sector MOU. The report was submitted on time and a review meeting carried out jointly with the implementing partner. IOM Rapid Response Fund carried out regular joint review meetings with Ireland to discuss progress and key decisions.
A new MOU with OCHA to implement a Country Based Pooled Fund was signed 2024 in a total of £3.6 million. All compliance requirements were followed including a new due diligence completed in November 2024. One amendment letter was signed in 2024 to increase £1.5 million to respond to Cyclone Chido. During last financial year, FCDO made two payments to OCHA humanitarian fund, one of £1.2 million and the other of £1.5 million. OCHA carried out regular Advisory Board meetings with donors to discuss progress and make key decisions. OCHA only submitted the financial report and the narrative report is not available yet. At the moment, the MHRP cluster relies on regular advisory board meetings provided regular updates on allocations and execution.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
During 2024, the MHRP programme has been monitoring its progress using a range of monitoring tools. These included regular review meetings, logframe reviews, follow ups on previous annual review recommendations, regular risk management including escalation of risk, taking in account that the programme is mostly implemented in a conflict zone. Outcomes of monitoring activities were integrated into the ongoing planning and implementation processes.

The MHRP Business Case includes a Monitoring, Evidence, Analysis and Learning supplier as it’s key monitoring mechanisms. However delays in the signature of the contract with CADMUS (the selected supplier) due to ODA budget uncertainty moved the start of the contract for 2025 financial year. In the meantime, the MHRP cluster is using review meetings with IOM Multisector, WFP, INSO and NRC. In the Pooled funds, the MHRP cluster is engaged in the OCHA Advisory Board while on the IOM Rapid Response Fund (RRF) is part of the Quarterly RRF Donor Meeting.

Evidence and Learning:
During the assessed period several evidence and learning pieces have been carried out through several implementing partners. NRC carried out an impact and Outcome Monitoring Survey on the delivery of Information, Counselling and Legal Assistance. This assessment provided valuable information on impact NRC legal assistance for beneficiaries to access basic services. INSO carried out the Partners Satisfaction Survey that provided insights on how humanitarian partners access to INSO services and use their advice to ensure safety of its staff. In addition, IOM conducted a Community Feedback and Referral Analysis to assess efficiency of CCCM services. The results of these assessments and other collected through regular reviews have direct implications for the programme’s future direction, particularly as FCDO design new intervention.

Date of last narrative financial report	IOM Multisector – 26/06/2025 / IOM RRF – 15/05/2025 / WFP – 30/15/2025 / INSO – 29/10/2025 / NRC – 21/10/2025 / OCHA – 18/09/2025	Date of last audited annual statement	INSO - / NRC – 13/10/2025