BUSINESS CASE ADDENDUM

PROGRAMME TITLE
Directorate/ Post	MAPUTO	Contact name
Original programme budget	£33,740,000	Country or region targeted	Mozambique
Cost extension value (if applicable)	£5,000,000	Original BC approver
New increased or reduced programme budget (if applicable)	£38,740,000	Original programme start and end dates	May 2022 – March 2027
Latest AR programme score and outcome confidence rating	AR Score: A / Outcome Confidence Rating: Green / A	New programme end date (if applicable)	As above
		Programme ID	301363

Detailed information
Programme summary	The Mozambique Humanitarian Response Programme (MHRP) was approved in May 2022, to provide lifesaving assistance for those affected by conflict and by climate disasters. There are over 1 million people displaced and affected by conflict in the country, and Mozambique is regularly severely impacted by annual cyclones, with more than 700,000 affected in late 2024 and early 2025. The MHRP responds to the need for flexibility of funding, allowing partners to scale up rapidly following a disaster or large-scale displacement, as well as ensuring preparedness activities in advance of disasters based on good practice. / The initial Business Case at the time of approval in 2022 focused on improving the enabling environment rather than on direct delivery. Following a time and cost extension in early 2024, there has been some investment in preparedness and response to climate and conflict displacement. / To date, the programme has reached at least 200,000 people a year affected by conflict and climate disasters with emergency assistance. It has also supported the development of anticipatory action initiatives allowing for early responses to disasters. / On 31 January 2024, it was approved a two-year extension for an additional £21.86m. The Business Case was increased from £11.8m to overall spend of £33.74m and a new end date of May 2027.
Changes	In December 2024 Mozambique Cyclone Chido made landfall and tore across much of the north of the country, resulting in 450,000 people being affected with widespread destruction of homes, education and health facilities. / It was allocated an additional £5m of budget. This enabled the UK to contribute to the UN's Flash Appeal and assist up to 100,000 vulnerable individuals immediately, many of whom were also affected by a second cyclone (Dikeleti) less than a month later. Up to 320,000 people will be support altogether over this cyclone season. / The fund was allocated to two existing UK partners in Mozambique: UN OCHA to support a rapid response from the humanitarian pooled fund and IOM for distribution of emergency shelter kits and vital non-food items. / Since that allocation, Mozambique has been impacted by a third major cyclone this season, with Cyclone Jude making landfall on 9 March, impacting many of the same areas for the third time since December 2024.
Implementation	For the cost extension, the approach has been to continue with existing partners, given their strong track record and progress on achieving outcomes under the MHRP.
Budget	The original BC was for three years, with a total funding of £11.8m. In January 2024, the programme received an additional £21.86m. This bought the total value for the MHRP, with the cost and time extension from 2024, to £33.74m over five years. In December 2024, the programme received this current emergency increase of £5m. The current value of the MHRP is now £38.74m over five years.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	Access constraints for partners pose challenges to aid delivery of assistance. / Safeguarding risks remain high in humanitarian response, and we have assured all partners have strong and effective mitigation measures in place.
Results/Monitoring and Evaluation	Results: / The approved uplift will support approximately 320,000 people with lifesaving assistance. / The logframe has been revised and approved to reflect this uplift. The overall Theory of Change remains the same, with the impact being to reduce suffering for disaster and conflict-affected communities.