Project Name: Project Rapid Response Fund (RRF) - Localization Fund - program responding to Emergency and Recovery Needs of Disaster- and Conflict-affected population in Mozambique, (Mozambique Humanitarian Response Programme/FCDO)
Project Number: 301363-403

I refer to the Memorandum of Understanding between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and the International Organization for Migration (“IOM”) signed on 01 November 2024, and Amendment Letter 01/2026 signed on 06 February 2026.

Following recent discussions, FCDO proposes to change the end date of the Memorandum of Understanding, and to decrease the amount made available to IOM by £300,000.00 (three hundred thousand Pounds Sterling).

I propose that the end date of 31 March 2027 in paragraph 5 of the original Memorandum of Understanding be deleted and replaced with 30 June 2026.

I propose that the figures and words £3,190,000 (three million, one hundred and ninety thousand Pounds Sterling) in paragraph 3 of the original MOU be deleted and replaced with the figures and words £2,890,000 (two million, eight hundred and ninety thousand Pounds Sterling).

The table in paragraph 3 of the MOU will be replaced with the following:

Date	Amount (£GBP)
November 2024 (upon signature of the present Agreement - paid)	£1,200,000
November 2025(paid)	£1,400,000
March 2026 (paid)	£490,000

The attached Cost Modification proposal to this Amendment is added to the Project Document attached to the Memorandum of Understanding.

Nothing in or relating to this letter of amendment or the Memorandum of Understanding referenced above shall be deemed a waiver, express or implied, of any of the privileges and immunities of the International Organization for Migration.

This letter of amendment will place on record our common understanding of the above change and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No.02/2026.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of the Partner:
Name:
Position:
Address/Contact Details:
Date:

Annex 1. Schedule of reporting

Deliverables	Due Date
Six month report (narrative and financial) covering October 2024 to March 2025 / Six month report (narrative and financial) covering April 2025 to September 2025 / Final report (narrative and financial) covering October 2025 to March 2026	15th May 2025 / 15th October 2025 / 15th July 2026
Regular progress update meetings to discuss activities, results, assess risks, value for money and delivery chain mapping	To be agreed between FCDO and IOM