## Annual Review

Title: Indo-Pacific Humanitarian Mechanism
Programme Value £ (full life): Up to £35,000,000		Review date: September 2025
Programme Code: 301369	AMP start date: 13/09/2024	AMP end date: 30/09/2029

Summary of Programme Performance
Year	24/25
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	D0006634.odt
DevTracker Link to results framework:	In the process of publishing

A. SUMMARY AND OVERVIEW
Description of the programme
The Indo-Pacific Humanitarian Mechanism (IPHM) was established in September 2024 to respond to new ‘rapid onset’ humanitarian crises (e.g. earthquakes, floods, cyclones, tsunamis, volcanos and major landslides), and ‘slow onset’, escalating or anticipated crises (e.g. droughts and outbreaks of conflict and disease). It strengthens the UK’s agility to prepare for and deliver rapid assistance to the most vulnerable populations in the Indo-Pacific region by providing a vehicle for channelling funds and establishing in advance the protocols for whether, how and with what resources and partners a response can be made. The programme supports the delivery of the Foreign Secretary’s priority to ensure a rapid and agile UK and international humanitarian system. The mechanism has two objectives:

Delivering a rapid response – channelling central and regional funds to the most vulnerable, crisis-affected populations in the region with protocols and arrangements for how and with whom a response could be made. Planning in advance enables rapid responses to major shocks (e.g. over 1,000 fatalities and 100,000 affected people) allowing immediate deployment of assistance, such as UK emergency medical and search and rescue teams, in the time critical window for saving lives, and contributing to the overall relief effort.

Building preparedness partnerships - enhancing readiness and reinforcing the UK response through stronger coordination, grounding and influence in the region. This smaller preparedness component focuses on building both regional partnerships, such as with the Partners in the Blue Pacific initiative to strengthen delivery of relief items in the Pacific and ASEAN‘s Coordinating Centre for Humanitarian Assistance in Disaster Management (AHA Centre), as well as bilateral humanitarian partnerships, enhancing coordination and innovation, so improving the effectiveness of responses regionally and globally.

In its first year, the IPHM has responded to three new disasters in the region: Typhoon Yagi in Vietnam (September 2024), multiple typhoons in the Philippines (November 2024) and an earthquake in Vanuatu (December 2024). So far, the IPHM has in total provided just over £2.8m of humanitarian assistance through the British Red Cross (supporting International Federation of the Red Cross and Red Crescent appeals), the UN Children’s Fund (UNICEF), the World Food Programme (WFP) and the bilateral reciprocal mechanism with Australia’s Department of Foreign Affairs and Trade (DFAT) (see table below).

Humanitarian Response	Partner	Allocation (GBP)	Sectors
Vietnam Typhoon Yagi	UNICEF	500,000	Multi-sector
	BRC/IFRC	500,000	Multi-sector
Philippines Multiple Typhoons	UNICEF	400,000	WASH
	WFP	600,000	Cash & logistics
Vanuatu Earthquake	UNICEF	400,000	WASH and education
	BRC/IFRC	425,000	Multi-sector
	DFAT	8,979	Relief items
Total		2,833,979

As IPHM is expected to channel limited duration funding contributions to multiple crises over the course of five years, each response is considered an output within the programme’s logframe. Hence, there has so far been three outputs (responses). To review them, it has been decided that each annual review will focus on those outputs (responses) that have been concluded (i.e. for which a final project report has been received and agreed) within a specific Annual Review (AR) period. Hence, this first AR focuses on the Philippines response, which is the only one completed. The other two other responses will be reviewed in the next AR, following receipt of their final reports.

Whilst the outcome indicators focus on the performance and quality of assistance provided by the mechanism with indicators on inclusion, speed, proportionality, accountability, localisation and safeguarding; the output indicators assess the delivery of each response. The latter are drawn from a common set of output indicators, which are included in the IPHM logframe. These are aggregated if more than one partner funded in the response is supporting a specific sector (e.g. cash assistance). This has been designed to allow consolidated reporting of the achievements made for each sector and for comparative analysis.

The Philippines Multiple Typhoon response
Six typhoons hit the Philippines in a period of 25 days in October and November 2024. Together they affected over 10m people (2.6m families) across 17 regions. Over 170 people died, over 50,000 houses were damaged and the costs to agriculture, infrastructure, and livestock were over $300m. Overall coordination of assistance was managed through the government-led National Disaster Risk Reduction and Management Council. International support was coordinated through the UN Humanitarian Country Team, to which the UK was given observer status during the response. The Government requested the UN to assist, to which the UN the subsequently responded with the launch of a Humanitarian Needs and Response Plan, budgeted at $42.2m (£33.3m).

FCDO provided £1m in bilateral assistance, which was sourced from regional funds. £600,000 was allocated to WFP to support the provision of cash assistance through the vertical expansion of the Government’s social protection programme (Pantawid Pamilyang Pilipino Program – 4Ps), and for the logistics to support the distribution of family food packs. Both aspects were in support of the Department of Department of Social Welfare and Development (DSWD). £400,000 was allocated to UNICEF to support WASH, which was identified as a critical requirement and gap in the response. The UK also indirectly supported the response through our central contributions to the UN’s Central Emergency Response Fund, which allocated $14m; as well as the IFRC’s Disaster Emergency Relief Fund (CHF 0.9m) and NGO disaster risk finance mechanism, Start Ready (£0.6m).

Summary supporting narrative for the overall score in this review
The overall score is an A (outputs met expectations). Progress was made in the delivery of the outcome indicators and the Philippines response demonstrated the benefits of having the IPHM by having protocols in place, pre-identifying potential partners and not having to divert limited staff time to develop new business cases for each response. The latter was reinforced by this response happening in-between two others (Vietnam and Vanuatu), all of which occurred within a five month period.

Major lessons and recommendations for the year ahead
- Continue to develop and update the assessment of potential implementing partners across the region to enhance readiness and the speed and effectiveness of response. This includes updating country preparedness plans and undertaking regular crisis training and exercises; coordinating with other donors on the performance and value for money of humanitarian agencies; monitoring the impact of aid cuts on response capabilities; consolidating the relationship with specific partners; and dovetailing this with FCDO’s broader humanitarian framework and priorities.
- Ensure Due Diligence Assessments (DDAs) are completed within three months of signing agreements. Where this is not possible due to partner’s policies (e.g. Red Cross can provide details for DDAs only after 3 months of an agreement), DDAs should be carried out as soon as possible. There is also a need to explore whether there are opportunities to streamline the DDA process.
- Ensure awareness and dissemination of the IPHM Humanitarian Inclusion principles among all implementing partners at the earliest opportunity and explore potential opportunity to support Women-Led and Women’s Rights Organisations (WLOs and WROs), such as in the Philippines, the Pacific and/or with pooled funds.
- Explore opportunities to sharpen some indicators, as well as develop the baselines (e.g. for speed and proportionality) as further information across FCDO is gathered; update the results framework with indicators for the preparedness component; and explore opportunities to enhance VFM metrics.
- Assess opportunities to speed up the early phase of a response and opportunities to streamline the process, such as in proposal development; and increase the sharing of best practice and learning between FCDO’s regional humanitarian teams.
- Continue to monitor preparedness arrangements in the Philippines, including the government’s new bill for anticipatory action; the updated CERF Anticipatory Action Framework; progress in developing shock-responsive social protection; and ensure that the UK remains part of the UN Humanitarian Country Team.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The expected impact of this programme is reduced suffering of the most vulnerable, crisis-affected populations in the Indo-Pacific (see theory of change diagram in Annex 1). Achieving this is feasible when humanitarian assistance is timely, proportionate and accountable, and delivered in a way that is effective, inclusive and principled. Delays in the arrival of assistance increase human suffering and risk of death. This mechanism is designed to enable timely, targeted and high-quality assistance by having the following: protocols and arrangements in place in advance of shocks; FCDO resources, capabilities and partnerships on standby; and access to accurate and up to date analysis of potential and emerging humanitarian situations. In addition, the preparedness component will help build partnerships with specific countries and regions to enhance readiness in the region and strengthen the UK’s bilateral response.

The logframe has been developed from the theory of change, with outcome indicators on inclusion, speed, proportionality, accountability, localisation and safeguarding (see assessment of each below). Further work needs to be undertaken to develop the outcomes for the preparedness component.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The following provides an assessment of the outcomes in this first annual review. All focus just on the Philippines response, though the detailed reporting considers broader progress on speed of response, proportionality and localisation. Detailed reporting on each of the outcome indicators is presented after the summary table.

Outcome	Planned	Achieved	Comment
People supported	50,795	47,730
Inclusion	Evidence of action taken to implement at least 1 of 5 inclusion principles	WFP: action towards two principles / UNICEF: action towards three principles	WFP provided evidence of progress towards principles 3 and 5. / UNICEF provided evidence of progress towards principles 1, 2 and 5.
Speed of response	N/A	1). 2 days / 2). 13 days	Days taken between government request and 1). decision to fund response; 2). approval of projects.
Proportionality	N/A	1). 3% / 2). 5.1%	1). share of total appeals requested / 2). share of total funding received against appeals
Accountability	100%	100%
Localisation	25%	60%	Based on support to national public safety net
Safeguarding	100%	100%	Although met, opportunities to reinforce PSEA
[note] Respectively: best practice in inclusive design, implementation and practice (including in monitoring and use of disaggregated data) [Principle 3] and safeguarding [principle 5].
[note] Respectively: twin-track approach was taken with both targeted and mainstreamed inclusive WASH interventions [principle 1]; examples of best practice in design, implementation and practice (including improving accessibility of WASH facilities for children through repairs) [principle 2] and safeguarding [principle 5].
[note] No benchmark has been set centrally but is starting to be tracked.
[note] No benchmark has been set centrally but this is starting to be tracked.

Total population supported
This table provides summarises the population supported in the Philippines response.

Partner	Planned Total	Achieved Total	Women/Girls	Men/Boys	PWD
WFP	21,750	21,750	9,831	10,289	621
UNICEF	29,095	25,980	12,357	13,533	274
TOTAL	50,795	47,730	22,188	23,822	895
[note] Persons with Disabilities.
[note] This is based on the estimated number of households reporting at least 1 person with disability, based on post-distribution monitoring data.
[note] It has not been possible to determine whether there is an overlap between WFP and UNICEF beneficiaries.

Inclusion
IPHM is guided by five humanitarian inclusion principles, which aim to ensure that assistance funded meets the needs of the most marginalised. The principles being piloted include: i). applying and funding a twin-track approach (mainstreaming and targeted interventions); ii). engaging and partnering with representative groups including WLOs/WROs; iii). adhering to best practice in design, implementation and practice; iv). leveraging humanitarian leadership for inclusion; and v). embedding inclusion, exclusion and safeguarding into the approach to risk. While the results framework requires evidence that implementing partners have taken action to implement one or more of these principles, it became apparent that some indicators are more relevant to partners (2, 3, 5) while others guide FCDO’s strategic direction (1, 2, 4).
[note] See Annex A of the IPHM Business Case.

For this first reporting period, partners were not given sight of the principles in advance. This was in part due to the business case going through final approval as the response was being developed. As such, the opportunity to utilise the principles to shape design and implementation was missed. However, by reporting against the principles retrospectively, this AR was able to glean important insights and lessons.

Given WFP predominantly delivered top-up cash assistance to beneficiaries already registered through the Government’s 4Ps mechanism as well as 318,000 family food packs and other non-food items from the DSWD, it did not engage with WLOs/WROs in its delivery chain nor deliver what would be classified as a “targeted intervention”. While FCDO funding did not support targeted gender-based violence (GBV) prevention activities, DSWD field staff who serve as case managers for 4Ps households have received GBV training as part of a wider comprehensive approach. Measures were taken to apply best practice in mainstreaming. This included use of disaggregated data (sex, age, disability) and distribution monitoring (DM) and post-distribution monitoring (PDM) to identify gender, disability, protection, and accountability challenges. PDM findings indicated that most respondents: i). did not encounter security or access challenges (99% and 95% respectively); ii). were treated with respect (99.95%); and iii). were well-informed about the amount of the top-up (90%), the schedule of assistance (89%), and how and where to receive/withdraw the cash (96%). It also showed an increase in the proportion of households reporting that women make the decisions on how to utilize the money received (such as what to buy or how to spend the amount). Some good practice was evident in disability accessible information to beneficiaries (e.g. use of multiple modes of communication) however did not go as far as best practice (e.g. partnership with organisations of persons with disabilities). Safeguarding measures were also put in place.
[note] Where challenges occurred, they related to crowded sites, long lines at ATMs and poor weather and the need to enhance awareness about selection criteria, the number of transfers and how to access the feedback mechanism.

In contrast, UNICEF took a twin track approach, implementing targeted measures via its specific focus on WASH for Aeta indigenous communities in the remote municipalities of Divilacan and Maconacon and through the range of interventions delivered (e.g. menstrual hygiene promotion and reproductive health activities in schools and sessions on prevention of PSEA). While UNICEF partnered with four INGOs/NGOs, including specialist organisations focused on targeted GEDSI interventions (e.g. Plan, Catholic Relief Services), they did not directly partner with WROs/WLOs. On principle three (best practice in design and implementation), actions were taken including simple design and adaptation tweaks, such as (re)scheduling community sensitisation sessions during off-peak hours to accommodate care responsibilities and prioritised special lanes for pregnant women, older persons, and persons with disabilities. For WASH repairs in schools, child centres and health facilities, while no new disability accessible facilities were built, a number of measures were taken to improve the accessibility of facilities repaired particularly for children (e.g. installing toilets appropriate for children’s height) and to some extent for some persons with disabilities (e.g. improving paving/pathways to facilities for easy access). Safeguarding measures were also put in place.
[note] GEDSI: Gender Equality, Disability and Social Inclusion.

Speed of response
FCDO fully supports the critical requirement for rapid response to save the lives and livelihoods of people affected by disasters. Specific targets have been set for global humanitarian instruments that FCDO centrally funds. For the UN’s Central Emergency Response Fund (CERF), the time between a UN Resident Coordinator submitting a request and for OCHA to then centrally review, approve and disburse funds should be within 12.1 days. In the case of IFRC’s Disaster Relief Emergency Fund (DREF), the time between the request from a National Society and the approval of the allocation should be less than 10 days. In the case of Start Fund, the average number of days between crisis onset and alert raised for rapid onset crises was 16.6 days. However, FCDO has not set benchmarks on the speed its bilateral support to sudden onset crises should be agreed, though is now being tracked.
[note] Start Fund Annual Review 2023/2024.
[note] An exception is the former Rapid Response Fund, in which it was expected that AGs with NGOs would be agreed within 13 days of a response.

For the the Philippines response, it is difficult to measure a specific event, as the country was hit by six typhoons within a 25-day period. There was initial variance in views within the UN on whether to mobilise only resources available in-country rather than seek external assistance. As the scale of the impact became clear, the UN launched an appeal. If this is taken as a yardstick, then FCDO approved a bilateral funding allocation 2 days later, and approved allocation against UNICEF and WFP proposals 12 and 14 days later respectively.

Although not part of this AR, this was in line with the timeliness of the Vietnam and Vanuatu, where it took on average 3.3 days between a government request to FCDO making a funding decision and a further 9.3 days for proposed projects to be approved. There are opportunities for further efficiencies, including on pre-selecting partners and streamlining proposals.

Proportionality
The table below sets out FCDO’s bilateral share of international assistance for the Philippines response as a percentage of total requirements based on UN and IFRC appeals and what funding both have received to date. There are currently no central FCDO benchmarks for what represents a reasonable share for disaster response, but this is something that is due to be tracked. Figures for the Vietnam and Vanuatu response have been added for comparison.

Response	UN appeal	IFRC appeal	Total UN & IFRC	FCDO bilat	% share of total required	Total appeal funds recd	% share received
Philippines Multiple cyclones	$42.2m / (£33.3m)	CHF5.8m / (£5.2m)	£38.51m	£1m	3%	£19.6m	5.1%
Vietnam Yagi	$31.7m / (£23.9m)	CHF4m / (£3.6m)	£27.5m	£1m	3.6%	£10.9m	9.1%
Vanuatu EQ	N/A	CHF5m / (£4.4m)	N/A	£0.8m	N/A	-	-
[note] The UN decided not to launch an appeal in Vanuatu.

Accountability
The target set for the indicator is 100% of projects involved affected communities in at least one of the following stages: needs assessment, project design, implementation, and review/evaluation. For the Philippines, both agencies met this target. For example, both undertook post-distribution monitoring to assess beneficiaries’ views of the assistance provided. There is a need to explore the opportunities of making this indicator sharper.

Localisation
FCDO strongly backs localising humanitarian assistance. As a signatory of the Grand Bargain, it has set a target of providing at least 25% of humanitarian funding to local and national responders. For the Philippines response, 60% of FCDO funding supported national responders through the contribution to the Government’s 4Ps for cash assistance, as well as the logistics support to the government’s provision of food packs. Both were through the Department of Social Welfare and Development (DSWD). Hence, the target has so far been reached. Although not part of this annual review, the responses to Vietnam and Vanuatu have also reached this target with both having over 50% due to funding provided to the respective national societies of the Red Cross/Crescent via the British Red Cross and IFRC.
[note] See for example: UK humanitarian framework - GOV.UK
[note] According to the Grand Bargain, national and local responders range from local governments to NGOs and community-based organisations (CBOs) to Red Cross and Red Crescent National Societies that are auxiliaries to their governments.
[note] A final figure will be provided in AR2 based on level of funding that went from UNICEF to local partners.

Safeguarding
The indicator set is evidence that IPHM partners have sexual exploitation and abuse and sexual harassment (SEAH) prevention and response policies and measures in place. Both WFP and UNICEF through their reporting and DDAs demonstrated that procedures were in place. WFP is the co-lead of the inter-agency Protection from Sexual Exploitation and Abuse (PSEA) network in the Philippines with dedicated focal points. During the response, these focal points cascaded reminders and guidance. 4Ps case managers received regular training on GBV. DSWD and WFP also co-developed sensitization materials, which included raising awareness on potential SEAH risks related to cash assistance, mitigation measures and reporting mechanisms. UNICEF conducted sessions on PSEA and its implementing partners organized sessions on PSEA for their staff, including those hired for the project, as well as delivering a social media campaign highlighting messages on PSEA. Neither agency reported SEAH cases during the response. Although procedures are in place, there are opportunities for both agencies to continue reinforcing them.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Although in its first year, the IPHM demonstrated its value in being able to respond rapidly and effectively. Hence, it warrants continuation as there is a very strong likelihood of major crises occurring within the region, for which there will be an expectation that the UK will respond. This first Annual Review has provided a good opportunity to take stock of the IPHM and highlighted a set of issues that need to be addressed to improve its agility and performance.

## C. DETAILED OUTPUT SCORING

Output Title	Philippines Multiple Typhoon Response
Output number:		1	Output Score:	A
Impact weighting (%):		100	Weighting revised since last AR?	N/A

Indicator(s)	Planned	Achieved	Score
Number of people provided with cash assistance	21,750	21,750	A
Number of people provided with drinking water	13,919	12,200	A
Number of people reached with sanitation activities	4,855	4,288	A
Number of people reached with hygiene kits	6,750	6,220	A
Number of people supported by WASH in schools & health clinics	8,426	7,470	A
Number of people benefiting from relief packages	170,000	170,000	A
[note] Following the PROF Scoring Template, a score of A (outputs met expectations) is met if the achieved figure is within 87.5% and 112.5% of the expected result.

Describe the output’s activities and provide supporting narrative for the score.
WFP’s response
WFP met its target for both cash assistance and provision of family food packs. In the case of cash assistance, WFP and DSWD rapidly organised the provision of cash assistance to help meet people’s immediate food and other urgent needs and recovery. This was in the form of a top-up to the government’s 4Ps social protection programme. It targeted the most affected areas and prioritised households with children under 5, given the high levels of stunting in children under 5 in the affected areas. Through FCDO funding, 4,350 households (21,750 people) received two months cash assistance as planned, of which 38% were women-headed households. This formed part of the 30,200 households (over 151,000 people) reached with cash assistance through the 4Ps.
[note] The UK provided the initial funding to develop the government centres that assemble and store food packs for humanitarian response. This was paid for from underspend from Typhoon Haiyan in 2013.
[note] A transfer of PHP 3,350 per household per top-up (approximately £44/US$57) was used and coordinated with government and Cash Working Group. The two-month top-up was paid in a single instalment to reduce costs.

Distribution and post-distribution monitoring was undertaken to assess access to assistance; protection, inclusion and accountability challenges; and immediate food security outcomes. For the latter, there was a marked (positive) reduction in the number of people adopting crisis and emergency coping strategies. Households also adopted less frequent or less extreme coping mechanisms to meet their basic food needs. Food consumptions scores were the only anomaly. They showed a slight drop between the distribution and post-distribution assessments. WFP considers that several factors may have skewed this, so making it less relevant to the other outcome indicators. These include that food packs were distributed just before the cash assistance; rapid response does not provide a true baseline; and some people used the cash for non-food expenditure, such as health, shelter and education.
[note] Based on an improvement in the Reduced Coping Strategy Index.
[note] Food Consumption Scores are a tool for measuring household food security, assessing the frequency of consumption of various food groups over a 7-day period.

DSWD’s Grievance Redress System was used for community feedback, which then fed into subsequent sensitisation and communications. WFP reported that of the 654 cases logged, 98% of them were positive. The remaining 2% included people excluded from this assistance. This risk was raised in WFP’s proposal. WFP and DSWD generated communications on the targeting rationale and decided that those excluded should receive other assistance being provided. In the joint-donor monitoring mission, it was reported that DSWD had freed up materials, such as for shelter, for those affected but excluded from cash assistance (see also under lessons learned below).
[note] 89% of the cases were logged by women.
[note] E.g. not registered on the 4Ps or on the 4Ps scheme but not having children under 5 nor expecting a child.

In the case of family food packs, FCDO’s funding covered the costs of 20 of the 200 trucks mobilised to transport the packs from their centres to the cyclone-affected areas. FCDO’s support allowed the transport of 34,000 packs for 170,000 people. This contribution built on the funding that the UK provided to the Philippines in response to Typhoon Haiyan in 2013 to build the centres assembling and storing these packs.

UNICEF response
UNICEF WASH intervention met expectations in all output indicators. When the proposal was developed, it was unclear the extent or how long water trucking (and use of vouchers) would be needed. Fortunately, it was limited allowing the shift and increased funding going to the rehabilitation of community water structures, which is better value for money and more sustainable. For each output, the number of people supported was just under the planned target, largely due to assumptions made on household size.

The joint donor monitoring visit in March 2025 revealed three main challenges. The first concerned the speed of the response, in particular delays in addressing sanitation needs, particularly the repair of damaged toilets at household level in flood affected areas. One of UNICEF’s implementing partners had combined FCDO-funded materials for sanitation repairs with funds from another donor to support shelter and wider repair costs. When funding from the latter was put on hold, it took additional time to re-organise this, so that all sanitation costs were covered. Speed was also affected by delays in on boarding some of UNICEF’s partners.

The second concerns the sustainability of interventions and the extent to which they increased resilience to future shocks. Although UNICEF has indicated that interventions, such as for sanitation in community buildings, contribute to strengthening resilience, there is concern that some will not withstand future floods, such as latrines built in informal settlements in flood prone areas. Hence, whilst humanitarian assistance helps address short term needs and integrates build back better as far as possible, there is a need for longer term engagement to build long term protection and resilience.

The third concerns readiness. This focused on the need to pre-position emergency stocks, such as WASH and hygiene kits, particularly on islands or areas that can get cut off for many days due to damage to infrastructure or the inability of ferries or boats to operate.

UNICEF has shown that there was a reduction in the number of cases of water borne diseases in its response areas, though there were not up to date figures for Isabela Province at the time of the final report. There is a need to explore the opportunities for a more dynamic link with the heath sector for the overall WASH response, such as with disease surveillance.
[note] This includes establishing baselines for water-borne disease prevalence and accounting for seasonal variation.

Describe any changes to this output during the past year, and any planned changes as a result of this review
The only change to the WFP logframe related to the small telecommunications and logistics component, for which it was decided that FCDO funding would only go to logistics support for the transport of family food packs. The main cash component remained unchanged.

In the case of UNICEF, a set of changes were made to the logframe, which were concluded in March 2025. These reflected shifts in requirements during the response, such as limited need for water trucking, so reallocating funds to rehabilitating community water sources; and increasing toilet repairs due to reduced need for semi-permanent toilets in evacuation centres.

Lessons learned this year and recommendations for the year ahead
Lessons for future Philippine responses

WFP/cash assistance
Cash assistance: providing rapid cash assistance, such as through the 4Ps, is an effective and efficient way of supporting typhoon and flood affected populations. There is a need to monitor how this evolves, including from the lessons learned from this response, and its potential to become a more regularised component of the Government’s response system. This includes considering issues raised in this AR, as well as the links with other social protection mechanisms, such as Walang Gutom.
[note] Government Food e-Voucher Program.

Targeting: WFP and DSWD decided to focus only on households with children under 5 or those expecting children, given the high levels of stunting in children under 5 in affected areas and resource constraints. Hence, they excluded other vulnerable groups both within and outside of the 4Ps. However, measures were reported to be in place to support those excluded with other assistance. Exclusion has been raised in other reviews and the risk matrix of this funding. The after-action review and final report acknowledge the need to look at targeting criteria and the potential to include other vulnerable groups already registered in the 4Ps. WFP has also noted that there are ongoing discussions about expanding support beyond the 4Ps, such as through the horizontal expansion of other government social protection programmes, such as Walang Gutom, but this requires overcoming policy and administrative challenges. There are also opportunities to look at the role that disaster risk finance could play in supporting rapid and predictable assistance.
[note] Such as by the World Bank and others, including in previous cases when the 4Ps has been vertically expanded to address shocks. This includes an Oxford Policy Management review for the 2013 Haiyan response.

Communications. Linked to targeting is the need for good communications, so there is clarity on the rationale for targeting and how the excluded can access other assistance.

Coordination: there needs to be close coordination between those agencies supporting DSWD in using 4Ps for shock-responsive social protection, such as UNICEF and WFP; as well as their engagement with other agencies providing cash assistance, such as through the cash working group.

Anticipatory action and disaster risk finance: proposed legislation, the Bill on the Declaration of State of Imminent Disaster, provides the opportunity to adapt social protection systems, such as the 4Ps, to support anticipatory action. This could include adjusting the CERF-funded Anticipatory Action Framework (to which the UK is a central contributor) to supporting the 4Ps. While the bill is being considered in Congress, ordinances may be pursued at a local level, particularly in disaster-prone areas.

UNICEF/WASH assistance
WASH will remain a priority for future typhoon and flood responses. There is a need to continue to explore the range of partners supporting WASH and consider their geographical footprint, readiness, cost and the ability to ratchet up a response rapidly, as well as address the other issues raised above, such as the sustainability of the response intervention and forging stronger links with the health sector, such as surveillance.

Pre-agreed partnerships: the time taken to onboard some partners caused delays. UNICEF is trying to mitigate this for the future by making sure standby partnerships are, as far as possible, in place in advance of the typhoon season.

After-action review: This had not been completed at the time of the final report, this will provide an opportunity to discuss with UNICEF and other partners opportunities for enhancing WASH sector delivery.

Other lessons identified by UNICEF include: i). once markets are operational, distributing vouchers (or cash) for household supplies is preferable to donating hygiene and water kits as it empowers households to purchase goods based on their specific WASH needs; ii). it may be necessary in low-income and geographically isolated areas to provide both materials and cash for labour to ensure toilet repairs are completed, given the pressures of other urgent needs; iii). limited availability of skilled labour for plumbing and water system repairs may affect future emergency responses, for which local government could expand the potential pool and arrange deployment of skilled labour from other areas; iv). the roll-out of the National Policy on WASH in Emergencies and Disaster needs to be accelerated, especially in the high-risk regions in the country; and v). successive occurrence of multiple severe storms underlines the need to develop climate-resilient WASH recovery plans at local level, making them a standard component of humanitarian response and integrating them into provincial development frameworks.

Overall preparedness and response
- Early warning: the quantity of rainfall and subsequent speed and scale of flooding due to the typhoons was unprecedented. This was a similar issue with Typhoon Yagi in Vietnam. There is a need to continue examining how effective impact-based forecasting is working in generating early warning and response, particularly at the local level.
- UN responsiveness: although some UN agencies, such as WFP, responded from the start of this succession of typhoons, there could have been a quicker and more determined response from the UN as a whole and after the impact of the first typhoons became apparent. In addition, there were concerns that the triggers for the CERF-funded Anticipatory Action Framework did not adequately match the risks faced, given that it was not triggered for any of the typhoons. There is a need to take stock of the revised framework, which is being updated.

## D. VALUE FOR MONEY

Value for money (VfM) for IPHM is in line with all FCDO humanitarian programmes and focuses on cost, quality, appropriateness, speed and timeliness. In the business case, a key factor in achieving VFM is by using pre-existing arrangements with trusted and experienced partners. In its first year, the IPHM followed this by using pre-existing framework agreements with UNICEF, WFP and BRC/IFRC. These help to ensure quality with partner policies and approaches being consistent with relevant legal requirements and policy commitments of the UK Government and international humanitarian standards.

The IPHM was designed to respond quickly through the most appropriate delivery partners depending upon the countries impacted and the specific needs identified. As indicated in section B, speed of response is one of the outcome indicators. For the Philippines response three responses to date, it took 2 days after the UN appeal was launched for funding to be approved and 13 days after this request for specific projects to be approved. The steps include assessing the need for a response following a disaster; setting out the case for a response and securing funding; requesting and reviewing a proposal from one or more humanitarian partners; getting approval for these; negotiating/setting up an agreement with the partner; receiving a request for funds and actioning the payment on the FCDO system. This timescale does not include funds being released by FCDO accounts as this is out of the programme’s control. Although there are currently no benchmarks for the speed of bilateral responses, this is starting to be tracked and there are opportunities for efficiencies, as systems and efficiencies are improved. The average response time for the first year can be used as an initial baseline and adapted when broader tracking figures from across FCDO appear.
[note] Taking the three responses to date, it has taken on average 2.8 days after a government (or UN) request for funding to be approved and 13.6 days after this request for specific projects to be approved. It has then taken a further 9 days for the payment to the agency to be processed by the IPHM team.

The IPHM has saved a considerable amount of time and resources without the requirement to write a business case for each response. Three business cases would have been needed to have been prepared within a 5-month period, which would have pulled people away from focusing on the responses. There is still a need to write submissions for each response, but this is a much less time intensive than writing a full business case. There is a need to explore whether there are ways to streamline the approval and start-up process.
[note] This includes the opportunity of developing a business case retrospectively within 3 months of a response.

WFP response
In the Philippines response, WFP’s use of the 4Ps to provide cash assistance demonstrated significant gains in operational efficiency and cost-effectiveness by leveraging the Government’s existing social protection infrastructure, particularly its pre-validated beneficiary lists. With targeted beneficiaries already holding active bank accounts, WFP was able to deliver cash assistance rapidly through secure, real-time digital transfers using WFP’s corporate payment platform, eliminating the need for field-level registration or verification. This streamlined approach reduced lead times, administrative overheads and logistical complexity. Additionally, the platform enabled faster reconciliation and accurate financial reporting. Providing cash is a best buy for humanitarian assistance. Cash allows the purchase of goods and services relevant to the varied needs of beneficiaries, supports local economies and provides a more efficient mechanism of value transfer than in-kind assistance where markets are functioning. To capitalise on these benefits in the future, there is a need to look at opportunities to reduce the costs associated with the provision of cash assistance to improve value for money further still. WFP has noted that it expects to see additional cost savings having entered into an agreement with Land Bank, which is expected to lead to a 40% reduction in fees for interbank transfers.
[note] Each beneficiary received US$114 (GBP 89.60) which is equivalent to two months worth of assistance. If transfer fees and associated costs are added (e.g, monitoring, salaries, etc), assistance then per beneficiary costs are US$151.62 (GBP 119.17).
In the case of equity (see also under targeting under section C above), DSWD and WFP, given resource-constraints, decided to focus only on providing cash assistance to households with children under 5 or those expecting children, given the high levels of stunting in children under 5 in the affected areas. Hence, targeting excluded other vulnerable groups (e.g. single-parent households with children over 5 and the elderly) who are registered with 4Ps and the near-poor affected by the typhoons/flooding but not eligible for 4Ps. DSWD and WFP noted that those excluded needed to be supported by other assistance. There is evidence DSWD provided this. Based on the PDM results, 38% of households supported by cash assistance are headed by women and 48% reported that women are usually the primary decision makers in relation to household resources.

UNICEF response
Efficiency and effectiveness were achieved by only having to provide a much smaller level of funding than expected to more expensive water trucking, which allowed funds to be directed to the more sustainable restoration of community water supply systems. Efficiencies were also enabled by taking a flexible approach with implementing partners, who adapted work schedules, leveraged existing resources, and empowered field teams to respond swiftly to supply chain constraints. Economically, local procurement of materials reduced costs and there were also savings on logistics and bulk purchasing. Equity was promoted with the focus on the poorest and most remote municipalities, including Aeta indigenous communities, who had been excluded from prior relief efforts. However, some of the gains were lost by the delays in the response.

Further exploration needs to be made to compare the costs of prospective partners in responding to specific needs, including exchanging information with other donors.

E: RISK

The IPHM programme has a risk register and appetite levels set for all categories. Risks are reviewed quarterly at a minimum. The SRO is informed of the main findings of the risk review and confirms if they agree with the assessment of the risk environment at that point in time. There is a standard risk escalation process for the department. As none of the risks are above appetite (nor materialised), there has been no escalation in the review period. For risks linked to specific partners, regular meetings provided an opportunity for issues to be raised and remedial action agreed.

For WFP and UNICEF there was agreement that, with Central Assurance Assessments (CAAs) in place, there was confidence to provide funding immediately and for DDAs of each agencies’ local offices to be completed in parallel with the emergency response, as allowed in FCDO’s Programme Operating Framework (PROF). These have been completed and were within IPHM’s risk appetite. However, the DDAs contain recommendations on follow-up steps to gain further assurance from partners for the future.
[note] WFP’s CAA was last updated in 2023 and UNICEF’s in 2021.

The common risks for both agencies were SEAH, fraud and the potential for further typhoons and flooding. Additional risks for WFP included exclusion, inflation, availability of ATMs and duplicate cases; and for UNICEF, potential slow down due to national holidays and the absorptive capacity of implementing partners. Both have indicated how they have sought to manage risk, some of which is captured elsewhere in the AR (e.g. exclusion and communications in the case of WFP, and absorption capacity in the case of UNICEF).

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Since the programme was approved in September 2024, there has been just over £2.83m in approved funding released under the programme. In all cases, these funds were sourced from regional resources rather than the central Humanitarian Crisis Reserve. As the responses in the Philippes (and also Vietnam) was linked to climate disasters, 100% of the funding is accrued to ICF and tracked against KP1, as it is helping affected populations replaced assets and restore services and hence help build resilience.
[note] Number of people supported to better adapt to the effects of climate change.

As noted in Section E. DDAs were undertaken retrospectively to avoid delays in providing humanitarian assistance, and in line PROF Rules. Both DDAs have been completed for the Philippes response within the AR period. There have been some delays in carrying out DDAs and there is a need assess opportunities for greater speed in concluding these for future responses. Opportunities could include streamlining the DDA questionnaire, so that it focuses more on the local offices of UN agencies and the status of their uptake of headquarter policy and procedures and, in the case of the Red Cross, the interaction between IFRC and national societies, and the latter’s financial, delivery capacity, governance and safeguarding arrangements. This would avoid the repeat of corporate measures already captured in CAAs. Another option would be to engage the FCDO country lead in the process. They could interview or visit partners at their offices to gain assurance of in-country systems. However, many posts that IPHM supports tend to be small and so have limited capacity to do this.
[note] PROF Rule 15.

WFP delivered its project within the agreed time frame, with the cash assistance disbursed very rapidly. In the case of UNICEF, a one month no-cost extension was requested, given the delays in part of the sanitation assistance provided and because of delays in onboarding some partners (see also under Section C above). This was agreed, though on the basis that it would not affect the deadline for the final report, which both agencies delivered on time.

Programme management was largely undertaken by the IPRD programme manager. However, an experienced humanitarian programme manager provided temporary support for the initial stages of the Vietnam response to cover leave. Similar temporary support was put in place for the Vanuatu response and to accelerate the finalisation of DDAs. A wider arrangement has been put in place to mobilise additional programme management support in the event of a major response from existing humanitarian teams in the region and from within the Indo-Pacific Regional Department (IPRD). Those selected have received training in humanitarian programme management by FCDO’s Humanitarian Department.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The Regional Humanitarian Adviser (and SRO) was visiting the Philippines during the time of the multiple cyclones, which provided the opportunity to work with the British Embassy to consult with those engaged in the response, including the UN, Red Cross, donors and NGOs. It also provided the opportunity to meet with WFP and UNICEF to discuss their initial concept notes and subsequent proposals. The UN also agreed for the UK to be an observer on the UN Humanitarian Country Team, which provided a further opportunity to monitor overall need and the response. The WFP proposal also benefited from the review of FCDO’s social protection team and discussions with the Cash Working Group.

Regular meetings were held during the delivery of the response between the individual agency and FCDO (both the British Embassy and IPRD) to discuss progress and challenges faced. Both agencies also provided regular reports, including post-distribution monitoring. In March 2025, the British Embassy participated on a joint donor monitoring organised by WFP and UNICEF to some of the main response areas. Australia, Canada and South Korea, as well as DSWD, also participated. Findings from this mission have been discussed with both agencies, taken up in their final reports and in this review.

There have also been discussions on WFP’s After-Action Review. The UNICEF one is still pending, which will be shared and discussed with FCDO.

The Annual Review was undertaken by a small group comprising the SRO/Senior Humanitarian Adviser, the PRO/Programme Manager, Senior Social Development Adviser (IPRD), Senior MEL Adviser (IPRD) and the Humanitarian Liaison Officer at the British Embassy Manila. It principally involved reviewing the final reports and other reporting of both agencies, as well as follow-up discussions with them, as well as the interactions during the response and the findings of the monitoring mission.

Evidence
For the WFP response, a rapid review was undertaken on the 4Ps prior experience of vertical expansion to support discussions with WFP for the design and delivery of cash assistance. A detailed review and discussions of the distribution and post-distribution monitoring were undertaken, as well as the food security outcome indicators for the WFP support. This included recommending the need for greater consistency between data sets to ease comparisons.

Learning
As this was the first year of the IPHM, the initial responses provided a valuable opportunity to test out the arrangements, so that improvements can be made to allow rapid, more effective response. These have been captured in the lessons learned, which need to be taken forward in the coming year to improve readiness and effectiveness. This should include greater exchange between similar arrangements in other FCDO geographies, as well as alignment with wider developments in FCDO’s humanitarian operating model and partnerships with the other main donor agencies operating in the Indo-Pacific.

The AR has also provided a good opportunity to take stock of the Philippines response and consider future readiness. In the case of another high impact disaster for which government requests external assistance and FCDO thresholds are met, shock responsive social protection offers an effective mechanism for rapid response. However, there will be a need to examine how exclusion is addressed and what efficiencies can be made in reducing delivery costs. WASH will also continue to be a major requirement, and there is a need to continue exploring different partners, including the potential for a more multi-sector response. Further preparatory work needs to be undertaken to explore opportunities for supporting women-led and women-rights organisations.

This annual review will be shared with FCDO’s Humanitarian Department as it provides lessons and evidence of how WFP and UNICEF are performing. This has links with FCDO’s central contribution to the CERF, given that the CERF-funded UN Anticipatory Action Framework that includes support to cash assistance and WASH. There are also links with the strategic partnerships that FCDO has with these UN agencies.

Date of last narrative financial report	30 June 2025	Date of last audited annual statement	N.A.

Annex 1: IPHM Business Case Theory of Change