Programme Completion Review

Title: Essential Services for Maternal and Child Health - Services Essentiels de Santé Maternelle et Infantile en RDC (SEMI)
Final Programme Spend £ (full life): £37,000,000	Review Date:	December 2025
Programme Code: 301372	Start Date: / 22/04/2022	End Date: / 30/09/2025

Summary of Programme Performance

Year	2022	2023	2024
Programme Score	A	B	C
Overall programme risk rating	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	Business Case and Summary (D0002941) 301372 (Published - April 2023)
DevTracker Links to all logframes used during programme lifetime:	Logical Framework (D0003613) 301372 (Published - September 2023)

A. Summary and Overview

The programme was designed to improve health outcomes for 1.6 million women, girls and children and contribute to ending preventable deaths in Kasai, the province with the highest maternal mortality rate in the DRC and one of the poorest provinces in the country. The programme supported the implementation of the government’s National Health Development Plan (PNDS) and the strategy for Universal Health Coverage.

The programme had a two-pronged approach designed to:
Strengthen health systems and improve access to quality, effective and affordable health services by improving the skills of health personnel; increasing the use of health information for better decision-making; improving drug supply chain management at sub-provincial level; improving preparedness for health emergencies; and providing technical support to develop a national strategy for quality of care, public financial management and civil service reform.

Deliver basic maternal, child health, nutrition and family planning services to meet immediate needs in Kasai province, working in tandem with the British Embassy’s girl’s education programme to deliver mutually reinforcing outcomes.

This Project Completion Report (PCR) has assessed performance of the programme over the 3-year period, July 2022, to closure on 31 December 2024 using the logical framework milestones agreed up to September 2024. Key achievements reported are:

- 8,054,563 curative consultations (the target was 7,423,756).
- 503,334 facility-based births (98% assisted by staff trained in providing safer deliveries),
- 502,116 Couple Years of Family Planning Protection (CYP) delivered (target was 259,000)
- 2.21 million Mid-Upper Arm Circumference (MUAC) nutrition screenings provided for under 5s, (achieving 93% coverage in Kasai) with a 74% recovery rate among malnourished children.
- 294,697 pregnant women received malaria Intermittent Preventive Treatments (IPT).
- Sexual and Gender-Based Violence (SGBV) response: 86% of 3,943 reported cases sought care within 72 hours; 92% received Post-Exposure Prophylaxis (PEP) kits.

Systems outcomes reported over the 3-year period include:
- 100% of the 18 health zones in Kasai achieving 90% (or greater) District Health Information Software 2 (DHIS2) completeness and regular HR governance via the open-source Health Workforce Information System (iHRIS).
- 94 motorcycle ambulances provided emergency transport for remote referrals.
- 429 providers trained in using Emergency Obstetric and Newborn Care (EmONC), helping to build capacity in Kasai province.

These achievements suggest (i) increased service utilisation, (ii) better facility-based delivery, (iii) increased family planning uptake and (iv) increased community nutrition screening.
System improvements are noted in (a) national health information system (through DHIS2 completeness), (b) adoption and use of iHRIS and in (c) supply-chain governance.

SEMI was implemented by IMA World Health, working in partnership with SANRU[1], PRODEK[2] and other downstream partners. IMA World Health reports noted delivery risks and challenges during the programme implementation including UK Official Development Assistance (ODA) funding decisions; stock management constraints; activities being donor dependent; attribution (since it received substantial commodity support from other donors); fiduciary and safeguarding concerns and early closure. These are recognised as having impacted on the programme’s ability to fully deliver its anticipated results. Annual review output scores declined over the 3-year period, (from A to B, and then C). A performance improvement plan was introduced to respond to delivery risks. A decision was taken in June 2024 to close the accountable grant on 31 December 2024, three months earlier than planned, due to lack of progress.
[1] Soins de Santé primaires en milieu Rurale
[2] Programme pour le Développement du Kasai (Program for the Development of Kasai)

This PCR assesses the key lessons from this programme’s experiences to achieve sustainable health outcomes in fragile contexts include:
1. greater alignment with national plans and government financing;
2. multi-year investments in systems and governance are needed;
3. procure a provider for robust and independent third-party monitoring, evaluation and validation of data and results;
4. sustained community engagement; and
5. coordinated supply chains (with other partners/donors).

Overall PCR Score and Rationale

The overall PCR score is a B: moderately did not meet expectations. The B score at outcome level reflects the strong performance at the initial stages of implementation, the partial delivery of programme objectives and the declining outputs trend over the 3-year period. The score draws on quantitative and qualitative information and factors in that achievement results have not been independently monitored, evaluated and verified (in 2024) and that early closure will have impacted how end of programme outputs were delivered.

The Business Case envisaged transformative improvements in maternal and child health in Kasai. Systemic constraints and early closure have prevented full delivery of the objectives. In summary:
- Year 1 achieved strong progress (Score A) with the rapid scale-up of maternal, neonatal and child health and family planning services and some systems strengthening.
- Year 2 maintained moderate gains (Score B) but was affected by supply chain delays, measles outbreaks, and attribution challenges.
- Year 3 underperformed (Score C) due to fiduciary and safeguarding risks and incomplete achievement of key outputs (e.g. community scorecards (51% vs 85%), maternal death reviews (88% vs 97%), and health financing indicators (unmeasured).

Major lessons learned, evidence generated and recommendations

- Donor-dependent service delivery support can only achieve short term gains. Broader health system strengthening is needed for sustainable outcomes. (e.g. ending additional support for community accountability mechanisms led to a reduction in the collection of indicators needed to complete score cards).
- Community engagement is critical in driving the uptake of service provision. (e.g. RECO[3]-led home visits and local mobilisation contributed to improved nutrition screening and increasing demand for family planning (FP) services. These gains are not sustainable without predictable support).
  [3] Relais Communautaire (Community Health Worker)
- Digital tools e.g. the Safe Delivery App and BHIMA can be transformative and contribute to improved clinical decision-making and supply chain transparency but need sustained investment in IT infrastructure and training.
- Data completeness does not equal data reliability - (e.g. DHIS2 reporting was strong with high coverage, but the measles outbreaks underscored the need for triangulation and independent verification of the data).

Recommendations

Future programmes should work with government on what a sustainable package looks like in light of financing shifts and focus on public financial management and reforms. Sustainability and systemic resilience can then be prioritised through:

- Focus on public financial management and reforms : e.g. flat-fee policies for the poorest and most vulnerable groups in provincial health plans; explore/consider mechanisms for promoting increased provincial government investment in health service delivery, support implementation of national insurance schemes to fund strategic purchasing of services. Working with government - to integrate programme interventions into government systems and domestic financing, reducing donor dependency and linking technical solutions to national policy and public financial management (PFM) reforms for sustainable ownership and predictable funding.
- Increase integration of impactful digital platforms into national systems: e.g. support Ministry uptake and expansion of iHRIS and BHIMA ; integrate DHIS2-IDSR[4] trackers for real-time outbreak surveillance.
  [4] Integrated Disease Surveillance and Response (IDSR)
- Improve supply chain resilience: e.g. integrate procurement processes into the national supply chain, have dual procurement pipelines; invest in infrastructure (e.g. depot capacity); align with a single national essential medicines list and harmonise support across donors.
- Focus on quality of care. Support the Ministry to operationalise the national strategy for quality of care and patient safety
- Strengthen community systems: e.g. predictable support for CODESA[5] and RECO structures so they can be sustained; link community scorecards to provincial planning and accountability.
  [5] Comité de Développement de l’Aire de Santé (Health Development Committee)
- Strengthen monitoring and verification: with independent third-party monitoring for data validation; immunisation coverage checks; triangulation of DHIS2 data with independent surveys.
- Tackle adolescent health gaps: e.g. by expanding adolescent-friendly Family Planning services and have targeted SBCC[6] campaigns to reduce early pregnancy and improve nutrition outcomes.
  [6] Social and Behaviour Change Communication (SBCC)

How this report was conducted

This PCR draws on the SEMI Business Case (April 2021), which outlines the programme’s strategic objectives, theory of change, expected outcomes, and VFM projections. It has provided the benchmark for performance assessment. The Years 1 to 3 annual reviews were also considered to track progress against the logical framework, output indicators, and milestones, alongside other reports.

Actions following approval of this report

Lessons will be used to inform future UK engagement in DRC.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£37,000,000	£24,624,611.38
Timeframe	22/04/2022 to 31/12/2024	32 months
Outcomes	to “improve [the] quality of delivery, family planning and child immunisation coverage, [achieve] stronger health systems and better quality, effectiveness and affordability of services to achieve sustainable impact”. To achieve this outcome, three intermediate outcomes were envisaged: / Intermediate outcome A: Better access to quality maternal, newborn, child and adolescent health services. / Intermediate outcome B: Stronger health system, including emergency preparedness and health security. / Intermediate outcome C: More access to rights-based family planning services for all women and girls in Kasai province.	Partial success was achieved at the outcome level. Service utilisation exceeded its milestone (79% vs 70%), and family planning uptake more than doubled (163,412 vs 82,500). Nutrition recovery met expectations (77%), but indicators for zero-dose children and Human resources for Health (HRH) harmonisation fell short due to early closure. Logframe changes during implementation, like changing service utilisation to the outcome level, and removing EmONC readiness, reflected the operational constraints and reality, but also affected measuring sustainability when the original assumptions made are considered. Overall, SEMI improved service use and HR systems, but systemic reforms and quality of care improvements have lagged behind, impacting sustainability.

Indicators	Over all Target		Over all Achievement		% of Target Achieved
	%	Number	%	Number
Outcomes: Improve Quality of delivery, family planning coverage and child immunisation coverage / Outcome score = B. Moderately did not meet expectations
Outcome Indicator 1: Number and percent curative utilization in Kasai province.	65%	7,423,756	71%	8,054,563	108%
Outcome Indicator 2: Number of couple years of protection (CYPs) distributed through the provision of family planning services.	_	295,000	_	502,116	170%
Outcome Indicator 3: Recovery rate of malnourished children between 6 to 59 months at 5th visit in health zones covered by the programme.	65%		74%		114%
Outcome Indicator 4 : Proportion of children who have received none of the recommended childhood vaccines (“Zero dose children”) in Kasai province.	17.5%	_	28.7%	_	63%
Outcome Indicator 5: Semi-annual harmonisation by the DPS of HRH "listes declaratives" in Kasai health zones with iHRIS data.		3		2	67%
Output 1: Increase access and uptake of essential health, family planning and nutrition services / Output score = A. Impact weighting = 30%. Revised since last annual review? = No
Outcome indicator1.1: Number and percent of pregnant women who received four doses of IPT while attending antenatal care .	64%	296,605	63%	294,697	99%
Output Indicator 1.2: Percentage of surveyed health facilities able to offer basic or comprehensive emergency obstetric and neonatal care	55%	_	45%	_	82%
Output Indicator 1.3 : Percent of births at surveyed health facilities for which required elements of partograph were correctly completed	60%	_	67%	_	112%
Output Indicator 1.4: Percent of maternal deaths reviewed using the MDSR methodology	95%	_	97%	_	102%
Output Indicator 1.5: Percent of sexual and gender-based violence (SGBV) survivors arriving at a health facility within 72 hours who received PEP kits.	99%	_	92%	_	93%
Output Indicator 1.6: Average number and proportion of children between 6 and 59 months screened for malnutrition by community volunteers each month.	84%	252,684	93%	276,318	109%
Output Indicator 1.7: Proportion of Confirmed malaria simple cases treated appropriately according to MOH guidelines during the reporting period	96%	_	94%	_	98%
Output 2: Increase community participation, mobilisation, planning, delivery, & monitoring health service delivery / Output score = B. Impact weighting = 10%. Revised since last annual review? = Yes, reduced in Year 3)
Output Indicator 2.1: Number of CODESA meetings held in Kasai province during the reporting period	98%	1191	99%	1205	101%
Output Indicator 2.2: % health centres with at least one community score card (BCP) completed in the last 6 months	85%	1377	51%	820	60%
Output Indicator 2.3: User satisfaction of health services expressed as a percentage (%) by the community through BCP	95%	_	75%	_	78%
Output 3: Improved health workforce quality and management / Output score = A. Impact weighting = 15%. Revised since last annual review? = No
Output Indicator 3.1: Number and percentage of health zones with at least 70% of staffs' HR data regularly submitted in iHRIS .	90%	16	89%	16	100%
Output Indicator 3.2: Relevant iHRIS data and analysis available 1 week prior to each HRWG meeting for decision makers at the right time .	_	12	_	15	125%
Output 4: Supply chain transparency and availability of essential medicines & commodities at health facility level / Output score = B. Impact weighting = 15%. Revised since last annual review? = No
Output Indicator 4.1: Percentage of days that health facilities report stock-outs of 5 tracer drugs (injectable contraception, Oxytocin, SP, Zinc, Amoxicillin)	9%	_	14%	_	64%
Output Indicator 4.2: Percentage of medicines that are wasted due to expiration at CDR CEDIMET.	<1%	_	0%	_	> 100%
Output Indicator 4.3: Drugs order satisfaction rate	90%	_	71%	_	79%
Output Indicator 4.4: Number and percentage of meetings with minutes of the Medication Working Group at the DPS level. Target: minimum two meetings per quarter.	_	17	_	20	118%
Output 5: Improve availability and quality of Health Information System / Output score = B. Impact weighting = 15%. Revised since last annual review? = No
Output Indicator 5.1: Number of health zones with a DHIS2 data completeness more than 90% .	90%	16	100%	18	113%
Output Indicator 5.2 : Number of health zones with less than 1 validation rule violated, per form, on average.	95%	17	100%	18	106%
Output Indicator 5.3: % Monthly feedback reports from provincial health information office to Health Zone .	95%	51	61%	33	65%
Output Indicator 5.4: Proportion of health facilities submitting disease surveillance weekly reports on time to the health zones .	75%	304	69%	281	92%
Output 6: Support improved governance and financial management / Output score = B Impact weighting = 10%. Revised since last annual review? = Yes. Indicators dropped after early closure decision)
Output Indicator 6.1 : % health zone work plans include reference to community score cards (BCP), gender equality, and an updated list of vulnerable groups	_	_	_	83%	_
Output Indicator 6.2: Average score of financial accessibility expressed by the community through community score cards (BCP), e.g. Cout abbordable et Tarif affiché	_	96%	_	98%	_

Overall assessment of programme outcomes, sustainability and VfM

The logframe outcomes were only partially achieved. Some indicators exceeded targets, but attribution is complex as gains made relied on commodities supplied by other donors. Improvements in quality of care were delayed because of funding interruptions, logistical challenges, incomplete implementation of planned activities and systemic governance issues. Maternal death reviews and SGBV responses also missed their targets. Workforce and health information systems (DHIS2, iHRIS) performed well, but supply chain governance and health financing reforms were not fully achieved. Early closure limited measuring sustainability and impact.

Performance in Year 3 declined due to the early closure decision (taken in June 2024), which also affected supply chain plans. External shocks (e.g. measles outbreaks) also affected delivery of the programme’s objectives. The digital systems (DHIS2, iHRIS, BHIMA) and HR governance introduced can be continued with investment and Ministry of Health (MOH) commitment. Otherwise, progress will be lost.

Value for Money, Unexpected Outcomes, and Adaptiveness

The Business Case envisaged strong value for money, estimating $190 per DALY[7] averted, below the $587 GDP per capita threshold, and indicating cost-effectiveness. Procurement savings, integration with other donor programmes, and digital tools (DHIS2, iHRIS, BHIMA) indicate improved efficiency. Increased service delivery and some system reforms enhanced effectiveness. Equity benefits from free childbirth and flat-rate pricing were not sustained after community accountability mechanisms ended and plans for third-party monitoring were not implemented, limiting independent verification.
[7] Disability Adjusted Life Years (DALY)

Adjustments in Years 2 and 3 shifted focus from systemic transformation to maintaining essential services and scaling digital tools. These changes improved short-term efficiency but constrained the original VFM case. In summary, the programme delivered short-term health benefits, but systemic changes for long-term impact remain incomplete. Lack of independent or third-party monitoring data constrains value for money analysis (a lesson from this programme).

SEMI programme’s Theory of Change and results framework (including any changes to outcome indicators)

The original Theory of Change (TOC) remains valid in terms of linking service delivery improvements to health gains. Key assumptions made about government engagement and sustainability have not held. During implementation key changes made included:

- Accelerating the digital tool rollout (e.g. the Safe Delivery App and BHIMA) to address training and supply chain gaps;
- Introducing a Performance Improvement Plan in Year 3 following identified need to strengthen fiduciary and safeguarding and shifting the focus to essential outputs;
- Ending parallel support for community engagement which weakened them as an accountability system; and
- Early closure decision which affected the push on systemic reforms.

## C: Detailed Output Assessment

Detailed Output Assessment

Progress against the outputs is summarised in the table above. The programme exceeded targets for curative consultations and family planning uptake, reflecting strong early demand generation, supported by other donors. Health information systems performed well, with DHIS2 reporting at 95% and full iHRIS adoption. Supply chain efficiency appeared strong, with zero drug expiry, though this was not independently validated. Some indicators fell short: community scorecard completion dropped to 11% (target 95%) after support ended, and surveillance timeliness reached only 72% (target 85%), exposing gaps in emergency preparedness despite high DHIS2 completeness.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The SEMI programme started well but ended off-track. In 2022, it scored A, reflecting good progress despite start-up delays and funding decisions. Lifesaving services were prioritised, and Output 1 indicators (e.g. antenatal care attendance, skilled deliveries, and immunisation) met or exceeded expectations.

Performance declined to B, in 2023 as systemic challenges emerged. Community participation and health workforce management improved, but emergency obstetric and neonatal care, supply chain reliability, and nutrition data quality reduced. Stockouts of essential medicines, undermined service delivery. Attribution remained unclear because family planning and nutrition depended on commodities supplied by other donors.

In 2024 the programme scored a C, after early closure in December 2024. Outputs on access to essential services and community accountability fell (e.g. maternal death reviews reached only 88% (target 97%), and SGBV survivors receiving PEP kits fell to 84.5% ( target 99%). Malnutrition screening only reached 86% (target 97%). Disease surveillance timeliness was 72% (target 85%). Supply chain performance improved slightly, but drug order satisfaction remained low at 71% and health financing indicators were not measured due to early closure. The only consistent success was Output 3 on health workforce management, with iHRIS adoption and HR data completeness targets being met, and the Kasai HR Statistical Directory developed.

Reporting confirms these findings and notes that although some utilisation indicators exceeded expectations, these were due to external factors like the Government of DRC’s free maternity care initiative and World Bank-funded commodity supply. Reporting highlights the governance and accountability challenges, weak financial controls and the absence of an independent third-party monitoring provider limiting confidence in reported results. Reporting also notes supply chain management and disease surveillance weaknesses, despite technical assistance support, and that sustainability relies on donor funding and incentive-based delivery models.

Monitoring and Evaluation Approach

The Monitoring and Evaluation (M&E) framework relied mainly on partner reporting, FCDO oversight, community feedback, and routine data systems. IMA and its partners provided quarterly narrative and financial reports, while FCDO monitored progress through meetings, reviews, and field visits. Community scorecards and CODESA meetings worked well in Years 1 and 2 but ceased in Year 3 when support ended. Indicators were tracked via DHIS2 and iHRIS, complemented with facility data and partner surveys. These were not independently triangulated. Conflicting sources, i.e. partner reports versus field findings and community feedback, reduced confidence in results and early closure meant end of programme assessments were not completed, leaving evidence gaps. The heavy reliance on partner reporting and the absence of third-party monitoring limited independent verification and makes attribution and sustainability difficult to assess.

Sustainability depends on strong government systems and financing. The programme’s reliance on donor-funded parallel mechanisms shows that future programme interventions should be integrated into national policies and domestic budgets and consider the health sector’s on-going public financial management (PFM) reforms and budget processes. This will allow investments in HR systems, supply chains, and community accountability to become institutionalised and government funded. Anchoring these priorities in dialogue with Ministries of Health and Finance will reduce donor dependency and build long-term resilience.

Lessons learned from the outputs / Recommendations for future programming

Key lessons to note include:
- Sustainability requires domestic financing and ownership - parallel systems and donor reliance undermine long-term viability.
- Technical interventions alone cannot solve systemic weaknesses - stockouts persisted despite BHIMA investments because of weak governance and accountability mechanisms. Political economy analysis is needed to complement technical solutions.
- Data integrity and attribution are critical - family planning and nutrition indicators were inflated by other donor inputs, highlighting the need for independent verification.
- Community accountability mechanisms proved fragile; scorecards ceased when support ended showing engagement must be institutionalised, not donor dependent.

Recommendations for future programming:

- Integrate programme interventions with government systems and domestic financing to reduce donor dependency, link technical solutions to national policy and PFM reforms for sustainable ownership and predictable funding.
- Keep programme design simple, focusing on fewer, high-impact interventions.
- Meet key government / provincial interlocutors at regular intervals to discuss the programme’s intervention and sense check it remains aligned with government policy and longer-term financing plans.
- Include independent monitoring and verification from the start.
- Institutionalise community engagement within Ministry of Health systems.
- Address governance and corruption risks before scaling technical solutions.
- Prioritise quality over quantity, shifting from utilisation metrics to indicators of safety and effectiveness.

E: Risk

Overview of programme risk during the past year and over the life of the programme

SEMI operated in a high-risk environment, rated as major from the outset. It faced structural challenges for fragile contexts (weak governance, corruption risks, logistical constraints, and political volatility) which were compounded by systemic weaknesses in DRC’s health sector, including underfunded public services and donor reliance.

In Year 1, risks were mainly operational and financial, driven by start-up delays and funding decisions. Mitigation focused on maintaining essential services and introducing fraud and safeguarding measures. By Year 2, risk exposure increased as supply chain governance and data integrity issues persisted. FCDO strengthened oversight through reviews and field visits. The absence of independent third-party monitoring limited assurance. In Year 3, fiduciary concerns, safeguarding gaps, and weak financial controls escalated risk. A performance improvement plan was put in place, but due to lack of progress the decision was taken (June 2024) to close the grant early (December 2024). Closure was managed through FCDO’s Programme Operating Framework, including risk mitigation and an asset disposal plan.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

IMA met reporting requirements and submitted timely quarterly narrative and financial reports, and have provided audited statements after the grant ended in December 2024. Early reporting was detailed and responsive, but data validation and attribution remained weak, and quality declined as activities wound down. Forecasting accuracy was challenging in Year 1 due to procurement delays and funding decisions. Asset management was strong, with registers maintained and disposal plans implemented.

Risk dialogue was proactive, including fraud and safeguarding awareness campaigns. Coordination with other donors could have been stronger to avoid duplication in supply chain interventions. These risks were flagged in the Business Case, but escalation measures were only applied during the Performance Improvement Plan (PIP) which was too late to reverse declining performance.

Prior to the PIP, there were signals that adaptation was needed. But emphasis was placed on compliance and meeting targets. This may have limited opportunities to explore innovative solutions and make timely adjustments. Adaptive programming needs continuous learning and flexibility for programmes to adjust strategy and approach as conditions evolve. FCDO and its partners can benefit from proactively doing so in fluid / fragile contexts, exploring possible changes to the direction of travel, before opting for more formal interventions like a PIP.

Lessons Learned and recommendations for programme management:

- Embed adaptability early – by designing programmes with flexible budgets and delivery mechanisms that can respond to changes in the operating context.
- Encourage continuous learning with implementer/partners – set time aside for iterative learning and responses during implementation.
- Act on early warning signs – use data (quantitative and anecdotal) and feedback to develop timely adjustment triggers, as a precursor to risk appetite escalation triggers and exit strategies.
- Simplify programme scope - by focusing on quality of care and governance reforms.
- Ensure sustainability - through domestic ownership and political economy analysis to design realistic engagement strategies.
- Invest in independent third-party monitoring and evaluation - from the start.
- Strengthen donor coordination - through joint planning; harmonised procurement frameworks to avoid duplication and maximise impact.

Date of last narrative financial report	31 March 2025	Date of last audited annual statement	May 2025

…