## Annual Review

Title: Essential Services for Maternal and Child Health - Services Essentiels de Santé Maternelle et Infantile en RDC (SEMI)
Programme Value £ (full life): £37 million		Review date: May 2025
Programme Code: [AMP ID#] 301372	AMP start date: 22/04/22	AMP end date: / 30/9/25

Summary of Programme Performance
Year	2022	2023	2024
Overall Output Score	A	B	C
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	Business Case and Summary (D0002941) 301372 (Published - April 2023)
DevTracker Link to results framework:	Logical Framework (D0003613) 301372 (Published - September 2023)

A. SUMMARY AND OVERVIEW

Description of programme

The British Embassy Kinshasa’s (BEK) Essential Services for Maternal and Child Health programme (Services Essentiels de Santé Maternelle et Infantile en RDC (SEMI)) strengthens the health system in the Democratic Republic of Congo (DRC) through direct interventions in the Kasai Province, supported by evidence-based health policy reform at the national level.

The programme was designed to improve health outcomes for 1.6 million women, girls and children and contribute to ending preventable deaths in Kasai, the province with the highest maternal mortality rate in the country and one of the poorest provinces in DRC. The programme supports the implementation of the government’s National Health Development Plan (PNDS) and the strategy for Universal Health Coverage.

The programme has a two-pronged approach designed to:
Strengthen health systems and improve access to quality, effective and affordable health services by improving the skills of health personnel; increasing the use of health information for better decision-making; improving drug supply chain management at sub-provincial level; improving preparedness for health emergencies; and providing technical support to develop a national strategy for quality of care, public financial management and civil service reform.

Deliver basic maternal, child health, nutrition and family planning services to meet immediate needs in Kasai province, working in tandem with BEK’s girl’s education programme to deliver mutually reinforcing outcomes.

Summary supporting narrative for the overall score in this review
This Annual Review covers the period January 2024 – December 2024. The previous Annual Review identified programme areas for improvement, such as data quality, reporting and results attribution and financial management. In February 2024, a Performance Improvement Plan (PIP) was agreed with the partner and the overall risk rating for the programme was increased. The Accountable Grant Agreement (AGA) was closed early as of 31 December 2024, three months earlier than planned due to lack of progress. The logical framework was updated with milestones agreed up to September 2024 and is the basis for this Annual Review.

A summary of overall performance by outputs is given below:

Output		Score	Weight
1	Increase access and uptake of essential health, family planning and nutrition services	C	30%
2	Increase community participation, mobilization, planning, delivery, and monitoring health service delivery.	C	10%
3	Improved health workforce quality and management	A	15%
4	Supply chain transparency and availability of essential medicines and commodities at health facility level	B	15%
5	Improve availability and quality of Health Information System	B	15%
6	Health financing to support access to health services	Output indicators could not be measured due to early closure.	10%
7	Annual indicators of supplier performance	The output was no longer relevant following decision to terminate the AGA	5%
Overall output score		C	100 %

Major lessons and recommendations for the year ahead

Key lessons from this programme include the need to ensure clear attribution of results in logical framework planning and the need for data validation through third party monitoring arrangements or similar mechanisms. The closure of the grant agreement followed the FCDO Programme Operating Framework.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
Impact:	to ‘reduce maternal and under-five mortality rates in Kasai province’.
Outcome:	to “improve [the] quality of delivery, family planning and child immunization coverage, [achieve] stronger health systems and better quality, effectiveness and affordability of services to achieve sustainable impact”. To achieve this outcome, three intermediate outcomes were envisaged:
- Intermediate outcome A: Better access to quality maternal, newborn, child and adolescent health services.
- Intermediate outcome B: Stronger health system, including emergency preparedness and health security.
- Intermediate outcome C: More access to rights-based family planning services for all women and girls in Kasai province.
As agreed in the revised logical framework, results were measured up to quarter two of Financial Year 24/25. Two output indicators could not be reported against due to early closure of activities.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Outcome Indicator(s)	Milestone	Progress up to Q2	Comments
1. Number and percent curative utilisation in Kasai province, during the reporting period	990,304 / (70%)	1,112,926 / (79%)	Results moderately exceeded expectations. Several factors including the availability of essential medicines, compliance with flat rate pricing and the implementation of free health care for pregnant women and newborn likely contributed to this success.
2. Number of couple years of protection (CYPs) distributed through the provision of family planning services (utilization) in Kasai province during the reporting period	82,500	163,412	Results moderately exceeded expectations. However, further analysis and data validation would be necessary to determine how far this outcome is attributable to SEMI. A World Bank funded project supplied commodities and supported family planning services. SEMI’s contribution to achieving CYPs was focused on community demand generation activities, notably the provision of sensitisation sessions on family planning, and community activities around international days of action.
3. Recovery rate of malnourished children between 6 to 59 months at 5th visit in health zones covered by the programme during the reporting period.	75%	77%	The partner reported that this outcome indicator met expectations. However, further analysis and data validation would be necessary to determine whether results were attributable to SEMI’s intervention of home visit approach by community health workers to support recovery of affected children. While this might contribute to recovery from acute malnutrition, treatment with Ready to Use Therapeutic Food (RUTF) and Ready to Use Supplementary Food (RUSF) in health centres is key to recovery and was not supported by the programme.
4. Proportion of children who have received none of the recommended childhood vaccines (“Zero dose children”) in Kasai province.	N/A	N/A	Early closure meant specific milestones were not determined, and outcome indicators could not be measured.
5. Semesterly harmonisation by the DPS of HRH "listes declaratives" in Kasai health zones with iHRIS data.	1	N/A	The end of year harmonisation activities did not occur with early closure and so the result did not meet expectations.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This Annual Review finds that the objectives of the programme remain relevant to the context.

## C. DETAILED OUTPUT SCORING

Output Title	Increase access and uptake of essential health, family planning and nutrition services
Output number:		1	Output Score:	C
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (Q2)	Progress
1.1. Number and percent of pregnant women who received four doses of intermittent preventative treatment (IPT) while attending antenatal care during the reporting period	89,520 (75%)	90,464 (76%). Met expectations
1.2. Percentage of surveyed health facilities able to offer basic or comprehensive emergency obstetric and neonatal care	70%	Not applicable in the revised logical framework
1.3. Percent of births at surveyed health facilities for which required elements of partograph were correctly completed	75%	Not applicable in the revised logical framework
1.4. Percent of maternal deaths reviewed using the MDSR methodology during the reporting period	97%	88%. Substantially did not meet expectations[1]
1.5. Percent of sexual and gender-based violence (SGBV) survivors arriving at a health facility within 72 hours who received PEP kits during the reporting period	99%	84.5%. Substantially did not meet expectations
1.6. Number and proportion of children between 6 and 59 months screened for malnutrition by community volunteers per quarter.	295,245 (97%)	262,238 (86%). Substantially did not meet expectations
1.7. Proportion of Confirmed malaria simple cases treated appropriately according to MOH guidelines during the reporting period	96%	85%. Substantially did not meet expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 measures activities related to primary care (the delivery of maternal and newborn health services), family planning, and community nutrition support. Only five indicators were measured as early closure of the grant agreement meant surveys to measure indicators could not be conducted. External factors impacted the attainment of some results, for example indicator 1.7 was impacted by a stock out of antimalaria commodities supplied by the Global Fund. In the absence of a third-party monitor, validation of results and their attribution to the programme was limited.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were adjusted in the revised logical framework to reflect an end of activities by September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Multiple indicators relied on the presence of commodities supplied by other programmes. As a result, success could not be fully attributable to the programme. The impact of stockouts could not be mitigated to achieve targets.

Output Title	Increase community participation, mobilization, planning, delivery, and monitoring health service delivery.
Output number:		2	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) up to Q2	Progress
2.1. Number of CODESA meetings held in Kasai province during the reporting period	2381(98%)	2411(99%) Met expectations
2.2. % health centres with at least one community score card (BCP) completed in the last 6 months	385 (95%)	43 (11%) Substantially did not meet expectations.
2.3. User satisfaction of health services expressed as a percentage (%) by the community through BCP	85%	Not applicable in the revised logical framework

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 measures activities related to the training and supervision of community agents and participative community structures for health. Inputs supported relevant agents and structures to undertake planning, mobilisation, implementation and monitoring of activities within their remits outlined by DRC’s Strategic Framework for Community Participation in Health (PARTICOM). While CODESA (health area development committees) continued to be active, community scorecard completion, indicator 2.2, was below expectations. The early closure of the grant agreement is understood to have contributed to this result.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were adjusted in the revised logical framework to reflect an end of activities by September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Careful consideration of the political economy of incentives for health workers in FCDO health programmes is needed to mitigate, for example, the risk of unsustainable approaches.

Output Title	Improved health workforce quality and management
Output number:		3	Output Score:			A
Impact weighting (%):		15%	Weighting revised since last AR?			No
Indicator(s)				Milestones up to Q2	Progress
3.1. Average number and percentage of health zones with HR data for at least 70% of staff submitted in iHRIS each month during the reporting period.				16 (90%)	16 (90%) - Met expectations
3.2. Relevant iHRIS data and analysis available 1 week prior to each Human Resources Working Group meeting for decision makers (twice per quarter)				4	5 - Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 relates to health workforce quality and management, including the implementation and use of iHRIS, an open-source health workforce information system, developed through the programme’s predecessor. iHRIS captures data on the health workforce at an individual level, supporting improved workforce management. Good progress was made during implementation. Under output 3.2, the programme supported development and validation of the Kasai 2024 Human Resources Statistical Directory, a document that enables provincial and national health authorities to make evidence-based decisions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were adjusted in the revised logical framework to reflect an end of activities by September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

iHRIS has potential and could be taken to scale through adoption by the Ministry of Health.

Output Title			Supply chain transparency and availability of essential medicines & commodities at health facility level
Output number:	4	Output Score:			B
Impact weighting (%):	15%	Weighting revised since last AR?			No
Indicator(s)			Milestone(s) up to Q2	Progress
4.1. Percentage of days that health facilities report stock-outs of 5 tracer drugs (injectable contraception, Oxytocin, SP, Zinc, Amoxicillin)			8%	8%. Met expectations
4.2. Percentage of medicines that are wasted due to expiration at CDR CEDIMET			<1%	0 % Met expectations
4.3. Drug order satisfaction rate			90%	71% Substantially did not meet expectations
4.4. Number and percentage of meetings with minutes of the Medication Working Group at the DPS level. Target: minimum two meetings per quarter.			4	4 Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 captures programme inputs to strengthen procurement and supply chain management for essential medicines and commodities that underpin basic medical care. Areas of weaker performance have been attributed to challenges in the supply chain, including logistical challenges on the road between Kinshasa and Kasai.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were adjusted in the revised logical framework to reflect an end of activities by September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

More sustainable methods to strengthen national supply chains are needed.

Output Title	Improve availability and quality of Health Information System
Output number:		5	Output Score:			B
Impact weighting (%):		15%	Weighting revised since last AR?			No
Indicator(s)				Milestone(s) up to Q2	Progress
5.1. Number of health zones with a DHIS2 data completeness more than 90%				16(90%)	18 (100%) met expectations
5.2. Number of health zones with less than 1 validation rule violated, per form, on average.				17(95%)	18 (100%) met expectations
5.3. Monthly feedback reports from provincial health information office to HZ (Sum of Feedback sent during the quarter)				102(95%)	88 (81%) substantially did not meet expectations
5.4. Proportion of health facilities submitting weekly disease surveillance reports, on time, to the health zones				344(85%)	290 (72%) substantially did not meet expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 5 captures activities to support data systems, management and surveillance. Progress on the implementation of DHIS2 as the national health information system continued, reflecting the support provided through the programme - including software, information technology, training and data links. Performance across indicators varied, including government engagement during later phases of the support which impacted results.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were adjusted in the revised logical framework to reflect an end of activities by September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Data systems are a critical component of health programmes to enable decision making.

Output Title		Health Financing to support access to health services
Output number:	6	Output Score:		N/A
Impact weighting (%):	10%	Weighting revised since last AR?		No
Indicator(s)		Milestone(s) for this review	Progress
6.1. % annual health zone workplans (PAO) include reference to community score cards (BCP), gender equality, and an updated list of vulnerable groups		16(90%)	N/A
6.2. Average score of financial accessibility expressed by the community through community score cards (BCP)		80%	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
Activities under output 6 aimed to improve governance of the health sector in Kasai province. Progress against these indicators is measured in December by which time programme activities had stopped.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Milestones were adjusted in the revised logical framework to reflect an end of activities by September 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Some factors outside of the control of the programme impacted these activity areas (e.g. provincial action plans were not developed this year) and the early closure of the grant agreement meant scored cards were not completed.

## D: VALUE FOR MONEY

Economy was to be delivered through procurement savings, efficiency through gains from donor programmes integration and digital tools (DHIS2, iHRIS, BHIMA) and effectiveness via improved service delivery and system reforms. In Year Three (3), value for money remained off-track as the major cost drivers - procuring medicines and assets - were reduced or discontinued. On improved efficiency, good progress was made on health workforce management and DHIS2 data completeness, but this cannot be attributed solely to the SEMI programme because of possible duplication with other donor programmes. The main effectiveness indicators - curative consultations and family planning uptake - were exceeded, but SEMI relied on commodities supplied by the World Bank and UNFPA to do so. Equity gains were made through free childbirth services and negotiated flat-rate pricing helped remove financial barriers to healthcare access but have not been sustained as the measures that kept community accountability mechanisms operational were ended. Third-party monitoring plans that would have independently measured economy, efficiency, or effectiveness were also not implemented.

E: RISK

In the previous Annual Review period (January to December 2023), controls relating to financial management and safeguarding were assessed to need significant strengthening. Efforts were made to improve these controls as part of the Performance Improvement Plan (PIP); however, mitigations remained inadequate.
A risk management plan, which also included reputational and safeguarding risks, and an asset disposal plan informed the early closure process and was monitored closely.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Final reports from the partner were submitted on schedule, with the last payment occurring during the financial closure period, post-reconciliation. The final audited financial statements were received in May 2025. The asset disposal plan was broadly delivered.

G: MONITORING, EVIDENCE AND LEARNING

The implementation of the programme was monitored through a combination of quarterly review meetings and reports; monthly (programmatic and technical) and ad hoc meetings, and site visits. A third-party monitor was not secured in the reporting period, which limited close monitoring and evaluation of the programme, particularly in areas that were difficult to reach.
Monitoring of the programme was supported be BEK’s Head of Programme Effectiveness and Risk Management and BEK’s Results Adviser and with the oversight of BEK’s Human Development Team Leader. Monitoring continued throughout the closure period.
Annual review
This Annual Review drew on a range of the information including a review of financial and narrative reports, monthly meetings with the implementing partner, weekly programme meetings and other contextual information, such as the Demographic and Health Survey 2023/2024

Learning
- Health Advisers in the team regularly attend FCDO health network meetings which facilitate learning and exchange, and continuous technical development.
- The team participates in BEK programme boards to share lessons and learn from other BEK programmes.

Date of last narrative financial report	31/03/2025	Date of last audited annual statement