ADDENDUM TO BUSINESS CASE

INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Democracy Deepening programme
Country or region targeted	Mozambique
Type of cost extension (if applicable)	N/A
Original project budget	Up to £5m
Original project start and end dates	1st September 2023 - 31st March 2028
Cost extension value (if applicable)	N/A
New reduced budget (if applicable)	N/A
New project end date (if applicable)	N/A
Business Case Quest Document No.

INFORMATION
What is the project’s purpose?
The Democracy Deepening (DD) programme takes a two-track approach. For the first 18 months of implementation, the focus was on activities to promote more credible and inclusive municipal (2023) and national (2024) elections. For the remaining three years of the programme, the objective is to ramp up our work to support greater civic and policy engagement on national priorities, particularly of vulnerable groups, and on the promotion and protection of human rights and media freedom.
What is the objective of the cost extension or other changes?
Following a highly disputed electoral process and post-elections violence, BHCM looked into lessons from the process and next steps for the programme. We ran consultations internally and externally – which came to a halt. However, BHCM has now received its budget allocation, including for the DD programme, we have resumed conversations on new partnerships and the way forward. / With this business case addendum, we are proposing changes to the programme’s delivery routes. The original business case stressed that “(…) On civic engagement, policy dialogue and human rights, (…). Given the importance of national ownership for taking forward these issues (…) our suggested approach is to deliver activities through national civil society organisations. (…) To ensure we identify the right partner to deliver this work, CSOs or CSO consortia will be sourced via a local Call for Proposals. (…)” / However, we are introducing two changes. First, after internal and external consultations, there is a sense that, at present, a ‘call for proposals’ could exacerbate competition and fuel mistrust within civil society and ultimately undermine our objectives on civic engagement, policy dialogue and human rights. Also, given delays in budget announcements, there is limited time to issuing a call for proposals – this could further delay programme activities and prevent the implementation of the work. Therefore, we are changing the delivery route away from ‘calls for proposals’ and drawing on internal and external discussions to identify our preferred partners – with the final approval resting with the Political, Governance and Comms Team. Second, as for the work with national civil society organisations, that remains our preference for the work on civic engagement but is no longer our suggested route for the work on human rights – where we suggest we partner with a UN agency. Going forward, in case we diversify our partners, we might either choose them directly with the approval of the PGC team leadership, or opt for a call for proposals. And partners could be both national organisations, international or multilateral partners.
What is the additional and total support the UK will provide?
This business addendum does not propose an increase in financial support. The value of the programme will remain at up £5m. Changing the delivery mechanisms will enable more tailored and context-specific support.
What are the expected results?
The expected impact and key output results will be agreed with partners as soon as partnerships are signed. This addendum is simply suggesting a change to the delivery mechanisms to achieve results.
What is the approach to implementation?
We are proposing different delivery routes that are more suited to the country’s current context, our ODA allocation and delivery timeframes. It is proposed that a total of up to £2,2 mln will be assigned to partners chosen through this new delivery route – with one of the preferred partners receiving up to £ 1,2 mln, and another receiving up to £ 1mln.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
This new approach to delivering the programme won’t have any impact on the theory of change. And there is no new evidence from our monitoring, evaluation or learning work that will have a bearing on this submission. / The main change, as discussed, is to the delivery routes. Accordingly, for our work on civic engagement, we propose that we partner with a local NGO. Still in line with the original business case, this choice is informed by the importance of national ownership for taking forward these issues, both for their legitimacy and for their sustainability. However, differently from the business case, we are no longer using a call for proposals to select our partner. This change relates to the fact that a call for proposals could lead to undue competition for resources between civil society organisations, which should be incentivised to work together towards common goals. And most importantly, a call for proposals would take considerable time and, given late ODA allocations, would likely prevent the adequate use of those resources within financial year. By partnering with the NGO, we are selecting the that has an excellent track-record of work within that programme area. And the organisation can seek for additional support to continue that work. / For our work on human rights, we will move away from working with local civil society organisations and instead provide funding to a UN agency. This is in recognition to the fact that, after the post-elections’ crisis, most work on this area has been heavily politicised – which limits the ability of existing local civil society organisations to engage on and have an impact on critical human rights issues. And external support to these organisations brings reputational risks to them and to us. Meanwhile, the UN has engaged across a range of priority areas for the BHCM, Cabo Delgado; National Human Rights Institutions; Accountability and Security Sector.