## AR 2024
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Democracy Deepening in Mozambique Programme
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
Consolidation of democratic norms and behaviours of political contestation and civic participation in society | Improved corruption perceptions index a) score and b) rank | Planned | 25 (score), 145 (rank) | N/A | 26 (score), 142 (rank) | 27 (score), 140 (rank)
Achieved
Source
TI Index
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date)
| Improved commitment to civil and political rights, as per Freedom House indicators (political and civil rights) | Planned | Civil liberties (30/60); Political rights (14/40) | N/A | Civil liberties (32/60); Political rights (16/40) | Civil liberties (34/60); Political rights (18/40) | Civil liberties (35/60); Political rights (19/40) | Civil liberties (36/60); Political rights (20/40)
Achieved
Source
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date)
| Improved state of democracy, as measured by the Global State of Democracy Index (participation/rights) | Planned | 0.43 (participation); 0.38 (rights) | N/A | 0.45 (participation); 0.40 (rights)
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
More credible, inclusive, and sustainable national democratic processes and actors with fewer risks of democratic backsliding | Increased electoral turnout nationally and in at least half of the country's provinces | Planned | 2019 elections results/turnout | Increase of 5% in at least 5 provinces; increase of 3% nationally | N/A |  |  | N/A | Turnout (AR). National: 51,4% Niassa: 41,6%; Cabo Delgado: 49,1; Nampula: 42,4%; Zambezia: 42,3%; Tete: 59,7%; Manica: 60,7%; Sofala: 57,6%; Inhambane, 53,8%; Gaza: 62%; Maputo Provincia: 54%; Maputo Cidade: 58%.
Achieved
Source
CNE/STAE reports + CC ruling (https://www5.open.ac.uk/technology/mozambique/sites/www.open.ac.uk.technology.mozambique/files/files/Acordao_25-CC-2019_changed-1Jan20.pdf)
| Outcome Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Largely peaceful and credible electoral process and results, as per assessments from international and national observer missions and Parallel Vote Tabulation (PVT) results, and implementation of key recommendations from observer missions | Planned | No major incidents of violence in 2019 general elections; 2019 elections credibility questioned by EU, CW and national observer groups; PVT compromised due to lack of access to polling stations; results not accepted by opposition parties.. | No major incidents of violence; EU, CW and Mais Integridade observer reports without significant criticisms of the process or results; PVTs results within 3% margin of error; all parties take up their seats in Parliament and Provincial Assemblies. | Agreement on key recommendations that should be implemented by 2028 | Kick-off of process to implement all recommendations (at least one action per area) | Sustained progress on implementation of all recommendations | At least 80% of agreed recommendations implemented
Achieved
Source
EU + CW + Integridade reports; PVT report; parties' official comms; reports from electoral authorities, parliament, civil society and government.
| Outcome indicator 3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| TBA on human rights (2025 on) | Planned
Achieved
Source
| Outcome Indicator 4 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| TBA on media/civic engagement (2025 on) | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Greater civic participation, scrutiny, transparency and accountability of electoral processes | Number of elections observers trained, accredited and deployed across all provinces of the country to observe the campaign and elections day, and qualitative reporting of impact | Planned | 0 | Campaign: 240 observers; Elections day: at least 1,500. Assessment of impact of observers on transparency of process.
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of PVTs carried out, completed and shared with electoral/judicial authorities | Planned | 0 | At least 2 provincial PVTs
Achieved
Source
Mais Integridade reports
| Output Indicator 1.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Uptake/use of national observer reports/data by media outlets and electoral stakeholders (reports from international observer groups; court decisions; CNE decisions). | Planned | 0 | At least 40 examples
Achieved
Source
Reports from open sources and Mais Integridade (media clippings)
| Output indicator 1.4 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of civic education campaigns designed and implemented, with a focus on specific groups, particularly women, people with disabilities, and the youth, and qualitative reporting of impact. | Planned | 7 (municipal elections) | 10 campaigns; assessment of impact of campaigns on participation.
Achieved
Source
UNDP reports
| Output Indicator 1.5 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of diplo-watch observers and locations covered | Planned | 18 observers, 6 locations for e-day only (municipal elections) | 14 observers, 4 locations for e-day, 4 locations for campaign
Achieved
Source
Internal reports
IMPACT WEIGHTING (%)
100% (2024); 0% (2025/8)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Improved enabling environment for civic engagement and policy dialogue. | Number of civic coalitions and partnerships and advocacy campaigns supported to protect the civic space and improve engagement between civil society and state authorities. | Planned |  | N/A
Achieved
Source
|  |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
0% (2024); 50% (2025/8) |  | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Stronger promotion and protection of human rights, including media freedom. | Number and qualty of campaigns/partnerships to ensure human rights violations, including at local level, are systematically monitored, documented, and analysed. | Planned |  | N/A
Achieved
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 |  |  | Target (date)
| Number and quality of civic coalitions supported to promote and protect media freedom, LGBTQ+ rights, rights of people with disabilities, gender. | Planned |  | N/A
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
0% (2024); 50% (2025/8) |  | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date) | Assumptions
Planned
Achieved
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date)
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date)
Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date) | Assumptions
Planned
Achieved
Source
| Output Indicator 5.2 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date)
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline | Milestone 1 | Milestone 2 |  |  | Target (date)
40% |  | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## AR 2025
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Democracy Deepening in Mozambique Programme
IMPACT | Impact Indicator 1 |  | Baseline (2023) | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
Consolidation of democratic norms and behaviours of political contestation and civic participation in society | Improved corruption perceptions index a) score and b) rank | Planned | 25 (score), 145 (rank) | N/A | 27 (score), 135 (rank) | 28 (score), 133 (rank) | 28 (score), 133 (rank)
|  | Achieved |  | 26 (score), 146 (rank) | NOT MET. 21 (score), 161 (rank)
Source
TI Index (https://www.transparency.org/en/cpi/2024)
| Impact Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) |  |  | Target (date)
| Improved commitment to civil and political rights, as per Freedom House indicators (political and civil rights) | Planned | Civil liberties (30/60); Political rights (14/40) | N/A | Civil liberties (32/60); Political rights (16/40) | Civil liberties (34/60); Political rights (18/40) | Civil liberties (35/60); Political rights (19/40) | Civil liberties (36/60); Political rights (20/40)
|  | Achieved |  |  | NOT MET. Civil liberties (29/60); Political rights (12/40)
Source
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 (2025) | Milestone 3 (2026) |  | Target (date)
| Improved state of democracy, as measured by the Global State of Democracy Index (participation/rights) | Planned | 0.43 (participation); 0.38 (rights) | N/A | 0.45 (participation); 0.40 (rights) | 0.45 (participation); 0.40 (rights)
|  | Achieved |  |  | NOT MET. 0.439 (participation); 0.358 (rights)
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
More credible, inclusive, and sustainable national democratic processes and actors with fewer risks of democratic backsliding | Increased electoral turnout nationally and in at least half of the country's provinces | Planned | 2019 elections results/turnout | Increase of 5% in at least 5 provinces; increase of 3% nationally | N/A | N/A | N/A | N/A | Key political actors and institutions remain committed to inclusive, peaceful and reform-oriented democratic processes, uphold civic and human rights, and permit credible independent monitoring and reporting. Turnout (AR). National: 51,4% Niassa: 41,6%; Cabo Delgado: 49,1; Nampula: 42,4%; Zambezia: 42,3%; Tete: 59,7%; Manica: 60,7%; Sofala: 57,6%; Inhambane, 53,8%; Gaza: 62%; Maputo Provincia: 54%; Maputo Cidade: 58%.
|  | Achieved |  | NOT MET. 2019: National, 51.4%; 2024: 50.3%. At provincial level, only increases were Inhambane, Maputo Province and Cabo Delgado (+01%)
Source
CNE/STAE reports + CC ruling (https://www5.open.ac.uk/technology/mozambique/sites/www.open.ac.uk.technology.mozambique/files/files/Acordao_25-CC-2019_changed-1Jan20.pdf)
| Outcome Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Largely peaceful and credible electoral process and results, as per assessments from international and national observer missions and Parallel Vote Tabulation (PVT) results, and implementation of key recommendations from observer missions | Planned | No major incidents of violence in 2019 general elections; 2019 elections credibility questioned by EU, CW and national observer groups; PVT compromised due to lack of access to polling stations; results not accepted by opposition parties.. | No major incidents of violence; EU, CW and Mais Integridade observer reports without significant criticisms of the process or results; PVTs results within 3% margin of error; all parties take up their seats in Parliament and Provincial Assemblies. | Electoral system, laws and policies under discussion as part of National Inclusive Dialogue. | Changes to electoral system, laws and policies agreed on by all main political parties | New electoral system, polices and laws under implementation. | No major incidents of violence in 2028 Municipal Elections - and results accepted by all parties.
|  | Achieved |  | NOT MET. | MET.
Source
EU + CW + Integridade reports; PVT report; parties' official comms; reports from electoral authorities, parliament, civil society and government.
| Outcome indicator 3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Post-elections national dialogue is politically inclusive and reform-oriented | Planned |  | N/A | All key political actors contribute to the national dialogue, and a roadmap for reforms is under discussion | Democratic reforms are agreed on by all main political parties and submitted to Government and Parliament
|  | Achieved |  |  | PARTLY MET/ON TRACK.
Source
Outcome indicator 4
| National institutions protect human rights and provide accountability for violations. | Planned | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
|  | Achieved |  | N/A | a. Nampula military academy integrates human rights module; b. GoM submits one report to a treaty body. | a)Nampula military academy integrates human rights module; b) With OHCHR support, Mozambique submits its UPR State Report, increases the acceptance of UPR recommendations, and begins implementing priority recommendations through an approved national implementation framework; c) Workshop with PRM central command on Human Rights compliance
PARTLY MET. a.Ongoing process. b. Ready for submission, pending approval by Council of Ministers
Source
Outcome Indicator 5
| Number of cases of policy, legal and institutional changes achieved through evidence-based advocacy led by CIP | Planned | 7 | N/A | 8 | 8
|  | Achieved |  |  | PARTLY MET. 5
Source
CIP reports/case studies
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Greater civic participation, scrutiny, transparency and accountability of electoral processes | Number of elections observers trained, accredited and deployed across all provinces of the country to observe the campaign and elections day, and qualitative reporting of impact | Planned | 0 | Campaign: 240 observers; Elections day: at least 1,500. Assessment of impact of observers on transparency of process. | N/A | N/A |  |  | Electoral authorities and political actors enable nationwide observation, PVT, civic education and reform analysis, while media and stakeholders use the resulting evidence.
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of PVTs carried out, completed and shared with electoral/judicial authorities | Planned | 0 | At least 2 provincial PVTs | N/A | N/A
Achieved
Source
Mais Integridade reports
| Output Indicator 1.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Uptake/use of national observer reports/data by media outlets and electoral stakeholders (reports from international observer groups; court decisions; CNE decisions). | Planned | 0 | At least 40 examples | N/A | N/A
Achieved
Source
Reports from open sources and Mais Integridade (media clippings)
| Output indicator 1.4 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of civic education campaigns designed and implemented, with a focus on specific groups, particularly women, people with disabilities, and the youth, and qualitative reporting of impact. | Planned | 7 (municipal elections) |  | N/A | N/A
Achieved
Source
UNDP reports
| Output Indicator 1.5 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of diplo-watch observers and locations covered | Planned | 18 observers, 6 locations for e-day only (municipal elections) | 14 observers, 4 locations for e-day, 4 locations for campaign | N/A | N/A
Achieved
Source
Internal reports
| Output Indicator 1.6 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Post-elections work on electoral reforms (UNDP) | Planned | N/A | N/A | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout
|  | Achieved |  |  | NOT MET. Ongoing, pending completion.
Source
UNDP reports
IMPACT WEIGHTING (%)
100% (2024); 15% (2025/8) | FCDO (£) | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (£)
FCDO (FTEs)
INPUTS (HR)
OUTPUT 2 | Planned | N/A | N/A | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout
| Achieved |  |  | NOT MET. Ongoing, pending completion.
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Improved enabling environment for civic engagement and policy dialogue. | Number of civic coalitions and partnerships and advocacy campaigns supported to protect the civic space and improve engagement between civil society and state authorities. | Planned |  | N/A | At least 1 partnership | N/A |  |  | Government, private-sector and civic actors remain open to constructive advocacy and policy dialogue, while target audiences retain access to independent media and digital platforms.
|  | Achieved |  |  | MET. Signed with CIP.
Source
| Output indicator 2.2 |  | Baseline (2024) | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| A. Number of videos produced and views: (Youtube and facebook) B. Number of visitors to CIP’s website C. Number of social media followers (Facebook, Linkedin, Tiktok e WhatsApp canal; instagram); D. Number of views on social media (Facebook and youtube); E. Number of press conferences | Planned | N/A | N/A | A. Youtube: 10 (videos), 10.000 views; Facebook: 10 (videos), 20.000 views B. 15.000 C. FB: 1000. Linkedin: 500 Tiktok: 1500 Instagram: 300 WhatsApp chanel: 100 D. 700.000, Youtube; 1.000.000 facebook. E. 5 | A. Youtube: #14 (videos), 1.818.642 views (+478.400); Facebook:#14 (videos), 4.338.251 views ((+1.051.697) B. #1.179.034 (+285.827) C. FB: #192.000 (+68.000) Linkedin: #78.000 (+22.960) Tiktok: #34.800 (+9.700) Instagram: #28.800 (+8.200) WhatsApp channel: # 19.200 (+11.469) D. #4.735.831 (+1.148.080) youtube; #15.521.177 (+3.762.710) facebook ; E. #13
|  | Achieved |  |  | EXCEEDED. A. 18 new videos; Youtube:1.340.242 views; Facebook: 3.286.554 views. B. 893.207 C. Facebook: 52.000; LinkedIn: 55.040; TikTok: 25.100 ; Instagram: 20.600 ; WhatsApp channel: 7.731 D. Facebook: 11.758,467; Youtube: 3.587,751. E.10.
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
0% (2024); 35% (2025/8) | Number of times government officials and private sector actors respond to CIP's advocacy work | Planned | N/A |  | 50 | 50
|  | Achieved |  |  | 53
Source
CIP reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Stronger promotion and protection of human rights, including media freedom. | Number and qualty of campaigns/partnerships to ensure human rights violations, including at local level, are systematically monitored, documented, and analysed. | Planned |  | N/A | At least 1 partnership | N/A |  |  | State, justice and security institutions cooperate with OHCHR and civil-society partners, allow independent human-rights monitoring and review, and act on documented findings.
|  | Achieved |  |  | MET. Signed with OHCHR
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) |  |  | Target (date)
| Number of State reports submitted to UN human rights mechanisms. | Planned |  | N/A | Technical assistance provided for preparing and submitting a State report to a treaty body. | Technical assistance provided for preparing and submitting a State report to the UPR
|  | Achieved |  |  | MET. TA provided, report is waiting Council of Ministers sign-off.
Source
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
0% (2024); 35% (2025/8) | Number of detention cases legally reviewed to ensure compliance with human rights standards and number of people released from arbitrary detention. | Planned |  |  | Support provided to at least one field mission by justice actors. | Support provided to at least 5 field mission by justice actors.
|  | Achieved |  |  | EXCEEDED.
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
BHC supports a more inclusive and reform-oriented post-elections national dialogue. | Quantity/number, quality, strategic aligment and impact of BHC stakeholder engagement | Planned | N/A | N/A | Agreement on UK Strategic Approach to Dialogue, with at least 2 meetings every month with key stakeholders (technical, political, IC). | Implementation of UK Strategic Approach to Dialogue, with at least 12 senior-level meetings held throughout the period |  |  | Key political stakeholders remain willing and available to participate in an inclusive national dialogue and accept coordinated UK and partner technical support for agreed reforms.
|  | Achieved |  |  | MET. Approach agreed on, and more than 30 meetings held throughout the period
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
|  |  |  | Agreement on programme support to post-elections national dialogue | Technical assistance provided to political parties, with positive feedback, and conclusion of PEA study on NID reforms.
MET. Through CIP, partnership with International IDEA to provide support to key political parties engaging in the dialogue.
Source
IMPACT WEIGHTING (%) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
15% (2025/8)
INPUTS (£) | FCDO (FTEs)
INPUTS (HR)

## AR 2026
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Democracy Deepening in Mozambique Programme
IMPACT | Impact Indicator 1 |  | Baseline (2023) | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
Consolidation of democratic norms and behaviours of political contestation and civic participation in society | Improved corruption perceptions index a) score and b) rank | Planned | 25 (score), 145 (rank) | N/A | 27 (score), 135 (rank) | 28 (score), 133 (rank) | 28 (score), 133 (rank)
|  | Achieved |  | 26 (score), 146 (rank) | NOT MET. 21 (score), 161 (rank)
Source
TI Index (https://www.transparency.org/en/cpi/2024)
| Impact Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Improved commitment to civil and political rights, as per Freedom House indicators (political and civil rights) | Planned | Civil liberties (30/60); Political rights (14/40) | N/A | Civil liberties (32/60); Political rights (16/40) | Civil liberties (34/60); Political rights (18/40) | Civil liberties (35/60); Political rights (19/40) | Civil liberties (36/60); Political rights (20/40)
|  | Achieved |  |  | NOT MET. Civil liberties (29/60); Political rights (12/40)
Source
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Improved state of democracy, as measured by the Global State of Democracy Index (participation/rights) | Planned | 0.43 (participation); 0.38 (rights) | N/A | 0.45 (participation); 0.40 (rights) | 0.45 (participation); 0.40 (rights)
|  | Achieved |  |  | NOT MET. 0.439 (participation); 0.358 (rights)
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
More credible, inclusive, and sustainable national democratic processes and actors with fewer risks of democratic backsliding | Increased electoral turnout nationally and in at least half of the country's provinces | Planned | 2019 elections results/turnout | Increase of 5% in at least 5 provinces; increase of 3% nationally | N/A | N/A | N/A | N/A | Key political actors and institutions remain committed to inclusive, peaceful and reform-oriented democratic processes, uphold civic and human rights, and permit credible independent monitoring and reporting. Turnout (AR). National: 51,4% Niassa: 41,6%; Cabo Delgado: 49,1; Nampula: 42,4%; Zambezia: 42,3%; Tete: 59,7%; Manica: 60,7%; Sofala: 57,6%; Inhambane, 53,8%; Gaza: 62%; Maputo Provincia: 54%; Maputo Cidade: 58%.
|  | Achieved |  | NOT MET. 2019: National, 51.4%; 2024: 50.3%. At provincial level, only increases were Inhambane, Maputo Province and Cabo Delgado (+01%)
Source
CNE/STAE reports + CC ruling (https://www5.open.ac.uk/technology/mozambique/sites/www.open.ac.uk.technology.mozambique/files/files/Acordao_25-CC-2019_changed-1Jan20.pdf)
| Outcome Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Largely peaceful and credible electoral process and results, as per assessments from international and national observer missions and Parallel Vote Tabulation (PVT) results, and implementation of key recommendations from observer missions | Planned | No major incidents of violence in 2019 general elections; 2019 elections credibility questioned by EU, CW and national observer groups; PVT compromised due to lack of access to polling stations; results not accepted by opposition parties.. | No major incidents of violence; EU, CW and Mais Integridade observer reports without significant criticisms of the process or results; PVTs results within 3% margin of error; all parties take up their seats in Parliament and Provincial Assemblies. | Electoral system, laws and policies under discussion as part of National Inclusive Dialogue. | Changes to electoral system, laws and policies agreed on by all main political parties | New electoral system, polices and laws under implementation. | No major incidents of violence in 2028 Municipal Elections - and results accepted by all parties.
|  | Achieved |  | NOT MET. | MET.
Source
EU + CW + Integridade reports; PVT report; parties' official comms; reports from electoral authorities, parliament, civil society and government.
| Outcome indicator 3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Post-elections national dialogue is politically inclusive and reform-oriented | Planned |  | N/A | All key political actors contribute to the national dialogue, and a roadmap for reforms is under discussion | Democratic reforms are agreed on by all main political parties and submitted to Government and Parliament
|  | Achieved |  |  | PARTLY MET/ON TRACK.
Source
Outcome indicator 4
| National institutions protect human rights and provide accountability for violations. | Planned | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
|  | Achieved |  | N/A | a. Nampula military academy integrates human rights module; b. GoM submits one report to a treaty body. | a)Nampula military academy integrates human rights module; b) With OHCHR support, Mozambique submits its UPR State Report, increases the acceptance of UPR recommendations, and begins implementing priority recommendations through an approved national implementation framework; c) Workshop with PRM central command on Human Rights compliance
PARTLY MET. a.Ongoing process. b. Ready for submission, pending approval by Council of Ministers
Source
Outcome Indicator 5
| Number of cases of policy, legal and institutional changes achieved through evidence-based advocacy led by CIP | Planned | 7 | N/A | 8 | 8
|  | Achieved |  |  | PARTLY MET. 5
Source
CIP reports/case studies
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Greater civic participation, scrutiny, transparency and accountability of electoral processes | Number of elections observers trained, accredited and deployed across all provinces of the country to observe the campaign and elections day, and qualitative reporting of impact | Planned | 0 | Campaign: 240 observers; Elections day: at least 1,500. Assessment of impact of observers on transparency of process. | N/A | N/A |  |  | Electoral authorities and political actors enable nationwide observation, PVT, civic education and reform analysis, while media and stakeholders use the resulting evidence.
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of PVTs carried out, completed and shared with electoral/judicial authorities | Planned | 0 | At least 2 provincial PVTs | N/A | N/A
Achieved
Source
Mais Integridade reports
| Output Indicator 1.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Uptake/use of national observer reports/data by media outlets and electoral stakeholders (reports from international observer groups; court decisions; CNE decisions). | Planned | 0 | At least 40 examples | N/A | N/A
Achieved
Source
Reports from open sources and Mais Integridade (media clippings)
| Output indicator 1.4 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of civic education campaigns designed and implemented, with a focus on specific groups, particularly women, people with disabilities, and the youth, and qualitative reporting of impact. | Planned | 7 (municipal elections) |  | N/A | N/A
Achieved
Source
UNDP reports
| Output Indicator 1.5 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Number of diplo-watch observers and locations covered | Planned | 18 observers, 6 locations for e-day only (municipal elections) | 14 observers, 4 locations for e-day, 4 locations for campaign | N/A | N/A
Achieved
Source
Internal reports
| Output Indicator 1.6 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| Post-elections work on electoral reforms (UNDP) | Planned | N/A | N/A | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout
|  | Achieved |  |  | NOT MET. Ongoing, pending completion.
Source
UNDP reports
IMPACT WEIGHTING (%)
100% (2024); 15% (2025/8) | FCDO (£) | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (£)
FCDO (FTEs)
INPUTS (HR)
OUTPUT 2 | Planned | N/A | N/A | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout | Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout
| Achieved |  |  | NOT MET. Ongoing, pending completion.
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Improved enabling environment for civic engagement and policy dialogue. | Number of civic coalitions and partnerships and advocacy campaigns supported to protect the civic space and improve engagement between civil society and state authorities. | Planned |  | N/A | At least 1 partnership | N/A |  |  | Government, private-sector and civic actors remain open to constructive advocacy and policy dialogue, while target audiences retain access to independent media and digital platforms.
|  | Achieved |  |  | MET. Signed with CIP.
Source
| Output indicator 2.2 |  | Baseline (2024) | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
| A. Number of videos produced and views: (Youtube and facebook) B. Number of visitors to CIP’s website C. Number of social media followers (Facebook, Linkedin, Tiktok e WhatsApp canal; instagram); D. Number of views on social media (Facebook and youtube); E. Number of press conferences | Planned | N/A | N/A | A. Youtube: 10 (videos), 10.000 views; Facebook: 10 (videos), 20.000 views B. 15.000 C. FB: 1000. Linkedin: 500 Tiktok: 1500 Instagram: 300 WhatsApp chanel: 100 D. 700.000, Youtube; 1.000.000 facebook. E. 5 | A. Youtube: #14 (videos), 1.818.642 views (+478.400); Facebook:#14 (videos), 4.338.251 views ((+1.051.697) B. #1.179.034 (+285.827) C. FB: #192.000 (+68.000) Linkedin: #78.000 (+22.960) Tiktok: #34.800 (+9.700) Instagram: #28.800 (+8.200) WhatsApp channel: # 19.200 (+11.469) D. #4.735.831 (+1.148.080) youtube; #15.521.177 (+3.762.710) facebook ; E. #13
|  | Achieved |  |  | EXCEEDED. A. 18 new videos; Youtube:1.340.242 views; Facebook: 3.286.554 views. B. 893.207 C. Facebook: 52.000; LinkedIn: 55.040; TikTok: 25.100 ; Instagram: 20.600 ; WhatsApp channel: 7.731 D. Facebook: 11.758,467; Youtube: 3.587,751. E.10.
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
0% (2024); 35% (2025/8) | Number of times government officials and private sector actors respond to CIP's advocacy work | Planned | N/A |  | 50 | 50
|  | Achieved |  |  | 53
Source
CIP reports
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
Stronger promotion and protection of human rights, including media freedom. | Number and qualty of campaigns/partnerships to ensure human rights violations, including at local level, are systematically monitored, documented, and analysed. | Planned |  | N/A | At least 1 partnership | N/A |  |  | State, justice and security institutions cooperate with OHCHR and civil-society partners, allow independent human-rights monitoring and review, and act on documented findings.
|  | Achieved |  |  | MET. Signed with OHCHR
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) |  |  | Target (date)
| Number of State reports submitted to UN human rights mechanisms. | Planned |  | N/A | Technical assistance provided for preparing and submitting a State report to a treaty body. | Technical assistance provided for preparing and submitting a State report to the UPR
|  | Achieved |  |  | MET. TA provided, report is waiting Council of Ministers sign-off.
Source
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
0% (2024); 35% (2025/8) | Number of detention cases legally reviewed to ensure compliance with human rights standards and number of people released from arbitrary detention. | Planned |  |  | Support provided to at least one field mission by justice actors. | Support provided to at least 5 field mission by justice actors.
|  | Achieved |  |  | EXCEEDED.
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028) | Assumptions
BHC supports a more inclusive and reform-oriented post-elections national dialogue. | Quantity/number, quality, strategic aligment and impact of BHC stakeholder engagement | Planned | N/A | N/A | Agreement on UK Strategic Approach to Dialogue, with at least 2 meetings every month with key stakeholders (technical, political, IC). | Implementation of UK Strategic Approach to Dialogue, with at least 12 senior-level meetings held throughout the period |  |  | Key political stakeholders remain willing and available to participate in an inclusive national dialogue and accept coordinated UK and partner technical support for agreed reforms.
|  | Achieved |  |  | MET. Approach agreed on, and more than 30 meetings held throughout the period
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Target (2028)
[5 empty] | Agreement on programme support to post-elections national dialogue | Technical assistance provided to political parties, with positive feedback, and conclusion of PEA study on NID reforms.
MET. Through CIP, partnership with International IDEA to provide support to key political parties engaging in the dialogue.
Source
IMPACT WEIGHTING (%) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
15% (2025/8)
INPUTS (£) | FCDO (FTEs)
INPUTS (HR)

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) |  | 2018-01-01
E.g. | Output 1, Indicator 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) |  | 2018-01-01
1 | Impact, indicator 1 | Milestone 3 added/reviewed: 28 (score), 133 (rank) |  | 2026-08-18
2 | Impact, indicator 2 | Milestone 3 added/reviewed: Civil liberties (34/60); Political rights (18/40) |  | 2026-08-18
3 | Impact, indicator 3 | Milestone 3 added/reviewed: 0.45 (participation); 0.40 (rights) |  | 2026-08-18
4 | Outcome, indicator 2 | Milestone 3 reviewed to add list of political parties: Changes to electoral system, laws and policies agreed on by all main political parties |  | 2026-08-18
5 | Outcome, indicator 3 | Milestone 3 reviewed to add list of political parties: Democratic reforms are agreed on by all main political parties and submitted to Government and Parliament |  | 2026-08-18
6 | Outcome, indicator 4 | Milestones added: a)Nampula military academy integrates human rights module; b) With OHCHR support, Mozambique submits its UPR State Report, increases the acceptance of UPR recommendations, and begins implementing priority recommendations through an approved national implementation framework; c) Workshop with PRM central command on Human Rights compliance |  | 2026-09-16
7 | Output 1, Indicator 5 | Milestone 3 added: Completion of two pieces of analytical work: 1. Assessment of cost and sustainability of elections in Mozambique; 2.Assessment of 2023/4 electoral process, including impact of civic/voter education and causes of low voter turnout |  | 2026-08-18
8 | Output 2, indicator 2 | Milestone 3 added: A. Youtube: #14 (videos), 1.818.642 views (+478.400); Facebook:#14 (videos), 4.338.251 views ((+1.051.697) B. #1.179.034 (+285.827) C. FB: #192.000 (+68.000) Linkedin: #78.000 (+22.960) Tiktok: #34.800 (+9.700) Instagram: #28.800 (+8.200) WhatsApp channel: # 19.200 (+11.469) D. #4.735.831 (+1.148.080) youtube; #15.521.177 (+3.762.710) facebook ; E. #13 |  | 2026-08-26
9 | Output 2, indicator 3 | Milestone 3 added: 50 |  | 2026-08-18
10 | Output 3, indicator 2 | Milestone 3 added: Technical assistance provided for preparing and submitting a State report to the UPR |  | 2026-08-18
11 | Output 3, indicator 3 | Milestone 3 added: Support provided to at least 4 field mission by justice actors. |  | 2026-08-18
12 | Output 4, indicator 1 | Milestone 3 added: Implementation of UK Strategic Approach to Dialogue, with at least 12 senior-level meetings held throughout the period |  | 2026-08-18
13 | Output 4, indicator 2 | Milestone 3 added: Technical assistance provided to political parties, with positive feedback, and conclusion of PEA study on NID reforms. |  | 2026-08-18