## Annual Review Template

Title: Tanzania Humanitarian Assistance Programme (T-HAP)
Programme Value £ (full life): 19,800,000		Review date: Nov 2025
Programme Code : [AMP ID#] 301375	AMP start date: 01 Aug 2024	AMP end date: 31 March 2029

Summary of Programme Performance
Year	2025
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logical Framework

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Tanzania Humanitarian Assistance Programme (T-HAP) is a £19.8 million programme running from 2024 to 2029. It is designed to strengthen Tanzania’s humanitarian system by supporting both refugee assistance and national disaster management efforts. The programme delivers essential aid—including food, clean water, sanitation, protection, clean energy, and economic opportunities—to improve the lives of more than 230,000 refugees and asylum-seekers, mainly from Burundi and the Democratic Republic of Congo (DRC). Most of these individuals are hosted in Nyarugusu and Nduta refugee camps in the Kigoma Region. In addition to refugee support, T-HAP aims to enhance national disaster preparedness by building institutional capacity through policy development and training.

The programme is implemented through partnerships with the UN Refugee Agency (UNHCR), the World Food Programme (WFP), and a consortium led by the Danish Refugee Council (DRC), which collaborates with downstream non-governmental organisations (NGOs). It also supports Tanzania’s capacity to respond to natural disasters, with WFP working in partnership with the Disaster Management Department under the Prime Minister’s Office.

The refugee population is not decreasing despite efforts to promote repatriations of Burundian refugees. Between January and 30 June 2025, only 467 Burundian refugees voluntarily repatriated, far below the target of 3,000 per week set during the December 2024 Tripartite Meeting in Bujumbura, and significantly less than the 5,887 repatriated during the same period in 2024. This low return rate has led to no significant change in net refugee population figures. The slow pace of repatriation is mainly due to refugees’ reluctance to return, driven by ongoing challenges in Burundi such as extreme poverty, lack of land access, limited socio-economic services, and security concerns.

Tanzania’s humanitarian situation remains deeply challenging. Longstanding restrictive policies toward refugees—particularly those from Burundi—have left this population heavily reliant on humanitarian assistance. The suspension of support from the United States has further strained available resources. Health, Education, WASH, and Child Protection sectors are already severely affected, and the imminent closure of key programmes threatens a complete halt in service delivery across both refugee camps. Major operational partners such as DRC, NRC, and IRC are closing operations by December 2025, following budget reductions resulting in mass job losses, reduced numbers of frontline workers, and a sharp decline in protection and education services. UNHCR’s restructuring towards “protection solutions and emergency response” further illustrate the scale of disruption.

In response, T-HAP has used the last four months and coming two months to pivot and ensure a responsible and sustainable exit for the components where partners are closing operations. The programme will prioritize delivery of Year Two targets while halting all capacity-building activities and large procurements by October 2025. FCDO funding is strictly directed to core service delivery, avoiding additional overheads except under exceptional circumstances. Additionally, the programme is working closely with UNHCR, WFP, and the INGO consortium to maintain critical services during the transition, while advocating for urgent resource mobilization to mitigate the humanitarian gap. This pivot underscores the need for high-level prioritization and coordinated planning to safeguard the most vulnerable amid unprecedented funding constraints.

Continued instability in the Democratic Republic of Congo has added pressure to an already fragile environment. Despite these difficulties, the UK has maintained its support, enabling it to reach the most vulnerable populations in line with the UK Government’s humanitarian priorities.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

During the reporting period, T-HAP disbursed £5.5 million and has been assessed as meeting expectations, a rating of A. The programme provided protection, food, nutrition, water, sanitation and hygiene (WASH), education, and livelihoods support to at least 230,000 refugees and asylum-seekers in Nduta and Nyarugusu camps. It also extended assistance to host communities surrounding the camps, focusing primarily on economic recovery and environmental sustainability. Additionally, the programme supported the Government of Tanzania in revising the national disaster management policy.

This annual review covers the activities undertaken during the period from October 2024 to August 2025. This review was conducted by the British High Commission in Dar es Salaam Humanitarian Team, and was quality assured by the Development Director. Quantitative data was sourced from implementing partners and qualitative data was collected through consultation during meetings with implementing partners and field visits.

Major lessons and recommendations for the year ahead [1/2 page]

- Revision of the programme results framework to reflect the exit of consortium partners, revised scope and priorities. Reflecting on wider resource constraints the programme should restructure, in order to optimize resources and focus on areas with the greatest impact. - Humanitarian Team, by February 2026.
- The programme should collaborate closely with UNHCR and WFP to develop scenario analyses that consider varying funding levels, policy constraints, and their potential impacts on refugee populations. These analyses should be used to guide prioritisation decisions and ensure alignment with other development partners, fostering a coordinated and evidence-based approach to resource allocation and programme planning. – Programme SRO by January 2026

Increased targeted advocacy aimed at key decision-makers and the broader international community. These should focus on improving camp conditions, particularly in the area of livelihoods, in light of limited international funding. Advocacy should also reinforce the importance of maintaining the voluntary nature of refugee repatriation.

Conduct deeper analysis of the decision-making landscape and key influencers on refugee-related issues. This will help refine advocacy strategies and ensure they are directed at the most effective channels and individuals.

Increase protection-focused assessments in the camps, especially in relation to the repatriation process. This should include better documentation of the sources of information available to refugees, as well as their motivations and barriers to repatriation. Findings should inform both operational planning and advocacy efforts with government stakeholders.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The T-HAP programme’s Theory of Change (ToC) is built on the understanding that coordinated humanitarian action, strategic policy engagement, and targeted service delivery are critical to improving the protection, wellbeing, and resilience of refugees and asylum seekers in Tanzania. The ToC also places emphasis on strengthening government systems and capacities in disaster risk management through enhanced coordination mechanisms. Throughout the reporting period, the programme has leveraged the complementarity between UK diplomatic engagement and humanitarian programming to drive progress towards its intended impact: a more supportive, coordinated, and efficient humanitarian response. This includes ensuring that vulnerable refugee populations are protected, able to meet their basic needs, and that Tanzania is better equipped to respond to shocks and disasters.

Programme outputs have focused on the provision of humanitarian services, including protection, food and nutrition assistance, access to education, WASH, and livelihoods opportunities, alongside efforts to prevent environmental degradation and facilitate dialogue with the Government of Tanzania and other stakeholders on the refugee crisis. Delivery has been supported by consultations with affected populations, a multi-year funding approach, and coordination through operational partners. The programme’s outcomes aim to establish an improved enabling environment for humanitarian response, ensure sustained and effective needs-based assistance, and enhance national capacity to anticipate and respond to disasters and shocks.

The UK are playing a leading diplomatic role on overall humanitarian efforts in Tanzania. The UK engaged with the Government of Tanzania regularly during the review period, including the Ministry of Foreign Affairs and East African Cooperation, Ministry of Home Affairs and the Disaster Management Department within the Prime Minister’s Office, to discuss how the UK can best support the government to respond to the crisis.
Over the reporting period, the programme has made notable progress in enhancing coordination among humanitarian actors and government stakeholders. The programme has achieved this through active participation in and organization of key coordination forums at national and camp levels, ensuring alignment of priorities and fostering joint planning. The programme has strengthened advocacy by working closely with like-minded donors and engaging multiple ministries to deliver coherent messages that influence policy. Thought leadership has been brought to the fore through commissioning research, facilitating evidence-based dialogue, and engaging academia to enrich humanitarian discourse. Additionally, the programme has joined joint field visits with partners and government representatives, reinforcing transparency, promoting shared learning, and ensuring that operational realities inform strategic decisions.

These efforts have contributed to more timely and targeted humanitarian assistance particularly with newly arriving Congolese Refugees as well as delivering on policy frameworks that strengthen Tanzania’s capacity manage disasters. However, several foundational assumptions underpinning the original ToC have not held, necessitating a reassessment of the programme’s outcomes and impact indicators. Key contextual challenges have emerged, particularly the persistence of restrictive Government of Tanzania policies affecting refugee populations, most notably Burundians, which have limited meaningful policy engagement and constrained protection environment. Additionally, severe resource shortfalls have significantly undermined the humanitarian architecture, leading to the closure or scaling down of operations by key delivery partners. This has resulted in a reduction of services in critical areas and a shift in programme outputs.

Consequently, the programme’s ability to achieve several intended outputs is at risk. The outcomes and impacts remain valid, but our ambition will need to be reduced given the reduction in resources from others and the deteriorating policy environment. Some minor modifications have been made to the logframe over the reporting period, primarily around output 1 to tighten up and adjust some of the programme indicators for the provision of continued assistance in refugee camps. For year two and beyond, more fundamental changes are needed to the logframe to reflect the changes in the operating context, including amending outputs and outcome targets. An internal discussion is currently underway to determine future engagement with the humanitarian portfolio in alignment with the Country Business Plans (CBP).

Proposed changes to the logframe
Outcome /Output Area	Proposed action
Outcome 1	Refugee response. Outcome and output changes to reflect the imminent closures of operations for the consortium partners. With the exception of WFP related outputs, other outputs under the consortium arrangement should be deleted after year 2. The next review will consist PCR of the activities that continue to take place to December 2025 / The outcome should be sharpened to focus on food security. Deleted indicators should potentially be replaced by outputs focusing on food security, food and nutrition support
Outcome 3	Output indicators 3.1 and 3,2 should be removed. And potentially replaced by more coordination and advocacy indicators.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Refugee response: The programme’s multi-sectoral interventions contributed to the outcome of providing assistance and protection to refugees and asylum seekers to sustain lives and livelihoods. Major milestones were seen through the food and nutrition interventions. Nearly 186,066 individuals received food rations, and 42,267 nutritionally vulnerable people were supported with fortified commodities, ensuring basic nutritional needs were met despite funding constraints. Similarly, compared to last year when the food rations were at 50% and limitation in kitchen gardens initiatives, there has been improvements in the percentage of households with an acceptable Food Consumption Score (from 68% to 73%[1]). WASH and shelter interventions, improved access to clean water (23 litres per person/day), sanitation, and emergency shelter, directly enhancing health and dignity, especially for women and girls. Over 750 newly arrived households were supported with emergency shelters, decongesting receptions centres and ensuring new arrivals are self-sustaining. Energy interventions addressed environmental degradation and improved cooking practices by installing LPG systems in large institutions and distributing bio-briquettes to over 1,550 persons with specific needs, avoiding deforestation across 93 hectares. These integrated efforts not only met immediate humanitarian needs but also built resilience, promoted dignity, and supported long-term wellbeing for refugee populations, aligning strongly with the programme’s intended outcome.
[1] WFP country Report 2024 docs.wfp.org/api/documents/WFP-0000165371/download/

Despite positive trends towards intended outcomes, progress in certain areas has been challenging to measure. Specifically, indicators related to education, shelter provision for the protracted caseload, and selected protection outcomes have shown limited advancement. This is largely attributable to increased operational restrictions and systemic constraints, including prolonged school closures driven by financial shortfalls and policy decisions. These factors have significantly reduced opportunities for service delivery and monitoring, thereby limiting the programme’s ability to demonstrate measurable progress against these outcome areas.
In the reporting year, engagement with policy makers and like-minded actors was high however, research engagement remained low and difficult to achieve. Therefore, for this reporting period, there was no meaningful progress toward effective policy and research engagement as another element of the refugee response.

National disaster responses: progress towards outcomes was made, with the programme significantly contributing toward the development, and review of the national disaster management policies and frameworks. In the reporting year, the programme was instrumental in the Review of the National Disaster Management Policy, development of National Disaster Risk Financing Framework (DRFF) and its Implementation Plan for 2025/26–2030/31 and development of Disaster Management Information System (DIMS). These instruments are critical for strengthening multi-agency disaster management and capacities across Tanzania. They provide a unified strategic direction and operational clarity for all stakeholders involved in disaster preparedness, response, and recovery, a departure from past fragmented approach to disaster management. By institutionalizing roles and responsibilities, they enable better coordination among government ministries, humanitarian actors, and development partners

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

While the refugee crisis is protracted and with significant challenges, T-HAP remains a critical instrument in addressing persistent humanitarian needs driven by regional instability and climate-related shocks. Despite funding constraints and rising protection risks, T-HAP has demonstrated consistent performance and resilience. With limited durable solutions and declining repatriation rates, refugees continue to rely heavily on donor-funded support for their safety and wellbeing. In this context, the UK’s role is increasingly vital, not only in bridging resource gaps to ensure delivery of essential services, but also in convening and influencing peers with the aim of expanding the donor base.

As donor support contracts, a strategic restructuring of T-HAP is recommended to enhance value for money and focus on high-impact areas. Going forward, we recommend the programme should prioritize food and nutrition assistance, targeted protection interventions, and disaster preparedness, while phasing out operations in areas where partners have ceased activities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Assistance and protection provided to existing caseload of refugees and new asylum seekers to sustain lives and livelihoods
Output number:		1	Output Score:	A
Impact weighting (%):		60%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.1: Number of nutritionally vulnerable people receiving food/cash-based transfers/commodity vouchers/capacity strengthening transfers through malnutrition treatment and prevention programmes (WFP)	42,550	42,267** / (<5 F:18,672; M:16,726) / (PBWG[2] aged 18-30yrs- 1,100; PBWG aged 31-59 -6,129)
Output Indicator 1.2: Number of people receiving assistance unconditionally or conditionally (WFP)	187,418	186,066** / (F:97,712; M:93,879)
Output Indicator 1.3: % Moderate acute malnutrition treatment performance rate (WFP Recovery)	>75%	92.60%
Output Indicator 1.4: Average # of litres of water per person per day (l/p/d) available. (Consortium WASH)	25l/p/d	23l/p/d
Output Indicator 1.5: # of individuals receiving contribution for shelter (transitional/long-term shelter response). Consortium WASH	130 households	198 households
Output Indicator 1.6: % of teachers demonstrating subject specific knowledge, and inclusive child cantered and gender sensitive pedagogical approaches. (Consortium Education)	75%	94% (progress measured through classroom observations)
Output Indicator 1.7: Number of targeted students provided with additional support: disability services, girls shine, SAFE school activities, psychosocial support (with evidence of effectiveness when available). (Consortium Education)	3,300	3,450 students received targeted support. / 835 students needing psychological care received referrals
Output Indicator 1.8: % of community members actively participating in prevention program activities, and (b) % with improved knowledge to report protection risks (consortium CBP)	65%	75% participating in prevention program activities
Output Indicator 1.9: % of feedback, referral pathways and individual cases responded to through CFM. (consortium Protection)	75%	99.8%
Output Indicator 1.10: # of refugees and asylum seekers in the camps with improved access to agricultural/vegetable production for dietary diversification and income gain. (consortium Livelihoods)	2500 Households	2500 Households
Output Indicator 1.11: Number of people and institutions supported to use cleaner energy or cooking. (consortium ICF)	2 Public institutions supported / 2500 PSN receiving cleaner cooking energy	3 Public institutions supported with LPG / 2500 PSN supported with bio-briquettes
Output Indicator 1.12: Number of hectares where (a) deforestation has been avoided or (b) conservation agriculture is being practiced. (consortium ICF)	93Ha	93 hectares (same as 250 HH firewood consumption)
Output Indicator 1.13: Proportion of people that receive non-food items (UNHCR)	82%	100% (186,066**)
[2] Pregnant and Breastfeeding Women and Girls (PBWG)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall, the output scored an A meeting expectations. This output focused on delivering quality, cost-effective, and multi-sectoral humanitarian assistance to refugees and host community members, with particular attention to the inclusion of disadvantaged groups. Despite significant underfunding across the response, a slow start due to pending government approvals on partnership agreements, the programme was able to meet its objectives. The UK’s contribution was instrumental in complementing limited resources from UNHCR, WFP, and other humanitarian actors. Notably, some of the UK’s funding was earmarked for sectors facing acute financial constraints and at risk of reversing critical gains made in previous years. This support helped mitigate the impact of resource shortages, safeguarding the quality and continuity of essential services.

Supporting narrative

Food and Nutrition (O.I. 1.1- O.I. 1.3): WFP led the implementation of this output, delivering general food assistance and specialized nutrition support to refugees in camps. During the reporting period, 186,066 individuals received food rations (99% of the target), and 42,267 nutritionally vulnerable individuals including pregnant and breastfeeding women and girls (PBWG), children under five, and people living with HIV or TB were supported with fortified commodities (target met). Slight target variations were due to the ongoing repatriation of Burundian refugees and population movements out of camps. WFP also supported new arrivals with high-energy biscuits and hot meals and provided similar support to voluntary Burundian repatriates. Hospital patients received full rations, and local health providers were trained to ensure inclusive and needs-based targeting.

UK funding was received at a critical time of deepening funding constraints. It enabled WFP to maintain food ration sizes at 82% before reductions to 50%, later adjusted to 65%. This support was essential in sustaining food assistance during a period when other funding sources were limited, helping to prevent further deterioration in food security among refugee populations.

To complement food assistance and mitigate the impact of ration cuts, the programme supported kitchen garden initiatives targeting the most vulnerable households. These gardens reached 2,000 households (100% of the target), improving dietary diversity, reducing food insecurity, and enhancing self-reliance. Post-distribution monitoring showed that supported households had lower food insecurity (27% vs. 33%), better coping strategy scores (rCSI 13.9 vs. 17.9), and greater reliance on own food production (21% vs. 7%) compared to non-supported households. Overall food security remains a concern and dependence on WFP assistance remains high, with 82% of refugees relying on rations as their primary livelihood source.

Protection: Access to justice and legal remedies for refugees and asylum seekers continued to improve, supported through UNHCR’s legal aid partnerships. Legal Assistance interventions reached over 12,000 individuals through legal awareness sessions on family law, SGBV, and inheritance rights. The consortium trained and supported 80 Community Legal Aid Providers (CLAPs), who managed more than 1,500 legal referrals. Over 500 individuals received direct legal aid, with 60% of cases resolved at the community level, contributing to peaceful dispute resolution. These interventions strengthened community confidence in formal mechanisms and contributed to successful outcomes in 17 gender-based violence (GBV) cases, including 11 convictions. In addition, 1,200+ individuals secured civil documentation, improving legal identity and access to services. 85% of beneficiaries reported satisfaction with the support received.

WASH and shelter. In alignment with the UK’s strategic investments to enhance living conditions in refugee settings, significant progress was achieved in the provision of Water, Sanitation, and Hygiene (WASH) services across Nyarugusu and Nduta camps. The Norwegian Refugee Council (NRC) led targeted infrastructure upgrades, including the procurement of 14 new 95,000-liter water tanks and 10 liners for rehabilitating existing tanks, directly improving access to safe and clean potable water. To ensure uninterrupted water supply, essential equipment such as pumps and generator accessories was procured, enabling the successful restoration of a 250KvA generator in Nduta-Nyangwa. These efforts resulted in water access reaching 23 litres per refugee per day, meeting Sphere standards[3]. Water access capacity did not reach the planned 25l/p/d due to challenges relating to quantities at the source, and pumping capacity as only 1 diesel generator was operational. Additionally, over 21,700 water samples confirmed compliance with chlorine safety thresholds, underscoring the effectiveness of water treatment interventions and the commitment to public health standards.
[3] UNHCR’s Weekly Monitoring System (March 2025)
Complementary sanitation and shelter interventions further contributed to improved well-being among refugees, asylum seekers, and host communities. A total of 75 communal handwashing stations, 500 latrines (both new and rehabilitated), and 4 Menstrual Hygiene Management (MHM) rooms in schools were completed, enhancing hygiene and dignity, particularly for women and girls. Due to the need for latrines being high, shared latrines were prioritised benefiting 4,221 people.  Shelter support included repairs to 138 emergency shelters and youth-led construction initiatives that fostered local leadership and community engagement. The programme also provided emergency shelters for over 198 households (approximately 1,000 people) of newly arriving Congolese asylum seekers, significantly contributing to the decongestion of reception centres. These achievements reflect a holistic approach to service delivery, reinforcing the UK’s commitment to expanding access to basic services and improving the quality of life in refugee camps through sustainable and inclusive programming.
Education: During the reporting period, a total of 1,149 teachers in Nduta and Nyarugusu refugee camps were trained in key professional competencies to enhance curriculum delivery. As a result, 94% of trained teachers demonstrated improved capacity in subject-specific knowledge and adopted more inclusive, child-cantered, and gender-sensitive pedagogical approaches. In parallel, 48,220 students received scholastic materials—marking a critical intervention in a context where learners had gone over three years without such support, contributing to improved school attendance and retention. These combined efforts led to 50% of learners showing measurable improvements in learning outcomes.
Additionally, interventions embedded protection work in the school settings. These interventions played a critical role in protecting children from abuse, neglect, violence, and exploitation in schools and outside the school environment. Through strengthened school clubs, over 14,000 children (8,189 girls, 6,510 boys) participated in awareness sessions on child rights, gender-based violence (GBV), and protection reporting mechanisms, creating safe spaces for open dialogue and peer support. The IRC also trained 698 teachers on safeguarding, the prevention of sexual exploitation, and the teachers’ code of conduct, reinforcing a protective school environment. The Girl Shine program empowered 75 adolescent girls with knowledge and skills to recognize and respond to GBV, resulting in a 50% increase in their understanding of safety and rights. Additionally, the distribution of menstrual hygiene kits, WASH supplies, and sports and gardening materials supported girls’ health, dignity, and school attendance, reducing their vulnerability to exploitation and enhancing their participation in school life.

However, the education sector faced significant instability due to resource constraints. Government-led school closures and threats to suspend services, particularly targeting Burundian refugee learners, disrupted learning and prevented students from sitting final exams. This is a risk that is expected to continue in the future. The UK’s funding played a pivotal role, complementing existing resources and sustaining education delivery amid these challenges. Despite the positive outcomes achieved, the sustainability of education services in the camps remains uncertain. Early indications suggest that education for refugees will be deprioritized in 2026, with the government already closing all secondary schools and early childhood learning centres for Burundian children and initiating consolidation of primary schools as part of broader efforts to encourage repatriation.

Energy. Energy access remains a significant challenge for refugee populations and institutions, disproportionately affecting persons with disabilities and those with comorbidities. The heavy reliance on firewood contributed to environmental degradation in and around the camps. In 2024, the Government of Tanzania issued a nationwide directive to transition from firewood to cleaner energy sources, mandating institutions serving over 100 individuals to cease firewood use. In response, the programme worked closely with UNHCR to provide systems for clean cooking. UNHCR procured and installed three LPG systems at Kigoma NMC Arrival Centre, Departure Centre, and Nyarugusu Camp Hospital. Complementary support from UK through DRC enabled procurement and preparation for installation of LPG systems at police posts in Nduta and Nyarugusu camps. DRC also facilitated monthly refilling of LPG cylinders across all supported institutions.

Bio-briquette production continued to be a vital energy solution, particularly for Persons with Specific Needs (PSNs), enhancing cooking practices and contributing to environmental protection. In the reporting year, 1,064.5 tons of biomass materials were procured, resulting in the production and monthly distribution of 375 tons of bio-briquettes to 1,550 PSNs (994 women, 556 men) in Nduta and Nyarugusu camps, with each PSN receiving 50kg per month. As a result of the shift to clean energy, an estimated 93 hectares of land deforestation (equivalent to the firewood needs of 250 households) was avoided. To promote efficient energy use, DRC conducted sensitisation through home visits, reaching 16,551 individuals (8,268 women, 8,283 men) with awareness on best cooking practices and fuel-efficient stove (FES) usage. This led to the fabrication of 5,880 FES units (2,076 in Nduta, 3,804 in Nyarugusu), further supporting sustainable energy adoption in the camps.

Livelihood In 2024, notable progress was made following the easing of previous government restrictions on kitchen gardening. As a result, 1,000 refugees (778 women, 222 men) in Nduta and Nyarugusu camps benefited from organic kitchen gardening activities. Targeting the most vulnerable households, beneficiaries received training in vegetable production techniques, including seedbed preparation, harvesting, and post-harvest handling. Additional training on plant companionship and food preparation further enhanced their capacity for sustainable gardening. Kitchen gardens were established at household level and Farming Training Centres (FTCs), serving as demonstration plots. Distribution of vegetable kits—comprising seeds, hand hoes, watering cans, and organic manure—enabled households to improve dietary diversity and household nutrition.

In the host communities of Kibondo and Kasulu districts, DRC implemented complementary agricultural and income-generating activities aimed at enhancing food production and economic resilience. A total of 350 individuals (230 women, 120 men) received training and inputs to support vegetable production for both consumption and commercial purposes. Agro-processing support was extended to Kitahana AMCOS in Kibondo, in collaboration with SIDO Kigoma, focusing on sunflower value chain development, packaging, marketing, and machine operation. In Kasulu, fish farming initiatives were launched, with selected community groups trained and supported to establish fishponds stocked with catfish and tilapia. In Nduta/Kibondo, fish farming was integrated into TVET programmes to build entrepreneurship skills among youth and interested community members. These interventions, implemented in close coordination with local government authorities, contributed to improved nutrition, sustainable livelihoods, and environmental conservation through nature-based solutions.

Non-Food Items (O.I. 1.13): Soap remains a critical non-food item (NFI) in promoting health, protection, and dignity among refugee populations in Tanzania. In camp settings, its role in preventing communicable diseases such as cholera, diarrhoea, and respiratory infections is indispensable. Additionally, soap availability has been essential in supporting menstrual hygiene management and safeguarding the dignity of women and girls. At the beginning of the reporting period, a complete pipeline break in soap distribution occurred due to resource constraints, posing a significant risk to public health and hygiene standards in the camps.

Despite these initial challenges, the programme successfully restored and scaled up soap distribution, reaching 189,696 refugees and asylum seekers across Nduta (56,531) and Nyarugusu (133,165) camps with a total of 397,868.5 kg of bar soap. Each individual received 250g of soap per month, which, although below the recommended 500g standard, contributed meaningfully to improved hygiene outcomes and reduced pressure on health services. A temporary disruption caused by the USAID stop work order affected UNHCR’s procurement systems, resulting in a three-month gap in distribution. However, by the time of this review, soap distribution had resumed and continues as planned, ensuring consistent access to this essential item for all camp residents.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

During the reporting year, several significant developments impacted the delivery of this output. The suspension of funding by the US placed considerable pressure on implementing partners, as UK resources were designed to be complementary. This funding uncertainty led to the announcement of operational closures for consortium-led activities. In response, and in close coordination with delivery partners, efforts were made to safeguard UK contributions and ensure delivery of Year One and Year Two outputs. A rationalisation process was undertaken to prioritise deliverable components, while deferring or cancelling activities that were no longer feasible due to funding constraints or an increasingly restrictive operating environment.

Additionally, a key change involved the reallocation of the £0.45 million crisis modifier, originally reserved for nationally declared emergencies. As no such crises occurred and new asylum seekers were accommodated through existing mechanisms, approval was granted to redirect these funds to address urgent food and nutrition needs, which had become increasingly critical.

Describe major changes in the past year and their implications for the programme.

During the year, the main change to the programme was adjusting activities to support newly arriving asylum seekers. The programme had built-in funding to respond to such needs, but when the number of arrivals was higher than expected, the programme was able to find savings within the existing budget to fill the gaps and continue support.

Another important change happened in the education sector. The suspension of US aid had a major impact—some schools were closed, incentive workers stopped receiving payments, and exams were put on hold. To help manage this, UK and partners agreed to pause most capacity-building activities and use the savings to keep incentive teachers in classrooms until the end of December 2025. Although this was not part of the Year 1 targets, it will be tracked and reported in Year 2.

Lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

One of the key strengths of the programme this year was its ability to remain flexible and respond quickly to changes in the operating environment. For example, when Nyarugusu camp experienced a sharp increase in refugee arrivals due to instability in the DRC, the programme was able to adjust its support through the DRC-led consortium to meet the growing needs. Another major shift was the reduction of food rations to 50%, which led to increased protection concerns and food insecurity in the camps. In response, the programme worked with WFP to raise the ration level to 65%. While this was a modest increase, it helped reduce negative coping strategies among affected households and contributed to improved food consumption scores.

Recommendations for the year ahead

The programme gained valuable insights during the reporting period, particularly in response to the operational challenges following the US funding suspension. These circumstances provided an opportunity to reflect on the sustainability of interventions and highlighted the importance of coordinated delivery among partners operating in a constrained and shifting environment. A key lesson was the need for stronger collaboration mechanisms to ensure targeted and efficient support, especially under pressure.

Recommendations are proposed for the year ahead:

Logframe Revision: Update the programme logframe to reflect the exit of consortium partners, and revised scope and priorities. This will help maintain strategic coherence and improve measurement of impact under the new operating conditions.

The programme should collaborate closely with UNHCR and WFP ( the remaining actors) to develop scenario analyses that consider varying funding levels, policy constraints, and their potential impacts on refugee populations. These analyses should be used to guide prioritisation decisions and ensure alignment with other development partners, fostering a coordinated and evidence-based approach to resource allocation and programme planning.

Output Title	Extent to which national disaster management policies and frameworks are developed or strengthened
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 2.1: Number of national policies, strategies, developed or strengthened to enhance national and regional disaster management capacity.	4 National Polices or Strategies Developed on DRM	Total 4 National Polices or Strategies Developed on DRM / Review of the National Disaster Management Policy / National Disaster Risk Financing Framework (DRFF) / DRFF Implementation Plan for 2025/26–2030/31 / Disaster Management Information System (DIMS)
Output Indicator 2.2: Number of national and regional government officials trained on disaster management tools and framework and number of rapid emergency response teams formed in critical regions	40 multi-agency government officials trained	20 multi-agency government officials trained
Output Indicator 2.3: Number of capacities strengthening initiatives facilitated by WFP to enhance national stakeholder capacities around disaster risk reduction	3	3 capacity strengthening initiatives took place for Regional Response Team

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall, this output met expectations and has been assigned an “A” rating. While one activity partially met its targets, the rating is warranted given the significant gains achieved in the policy space. The programme successfully influenced key policy dialogues and strengthened engagement with government stakeholders, contributing to systemic changes that extend beyond immediate outputs. These achievements represent strategic progress toward long-term outcomes.

This component was introduced following the 2023 Capacity for Disaster Reduction Initiative (CADRI) assessment on disaster and climate risk management, at a time when there was no UK-support for strengthening Tanzania’s disaster response systems. Its launch was timely, coming shortly after two major natural disasters and increased national attention on preparedness, response and recovery. Delivered through WFP in partnership with the Prime Minister’s Office – Disaster Management Department (PMO-DMD), the programme’s niche has focused on addressing priority needs and ensuring alignment with both government strategies and the SENDAI Framework during the reporting period.

Over the past year, the programme successfully supported the development of two key policy frameworks, most notably the review of the National Disaster Management Policy (NDMP) 2004, resulting in the updated 2025 edition approved in January 2025. This process involved collaboration with various government ministries and agencies and marked a significant step in strengthening national disaster preparedness and response systems. The original 2004 policy played a foundational role in institutionalising disaster management in Tanzania, clarifying government responsibilities, and integrating risk reduction into development planning. It also paved the way for important reforms such as the Disaster Management Act (2015) and the 2022–2027 strategy. The continued relevance of the NDMP reflects sustained political commitment and progress toward a more proactive and resilient disaster management framework. While he NDMP is an operational document, work is underway to launch the policy.

The programme also successfully supported the development and approval of the National Disaster Risk Financing Framework (DRFF) and its Implementation Plan for 2025/26–2030/31, endorsed in July 2025. This framework represents a strategic shift from reactive disaster response to proactive financial preparedness. Key priorities include improving access to risk data, enhancing sovereign disaster risk financing capacity, and exploring private sector engagement through strengthened insurance markets. The DRFF also focuses on strengthening public financial management systems, making social protection programmes more responsive to shocks, and expanding the use of financial instruments for disaster risk management. These efforts are aligned with the broader goal of establishing an Adaptive Social Protection system. Implementation is led by the Disaster Management Department (DMD), with support from the Ministry of Finance and other stakeholders, aiming to safeguard development gains, ensure fiscal stability, and protect vulnerable populations through timely and sustainable disaster financing.

The programme is also supporting the Government to strengthen its understanding of disaster and climate risks. In July 2025, the Climate Vulnerability Mapping System was launched by the PMO, Vice-President’s Office, and TMA, with support from GCA and IMF. WFP is working with DMD to promote operational use of the platform through technical workshops and sectoral data integration. While the system offers valuable data for risk prioritisation and planning, it currently faces challenges related to limited data input, weak analysis, and low user capacity. Implementation efforts have been accelerated in the second half of 2025, with workshops focused on climate vulnerability mapping and system requirements for the Disaster Management Information System (DIMS).

In its first year of implementation, the programme achieved notable success in delivering policy-level outputs. While the initial target was to engage 40 government partners in capacity strengthening activities, only half (20) were engaged and the remainder of these were deferred as they depended on the establishment of key policy frameworks. With these foundational elements now in place, the programme will move forward with targeted capacity building efforts in the next phase.

Lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This output achieved notable success during the reporting period, meeting key milestones within the planned timeframe. Strong government interest and trust in WFP’s role as a delivery partner contributed to effective implementation, particularly in areas requiring close collaboration with national agencies.

Looking ahead, it is recommended that the programme strengthen coordination by establishing formal linkages with complementary initiatives led by the World Bank, UNICEF, UNDRR, and EW4A. A more integrated approach to disaster management would enhance impact and resource efficiency. This agenda will be advanced through the emergency coordination chair and existing informal networks with these actors.

Output Title	Effective Policy and Research Engagements
Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 3.1: Examples of successful campaigns to strengthen justice and protection systems and policies for refugees (UNHCR)	Successful campaign on access to asylum and protection.	In the reporting year, two campaigns were conducted. / (a) Access to asylum for newly arriving Congolese (over 3500 registered). / (b) on-going completion of naturalization processes for 6,620 children
Output Indicator 3.2: Number of research produced and disseminated covering Burundi Refugees and migration patterns and durable solutions and Number of stakeholders who attend the dissemination events and targeted engagement and reporting improved knowledge on the situation of Burundian cross-border labour migration to Kigoma Region. (Consortium Research)	N/A – No targets for year 1	N/A – No targets for year 1

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall, this output partially met expectations, Scoring B.

Throughout the reporting period, the UK maintained a leadership role in supporting the preservation of asylum space in Tanzania and advocating for improved conditions within refugee camps. This included targeted diplomatic engagement at senior levels within the Ministry of Home Affairs, with a particular focus on ensuring that any returns to Burundi are voluntary, informed, and aligned with reintegration capacity. The UK also played a key coordination role within the donor community, actively promoting unified positions and encouraging UNHCR to enhance its communication and transparency on refugee-related matters.

UNHCR continued its collaboration with the Government of Tanzania to ensure access to asylum in accordance with international protection standards. Over 3,500 new arrivals were registered, achieving full individual documentation for refugees and asylum-seekers. Civil registration efforts led to the issuance of birth certificates for 8,847 children, thanks to coordination with local authorities. This was especially important as repatriation efforts for Burundian refugees intensified. UNHCR also advocated for the completion of naturalization processes for 6,620 children from the 1972 Burundian refugee group and promoted refugee inclusion in national planning and sectoral dialogues, including education and women, peace, and security initiatives.

UNHCR engaged with ministries, judicial bodies, and civil society to align national protection frameworks with international and regional standards. Despite ongoing capacity-building and policy dialogue, Tanzania’s legal framework remained misaligned with key international conventions, including the 1951 Refugee Convention and the 1961 Statelessness Convention. The National Eligibility Committee (NEC) did not meet during the year, leaving nearly 40,000 asylum-seekers without refugee status determination. UNHCR continued to advocate for temporary prima facie recognition for Congolese and Sudanese arrivals to preserve protection space.

Despite ongoing advocacy, the Government of Tanzania intensified pressure for repatriation, including calls to close schools and camps, and restrict service delivery. In collaboration with UNHCR, a Comprehensive Protection and Solutions-Based Assessment was conducted in Nduta and Nyarugusu camps, Old Settlements (Mishamo, Katumba, Ulyankulu), Kigoma Villages, and Dar es Salaam, covering over 36,000 households. Findings showed low interest in return, with socio-economic barriers such as lack of land and livelihoods being key concerns. These results echoed previous surveys and underscored the need to distinguish protection risks from broader hesitations. Following the findings, it was recommended that voluntary repatriation is the most viable and sustainable solution as Burundian residing in Tanzania. At the time of this report, it is unclear if this includes those of the 1972 caseload as they were not? part of the assessment.

No major legislative reforms were enacted during the reporting period. There are no indications that this target will not be met. This is evidenced through structural challenges such as the encampment policy, restricted freedom of movement, limited access to employment, and the inactivity of the NEC continued to hinder protection outcomes for refugees and asylum-seekers in Tanzania.

During the reporting period, preparatory activities were undertaken to lay the groundwork for a research and analysis initiative aimed at informing and improving asylum policies and institutional frameworks in Tanzania. This output was to be delivered by the Mixed Migration Centre (MMC), operating under a consortium led by the Danish Refugee Council (DRC). While the first year was designated for preparatory work, including research design and data collection planning, all key milestones for this output were scheduled for implementation in Year Two.

Although this output is not subject to assessment in the current reporting year, early indications suggest that it may not achieve its intended targets. As of the time of this review, the Government of Tanzania had not granted the necessary research permits for studies related to Burundian refugees. This has significantly constrained the ability to generate new evidence and has limited opportunities for engaging government stakeholders through research-based advocacy.

Lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Identify and develop targeted advocacy messages aimed at key decision-makers and the broader international community. These should focus on improving camp conditions, particularly in the area of livelihoods, in light of limited international funding. Advocacy should also reinforce the importance of maintaining the voluntary nature of refugee repatriation.

Increase protection-focused assessments in the camps, especially in relation to the repatriation process. This should include better documentation of the sources of information available to refugees, as well as their motivations and barriers to repatriation. Findings should inform both operational planning and advocacy efforts with government stakeholders.
## D: VALUE FOR MONEY (1 page)

In the initial stages of the programme, all delivery partners were required to integrate VfM considerations into their planning and implementation processes. For WFP, this was relatively straightforward as several VfM indicators were already embedded within their annual country reporting framework. This also aligns with existing framework agreement. The programme team collaborated closely with WFP to define and contextualize indicators for economy, efficiency, and equity. For the consortium-led component, VfM indicators were identified through the steering committee. The programme emphasized collaborative approaches to enhance effectiveness, actively balancing national and international staff to manage cost drivers, and prioritizing interventions that targeted marginalized groups. Additionally, deliberate efforts were made to promote gender parity in delivery, reinforcing the programme’s commitment to equity and inclusivity while achieving VfM.

Key cost drivers and performance

T-HAP continues to deliver Value for Money (VfM) across all five dimensions, despite operating in an unpredictable, deteriorating funding and protection environment. While assessing and engaging partners in detailed VfM conversations, the programme has additionally, and successfully, adapted to shifting donor dynamics, rising unmet needs, and policy constraints by prioritizing resources on lifesaving services, leveraging long-term partnerships, and deploying cost-effective interventions.

VfM Criteria	VfM action
Economy	The programme demonstrated strong financial stewardship and cost-effective delivery across its components. WFP’s innovative procurement strategies, including local sourcing from smallholder farmers, notably reduced commodity unit costs and injected cash into Tanzania’s economy, with 22,490 metric tons of food procured locally. / The DRC-led consortium effectively managed cost drivers, primarily personnel and operational expenses. With a 1:150 ratio of international to national staff and only two international staff fully funded by the programme, personnel costs were significantly minimized. FCDO’s partial salary contributions (10–20%) for technical staff further reduced financial burden, to the programme and ensuring there is burden share. Procurement activities during the reporting period were primarily focused on refurbishment and rehabilitation works, including replacement of water tank liners and repairs to generators. The programme deliberately avoided large asset acquisitions, thereby reducing capital expenditure and ensuring resources were directed toward operational priorities and cost-efficient solutions. / Partners achieved up to 17% savings through competitive bulk procurement of key items such as LPG, SRH kits, and pressure cookers. FCDO ensured robust financial oversight via Due Diligence and independent audits. Earmarked funding enabled the programme to concentrate on areas of strategic importance, safeguarding priority activities from fluctuations in donor resources and ensuring critical needs were met. This approach contributed to cost efficiency by reducing financial uncertainty and streamlining resource allocation. In addition, partnering with an experienced NGO consortium delivered significant economies of scale. Through enhanced collaboration among actors, the programme achieved joint prioritization of needs, minimized duplication, and maintained low transaction and overhead costs, thereby reinforcing Value for Money across implementation.
Efficiency	WFP’s use of digital tools like SCOPE helped reduce staffing needs and errors, allowing for faster and more accurate distributions using the joint Government of Tanzania–UNHCR refugee data. Coordination efforts led by the Inter-Sector Coordination Group helped reduce duplication by streamlining services in camps. / In response to global aid budget cuts, organisations adapted by restructuring, forming local partnerships, and in some cases, closing or handing over programmes. Despite these challenges, the programme maintained strong delivery performance, meeting or exceeding key targets such as LPG refills, shelter improvements, and GBV/SRH services.
Effectiveness	WFP played a key role in enhancing Tanzania’s logistics capacity, regional food transport, and supply chain services while supporting both humanitarian operations and national economic development. WFP facilitated the transportation of 169,928 metric tonnes of food to regional countries through Tanzania’s supply chain corridor via the Port of Dar es Salaam, ensuring efficient logistics operations, including port and border clearances, cargo supervision, and handling. These activities contributed USD 23 million to the national economy and generated employment opportunities across multiple sectors
Equity	The programme embedded equity considerations throughout its design and implementation, ensuring tailored support for vulnerable groups. Partner proposals, aligned with FCDO guidance, outlined specific strategies to address the needs of women, children, older people, and persons with disabilities. / Operational delivery prioritized inclusivity, with targeted registration and distribution mechanisms for refugee subgroups such as child-headed households, orphans, and women at risk. Nutrition-sensitive interventions, including supplementary feeding and kitchen gardening, addressed dietary gaps identified in WFP’s 2024 baseline, particularly for women and girls of reproductive age.

Assessment of whether the programme continues to represent value for money

The programme continues to demonstrate strong Value for Money (VfM), consistently achieving milestone targets at the output level and remaining on track to deliver forecasted outcomes for the year. Progress to date reflects efficient delivery of humanitarian interventions aligned with cost drivers and focused on reaching the most vulnerable populations. However, as the programme pivots to respond to significant contextual changes, both outputs and outcomes will evolve. A comprehensive VfM reassessment will be undertaken for the remaining implementation period, including the introduction of additional VfM indicators to ensure continued accountability and alignment with the revised programme priorities.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk of the T-HAP continues to be rated as ‘major’. This is the result of challenges in delivering responses in a strict policy environment as well as volatility in resource allocation. The risk level of the programme remains within FCDO’s risk appetite. BHC Dar es Salaam’s Humanitarian Team maintains a risk register for the T-HAP, which sets out mitigation measures and trigger points for escalation. Critical mitigation measures that have ensured the programme does not go beyond the risk appetite have included regular meetings with the government, and delivery partners to understand the operational context and challenges, application of flexibility in our programming and regular monitoring. Documenting potential risks and raising those to SRO and Development Director level has also worked as a control mechanism. This is updated quarterly based on conversations with, and written reporting from, T-HAP’s delivery partners; information attained during FCDO field visits; and conversations with Government. T-HAP’s key risks are set out below.

During this period there were no residual risks above the programme’s and/or BHC Dar es Salaam’s risk appetite requiring escalation. UK and partners continue to pro-actively review risks and mitigation measures.

Strategic and contextual:

Reduced donor funding. Global funding cuts have had a profound and destabilising impact on the refugee response. This abrupt reduction in support poses a serious risk of deteriorating conditions for the refugee population. With no significant progress in promoting self-reliance and a shrinking pool of humanitarian funding, the wellbeing of refugees, especially refugees of Burundi origin, is increasingly at risk.

There is a risk that Burundian refugees will be forcibly returned to Burundi as a result of a combination of factors such as low levels of voluntary reparation targets being met, reduced resources, and increased government restrictions. There is also a risk that a lack of funding reduces the provision of services.

Further influx. As of October 2025, a total of 3,548 asylum-seekers from the DRC were registered and resided in Nyarugusu camp and Kigoma Reception Centre (NMC). While this number is small compared to registered new arrivals from DRC across the region, further escalation of conflict in Eastern DRC could result in a continued influx of new arrivals and the expansion of assistance mechanisms will have significant implications for the overall humanitarian response, including increased pressure on resources, service delivery, and protection systems.

There is a risk of an extreme natural disaster that causes significant loss of life, livelihoods, and property in Tanzania. UK mitigation includes continued support to strengthen response and preparedness systems and advocating to strengthen the Government’s risk mitigation measures.

These risks have been recorded and continue to be monitored closely. In response, we have accepted some risks, including the closure of operations for some partners. This has allowed the programme team to continue supporting the partners as they work toward eventual exit.

Financial and fiduciary
As with other humanitarian contexts, there is a risk of loss of funds because of fraud, misuse or aid diversion. UK is working to mitigate this by ensuring partners are following the FCDO aid diversion policy and using fraud registers; and that they fully understand and recognise the FCDO's zero tolerance of fraud and corruption, and their requirement to report incidents. This is followed by scrutiny of partners’ quarterly financial and narrative reports, and external audits undertaken by third parties. There was one fraud case reported during the review period. Partners’ financial capacity, corporate systems and policies (including on safeguarding, fraud and HR) are assessed through comprehensive Due Diligence Assessments, which are undertaken by FCDO on all partners directly receiving UK funding.

Safeguarding risk

The programme works in a very vulnerable context, where there is a risk that beneficiaries—especially women and girls—could face sexual exploitation, abuse, or harassment by partners or volunteers funded by the UK. From the start, the team focused on reducing this risk. All partners were required to have safeguarding policies, and these were checked during the enhanced due diligence process. The checks also looked at how well partners’ reporting systems worked.

During implementation, the programme received several reports of concerns, with one confirmed as a safeguarding case. The partner involved acted quickly and provided the right support services. All cases are recorded and tracked by central teams and compliance offices. They are monitored through investigations until they are resolved and actions are taken. The programme continues to keep strong case management systems in place. Partners meet regularly with the BHC during monitoring and field visits to make sure safeguarding standards are followed.

Programme Delivery

The programme faces heightened delivery risks due to a growing refugee caseload and declining donor support. Service provision for new arrivals is particularly vulnerable, as evidenced by the reduction in food rations to below 50% during the year, before partial recovery to 65%. The freeze in US aid has had a significant impact across all sectors, with education, child protection, and livelihoods experiencing the most severe disruptions. In the absence of substantial alternative humanitarian funding, both refugee and host communities are at risk of losing access to essential support.

A major operational risk stems from the planned exit of four core delivery partners by December 2025, directly linked to the US funding freeze. BHC has worked closely with cross-sectoral teams to manage this transition and minimize service gaps. However, the outlook remains uncertain, with limited prospects for qualified humanitarian actors to replace those exiting. In response, FCDO will begin a phased closure of programme components delivered through these partners, prioritizing continuity where feasible and mitigating disruption to affected populations.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

As set out in the document, the T-HAP’s implementing partners are UNHCR, WFP and a DRC led consortium of NGOs. To allocate funding, FCDO received proposals from partners and agreed allocations based on humanitarian needs. The partnerships between FCDO and its partners differed with some showing strong elements of coordination and communicating timely, while in other instances these elements were lacking.

The the FCDO partnership with the DRC led consortium and WFP programmes is strong, and the quality of programme management and delivery was satisfactory. Most of these partners have been implementing UK-funded activity to support the Tanzania refugee response since 2017 and consistently delivered quality programming.

While UNHCR continued to convene regular monthly coordination meeting between the government, UNHCR, donor and humanitarian actors, there were several operational and communication challenges observed during the reporting period. UNHCR has experience a huge turn over, and the position of country representative remained vacant for a year. The BHC team experienced delays in information sharing and inconsistent communication, which in turn limited timely decision-making and affected the quality of joint advocacy outputs. Limited external engagement resulted in critical updates not being shared in a timely manner, undermining coordination efforts and reducing the effectiveness of our collective influencing agenda. The lack of senior programme management expertise within UNHCR has also exacerbated the challenges in managing the programme.

Project Number	Partner	Project Name	Budget	Spent	Variance
301375-401	DRC	Support to provide life-saving interventions for encamped refugees in Tanzania.	2,276,934.00	2,276,993.00	(59.00)
301375-402	WFP	Provision of humanitarian assistance including food assistance nutrition, and disaster risk management in Tanzania	2,223,066.00	2,223,066.00	0.00
301375-403	UNHCR	Support critical essential services, camp management and policy influencing on refugee sector in Tanzania	1,000,000.00	1,000,000.00	0.00

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
The UK continues to play a leading role in humanitarian donor coordination in Tanzania, particularly in refugee operations. Through its leadership in coordination meetings, the UK has helped collate and triangulate critical data, enhancing the monitoring and collaboration among humanitarian actors and agencies operating in the field. This platform has been pivotal in aligning efforts, identifying gaps, and ensuring more effective responses to emerging needs.
Throughout the year, the programme maintained regular engagement with delivery partners to support effective monitoring and coordination. Monthly catch-up meetings were established with WFP and UNHCR to review progress and operational updates. While consistency in monthly meetings was occasionally impacted, the team demonstrated flexibility by ensuring quarterly engagements were upheld.
In response to a dynamic operational environment, particularly within the DRC-led consortium, a quarterly Steering Committee was instituted to provide strategic oversight. Following funding cuts and their potential impact on programme delivery, the frequency of Steering Committee meetings was increased to monthly. This proactive adjustment enabled closer management of activities, timely decision-making on critical issues, and sustained programme continuity. Through these intensified coordination efforts, the team successfully revised Year 2 logframes, identified cost-saving opportunities, and aligned partner delivery with programme objectives.
During the reporting period, the UK undertook three field missions to the Kigoma Region, visiting Nyarugusu and Nduta refugee camps, as well as the Kigoma Refugee Reception Centre (NMC). These missions aimed to monitor ongoing activities and engage directly with frontline delivery partners and the refugees. Notably, the visits included separate engagements by the UK High Commissioner and the Development Director, underscoring the strategic importance of the refugee response.
Insights from these missions were shared with the humanitarian donor group and informed key messaging between development partners and the Government of Tanzania (GoT). Findings from joint border missions, guided programme-level decisions, including prioritising core humanitarian assistance for new arrivals and strengthening protection services for asylum seekers from the Democratic Republic of Congo (DRC). On programme level outputs and outcomes, decisions were reinforced by evidence generated through partners’ Monitoring, Evaluation, and Learning (MEL) systems—such as WFP’s post-distribution monitoring, follow-up surveys, and established feedback and complaints mechanisms. Data from these processes provided insights into service quality, beneficiary satisfaction, and emerging risks, enabling adaptive management and refinement of key outputs to ensure relevance and effectiveness in a rapidly changing context.
Partners—both directly funded and unfunded by the UK programme, including DRC, MTI, IRC, and NRC—routinely shared internal monitoring data through periodic reports. These were verified through FCDO’s field visits, ensuring accountability and alignment with strategic objectives.
Below is a summary of the observations made during the various field visits

1. Protection and Policy Environment
- Refugees continue to face restrictive policies, with Burundians reportedly subjected to harsher treatment.
- Many Burundian refugees expressed hope in the comprehensive protection and solutions assessment, viewing it as a platform to voice their reasons for fleeing.
- A significant number of refugees remain in transit centres for extended periods, lacking access to education and living in overcrowded, substandard shelters.

2. Service Delivery and Resource Allocation
- The level of most service provision is low. In October -December 2024 there was a pipeline break NFI i.e. soap. Education services have been paused on a number of occasions. Sanitarian facilities at household levels are not sufficient and Primary Health Care in Nduta is near collapse.
- FCDO resources have been strategically deployed to address critical gaps, particularly in protection services for new arrivals and in reducing congestion at reception centres through the provision of emergency shelters for households. These interventions have restored dignity, reunited families, and mitigated protection risks as well as broader health and well-being concerns. While sustainability will be assessed in the coming years, early plans and indications suggest that UK investments have the potential to maintain service quality—especially in water supply—beyond the current implementation period.

3. Vulnerable Populations
- Children and youth constitute a large proportion of the refugee population, heightening the need for age-appropriate services.
- School closures have had a detrimental impact on refugee children, contributing to increased dropout rates, early marriages, and mental health challenges.
- Persons with disabilities face significant barriers in camps, including limited access to inclusive education, stigmatization, and inadequate support systems.

Evidence
Although not directly funded by FCDO, significant efforts were made over the reporting period to strengthen the evidence base for programming decisions through collaboration with FCDO partners and other humanitarian actors. The Regional Durable Solutions Secretariat (ReDSS)[4] conducted studies on the return and reintegration of Burundian refugees, contributing to a deeper understanding of the return environment and informing future strategic support in light of shifting political and aid dynamics.
[4] Supporting Durable Solutions in a Shifting Political and Aid Context: The future of refugee and returnee responses in Tanzania and Burundi
Complementary research by humanitarian actors provided a comprehensive analysis of prioritised needs in refugee camps, offering a holistic view of sectoral gaps. Collaboration with the University of Dar es Salaam’s East Africa Research Chair on Forced Displacement further enriched the knowledge base on durable solutions for refugees in Tanzania, with findings supporting advocacy and policy engagement.

Programme-specific surveys, including KAP surveys by the DRC-led consortium and WFP’s Community Household Surveys, were instrumental in establishing baselines and enhancing understanding of food security challenges as well as cross sectoral challenges. Feedback mechanisms within camps ensured two-way communication with refugee communities, enabling responsive programming based on community-identified priorities. Key concerns raised included reduced food rations, shelter maintenance, non-food item distribution, and improved WASH services.

Learning
A key area of learning over the past year has been the programme’s ability to adapt to shifts in the aid landscape and navigate sector-wide changes with flexibility. Initial documentation and analysis have captured lessons from these transitions; however, further work is needed to deepen understanding of operational viability in the face of continued funding constraints and a restrictive policy environment.

Looking ahead, targeted analysis of the capacity of local actors to sustain refugee response efforts will be critical, particularly in the context of the anticipated withdrawal of several international NGOs currently delivering humanitarian assistance. This assessment should examine feasible engagement modalities under conditions of diminishing resources and evaluate the potential impact on refugee populations. In parallel, close monitoring of how the international community adapts to the evolving operational landscape—especially in safeguarding refugee rights and managing voluntary repatriation processes—will be essential. Insights from this analysis will inform future strategic positioning, partnership approaches, and advocacy priorities.

Progress on recommendations from previous reviews (1/2 page)
N/A

Audited Financial Statement
Audited financial statements are aligned to a calendar year and programme calendar year for all implementing partners. The auditors’ opinion from the last audit statements was ‘unqualified.’

Date of last narrative financial report	DRC: 19 May 2025	Date of last audited annual statement	DRC: 13 October 2025