## Annual Review Template

Title: Overseas Development Institute (ODI) Fellowship Scheme Accountable Grant 2022-2025
Programme Value £ (full life): 9.6 million		Review date: August 2024 – July 2025
Programme Code: [AMP ID#] 301376-101	AMP start date: 01/04/2022	AMP end date: / 31/012/2026

Summary of Programme Performance
Year	2022/2023	2023/24	2024/25
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0002804.odt / https://iati.fcdo.gov.uk/iati_documents/D0002805.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0002838.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The ODI Fellowship Scheme, delivered by ODI Global, remains a flagship technical assistance programme for the Foreign, Commonwealth and Development Office (FCDO), supporting the development of effective, resilient public institutions across low- and middle-income countries. Now in its seventh decade, the scheme continues to place highly qualified economists and statisticians in key government ministries and agencies, providing critical support for policy development, capacity building, and institutional reform.

The scheme’s goal is to bolster the capabilities of local public sector agencies and encourage mutual learning by placing highly qualified early-career economists and statisticians in government roles.

During the 2024/25 reporting year, the scheme deployed 59 Fellows in post across Africa, Asia, the Pacific, and the Caribbean, including a significant increase in placements in Pacific Island countries. The programme’s focus on skills transfer, and mutual learning has ensured that both host institutions and Fellows benefit from the experience, with consistently high levels of satisfaction reported by supervisors and Fellows alike. The scheme’s adaptability and robust safeguarding mechanisms have enabled it to respond effectively to operational challenges, including evolving host government needs, security incidents, and the ongoing demands of a complex global environment.

In 2024, ODI has continued to successfully place new Fellows in ministries around the world, including the Pacific region, while supporting those who started their Fellowship in previous years, and those who have finished their programme. In March 2025, ODI Global launched a new offshoot of the Fellowship Scheme known as the Mission 300 (M300) Fellowship, in partnership with the Rockefeller Foundation. This initiative is designed to support electrification efforts across Africa by placing 14 Mission 300 Fellows in countries that have agreed to National Energy Compacts. While the M300 Fellowship operates on the same principles as the core ODI Fellowship Scheme—providing high-calibre technical assistance and capacity building within government institutions—it is managed separately and funded through a dedicated agreement. The ODI Fellowship Scheme team have been providing support and guidance during the inception phase, ensuring alignment with ODI’s established standards and approach. The Mission 300 Fellowship represents the first official expansion of the ODI model into a thematic, sector-focused programme, with standalone branding and management, further broadening ODI’s impact in international development. This first official expansion shows the strength of the model in bringing early career professionals to work with ministries around the world in different policy areas.

The ODI Fellowship Scheme programme was amended in September 2024, increasing the total budget to £9,651,500 and the project end date to December 2026. Of this, £7,735,546 is designated for the scheme’s core Fellows, supporting placements across Africa, Asia, and other regions. An additional £1,915,190 was provided by FCDO’s South-East Asia and Pacific Directorate (SEAPD) for Pacific Fellows, enabling the expansion and deepening of the scheme’s work in the region.

Summary supporting narrative for the overall score in this review

The Outputs that have been assessed this year largely met expectations and, with continued good value for money, the programme has an overall score of A - met expectations.

Major lessons and recommendations for the year ahead

- For indicator 1.3 - Number of Pacific Island countries and host institutions supported by the ODI Fellowship Scheme, it is recommended to review the milestone for this indicator by increasing the number of Pacific Fellows placements or assigning a more realistic target. (ODI)
- ODI continues to strengthen its reporting capacity to ensure accurate reports, financial forecasting and invoices are submitted on time. Quarterly reports and invoices are submitted within 30 days of the end of the quarter. (ODI)
- For Outcome Indicator 2 – The amount that most host ministries contribute towards Fellows’ salaries has been reducing or has been minimal, with 9 being less than £100 per month. Host governments paying towards the local salary has been a fundamental principle of the scheme since it started. ODI should carry out a review of host government contributions both in terms of financial and in-kind support before the next annual review of the programme. (ODI)
- The FCDO should develop a multi-year funding proposal for the ODI Fellowship Scheme to give long term stability to the scheme. A further recommendation as part of the multi-year proposal would be to revisit the NPAC funding for all FCDO funded ODI projects. (FCDO)
- ODI should continue to increase its funding base from other development partners to mitigate the risk of being over-reliant on the FCDO for its funding. (ODI)
- ODI should continue to carry out their recruitment processes virtually so that non-British nationals are not denied participating if they cannot obtain a visa to attend the interview in person in the UK. And to manage the financial and environmental costs of the recruitment process. (ODI)
- ODI should track and report instances of serving public servants in Low Income Countries being offered Fellowships through its risk register and investigate whether a change to eligibility criteria, like the Chevening Scholar commitment, is required to address unintended consequences of promoting diversity in future multiyear business case. (ODI)
- ODI should continue to monitor diversity data and protected characteristics data in their reporting. (ODI)

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change is well summarised in the Business Case:

The Fellowship Scheme aims to ensure services better reach poor people. This will be achieved through the dual approaches of better economic, financial and public sector engagement in host organisations and supplying Fellows who can gain experience of working within host organisations that they can then bring to the wider economic growth / development sector in their future careers which will allow donor organisations to deliver better results.

The above logic remains valid. Fellows indicated that they; (a) made valuable contributions to host institutions in delivering public services; and (b) gained useful experience in public sector institutions in low- and middle-income countries during their Fellowship

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Funding for the current phase of the ODI Fellowship Scheme was originally approved in March 2022. In this third year of the accountable grant the Fellowship Scheme has continued to develop with
- More Fellows: There are currently 49 Fellows in post, 41 are funded by FCDO, with 8 funded through other institutions. However, this number is still low compared to pre Covid levels.
- Recruitment and diversity:
  - The Fellowship continues to be offered to candidates from around the world, with the current 39 Fellows coming from 19 different countries, with over 1/3 from the Global South.
  - ODI have continued to promote the Fellowship through webinars, blogs, alumni, etc. For the 25/27 cohort recruitment, there were 956 applications in total, with 48 candidates interviewed. ODI ran this recruitment online rather than in person which reduces costs and allows Fellows to be interviewed without applying for a UK Visa. ODI are looking to update their systems to improve the diversity data they are able to capture throughout their recruitment process.
- Engaging alumni network: ODI continue engage with Fellowship Scheme alumni, to support current Fellows, and explore ways to further strengthen the scheme. There are now over 500 members of a dedicated LinkedIn group, as well as former Fellows taking part in recruitment activities such as shortlisting and interviewing Fellows; assisting with briefing week sessions to provide advice to the new cohort; and providing country connections and mentorship for Fellows whilst they are on their placements.
- FCDO staff visit to Fellows and ministries:This year FCDO travelled to Rwanda to meet with several Fellows and their host institutions. This visit highlighted the wide range of technical expertise that the Fellows provide, and the benefit that this programme has for both Fellows and hosts. Heads of UK missions have been informed of the presence of ODI Fellows in their countries. The majority of Heads of Missions are in contact with the Fellows and have reported the high technical and soft power value that Fellows bring. ODI have continued to effectively place Fellows in ministries across the world who are providing high quality technical expertise to their departments and wider ministries.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

Progress against the Outputs meets expectations, and the Fellows are providing value to the host institutions. The ODI Fellowship scheme is in line with the Foreign Secretary’s aims for the UK to become a partner of expertise and build modern respectful partnerships with global south countries. It is a recognized UK brand that not only provides technical assistance to countries but strengthens the UK’s reputation overseas. Thus, the programme should continue as resources allow.

## C. DETAILED OUTPUT SCORING

Output Title	Fellowship Scheme re-established after a three-year break and host institutions in low- and middle-income countries are provided with high calibre junior economists and statisticians to plug gaps in local capacity
Output number:		1	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of FCDO – funded ODI Fellows starting or completing (depending on year) their 2-year Fellowship’	85% of FCDO-funded ODI Fellows complete their Fellowship (21/25)	Achieved / During FY 24/25, 21 Fellows completed their Fellowships as planned. 4 Fellows ended their Fellowships prematurely. 38 Fellowships are ongoing.
Quarterly and annual reports accurately collect and collate data on reports and/or policy briefs co-devised and co-developed with local colleagues as well as the number of training sessions on the use of economic and statistical analysis in different thematic areas	Annual report with relevant, useful data on reports, policy briefs, and trainings	Achieved / ODI’s quarterly reports capture information on policy briefs co-devised and co-developed with local colleagues as well as training sessions. The reports also provide useful case studies providing examples of economic and statistical analysis in different thematical areas.
Number of Pacific Island countries and host institutions supported by the ODI Fellowship Scheme	Number of placements based on funding	Achieved / 5.5 FCDO Pacific Fellows were placed in the 2024-26 cohort (with one ODI Fellowship, in Fiji, co-funded with the Global Green Growth Institute)
Percentage of host institutions satisfied with the performance of FCDO-funded ODI Fellows	90% of Supervisors assess the placement of FCDO-funded ODI Fellows as very successful or successful	Achieved / 100% of Supervisors who responded (10 during the reporting period) expressed satisfaction and would like to continue hosting ODI Fellows

Briefly describe the output’s activities and provide supporting narrative for the score.

The previous FCDO programme ended with the 2019-21 cohort of 42 FCDO-funded Fellows in 17 countries. The COVID-19 pandemic caused considerable disruption to the Fellowship Scheme. Along with reductions in the ODA budget, this resulted in a hiatus in FCDO funding. No new FCDO-funded Fellows were posted between January 2020 and September 2022. However,13 Fellows funded by other agencies were posted.

In March 2022, FCDO approved funding of £4.5 million for two additional cohorts of about 20 and 10 Fellows in 2022 and 2023, respectively. This was subsequently supplemented by up to £1 million from the FCDO’s Southeast Asia & Pacific Directorate (SEAPD) for up to 6 additional Fellows to be posted to ministries in Pacific Island countries. In September 2024 this funding was again extended to £9.6m to incorporate the 24-26 Fellowship cohort.

As previously reported in annual reviews, the main objective of Output 1 was to re-establish the Fellowship Scheme following the nearly three-year hiatus. Since the start of the programme there have been 3 cohorts of Fellows, including placing Fellows in the Pacific islands. Indicators 1.2 and 1.4 help to determine the value of the programme in terms of impact that the Fellows provide to host institutions and whether they are happy with the performance of the Fellows. Thereby helping to ascertain the effectiveness of the Fellowship Scheme.

The current programme has had three cohorts: 25 FCDO-funded Fellows in FY22/23, 20 in FY23/24, and 27 in FY24/25.

The Outputs are on track across the 4 indicators. ODI have improved their quarterly reporting over the year to include more details and case studies of activities by Fellows.

Throughout 2024/25, ODI Fellows were deeply engaged in a wide range of activities that contributed to strengthening institutional capacity and supporting policy development across their host countries. Fellows led and facilitated formal training sessions, workshops, and mentoring programmes for local colleagues, covering topics such as economic modelling, statistical analysis, research methods, and the use of software tools like R and Excel. They played key roles in drafting and co-developing policy briefs, annual reports, and strategic plans, including multiannual financial frameworks, budget outlooks, and fiscal performance reviews in countries such as Somaliland, Ghana, and Malawi. In Zanzibar, a Fellow coordinated the development of the Africa Cup of Nations (AFCON) Strategic Plan and a new tourism sector strategy, while in Sierra Leone, Fellows contributed to the organisation of the National Health Summit and supported the integration of education into national climate strategies. In the Pacific, Fellows worked on fiscal policy papers, expenditure reviews, and trade policy reviews, supervised the production of flagship statistical reports such as the Food Price Index in Tonga, and provided technical support to ministries of finance and central banks. Across all placements, Fellows were instrumental in fostering knowledge transfer, building sustainable systems, and enhancing the analytical and operational capabilities of their host institutions.

Any changes to the output over the last year, progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

ODI should continue to improve and strengthen its reporting capacity to ensure accurate reports, financial forecasting and invoices are submitted on time. Quarterly reports and invoices should be submitted within 30 days of the end of the quarter.

Output Title	Postgraduate economists and statisticians gain and share practical experience through their Fellowship post
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR	n/a

Indicator(s)	Milestone(s) for this review	Progress

1. Percentage of FCDO-funded ODI Fellows satisfied with their Fellowship experience	Over 90% of FCDO-funded ODI Fellows assess the Fellowship as very successful or successful	Achieved / 92% (23 Fellows) completing their placements over the last year reported that their Fellowship was either ‘very successful’ or ‘successful’.
2. Percentage of FCDO-funded ODI Fellows who would recommend the ODI Fellowship Scheme to others and offer to stay engaged with the scheme (recruitment, alumni activities, etc.)	Over 80% of FCDO-funded ODI Fellows offer to stay engaged with the scheme after completing their Fellowships	Exceeding / 97.3% (36 of 37 respondents over the past 18 months) have said they would be happy to be contacted by new Fellows or otherwise remain engaged with the scheme.

Briefly describe the output’s activities and provide supporting narrative for the score.

The indicators for Output 2 capture Fellows’ assessment of their personal experience and of the benefits of the scheme for others. ODI monitors the Fellows’ experience and shares their feedback in their Quarterly Reports.

On indicator 2.1, the results show that ODI Fellows are satisfied with their Fellowship experience. This is also supported from FCDO staff visits to meet with 3 Fellows in Rwanda, who reported a high level of satisfaction. This was an extremely useful exercise and FCDO were able to hear first-hand the impact that this programme is having for both the Fellows and ministries.

On indicator 2.1 a number of Fellows have completed their Fellowship and have reported a high level of willingness to keep engaged with the Fellowship scheme. Having an active and engaged Alumni is a strength of the Fellowship scheme. Alumni actively contribute to briefing and mentoring new Fellows, participated in recruitment activities, and supported the identification of new host posts. This year the alumni network continued to grow, with over 500 members in the LinkedIn group and high engagement with the alumni newsletter. Alumni also provided valuable feedback on programme improvements and shared their experiences at events, helping to strengthen the scheme’s support system and institutional memory. Their ongoing involvement has been instrumental in sustaining the quality and reputation of the Fellowship Scheme.

Any changes to the output over the last year, progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

ODI should continue to encourage current ODI Fellows to engage with the Alumni community as this supports Fellows as they move onto the next part of their careers, while providing opportunities for ODI to further promote the programme.

Output Title	ODI manages the Fellowship Scheme efficiently and effectively, providing high quality duty of care and quickly addressing challenges, and offers good value for money
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
1. Percentage of FCDO-funded Fellows who feel they were well supported during their placements	85% of FCDO-funded ODI Fellows indicate they were well supported or very well supported	Achieved / 88.2% (30 Fellows) reported that they felt supported by ODI during their Fellowship.
2. Percentage of applicants and FCDO-funded ODI Fellows from under-represented groups	20% of FCDO-funded ODI Fellows from under-represented groups	Exceeded / Of the 46 FCDO-funded ODI Fellows in January 2025, 21 (46%) were female and 15 (33%) were from non-OECD countries.
3. Assessment of highest / lowest unit costs, i.e. full cost of FCDO-funded ODI Fellow per year	Assessment of highest/lowest unit costs, i.e. full cost of FCDO-funded ODI Fellow, per year	Achieved / Year 1 Vanuatu Ministry of Finance least expensive at £1,000 per month Ethiopia Ministry of Education most expensive at £3,467/month. Year 2 Rwanda Development Bank least expensive at £2,554/month Ethiopia Ministry of Finance most expensive at £3,467/month

Briefly describe the Output’s activities and provide supporting narrative for the score.

Indicator 3.1 is more representative of the quality of care received by the Fellows. Results indicate a high degree of satisfaction from the Fellows. ODI has been supporting them by ensuring care and safeguarding is provided including confidential counselling services for the Fellows. ODI provides the FCDO with weekly reports flagging any security, medical or safeguarding incidences that have occurred and detailing their response. The reports show that ODI are monitoring risk, responding fast and taking sensible precautions to guard the welfare of their Fellows. ODI staff have also been trained as mental health first aiders this year which will offer more support to Fellows in the future. Fellows also have been able to contact the Global Security Team in relation to any concerns that they have.

The 2021 Evaluation of the Fellowship Scheme recommended that ODI pay increased attention to the diversity of the scheme and start tracking and reporting against various dimensions of diversity. This is reflected in indicator 3.2. Results indicate that there has been an increase in the diversity of nationality of the ODI Fellows with increased participation of Fellows with non-UK/US/European citizenship. ODI are also looking to address limitations in their case management software to be able to capture more diversity data. Interviews for the scheme also take place online which allows greater flexibility for potential Fellows.

Analysis of the 2024/26 cohort reveals a tension between increased attention to diversity and the overall objectives of the Fellowship Scheme. As noted above, a primary objective is to bolster capacity in host governments. While opening the scheme to applicants from all over the world has made it much more diverse and increases the pool of talent the scheme can choose from, it also increases the risk that this is at the expense of government capacity in a Fellow’s home country. For instance, in 2024, a serving public servant from a Low-Income Country was deployed as an ODI Fellow in another country. Whilst there are benefits to providing opportunities for third country experience to candidates from low-income countries it does deplete the already fragile capacity in their home governments, therefore undermining the aims of the programme.

This raises difficult questions for the scheme. Can serving public servants be excluded? Should building government capacity trump diversity? While the answers are beyond the scope of this Review, possible changes to eligibility criteria to counter this unintended consequence of increased diversity should be investigated in any Business Case for further multi-year FCDO funding. In the meantime, this risk should be added to the ODI Fellowship Scheme risk register and monitored.

Indicator 3.3 is an assessment on costing and maintenance of each Fellow. While this would vary by the country of posting, outlining the highest and lowest cost will establish the variance in the cost per Fellow. The baseline of £43,689 was established based on the average cost of the Fellowship from 2019-20. The actual cost of the posting would vary based on factors such as location, housing, transport, and security costs.

Any changes to the output over the last year, progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

On Output 3.2 ODI capture diversity data during their application stage for those who have completed demographic data. However, they have identified some limitations in how they gather demographic information on candidates at each stage of the recruitment process. It is currently only possible to get demographic data at the application stage. ODI will explore this year how to get better data at each stage of the application process.

It is recommended that ODI tracks and reports instances of serving public servants in Low Income Countries being offered Fellowships through its risk register. ODI should consider whether a change to eligibility criteria, like the Chevening Scholar commitment, is required to address such unintended consequences in a future multi-year business case.

## D: VALUE FOR MONEY

Key cost drivers and performance

The 2021 Ecorys evaluation of the Fellowship Scheme estimated that the ‘average cost of the Fellowship per Fellow per year in 2019/20 was £43,689’ (Table 1). This ‘includes the full range of costs associated with each Fellowship (including advances and bonuses, travel, insurance, medical cover, security, language training, pre-departure briefing and selection), as well as a proportion of the overall management and administrative costs covering the entire scheme.’

Table 1: Average cost per Fellow per year, 2015–2020
	FY15/16	FY16/17	FY17/18	FY18/19	FY19/20
Average number of Fellows	87	88	87	78	78
Total expenditure	£3,515,638	£3,529,941	£3,395,042	£3,242,101	£3,407,706
Average cost per Fellow	£40,410	£40,113	£39,023	£41,565	£43,689

Source: Ecorys
Turning to the benefits of the scheme, three kinds of benefit can be identified:
Filling capacity gaps to help governments undertake core economic functions more effectively.
Building capacity to strengthen skills, economic management and policy.
Providing Fellows with work experience in low to middle income country governments, with subsequent benefits for development organisations employing them – and their development programmes.

While they cannot be quantified or given a cost value, the Ecorys evaluation provides strong evidence that all three types of benefit are real and significant. This baseline average cost per fellow will be reassessed for any new multi-year business case.

Assessment of whether the programme continues to represent value for money

The average cost per Fellow has slightly decreased from last year and is in line with the average cost over the last 5 years for Fellows. The Ecorys 2020 Evaluation of the Fellowship Scheme estimated the average cost per Fellow from 2015 – 2020 at £40,960 (Table 1). The average cost per Fellow from the last 5 years is £44,086 from 2020 – 2025 (Table 2). These estimates are calculated using a different methodology from the Ecorys evaluation so are not directly comparable. The figure (59) for 24/25 represents the total number of Fellows over the year and has been provided by ODI.

Table 2: Average cost per Fellow per year, 2020-2024

	FY 20/21	FY 21/22	FY 22/23	FY 23/24	FY24/25
Number of Fellows	49	27	24	35	59
Total expenditure	£2,326,994	£1,049,251	£997,555	£1,697,590	£2,596,839
Average cost per Fellow	£47,490	£38,861	£41,565	£48,502	£ 45,163

Source: ODI

Some factors influencing higher costs relate the increase in inflation rates, which raised costs for flights, hotels, insurance and rent. There was a £2000/per annum pay rise for Fellows. ODI have also invested in systems and expertise to better manage the ODI Fellowship Scheme, including investments in recruitment systems. A detailed spending profile breaks down as
- Direct spending on Fellows (62%)
- Management of Fellows (18%)
- NPAC (20%)

A contributor to the cost of the programme over the year has been an increase in the non-programme associated costs (NPAC). These costs cover a proportion of the running costs of ODI including office rent, staff salaries and administration. The NPAC were examined in the 2025 FCDO Due Diligence Assessment of ODI and will be considered in any future multiyear funding agreement.

In summary, the cost per Fellow has reduced compared to the last financial year, The costs are deemed reasonable, and the Fellowship Scheme continues to represent good value for money.

E: RISK

Overview of risk management

Overall, the risks to the programme remain similar to the previous annual review (table below). The rating for the programme during this reporting period is moderate with all residual risks falling within FCDO’s risk appetite. The table below highlights some of the relevant risks from the overall risk register that have been updated to reflect the findings of this review.

Risk Description	Risk Category	Likelihood	Impact	Gross Risk	Mitigation Strategy
ODI is unable to attract diverse candidates	Policy & Programme Delivery	Possible	Minor	Minor	In all recruitment materials, ODI includes a statement that it welcomes applicants from all backgrounds and continues to look to make the application form more accessible.
The Fellowship risks depleting home country capacity by redeploying Fellows from LIC governments to third countries	Policy & Programme Delivery	Possible	Moderate	Moderate	ODI will track where candidates were working previously and include this in reporting. ODI can consider introducing a post service commitment
A Fellow is not well utilised during their Fellowship so that they fail to deliver the expected impact.	Reputational	Likely	Minor	Minor	ODI reviews roles suggested by host governments to ensure they are a fit for the Fellowship Scheme. The scheme ensures that governments are provided with the best possible candidates of their choice for each post. Employers are asked to sign an MOU which outlines obligations of the employers and that of ODI, ensuring both sides are aware of their responsibilities towards Fellows.
Funding is not available for Fellows to complete their two-year Fellowships.	Public Service Delivery and Operations	Likely	Moderate	Moderate	FCDO will provide funding by cohort, and, if relevant, a no cost extension to ensure Fellows complete the full duration of their Fellowships.
Fellows are involved in Sexual Exploitation Abuse and Harassment.	Safeguarding	Unlikely	Major	Moderate	Pre-Fellowship training briefing, clear reporting lines, standards being clearly stated in MoUs, with hosts and ongoing monitoring by ODI who will immediately report concerns to FCDO. Fellows agree to ODI safeguarding policies.

Risks are regularly reviewed at the quarterly meeting and documented in the quarterly reports. The major in-country risk pertains to security of Fellows arising from health issues, political instability, theft, and weather-related events. ODI does weekly check-ins with the Fellows and escalates risks to the FCDO if there are any concerns. ODI have actively managed emergencies experienced by Fellows, providing immediate assistance and in some incidence's evacuation. This has helped to mitigate risks and challenges faced by Fellows. ODI staff have also recently undertaken Mental Health First Aid Training.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Financial Management

The review covers the period August 2024 to July 2025. Programme expenditure for FY25 totalled £2,596,839, versus the forecast of £2,642,631 with an underspend of £45,793. The placement of Fellows occurs with a time lag which affects the actual spend especially for salary payments to the Fellows. There is a higher spend in Q4 as this is when the majority of Fellows travel to host countries and start their placements. ODI have improved their financial reporting to explain any variances in forecast vs spend across budget lines for both the core and Pacific Fellows. As highlighted in the value for money section of this annual review there is a concern over the increasing NPAC, which for a programme of this size represents a substantial cost.

Quarterly Expenditure for the Review Period

All quarterly and annual reporting from ODI has been submitted, with updated forecasts submitted when requested. However, the reports have been late and included some inaccuracies. This was reported last year, and although reporting has improved over the course of the year, again a recommendation of this review is for ODI to strengthen its reporting capacity to ensure accurate reports and invoices are submitted on time.

The table below provides quarterly details for FY25:

ODI Spend	Q1	Q2	Q3	Q4	Total
Actuals	£505,174	£590,812	£687,239	£813,613	£2,596,838

Date of last narrative financial report	June 2025 – Quarterly report	Date of last audited annual statement	March 2023/24