## Annual Review

Title: African Humanitarian Response Fund II (AHRF II)
Programme Life Cycle: £83.33 million (£78m programmed, £5.33m remains in the Internal Risk Facility (IRF))		Review date: / June 2025
Programme Code: 301381	AMP start date: 10/08/2023	AMP end date: 30/06/2027

Summary of Programme Performance
Year	2023	2024
Overall Output Score	A	A
Risk Rating	Severe	Severe

DevTracker Link to Business Case:	D0003594.odt (live.com)
DevTracker Link to results framework:	D0005378.xlsx (live.com)

A. SUMMARY AND OVERVIEW

Description of programme
The African Humanitarian Response Fund II (AHRF II) delivers quality humanitarian assistance in countries where the FCDO has no in-country humanitarian expertise or where a regional response is more suitable. It addresses severe humanitarian needs in areas where the UK has comparative advantages, prioritising life-saving assistance to vulnerable populations in protracted crises in Cameroon, the Central African Republic (CAR), Eritrea, and Madagascar, and enables responses to sudden onset or emerging crises. AHRF II also provides technical assistance, operational support, and preparedness, drawing on UK expertise and scientific evidence.

This annual review covers initial implementation activities post-mobilisation from late 2023 until the end of the financial year, March 2024. There is one exception, a project that only mobilised in January 2024 and therefore reporting includes activities until the end of June 2024. The period covered for each project is set out within their output. Projects covered under this review include support the International Committee of the Red Cross (ICRC) in Cameroon with multi-sector humanitarian assistance for conflict-affected populations. In CAR, funding went to the CAR Humanitarian Fund (CHF) managed by the Office for the Coordination of Humanitarian Affairs (OCHA), an NGO Consortium led by the MENTOR Initiative for health and nutrition, and the World Food Programme (WFP) for food and cash-based assistance. Funding was also provided for Accountability to Affected Populations (AAP) programming in CAR through the United Nations Children’s Fund (UNICEF). The project uses beneficiary and community feedback to inform humanitarian response planning and implementation. In Eritrea, FCDO support improved the delivery of integrated health, nutrition and sanitation services to children and women.

Support to Madagascar began after a scoping visit during the review period, with a project now mobilised, this will be reviewed in the next Annual Review. The first response through the sudden onset or emerging crises, addressing cholera outbreaks in southern Africa, also started at the end of this period and will be reviewed in the next Annual Review.

Summary supporting narrative for the overall score in this review
Overall AHRF II has met expectations across all outputs and therefore overall scored an ‘A’.

	Output	Assessment	Score	Weighting
1	Responses improved by support to enabling actions and system reform	Output Met expectations – technical assistance requests were followed up promptly with relevant requests supported and the early stages of this phase of support to the Accountability to Affected Populations project in CAR has demonstrated good progress.	A	20%
2	Multisector humanitarian assistance provided to the populations affected by the conflict in Cameroon	Output Met expectations – support provided met or exceeded in all areas targeted except for cash support.	A	20%
3	Multisector humanitarian assistance provided to the populations affected by the conflict in the Central African Republic	Output Met expectations – there were mixed achievements across the indicators but overall the projects demonstrated delivery across multiple sectors.	A	40%
4	Improving the delivery of integrated nutrition and sanitation services to children and women in Eritrea	Output Met expectations – the project effectively addressed needs through nutrition and sanitation programming in Eritrea with all targets met.	A	20%

Major lessons and recommendations for the year ahead

Recommendation 1: Adhere to newly introduced ICF guidance adopted by FCDO, which recognises humanitarian programmes working in countries that fall into the bottom 10% in terms of recognised climate vulnerability rankings contribute to ICF results. Review activities and the AHRF II logframe to identify which results can be reported as ICF. This is especially important for Madagascar, where climate hazards drive humanitarian needs.
[note] International Climate Finance
[note] ND-GAIN Country Index rankings | ND-GAIN Index

There is demand for technical assistance across the UN system, and as identified in the last annual review. Recommendation 2: When the programme team are fully staffed they should explore additional opportunities to expand technical assistance, such as supporting the rollout of the Livingstone Principles curriculum.

The programme team have conducted or planned monitoring visits to all supported contexts. These visits are vital for risk management, ensuring activity relevance and quality, and assessing impact on vulnerable populations. In a reduced ODA environment, these visits will also be used to carefully consider prioritisation and timing of interventions and assess the robustness of in-country humanitarian operations. Recommendation 3: The FCDO team should continue annual monitoring visits to each context, supplemented with regular remote engagement, and use third-party monitoring where appropriate and feasible are unable to gain access to a context or if we do not have the capacity.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

AHRF II’s impact and outcome indicators remain unchanged.

In this period the FCDO adopted ICF guidance, which recognises that humanitarian programmes working in countries that fall into the bottom 10% in terms of recognised climate vulnerability rankings contribute to ICF results, some parts of the AHRF II programme may now contribute to ICF, especially Madagascar which was being mobilised at the end of this review period.
[note] ND-GAIN Country Index rankings | ND-GAIN Index

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

At this early stage, the Theory of Change remains appropriate, and the programme is on track. However, FCDO support alone is insufficient to significantly reduce suffering across Sub-Saharan Africa. Funding reductions among donors means that many humanitarian needs will remain unmet, making prioritisation by FCDO and the wider humanitarian system essential in the coming years.

It is not yet appropriate to assess the programmes impact: Reduced suffering of vulnerable and crisis-affected populations across Sub-Saharan Africa. [% of people in need in SSA reached by humanitarian assistance (not FCDO attributable)]. A milestone of 43% has been agreed for 2025 onwards. This is based on the 2024 result of 43% of people in need in SSA receiving humanitarian assistance. With growing needs across the and declining funding from many donors it is likely that the % of people in need who are reached will reduce. The indicator has therefore also been adapted to include % of people targeted reached. In 2024 this was 72% and this has been included as the milestone from 2025. This should enable to programme to consider the prioritisation of the response.

Outcome 1
Timely, proportional, and accountable response to affected populations. (this outcome relates to direct delivery attributable to the FCDO)
Outcome Indicator(s)		Milestone(s) for this review	Progress	Commentary
1.1	Number of people targeted by humanitarian emergency appeals reached by the programme	491,062	550,037	The target has been moderately exceeded overall but, there has been some variance across partners, detailed under each output. / Moderately exceeded expectations

Outcome 2
Humanitarian actors deliver a more effective, principled, and inclusive humanitarian response. (this outcome relates to the wider humanitarian system e.g. AAP)
Outcome Indicator(s)		Milestone(s) for this review	Progress	Commentary
2.1	Evidence of FCDO funded TA support leading to improvements in humanitarian response	Contribution of FCDO funded TA leads to improvements in response. / Assessed through consideration of timeliness, relevance and effectiveness	Two deployments completed during this period: / 1.Met expectations in all areas / 2.Met expectations for relevance but, moderately not met for timeliness and effectiveness.	This review only covers the first six months of the programme, during which time only two technical standby partnership deployments have fully completed. There is therefore limited information available to assess an improvement of humanitarian responses to draw from. / Moderately not met expectations

Summary of deployment scoring
Technical Assistance (TA) deployed to bolster response structures in coastal West Africa at risk of escalating needs from Sahel, assessed as timely, relevant and effective in delivery of TORs.

TA deployed to support West Africa monsoon flood mapping however has only made a limited contribution to improving preparedness and response activity, Expectations of timeliness (late deployment in relation to the monsoon season) and effectiveness (TORs only partially delivered within the deployment period) were not met.

Previous Annual Review Recommendations

Recommendation	Progress
The FCDO programme team should review the % of people in need reached during 2024 when the results are published in the Global Humanitarian Overview in December 2024 to recommend impact milestones from 2025.	The logframe has been updated to include impact milestones as detailed above. / Complete

Recommendations
In order to adhere to newly introduced ICF guidance adopted by FCDO, which recognises humanitarian programmes working in countries that fall into the bottom 10% in terms of recognised climate vulnerability rankings contribute to ICF results, a review of activities and the AHRF II logframe to identify which results can be reported as ICF. This is especially important for Madagascar, where climate hazards drive humanitarian needs.
[note] ND-GAIN Country Index rankings | ND-GAIN Index

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
AHRF II should continue. It has met expectations across its outputs which continue to be relevant to FCDO priorities. During the course of completing this review the UK Prime Minister took the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. However, the UK remains fully committed to playing a globally significant role in humanitarian aid and development. The programme team will need to assess how this specific programme will be impacted.

C. DETAILED OUTPUT SCORING

Output Title	Responses improved by support to enabling actions and system reform
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 FCDO funded TA support provided in a timely and responsive way.	- Stand By Partnership requests responded to within 5 working days / - Engagement with Posts to identify strategic gaps the programme could support maintained	-11/12 Stand By Partnership requests were responded to within 5 working days. 8 within one day, 2 within two days, 1 in four days and 1 took 13 days due to break in the line of communication (request not shared with the full team). / -Engagement with Post limited due to capacity constraints (vacant humanitarian adviser positions) however this scaled up following recruitment of a Southern Africa Humanitarian Adviser, including a visit to Madagascar. For responses to epidemics, appropriate referrals made for post to the relevant FCDO health teams for support. / Met expectations
1.2 Supported response in CAR implements AAP programmes and makes use of feedback to inform planning and implementation.	Scoring methodology: / 1=No AAP system in place / 2=AAP system in place but not used to inform planning or implementation / 3=AAP system used to inform planning and implementation of response / 4= AAP system used to inform planning and implementation of response and AAP system regularly reviewed and updated. / (Weighted score across responses receiving AAP.) / A target from the scoring was not included in the logframe for this period, the assessment of performance reflects where the project can be expected to deliver in this period.	2 – Due to timing of agreement signing with UNICEF and the time needed for finalisation of agreements with local partners, the period under review is the initial six months of calendar year 2024. Supporting UN-wide planning as per the humanitarian programme cycle and Humanitarian Response Plan (HRP) will only be evident later in the year and covered through the next AR. The score of ‘2’ has been applied because only the beginning of informed planning and implementation was accomplished – while the work done was satisfactory there is more still to be done. / Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 has two main components. The first is technical assistance to humanitarian organisations to build or strengthen their strategic and/or operational capacity, tailored to context and humanitarian architecture. The second is partner support to improve affected population engagement, feedback, and humanitarian planning to enhance the in-country response.

The technical assistance provided by the FCDO was relevant for preparedness and support, demonstrating UK commitment to strengthening humanitarian systems. For this review period (1 December 2023 to 31 March 2024), a relatively short period after the initial mobilisation stage which had involved intensive engagement with Posts. Two out of 12 technical assistance requests were approved; others were redirected or declined due to limited strategic impact for humanitarian response and populations at risk. Limited advisory and programme management capacity restricted proactive engagement with posts and UN agencies to identify opportunities for technical assistance. Though this followed intensive engagement over the mobilisation period. A visit to Madagascar to understand humanitarian response structures took place in March 2024, with the new Southern Africa Humanitarian Adviser, which allowed for identification of appropriate support (to be captured in next AR period).

The second component, delivered by UNICEF, implements an Accountability to Affected Populations (AAP) project across CAR. Mobilised at the end of January 2024, the review covers the first five months to June 2024. Initial stages focused on finalising agreements with local NGOs helping to implement AAP. Completing all the due diligence requirements took some time and meant the community-led mechanisms were only established from, mid-April 2024. This is pivotal for localisation of AAP programming. UNICEF’s and UN-wide planning will occur after this reporting period, with results to be covered in the next Annual Review.

UNICEF and a local partner improved mobile feedback and complaints collection, expanding AAP mechanisms to 16 localities, including hard-to-reach areas. They conducted 240 home visits and 60 community meetings, reaching at least 9,936 people with information on accessing humanitarian aid such as cash distributions and guiding people on how to use feedback and complaint mechanisms

	Women	Men	Girls	Boys	Total
People reached	4,105 (42 %)	3,500 (35 %)	1,089 (11 %)	1,242 (12 %)	9,936

The home visits and community meetings provided valuable opportunities to gather feedback and complaints about humanitarian aid:

	Women	Men	Girls	Boys	Total
Feedback collected	1,359 (42 %)	1,626 (50 %)	113 (4 %)	113 (4 %)	3,211

2,210 (68.5%) were referred to relevant organisations for action. The referral process was initially slow due to manual handling but improved after IT staff trained 40 focal points and community agents to use a community digital platform.

The project also collaborated with Clusters and the Inter-Cluster Coordination Group to develop an AAP minimum standard for listening and responding to community concerns. A mapping exercise involving 116 humanitarian organisations identified existing community engagement practices. Three technical groups were formed to help draft the minimum standard and an action plan to ensure partners adhere to the standards and improve responsiveness.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to the output. A target should be set for the AAP project using the scoring methodology for future years.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation	Progress
There is demand for technical assistance across the UN System but this pillar has scope to deliver much more across Africa. The FCDO programme team should consider what other opportunities there are to expand support under this pillar, for example supporting the delivery of the roll out of the Livingstone Principles curriculum.	Technical assistance requests continue to be received and promptly handled although in early 2024 there were FCDO staffing gaps that meant a decision was taken to raise the threshold for agreeing new deployments. / The Livingstone Syllabus as part of the African Union (AU) Law and Policy Training Programme is a promising initiative for policy makers, civil servants and emergency personnel to deepen understandings of humanitarian architecture including institutions, legal and policy frameworks and instruments but capacity constraints within the FCDO limited the ability pursue engagement or support. / Ongoing

Recommendations: the recommendation from the last annual review remains relevant and should be a priority to identify opportunities to expand support under this pillar beyond technical assistance and one system wide AAP approach when the programme team has both advisory and programme capacity in place. The Livingstone Syllabus remains a potential area of support.

Output Title	Multisector humanitarian assistance provided to the populations affected by the conflict in the Cameroon
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of people receiving humanitarian assistance (all sectors included).	50,716	Total 60,082 / Female 13,992 / Male 12,669 / Children 33,422 / Moderately exceeded expectations
2.2 Number of people assisted by FCDO through cash, voucher and food.	Total 6,673 / Food 4,861 / Cash for work 1,812	Total 6.325 / Food 5,155 / Female 1,496 / Male 1,243 / Children 2,416 / Cash for work 1,170 / Female 353 / Male 344 / Children 473 / Met expectations
2.3 Number of people receiving food production assistance.	44,043	Total 53,753 / Female 12,142 / Male 11,083 / Children 30,532 / Moderately exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
The crisis in North-West and South-West Cameroon has resulted in at least 6,000 civilian deaths. Approximately, 573,000 people are displaced as a result of the concurrent crisis in the far north of Cameroon related to Boko Haram and other extremist groups in the Sahel Region. From October to December 2023, over 2.9 million people in Cameroon faced crisis or higher levels of food insecurity, including many internally displaced people (IDPs) in the North-West and South-West regions. In 2024, 2.5 million people were identified as needing food assistance in the HRP, but only 1 million were targeted. FCDO support through the ICRC 2023 calendar year appeal, met or exceeded most targets, except for a shortfall in cash-for-work beneficiaries. Cash is a priority area for the UK so overall the output met expectations. FCDO results are based on the amount of funding the FCDO has contributed towards the total appeal.

While indicators focus on cash and food assistance, the ICRC also undertakes a wide range of humanitarian activities, including monitoring the humanitarian situation, promoting compliance with International Humanitarian Law (IHL), and advocated for civilian protection and access to essential services. The ICRC worked with authorities and weapon bearers to uphold humanitarian principles and integrate IHL into military and security operations.

With the Cameroon Red Cross Society, the ICRC assisted people affected by conflict, especially in the Far North, North-West, and South-West. Regular engagement with key actors enabled the ICRC in some cases, to reach more people than planned. IDPs, refugees, and host communities received food aid, hygiene items, and other essentials. People produced more food thanks to animal vaccination, as well as seeds and tools for farmers. In addition, cash grants and training helped improve livelihoods. The ICRC also improved access to clean water by renovating and building water systems and training local technicians. Emergency activities provided immediate assistance after armed clashes, and ICRC-supported health centres offered care, including psychosocial support for victims of violence. The ICRC continued to strengthen the Cameroon Red Cross’s operational and administrative capacity, and Red Cross Movement members coordinated activities, especially in the Lake Chad region.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following publication of the 2025 appeal targets were added to the logframe for milestone 4.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first annual review for this output so there are no previous recommendations.

Output Title	Multisector humanitarian assistance provided to the populations affected by the conflict in the Central African Republic
Output number:		3	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of people receiving humanitarian assistance (all sectors included)	130,346	Total 171,558 / Female 94,345 / Male 77,213 / Met expectations
3.2 Number of people assisted by FCDO through cash, voucher and food	Cash or Voucher Total: 28,613 / Female 15,108 / Male 13,505 / 0-23 months 2,032 / 24-59 months 2,718 / 5-17 years 7,811 / 18-59 years 14,307 / 60+ years 1,745 / Disabled 2,240	Cash or Voucher Total: 64,037 / Female 33,747 / Male 30,290 / 0-23 months 4,547 / 24-59 months 6,083 / 5-17 years 17,482 / 18-59 years 33,235 / 60+ years 2,690 / Disabled 4,482 / Met expectations
3.3 Number of Healthcare Consultations Provided	Total 29,977 / Female over 5 7,389 / Male over 5 3,670 / Female under 5 9,248 / Male under 5 9,670	Total 19,282 / Female over 5 4,554 / Male over 5 2,815 / Female under 5 5,924 / Male under 5 5,989 / Substantially did not meet expectations
3.4 Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions.	1,278	1,885 / Substantially exceeded expectations
3.5 Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions.	334	140 / Substantially did not meet expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
The humanitarian crisis in CAR began in 2012 and is prolonged, complex emergency driven by ongoing armed conflict and insecurity. Rising prices of basic goods have worsened food insecurity. Despite these challenges, the humanitarian system in CAR is effective, with recent HRPs based on strong assessments, realistic targeting, and good donor support. This output has met expectations.

Indicator 3.1: The CAR Humanitarian Fund (CHF) has performed well, efficiently managing grants, vetting partners, and increasing funding to local NGOs—from 7% in 2022 to 20% in 2023. While indicator 3.1 has substantially exceeded the original target, the number of individuals reached through healthcare interventions totalled 792,500 which included health referrals and consultations that are valuable services but do not necessarily result in a particular or ongoing treatment. As a result, the output has been assessed as having met, but not exceeded, expectations.

Indicator 3.2: WFP received support for the first time due to high food insecurity. While their results, show they reached 124% of beneficiaries targeted this was achieved because the planning figures are based on an average distribution of $13.29 per person per month. However, the actual ration distributed is based on the size of the household with larger households (over 7 people) receiving $59.50 ($8.50 each). With large households more present than anticipated, WFP exceeded its target but, is considered to have met expectations overall.

Indicators 3.3; 3.4 and 3.5: The MENTOR Consortium’s health and nutrition response in two areas of CAR exceeded one milestone but missed two others. This was mainly due to a short implementation period (2 months); local labour laws that meant some local staff had to have a one-month break before they could be re-recruited for the new phase of support; and some challenges in communication within the consortium between HQs and the country office teams on signing of the agreement at the start of this phase of support slowed support in the hospital in Alindao.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes were made to the output during the year and no changes are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first annual review for this output so there are no previous recommendations.

Output Title	Improving the delivery of integrated nutrition and sanitation services to children, and women in Eritrea
Output number:		4	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of people receiving humanitarian assistance.	310,000	318,397 / Met expectations
4.2 Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions.	GAM 7,490 / SAM 3,400 / MAM 4,090 / Female 3,670 / Male 3,820	GAM 7,690 / SAM 3,500 / MAM 4,190 / Gender breakdown not available / Met expectations
4.3 Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions.	Pregnant & lactating women receiving iron folic acid supplements: 50,000 / Children receiving Vit A: 334,620 / Number of primary caregivers counselled for MIYCF: 80,000	54,819 pregnant & lactating women received iron & folic acid tablets to prevent anaemia & low birth weight / 343,200 children aged 6 to 59 months received vitamin A supplementation. / 81,234 primary caregivers & mothers were counselled for maternal infant & young child feeding (MIYCF). / Met expectations
4.4 Number of individuals reached with sanitation activities.	Total 30,000 / Female 15,300 / Male 14,700	Total 32,268 / Gender breakdown not available / Met expectations
[note] Author note: GAM = Global Acute Malnutrition, SAM = Severe Acute Malnutrition and MAM = Moderate Acute Malnutrition
[note] Author note: MIYCF = Maternal, Infant and Young Child Feeding campaign

Briefly describe the output’s activities and provide supporting narrative for the score.
Malnutrition in Eritrea, has been a major concern since the country’s independence. While reliable official information is limited, we know from humanitarian partners that malnutrition continues to be a significant public health issue. Under Output 4, UNICEF, in collaboration with government line ministry partners, supports a range of life-saving nutrition interventions, with an emphasis on children and women in rural or remote and hard-to-reach communities (characterised by high household and community vulnerability). The programme encompasses curative, rehabilitative, preventive and promotive nutrition activities, hygiene promotion, sanitation support, and health worker capacity building, operating across all zobas (regions) of Eritrea.
[note] The last Eritrea Public Health Survey was conducted in 2010 (EPHS 2010)

Between October 2023 and March 2024, all targets were met or slightly exceeded. Acute malnutrition rate, determined through proxy mid-upper arm circumference (MUAC) data, indicates 11% of children in the target population are malnourished, slightly below the 11.3% target demonstrating programme effectiveness in mitigating malnutrition.

UNICEF originally proposed gender-disaggregated targets, however this breakdown is not available via published national level reporting. Disaggregated sub-zoba level data from District Health Information Systems (DHIS) however is still used to inform programme decisions and improve targeting. FCDO and UNICEF will continue to advocate for national-level disaggregated data.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes to the output were made during the year. Following updated information from UNICEF that, for reasons beyond their control, they will not be able to provide gender disaggregation for indicators 4.2 and 4.4 the gender targets should be removed from future milestones.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is the first annual review on this output, so there are no recommendations from the previous annual review.

Challenges and lessons learned:
- Regular access for monitoring and supportive supervision remains challenging; an FCDO visit planned for April 2024 was postponed to December 2024. However, UNICEF have documented regular monitoring visit access.
- The project has adapted protocols and in response to technical feedback has shifted approaches towards more prevention activities.
- Last-mile delivery remains a challenge, especially in remote communities. Efforts are increasing to build the capacity of “barefoot doctors” and other community health workers to administer essential nutrition interventions.
Recommendations
Supportive supervision visits by Ministry of Health - accompanied by UNICEF - should continue as much as possible, and be documented as part of regular reporting to FCDO.
## D: VALUE FOR MONEY

Key cost drivers and performance
Key cost drivers for AHRF II include partner staffing, training, procurement, global transport, and shipping, with security costs notable in Cameroon and CAR. For UNICEF’s AAP efforts in CAR, managing nearly 1,000 feedback stations (mailboxes, committees and surveys) and coordinating NGOs are significant costs.

Each technical assistance proposal has been reviewed to ensure it would enhance the overall humanitarian response. Costs range from £70,000 to £90,000 for a six-month deployment.

VfM performance compared to the original VfM proposition in the business case
VfM metrics have been agreed for the programme and are detailed in annex 1.

Economy metrics, such as cost per beneficiary, show mixed results, from £3.14 in Eritrea to £36.86 in Cameroon. Different activities and environments influence the costs. Despite high delivery costs in CAR due to isolation and transport challenges, beneficiary costs have decreased through the CHF. Costs have remained stable in Eritrea and increased in Cameroon, where the ICRC operates in remote or hard-to-access areas due to insecurity and adverse weather conditions, which destroyed many roads in remote and hard-to-reach areas. However, a mapping of these areas has been completed and alternative modalities will be used where possible. Other metrics, like cost per health consultation or cash transfer, are new and will be assessed in future reviews.

Efficiency is supported by rapid personnel deployment through Standby Partnerships and consultants to strengthen UN and FCDO capacity. Multi-year planning improves supply chain management. Stockouts, monitored by the MENTOR Initiative for six essential medicines, showed only one paracetamol stockout for two months in one of three supported areas during the initial reporting period. Locally managed responses can improve efficiency, and the CHF increased delivery through local organisations from 7% to 20% in this period. Operating costs rose slightly but remained below the 10% target, with the increase expected due to the focus on localisation and the additional controls implemented to manage the risks.

Effectiveness at this early programme stage is strong, with continued support to previous projects demonstrating quality and meeting expectations as set out in the output sections. One example is the OCHA assessment of all Humanitarian Funds through the Common Performance Framework (CPF). The CHF scored 100% in 14 of 20 categories. On a scale of 5, the indicators averaged a mark of 4.25 so above the target of 4, demonstrating effective management of projects in CAR.

On equity, access has been prioritised across the responses with the project in Eritrea active across all zobas, ensuring all ethnic groups maintain access to support. In Cameroon, the ICRC have bases in both the Far North and North-west, South-west Regions, ensuring vulnerable people in both regions maintain access to humanitarian support. In CAR, the AAP project has improved access for women, girls, and disabled people to provide feedback by diversifying mechanisms, including mobile collective feedback and complaints systems.

Assessment of whether the programme continues to represent value for money
Overall, the programme has shown adequate results in its initial stages and should continue, a fuller assessment of value for money will be possible in future reviews.

E: RISK

Overview of risk management
The programme’s risk level remains severe due to the high residual risks associated with its activities, but within business case appetite. The programme continues to have an eager appetite to policy and programme delivery, strategy, and external context risks that are also significant because of the fragile security situation in some of the countries supported by the programme. Partners lead on managing some risk including assistance delivery risks and the physical safety of their staff.

The programme has maintained a receptive appetite for safeguarding risks, but the programme enforces zero tolerance for inaction or mishandling of incidents, requiring partners to monitor, report, mitigate and respond robustly. Accountability to Affected Populations (AAP) mechanisms are integrated to ensure beneficiaries can report concerns through multiple channels.

A receptive appetite is also in place for fiduciary risks recognising the potential for small-scale aid diversion or loss. Partners are required to report and address any incidents of fraud, diversion, or corruption immediately. and, if present, pursue recovery.

There is also a receptive appetite for reputational risks since it is most likely that fiduciary and safeguarding issues, and risks have potential for reputational damage to the FCDO. Risks are mitigated through counter-fraud and safeguarding procedures. There is also reputational risk if FCDO fails to respond to emerging crises. The programme has been mobilised to respond to the onset of cholera in southern Africa, at the end of the period covered by this annual review, although this response was slightly late.

The programme has a receptive appetite for operational risks, given the difficulty of field monitoring in some areas. This is mitigated by regular remote engagement with partners. An initial visit to Eritrea had to be postponed to ensure access to the field to monitor delivery could take place and was completed in late 2024. FCDO staff safety is prioritised, with security advice and missions supporting risk assessments before visits where needed.

All severe or above-appetite risks have been escalated to senior leadership in the Africa Programmes and Expertise Department (APEX). One increased risk, escalated in this period was FCDO’s internal capacity, with ongoing staffing challenges, though some improvements have been made but, only with temporary support so far on the advisory side and some continued challenges on the programme management side.

The Programme Team maintains a detailed, regularly updated risk register, and partner risk management is monitored through Due Diligence Assessments (DDAs) and recommendations have been followed up through regular partner engagement. Partners must also provide delivery chain information to support risk mapping.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

By 31 March 2024, AHRF II had disbursed £13.6 million across four contexts—CAR, Cameroon, Eritrea, support technical assistance and operations support in Africa and the cholera response in Southern Africa (assessed in the next annual review).

Operational Support, Technical Assistance and Preparedness
UNICEF in CAR was mobilised in January 2024, through a Contribution Agreement, to continue the system-wide Accountability to Affected Populations (AAP) project. As of July 2024, the UNICEF CAR Country Office achieved a 100% completion rate for mandatory Prevention of Sexual Exploitation and Abuse (PSEA) training among staff, consultants, and volunteers. Additionally, 708 staff from UN agencies, MINUSCA, international and national NGOs and the CAR Government were trained on PSEA basics and reporting mechanisms. Two partners were selected to deliver the AAP project in 2024, with no assets procured. Partners were assessed for PSEA capability and ensuring all due diligence requirements were met which delayed mobilisation but was essential for risk management. Partner engagement has been strong with timely reporting on progress, risk, value for money, and demonstrating the utilisation of funds.

Technical Assistance for FCDO or UN partners through the HEROS contract and for the Standby Partnership positions through Accountable Grant agreements with four NGOs are managed through central agreements with the FCDO Humanitarian Department.
[note] DevTracker Programme GB-1-205176

Central African Republic (CAR)
The CAR Humanitarian Fund (CHF) remains a high-performing fund, with FCDO’s contribution managed through a Memorandum of Understanding (MoU) to contribute to their pooled funds for allocations. In 2023, CHF allocated 27% of its budget ($4.2m) to protection activities, a 10% increase from the previous year. Protection guidelines were integrated throughout the humanitarian response, with all project proposals evaluated for their alignment with protection activities. Two training sessions were held for 35 staff from 34 partner organisations on combating sexual exploitation and abuse, reinforcing obligations under the Code of Conduct and PSEA guidelines. CHF maintained a strong focus on risk management, conducting all required monitoring visits and 20% of non-required visits, as well as 97% of required financial spot checks and 8% of non-required spot checks. While experienced partners reported on time, new partners caused delays, resulting in 79% of required reports being submitted. All 44 audits initiated in late 2023 were ongoing as of the reporting period. CHF plans to strengthen the financial reporting and risk management capacity of new and national actors, supported by a dedicated compliance and risk management officer recruited in 2023. CHF own reporting to donors was delivered on time and demonstrated utilisation of funds. All assets are managed and disposed of according to UN rules and regulations.

The health consortium, led by the MENTOR Initiative is funded through an Accountable Grant with funding provided in advance for MENTOR and in arrears for their consortium partner. Safeguarding training in CAR achieved 100% completion, with base focal points delivering in-person Code of Conduct training. MENTOR’s due diligence confirmed ACF’s safeguarding training and they have been monitoring completion rates. Consortium assets are recorded in a register shared with FCDO, detailing asset number, description, location, responsible person, value, purchase date, expected lifespan, and condition. A remote asset spot-check using date-stamped photos was conducted in early 2024. Regular reporting has been maintained. Although there were initial delays in mobilisation, leading to reduced reach and underspend in the first two months, close engagement with the partner has improved delivery and increased both service reach and expenditure.

The World Food Programme (WFP) were supported for the first six months of the programme, through a Contribution Agreement to deliver cash transfers, working with EcoBank as the Financial Services Provider and funding two NGOs for project monitoring. WFP requires all staff to complete a mandatory Sexual Exploitation and Abuse (SEA) training module, with 100% compliance on the original course. However, compliance for a new course introduced in mid-2023 was initially 63%, with management taking steps to improve this rate. Additionally, 150 frontline staff from WFP, service providers, and partners received training, with more sessions planned. WFP is not expected to purchase significant assets for this short project, but any assets will be managed according to WFP regulations. Reporting was timely and showed full utilisation of funds.

Cameroon
Support in Cameroon is provided in the Far North and North-West/South-West regions through an MoU with the International Committee of the Red Cross (ICRC), with FCDO funding contributing to ICRC’s Yaoundé Regional Appeal. ICRC delivers most assistance directly, with less than 5% managed by the National Society or other partners. Safeguarding is addressed through Integrity training (99% completion) and Code of Conduct training (100%). FCDO’s due diligence recommendations are regularly followed up with ICRC in Yaoundé and Geneva, and an FCDO monitoring visit took place in March 2025. ICRC provides timely mid-year and annual reports for all donors, shared via the donor portal, along with regular updates on funding utilisation. All assets are owned by ICRC, procured through their Geneva headquarters, and managed according to ICRC policies and procedures.

Eritrea
UNICEF in Eritrea continued delivering humanitarian assistance through a Contribution Agreement, maintaining regular engagement with FCDO and addressing due diligence recommendations. Staff safeguarding training completion increased to 100% from 94% at agreement. UNICEF’s only downstream partners are Eritrean government line ministries – the Ministry of Health and Ministry of Land, Water and Environment. In-person PSEA training has been delivered. Partners have previously been slow to utilise funds, so this is being closely monitored, with joint government-UNICEF delivery plans now in place to improve timely utilisation. Reporting has been timely and comprehensive. The project is not anticipated to purchase significant assets. All procurement will be managed centrally by UNICEF and assets will be handled according to UNICEF regulations.

Two new partnerships were mobilising towards the end of the review period for this annual review, including the first response under the Sudden Onset and Emerging Crises pillar. Their performance will be assessed fully in future reviews.

Southern Africa Cholera response
In February 2024, a regional response to a cholera outbreak was mobilised funding the International Federation of the Red Cross and Red Crescent Societies (IFRC) emergency appeals covering Malawi, Zambia, and Zimbabwe through an MoU. The appeals addressed immediate treatment needs, preparedness for the next season, and prevention through WASH interventions. A due diligence assessment was scheduled after the first payment, in line with the FCDO rules for humanitarian emergency funding. The IFRC Zimbabwe cluster office manages the response and funding to national societies, confirming 100% completion of PSEA and child safeguarding training, with AAP mechanisms in place in each country. All assets will be managed and disposed of according to partner policies.

Madagascar
After a scoping mission in March 2024 a concept note was received from the IFRC with the British Red Cross (BRC) as grant holder. Following discussions a full proposal, leading to a three-year, £7.5 million project agreement through an MoU over three years. The project aims not only to provide emergency response to sudden crises like cyclones, but also seeks to improve coordination efforts and strengthen the resilience of vulnerable populations in the face of increasing weather and climatic hazards and disasters in Madagascar. Due diligence was completed under previous cyclone response funding, with all recommendations either resolved or incorporated into monitoring plans. All cluster staff have completed core training, including safeguarding. A six-month inception period was included to refine the resilience and innovation approach, recruit technical staff, and pre-position for the cyclone season. FCDO is planning a monitoring mission to Madagascar to review progress and update due diligence. Assets will be procured, with high-value purchases subject to VFM analysis and FCDO approval before procurement.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
The programme team, based in the UK and South Africa, includes at least one field visit to each context as a control measure due to the programme’s high risk. Between November 2023 and March 2024, FCDO staff conducted two visits: one to Bangui, CAR, for partner and donor meetings as projects mobilised and another to Madagascar to explore funding options. Other projects were monitored remotely through partner meetings and reporting reviews to stay informed about evolving contexts, delivery challenges, and to reinforce reporting requirements, especially regarding risks such as fraud or safeguarding.

Additional field visits to all active contexts were planned during this period to take place over the following 12 months.

The FCDO programme team holds monthly meetings, chaired by the Programme Responsible Owner (PRO) and attended by the SRO, Humanitarian Advisers (HA), and Programme Managers (PM), to monitor programme delivery and address emerging risks or issues.

The first draft of this annual review was prepared by a Humanitarian Adviser contracted through the HEROS contract with a field visit to CAR, discussions with partners, the programme team and review of partner reports. The programme team then reviewed and finalised the report.

Evidence, Evaluation and Learning
Africa Programmes and Expertise Department (APEX) independent third-party monitoring (TPM) contract completed an Expenditure Monitoring (EM) review of WFP in CAR, a new partner that FCDO could not monitor directly. There were some limitations to the EM with WFP unable to share some of the documents to ensure the privacy, but beneficiary interviews provided useful insights:
73% of beneficiaries preferred cash-based assistance, which aligns with WFP's shift to a vulnerability-based approach.
- WFP adopted the approach recommended by the Minimum Expenditure Basket (MEB) which is tiered assistance model based on household size, aligning support with the needs of larger families.
- WFP’s internal structure, with clear segregation of duties, improved transparency and reduced errors.
- Despite the establishment of various complaint mechanisms, 62% of beneficiaries were unaware that they could report issues, indicating a significant gap in communication.
- Beneficiaries were dissatisfied with the irregular frequency of cash distributions, which affected timely access to aid.

FCDO will use its own monitoring and any partner evaluations to inform learning throughout programme delivery.

The previous Annual Review recommendations concerning monitoring were as follows:

Recommendation	Progress
The mobilisation process was primarily completed through a desk-based review of proposals and documents and supported by discussions with partners and visits from previous programmes. The FCDO programme team should plan monitoring visits to each context to assess the delivery of projects. Ensuring the appropriateness of the activities, impact on vulnerable populations and the application of partner safeguarding and fiduciary policies. Regular remote engagement should also take place to supplement any visits and third-party monitoring may be used where appropriate and feasible.	In-country monitoring visits took place in CARand a scoping visit was completed in Madagascar in the period of this annual review. Remote partner engagement has continued throughout this period and third party monitoring was completed on one partner who were receiving support for the first time. / Ongoing and remains a priority for the programme team to continue to prioritise as a key risk mitigation.

Partner Reporting

	Organisation	Report receipt date
Date of receipt for last narrative financial report(s)	CAR – CHF	10 June 2024
	CAR – MENTOR Consortium	1 April 2025
	CAR – WFP	28 June 2024
	CAR – UNICEF	17 October 2024
	Cameroon – ICRC	30 June 2024
	Eritrea - UNICEF	18 April 2025
Date of last audited annual statement(s)	CAR – CHF	24 July 2024
	CAR – MENTOR	31 March 2025
	CAR – WFP	28 June 2024 (2023)
	CAR – UNICEF	Due July 2025 (2024)
	Cameroon – ICRC	30 June 2024 (2023)
	Eritrea - UNICEF	24 July 2024 (2023)

H: Annex 1 – Value for Money Framework
	VFM Metric	Partner	Baseline/target	Progress (FY2023/24)
Economy	Cost per beneficiary	CHF (CAR)	Baseline: £26.64	£19.70
		MENTOR (CAR)	Baseline: £19.12	£21.10
		WFP (CAR)	New partner	£15.62
		ICRC (Cameroon)	Baseline: £27.59	£36.86
		UNICEF (Eritrea)	Baseline: £3.11	£3.14
	Total cost per child treated for Global Acute Malnutrition (GAM)	UNICEF (Eritrea)	New indicator	£81.71
	Cost per consultation Ouham Pende/ Alindao (Health Facilities (FOSAs)/Community Health Workers (CHWs) / WASH)	MENTOR (CAR)	New indicator	£1.77
	Cost per consultation Alindao (District Hospital/ WASH)	MENTOR (CAR)	New indicator	£5.78
	Cost per cash transfer	WFP (CAR)	New partner	£5.86
Efficiency	Total number of days of stockout of essential medicines	MENTOR (CAR)	6 essential drugs are monitored for the average number of days of stockout, with a target of less than 5 days/month.	Of the six essential medicines monitored: ACT, / Paracetamol, Iron/folic acid, Amoxicillin, Albendazole, Fansidar the only stockout reported was: / -Paracetamol – 60 days, for MENTOR in Basse Kotto. ACF had zero stockouts and MENTOR in Ouham Pende had zero stockouts
	% of funding to National Non-Government Organisations (NNGOs)	CHF (CAR)	Baseline: 7% (2022) / Target: International localisation target is 20%, CAR is starting from a much lower level so this indicator will look at the increase and how it is managed.	20%
	CHF operations costs as % overall utilisation of fund	CHF (CAR)	Baseline: 5.7% / Target: less than 10% of overall utilisation of funds	6.97%
Effectiveness	Under-five prevalence of acute malnutrition (wasting)	UNICEF (Eritrea)	Baseline 12.3%; Target: March 2024 11.3%	11%
	CHF performance assessed in the Common Performance Framework (CPF)	CHF (CAR)	Target: average score of 4 out of 5	4.25
Equity	% of zobas (regions) UNICEF is active in	UNICEF (Eritrea)	Target: 100%	100%
	Bases maintained in regions with humanitarian need in Cameroon	ICRC (Cameroon)	Target: Far North and North-West/South-West (NW/SW)	2 in the Far North / 3 in the NW & SW
	% users that are women and girls, people with disability among those participating in community feedback and complaints mechanisms.	UNICEF (Accountability to Affected Populations in CAR)	Baseline: Women and Girls: 60% People with Disability: 15%	Women and Girls: 46% / People with Disability: 14%
[note] Correction from previous annual review which had 1%.