## Mobilisation Logframe
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (10 August 2023-30 November 2023) | Assumptions
Mobilisation of support to enabling actions and system reform to improve humanitarian responses. | Mobilisation of technical assistance | Planned |  | - Stand By Partnership requests responded to within 3 working days - engagement with Posts to identify any gaps the programme could support - TORs for West Africa and Southern Africa consultants completed by 20 October 2023 - Candidates identified and offered by 30 November 2023 | -Suitable candidates on Palladium roster. -Partners engage in a timely manner sharing documentation and reviewing draft DDAs and agreements. -Due dilligence assessment recommend proceeding with agreements -Sufficient staff capacity to manage ongoing engagement and not surged to other FCDO priorities
|  | Achieved |  | - 7/7 requests received in this period were responded to within three working days (4 within 1 day, 2 within 2 days and 1 within 3 days). - Africa Directorate Development Advisers/Desk Officers briefed on AHRF II capabilities (briefing series completed 4 October 2023) and meetings with Post taking place as needs emerge. - Formal consultation on Southern Africa Consultant commenced 19 October 2023. TOR finalised and recruitment launched 21 December 2023. Formal consultation on West Africa TOR launched 7 December; decision to pause recruitment until next financial year taken 22 November 2023. - Southern Africa candidate identified/ offered 5 January 2024
Source
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Milestone 1
25% | Mobilisation of Accountability to Affected Populations Project in the Central African Republic. | Planned |  | - Due Diligence Assessment completed and agreement signed by 30 November 2023
|  | Achieved |  | - Due Diligence Assessment finalised 17 January 2024, agreement signed 22 January 2024.
Source
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (10 August 2023 - 30 November 2023) | Assumptions
Humanitarian support to protracted crises in CAR, Cameroon and Eritrea mobilised. | Mobilisation of humanitarian response in the Central African Republic through three partners. | Planned |  | -Health consortium proposal received, due diligence completed and agreement signed by 1 November 2023. -CAR Humanitarian Fund due diligence completed and agreement signed by 30 November 2023 -WFP due diligence completed and agreement signed by 30 November 2023 | -Partners engage in a timely manner sharing documentation and reviewing draft DDAs and agreements. -Due dilligence assessments recommend proceeding with agreements -Sufficient staff capacity to manage multiple mobilisations in a short space of time and not surged to other FCDO priorities
|  | Achieved |  | - Health Consortium: the proposal was received on 3 October 2023; the due diligence was completed on 24 October 2023; and the agreement was countersigned on 31 October 2023. - CHF: the due diligence was completed on 9 November 2023 and the agreement was countersigned on 10 November 2023. - WFP: the due diligence was completed on 2 November 2023 and the agreement was countersigned on 7 November 2023.
Source
| Output Indicator 2.2 |  | Baseline | Milestone 1
| Mobilisation of humanitarian response in Cameroon through one partner. | Planned |  | -ICRC due diligence completed and agreement signed by 15 November 2023.
|  | Achieved |  | - The due diligence was completed on 7 November 2023 and the agreement was countersigned on 10 November 2023.
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1
75% | Mobilisation of humanitarian response in Eritrea through one partner. | Planned |  | -UNICEF proposal received, due diligence completed and agreement signed by 31 October 2023
|  | Achieved |  | - The final UNICEF proposal was received on 7 September 2023; the due diligence was completed on 3 October 2023; and the agreement was countersigned on 11 October 2023.
Source

## Implementation Logframe
Africa Humanitarian Response Fund II
AFRICA HUMANITARIAN RESPONSE FUND II
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Nov 2023) | Milestone 2 ( August-December 2023) 2024 AR | Milestone 3 (1 Jan-31 Dec 2024) 2025 AR | Milestone 4 (1 Jan-31 Dec 2025) 2026 AR | Milestone 5 (1 Jan-31 Dec 2026) PCR 2027 | Final Target PCR 2027 | Assumptions
Reduced suffering of vulnerable and crisis-affected populations across Sub-Saharan Africa, Egypt and Libya. | % of people in need and % of people targeted in SSA, Egypt and Libya reached by humanitarian assistance (not FCDO attributable) | Planned % of people in need reached |  |  |  |  | 43% | 43% | 43% | 1. People in need estimates are sufficiently accurate, and people reached received timely and appropriate assistance.
|  | Planned % of people targeted reached |  |  |  |  | 72% | 72% | 72%
Achieved % of people in need reached
Achieved % of people targeted reached
Source
FTS/GHO
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Nov 2023) | Milestone 2 ( August-December 2023/March 2024) 2024 AR | Milestone 3 (1 Jan-31 Dec 2024)/(1 Apr--31 March 2025) 2025 AR | Milestone 4 (1 Jan-31 Dec 2025)/(1 Apr--31 March 2026) 2026 AR | Milestone 5 (1 Jan-31 Dec 2026)/(1 Apr--31 March 2027) | Final Target PCR 2027 | Assumptions
Timely, proportional, and accountable response to affected populations. (this outcome relates to direct delivery attributable to the FCDO) | Number of people targeted by humanitarian emergency appeals reached by the programme | Planned | 0 |  | 491062 | 2592988 | 1187492 | 1299951 | 4627231 | 1. The IRF will increase AD’s capacity to quickly respond to new crises across the region through reducing the need to develop a new business case for each humanitarian intervention. 2. Sufficient funding and human resources are available for the IRF (e.g. via CCR, underspends in Africa) to respond to prioritised sudden onset disasters or spikes in humanitarian need. 3. Where anticipatory action or early intervention is prioritised, this may save lives and will represent good VFM compared to a later response. Having the IRF facility in place will enable early interventions, meeting VFM criteria for the programme. 4. Multi-year funding reduces transaction costs, process and hence increases efficiency. 5. Multi-year funding mechanisms strengthen the humanitarian systems in-country by providing predictable financing and a greater focus on delivery. 6. Assistance provided is timely and appropriate (monitoring is in place to check that).
|  | Achieved |  |  | 550037 | #VALUE! | 0 | 0 | 0
Source
Partner reports
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Nov 2023) | Milestone 2 ( August-March 2024) 2024 AR | Milestone 3 (1 Apr 2024-31 March 2025) 2025 AR | Milestone 4 (1 Apr 2025-31 March 2026) 2026 AR | Milestone 5 (1 Apr 2026-31 March 2027) PCR | Final Target PCR 2027 | Assumptions
Humanitarian actors deliver a more effective, principled, and inclusive humanitarian response. (this outcome relates to the wider humanitarian system e.g. AAP) | Evidence of FCDO funded TA support leading to improvements in humanitarian response | Planned |  |  | Contribution of FCDO funded TA leads to improvements in response. Assessed through consideration of timeliness, relevance and effectiveness. | Contribution of FCDO funded TA leads to improvements in response. Assessed through consideration of timeliness, relevance and effectiveness. | Contribution of FCDO funded TA leads to improvements in response. Assessed through consideration of timeliness, relevance and effectiveness. | Contribution of FCDO funded TA leads to improvements in response. Assessed through consideration of timeliness, relevance and effectiveness. | Contribution of FCDO funded TA leads to improvements in response. Assessed through consideration of timeliness, relevance and effectiveness. | 1. FCDO can contribute to more efficient and effective humanitarian system response through support to technical assistance, operational support and preparedness. 2. Technical assistance improved a more effective, principled, and inclusive humanitarian response. 3. Technical Assistance to be understood very widely, from SBP support to more comprehensive packages. 4. Sufficient advisory and programme management resources to respond to TA needs and strategically engage with posts and partners.
|  | Achieved |  |  | Two deployments completed during this period: 1.Met expectations in all areas 2.Met expectations for relevance but, moderately not met for timeliness and effectiveness
Source
SBP tracking sheet which reviews reports from FCDO deployed experts and/or reports from partners
OUTPUT 1 - Technical Assistance | Output Indicator 1.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Nov 2023) | Milestone 2 ( 1 December-March 2024) 2024 AR | Milestone 3 (1 Apr 2024-31 March 2025) 2025 AR | Milestone 4 (1 Apr 2025-31 March 2026) 2026 AR | Milestone 5 (1 Apr 2026-31 March 2027) PCR | Final Target PCR 2027 | Assumptions
Responses improved by support to enabling actions and system reform | FCDO funded TA support provided in a timely and responsive way. | Planned |  |  | - Stand By Partnership requests responded to within 5 working days - Engagement with Posts to identify any gaps the programme could support maintained | - Stand By Partnership requests responded to within 5 working days - Engagement with Posts to identify any gaps the programme could support maintained | - Stand By Partnership requests responded to within 5 working days - Engagement with Posts to identify any gaps the programme could support maintained | - Stand By Partnership requests responded to within 5 working days - Engagement with Posts to identify any gaps the programme could support maintained | - Stand By Partnership requests responded to within 5 working days - Engagement with Posts to identify any gaps the programme could support maintained | 1. Investment in technical assistance via consultants or standby personnel arrangements supporting implementing partners will result in better quality monitoring data (results, contextual or risk monitoring) and will lead to improved programming and improved quality of humanitarian response. 2. FCDO programme management capacity is sufficient to support enabling actions. 3. Partner organisations submit timely requests for capacity. 4. Suitable candidates on Palladium and SBP rosters. 5. Response plans sufficiently address and support principles from UK humanitarian reform policy and Grand Bargain principles. Including maximising inter-agency coordination and accountability to affected populations. 6. Humanitarian actors continue to engage with AAP system in CAR. 7. Humanitarian Coordinator continues to prioritise AAP as part of the HRP in CAR.
|  | Achieved |  |  | -11/12 Stand By Partnership requests responded to within 5 working days, 8 within one day, 2 within two days, 1 in four days and 1 took 13 days due to break in the line of communication (request not shared with the full team). -Engagement with post limited due to capacity constraints (vacant humanitarian adviser positions) however this scaled up following recruitment of Southern Africa Humanitarian Adviser, including a visit to Madagascar. For responses to epidemics, appropriate referrals made for post to dedicated health teams for support.
Source
SBP tracking sheet and AHRF II Programme Meetings
| Output Indicator 1.2 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 (22 Jan 2024- 30 June 2024) 2024 AR | Milestone 3 (1 July 2024-30 June 2025) 2025 AR | Milestone 4 (1 July 2025 - 31 March 2026) | Milestone 5 (1 April 2026-31 December 2026) PCR | Final Target PCR 2027
| Supported response in CAR implements AAP programmes and makes use of feedback to inform planning and implementation | Planned |  |  | Scoring methodology: 1=No AAP system in place 2=AAP system in place but not used to inform planning or implementation 3=AAP system used to inform planning and implementation of response 4= AAP system used to inform planning and implementation of response and AAP system regularly reviewed and updated. Weighted score across responses receiving AAP. | 4 | 4 | 4 | 4
|  | Achieved |  |  | 2 – Due to timing of agreement signing with UNICEF and the time needed for finalisation of agreements with local partners, the period under review is the initial six months of 2024. Supporting UN-wide planning as per the humanitarian programme cycle and HRP will only be evident later in the year and covered through the next AR. The score of ‘2’ has been applied because only the beginning of informed planning and implementation was accomplished albeit satisfactory but with more still to be done.
IMPACT WEIGHTING (%) |  | Source
20% |  | UNICEF CAR reports and HRP Scoring methodology: 1=No AAP system in place 2=AAP system in place but not used to inform planning or implementation 3=AAP system used to inform planning and implementation of response 4= AAP system used to inform planning and implementation of response and AAP system regularly reviewed and updated. Weighted score across responses receiving AAP.
OUTPUT 2 - Cameroon | Output Indicator 2.1 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 ( November-December 2023) 2024 AR | Milestone 3 (1 Jan-31 Dec 2024) 2025 AR | Milestone 4 (1 Jan-31 Dec 2025) 2026 AR | Milestone 5 (1 Jan-31 Dec 2026) PCR | Final Target PCR 2027 | Assumptions
Multisector humanitarian assistance provided to the populations affected by the conflict in the Cameroon | Number of people receiving humanitarian assistance (all sectors included) | Planned | 0 |  | 50716 | 73419 | 55462 |  | 0 | 1. Humanitarian access is sustained. 2. Security context will allow field monitoring for delivery partner(s) and FCDO programme team. 3. Beneficiary targeting will be strengthened by the appropriate use of available data and needs analysis when designing each deployment, and will align with the wider FCDO Humanitarian Strategic Framework. 4. Response plans sufficiently address and support principles from UK humanitarian reform policy and Grand Bargain principles. Including the use of multi-purpose cash transfers where possible and appropriate. 5. Budgets for next Spending Review period/ outer years allow for planned allocations to be disbursed in full. 6. Responses will be adapted based on learning.
|  | Achieved (Total) |  |  | 60082 |  |  |  | 0
|  | Achieved (Female) |  |  | 13991 |  |  |  | 0
|  | Achieved (Male) |  |  | 12670 |  |  |  | 0
|  | Achieved (Children) |  |  | 33421 |  |  |  | 0
Source
ICRC Reports
| Output Indicator 2.2 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 ( November-December 2023) 2024 AR | Milestone 3 (1 Jan-31 Dec 2024) 2025 AR | Milestone 4 (1 Jan-31 Dec 2025) 2026 AR | Milestone 5 (1 Jan-31 Dec 2026) PCR | Final Target PCR 2027
| Number of people assisted by FCDO through cash, voucher and food | Planned (food) | 0 |  | 4861 | 7601 | 3139 |  | 0
|  | Planned (cash for work) | 0 |  | 1812 | 5052 | 6730 |  | 0
|  | Achieved (food Total) |  |  | 5155 |  |  |  | 0
|  | Achieved (food female) |  |  | 1496 |  |  |  | 0
|  | Achieved (food male) |  |  | 1243 |  |  |  | 0
|  | Achieved (food children) |  |  | 2416 |  |  |  | 0
|  | Achieved (cash for work total) |  |  | 1170 |  |  |  | 0
|  | Achieved (cash for work female) |  |  | 353 |  |  |  | 0
|  | Achieved (cash for work male) |  |  | 344 |  |  |  | 0
|  | Achieved (cash for work children) |  |  | 473 |  |  |  | 0
Source
ICRC Reports
| Output Indicator 2.3 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 ( November - December 2023) 2024 AR | Milestone 3 (1 Jan-31 Dec 2024) 2025 AR | Milestone 4 (1 Jan-31 Dec 2025) 2026 AR | Milestone 5 (1 Jan-31 Dec 2026) PCR | Final Target PCR 2027
| Number of people receiving food production assistance | Planned | 0 |  | 44043 | 60766 | 45593 |  | 0
|  | Achieved (Total) |  |  | 53757 |  |  |  | 0
|  | Achieved (Female) |  |  | 12142 |  |  |  | 0
|  | Achieved (Male) |  |  | 11083 |  |  |  | 0
|  | Achieved (Children) |  |  | 30532 |  |  |  | 0
IMPACT WEIGHTING (%) |  | Source
15% |  | ICRC Reports
OUTPUT 3 - Central African Republic | Output Indicator 3.1 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 (November-December 2023) 2024 AR | Milestone 3 (1 Jan-31 Dec 2024) 2025 AR | Milestone 4 (1 Jan-31 Dec 2025) 2026 AR | Milestone 5 (1 Jan-31 Dec 2026) PCR | Final Target PCR 2027 | Assumptions
Multisector humanitarian assistance provided to the populations affected by the conflict in the Central African Republic | Number of people receiving humanitarian assistance (all sectors included) | Planned | 0 |  | 130346 | 266934 |  |  | 397280 | 1. Humanitarian access is sustained. 2. Security context will allow field monitoring for delivery partner(s) and FCDO programme team. 3. Beneficiary targeting will be strengthened by the appropriate use of available data and needs analysis when designing each deployment, and will align with the wider FCDO Humanitarian Strategic Framework. 4. Response plans sufficiently address and support principles from UK humanitarian reform policy and Grand Bargain principles. Including the use of multi-purpose cash transfers where possible and appropriate. 5. Responses will be adapted based on learning. 6. Collaboration with key government and UN agencies in not reduced. 7. MINUSCA forces are maintained on the field. 8. IDPs and host communities support the projects. 9. Security situation allows for supply lines and staff 10. License to import pharmaceuticals is maintained for all partners. 11. Transport to carry supplies to the field sites remain available (flights, road) and a sufficient cold chain is available. 12. Insecurity and/or climatic conditions don't render projects inaccessible for beneficiaries. 13. Cultural barriers don't prevent beneficiaries from seeking access to services (for instance women not willing to be visited by a male health worker)
|  | Achieved (Total) |  |  | 171558
|  | Achieved (Female) |  |  | 94345
|  | Achieved (Male) |  |  | 77213
Source
CHF Reports & MENTOR Consortium Report
| Output Indicator 3.2 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 ( November 2023-March 2024) 2024 AR | Milestone 3 (1 Apr 2024-31 March 2025) 2025 AR | Milestone 4 (1 Apr 2025-31 March 2026) 2026 AR | Milestone 5 (1 Apr 2026-31 March 2027) PCR | Final Target PCR 2027
| Number of people assisted by FCDO through cash, voucher and food | Planned (Total) | 0 |  | 28613 |  |  |  | 28613
|  | Planned (Cash or Voucher) | 0 |  | 28613 |  |  |  | 28613
|  | Planned (Food) | 0 |  | 0 |  |  |  | 0
|  | Planned (Female) | 0 |  | 15108 |  |  |  | 15108
|  | Planned (Male) | 0 |  | 13505 |  |  |  | 13505
|  | Planned (0-23 months) | 0 |  | 2032 |  |  |  | 2032
|  | Planned (24-59 months) | 0 |  | 2718 |  |  |  | 2718
|  | Planned (5-17 years) | 0 |  | 7811 |  |  |  | 7811
|  | Planned (18-59 years) | 0 |  | 14307 |  |  |  | 14307
|  | Planned (60+ years) | 0 |  | 1745 |  |  |  | 1745
|  | Planned (Disabled) | 0 |  | 2240 |  |  |  | 2240
|  | Achieved (Total) |  |  | 64037 |  |  |  | 64037
|  | Achieved (Cash or voucher) |  |  | 64037 |  |  |  | 64037
|  | Achieved (Food) |  |  | 0 |  |  |  | 0
|  | Achieved (Female) |  |  | 33747 |  |  |  | 33747
|  | Achieved (Male) |  |  | 30290 |  |  |  | 30290
|  | Achieved (0-23 months) |  |  | 4547 |  |  |  | 4547
|  | Achieved (24-59 months) |  |  | 6083 |  |  |  | 6083
|  | Achieved (5-17 years) |  |  | 17482 |  |  |  | 17482
|  | Achieved (18-59 years) |  |  | 33235 |  |  |  | 33235
|  | Achieved (60+ years) |  |  | 2690 |  |  |  | 2690
|  | Achieved (Disabled) |  |  | 4482 |  |  |  | 4482
Source
WFP Reports
| Output Indicator 3.3 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 (1 November - 31 December 2023) 2024 AR | Milestone 3 (1 Jan - 31 Dec 2024) 2025 AR | Milestone 4 (1 Jan -31 Dec 2025) 2026 AR | Milestone 5 (1 Jan -31 Dec 2026) PCR | Final Target PCR 2027
| Number of Healthcare Consultations Provided | Planned (Total) | 167,279 |  | 29977 | 166565 |  |  | 166565
|  | Planned Female over 5 | 42,010 |  | 7389 | 40228 |  |  | 40228
|  | Planned Male over 5 | 26,359 |  | 3670 | 24121 |  |  | 24121
|  | Planned Female under 5 | 48,393 |  | 9248 | 49826 |  |  | 49826
|  | Planned Male under 5 | 50,517 |  | 9670 | 52390 |  |  | 52390
|  | Achieved (Total) |  |  | 19282 | 0 |  |  | 0
|  | Achieved Female over 5 |  |  | 4554 |  |  |  | 0
|  | Achieved Male over 5 |  |  | 2815 |  |  |  | 0
|  | Achieved Female under 5 |  |  | 5924 |  |  |  | 0
|  | Achieved Male under 5 |  |  | 5989 |  |  |  | 0
Source
MENTOR Consortium Reports
| Output Indicator 3.4 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 (1 November - 31 December 2023) 2024 AR | Milestone 3 (1 Jan - 31 Dec 2024) 2025 AR | Milestone 4 (1 Jan -31 Dec 2025) 2026 AR | Milestone 5 (1 Jan -31 Dec 2026) PCR | Final Target PCR 2027
| Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions | Planned (Female over 5) | 6927 |  | 1278 | 9204 |  |  | 10482
|  | Achieved (Female over 5) |  |  | 1885 |  |  |  | 1885
Source
MENTOR Consortium Reports
| Output Indicator 3.5 |  | Baseline | Milestone 1 - Mobilisation (August-November 2023) | Milestone 2 (1 November - 31 December 2023) 2024 AR | Milestone 3 (1 Jan - 31 Dec 2024) 2025 AR | Milestone 4 (1 Jan -31 Dec 2025) 2026 AR | Milestone 5 (1 Jan -31 Dec 2026) PCR | Final Target PCR 2027
| Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions | Planned (Under 5) | 1724 |  | 334 | 2681 |  |  | 3015
|  | Achieved (Under 5) |  |  | 140 |  |  |  | 140
IMPACT WEIGHTING (%) |  | Source
20% |  | MENTOR Consortium Reports
OUTPUT 4 - Eritrea | Output Indicator 4.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 (October 2023 - March 2024) 2024 AR | Milestone 3 (1 Apr 2024 -31 Mar 2025) 2025 AR | Milestone 4 (1 Apr 2025 -31 Mar 2026) 2026 AR | Milestone 5 (1 Apr 2026 -31 Mar 2027) | PCR 2027 | Assumptions
Improving the delivery of integrated nutrition and sanitation services to children, and women in Eritrea | Number of people receiving humanitarian assistance | Planned | 0 |  | 310000 | 310000 | 350000 | 403926 | 1373926 | 1. Monitoring access possible for delivery partner and FCDO programme team 2. Permission to procure nutrition supplies directly through the UNICEF Procurement platform continues to be granted by Government of the State of Eritrea (GoSE) 3. Strategic Partnership Cooperation Framework between GoSE and the UN and the associated Annual Workplans are agreed in a timely manner. 4. Security situation in country remains stable. 5. Budgets for next Spending Review period/ outer years allow for planned allocations to be disbursed in full. 6. Beneficiary targeting will be strengthened by the appropriate use of available data and needs analysis when designing each deployment, and will align with the wider FCDO Humanitarian Strategic Framework. 7. Responses will be adapted based on learning.
|  | Achieved |  |  | 318397
Source
Partner reports (UNICEF Eritrea)
| Output Indicator 4.2 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 (October 2023 - March 2024) 2024 AR | Milestone 3 (1 Apr 2024 -31 Mar 2025) 2025 AR | Milestone 4 (1 Apr 2025 -31 Mar 2026) 2026 AR | Milestone 5 (1 Apr 2026 -31 Mar 2027) | PCR 2027
| Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions | Planned (Total) | 0 |  | GAM: 7,490 SAM: 3,400 MAM: 4,090 | GAM: 9,370 SAM: 4,000 MAM: 5,370 | GAM: 9,370 SAM: 4,000 MAM: 5,370 | GAM: 9,370 SAM: 4,000 MAM: 5,370 | GAM: 35,600 SAM: 15,400 MAM: 20,200
|  | Planned (Female) | 0 |  | 3670
|  | Planned (Male) | 0 |  | 3820
|  | Achieved |  |  | GAM -7,690 SAM - 3,500 MAM - 4,190
Source
Partner reports (UNICEF Eritrea)
| Output Indicator 4.3 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 (October 2023 - March 2024) 2024 AR | Milestone 3 (1 Apr 2024 -31 Mar 2025) 2025 AR | Milestone 4 (1 Apr 2025 -31 Mar 2026) 2026 AR | Milestone 5 (1 Apr 2026 -31 Mar 2027) | PCR 2027
| Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions. | Planned | Children receiving Vit A: 299,425 |  | Pregnant & lactating women receiving iron folic acid supplements: 50,000 Children receiving Vit A: 334,620 Number of primary caregivers counselled for MIYCF: 80,000 | Pregnant & lactating women receiving iron folic acid supplements: 50,000 Children receiving Vit A: 343,200 Number of primary caregivers counselled for MIYCF: 80,000 | Pregnant & lactating women receiving iron folic acid supplements: 50,000 Children receiving Vit A: 351,780 Number of primary caregivers counselled for MIYCF: 120,000 | Pregnant & lactating women receiving iron folic acid supplements: 50,000 Children receiving Vit A: 364,650 Number of primary caregivers counselled for MIYCF: 130,000 | Pregnant & lactating women receiving iron folic acid supplements: 200,000 Children receiving Vit A: 364,650 Number of primary caregivers counselled for MIYCF: 410,000
|  | Achieved |  |  | • 54,819 pregnant & lactating women received iron & folic acid tablets to prevent anaemia & low birth rate. • 343,200 children aged 6 to 59 months received vitamin A supplementation. • 81,234 primary caregivers & mothers were counselled for maternal infant & young child feeding (MIYCF).
Source
Partner reports (UNICEF Eritrea)
| Output Indicator 4.4 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 (October 2023 - March 2024) 2024 AR | Milestone 3 (1 Apr 2024 -31 Mar 2025) 2025 AR | Milestone 4 (1 Apr 2025 -31 Mar 2026) 2026 AR | Milestone 5 (1 Apr 2026 -31 Mar 2027) | PCR 2027
| Number of individuals reached with sanitation activities. | Planned (Total) | 1564990 |  | 30000 | 30000 | 30000 | 30000 | 120000
|  | Planned (Female) |  |  | 15300
|  | Planned (Male) |  |  | 14700
|  | Achieved (Total) |  |  | 32268
Source
Partner reports (UNICEF Eritrea)
| Output Indicator 4.5 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 (October 2023 - March 2024) 2024 AR | Milestone 3 (1 Apr 2024 -31 Mar 2025) 2025 AR | Milestone 4 (1 Apr 2025 -31 Mar 2026) 2026 AR | Milestone 5 (1 Apr 2026 -31 Mar 2027) | PCR 2027
| Number of healthcare consultations provided | Planned (Total) |  |  |  |  | 0 | 43,926 - 22,061 pregnant women skilled birth attendance - 21,865 newborns reached | 43,926 - 22,061 pregnant women skilled birth attendance - 21,865 newborns reached
Achieved (Total)
Source
Partner reports (UNICEF Eritrea)
| Output Indicator 4.6 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 (October 2023 - March 2024) 2024 AR | Milestone 3 (1 Apr 2024 -31 Mar 2025) 2025 AR | Milestone 4 (1 Apr 2025 -31 Mar 2026) 2026 AR | Milestone 5 (1 Apr 2026 -31 Mar 2027) | PCR 2027
| Number of health facilities supported - Neonatal Intensive Care Units (NICU) and Emergency Obstetric and Newborn Care (EmONC) centres | Planned | 243 |  |  |  | 243 | 265 (12 new /rehabilitated) | 265 (12 new /rehabilitated)
Achieved
IMPACT WEIGHTING (%) |  | Source
15% |  | Partner reports (UNICEF Eritrea)
OUTPUT 5 - Southern Africa Cholera | Output Indicator 5.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (23 Feb 2024 -31 Dec 2024) 2025 AR | Milestone 4 2026 AR | Milestone 5 | PCR 2027 | Assumptions
Humanitarian assistance provided to populations affected by cholera outbreak in Malawi, Zambia and Zimbabwe. | Number of people receiving humanitarian assistance | Planned | 0 |  |  | 1700000 |  |  | 1700000 | 1. Humanitarian access is sustained. 2. Procurement isn't delayed. 3. Response plans sufficiently address and support principles from UK humanitarian reform policy and Grand Bargain principles.
|  | Achieved |  |  | 0
Source
Partner reports (IFRC)
| Output Indicator 5.2 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (23 Feb 2024 -31 Dec 2024) 2025 AR | Milestone 4 2026 AR | Milestone 5 | PCR 2027
| Number of health workers trained | Planned | 0 |  |  | 1400 |  |  | 1400
Achieved
Source
Partner reports (IFRC)
| Output Indicator 5.3 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (23 Feb 2024 -31 Dec 2024) 2025 AR | Milestone 4 2026 AR | Milestone 5 | PCR 2027
| Number of health facilities supported | Planned | 0 |  |  | 155 |  |  | 155
Achieved
Source
Partner reports (IFRC)
| Output Indicator 5.4 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (23 Feb 2024 -31 Dec 2024) 2025 AR | Milestone 4 2026 AR | Milestone 5 | PCR 2027
| Number of Individuals reached with hygiene activities | Planned | 0 |  |  | 1700000 |  |  | 1700000
Achieved
Source
Partner reports (IFRC)
| Output Indicator 5.5 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (23 Feb 2024 -31 Dec 2024) 2025 AR | Milestone 4 2026 AR | Milestone 5 | PCR 2027
| Number of water points (new, rehabilitated or upgraded) and providing access to safe water supply for the affected communities | Planned | 0 |  |  | 200 |  |  | 200
Achieved
IMPACT WEIGHTING (%) |  | Source
15% |  | Partner reports (IFRC)
OUTPUT 6 - Madagascar | Output Indicator 6.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (July 2024 - March 2025) 2025 AR | Milestone 4 (April 2025-March 2026) 2026 AR | Milestone 5 (April 2026-March 2027) | PCR 2027 | Assumptions
Improving hunanitarian resilience and preparedness in Madagascar. | Number of people benefiting from humanitarian aid (all sectors combined) | Planned (total) |  |  |  | 242635 | 522030 | 896025 | 896025
|  | Planned (female over 18) |  |  |  | 60659 | 130508 | 224006 | 224006
|  | Planned (male over 18) |  |  |  | 60659 | 130508 | 224006 | 224006
|  | Planned (female under 18) |  |  |  | 60659 | 130508 | 224006 | 224006
|  | Planned (male under 18) |  |  |  | 60659 | 130508 | 224006 | 224006
|  | Planned (disabled) |  |  |  | 14558 | 31322 | 53762 | 53762
Achieved (total)
Achieved (female over 18)
Achieved (male over 18)
Achieved (female under 18)
Achieved (male under 18)
Achieved (disabled)
Source
Beneficiary Registration, Baseline/endline survey
| Output Indicator 6.2 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (July 2024 - March 2025) 2025 AR | Milestone 4 (April 2025-March 2026) 2026 AR | Milestone 5 (April 2026-March 2027) | PCR 2027
| # of integrated multi-sectoral action plans developed and implemented, including Protection, Gender and Inclusion (PGI) and Prevention of and Protection against Sexual Exploitation and Abuse (PSEA) | Planned | 0 |  |  | 8 | 24 | 36 | 36
Achieved
Source
EVCA reports
| Output Indicator 6.3 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (July 2024 - March 2025) 2025 AR | Milestone 4 (April 2025-March 2026) 2026 AR | Milestone 5 (April 2026-March 2027) | PCR 2027
| # of people made aware of the early warning system (EWS) | Planned (total) | 0 |  |  | 56760 | 170280 | 338400 | 338400
|  | Planned (female over 18) |  |  |  | 14190 | 42570 | 84600 | 84600
|  | Planned (male over 18) |  |  |  | 14190 | 42570 | 84600 | 84600
|  | Planned (female under 18) |  |  |  | 14190 | 42570 | 84600 | 84600
|  | Planned (male under 18) |  |  |  | 14190 | 42570 | 84600 | 84600
|  | Planned (disabled) |  |  |  | 3406 | 10217 | 20304 | 20304
Achieved (total)
Achieved (female over 18)
Achieved (male over 18)
Achieved (female under 18)
Achieved (male under 18)
Achieved (disabled)
Source
Beneficiary Registration, Baseline/endline survey
| Output Indicator 6.4 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 (July 2024 - March 2025) 2025 AR | Milestone 4 (April 2025-March 2026) 2026 AR | Milestone 5 (April 2026-March 2027) | PCR 2027
| # of action plans developed and implemented following the Branch Organizational Capacity Assessment (BOCA) exercise exceeding 50% completion | Planned | 0 |  |  | 2 | 6 | 6 | 6
Achieved
IMPACT WEIGHTING (%) |  | Source
15% |  | Progress report, Review meeting
OUTPUT 7 - Sudan Regional Response | Output Indicator 7.1 |  | Baseline | Milestone 1 - Mobilisation (Aug-Oct 2023) | Milestone 2 2024 AR | Milestone 3 2025 AR | Milestone 4 (Nov 2024- 31 March 2025) 2026 AR | Milestone 5 | PCR 2027 | Assumptions
Protection and education assistance provided to the populations in the region affected by the conflict in Sudan | Number of people benefiting from humanitarian aid (protection and education) | Planned (Total) | 0 |  |  |  | 260000 |  | 260000 | 1. Humanitarian access is sustained. 2. Security context will allow field monitoring for delivery partner(s) and FCDO programme team. 3. Response plans sufficiently address and support principles from UK humanitarian reform policy and Grand Bargain principles. 4. Responses will be adapted based on learning.
|  | Achieved (Total) |  |  | 0 |  |  |  | 0
|  | Achieved (Female, Child 3-18) | [6 empty] | 0
|  | Achieved (Male, Child 3-18) | [6 empty] | 0
|  | Achieved (Child 3-18, with Disabilities) | [6 empty] | 0
IMPACT WEIGHTING (%) |  | Source
ECW Annual Report

## List of Indicators
Sector | No. | Core Indicator | Definition
Multi-sector * | 0 | Number of people receiving humanitarian assistance (all sectors included) | Total number of individuals assisted aggregating all other indicators to calculate total reach. Where other indicators could support the same population just the indicator with the highest target will be counted to avoid the risk of double counting.
Food | 1.1 | Number of supplementary food interventions provided to individuals. | Supplementary food interventions only partially meet the Sphere standard for one individual’s daily nutritional requirements (e.g. flour, hot meals and basic food items).
Food, agriculture, multi-sector * | 1.2 | Number of people assisted by FCDO through cash, voucher and food | Cash/vouchers provided to target populations to meet their needs for a minimum of 30 days
WASH | 2.1.1 | Number of individuals provided with sustainable drinking water. | Sustainable water includes water provided through rehabilitation/maintenance of water infrastructure. It can also include provision of chemicals to major municipal treatment plants.
| 2.1.2 | Number of individuals provided with emergency drinking water. | Emergency drinking water includes water provided as part of an emergency response (e.g. water trucking, bottled water) or as part of a temporary solution (e.g. purification tablets).
| 2.2 | Number of individuals reached with sanitation activities. | Sanitation activities include activities that seek to prevent human contact with the hazards of waste (e.g. waste management, latrines, and sewage systems).
| 2.3 | Number of individuals reached with hygiene activities. | Activities that seek to preserve the health and cleanliness of individuals. These may include, awareness sessions, training, provision of non-food items, including hygiene kits, dignity kits, soap, shampoo, other sanitary materials, etc.
Health | 3.2 | Number of healthcare consultations provided. | Includes primary, secondary and tertiary (non-trauma only) healthcare consultations. Primary healthcare is generally the first point of contact for someone when they contract an illness, suffer an injury or experience symptoms that are new to them. It can be a ‘gateway’ to receiving more specialist care through referral to secondary (disease specialists) or tertiary (highly specialised expertise mostly dealing with inpatients) health care levels, when the case cannot be managed at primary level.
| 3.3 | Number of health workers trained. | Health workers include doctors, nurses, paramedics, civil protection staff, community health workers, and other individuals who provide professional health services.
| 3.4.1 | Number of vaccinations provided through routine immunisation | Routine immunisation refers to a regular and systematic delivery of EPI (expanded programme of immunisation – i.e. vaccines from a specific WHO established list) from fixed posts (e.g. Primary Health Clinic) or through outreach with no time limitation and to all eligible persons and successive birth cohorts (in principle within the health facility catchment population).
| 3.4.2 | Number of vaccinations provided through immunisation campaigns | This includes mass immunisation campaigns and vaccination campaigns, aimed at vaccinating a large number of people (usually nationwide or large areas) in a limited amount of time (usually several rounds per year) to prevent or stem disease outbreaks or to initiate a catch-up in coverage. Polio and Measles are examples of vaccination campaigns in Syria since the beginning of the war.
| 3.5 | Number of health facilities supported. | Health facilities include hospitals, community health centres, clinics, rehabilitation centres, hospices, mobile clinics, pharmacies, etc.
Shelter/NFI | 4.1 | Number of individuals supported through shelter interventions. | Shelter interventions include activities that seek to provide security, personal safety and protection from the elements to individuals and to promote resistance to ill health and disease. Shelter interventions are wide ranging and include temporary tent accommodation, transitional shelter (e.g. public buildings, permanent housing, renovations or rent subsidies).
| 4.2 | Number of individuals benefiting from relief packages. | Packages distributed to affected populations and containing one type or more of non-food items. Packages typically include some of the following essential household items, kitchen utensils, mattresses, blankets jerry cans and clothes. There are often winter specific non-food item packages. Please note that hygiene related non-food items are counted under indicator 2.3.
Agriculture/ Livelihoods | 5.1 | Number of individuals directly or indirectly supported through in-kind agricultural interventions. | In-kind agricultural interventions include goods and services such as, but not limited to, seeds, tools, fertilisers, livestock, vegetable kits, horticulture packages, livestock care/vaccines, and value chain support or technical assistance.
Protection | 6.1 | Number of individuals benefitting from SGBV services. | Any service/intervention designed to address the needs of victims of gender-based violence (e.g. preventative measures such as physical safety interventions or initiatives to change the culture of violence, or responsive – counselling or safe houses).
| 6.2.1 | Number of safe spaces established (including child friendly spaces and female friendly spaces). | Safe spaces are places where individuals can go at any time to feel safe and empowered. This may include female friendly spaces, where females have access to information, education, recreational activities, support and services, and child friendly spaces where children are provided with a safe environment and where recreation, education, and psychosocial support can be delivered and/or information about services/support provided. These spaces may include temporary or permanent structures, including schools, sport facilities, clubs and other structures.
| 6.2.2 | Number of individuals who access safe spaces (including child friendly spaces and female friendly spaces).
| 6.3 | Number of children benefitting from general child protection. | General child protection includes any activity that specifically seeks to protect children from any form of violence, exploitation, abuse and neglect other than psychosocial counselling with is counted separately below.
| 6.4.1 | Number of children benefitting from psychosocial support. | Psychosocial support mainly includes counselling consultations which encourage communication of trauma and insight into problems leading to improved ability to cope with past and future traumatic events.
| 6.4.2 | Number of adults benefitting from psychosocial support.
| 6.5 | Number of individuals trained in MH/PSS and GBV services. | People trained on the provision of Mental Health, Psychosocial Support and Gender Based violence focused services
| 6.6 | Number of persons with disability benefitting from protection activities or other types of assistance. | Protection for persons with disability includes any activity that specifically seeks to protect them from violence, exploitation, abuse and neglect, including activities such as psychosocial counselling, rehabilitation, physical and occupational therapy, prosthetics/orthotics, and/or restorative aids. Indicators counting number of persons with disability provided with other types of assistance (food, NFIs, shelter, etc.) can also be tagged against this indicator.
Education | 7.1 | Number of pupils provided with access to formal primary education. | Formal education is education that is institutionalised, intentional and planned through public organisations and recognised private bodies and – in their totality – constitute the formal education system of a country. Formal education programmes are thus recognised as such by the relevant national education authorities or equivalent authorities, e.g. any other institution in cooperation with the national or sub-national education authorities (source: UNEVCO).
| 7.2 | Number of pupils provided with access to formal secondary education.
| 7.3 | Number of pupils provided with access to non-formal primary education. | Non-formal education is education that is institutionalised, intentional and planned by an education provider. The defining characteristic of non-formal education is that it is an addition, alternative and/ or complement to formal education within the process of the lifelong learning of individuals. It is often provided to guarantee the right of access to education for all. It caters to people of all ages but does not necessarily apply a continuous pathway-structure; it may be short in duration and/or low-intensity, and it is typically provided in the form of short courses, workshops or seminars (source: UNEVCO).
| 7.4 | Number of pupils provided with access to non-formal secondary education.
| 7.6 | Number of teachers trained. | Any type of training targeted at teachers.
| 7.8 | Number of schools re-habilitated, re-built or built. | Schools refer to institutions formally recognised by the government as schools. In Syria, it may also include schools in opposition held areas that are managed by Education Directorates which are affiliated to the Syria Interim Government Ministry of Education.
Nutrition * | 8.1 | Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions | Malnutrition prevention interventions include Infant Young Child Feeding (IYCF) programmes to protect and support the nutritional needs of both breastfed and non-breastfed infants and young children. Priority interventions include breastfeeding protection and support, minimising the risks of artificial feeding and enabling appropriate and safe complementary feeding.
| 8.2 | Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions | This includes blanket or targeted supplementary feeding for the prevention and treatment of moderate acute malnutrition (MAM) and therapeutic care for the treatment of severe acute malnutrition (SAM)
International Climate Finance (ICF) | 9.1 | Number of people supported to better adapt to the effects of climate change | https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/1139423/international-climate-finance-KPI_1_Methodology_Note_People_supported_to_adapt_to_the_effects_of_climate_change.pdf
* Priority Core Indicators

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Implementation Logframe: Impact indicator; outcome indicators; Output 1 indicator 1, Outputs 2-5 | Completion of impact indicator, outcome indicators and milestones, output 1, 2 (2023-2024), 3 and 4 indicators, milestones and weighting, output 5 indicators and milestone. | PRO and Eritrea PM | September 2023-May 2024
2 | Mobilisation Logframe | Achievements added to outputs | PRO | 2024-06-25
3 | Output 6, outcome indicator 1 milestones | Indicators added for new context (Madagascar); outcome indicator 1 milestones updated to include new context | Madagacar PM | 2024-09-24
4 | Output 7, impact statement, outcome indicator 1 miletsones | Impact statement updated following BC Addendum approval; Indicator added for new context (Sudan Regional); outcome indicator 1 milestones updated to include new context | Sudan Regional PM | 2024-12-05
5 | Impact indicator and targets | Impact indicator updated and target added | PRO | 2025-05-15
6 | Output 2 milestone 3 | Milestones added based on appeal for 2025 | PRO | 2025-05-15
7 | Outcome and Outputs | Achievements added for milestone 2 | PRO | 2025-05-15
8 | Output | Output weightings for milestone 3; implementing AR recommendations on output 1.2 and output 4 milestones gender targets removed. | PRO | 2025-06-26
9 | Output 4, new output indicators | New output added to reflect new health activitities and targets for remaining outputs adjusted in Y3/4 following change to scheduled funding dispersement. | Eritrea PM | 2025-07-29
10

## Guidance Notes (hidden)
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.