## Annual Review

Title: Africa Humanitarian Response Fund II (AHRF II)
Programme Value £ (full life): £92.5 million (£83.3m programmed, £9.2m remains in the Internal Risk Facility (IRF))		Review date: November 2025
Programme Code: 301381	AMP start date: 10/08/2023	AMP end date: 30/06/2027

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	A	A
Risk Rating	Severe	Severe	Severe

DevTracker Link to Business Case:	D0003594.odt (live.com)
DevTracker Link to results framework:	D0005378.xlsx (live.com)

A. SUMMARY AND OVERVIEW

Description of programme
The African Humanitarian Response Fund II (AHRF II) delivers quality humanitarian assistance in countries where the FCDO has no in-country humanitarian expertise or where a regional response is more suitable. It addresses severe humanitarian needs in areas where the UK has comparative advantages, prioritising life-saving assistance to vulnerable populations in protracted crises in Cameroon, the Central African Republic (CAR), Eritrea, and Madagascar, and enables responses to sudden onset or emerging crises. AHRF II also provides technical assistance, operational support, and preparedness, drawing on UK expertise and scientific evidence.

The annual review broadly covers the financial year from 1 April 2024 to 31 March 2025. However, some partners operated on different reporting cycles. The period covered for each project is set out in the output. The programme also initiated support to regional projects in response to the crises in eastern Democratic Republic of Congo (DRC) and Sudan, which will be assessed in the next annual review.

In February 2025, the UK government took the decision to reduce its Official Development Assistance (ODA) to the equivalent of 0.3% Gross National Income (GNI). As a result of this, it has been decided that the protracted crises supported under AHRF II will gradually close. This annual review has therefore had a particular focus on maximising the remainder of these projects, through ensuring the greatest impact, a responsible exit and generating learning.

Summary supporting narrative for the overall score in this review
Overall AHRF II has met or exceeded expectations across all but one output and therefore overall scored an ‘A’

	Output	Assessment	Score	Weighting
1	Responses improved by support to enabling actions and system reform	Output met expectations - technical assistance requests were followed up promptly with relevant requests supported and the AAP initiative in CAR has made good progress.	A	20%
2	Multisector humanitarian assistance provided to the populations affected by the conflict in Cameroon	Output significantly exceeded expectations – support provided met or exceeded in all areas with a significant overachievement on cash in a challenging context.	A+	15%
3	Multisector humanitarian assistance provided to the populations affected by the conflict in the Central African Republic	Output Met expectations – there were mixed achievements across the indicators but under achievements had a strong justification.	A	20%
4	Improving the delivery of integrated nutrition and sanitation services to children and women in Eritrea	Output moderately exceeded expectations – support provided met or exceeded expectations in all areas.	A+	15%
5	Humanitarian assistance provided to populations affected by cholera outbreak in Malawi, Zambia and Zimbabwe.	Output Met expectations – there were mixed achievements across the indicators with some areas significantly exceeding, but also some under achievements.	A	15%
6	Improving humanitarian resilience and preparedness in Madagascar.	Output moderately not met expectations - there were mixed achievements across indicators, including a significant underachievement on people reached for a new project in its inception.	B	15%

Major lessons and recommendations for the year ahead
- Given the decision to end support to protracted crises under AHRF II, FCDO should use the remaining programme period to ensure a responsible, well-managed exit from Cameroon, CAR, Eritrea, and Madagascar. This should include tailored exit strategies and direct monitoring for risk management and to ensure quality as projects complete. Clear plans for future monitoring of these fragile contexts and emerging crises across Africa.
- AHRF II has demonstrated that FCDO can deliver effective humanitarian assistance without in-country humanitarian capacity. However, this remote delivery model inherently limits FCDO’s ability to engage with and influence the broader humanitarian system which typically rely on sustained in-country presence and relationships. The Southern Africa Humanitarian Adviser role showed that regional positions can help mitigate these limitations by enabling greater engagement and influence. These constraints should be considered in future programme design, particularly where direct in-country presence is not feasible.
- As AHRF II shifts away from protracted crisis funding, FCDO should place greater strategic emphasis on the Operational Support, Technical Assistance and Preparedness (OSTAP) pillar. A clear strategy should be developed to guide its future role.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programmes theory of change, as well as impact and outcome indicators remain unchanged. Since the last annual review, AHRF II has added responses to the eastern DRC and Sudan regional crises, both responses fit within the existing framework.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
It is not yet appropriate to assess the programmes impact: Reduced suffering of vulnerable and crisis-affected populations across Sub-Saharan Africa. [% of people in need in SSA reached by humanitarian assistance (not FCDO attributable)]. A milestone of 43% has been agreed for 2025 onwards which will be reviewed in the next annual review. However, it is likely that the target will not be met following significant reductions in humanitarian assistance from the UK and other donors.

Outcome 1
Timely, proportional, and accountable response to affected populations. (this outcome relates to direct delivery attributable to the FCDO)
Outcome Indicator(s)		Milestone(s) for this review	Progress	Commentary
1.1	Number of people targeted by humanitarian emergency appeals reached by the programme	2,592,988	3,190,470	There is a significant over achievement. This is mainly due to the Southern Africa cholera response which included an urban centre response that enabled delivery of some activities to a greater number of people. But there was also underachievement’s in Madagascar with a new project that took time to mobilise and CAR where prioritisation towards protection activities meant a reduction in overall reach. This is explained in the respective outputs. / Substantially exceeded expectations

Outcome 2
Humanitarian actors deliver a more effective, principled, and inclusive humanitarian response. (this outcome relates to the wider humanitarian system e.g. AAP)
Outcome Indicator(s)		Milestone(s) for this review	Progress	Commentary
2.1	Evidence of FCDO funded TA support leading to improvements in humanitarian response	Contribution of FCDO funded TA leads to improvements in response. / Assessed through consideration of timeliness, relevance and effectiveness	Six deployments completed during this period: / Four deployments met or exceeded expectations in all areas. / One deployment didn’t meet expectations for timeliness. / One deployment didn’t meet expectations for effectiveness.	Deployments contributed meaningfully to strengthening coordination and preparedness capacities in priority countries. While relevance and timeliness were generally strong, effectiveness was mixed due to operational constraints and limited sustainability planning. / Met expectations

Summary of deployment scoring
Deployments in Angola (two), Benin, Madagascar, CAR, and Namibia addressed critical gaps in coordination, information management, and technical expertise. Most were well-timed and aligned with humanitarian needs, with several consultants delivering outputs that supported national systems and inter-agency planning. However, challenges such as delayed starts and weak institutional support affected the overall impact. In some cases, limited access to deployed personnel hindered efforts to fully understand the operating context and assess the deployment’s effectiveness.

Effectiveness was strongest where deployments were embedded within broader coordination structures or linked to anticipatory action planning. However, the absence of follow-on funding, succession planning, and measurable outcomes for affected populations limited the strategic value of some deployments. Despite these gaps, the deployments provided critical support to the UN system, enabling a more rapid scale-up of humanitarian responses.

FCDO deployed an experienced humanitarian adviser through Palladium, based in Pretoria and supporting humanitarian preparedness and responses in Southern Africa. The regional humanitarian adviser monitored the FCDO funded activities in Madagascar and Angola. She participated in the Regional Inter Agency Standing Committee (RIASCO), Humanitarian Country Team (HCT) as well as cluster and regional and donor meetings, technical working groups as well as dialogue with the Office for the Coordination of Humanitarian Affairs (OCHA) Regional Office. She contributed to supporting the humanitarian coordination system and identifying the gaps in the humanitarian needs caused by the compounded effects of multiple shocks, including cholera outbreaks. She provided humanitarian briefings and technical advice to the British High Commissions in the region. She contributed to FCDO HQ understanding of the different contexts to adjust our response strategy and FCDO influencing strategy.

FCDO recruited another experienced humanitarian adviser to provide technical assistance in the contexts of the Central African Republic and Cameroon, where he engaged with other donors, the Humanitarian Country Team and partners. He monitored the activities on the ground in both countries.

Previous Annual Review Recommendations

Recommendation	Progress
In order to adhere to newly introduced ICF guidance adopted by FCDO, which recognises humanitarian programmes working in countries that fall into the bottom 10% in terms of recognised climate vulnerability rankings contribute to ICF results, a review of activities and the AHRF II logframe to identify which results can be reported as ICF. This is especially important for Madagascar, where climate hazards drive humanitarian needs.	FCDO central climate team and Africa Programmes and Expertise (APEX) Climate Advisers have reviewed contexts covered by the ICF guidance. The project in Madagascar is majority ICF; Eritrea and CAR will count 30% as ICF. ICF results will be reported in the next commission. / Complete

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme remains highly relevant, if not more so, given escalating humanitarian needs in the region and widening gaps caused by severe global funding cuts. However, in light of the UK’s decision to reduce ODA to 0.3% of GNI, the protracted crises pillar will be discontinued. It is therefore essential to maximise the remaining implementation period to ensure a responsible exit and deliver sustainable results in affected contexts. At the same time, the programme must adapt to a resource-constrained environment by prioritising efficiency and targeting to achieve the greatest possible impact with available resources.

## C. DETAILED OUTPUT SCORING

Output Title	Responses improved by support to enabling actions and system reform
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 FCDO funded TA support provided in a timely and responsive way.	- Stand By Partnership requests responded to within 5 working days / - Engagement with Posts to identify strategic gaps the programme could support maintained	-45/47 Stand By Partnership requests were responded to within 5 working days. The two that took over five days were six and eight days and were due to gaps in the team. / -Engagement with Post was scaled up, particularly with the support of the Southern Africa Humanitarian Adviser. A more proactive approach was taken for some deployments with engagement on shaping ToRs. / Moderately exceeded expectations
1.2 Supported response in CAR implements AAP programmes and makes use of feedback to inform planning and implementation.	4 / Scoring methodology: / 1=No AAP system in place / 2=AAP system in place but not used to inform planning or implementation / 3=AAP system used to inform planning and implementation of response / 4= AAP system used to inform planning and implementation of response and AAP system regularly reviewed and updated. / (Weighted score across responses receiving AAP.)	4 – Good progress has been made in strengthening the foundations of the AAP system. UNICEF has highlighted that cash assistance is a recurring theme raised by communities, and this feedback has been used to inform the Humanitarian Response Plan (HRP). While this demonstrates that the system is being used to inform planning and implementation, further work is needed to translate positive engagement into clearer evidence of how feedback has tangibly influenced the response. / Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 has two components; the first component covers technical assistance covering FCDO’s support to Stand By Partnerships (SBP) surging expert capability into the UN. The second component covers an Accountability to Affected Populations (AAP) project in CAR through UNICEF. The AAP initiative in CAR is a system-wide approach designed to embed community-led feedback and complaint mechanisms into the humanitarian response, ensuring that crisis-affected populations are meaningfully involved in decisions that impact their lives.

The technical assistance component covers from 1 April 2024 to 31 March 2025. During this period, six out of 47 Stand By Partnership (SBP) requests were approved. Requests were rejected for a range of reasons, including a lack of alignment with FCDO strategic priorities and specific reservations to the proposed deployment. Some requests were also considered more appropriate for other programmes based on their geographic or thematic profile. All decisions are communicated back to the SBP team, explaining why the team will not fund a position and including other teams where relevant to consider support under their own business cases. Engagement with posts has improved since the last annual review, supported by the addition of a Humanitarian Adviser for Southern Africa within the APEX team, which has increased capacity and responsiveness. This engagement has supported the team to make decisions on SBP requests and ensure funding is not approved for positions that are not considered a priority. A more proactive approach was taken to deployments, moving beyond reactive approval of SBP requests to active engagement in shaping Terms of Reference for key positions, such as the Office for the Coordination of Humanitarian Affairs (OCHA) deployments in Angola and Madagascar. The component continues to function effectively, offering a cost-efficient mechanism for FCDO to support rapid UN surge capacity in Africa. However, in light of ongoing UN funding shortfalls and restructuring, it remains essential to apply decision-making criteria consistently to avoid inadvertently funding SBPs that are primarily intended to fill internal agency budget gaps.

During the review period (1 July 2024 – 30 June 2025) for the AAP project in CAR, the initiative reached over 63,000 individuals and collected nearly 16,000 feedback and complaints. Twenty community-led feedback centres were established, while steering committees composed of community leaders, youth, women, and persons with disabilities oversaw operations. The system-wide response mechanism grew to include 120 focal points from implementing organisations. There were positive outcomes on inclusion, with women and girls contributing 57% of feedback and complaints. However, participation from persons with disabilities remained low, at around 1%. While progress in implementing a system-wide approach in a difficult operating environment is commendable, key challenges persist, particularly ensuring the feedback loop is closed, with a low response rate (73.6%) and while some evidence has been shared of how feedback and complaints have influenced the response, there could be more detailed analysis of this. UNICEF is conducting an internal review of the initiative. FCDO should engage with this process and consider how learning can be applied to similar initiatives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Indicator 1.2 was amended following the last annual review to set the score target.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation	Progress
There is demand for technical assistance across the UN System but this pillar has scope to deliver much more across Africa. The FCDO programme team should consider what other opportunities there are to expand support under this pillar, for example supporting the delivery of the roll out of the Livingstone Principles curriculum.	Ongoing / There was engagement with FCDO’s Development Counsellor for the African Union (AU) to explore opportunities, as well as with UNHCR on the Livingstone syllabus. There was no concrete progress during this annual review period, however, discussions are ongoing and progress should be reported in the next annual review. / The current funding environment, as well as the UK’s decision to reduce aid spending to 0.3% GNI, have put an even greater emphasis on ensuring the humanitarian system is working as effectively as possible. FCDO should continue to explore opportunities beyond UN system.

Lessons learned:
- The addition of a Southern Africa Humanitarian Adviser enabled a more proactive and strategic approach to Standby Partnerships, including greater engagement in shaping deployments, which contributed to stronger outcomes. As this resource will not be available in future, FCDO will need to consider how best to balance competing demands with the benefits of deeper engagement in this area.
- The application of a system-wide approach to AAP is a notable achievement, offering affected populations a simpler way to engage with a complex humanitarian system. However, challenges in making this approach universal, including low response rates and limited NGO participation, and in translating engagement into meaningful changes in the response should not be underestimated. These insights should be considered in future AAP initiatives, particularly in contexts where FCDO may not have a direct role.
Recommendation:
FCDO should engage with UNICEF’s internal review of the initiative. However, in future, if FCDO supports system-wide efforts such as this, an external and independent review or evaluation should be promoted to ensure objectivity and credibility.
Output Title	Multisector humanitarian assistance provided to the populations affected by the conflict in the Cameroon
Output number:		2	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	Yes[1] ↓ (20%)
[1] Two additional outputs are being reviewed this year which has led to an adjustment in the previous outputs.

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of people receiving humanitarian assistance (all sectors included).	73,419	Total 84,420 / Female 21,572 / Male 18,339 / Children 44,509 / Moderately Exceeded Expectations
2.2 Number of people assisted by FCDO through cash, voucher and food.	Total 12,653 / Food 7,601 / Cash for work 5,052	Total 21,977 / Food 10,674 / Female 3,732 / Male 2,378 / Children 4,563 / Cash for work 11,303[2] / Female 3,418 / Male 3,055 / Children 4,830 / Substantially Exceeded Expectations
2.3 Number of people receiving food production assistance.	60,766	Total 62,443 / Female 14,421 / Male 12,906 / Children 35,116 / Met expectations
[2] Figures include whole household, not just direct recipient, with breakdown of males, females and children in households supported.

Briefly describe the output’s activities and provide supporting narrative for the score.
Cameroon continues to face a complex and protracted humanitarian crisis driven by conflicts in the Far North and North-West/South-West (NW/SW) regions, displacing hundreds of thousands of people. The operating environment is very challenging with significant barriers to access in respect of humanitarian principles In 2024, Cameroon was ranked the world’s most neglected displacement crisis by the Norwegian Refugee Council (NRC), reflecting the acute gap between needs and international attention.

FCDO supported the ICRC (January-December 2024) to reach over 84,000 people with assistance, including 21,977 through food and cash-based support and 62,443 through food production. The overall ICRC response also covered protection (protection of family links, detention visits) and other essential services (water and health infrastructure, mental health and psychosocial support, physical rehabilitation). Additionally, ICRC had considerable engagement with weapon bearers to promote the respect of International Humanitarian Law (IHL) and other norms. The ICRC remains one of the few actors with sustained access and acceptance across Cameroon’s most insecure regions. Its principled approach, operational reach, and protection mandate are critical in a context where humanitarian needs are rising and funding is shrinking.

The programme met or exceeded all indicator targets despite the challenging operating environment, hence, a score of A+ has been awarded for this output.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to the output since the last annual review. When the 2026 appeal is published at the end of the year the targets will be added to milestone 5 and the final project target.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned:
- In a highly challenging operating environment, and in the absence of FCDO humanitarian capacity in-country, supporting a principled actor such as the ICRC has proven to be an effective approach to supporting humanitarian assistance. The ICRC has demonstrated strong operational capability, particularly in negotiating access without compromising humanitarian principles.
- FCDO’s ability to influence the humanitarian system in Cameroon has been limited, reflecting both the absence of in-country humanitarian capacity and longstanding challenges within the response architecture. In such contexts, it is important that the UK’s strategic ambition to shape the humanitarian system is proportionate to its operational presence, technical capacity and available resources. This ensures that expectations remain realistic and that engagement is targeted where it can have the greatest impact.
Output Title	Multisector humanitarian assistance provided to the populations affected by the conflict in the Central African Republic (CAR)
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes ↓ (40%)

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of people receiving humanitarian assistance (all sectors included)	266,934	Total 218,358 / Female 123,995 / Male 94,363 / Moderately not met expectations
3.3 Number of Healthcare Consultations Provided	Total 166,565 / Female over 5 40,228 / Male over 5 24,121 / Female under 5 49,826 / Male under 5 52,390	Total 163,891 / Female over 5 38,252 / Male over 5 25,969 / Female under 5 51,036 / Male under 5 48,634 / Met expectations
3.4 Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions.	9,204	18,085 / Substantially exceeded expectations
3.5 Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions.	2,681	2,061 / Substantially not met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
The humanitarian crisis in CAR stems from over a decade of armed conflict, political instability, and chronic underdevelopment. Currently, 38% of the population are in need of humanitarian assistance, with widespread displacement, food insecurity, and protection risks exacerbated by poor infrastructure and limited access to basic services. Despite the challenging context, the humanitarian system is working well with robust leadership from successive Resident Coordinator/Humanitarian Coordinator (RCHC’s) and strong coordination from OCHA.

Indicator 3.1: In 2024, FCDO continued to support the CAR Humanitarian Fund (CHF) with a contribution of $3.8 million, representing approximately 23% of total donor funding of $18.5m. The CHF played a key role in responding to various emergencies and had a strong protection focus with a particular emphasis on Gender Based Violence (GBV) prevention and child protection. Considerable progress was made on localisation with 30% of funding channelled directly to national NGOs, up from 20% in 2023 and 7% in 2022, including targeted support for women-led organisations. The significant increase in funding to local actors has been complemented with capacity strengthening and sharing initiatives, active cluster participation and robust risk management to ensure the scale up is responsible and sustainable.

Indicator 3.1, 3.3-3.5: The FCDO-funded consortium, led by the MENTOR Initiative and including ACF, reached over 569,000 people with integrated health, nutrition, WASH, and GBV services between 1 January – 31 December 2024. The project met expectations for Indicator 3.3, delivering 163,891 curative consultations and Indicator 3.4 (malnutrition prevention) was significantly overachieved. However, Indicator 3.5 (malnutrition treatment) underperformed due to a change in national protocols: the Ministry of Health did not adopt community-based management of Severe Acute Malnutrition (SAM) as originally planned. As a result, treatment was only provided at primary health care facilities, limiting reach and coverage.

The output has been scored as an A despite significant underachievement on two indicators, due to clear and justified mitigation in both cases. Indicator 3.1 underachieved, with the CHF component reaching 54,467 beneficiaries against a target of 100,369. This shortfall is attributed to a strong emphasis on localisation, protection activities and targeting hard to reach communities, which are more resource-intensive and should be supported, as well as an adjustment to CHF calculations to try and avoid double counting across clusters. Indicator 3.5 also underachieved, as noted above, due to changes in national protocols.

While the context in CAR has relatively stabilised, it remains a very fragile context with a heavy dependence on humanitarian assistance. FCDO have taken the decision to end funding in 2026 which will allow sufficient time for a gradual reduction in funding to CHF. The CHF has been performing well, particularly on localisation, and efforts should be made for a responsible exit. FCDO was the second largest donor to CHF in 2024, but there were eight other institutional donors providing funding which provides some mitigation to the risk of FCDO’s exit. Funding for the MENTOR initiative already ended, as planned, at the end of 2024.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to the output since the last annual review. Following approval to continue support in CAR for 2025 additional targets should be added for milestone 5.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned:
- FCDO’s ability to influence the humanitarian system in CAR was constrained during the review period, with only one field visit conducted. Limited access, including restrictions on travel outside Bangui, has reduced opportunities for direct engagement and relationship-building, particularly in comparison to other donors and agencies operating in-country.
- In this context, the CHF has proven to be an effective channel for UK support. It enables actors with deeper contextual knowledge to prioritise resources based on need, while maintaining alignment with UK humanitarian objectives. The CHF’s strong focus on localisation has allowed FCDO to indirectly support national and local actors in a way that would have been difficult to achieve directly. Its recognition as a high-performing Country Based Pooled Fund (CBPF) reflects both the strength of the humanitarian system in CAR and provides a mechanism through which FCDO can acknowledge and reinforce effective system leadership.
- The MENTOR consortium has evolved over time, with changes in NGO membership. Previously, its diverse geographic and thematic strengths enabled a complementary approach that maximised impact. With the consortium now reduced to two members, the project continued to deliver strong results, but the added value of a multi-partner model is less evident. The consortium model remains a useful mechanism for channelling funding to NGOs. However, sustaining an effective consortium requires a significant level of engagement and support, particularly challenging in contexts like CAR, where there is no in-country FCDO humanitarian capacity.

Output Title	Improving the delivery of integrated nutrition and sanitation services to children, and women in Eritrea
Output number:		4	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	Yes ↓ (20%)

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of people receiving humanitarian assistance.	310,000	325,367 / Met Expectations
4.2 Number of children under five, pregnant and lactating women reached through malnutrition treatment interventions.	GAM[3] 9,370 / SAM 4,000 / MAM 5,370	GAM 10,911 / SAM 5,471 / MAM 5,370 / Moderately Exceeded Expectations
4.3 Number of children under five, pregnant and lactating women reached through malnutrition prevention interventions.	Pregnant & lactating women receiving iron folic acid supplements: 50,000 / Children receiving Vit A: 343,200 / Number of primary caregivers counselled for MIYCF[4]: 80,000	60,824 pregnant & lactating women received iron & folic acid tablets to prevent anaemia & low birth weight / 464,608 children aged 6 to 59 months received vitamin A supplementation. / 88,933 primary caregivers & mothers were counselled for maternal infant & young child feeding (MIYCF). / Substantially Exceeded Expectations
4.4 Number of individuals reached with sanitation activities.	30,000	42,268 / Substantially Exceeded Expectations
[3] Author note: GAM = Global Acute Malnutrition, SAM = Severe Acute Malnutrition and MAM = Moderate Acute Malnutrition
[4] Author note: MIYCF = Maternal, Infant and Young Child Feeding campaign

Briefly describe the output’s activities and provide supporting narrative for the score.
Eritrea remains a challenging operating context, with heavy restrictions on access, no NGO presence, and extremely limited data (the last Demographic and Health Survey was conducted in 2010 – a new survey is currently being conducted and activities should be reviewed when it is released). Despite the lack of verifiable information, FCDO’s partnership with UNICEF and monitoring visits confirm significant needs.

FCDO has maintained a longstanding partnership with UNICEF in Eritrea, which supports life-saving nutrition interventions targeting children and women in remote and vulnerable communities. The programme delivers integrated nutrition and WASH services across all six Zobas (regions), encompassing curative, preventive, and promotive nutrition activities, hygiene promotion, sanitation support, and health worker capacity building. Between April 2024 and March 2025, the programme reached 325,367 beneficiaries[5], exceeding targets across all output indicators. A key outcome of the project is to reduce acute malnutrition rates, however, the acute malnutrition rate stood at 10.8%, which is slightly above the 10% target. FCDO observed strong hygiene promotion coverage during site visits, but some concerns were noted around latrine quality and raised with the partner. The programme exceeded all indicator targets, including two which substantially exceeded expectations, therefore a score of A+ has been awarded for this output.
[5] Children reached with Vitamin A not factored into this number, as despite positive impact it is a less intensive intervention

Beyond direct service delivery, the partnership with UNICEF has enabled FCDO to support one of the few international development actors operating in Eritrea, ensuring continued presence and operational capacity in a highly restricted environment. It has also provided FCDO with critical insights into the critical needs, positioning the UK to respond effectively should conditions deteriorate. With the decision for AHRF II to exit Eritrea, driven by the decision to reduce ODA to 0.3% of GNI, FCDO will need to consider how best to maintain engagement and situational awareness.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Indicators 4.2 and 4.4 were amended following the last annual review to remove the gender disaggregation.

Following a joint monitoring visit in December 2024, which included visits to zoba and community hospitals, it was agreed to expand health activities conducted under the programme and provide critical antenatal health care equipment via central UNICEF procurement routes e.g. incubators. Two new Output Indictors have been added to the logframe and milestones agreed. [4.5 Number of healthcare consultations provided and 4.6 Number of health facilities supported - Neonatal Intensive Care Units (NICU) and Emergency Obstetric and Newborn Care (EmONC) centres]

Agreement was reached to reprofile the budget to allow for procurement of health equipment in 2025/26 and bring forward final year budget to encourage prompt utilisation before implementation period concludes. Nutrition reach milestones for outer year have been adjusted.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendation	Progress
Supportive supervision visits by Ministry of Health - accompanied by UNICEF - should continue as much as possible and be documented as part of regular reporting to FCDO.	Partially implemented. A joint FCDO–UNICEF monitoring visit to Debub region took place in December 2024, with additional visits to Gash Barka and Anseba. Access remains a challenge, with only five Ministry of Health-approved visits in 2024. UNICEF is exploring multi-sector monitoring and developing checklists to improve efficiency.

Lessons learned:
FCDO’s longstanding partnership with UNICEF, and its indirect engagement with the Ministry of Health, has helped build a good understanding of the humanitarian situation in Eritrea. This would have been difficult to achieve given the severe data limitations and restricted access. The experience highlights the broader value of investing in long-term relationships with trusted partners, which can support both programme delivery and situational awareness in complex operating environments.

Output Title	Humanitarian assistance provided to populations affected by cholera outbreak in Malawi, Zambia and Zimbabwe.
Output number:		5	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A, new output

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of people receiving humanitarian assistance	1,700,000	2,427,092[6] / Female under 18 769,943 / Female over 18 568,904 / Male under 18 580,033 / Female over 18 502,632 / Substantially exceeded expectations
5.2 Number of health workers trained	1,400	2,925 / Substantially exceeded expectations
5.3 Number of health facilities supported	145	71 / Substantially not met expectations
5.4 Number of Individuals reached with hygiene activities	1,700,000	2,427,092 / Female under 18 769,943 / Female over 18 568,904 / Male under 18 580,033 / Female over 18 502,632 / Substantially exceeded expectations
5.5 Number of water points (new, rehabilitated or upgraded) and providing access to safe water supply for the affected communities	200	128 / Substantially not met expectations
[6] Disaggregation included, except for 5,580 beneficiaries in Malawi

Briefly describe the output’s activities and provide supporting narrative for the score.
Between late 2023 and mid-2024, Southern Africa experienced one of its most severe cholera outbreaks in recent years, affecting Zambia, Zimbabwe, Malawi, Mozambique and Angola. The crisis was compounded by climate shocks, including droughts, floods, and cyclones, that disrupted water and sanitation infrastructure, which were already suffering from underinvestment, and heightened vulnerability in already fragile communities. Cross-border transmission, poor sanitation, and limited access to safe water were key drivers of the outbreak.

FCDO funding, channelled through the British Red Cross and IFRC, supported a coordinated response across Zambia, Zimbabwe, and Malawi. FCDO closely monitored the situation from the outset of the outbreak and began exploring a possible response in late 2023, but internal decision-making delays meant the funding agreement was only signed at the end of February 2024 (and ran until 31 December 2024). This delay impacted timeliness, with the peak of the epidemic curve already passed by the time implementation began. As a result, the programme pivoted from outbreak response to preparedness for future epidemics. Despite this shift the number of people reached through humanitarian assistance and hygiene activities, as well as number of health workers trained, substantially exceeded targets (for people reached, this is largely attributable to Zambia where the response was focused in Lusaka). However, indicators for the number of health facilities and water points fell short. The partner managed to continue to utilise Oral Rehydration Points (ORPs) which had been provided by other donors previously reducing the need for additional health facilities, and enabling efficiency gains. Water point costs were found to be more expensive however; this was an important activity to ensure communities have safe access to water and reduce the risk of further outbreaks. However, the challenges were not communicated quickly enough to enable re-prioritisation. Monitoring visits found the programme well implemented, with general consensus that the partner performed strongly. The output has been scored as A due to substantial overperformance against most indicators but, noting the underperformance on the water points indicator.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This was a new response mobilised in the last annual review period with the output, indicators and targets added. There are no changes planned, this response has now completed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is a new output, so there were no previous recommendations.

Lessons learned:
- Timeliness is critical in outbreak response, effective action requires rapid decision-making. Delays can significantly reduce the impact of interventions and limit opportunities to contain disease spread. This response highlighted limitations within FCDO systems to meet the speed of decision-making required. With the reduction in ODA to 0.3%, which raises the threshold for engagement, such challenges are likely to become more pronounced.
- IFRC emergency appeals offer a flexible and effective funding mechanism. They enable rapid mobilisation of reliable partners and allow for adaptation as the situation evolves. In this case, the ability to pivot from outbreak response to future prevention was a key strength. However, IFRC’s operational capacity varies by country and should be carefully assessed when determining the suitability of this mechanism for specific responses.

Output Title	Improving humanitarian resilience and preparedness in Madagascar.
Output number:		6	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	N/A, new output

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number of people benefiting from humanitarian aid (all sectors combined)	Total 242,635 / Female (over 18) 60,659 / Male (over 18) 60,659 / Female (under 18) 60,659 / Male (under 18) 60,659 / Disabled 14,558	Total 135,233 / Female (over 18) 34,609 / Male (over 18) 31,022 / Female (under 18) 36,145 / Male (under 18) 33,457 / Disabled 20,283 / Substantially not met expectations
6.2 # of integrated multi-sectoral action plans developed and implemented, including Protection, Gender and Inclusion (PGI) and Prevention of and Protection against Sexual Exploitation and Abuse (PSEA)	8	12 / Substantially exceeded expectations
6.3 # of people made aware of the early warning system (EWS)	Total 56,760 / Female (over 18) 14,190 / Male (over 18) 14,190 Female (under 18) 14,190 / Male (under 18) 14,190 / Disabled 3,406	Total 67,221 / Female (over 18) 17,958 / Male (over 18) 16,040 / Female (under 18) 15,775 / Male (under 18) 13,643 / Disabled 3,805 / Moderately exceeded expectations
6.4 # of action plans developed and implemented following the Branch Organizational Capacity Assessment (BOCA) exercise exceeding 50% completion	2	0 / Substantial not met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.
Madagascar is a vast, sparsely populated country highly exposed to multiple hazards including cyclones, floods and droughts. Physical access to communities is extremely limited, especially post-disaster, making the Malagasy Red Cross Society (MRCS) a critical actor due to its extensive volunteer network and auxiliary role. Despite past institutional challenges, MRCS is rebuilding, and FCDO has supported this recovery, recognising its strategic importance in a fragile and under-resourced environment.

The agreement was signed with the Red Cross in July 2024 with an initial inception phase until December 2024 with the results covering until 31 March 2025. The programme reached over 135,000 people across 12 fokontany (villages) in Toliara and Morondava by improving household disaster preparedness through awareness campaigns and early warning systems and development of 12 community action plans. MRCS strengthened its institutional capacity through staff training, strategic planning, and partnerships with government and meteorological services. Activation of the crisis modifier for Cyclones Dikeledi, Honde, and Jude, enabled emergency response to over 110,000 people. However, while one crisis modifier activation met timeliness standards (Anticipatory Actions for Tropical Cyclone Dikeledi), the other activation (Tropical Cyclones Honde and Jude) fell short, prompting SOP revisions. Despite these achievements, the programme substantially underperformed against its target for total people reached (135,232 vs. 242,635), primarily due to delays in implementation, as well as challenges in crisis response timeliness. Additionally, although Branch Organizational Capacity Assessment (BOCA) exercises were conducted in two regions with two action plans developed, the implementation hadn’t yet started. Due to these underachievement’s and delays a score of B has been awarded for this output.

With no follow-on programme planned and a reduced Year 3 budget due to the UK’s ODA cut to 0.3% of GNI, FCDO and Red Cross partners must now focus on maximising impact of the remainder of the programme. Priority should be given to strengthening MRCS’s institutional capacity and local and national response capacities under Outcomes 2 and 3 to ensure long-term, sustainable gains are made from the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This was a new response mobilised in the last annual review period with the output, indicators and targets added.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This is a new output, so there were no previous recommendations.

Lessons Learned
The Enhanced Vulnerability and Capacity Assessments (EVCA) tool were revised to incorporate climate science and assess future and changing disaster risk. The new tool, the EVCA–Climate Change and Adaptation (EVCA-CCA), was designed in collaboration with the Red Cross Climate Centre, fostering collaboration within the IFRC network. Beyond the direct impact in Madagascar, the Red Cross is planning to roll out the tool at the global level. Effectively, the programme in Madagascar has worked as a successful pilot and is changing the way they carry out vulnerability and disaster risk assessments worldwide.

Recommendations
The Malagasy Red Cross Society (MRCS) should address delays in emergency response and ensure that preparedness investments translate into timely delivery. This includes finalising and operationalising revised Crisis Modifier Standard Operating Procedures (SOPs).

D: VALUE FOR MONEY

Key cost drivers and performance
Key cost drivers across AHRF II include the delivery model, operating context and strategic focus of each partner. Costs were highest in contexts prioritising localisation and protection, such as CHF in CAR, and in facility-based service delivery, as seen with MENTOR’s health consultations. Partners operating in more integrated way with national systems, such as UNICEF in Eritrea, maintained low unit costs. Performance varied accordingly, with cost increases generally reflecting justified shifts in strategy or context rather than inefficiency.

VfM performance compared to the original VfM proposition in the business case
Economy: Performance under the economy dimension varied across partners and contexts. MENTOR in CAR improved its cost per beneficiary to £18.22, but cost per consultation rose significantly (£5.80 in Ouham Pende/Alindao and £29.67 at Alindao District Hospital) reflecting the higher costs of facility-based care and changes in national health protocols. ICRC in Cameroon reported a cost per beneficiary of £35.54, slightly down from last year but still above baseline, justified by its unique access and operational reach in insecure regions. CHF in CAR saw a sharp increase to £55.08 per beneficiary, driven by a strategic shift toward localisation and protection-focused programming. UNICEF in Eritrea maintained strong cost-efficiency at £3.07 per beneficiary, while IFRC in Madagascar reported £9.96, reasonable given the geographic and operational challenges. While some unit costs increased, these reflect strategic choices and contextual constraints rather than inefficiency.

Efficiency metrics show progress in localisation, with CHF increasing funding to national NGOs from the baseline of 7%, and last year’s figure of 20%, to 30%, exceeding the international target. However, operational costs for CHF rose to 9.02%, approaching the 10% ceiling, although understandable given the investment in localisation. Crisis modifier responsiveness in Madagascar met the 50% target, but delays in some activations suggest room for improvement.

In terms of effectiveness, UNICEF in Eritrea didn’t meet the target for under-five acute malnutrition prevalence (10.8% vs. 10%), but there was improvement from the baseline of 12.3%. IFRC in Madagascar exceeded its training targets, with 163 participants improving emergency management skills, and 50% applying them during real interventions, meeting the target.

Equity indicators show strong geographic coverage (100% of zobas in Eritrea) and sustained presence in priority regions in Cameroon. However, the AAP programme in CAR saw a decline in participation from persons with disabilities (1% vs. 14% in the previous year), highlighting a need for more inclusive engagement strategies.

Assessment of whether the programme continues to represent value for money
Overall, the programme continues to represent good value for money in several areas, particularly in localisation, strategic partnerships, and cost-efficiency in constrained environments. There were significant increases in some of the economy indicators but with strong justification and should not be considered a reflection on the value for money. The significant reduction in the participation from persons with disabilities in the AAP initiative in CAR is a concern and should be reviewed during the next annual review.

E: RISK

Overview of risk management
The programme’s risk level remains severe due to the high residual risks associated with its activities, but within business case appetite. The programme continues to have an eager appetite for policy and programme delivery, strategy, and external context risks, reflecting the fragile security situation in many of the countries supported. Partners lead on managing key risks, including delivery and staff safety.

The programme maintains a receptive appetite for safeguarding risks, enforcing zero tolerance for inaction or mishandling of SEAH incidents. Partners are required to monitor, report, and respond robustly, with AAP mechanisms integrated to support beneficiary feedback and identify social safeguarding concerns.

A receptive appetite remains in place for fiduciary risks, recognising the potential for small-scale aid diversion or loss. Partners must report and address any incidents of fraud, diversion, or corruption immediately and pursue recovery where necessary.

Reputational risks are also managed within a receptive appetite, given the potential impact of fiduciary and safeguarding issues. These are mitigated through robust procedures, though risks remain if FCDO fails to respond promptly to emerging or protracted crises, particularly in the context of budget reductions.

The programme’s appetite for people risks related to FCDO capacity has been revised from receptive to cautious, reflecting concerns about resourcing as the programme enters later stages. While all contexts have been monitored to date, future field visits may be constrained by security and staffing challenges. Staff safety continues to be prioritised, with training, security support, and thorough assessments in place ahead of field missions.

All severe or above-appetite risks have been escalated to senior leadership in the Africa Programmes and Expertise Department (APEX). No new risks were escalated during this annual review period. The team have been working with the partner to increase controls and reduce this risk.

The Programme Team continues to maintain a detailed, regularly updated risk register, and partner risk management is monitored through Due Diligence Assessments (DDAs) and recommendations have been followed up through regular partner engagement. Partners must also provide delivery chain information to support risk mapping.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
By 31 March 2025, AHRF II had disbursed £46.7 million across all three pillars. Support has continued through the technical assistance and operations support in Africa. Humanitarian responses receiving support to date are: CAR, Cameroon, Eritrea, Madagascar, a cholera response in southern Africa, and responses to the regions affected by the Sudan conflict and eastern DRC conflict.

Operational Support, Technical Assistance and Preparedness
UNICEF in CAR continues to deliver the system-wide Accountability to Affected Populations (AAP) project through a Contribution Agreement. The UNICEF CAR Country Office maintained a 100% completion rate for mandatory Prevention of Sexual Exploitation and Abuse (PSEA) training among staff, consultants, and volunteers. Additionally, 1,569 staff from UN agencies, MINUSCA, international and national NGOs, service providers, vendors, construction firms and the CAR Government were trained on PSEA basics and reporting mechanisms, almost double the number achieved in the previous period. Three partners were continued to deliver the AAP project in this period, with no assets procured. Partners were assessed for PSEA capability and ensuring all due diligence requirements. Partner engagement has been good with timely reporting on progress, risk, value for money, and demonstrating the utilisation of funds through commitment and expenditure rates. Further detail on the impact of the FCDO support could be included in progress reporting.

Technical Assistance for FCDO or UN partners through the HEROS contract[7] and for the Standby Partnership positions through Accountable Grant agreements with four NGOs are managed through central agreements with the FCDO Humanitarian Department.
[7] DevTracker Programme GB-1-205176

Central African Republic (CAR)
The CAR Humanitarian Fund (CHF) remains a high-performing fund, with FCDO’s contribution managed through a Memorandum of Understanding (MoU) to contribute to their pooled funds for allocations. Reporting was delivered on time following the standard Humanitarian Fund templates and demonstrated utilisation of funds. Data is also available throughout the year on the Country Based Pooled Funds Data Hub. All assets are managed and disposed of according to UN rules and regulations. The CHF conducted training for 71 NGOs (27% INGO partners, 34% NNGO partners and 39% NNGOs who are not yet partners of the CHF), 923 people. Training focused on Humanitarian Access, Prevention of Fraud and Misconduct, PSEA, project management including Financial Management, Communication, and AAP. CHF monitoring of partners was also maintained with 146 field visits; financial verifications with 33 partners; audits commenced for 70 projects.

The health consortium, led by the MENTOR Initiative was funded through an Accountable Grant with funding provided in advance for MENTOR and in arrears for their consortium partner. This project has now completed and a utilisation of 98% achieved at the end of the project. Reporting followed the agreed template and was received throughout the project with any small delays in submission discussed with the FCDO in advance and clarifications have been responded to clearly by the partner. The consortium partner invested significant time on safeguarding over the final year of the project with updated training completed for staff and service providers. Consortium assets are recorded in a register shared with FCDO, detailing asset number, description, location, responsible person, value, purchase date, expected lifespan, and condition. A remote asset spot-check using date-stamped photos was conducted in early 2024. Asset disposal is being finalised.

Cameroon
Support in Cameroon is provided in the Far North and North-West/South-West regions through an MoU with the International Committee of the Red Cross (ICRC), with FCDO funding contributing to ICRC’s Yaoundé Regional Appeal. The ICRC continues to deliver humanitarian assistance in Cameroon with operations split 40% in Northwest/Southwest (NW/SW) and 60% in the Far North. Narrative reporting has been timely and generally strong, though greater clarity on disaggregated beneficiary data and outcome-level indicators would improve transparency. PSEA remains a priority, with a reported 100% staff training completion rate. Financial reporting shows timely commitment of funds. All assets are owned by ICRC, procured through their Geneva headquarters, and managed according to ICRC policies and procedures

Eritrea
UNICEF in Eritrea continued delivering humanitarian assistance through a Contribution Agreement, working closely with Eritrean government line ministries as downstream partners. Narrative reporting against this contribution has been submitted to agreed deadlines and the partner has responded to feedback clearly, with any requests for additional detail provided in a timely manner. The partner remains unable to include sex, age and disability disaggregated data in reporting, however advocacy around changes to government Health Information Systems to allow this to be extracted is ongoing. Financial reporting has shown timely commitment of funds, however reported spend levels continues to indicate slow utilisation by downstream partners. UNICEF is working closely with downstream partners to rectify, following agreed joint government-UNICEF delivery plans. Although no assets have been purchased during this reporting period, an expansion in health activities from July 2025 onwards will result in assets being acquired in the next reporting period. Those assets will be purchased through UNICEF central procurement mechanisms and as per the FCDO-UNICEF Framework Agreement, considered as owned by UNICEF/ governed by UNICEF’s own asset policies. UNICEF has maintained a 100% completion rate for staff safeguarding training (last reported in writing May 2025).

Southern Africa Cholera response
A regional response to a cholera outbreak was mobilised in February 2024, funding the International Federation of the Red Cross and Red Crescent Societies (IFRC) emergency appeals covering Malawi, Zambia, and Zimbabwe through an MoU with the British Red Cross (BRC). The IFRC Zimbabwe cluster office manages the response and funding to national societies, confirming 100% completion of PSEA and child safeguarding training, with AAP mechanisms in place in each country, although some gaps in communication of the AAP mechanisms were identified in some areas there was also clear demonstration that feedback mechanisms were utilised in all countries. All assets will be managed and disposed of according to partner policies. Final financial reports confirmed 99.97% utilisation of funds. Final pledge reports were received but, final appeal reports were delayed, as a result there was a misunderstanding of the results attributed to the FCDO initially.

Madagascar
The Malagasy Red Cross Society (MRCS), with the BRC as grant holder and IFRC as the main supporting organisation, began delivery of a new preparedness and resilience project in Madagascar in July 2024, initiating an inception phase that ran until December 2024. Full implementation began in January 2025, aligning with the start of Year 2 activities. Given the project’s focus on community preparedness and humanitarian response, the integration of PSEA was a priority from the outset. During inception, PSEA was integrated into community planning processes, and 100% of programme staff completed mandatory safeguarding training. To strengthen accountability and feedback systems, the MRCS externalised its Community Engagement and Accountability (CEA) function to a specialist local non-governmental organisation. Asset management systems were established and a comprehensive Asset Register is in place. In line with the Accountable Grant Agreement, the FCDO retains ownership of all assets. The crisis modifier was activated twice (Cyclones Dikeledi and Honde/Jude), with some delays in mobilisation and gaps in response coordination. These experiences have informed plans to revise the Standard Operating Procedures (SOPs), with a focus on clearer activation triggers and improved timeliness. Financial forecasting and reporting improved following the appointment of a Finance Manager, though Year 1 budget absorption was low due to procurement delays and crisis response bottlenecks. Narrative reporting has been timely and generally strong. BRC has responded to feedback constructively, with requests for additional detail addressed promptly. Continued collaboration is underway to improve clarity on disaggregated beneficiary data and outcome-level indicators. As implementation continues efforts are focused on improving budget absorption and operational efficiency.

Two new partnerships below were mobilising towards the end of the review period for this annual review. Their performance will be assessed in future reviews.

Sudan Regional
The Sudan Regional response was mobilised in November 2024 and is managed through Education Cannot Wait (ECW). FCDO provides funding to ECW, via a standard contribution agreement held by UNICEF’s Funds Support Office (FSO). ECW’s Secretariat works alongside the FSO to issue and oversee grants at the country and global level, with ECW acting as the Grant Agent that sub-contracts other downstream grantees. The contribution from FCDO will be pooled with funds from other sources, with some earmarking to the specific countries affected by the conflict in Sudan. It will follow the regular approval procedures through ECW governance boards and results will be reported through the 2025 ECW Annual Results Report (released mid-2026). FCDO's due diligence confirmed that ECW, as implementing partner, is subject to UNICEF’s robust financial, logistical, and fraud management controls, with annual re-assessment and prompt investigation of any misuse. All partners undergo HACT (Harmonised Approach to Cash Transfers) and PSEA assessments. FCDO’s contribution of £14m across eight countries has been fully committed. All assets will be managed and disposed of in accordance with UNICEF’s policies and procedures.

DRC Regional
Following the outbreak of conflict in eastern DRC, the AHRF II mobilised support for the DRC Regional Response delivered through a partnership with UNHCR to support its preparedness and response to displacement in the Democratic Republic of the Congo and refugees in neighbouring countries. FCDO’s £5.3m contribution is for the period March to December 2025. Stringent financial management and governance measures are applied through operating under UNHCR’s financial rules and regulations. UNHCR is required to regularly assess the internal controls and systems of its downstream partners before and during implementation, ensuring they can manage funds, deliver outputs, and comply with relevant regulations. A due diligence assessment has been completed. All assets procured are managed under UNHCR’s policies, with UK aid visibility provided where feasible and appropriate, subject to safety and security considerations.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
The programme team, based in the UK and South Africa, includes at least one field visit a year to each context as a control measure due to the programme’s high risk. Between April 2024 and March 2025, FCDO conducted eight visits including one visit to each of the contexts targeted, see table below for full details:

Date	Location	Purpose	Who
June 2024	Angola	Joint donor visit to drought affected areas in the south/south east	HA
November 2024	Zimbabwe	Cholera response monitoring and due diligence assessment	PRO and PM
December 2024	Madagascar	Partner and programme monitoring ahead of cyclone season	HA and PM
December 2024	Eritrea	Partner monitoring	SRO and PM
January 2025	South Africa	Regional Humanitarian Adviser Meeting	SRO and HA
February 2025	CAR (Bangui, Obo, Kaga Bandoro)	Partner monitoring and discussions with other donors	HA
March 2025	Cameroon (Yaoundé and Buea)	Partner monitoring	HA
March 2025	Uganda	Monitoring Sudan Regional response	PM

In addition, FCDO monitored remotely through partner meetings and reporting reviews to stay informed about evolving contexts, delivery challenges, and to reinforce reporting requirements, especially regarding risks such as fraud or safeguarding.

The FCDO programme team holds monthly meetings, chaired by the Programme Responsible Owner (PRO) and attended by the SRO, Humanitarian Advisers (HA), and Programme Managers (PM), to monitor programme delivery and address emerging risks or issues.

The first draft of this annual review was prepared by a Humanitarian Adviser in the APEX team through discussions with partners, the programme team and review of partner reports. The programme team then reviewed and finalised the report.

Evidence, Evaluation and Learning
UNICEF is currently conducting a review of the Accountability to Affected Populations (AAP) initiative in CAR, which FCDO will follow and use to inform future engagement. In addition, the programme team plans to undertake a lessons learned exercise on the crisis modifier activation in Madagascar to assess its effectiveness and identify opportunities to strengthen future rapid response mechanisms.

The previous Annual Review recommendations concerning monitoring were as follows:

Recommendation	Progress
The programme team have conducted or planned monitoring visits to all supported contexts. These visits are vital for risk management, ensuring activity relevance and quality, and assessing impact on vulnerable populations. In a reduced ODA environment, these visits will also be used to carefully consider prioritisation and timing of interventions and assess the robustness of in-country humanitarian operations. The FCDO team should continue annual monitoring visits to each context, supplemented with regular remote engagement, and use third-party monitoring where appropriate and feasible are unable to gain access to a context or if we do not have the capacity.	Annual monitoring visits were conducted for all contexts; Cameroon, CAR, Eritrea, Madagascar, SA cholera (Zimbabwe). The in-country visits were complemented with regular partner engagement. Third-party monitoring was not required. / Ongoing and remains a priority

Partner Reporting

	Organisation	Report receipt date
Date of receipt for last narrative financial report(s)	CAR – CHF	28 April 2025
	CAR – MENTOR Consortium	30 June 2025
	CAR – UNICEF	16 July 2025
	Cameroon – ICRC	1 July 2025
	Eritrea - UNICEF	14 May 2025 narrative / 16 June 2025 financial
	Madagascar - BRC	31 July 2025
	Southern Africa Cholera - BRC	30 May 2025
Date of last audited annual statement(s)	CAR – CHF	6 November 2025 (2024)
	CAR – MENTOR	31 March 2025 (Oct 2023-Sept 2024)
	CAR – UNICEF	10 November 2025 (2024)
	Cameroon – ICRC	14 May 2025
	Eritrea - UNICEF	10 November 2025 (2024)
	Madagascar - BRC	7 May 2025 (2024)
	Southern Africa Cholera - BRC	7 May 2025 (2024)

H: Annex 1 – Value for Money Framework
	VFM Metric	Partner	Baseline/target	Progress (FY2023/24)	Progress / (FY2024/25)
Economy	Cost per beneficiary	CHF (CAR)	Baseline: £26.64	£19.70	£55.08
		MENTOR (CAR)	Baseline: £19.12	£21.10	£18.22
		WFP (CAR)	New partner	£15.62
		ICRC (Cameroon)	Baseline: £27.59	£36.86	£35.54
		UNICEF (Eritrea)	Baseline: £3.11	£3.14	£3.07
		IFRC (Southern Africa Cholera)	New partner		£2.41
		IFRC (Madagascar	New partner		£9.96
	Total cost per child treated for Global Acute Malnutrition (GAM)	UNICEF (Eritrea)	New indicator	£81.71	£78.72
	Cost per consultation Ouham Pende/ Alindao (Health Facilities (FOSAs)/Community Health Workers (CHWs) / WASH)	MENTOR (CAR)	New indicator	£1.77	£5.80
	Cost per consultation Alindao (District Hospital/ WASH)	MENTOR (CAR)	New indicator	£5.78	£29.67
	Cost per cash transfer	WFP (CAR)	New partner	£5.86
Efficiency	Total number of days of stockout of essential medicines	MENTOR (CAR)	6 essential drugs are monitored for the average number of days of stockout, with a target of less than 5 days/month.	Of the six essential medicines monitored: ACT, / Paracetamol, Iron/folic acid, Amoxicillin, Albendazole, Fansidar the only stockout reported was: / -Paracetamol – 60 days, for MENTOR in Basse Kotto. ACF had zero stockouts and MENTOR in Ouham Pende had zero stockouts	Average days/month stockouts: / -Paracetamol, 6 days for MENTOR in Basse Kotto / -Amoxicillin, 8, 5 and 7 days respectively for MENTOR in Ouham Pende and Basse Kotto and ACF in Basse Kotto / -Albendazole, 15 and 7 days respectively for MENTOR in Ouham Pende and ACF in Basse Kotto / -Fansidar, 5 days for MENTOR in Ouham Pende / All other stockouts were under 5 days.
	% of funding to National Non-Government Organisations (NNGOs)	CHF (CAR)	Baseline: 7% (2022)[8] / Target: International localisation target is 20%, CAR is starting from a much lower level so this indicator will look at the increase and how it is managed.	20%	30%
	CHF operations costs as % overall utilisation of fund	CHF (CAR)	Baseline: 5.7% / Target: less than 10% of overall utilisation of funds	6.97%	9.02%
	% of interventions carried out in less than 10 days thanks to supported national initiatives.	IFRC (Madagascar)	Target: March 2025 50%		50%
Effectiveness	Under-five prevalence of acute malnutrition (wasting)	UNICEF (Eritrea)	Baseline 12.3%; Target: March 2025 10%	11%	10.8%
	CHF performance assessed in the Common Performance Framework (CPF)	CHF (CAR)	Target: average score of 4 out of 5	4.25	4.15
	Number of participants in training as part of the implementation of the agreement with the BNGRC who improved their emergency management skills and applied them during real interventions.	IFRC (Madagascar)	Target: March 2025 125		163
	% of participants in training as part of the implementation of the agreement with the BNGRC who improved their emergency management skills and applied them during real interventions.	IFRC (Madagascar)	Target: March 2025 50%		50%
Equity	% of zobas (regions) UNICEF is active in	UNICEF (Eritrea)	Target: 100%	100%	100%
	Bases maintained in regions with humanitarian need in Cameroon	ICRC (Cameroon)	Target: Far North and North-West/South-West (NW/SW)	2 in the Far North / 3 in the NW & SW	2 in the Far North / 3 in the NW & SW
	% users that are women and girls, people with disability among those participating in community feedback and complaints mechanisms.	UNICEF (Accountability to Affected Populations in CAR)	Baseline: Women and Girls: 60% People with Disability: 15%	Women and Girls: 46% / People with Disability: 14%	Women and Girls: 55% / People with Disability: 1%
[8] Correction from previous annual review which had 1%.