## Annual Review

Title: Climate, Environment and Nature (CLEAN) Helpdesk
Programme Value £ (full life): £ 400,000.00 Committed Value £ (full life): £3,300,000		Review date: 21 November 2025
Programme Code : 301406	AMP start date: 21 November 2023	AMP end date: 31 March 2026

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	A	A
Risk Rating	Minor	Minor

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005097.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005226.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Climate, Environment and Nature (CLEAN) Helpdesk is a centrally managed FCDO programme, that provides short-term technical assistance (TA) to support FCDO and other UK government departments (OGDs) to integrate climate, environment and nature (CEN) into ODA policy and programming. The Helpdesk is delivered by a consortium led by SouthSouthNorth, working in partnership with ODI Global, Social Development Direct, and Paul Watkiss Associates.

Now in its third year, CLEAN builds on the recommendations from the previous years, expanding the scope to deliver on-demand TA, complemented by knowledge synthesis and learning products. These services strengthen the UK’s capacity on CEN integration, delivery of the UK’s international commitments, including Paris alignment, nature-proofing and International Climate Finance (ICF) reporting.

The Helpdesk delivers tailored technical advisory inputs of up to 20 days of expert/s support per request, with flexibility for additional support as required. It has established a strong pipeline of requests and continues to respond to high demand. CLEAN’s overarching impact ambition is to ensure UK ODA meaningfully contributes to building resilience, halting nature loss, and reducing emissions, while ensuring Paris alignment and adherence to ICF reporting. The programme mainstreams gender equity, disability and social inclusion (GEDSI) and safeguarding across all TA and knowledge outputs, recognising GEDSI’s central role in sustainable and inclusive climate action. The delivery of the programme is supported by continuously expanding the roster of experts based on the evolving demand for expertise in different sectors, a dedicated CLEAN Helpdesk website that provides a comprehensive resource library – open-access resources for external audiences, as well as a secure portal for UK officials to access sensitive materials, latest communications and access to other related UK technical assistance offers. CLEAN also ensure that all outputs mainstream GEDSI in delivery of CEN outcomes.

Summary supporting narrative for the overall score in this review

The CLEAN Helpdesk has delivered well against its ambitions and logframe indicators during this review period and maintained its relevance to FCDO and wider UK priorities. This highlights the strategic value of the facility which, particularly following the UK ODA reductions, can help deliver cost effectively the UK’s international CEN commitments.

The majority of milestones have been met or exceeded, and the programme continues to demonstrate progress towards its intended impact and outcomes. Since its inception, CLEAN has received 94 TA requests, of which 36 were completed and a further 18 are in progress or upcoming. 32 Requests have been received between 1 October 2024 – 30 September 2025. This level of demand reflects both the importance and utility of a central, demand-led TA facility to support climate, environment and nature across HMG. Demand did dip temporarily whilst FCDO’s new strategy was being developed but has since recovered sharply highlighting the programme’s ability to respond to the new FCDO partnership led approach where expertise is critical to the UK offer.

Based on feedback in last year’s annual review CLEAN has now gone beyond the delivery of short-term technical assistance to generation of knowledge synthesis products and learning events, to extend its reach and impact. As a result, CLEAN products are being used to influence both central policy and strategic decision-making and programme design and delivery at the country level.

While performance is strong overall, some activities were put on hold whilst longer-term work on Centres of Expertise e.g. changes to governance structures , development of communities of practice and linkages with other facilities. Nonetheless, CLEAN remained proactive in engaging with posts and policy teams and as a result , uptake has exceeded initial forecasts. Against this backdrop, the programme is assessed as A (Meeting Expectations): CLEAN continues to deliver effectively, remains well-aligned to UK priorities, and is proving responsive and resilient in the face of a shifting ODA landscape and represents excellent value for money.

Major lessons and recommendations for the year ahead

Action on previous recommendations
The six recommendations from the previous annual review (please see list below) were all addressed and integrated into the programme delivery. Please see bullet points below for the course of action taken to address the recommendations.

By December 2024, CLEAN Helpdesk to make it explicit that receiving technical assistance is conditional on completing a feedback form and annual user survey.
This recommendation stemmed from low response rates to feedback forms.
- The TA request form was updated to include a required field stating the following:
   ‘The CLEAN Helpdesk uses feedback forms and an annual user survey to monitor the success of the Helpdesk and to inform learning and adaptive management. Receiving technical assistance from the CLEAN Helpdesk is conditional on responding to a short feedback form once the request is finalised, as well as responding to our annual user survey which is usually sent out in September. We estimate that it will take less than 30 minutes in total to respond to both surveys.’
- In addition, during the initial meetings with the requester, we verbally request that they participate in the forms and surveys to support us in our reporting and improving the delivery of the programme.
1. By January 2025, agree a new approach to programme governance, in particular for the ‘Programme Delivery Board’ which was designed for regular engagement with other technical facilities to ensure coherence, avoid duplication and learning across facilities.
  1. Adjust logframe output indicator 2.2 accordingly.
     Logframe output indicator 2.2 was reviewed in January and updated in March 2025 from the ‘Number of ‘Programme Delivery Board of TA facilities’ meetings attended’ to indicate the ‘Number of HMG TA facilities included on the CLEAN Gateway Platform’. This indicator captures the collaboration on the provision of TA between other facilities and the CLEAN Helpdesk and is achieved through the outreach to key facilities including those managed by OGDs, for example, the CASA technical facility under DESNZ.
A proposal to put in place a Programme Delivery Board of TA Facilities was discussed and agreed with the FCDO SRO team during the March 2025 workshop. Following this, an indicator which reflected this review was amended in the LF: a meeting of the proposed Technical Facility Working Group by Feb 2026.
Work on developing both the proposed CLEAN Advisory Panel and the Technical Facility Working Group is currently paused, pending internal FCDO discussions on the form and structure of future Centres of Excellence / Expertise.
By March 2025, conduct a joint review of the logframe to assess whether it is too dependent on survey data and whether metrics are appropriate and ambitious enough to demonstrate both impact and value for money.
- A joint review was conducted on the logframe and the following outcome indicators were revised to be captured as case studies on the provision of services from CLEAN Helpdesk to reduce the dependence on survey data.:
  - Outcome indicator 1.2.b was revised to ‘CLEAN HD users can demonstrate how the support received from CLEAN HD has helped them to design a programme/policy with potential to deliver co-benefits’.
  - Outcome indicator 2.2 was revised into 2.2.a ‘CLEAN HD users can demonstrate how the support received has improved HMG capacity on Climate, Environment and Nature outcomes’ and 2.2.b ‘CLEAN HD users can demonstrate how the support received has improved HMG capacity on inclusive and equitable Climate, Environment and Nature outcomes’.
- The feedback from the TA form and annual user survey still provide important data for supporting the fulfilment of the logframe targets and improving the delivery of the Helpdesk while ensuring the programme is not overly dependent on these data.
- Targets were also increased for four indicators to raise the ambition of the CLEAN Helpdesk.
By March 2025, agree a revised workplan and communications plan. The workplan should include recommendations made under indicator outputs 1 and 2 for the resource library and coordination with other facilities respectively, as well as agreed milestones for the PrOF5 MEL role. The communications plan should include engagement with FCDO as well as other government departments such as Defra.
- A revised workplan and communication plan was submitted and approved by FCDO in February 2025. This outlined priority actions, target groups and communications assets. The plans are being implemented and continuously updated as the needs of the programme evolve and opportunities arise.
- The PROF5 MEL role was fulfilled by wo experts since 17 December 2025 and support will continue until 31 March 2026. A series of outputs have been produced and a presentation of outcomes and findings were developed and provided to the ECED Paris Alignment team to be featured in the Value for Money segment of the CEIE conference.
- Further to this, the vacant role of Stakeholder Engagement Coordinator was repurposed into a communications manager role based on the evolving needs of the programme. This role was successfully recruited and onboarded to the CLEAN Helpdesk.
- The resource library has also been updated on a continuous basis with a number of publications and communications products both from CLEAN as well as other TA facilities.
By April 2025, ensure that consortium members and FCDO have opportunity to reinforce a shared vision for the programme - considering a similar format to the inception workshop, to foster a deeper shared understanding of what CLEAN is setting out to achieve in its final year.
A planning workshop was held on 4-6 March 2025 for the consortium and FCDO counterparts to discuss and reshape the programme based on the successes and challenges experienced as well as the expectation and planning for the financial year ahead.
For FCDO and CLEAN to collaborate on a web/sharepoint page so that CLEAN has additional visibility on the FCDO intranet, similar to the ‘centres of expertise’.
Since this recommendation was made, FCDO have advised that this is no longer an option as obtaining internal permissions for new intranet pages were not possible.
Lessons learned
The main lessons learned from this review period (1 October 2024 – 30 September 2025) can be summarised as follows:

1. Managing demand amid ODA uncertainty: Uncertainty in ODA allocations has impacted the demand for CLEAN’s TA service offering, creating short-term pauses in requests, impacting delivery and spend. Maintaining engagement requires a proactive approach, including developing a strong pipeline of requests, enhancing engagement with posts, and actively promoting CLEAN’s offering across HMG. Aligning support with evolving FCDO, ICF and country priorities ensures that resources are deployed effectively, sustaining impact despite funding uncertainty.
2. Addressing ICF methodological gaps across HMG: Challenges remain on alignment of ICF methodologies with FCDO and other government departments such as Defra and DHSC. This misalignment creates complexity in CLEAN’s ability to provide coherent TA across departments as the FCDO guidance that CLEAN adheres to, does not fully align with other department’s business development process and programme design. CLEAN is well placed to help convene cross-HMG dialogue and contribute to the development of standardised ICF guidance, ensuring consistent application and reporting practices.
3. Advancing GEDSI mainstreaming in TA: The CLEAN Helpdesk’s approach to GEDSI mainstreaming within TA has been successful in ensuring that all outputs are GEDSI sensitive, with many achieving a higher level of ambition by identifying linkages between GEDSI and CEN topics and building the capacity of requesters. Key challenges have included gaps in awareness of GEDSI and safeguarding links among some requesters, as well as capacity gaps in GEDSI understanding among rostered CEN experts. These challenges have been effectively addressed through GEDSI quality assurance of ToRs, the participation of GEDSI experts in kick-off calls, and the inclusion of GEDSI/safeguarding specialists with the expert teams.
4. Enhancing institutional value through portfolio reviews: Products like a portfolio review have demonstrated strong systemic value, strengthening ICF reporting and informing policy and practice beyond individual TA requests. CLEAN should build on this success by scaling up proactive reviews and synthesis products to capture wider institutional insights and strengthen cross-programme learning.
5. Streamline knowledge management and communications publications processes: Delays in securing publication approvals from FCDO slowed the dissemination of TA outputs in early Year 2. A streamlined clearance process has now been introduced, allowing faster publication of approved materials. CLEAN has also begun seeking commissioner (requester) approval earlier in the process to further accelerate delivery and visibility.
6. Strengthening engagement with wider HMG stakeholders: Engagement with OGDs to explain and promote CLEAN has been more challenging than planned. CLEAN had originally planned to create bespoke communications materials for non-FCDO departments but interest has been low. Instead – CLEAN has created short/ HMG wide materials and published these – directing wider Departments to them as appropriate.
7. Increasing platform sign-ups and visibility: Low sign-up rates from HMG staff persist due to limited entry points and unclear incentives to sign up. Although existing messaging is clear, uptake remains low, suggesting awareness and perceived value are the main barriers. The sign-up process has been simplified, promoted through internal FCDO channels and the CLEAN Helpdesk newsletter. Future efforts will focus on strengthening awareness and demonstrating the platform’s value through clearer messaging and targeted outreach.
8. Improving Monitoring and Evidence of effectiveness: Challenges with securing user feedback and interviews have made it more difficult to demonstrate outcome-level results. CLEAN has mitigated this to some extent by diversifying data collection, including regular requester surveys, written and verbal feedback and structured feedback forms, and by embedding qualitative learning through case studies and consortium learning sessions.
9. Strengthening financial management and forecasting: Spend to date remains below forecast due to fluctuating reduced demand and lack of clarity on future funding into next FY. As the programme enters its final two quarters, close monitoring and proactive financial management will be essential. Measures such as overcommitment strategies and flexible resource allocation are being implemented to ensure efficient budget utilisation and maintain value for money. Further details in section F.
Recommendations for the year ahead
The main recommendations for the year ahead can be summarised as follows:

1. Maintaining climate and environment support: Extension of CLEAN beyond 31 March 2026: Given ongoing organisational changes within FCDO and the planned establishment of Centres of Expertise (CoEs), it is recommended that the CLEAN Helpdesk be extended for at least one more year e.g. 31 March 2027 to ensure continuity of technical assistance, knowledge management, and portfolio learning on CEN mainstreaming. An extension would enable continued support to FCDO and other government departments while longer-term institutional arrangements are finalised. This would help ensure a smooth transition, safeguard institutional memory, maintain delivery momentum, and sustain coordination across the technical assistance facility network.
2. Continuation of the CLEAN Helpdesk function : CLEAN is well on track and is already exceeding the number of TA requests that are received and completed. This is in part due to greater use of opportunities to increase demand through events such as the CEIE conference 2025, promotional products and events and through the website. This increase in support will be critical to helping deliver FCDO’s climate, nature and energy objectives.
3. Increase CLEAN value add : This includes actively communicating key findings, producing accessible synthesis materials, and showcasing success stories to increase uptake and use of CLENA products and demonstrate the value and results of CLEAN’s support. Achieving this will require collaboration across consortium partners and active engagement from FCDO teams.
4. Prioritise short-term requests to ensure timely completion (if no extension is granted): CLEAN should prioritise requests that can be delivered and closed out before 31 March 2026. This will ensure that all ongoing and new work is completed within current contractual timelines.
## B. THEORY OF CHANGE

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The CLEAN Helpdesk Theory of Change (ToC) was reviewed as part of a consortium-wide learning and reflection process following the Year 1 Annual Review. The review confirmed that the underlying logic from outputs to outcomes and impact remains sound, and no significant revisions to the ToC were required. However, some outcome indicators (outlined below) were revised to improve measurability and better reflect the programme’s timeframe. Adjustments focused on addressing the challenges with data collection and the complexity of demonstrating outcome-level change in a short time period. These revisions ensure that the ToC and logframe continue to provide a realistic and evidence-based framework for tracking progress and learning. In parallel, CLEAN’s MEL approach was strengthened through improved uptake tracking, quarterly feedback, and clearer links between TA provided and CEN integration into climate and resilience programming.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact: The UK delivers meaningful contributions to build resilience to current and future climate impacts, halt and reverse global nature loss and halve global emissions.

The CLEAN Helpdesk remains on track to contribute to its expected outcomes and impact, with evidence showing that CLEAN is exceeding logframe benchmarks at the impact level. The Helpdesk has supported 32 countries through 36 completed and 18 ongoing TA requests to date[1].– surpassing the original impact indicator target of 25. This demonstrates CLEAN’s growing global reach and relevance to building resilience, halting nature loss and reducing emissions. The countries which have been supported by CLEAN technical assistance are:
[1] N.b. Some requests cover more than one country

1. Democratic Republic of Congo
2. Bolivia
3. Brazil
4. Colombia
5. Ecuador
6. Peru
7. Ethiopia
8. Morocco
9. Jordan
10. South Sudan
11. Lebanon
12. Syria
13. Egypt
14. Algeria
15. Tunisia
16. Nepal
17. Zambia
18. Mali
19. Niger
20. Iraq
21. Vietnam
22. SIDS: Caribbean region
23. SIDS: Atlantic region
24. SIDS: Pacific Region
25. Ghana
26. Guyana
27. Nigeria
28. Suriname
29. The Gambia
30. Venezuela
31. Yemen
32. Indonesia

In addition, CLEAN has responded to 13 requests which are not country specific. Five have been completed, and eight are ongoing. Both country specific and non-country specific requests have further strengthened cross-portfolio coherence and collaboration. The full list requests are in the annex below.

Requests have been received from FCDO, DEFRA, DESNZ, CEFAS, and DHSC.

Outcome 1: UK ODA programmes and policies deliver positive co-benefits, including for communities, are Paris Aligned, Nature Proofed and follow ICF (PrOF5) guidance

CLEAN is on track to achieve Outcome 1, with strong evidence that its TA is improving the quality and climate ambition of the UK ODA programmes and policies.

For outcome indicator 1.1, 96% (22 of 23) of TA users who completed feedback forms in Year 2 reported that they are very likely or likely to integrate the advice received through the CLEAN Helpdesk into the policy and programme design that they work on - exceeding the target of 70%. One user noted, “The feedback from CLEAN helpdesk has been actively incorporated into the project design and forms the backbone of our strategic case.” This indicates that CLEAN’s advice is not only being used but is shaping the structure and rationale of new programmes.

For Outcome Indicator 1.2a, 78% (14 out of 18) of relevant TA users strongly agreed or agreed that CLEAN’s support had strengthened Paris alignment, nature proofing, and/or adherence to ICF (PrOF5) guidance within their programmes (target met).

Outcome indicator 1.2b was revised the following Year 1 to use case studies rather than rely on survey data to demonstrate how CLEAN HD support has helped UK officials to design a programme/policy with potential to deliver co-benefits. A case study (see annex B) illustrates how CLEAN’s technical input was instrumental in designing the six-year regional Amazon Catalyst for Forest Communities (AMCAT) programme to be participatory and inclusive, supporting efforts to protect forests and support Indigenous Peoples and local communities (IPLCs) across the Amazon basin (target met). This evidence confirms CLEAN is directly contributing to FCDO’s ability to design Paris-aligned, nature-positive, and inclusive ODA programmes that deliver co-benefits.

Outcome 2: Improved capacity of HMG staff to design and deliver safe programmes and policies with inclusive and equitable CEN outcomes
CLEAN is on track to achieve Outcome 2, with feedback indicating that the Helpdesk continues to strengthen FCDO and wider HMG staff capacity to design and deliver high-quality CEN outcomes.

For Outcome Indicator 2.1, 96% (22 out of 23) TA users who submitted feedback strongly agreed or agreed that the support received from the CLEAN Helpdesk improved their confidence and knowledge for designing, delivering and/or monitoring CEN outcomes (target met). One user reflected, “My confidence is increased as TL (Team Lead). The challenge will be to keep integrating this knowledge and empower others to act on it as well. We are therefore considering another helpdesk request for after the portfolio has been refreshed, and ODA allocations are known.” This feedback demonstrates that CLEAN is successfully strengthening individual and team capability across key sectors.

Outcome Indicator 2.2 uses case studies (Annex B) to demonstrate how CLEAN HD support has improved HMG capacity on inclusive and equitable Climate, Environment and Nature outcomes. Nine case studies are shared in annex B, including two which are focused on GEDSI-mainstreamed support. These examples illustrate how CLEAN has supported staff to meet technical standards and to integrate social inclusion and equity into programme design – reinforcing FCDO’s commitment to learning no one behind.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue, as it represents a unique offer that delivers highly relevant CEN services to FCDO and the wider HMG portfolio and consistently strong value for money. CLEAN has consistently exceeded its targets, supporting 32 countries through 36 completed and 18 ongoing TA requests and addressing both country-specific and cross-cutting priorities. In addition to providing direct, tailored TA, CLEAN coordinates wider support through its curated resource library and referral to other facilities, maximizing efficiency and coherence across FCDO advisory services on climate and related areas. CLEAN is demonstrably strengthening institutional capacity to mainstream CEN, supporting PrOF Rule 5 compliance, and integrating GEDSI considerations into CEN programming.

Despite uncertainty around ODA budgets, CLEAN has met or exceeded most of its objectives, overcoming initial delays in Year 1 and demonstrating steady progress against all outputs and outcomes. The high demand for its services – with 94 requests logged in less than two years – illustrates the growing need for flexible, expert-driven support on climate. In the context of the ODA reductions where resource and capacity constraints are further placed under pressure, CLEAN fills a critical niche. Providing access to responsive, cross-cutting UK expertise that complements larger ICF investments, strengthening in-country capacity, promoting portfolio coherence, and supporting the UK to deliver its international climate, environment and nature objectives.
## C. DETAILED OUTPUT SCORING

Output Title	Output one: Increased knowledge of CLEAN HD users of UK-ODA related inclusive and equitable CEN work
Output number:		1	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	No (but weightings were added to the indicators)

Indicator(s)	%	Milestone(s) for this review	Progress
1.1 Number of knowledge products hosted on the Gateway Platform / (disaggregated by knowledge product type)	30%	80 products	Substantially exceeded / 111 products; / 15 CLEAN-produced products / New CLEAN newsletter designed and produced. Two editions* shared. There are 56 subscribers. / Third edition published in October 2025.
1.2 Percentage of CLEAN HD knowledge products which include GEDSI sensitive/ strategic/ transformative advice	25%	100% of CLEAN HD knowledge products include GEDSI sensitive advice. At least 30% of new (Y2) knowledge products include GEDSI strategic advice.	Substantially exceeded / 100% of CLEAN HD knowledge products include GEDSI sensitive advice as a minimum. / 63% of knowledge products include GEDSI strategic or transformative advice.
1.3 Percentage of CLEAN HD knowledge product users who found CLEAN HD knowledge products Very Useful / Useful	25%	70% find Very Useful / Useful	Moderately exceeded / 100% (of 7) website users have rated CLEAN knowledge products as useful / 87% of 23 requesters who completed feedback forms were satisfied that CLEAN support is likely to be useful for their TA request.
1.4 Number of events / (disaggregated by event type and by HMG department)	20%	8 events	Substantially exceeded / 13 events / 7 TA-related events (all FCDO-focused) e.g. presentation to post on: / Ethiopia Climate Risk and Adaptation Assessment (CRAA) / Building Local Resilience in Syria (BLRS) - presentation to post. / Jordan climate & environment scoping for concept note / Jordan mining diagnostic / Vietnam climate mapping - / Egypt Impact Mapping – / Integrating GEDSI into ICF / 6 wider learning events to FCDO and HMG partners: / Serious and Organised Crime links to Climate Change / ICF 101 Training to Nepal FCDO post and partners. / International Education Funders Group / Greening Education Partnerships quarterly meeting / CEIE Cadre conference 2025 - presentation of CLEAN offer and high-level findings of work. / Launch of Earth Capital Nexus - Catalysing finance for a resilient future

Briefly describe the output’s activities and provide supporting narrative for the score.

Output indicator 1.1: As of 30 September, the website’s resource library hosts 111 knowledge products, including 15 developed by the CLEAN Helpdesk. The current number of resources substantially exceeds the final programme target of 90 products, and more are in the pipeline. To date, there have been 5,900 new website users and 61,000 total website views. New features on the website include a scrolling newsfeed on the homepage and an upcoming blog/news article feature. In addition to this, the CLEAN Helpdesk publishes quarterly newsletters to keep stakeholders informed of CLEAN’s latest activities, impact and learning, while showcasing how it works to support the UK CEN priorities. The newsletter highlights key TA resources and case studies, invites the reader to explore the resource library and the benefits of signing up to the secure portal accessible to UK officials only for sensitive resources and materials. The newsletter strengthens engagement, transparency, and demand for CLEAN’s tailored TA.

Output indicator 1.2: A strong process for mainstreaming GEDSI and safeguarding has been established and consistently applied across all CLEAN activities. GEDSI and safeguarding quality assurance is undertaken for every TA request, with all Terms of Reference (ToRs) and outputs reviewed from a GEDSI and safeguarding perspective. Feedback is provided to experts, and additional GEDSI and safeguarding expertise is commissioned where required to ensure quality and consistency. As a result, all CLEAN outputs produced from the implementation phase of the programme onwards are GEDSI sensitive as a minimum standard, and 63% have been assessed as GEDSI strategic or transformative. The publication of the Info Note: Our Approach to Integrating GEDSI into Technical Assistance Requests on the CLEAN website has further promoted good practice and transparency. In addition, the second edition of the Helpdesk newsletter focused on GEDSI, helping to share learnings from GEDSI mainstreaming in TA pieces that have been commissioned and raise awareness across HMG on GEDSI mainstreaming in CEN. These achievements demonstrate that GEDSI considerations are now systematically embedded within CLEAN’s delivery processes and outputs, fully meeting and exceeding expectations for this reporting period.

Output indicator 1.3: Significant progress has been achieved in Year 2 to expand and enhance the accessibility of resources available through resource library on the CLEAN website. Efforts have focused not only on increasing the volume of materials uploaded but also on understanding user needs and tailoring content to meet the priorities of FCDO and wider HMG stakeholders. To assess the usefulness of products, a feedback module was deployed on the website, with 100% of seven respondents rating the resources as useful. Although respondents to the annual user survey did not engage with the products on website, 87% of the 23 TA users who completed feedback forms reported that the support received from CLEAN was useful and relevant to the intended purpose of their request. These findings suggest that CLEAN resources and TA are valued by users and are effectively meeting their needs demonstrating that the programme has moderately exceeded the milestone for this output indicator.

Output indicator 1.4: CLEAN has exceeded expectations under this output indicator, delivering strong programme of engagement and knowledge sharing events during Year 2. The Helpdesk held seven TA-related events to present findings and recommendations directly to requester teams, country offices and ambassadors, ensuring that learning was immediately relevant and actionable. In addition six wider learning events were organised to share insights across public and FCDO cadres and thematic areas, including sessions on CEN mainstreaming, GEDSI integration and portfolio learning. CLEAN also contributed to and presented at the HMG Climate, Environment, Infrastructure and Energy (CEIE) cadre conference 2025 in September/October, showcasing key findings and lessons from Helpdesk delivery. With a total of 13 events held, the final target to have 10 events by February 2026 has already been exceeded. The strong performance reflects CLEAN’s growing role as a platform for institutional learning and cross-programme knowledge exchange across HMG.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output in the past year beside the recommendations from the previous annual review to make changes to the indicators to strengthen the measurement and ensure indicators remain relevant and achievable. A light-touch review of all indicators will be undertaken following this review to assess the appropriateness of targets and data sources; however, no significant changes are anticipated.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Following the recommendations of the previous annual review, refinements were made to strengthen this output’s indicators and improve data quality. The targets for output indicators 1.1 and 1.2 were increased to reflect higher-than-anticipated delivery, while output indicator 1.3 was updated to include the website feedback mechanism as an additional data source to capture user perceptions of resource usefulness. Output indicator 1.4 was revised from tracking the number of attendees at events to counting the total number of events delivered, providing a clearer measure of outreach and engagement. These adjustments have improved the relevance and reliability of the indicators and better reflect the Helpdesk’s evolving delivery model.

In line with CLEAN’s “one-stop-shop” ambition and GEDSI commitments, the resource library has been expanded to include selected CEN-relevant publications from other FCDO-funded helpdesks – including the Disability Inclusion Helpdesk, Violence Against Women and Children (VAWC) Helpdesk, and the Work and Opportunities for Women (WOW) Helpdesk. This collaborative approach enhances cross-learning, reduces duplication and ensures users have easier access to a broader suite of CEN GEDSI resources. For the six-months ahead, CLEAN will continue to strengthen data capture and analysis through website engagement tools, promote cross-Helpdesk learning products and ensure knowledge resources remain accessible, relevant and aligned to FCDO and HMG priorities.

Output Title	Output two: HMG demand met for informed CEN TA through improved access to, and coordination of, suitable inclusive and equitable CEN TA
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 2.1: ICF TA KPI 2: Number of individuals[2] informed by International Climate Finance technical assistance	155	Moderately exceeded / 165 individuals and 14 organisations, across 36 completed requests and 18 ongoing requests, have been informed by the ICF TA.
Output indicator 2.2: Number of HMG TA Facilities included on CLEAN Gateway Platform	8	Moderately exceeded / 10 TA Facilities
Output indicator 2.3: Percentage of CLEAN Helpdesk users and CLEAN TA providers who felt confident that they knew what to report and how should a safeguarding concern arise.	70%	Moderately exceeded / 80% of TA providers and users agree/strongly agree (9 of 10 experts and 15 of 20 users)
[2] The number of individuals informed by technical assistance requests is estimated using feedback from those submitting the request, i.e. TA requesters specify how many other individuals have been informed, and the number of UK government officials who are involved in the technical assistance delivery process.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output indicator 2.1: The CLEAN Helpdesk continues to deliver a high volume and diversity of TA requests, reflecting its strong relevance and demand across FCDO and HMG. To date, 94 requests for support have been received; 36 completed, 18 ongoing, 10 upcoming (ToR in development), 8 on hold, 1 referred to another facility, and 21 cancelled. Compared with CMF, this is a substantially large number of requests, with a good distribution across multiple regions and covering a wide range of thematic areas. Across completed and ongoing requests, 165 individuals and 14 organisations have been informed by CLEAN TA – exceeding the Year 2 milestone of 155 individuals. This figure likely underestimates total reach, as data collection relies on feedback forms which are usually not completed by all users. The breadth of engagement and achievement against milestones demonstrates strong performance and confirms that CLEAN is on track and exceeding under this indicator.

Output indicator 2.2: Significant progress has been made in strengthening coordination across HMG’s TA landscape through the CLEAN Helpdesk website. CLEAN’s role as a central platform for information-sharing by including a page with a description of other technical facilities, their website link and request form, enabling users to understand the range of support available across government. To date, 10 other technical facilities are now hosted on the CLEAN Helpdesk website -exceeding the target of eight. This “umbrella” approach has created a single, accessible entry point for officials seeking technical assistance, improving coherence and user experience. The offer to host additional facilities has been extended to several others, although responses are still pending. Through this engagement, CLEAN has strengthened relationships across the TA network, successfully referring one request to another facility and co-delivering a joint request with the Nature Facility. While user data on traffic or referrals via hosted links is not available, the platform is well-positioned to become a central hub for coordination across the UK’s CEN-related technical facilities.

Output indicator 2.3: Safeguarding has been fully embedded across all aspects of CLEAN delivery. A safeguarding framework has been developed and training provided to all consortium members to ensure compliance with FCDO standards. Each TA request undergoes GEDSI and safeguarding review at the ToR stage, with additional safeguarding expertise brought in as required to mitigate specific risks related to the request. Feedback indicates strong user confidence: 80% (of 30) TA users and experts confirmed they know how to report a safeguarding concern, and 100% reported feeling safe, respected and comfortable during their engagement with CLEAN. A safeguarding banner and reporting form are prominently displayed at the bottom of every page on CLEAN Helpdesk website, reinforcing accessibility and transparency. Further to this, the initial email acknowledging receipt of the request to the user includes the following text, ‘Please note that the CLEAN Helpdesk takes a zero tolerance approach across all of our work. Please see our safeguarding policy statement.’ These measures demonstrate a strong safeguarding culture within the programme, meeting and exceeding expectations for this output.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year with the exception of the recommendation from the previous AR to revise output indicator 2.2 (more details provided below). A light-touch review of all indicators will take place following this review; however no significant changes are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Following the recommendations of the previous Annual Review, logframe output indicator 2.2 was revised to better reflect CLEAN’s coordination role across HMG technical facilities. The indicator was updated from ‘Number of ‘Programme Delivery Boad of TA facilities’ meetings attended’ to indicate the ‘Number of HMG TA facilities included on the CLEAN gateway Platform’. The change provides more accurate measure of collaboration through outreach and hosting of other TA facilities on the CLEAN website, including those manged by OGDs. The Helpdesk has the potential for being the central platform for cross-facility coordination.

Work to develop both a CLEAN Advisory Panel and a Technical Facility Working Group has currently been placed on hold, pending internal FCDO discussions. For the six-months ahead, CLEAN will maintain and initiate engagement with additional TA facilities, monitor platform usage, and support FCDO decisions on the most effective governance arrangements for coordinated TA delivery.

Output Title	Output three: Strengthened capacity of CLEAN HD users to monitor, evaluate and develop learning to support Paris alignment and nature proofing
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 3.1: Number of completed learning outputs developed to improve FCDO PrOF5 compliance across programmes	5	Moderately exceeded / 7 learning outputs completed. / An introduction to ICF: ICF 101 slide deck / Application of UK International Climate Finance to FCDO Infrastructure and Urban Programmes / Application of UK International Climate Finance (ICF) to Social Protection Projects and Programmes / Integrating GEDSI into ICF indicators / Paris Alignment literature review, full technical report, and findings slide deck / International Climate Finance Supplementary Note / Information Note: CLEAN support to ICF programming across sectors
Output indicator 3.2: Number of programmes/ cadres/teams which are provided with technical assistance to improve PrOF5 and EPPS monitoring and reporting compliance	20	Moderately exceeded / 30 ongoing and completed requests (21 complete)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output indicator 3.1: Nine learning outputs have been developed to strengthen compliance with PrOF5. These resources provide targeted, accessible resources to support teams in applying ICF requirements and improving report quality. Progress remains strong, with the programme substantially exceeding the set milestones – demonstrating the robust delivery and clear value.

Output indicator 3.2: The programme has exceeded delivery milestone expectations in delivering technical assistance to improve PrOF5 and EPPS monitoring and reporting compliance. A total of 21 programmes/cadres/teams have received completed PrOF5-related TA, with a further nine requests in progress. This represents strong demand and engagement across the HMG portfolio, reflecting the relevance and quality of support provided. Delivery remains on track to meet the final milestone for February 2026 of 24 completed PrOF5 requests, demonstrating sustained performance and high value to stakeholders.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the past year, Output indicator 3.1 was revised to clarify that only completed outputs are counted. Indicator 3.2 was expanded to include cadres/teams in addition to programmes receiving technical assistance, and to incorporate the Environmental Principles Policy Statement (EPPS) alongside PrOF5. Reflecting stronger than anticipated performance in Year 1, the target for this indicator was increased to ensure it remains ambitious and aligned with demand.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

There were no specific recommendations related to output indicator 3 in the previous AR. Minor clarifications were made to the indicators to ensure more accurate data measurement and stronger alignment with programme objectives.

A key learning this year is that while OGDs follow different ICF methodologies, CLEAN uses FCDO guidance. This creates complexity in providing consistent TA, as FCDO guidance is not fully aligned with OGD processes.

Looking forward, there is an opportunity for CLEAN to play a convening role with HMG by catalysing discussions on a standardised ICF methodology, particularly in light of the upcoming revision of the ICF strategy. Such alignment could enhance efficiency, strengthen compliance and improve coherence across departments. In addition, CLEAN will continue to provide PrOF5 and EPPS support to new requests, looking at opportunities to promote this offering from the CLEAN Helpdesk to posts.
## D: VALUE FOR MONEY

Key cost drivers and performance
Key costs	% total spend (Oct 24 - Sept 25)	Cost drivers	Actions to manage key costs
Platform development (gateway/website)	8	Website development and staff	Beyond the initial platform development budget, new features were scoped and budgeted separately by the selected development house. This approach allowed for tighter budget management and clearer evaluation of each feature's value.
Knowledge Management, communications and stakeholder engagement	12	Staff majority based in South Africa with the lead based in the UK, costs for copyediting, design of products	Majority of the knowledge management and communications staff are based in South Africa and commensurate rates are applicable. / The knowledge management lead is based in the UK and supports at 0.46 FTE. / Copyediting and design services are sourced from the Global South to allow for commensurate rates and undergo a competitive open-source procurement process as per the SSN procurement policy. This allowed for quality assurance processes as well as due diligence and was assessed for value for money and feasibility.
Technical assistance support	19	Technical leads and co-leads	Costs of leading experts to provide guidance, lead on TA, integrate GEDSI, develop outputs. Leveraging impactful technical expertise without their time being used for administrative support.
Direct technical assistance	26	Expertise costs to deliver high-quality TA	The experts were selected from the pre-screened roster of experts and were evaluated further based on their suitability (thematic expertise, geographic experience, availability) to undertake the request and value for money in terms of their rate. CLEAN has benchmark rate caps for expert rates which are applied and in cases where the cap is exceeded and cannot be negotiated for a discount rate, approval from the SRO is sought with a rationale for the higher rate requirement.
CLEAN Helpdesk consortium	11	Coordination and delivery of TA team based in South Africa and the rest of the consortium based in the UK.	Approximately 45% of the consortium is based in South Africa and commensurate rates are applicable. / Others in the consortium based in Europe have applied discounted rates to ensure good value for money.
Travel, events and expenses	1	Travel costs linked to programme and TA requests travel	Flights with the shortest layovers, economy seats and best pricing were selected. Accommodation was selected according to pricing and distance from venue and public transport was used where appropriate to allow for reduced costs and emissions. Additionally, where virtual engagement was possible and did not inhibit the process it was selected as the preferred option as VFM and from a sustainability perspective.
MEL	5	Staff	Dedicated MEL staff working on the programme’s monitoring, evaluation and learning on a continuous basis in addition to the Monitoring and Evaluations experts working on the review of the status quo on Paris Alignment for UK

VfM performance compared to the original VfM proposition in the business case

Economy
The business case set out three key economy measures: i) use of a pre-screened roster of experts that have defined day rates, ii) use of individual experts as opposed to larger consultancies that allows for more competitive rates, and iii) using a non-profit delivery partner meaning no mark-up is applied to the roster of experts meaning that day rates remain lower. These measures have all been successfully delivered.

The day rates remained within the benchmark rates for Year 2, and where expert rates were higher, the rates were discussed and discounted rates negotiated, reflecting increasing economy. There have been no difficulties in securing suitable expertise despite rate caps. The lead delivery partner for CLEAN Helpdesk is based in South Africa further strengthening the value for money as staff costs remain relatively low. In addition to this, website development, copy-editing and design services are sourced from local Global South suppliers further strengthening the economy case for the programme.

Efficiency
The CLEAN Helpdesk’s business case approach aims to limit requests to a maximum number of days (20) provides a ‘service ceiling’ which encourages efficient delivery, particularly when combined with the use of a roster of experts with pre-agreed rates. Out of 36 completed requests, 15 requests have exceeded the 20-day threshold, with the majority taking 25 expert days to complete, in several of these requests these additional days were to provide dedicated GEDSI expertise to a request. In all cases, the impact was justified and careful management ensured that sufficient budget was available to support the additional days. Where requests exceeded 25 expert days, co-financing agreements were used to cover the additional days or further justification was required to access CLEAN resourcing.

To date, CLEAN Helpdesk has supported 619.8 days of technical assistance (excluding consortium time), with an average of 20.5 days per request[3].
[3] Completed and ongoing requests.

Demand remains strong with 94 requests have been received to date – 82 from FCDO and others from DESNZ, Defra and DHSC. Delivery progress includes:
- 36 completed requests,
- 18 ongoing,
- 10 upcoming,
- 8 on hold,
- 1 request has been referred to another TA facility, and
- 21 cancelled.

Beyond direct delivery, CLEAN’s ability to signpost to other TA facilities could further increase efficiency. The programme has successfully leveraged co-financing with PHENOMENAL and the Nature Facility, and the CLEAN mechanism has been used for one request but funded in its entirety by CEFAS, leveraging full utilisation of CLEAN staff resources for TA delivery.

The CLEAN Helpdesk’s integrated approach to GEDSI mainstreaming demonstrates efficiency, as GEDSI and safeguarding considerations are embedded in CEN TA representing a further efficiency in delivering inclusive outcomes without separate processes.

Effectiveness
The CLEAN Helpdesk website provides a gateway to 10 other technical facilities offering which allows users to decide where best their request should be submitted. This supports the ambition stated in the CLEAN business case for the website to triage requests to the appropriate facility, increasing access to TA across HMG. The full extent of its effectiveness is unknown as there is currently no way to track if users have accessed the CLEAN Helpdesk website and directly used the links to request support from other TA facilities.

Feedback from TA users has been extremely positive, with 96% planning to integrate CLEAN advice into their programmes and policies, and 96% agreeing that CLEAN support has improved their confidence and knowledge for designing, delivering and/or monitoring CEN outcomes. Interviews with users conducted for case studies also demonstrate the effectiveness of CLEAN support. For instance, one FCDO official commented, “The study was critical in informing our business case for the new bilateral programme. It ensured we were strategic in targeting gaps, aligning with other donor programmes, and designing interventions that truly add value. It made our work significantly more effective.”

Equity
Further progress has been made in Year 2 for CLEAN’s service offering to expand beyond HMG to OGDs and to include GEDSI mainstreaming as a core aspect of delivery as outlined in the business case. In Year 2, the process of mainstreaming GEDSI and safeguarding consideration across TA requests has shown clear progress compared to the inception phase; legacy CMF requests which did not undergo a GEDSI QA were more likely to be GEDSI unaware. Enhanced GEDSI support is deployed where needed (e.g., due to expert capacity or requests with greater GEDSI/safeguarding risks or opportunities). This includes providing expertise on economic inclusion, equal education, gender-based violence, diverse participation and leadership, and safeguarding. These results are featured in an upcoming learning note on “Prioritising Gender Equity, Disability, and Social Inclusion in the CLEAN Helpdesk and an information note on “Our approach to integrating Gender Equity, Disability, and Social Inclusion (GEDSI) into technical assistance requests”. The CLEAN Helpdesk takes an intersectional approach and has provided evidence on the risks facing different groups, including children, people with disabilities, indigenous peoples, and women, alongside providing guidance on how to promote their inclusion and leadership.

Assessment of whether the programme continues to represent value for money

The CLEAN Helpdesk continues to represent strong value for money across all four VfM dimensions – economy, efficiency, effectiveness and equity. Cost control remains robust, with the average expert day rate well within the benchmark rates outlined in the POMM. The use of a pre-screened roster, individual experts and non-profit delivery partner for CLEAN based in the Global South ensures competitive pricing and avoids mark-ups, while sourcing copy-editing and design services from local Global South suppliers further strengthens the economy case. Where higher rates were necessary for niche expertise, discounts were negotiated, and approvals secured, demonstrating prudent financial management and effective cost oversight.

The programme has also maintained a strong record of efficiency and delivery. The ‘service ceiling’ of 20 days per request continues to drive cost discipline and timely outputs, with larger assignments exceeding this threshold only when impact justified additional inputs. Co-financing with other programmes such as PHENOMENAL and the Nature Facility, and collaboration with CEFAS, further enhance efficiency and maximise the use of CLEAN resources. User feedback evidences the effectiveness and utility of CLEAN support, with 96% of respondents reporting that TA has strengthened their confidence and knowledge for designing and monitoring CEN outcomes. The platform’s gateway function has also enabled better triage and access to TA across HMG, as intended in the business case.

CLEAN’s embedded approach to GEDSI mainstreaming ensures equitable delivery and reinforces VfM by integrating inclusion and safeguarding considerations within all TA requests, rather than as standalone activities. This approach enhances the quality and sustainability of outcomes, ensuring that TA contributes to inclusive and resilient climate action. Overall, CLEAN continues to deliver high-quality, cost-effective technical assistance that remains relevant, efficient, and equitable—fully justifying its continuation as a strong value-for-money investment.

E: RISK

Overview of risk management

The CLEAN Helpdesk continues to maintain an active and structured approach to risk management, using the SSN risk management process and monthly reviews with consortium partners. The risk register is updated regularly, with the top five to six priority risks reflected in the Quarterly Progress Report (QPR). Risks cover political, compliance, fiduciary, operational, partnership, delivery, and reputational dimensions. All consortium partners are invited and encouraged to contribute to the risk register, ensuring risks are identified early and mitigation strategies are collectively owned.

The overall risk rating for CLEAN is minor and over the past 12 months the programme has encountered a number of different risks (all within risk appetite) which are reviewed at regular intervals.

During this reporting period, no high (red) risks were recorded, though several medium (amber) risks required close management. The most significant risks relate to uncertainty over programme options beyond March 2026, potential fluctuations in demand linked to changing FCDO priorities , and internal capacity pressures due to sustained high levels of activity. These are being mitigated through continued engagement with FCDO and a risk-sharing financial model (more details in section F), active pipeline management, and strategic resource reallocation. Proactive communication and recruitment have helped stabilise delivery and maintain responsiveness to requests. Operational and delivery risks, such as underspend in FY 25/26 Q1 and Q2 and low engagement from requesters for interviews for case studies and website sign-ups, are being managed through targeted interventions, with positive early results. For example, since August – September 2025 and following the CEIE cadre conference there has been an increase in demand for TA.

Overall, the programme’s risk profile remains stable and well controlled. The consortium’s consistent monitoring, adaptive planning, and strong internal coordination have ensured timely mitigation and prevented escalation of key risks. The team remains agile and responsive, with regular oversight through fortnightly calls and monthly reviews, ensuring that risks are effectively managed as the programme moves into the latter stages of delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Year	Actual Spend (£) (cumulative)	Budget (£) (cumulative)	% Spent
23/24 (Q3+Q4)	339,131.71	600,000	56.52
24/25 (Q1-4)	1,717,148.93	1,800,000	95.40
25/26 (Q1+Q2)	2,154,040.40	3,300,000	65.27
25/26 (Q3+Q4)	3,216,731.99*	3,300,000*	97,48%

  * Includes forecast spend in Q4.
 ** The approved business case allocation for CLEAN was £4 million.
     However due to delays in approvals this was reduced by £700,000 in year one reducing
     the total commitment to CLEAN to £3.3m

The CLEAN Helpdesk continues to demonstrate strong financial management and compliance with FCDO standards, with regular monitoring and forecasting undertaken jointly by the programme management and finance teams. Financial reporting remains timely and accurate, with clear documentation of expenditure. However, quarterly spend targets have been challenging to meet due to the inherently demand-led nature of the Helpdesk and the wider uncertainty linked to reduced UK ODA budgets. Variations in the timing and scale of requests have created fluctuations in quarterly spend, despite consistent delivery performance. The Helpdesk has recently seen a sharp spike in demand indicating renewed demand now that FCDO climate objectives are more precise and means that the overall spend targets are still likely to be met.

To mitigate these challenges of low spend rates and strengthen financial predictability, the programme has adopted a risk-sharing financial model, which includes base, probable and high spend scenarios. This approach provides greater flexibility to adjust delivery in response to changes in demand and funding availability while maintaining value for money and better management of the finances.

In agreement with FCDO, the programme will implement an over-commitment strategy for initial requests (30-50%) to help meet financial year spend targets more consistently. This approach recognises that not all forecasted spend activities will proceed at the same pace or at full cost and allows the Helpdesk to manage delivery pipelines proactively without risking underspend. Continued close coordination between the programme management team, consortium partners, and the FCDO SRO and PRO will ensure ongoing alignment between financial performance, delivery priorities and strategic objectives.

Financial management continues to support the programme’s strong Value for Money performance. Robust cost control, competitive procurement and strategic use of expertise from across the consortium ensure economy and efficiency, while regular financial reviews with FCDO promote transparency and accountability. The programme’s agile budgeting and over-commitment strategy are expected to further strengthen VfM by maximising the utilisation of available funds and maintaining delivery momentum in a constrained fiscal environment.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Following the Year 1 annual review, the theory of change, logframe and indicators were reviewed through participatory workshops with consortium partners and FCDO. In response to AR recommendations several indicators were revised to better measure outcomes and outputs, some targets were increased to raise ambition, and data sources were diversified to avoid overreliance on the feedback forms and annual user survey and better monitor progress in real-time.

Building on the learning from last year, regular monthly meetings between the MEL and programme management teams have been institutionalised to review progress against logframe indicators. These sessions provide a structured opportunity to reflect on monitoring data and user feedback, enabling timely adaptation and prioritisation. This is supported by a more robust process for collecting regular requester feedback – where CLEAN TA support is contingent on completing feedback forms.

Case studies are an additional means of qualitative data collection this year – developed through interviews with TA users to better understand and demonstrate CLEAN Helpdesk’s outcomes of supporting users to design programmes with potential to deliver co-benefits and to improve HMG capacity on inclusive and equitable CEN programming.

There is no evaluation linked to this programme.

Evidence
Feedback received from TA users - via feedback forms, interviews for case studies and regular communications - continues to be positive, indicating the value, relevance and usefulness of CLEAN TA support. Evidence collection on other aspects of CLEAN’s work has been more challenging to collect particularly where voluntary engagement is required. For instance, uptake of the annual user survey and a website feedback function has been low; however, website analytics has shown positive trends in site traffic following the publication of the newsletters.

Learning
Quarterly learning sessions have been held with all consortium members to reflect on various aspects of programme delivery, including MEL, GEDSI and building equitable partnerships. The three-day planning workshop in March 2025 provided an opportunity to reflect on achievements, challenges and changes needed to inform Year 2 delivery. Using the Theory of Change as the framework, the consortium reflected that progress had been positive overall, with several logframe targets revised upwards to reflect strong achievement to date.

The Equitable Partnerships Review (developed into an external-facing case study) found evidence of strong collaboration and a shared vision across CLEAN consortium partners attributed to the open and collaborative leadership style and good engagement from consortium partners as well as the SRO and PRO; however, the demand-led nature of helpdesks sometimes constrains co-creation and scope for broader influence. A light-touch partnerships check-in will be planned next quarter to maintain alignment.

A GEDSI-focused learning sessions, informed by the participatory GEDSI scan led by MEL partner, confirmed strong commitment and tangible progress in embedding GEDSI and safeguarding principles throughout the programme cycle. The GEDSI scan identified a number of contributing factors to successful GEDSI integration, including, having dedicated GEDSI expertise within the team, integrating GEDSI and safeguarding across the TA process, and providing tailored GEDSI and safeguarding trainings relevant to the CEN and helpdesk context. A follow-on GEDSI training session in August addressed remaining capacity gaps, focusing on navigating power dynamics and applying practical examples of GEDSI mainstreaming in TA requests to further build understanding. Findings from this process have been synthesised in a forthcoming learning brief.

Date of last narrative financial report	15 October 2025	Date of last audited annual statement	28 February 2025

Annexes
Annex A: list of ‘global’ or ‘regional’ requests that CLEAN is responding to (36 completed, 16 ongoing).

Completed:
No.	Request	Region	Date Completed
1	Green Growth Programme (DRC): Business Case	Africa	Y1: 02/2024
2	Electric Vehicles for Ethiopian Red Cross Society (ERCS): EOI Development	Africa	Y1: 08/2024
3	South Sudan Humanitarian and Resilience Programme (SSHARP) - Climate Risk and Adaptation Assessment (CRAA)	Africa	Y1: 09/2024
4	South Sudan Humanitarian and Resilience Programme (SSHARP): Climate Mainstreaming Assessment	Africa	Y1: 09/2024
5	Sexual and Reproductive Health and Rights (SRHR): Business Case	Global	Y1: 02/2024
6	Research and Evidence Division (RED) - Global Goal on Adaptation (GGA) Assessment and Analysis	Global	Y1: 06/2024
7	Energy Climate and Environment Directorate (ECED): Value for Money Guidance Note	Global	Y1: 06/2024
8	Partnerships and Infrastructure Team: ICF Guidance Note	Global	Y1: 06/2024
9	Manufacturing, Business Environment and Growth Gateway: Job Description	Global	Y1: 09/2024
10	Amazon Forest Programme: Business Case	South America	Y1: 04/2024
11	Support to Morocco Delegation for COP29	MENA	Y1: 06/2024
12	Humanitarian and Resilience Building Programming (Jordan): ICF Review	MENA	Y1:09/2024
13	Zambia: Girls’ Education and Women’s Empowerment and Livelihoods (GEWEL 2)	Africa	Y2: 03/2025
14	Sahel: Justice and Security in the Sahel region ICF Review	Africa	Y2: 03/2025
15	Ethiopia Crisis 2 Resilience (EC2R): Climate Risk and Adaptation Assessment (CRAA)	Africa	Y2: 06/2025
16	Ethiopia: Education Programme Logframe Development and support on ICF KPI identification	Africa	Y2: 09/2025
17	DRC: Review of Schools Construction Plans	Africa	Y2: 09/2025
18	Nepal: ICF Training and Strategy Review	Asia	Y2: 07/2025
19	Vietnam: Climate Mapping	Asia	Y2: 09/2025
20	DEFRA - Independent Evidence Panel on AMR Health	Global	Y2: 10/2024
21	Animal Health Systems Strengthening Programme: ICF Review	Global	Y2: 12/2024
22	Serious and Organised Crimes: Regional Review	Global	Y2: 01/2025
23	International Forest Unit - Land Use sector finance sector programming guidance	Global	Y2: 08/2025
24	ECED - Mainstreaming Nature in CCDRs	Global	Y2: 08/2025
25	Commercial Agriculture for Smallholders and Agribusinesses (CASA) programme: Climate Risk Assessment Tool	Global	Y2: 07/2025
26	Commercial Agriculture for Smallholders and Agribusiness (CASA) programme: ICF Review	Global	Y2: 07/2025
27	ICF Guidance Note for Social Protection Team	Global	Y2: 02/2025
28	Global Agriculture and Food Security Programme (GAFSP): ICF Review	Global	Y2:03/2025
29	Global Goal on Adaptation (GGA) negotiation support	Global	Y2: 12/2024
30	Negotiations Support to North African Countries ahead of COP 29	MENA	Y2: 11/2024
31	SB60 Negotiations Support (Morocco)	MENA	Y2: 11/2024
32	Egypt: Climate Initiative Impact Evaluation	MENA	Y2: 09/2025
33	Jordan: Mining Diagnostic Study	MENA	Y2: 09/2025
34	Kurdistan Region: ICF Opportunity Mapping for KRG	MENA	Y2: 09/2025
35	Jordan: Climate and Environmental Scoping	MENA	Y2: 07/2025
36	Syria: Climate Recovery Support and Earthquake Resilient Schools	MENA	Y2: 03/2025
Ongoing:
No.	Request	Region	Date Requested
1	CRiSP: ICF and Results Framework	Africa	Y2: 08/2025
2	Ethiopia: Guidance Note for Climate Risk information	Africa	Y2: 10/2024
3	Indonesia: Review of Low Carbon Development Initiative programme phase two (Country Business Planning)	Asia	Y2: 08/2025
4	Education: COP28 Declaration on Education and climate change	Global	Y1: 09/2024
5	ICF-badging in Education Programmes	Global	Y1:09/2024
6	ECED - Evaluation Unit: ‘Best Buys’ Evidence Piece	Global	Y1: 09/2024
7	Mapping Climate Finance Mechanisms in Education	Global	Y2:03/2025
8	Serious and Organised Crimes: Case Studies	Global	Y1: 07/2024
9	GGA Analytical Support for Negotiators	Global	Y2:02/2025
10	ECED: Integration of nature into DSA and LIC-DSF	Global	Y2: 03/2025
11	Climate-Health Nexus Case Studies	Global	Y2: 05/2025
12	CEFAS: Regional analyses literature review: Caribbean	Global	Y2: 10/2024
13	CEFAS: Regional Analysis literature review: Pacific	Global	Y2: 10/2024
14	CEFAS: Regional Analysis literature review: Comoros	Global	Y2: 10/2024
15	Department of Health and Social Care (DHSC) ICF Review	Global	Y2: 12/2024
16	Syria: Building Local Resilience in Syria Programme	MENA	Y1: 05/2024
17	Lebanon: Updating the National Renewable Energy Plan (NREAP 2024-2030)	MENA	Y1: 02/2024
18	Yemen: Climate Security Programme	MENA	Y2: 11/2024

Annex B: Case studies

Number	Title	Logframe indicator	Year
1.	Amazon Catalyst for Forest Communities programme	Outcome 1.2 (a)	Y1
2.	Strengthening climate resilience programming in Zambia	Outcome 2.2 (a)	Y2
3.	Strengthening climate, environment and nature programme outcomes in the Congo Basin	Outcome 2.2 (b)	Y2
4.	CLEAN technical assistance related to climate finance and education	Outcome 2.2 (a)	Y2
5.	CLEAN technical assistance related to GEDSI integration for a Jordan mining diagnostic	Outcome 2.2 (b)	Y2
6.	Mainstreaming climate into Humanitarian and Resilience programming in Jordan	Outcome 2.2 (a)	Y2
7.	Supporting programme design in the face of shifting government priorities	Outcome 2.2 (a)	Y2
8.	Strengthening ICF Reporting and Climate Linkages in the Justice and Stability in the Sahel Programme	Outcome 2.2 (a)	Y2
9.	Integrating Nature into the Global Financial System	Outcome 2.2 (a)	Y2