Business Case

Summary Sheet

Country Plan Summary: South Sudan is the world’s third most fragile state and ranks last out of 191 countries in the UN Human Development Index. Progress towards democratic elections and implementation of the 2018 Peace Agreement is significantly off track. Multiple political and intercommunal conflicts, the war in neighbouring Sudan, a deteriorating economy, gender inequality, and vulnerability to climate-driven shocks means that South Sudan is caught in a fragility trap. In this context, sustainable development remains extremely challenging, and humanitarian and development support is critical to saving lives. / Since South Sudan’s independence in 2011, the UK has sought to promote stability through preventing and reducing the systemic drivers of conflict and promoting peace; supporting the establishment of democratic and accountable institutions; providing humanitarian assistance to alleviate suffering and build resilience; and delivering essential services. This programme directly contributes to British Embassy Juba’s Country Plan. Better health outcomes contribute to empowering women and girls, driving long term economic growth, and providing opportunities to address conflict drivers and contribute to peace. / We will continue to use ODA to support direct delivery of essential health services to save lives. However, we will now channel our efforts through a ‘partnership’ with the Government of the Republic of South Sudan (GRSS), in line with the Foreign Secretary’s modernising development agenda. We will use our diplomatic, policy, and programmatic levers to strengthen core building blocks of South Sudan’s health system and encourage GRSS to spend more of its resources on the health of its population. / Our approach is in line with the Foreign Secretary’s priority to ‘harness health and education opportunities and build human capital to drive growth’. We will focus on ‘improving equitable health outcomes through a renewed approach to multilateral leadership and country partnerships’.

Title: Strengthening the Health System and Provision of Essential Services in South Sudan (SHAPES)
Programme summary / South Sudan has the highest maternal mortality rate in the world. One in 10 children are not expected to reach their fifth birthday. The health system is strained and made worse by the ongoing war in Sudan following an influx of refugees and returnees. The SHAPES programme aims to save lives through improving the coverage of quality reproductive, maternal, newborn, and child health (RMNCH) services and the responsiveness and efficiency of the health system, whilst also supporting GRSS to take on stronger leadership, management, and responsibility for the health system. Our long-term goal is to significantly reduce maternal, newborn, and child mortality rates.
What is the rationale for UK Aid spending? / Responding to health and humanitarian needs in South Sudan is a priority for the UK. 75% of this five-year humanitarian plus programme will deliver lifesaving essential RMNCH services and commodities nationwide, including for displaced populations from Sudan. Through reducing inequitable access to basic services, one of the major drivers of grievance and conflict in South Sudan, it will contribute to the Foreign Secretary’s priority to ‘prevent and reduce the systemic drivers of violent conflict’. Our approach, building ‘a genuine partnership’ with the government and the World Bank, is based on the ‘beyond aid’ and ‘alliance-based’ model outlined in the Development Review, and the Lusaka Agenda. We will embed a more sustainable division of labour between humanitarian and development-funded services, and provide an entry point for other sectors, through gathering lessons learnt from our new ‘partnership’ approach with the government.
Programme Value: Up to £123.2m UK funding.		Country/ Region or Sector: South Sudan, Health Sector
Department/Country Office confirmation of review processes / British Embassy Juba / West Africa, Sahel, Sudan and South Sudan Directorate		Sebastian Fouquet OBE, Development Director. / Confirmation that Departmental processes for BC review were followed prior to submission.
Contact names:		Ayesha Ragunathan-James, Health Adviser, British Embassy Juba / Gemma Walters, Programme Manager, British Embassy Juba / Jill Fletcher, SRO, Essential Services Team Leader, British Embassy Juba
Threshold for final approval of Business Case: Minister; All programmes over £200m must be approved by HMT
Date of Approval of Concept Note:	28/09/2022	Name and role of Approver: Minister Gillian Keegan
Date of Approval of Business Case:		Name and role of Approver: Minister of State for Development, Baroness Chapman
Programme Code: 301416	AMP Start Date: Expected 01/05/2025	AMP End Date: 30/04/2030
Overall programme risk rating:	Major

Contents

## Table of Acronyms
ANC - Antenatal care
ARRO - Africa Rapid Response to Outbreaks
BE Juba - British Embassy Juba
BEmONC - Basic Emergency Obstetric and Newborn Care
BHWs - Boma Health Workers
BPHNS - Basic Package of Health and Nutrition Services
CAA - Central assurance assessment
CEmONC - Comprehensive Emergency Obstetric and Newborn Care
CERC – Contingent Emergency Response Component
CERHSP - COVID-19 Emergency Response and Health Systems Preparedness
CHD - County Health Department
CMP - Centrally Managed Programmes
CRSV - Conflict-related sexual violence
CRVS - Civil registration and vital statistics system
CSOs – Civil society organisations
CYPs - Cost per Couple Years of Protection
DALYs - Disability Adjusted Life Years
DHIS2 - District Health Information System 2
DTP1 - Diphtheria-tetanus-pertussis first-dose
ECD – Early Childhood Development
ECHO – European Community Humanitarian Aid Office
EFASS - Education for All South Sudan
eLMIS - electronic Logistic Management Information Systems
EQUAL - Ensuring Quality Access and Learning for mothers and newborns in conflict-affected contexts
ESS - Environmental and social safeguards
EST – Essential Services Team
EWARS - Early Warning, Alert and Response System
FCAS - Fragile and conflict affected state
Gavi – Gavi, the Vaccine Alliance
GBV - Gender Based Violence
GBVPSS – Gender Based Violence Prevention South Sudan
GDD - Global Development Delivery
GDP - Good Distribution Practice
GEMFA - Global Evaluation and Monitoring Framework Agreement
GFATM – Global Fund to Fight TB, Aids, and Malaria
GHIs - Global Health Initiatives
GRSS - Government of the Republic of South Sudan’s
HCWs - Health workers
HDPG - Health Development Partners Group
HMG – His Majesty’s Government
HPF - Health Pooled Fund
HRIS - Human resources information system
HSC - High-Level Steering Committee
HSDG - Health Sector Donor Group
HSS - Health System Strengthening
HSSP - Health Sector Strategic Plan
HSTP - Health Sector Transformation Project
HWCN - Healthy Women, Children and Newborns
IAD - Internal Audit Department
ICAI – Independent Commission for Aid Impact
IDA - International Development Association
IDPs - Internally displaced persons
IDSR - Integrated Disease Surveillance
IHR - International Health Regulations
IMF - International Monetary Fund
IOM - International Organisation for Migration
IP – Implementing Partner
IPC - Infection Prevention and Control
IRF - Internal Risk Facility
LLINS – Long-lasting insecticide treated bed nets
LMICs - Low and middle-income countries
MDTF - Multi-Donor Trust Fund
MEL - Monitoring Evaluation and Learning
MHPSS - Mental Health and Psychosocial Support
MHRA – Medicines and Healthcare Regulatory Authority
MO – Management Organisation
MoFP - Ministry of Finance and Planning
MoH - Ministry of Health
MoU - Memorandum of Understanding
MUAC – Middle upper arm circumference
NNGOs/ INGOs – National/International Non-Governmental Organisations
NGOs – Non-Governmental Organisations
ODA - Overseas Development Assistance
OPD - Outpatient Department
OSC - Operational Steering Committee
PCR - Project Completion Report
PDCT – Programme Delivery Commercial Team
PFP - Programme Funded Posts
PHC – Primary Healthcare
PHCCs – Primary Healthcare Centres
PHCUs - Primary Healthcare Units
PHRST - Public Health Rapid Support Team
PMU - Project Management Unit
PNC – Postnatal care
POCA - Proceeds of the Crime Act 2002
PPE - Personal protective equipment
PRO - Programme Responsible Owner
PrOF - Programme Operating Framework
PRSEAH - Preventing and responding to sexual exploitation, abuse and harassment
PSED - Public Sector Equality Duty
PWD - Persons with disability
QoC - Quality of care
R-ARCSS - Revitalised Agreement on the Resolution of the Conflict in the Republic of South Sudan
R-NDS - Revitalised-National Development Strategy
RMNCH- Reproductive, maternal, neonatal, child, and adolescent health
RSH - Resource and Support Hub
SAA - Standard Administrative Agreement
SBA - Skilled birth attendant
SMART- Specific, measurable, achievable, relevant and timely
SMoH – State Ministry of Health
SOPs - Standard operating procedures
SRHR - Sexual Reproductive Health and Rights
SRO - Senior Responsible Owner
SSHARP - South Sudan Humanitarian Assistance and Resilience Programme
TA - Technical assistance
ToC - Theory of change
TORs – Terms of Reference
TPM - Third-party monitoring
TRAs – Travel Risk Assessments
UNFPA – United Nations Population Fund
UNICEF - United Nations Children’s Fund
UNMISS – United Nations Mission in South Sudan
USAID – U.S. Agency for International Development
VfM - Value for Money
WASH - Water, Sanitation and Hygiene
WB - World Bank
WHO - World Health Organisation
WISH-Dividend - Women’s Integrated Sexual Health – Dividend
Strategic Case

Children born in South Sudan face significant health challenges at every stage of their lives. One in every ten children die before they turn five. Preventable diseases such as malaria, diarrhoea, and pneumonia continue to threaten lives. South Sudan also has one of the highest maternal mortality rates in the world, with an estimated 1,223 women dying per 100,000 live births due to pregnancy-related causes.[1] The Government of the Republic of South Sudan (GRSS) spends proportionally less on health than most other countries. In 2022/23, little more than 1% of GDP, and 0.5% of total government expenditure was spent on health. Delivery of essential health services is critical to delivering the Foreign Secretary’s priority for building ‘human capital’ through a healthy and well-nourished population, to drive South Sudan’s future economic development, security, and stability.
[1] Estimates developed by the UN Inter-agency Group for Child Mortality Estimation (UNICEF, WHO, World Bank, UN DESA Population Division) at childmortality.org

This strategic case outlines the profound reproductive, maternal, newborn, and child health (RMNCH) needs in South Sudan, and explains why FCDO should continue to invest in its health sector.

### A1: South Sudan Overall Context

South Sudan is the third most extremely fragile country in the world.[2] Following independence in 2011, South Sudan fought a five-year civil war which ended in 2018 with the signing of a peace agreement, the Revitalised Agreement on the Resolution of the Conflict in the Republic of South Sudan (R-ARCSS). The R-ARCSS sets out steps for the Transitional Government of National Unity to build democratic and peaceful institutions and hold elections. However, in September 2024, the GRSS extended R-ARCSS for a second time, delaying the country’s first elections until December 2026 and the tenure of the transitional government for a further two years.
[2] https://fragilestatesindex.org/country-data/

The R-ARCSS has embedded an elite power-sharing deal in the transitional government, formalising a rentier economy in which power and political influence are reliant on vast patronage networks, incentivising extraction of state resources and local-level violence to control rents.[3] The state lacks the ability to responsibly raise and manage public finances in the interest of its people. The GRSS has deprioritised spending on health and instead prioritises funds for personal gain and other sectors. Lack of accountability in the use of public resources and untransparent governance, combined with increasingly restricted civic, political and media space, has left citizens disempowered, lacking confidence in government but unable to hold their political leaders to account for providing essential services, safety, and security. The continued failure to implement R-ARCSS is likely to exacerbate conflict dynamics across the country and stymie potential for positive change.
[3] Death by Peace: How South Sudan’s Peace Agreement Ate the Grassroots, African Arguments

### A2: Fragility Trap

The world’s youngest country remains stuck in a fragility trap driven by five interconnected crises, which have severe implications on the health sector and health outcomes.
Fragility trap - impacts RMNCH outcomes
Conflict
Govern-ance crisis
Unstable economy
Climate crisis
Gender inequality

Multi-dimensional and inter-linked conflict: Although the 2018 Peace Agreement nominally brought an end to the civil war, subnational violence has increased and affected wider swathes of the country each year since.[4] Since March 2025, political tensions between the two main political parties have turned into military clashes in Upper Nile State. Local conflict, often fuelled by elites, is intractable and linked to political competition at the national level. 1,275 people died in 2023 as a direct result of violent conflict. Violence remains the main driver of internal displacement and humanitarian needs. There are 2 million internally displaced persons (IDPs), and 2.2 million South Sudanese refugees in the wider region. Conflict contributes to psycho-social trauma, Gender Based Violence (GBV), and conflict-related sexual violence (CRSV). Impacts are disproportionately borne by the most vulnerable, particularly women and children, IDPs, and people with disabilities.[5] Health facility infrastructure is often looted, damaged, or destroyed, supply routes blocked, and access to and availability of services deliberately manipulated by armed groups. Insecurity led to the closure of at least four health facilities for between one and ten months in 2022-23.[6] Health workers (HCWs) have been displaced, kidnapped, and killed. In addition, ongoing conflict in neighbouring Sudan since mid-April 2023, has led to an influx of over 675,000 returnees and refugees, increasing the burden on services and the risk of disease outbreaks, such as cholera. Conflict distorts domestic finance priorities, further reducing investment in health.
Figure 1: Fragility Trap
[4] ACLED | Bringing Clarity to Crisis (acleddata.com)
[5] UNFPA (2016) 10 things you should know about women & the world’s humanitarian crises: https://www.unfpa.org/fr/node/14963
[6] Health Pooled Fund Phase 3 Annual Report, 2022-23.

Governance crisis: GRSS lacks a coherent long-term vision that prioritises the health and needs of its citizens. It instead focuses on short-term personal enrichment through which elites manipulate patronage networks to stay in power and compete for control through armed violence. Institutions are weak and oversight functions are often toothless.

Unstable economy: An estimated 80% of the population lives below the international poverty line of $1.90 per person per day.[7] Almost half (46%) of the population were at crisis or worse levels of food insecurity between September and November 2023.[8] Conflict, economic mismanagement, corruption, inflation, and over-reliance on oil production has contributed towards a weak economy. South Sudan ranks as the most corrupt country in the world in Transparency International's 2024 report.[9] Oil production is subject to many barriers, including the civil war in Sudan, flooding, and aging equipment.[10] Recent damage to oil pipelines has starved the Government of two thirds of its revenue, and similar failures could occur again. Since the beginning of 2024, GRSS’ poor economic response to the crisis has led to significant inflation and currency depreciation, and it has in turn lost control of the macroeconomy.
[7] World Bank South Sudan Country Economic Monitor: Investing in Humans, 2023. World Bank Document
[8] South Sudan: Acute Food Insecurity Situation for September - November 2023 and Projections for December 2023 - March 2024 and for April - July 2024 | IPC - Integrated Food Security Phase Classification (ipcinfo.org)
[9] Transparency International Corruption Perceptions Index 2024 (transparency.org)
[10] World Bank South Sudan Country Economic Monitor: Towards a Job Agenda, 2022. World Bank Document

Accelerating climate crisis: South Sudan is ranked as the second most vulnerable country to natural hazards.[11] Climate projections suggest that by the 2050s South Sudan will be subject to temperature increases of 1–4°C, and increased high intensity rainfall events.[12][13] More than 1 million people were affected by severe flooding in 2022, which has occurred every year since 2019.[14][15] Climate induced natural disasters drive conflict and undermine communities’ resilience, contributing to economic losses, displacement, water scarcity and food insecurity.[16] Flooding and extreme heat have constrained access to health services, and impacted ecosystems, migration, food security, and transmission patterns for infectious diseases such as malaria and yellow fever. Although GRSS published its First National Action Plan for Climate Change in 2021, a vulnerability assessment of the health sector to inform adaptation and mitigation priorities has yet to be undertaken.[17]
[11] INFORM > INFORM Risk > Risk Facts & Figures (europa.eu)
[12] South Sudan Climate Change Adaptation Report, Climate Mainstreaming Facility, March 2022
[13] First National Adaptation Plan for Climate Change – Republic of South Sudan (2021)
[14] This figure includes Abyei Administrative Area
[15] Humanitarian Needs and Response Plan: South Sudan, 2024. South_Sudan_HNRP_2024.pdf
[16] South Sudan: IPC Acute Food Insecurity & Malnutrition Snapshot - Acute Food Insecurity: October 2022 – July 2023; Acute Malnutrition July 2022 – December 2023 - South Sudan | ReliefWeb
[17] First National Adaptation Plan for Climate Change Republic of South Sudan | United Nations Development Programme (undp.org)

Systemic gender inequality: It is estimated that 52% of South Sudanese women marry before they reach 18 years, and a third of all girls fall pregnant before turning 15.[18] Gender inequality contributes to lower demand for RMNCH services. Health workers frequently face threats and aggression by male partners and relatives when delivering family planning services. Adolescents are especially vulnerable given the risks of early marriage and dropping out of school[19]. An estimated 3.1 million children and adolescents are at risk of violence, exploitation, and neglect and are in acute need of immediate child protection.[20] In 2022, UNFPA reported that an estimated 2.6 million people were at risk of GBV, a 25% increase on 2021 estimates. Whilst policy and legal documents commit to ending child marriage and promoting human rights, child marriage remains the least rejected GBV practice and the transaction of the bride price between families continues.[21][22][23]
[18] State of the World’s Population, 2023. UNFPA.
[19] WHO. (2009). Generating demand and community support for sexual and reproductive health services for young people: A review of the literature and programmes. Department of Child and Adolescent Health and Development, WHO Geneva
[20] South Sudan Humanitarian Needs Overview 2023 (November 2022) - South Sudan | ReliefWeb
[21] National Girls Education Strategy 2018-22
[22] Revised National Development Strategy: Consolidate Peace and Stabilise the Economy (2021-24).
[23] Some things are not fit for children – marriage is one of them (unicef.org)

The result of the fragility trap is a humanitarian crisis that affected approximately 9 million people in 2024, at least three quarters of the population.[24] Conflict, widespread flooding, food insecurity, inflation, high food prices, and gender inequality all compound to limit access to and utilisation of health services, in turn impacting RMNCH outcomes. The international community, through humanitarian assistance and maintaining basic health services, has provided a safety net for millions of South Sudanese citizens in the absence of a functional state. However, only 75% of the 6.3 million people in need of humanitarian assistance were targeted in 2024.[25] Reduced humanitarian support following ODA cuts means that humanitarians are unlikely to reach their target.
Figure 2: Estimated national health need and severity (Humanitarian Needs and Response Plan 2024)
[24] Humanitarian Needs and Response Plan: South Sudan, 2024. South_Sudan_HNRP_2024.pdf
[25] Humanitarian Needs and Response Plan: South Sudan, 2024. South_Sudan_HNRP_2024.pdf

### A3: Health and Nutrition Challenges

As a consequence of the fragility trap, South Sudan has profound RMNCH needs, with one of the highest maternal and child mortality rates globally.[26]
[26] Estimates developed by the UN Inter-agency Group for Child Mortality Estimation (UNICEF, WHO, World Bank, UN DESA Population Division) at childmortality.org

The maternal mortality ratio is estimated at 1,223 deaths per 100,000 live births.[27] Mothers face extraordinary obstacles to access services. Approximately 31% of all pregnant women receive antenatal care (ANC) and less than half (40%) of women deliver in a health facility with a skilled birth attendant (SBA).[28] Only 8% of women received postnatal care within two days of giving birth. The leading causes of maternal deaths, haemorrhage, hypertension, and infection are treatable with basic and comprehensive emergency obstetric care (BEmONC and CEmONC). However, availability, access to, and referral between BEmONC and CEmONC services in South Sudan is limited. The neonatal mortality rate is estimated at 40 deaths per 1,000 live births.[29]
[27] Maternal mortality ratio (modelled estimate, per 100,000 live births) - South Sudan | Data (worldbank.org)
[28] UNICEF (2024), Country Profiles, available at: https://data.unicef.org/country/dji/ [accessed 18th Oct 2024]
[29] United Nations Inter-agency Group for Child Mortality Estimation (2023).

One in ten children are estimated to not reach their fifth birthday.[30] Malaria, pneumonia, and diarrhoea account for around 70% of all child deaths under five. South Sudan has one of the highest malaria incidences, with 2.8 million paediatric cases and 6,680 deaths recorded in 2022.[31]
[30] United Nations Inter-Agency Group for Child Mortality estimations, (2022)
[31] Gavi, Battling malaria, South Sudan anticipates roll-out of life-saving vaccines

South Sudan is home to one of the largest cohorts of zero-dose children in the world (72,096 children in 2022). As a result of suboptimal immunisation coverage, over the past year there have been outbreaks of measles, yellow fever, and vaccine-derived poliovirus.

Increased levels of malnutrition are driven by protracted food insecurity, poor childcare practices, insufficient health services and high disease prevalence.[32] Acute food insecurity has worsened year on year, with over 5.8 million people classified as in crisis or worse in November 2023. Between July 2023 and June 2024, an estimated 1.65 million children between 6 and 59 months suffered from acute malnutrition, which included 480,000 children with severe acute malnutrition.[33] Acute malnutrition increases the risk of preventable diseases such as diarrhoea, impacts foetal health, and drives intergenerational health outcomes, that are set to worsen under the climate crisis.
[32] South Sudan: Acute Food Insecurity Situation for September - November 2023 and Projections for December 2023 - March 2024 and for April - July 2024 | IPC - Integrated Food Security Phase Classification (ipcinfo.org)
[33] South Sudan: Acute Malnutrition Situation for July - September 2023 and Projections for October 2023 - March 2024 and April- June 2024 | IPC - Integrated Food Security Phase Classification (ipcinfo.org)

Access to comprehensive reproductive health care remains inadequate. The coverage of modern contraceptives is low with only an estimated 11.1% of all women aged 15-49 years using modern methods, with considerable variation across states (0%-20.6%).[34]
[34] Mini-Household Health Survey using LQAS in Four Health Pooled Fund States, 2023.

South Sudan is beset with infectious disease outbreaks, namely measles, anthrax, hepatitis, yellow fever, and cholera, and hosts 19 of the 20 neglected tropical diseases.[35] Outbreaks place increased pressure on the already weak health system, which is often reliant on the humanitarian system to respond.
[35] Sustaining the fight against neglected tropical diseases in South Sudan | WHO | Regional Office for Africa

People with disabilities struggle to access and afford healthcare and are among those most vulnerable to malnutrition. There is limited data on disability in South Sudan. It is likely that the last estimate of 5.1% in the 2009 census pre-independence reflects significant under-reporting. In 2020, 25.8% of households were estimated to have a person with a functional difficulty.[36] Client exit interviews from supported health facilities between July and September 2022 found that 3.3% (181/5,500) of respondents had a disability, with the majority facing eyesight or mobility challenges.[37] Conflict, poverty and poor access to services have increased the rate of disability. Children and mothers with disabilities have limited access to specialised services due to inadequate mainstreaming of disability into health services. People with disabilities face numerous attitudinal, environmental and institutional barriers, and a lack of concerted efforts to include them in society.[38]
[36] National Household Health Survey, 2020. Liverpool School of Tropical Medicine.
[37] Health Pooled Fund Phase 3 Quarterly Report, Quarter 2 (July to September) 2022.
[38] Rohwerder, B., 2018. Disability_in_South_Sudan.pdf (southsudanngoforum.org)

Long distances to the nearest functioning health facility are a key barrier to accessing healthcare for many people. Only 25.7% of the population are able to access a health facility within one hour.[39] This is compounded by other barriers including access constraints due to insecurity, risk of GBV, floods, poor infrastructure (South Sudan’s road density is among the lowest in Africa with 15km of road and only 0.2km paved road, per 1,000km of arable land), insufficient medicine, staff and equipment, and prohibitive costs.[40] Women, children, adolescents and people with disabilities are particularly vulnerable to the limited access to health care.
[39] HPF3-Access-to-healthcare-study-A-qualitative-analysis-report.pdf (kit.nl)
[40] https://www.worldbank.org/en/news/press-release/2012/05/18/world-bank-boosts-south-sudan-government-efforts-to-improve-rural-roads-and-increase-agriculture-potential#:~:text=At%20present%2C%20South%20Sudan%20only,101%20km%20to%201%2C000%20Km2.

Whilst 76% of the 1,988 health facilities in South Sudan are functional, only 11% provide the full Basic Package of Health and Nutrition Services (BPHNS).[41] Most facilities lack vital infrastructure elements, with only 28% of functional facilities having electricity and 47% an improved water source.[42] This results in inadequate availability of health services in many parts of the county.
[41] The BPHNS includes safe motherhood/essential obstetric care, antenatal care (ANC), delivery care, care for newborns, postpartum care, information, education, and communication. The primary healthcare unit (PHCU) is the immediate point of contact for ANC and postnatal care services. The services offered by Primary Health Care Centres (PHCC) include basic diagnostic laboratory services and maternity care while County and State Hospitals provide secondary care including comprehensive obstetric care.
[42] South Sudan Health Service Functionality Dashboard (shinyapps.io)

As a result, South Sudan still lags behind neighbouring developing countries on key health indicators, as highlighted in Table 1 below.

Table 1: Key Health Outcome and Service Delivery Indicators, South Sudan and Neighboring Countries
Country	South Sudan	Chad	DRC	Ethiopia	Kenya	Somalia
Total Fertility Rate	4.1	6.2	6.1	3.9	3.2	6
Percent of Married Women Using Modern Contraceptives	8	8	17	41	63	2
Infant Mortality Rate /1000 live births	64	64	60	34	31	68
Under Five Mortality Rate /1000 live births	99	103	75	46	41	106
Maternal Mortality Ratio /100,000 live births	1,223	1,063	547	267	530	621

Sources: World Population Dashboard, United Nations Population Dashboard for Total Fertility Rate and Percent of Married Women Using Modern Contraceptives. World Development Indicators, WB for Mortality data

### A4: Health System Building Blocks

Due to years of conflict, humanitarian crises, and underfunding, the health system in South Sudan is nascent, with service provision in government-run facilities at a lower quality than that provided by humanitarian actors. Table 2 analyses the capacity of South Sudan’s health system, against the WHO’s six building blocks (Figure 3): service delivery, health workforce, health information systems, access to essential medicines, financing, and leadership/governance.[43]
Figure 3: WHO Health Systems Framework
[43] World Health Organization. (‎2010)‎. Monitoring the building blocks of health systems: a handbook of indicators and their measurement strategies. World Health Organization. https://iris.who.int/handle/10665/258734

Table 2: Analysis of Health System Building Blocks in South Sudan
Health System Building Blocks
1.Service delivery	Significant health service delivery challenges persist across all health services. Supply-side gaps include aging and damaged physical infrastructure, stock outs of essential medicines, and a long history of suboptimal quality of care, and minimal reporting of data. Utilisation rates for family planning, nutrition, antenatal, and postnatal services are low. These gaps are the result of wider determinants of health such as patriarchal social norms, low road density, user fees, and conflict and climate shocks which make travelling to facilities even more difficult. Bottlenecks across each of the other five health system building blocks constrain the ability of GRSS and partners to deliver services. / Service delivery is fragmented across GRSS donor supported facilities, humanitarian support to IDPs, and the private sector. GRSS-run health services are delivered through primary health care units (PHCUs), centres (PHCCs), county hospitals, and state and referral hospitals. Since 2019, donors have supported the implementation of the MoH’s Boma Health Initiative (BHI) creating a cadre of over 5,000 full-time, trained, and salaried Boma Health Workers (BHWs). BHWs are embedded within the community and are trained to provide ANC, obstetric care, postnatal care (PNC), counselling for mothers who have delivered at home, kangaroo mother care (KMC) for low-birth-weight/ preterm babies, and referral. BHWs have increased access to basic health services and treatment of common childhood diseases. However, lack of education and training for BHWs contributes to limited equitable coverage of BHI across all Bomas. / Exiting from humanitarian support and transitioning to development led support is challenging due to the offer of higher Quality of Care (QoC) and package of services provided by humanitarian partners for IDPs. ODA cuts have necessitated a sudden halt to humanitarian supported service delivery in some counties, or transition to partners that support government-run health facilities. The government-run system provides a Basic Package of Health and Nutrition Services (BPHNS), which focuses on lifesaving interventions in GRSS health facilities. The health system cannot meet the additional demand, or the higher package of services provided by traditional humanitarian actors. The private sector plays a significant role in urban centres but there is limited oversight.
2.Health Workforce	A critical shortage of skilled healthcare workers impacts QoC and access. Salary payments by GRSS are consistently delayed and have not kept pace with inflation. Trained midwives and nurses receive a salary below the international poverty line. Health workers are reliant on donor incentives, paid by most partners in line with the 2019 Harmonised Incentive Scale, to remain in post. / The number of primary HCWs, clinical officers, midwives, and nurses, is insufficient to meet basic health and nutrition needs and is biased to urban areas. There are only 3.5 health workers per 10,000 people in South Sudan – well below the WHO recommendation of 44.5 health workers per 10,000 people.[44] Health facilities are staffed at only 10-20 percent of staffing norms. Although BHWs are meant to cover ~40 households in the community at a maximum, they often are relied upon to serve up 100 households. As a result, health facilities rely on SBAs and BHWs to detect and manage BEmONC.58,59 A separate cadre of Community Nutrition Volunteers focus solely on nutrition services, distorting services. / Training is limited, and the MoH depends on neighbouring countries to train its personnel. Low baseline education levels further limit the recruitment of qualified HCWs and BHWs. Without a human resources information system (HRIS), there is no reliable data on HCWs, locations, or qualifications, making gap analysis and planning difficult.
3.Health information systems	Limited reliable data makes planning and prioritisation challenging. Information systems are fragmented across disease specific health verticals, donors, and geographies. Data are recorded on paper-based registers at the facility level on infectious diseases and RMNCH indicators. County Health Department (CHD) officials are meant to input data into the District Health Information System 2 (DHIS2) and Integrated Disease Surveillance (IDSR) which is accessible to State and National MoHs. / Data is often inaccurate because overburdened staff at the facility level have little time to devote to data collection. Infectious diseases are reported by HCWs and BHWs via the Early Warning, Alert and Response System (EWARS), but this is often bypassed due to limited internet or network connection in rural areas. Furthermore, without a civil registration and vital statistics system (CRVS), there is a severe lack of accurate population data information on births and deaths, meaning that the country is reliant on surveys and estimates for key indicators (which are expensive and are not carried out frequently). The last Multiple Indicator Cluster Survey (MICS) was conducted in 2010, pre-independence. Donors collect data for their own programming, often within siloed disease verticals, and this is not always shared with the MoH or other partners.
4.Access to essential medicines	Health facilities experience regular gaps in the availability of pharmaceuticals. In the absence of strong pharmaceutical management capacity and consumption reports, a ‘push’ system is used to supply medicines.[45] This means that supply is often misaligned to needs and not based on utilisation and consumption data. Leakage, theft, and high levels of over prescribing result in stock outs of essential medicines and are likely to impact levels of antimicrobial resistance.
5.Financing	Severely low GRSS budget execution for health limits ownership and accountability for health and demonstrates GRSS’ reliance on donors. GRSS has not met its own commitment to the Abuja Declaration’s target of 15% allocation to health. Only $10m, approximately $0.83 per person was spent on health in 2022/23.[46] In the very same year, GRSS assigned $20m to meet the health expenses of Parliamentarians. Co-financing agreements to Gavi and the Global Fund have consistently not been met. / A MoH-commissioned WHO Health Sector Budget Execution Report in 2022, has not been published, despite lobbying by donors and development partners, raising concerns over its findings. One example of this is a $10m International Monetary Fund (IMF) loan in early 2023 that was reported by the MoH to have been used to procure drugs and medical commodities. However, an audit by the South Sudan National Audit Chamber found no evidence of the existence of these commodities despite the loan being fully executed, casting further doubt on MoH’s procurement capability. / Those without access to services provided by humanitarian and development partners pay for health expenditure out of pocket. In 2021, the WHO estimated that $33 per capita was spent out of pocket for health in 2021.[47] By way of context, a primary school teacher in 2021 earned only ~$10 a month, meaning that for many South Sudanese health costs can absorb a large portion of household resources, disrupting the ability to meet other essential needs, depleting assets, and driving people into poverty.
6. Leadership/ governance	Due to a complex donor landscape and limited government funding for health, the Ministry of Health (MoH) has struggled to provide political leadership. The MoH, as with other ministries across GRSS, lacks clear and effective governance, accountability, public financial management, and reporting structures. Accountability between MoH and external health partners is limited, and investments are fragmented and driven by external priorities. Many policy documents are unimplemented due to a lack of funding. / Almost half of government health facilities in South Sudan are supported by donor investments via international and national non-governmental organisations (INGOs/NNGOs). [48] This support has focused on saving lives through an essential package of services and provision of humanitarian assistance with some, but limited, system strengthening. It has not been sustainable or transformative due to third-party led delivery models, and significant gaps in health system building blocks, including GRSS’ limited political will to finance the sector and provide leadership.
[44] Lajul, G., & Morton, H. (2022). Boma Health Initiative - Successes and Opportunities in South Sudan. In Health Pooled Fund South Sudan. Crown Agents. https://hpfsouthsudan.org/wp-content/uploads/2022/04/The-Boma-Health-Initiative-1.pdf
[45] Health facilities receive supplies based on consumption estimates and forecasting, rather than being informed by accurate real-time stock level data, creating an inaccurate system whereby health facilities receive a standard package of commodities, regardless of need.
[46] Assuming a population of 12 million.
[47] Global Health Expenditure Database (who.int) accessed 12/10/2024.
[48] South Sudan Health Service Functionality Dashboard (shinyapps.io)

### A5: FCDO’s past investments in South Sudan and lessons learnt

1. Health Pooled Fund: The UK’s investments as lead donor to the Health Pooled Fund (HPF) programme from 2012 to 2024, supported essential health service delivery in originally five, then eight, and latterly seven of South Sudan’s ten states. HPF supported up to 1,000 health facilities by paying over 8,000 health workers a monthly incentive, providing in-service training and a regular supply of essential medicines and commodities. There have been three phases of HPF: HPF1 2012-2016; HPF2 2016-2018; and HPF3 2018-2024. FCDO held a contract with a fund manager, who worked in consortium with two other organisations, and managed a consortium of downstream INGO/NGO implementing partners to provide support, supervision, and direction to health facilities on core areas such as payment of incentives for HCWs, supply chain, and data collection.
2. The strength of the HPF programme helped to reduce fragmentation of donor investment, leveraging additional funding from Canada, the United States, Sweden, the EU and Gavi, the Vaccine Alliance worth around £30.5m in 2023/24. Despite this, there remains a plethora of donors and programmes across the country, thus further harmonisation is needed.

The UK’s programming and policy engagement under HPF enabled BE Juba Health Advisers and Team Leaders to build strong relationships with key decision-makers in the MoH and actors across the sector, such as INGOs, national NGOs, and humanitarian organisations. These relationships have given the UK strong influence over the health sector, enabling BE Juba to shape and steer decision-making on strategic health challenges, such as transitioning from HPF to HSTP, strengthening coordination at national, state, and county levels in the response to a cholera outbreak in 2024 and encouraging a longer-term approach to transitioning health sector support from humanitarian to government.

HPF Results: Although it has been difficult to measure progress in the absence of population surveys, our monitoring at the facility level has shown that HPF achieved substantial results. HPF3 has:
- provided over 33m curative consultations;
- reached 14.7m community members through health education sessions;
- immunised 1.5m children;
- registered 358,000 new family planning users and delivered 254,000 couple years of protection;
- supported more than 450,000 safe deliveries.

Statistical estimates produced by WHO show improved coverage on some RMNCH indicators following implementation of HPF. For example, the proportion of mothers attending at least one antenatal care (ANC) visit is estimated to have increased by 25.9% and the proportion of mothers who delivered with an SBA by 12.3% between 2015 and 2020. However, persistent high rates of maternal and child mortality remain concerning, and there is likely to be significant inequity at the subnational level across states, counties, and payams. HPF delivered some initial progress towards health systems strengthening in CHDs through implementing partners providing incentives, training, and hand-holding support on data collection and supply chain management. Implementing partners also located some of their own staff in State Ministries of Health (SMoH), which built capacities for supervision of the sector.

COVID-19 Emergency Response and Health Systems Preparedness (CERHSP): The World Bank supported service delivery, managed by the United Nations Children’s Fund (UNICEF), in the remaining three states through its CERHSP project. Provision of essential health and nutrition services was prioritised for the most vulnerable, including refugees and host communities in two of the hardest to-reach areas; Jonglei and Upper Nile states and Pariang County in Unity State.

Lessons learnt: HPF and CERHSP were the backbone of health service delivery in South Sudan for over a decade. They delivered services in a better Value for Money (VfM) and sustainable way than health services provided through humanitarian assistance. However, in the absence of government leadership, investment and systems building, they have not led to sustainable improvements in the sector.

Table 3: Headline lessons learned from HPF and CERHSP
Fragmentation	HPF and CERHSP programmes created an arbitrary geographical divide, with two separate systems offering distinct packages of services and processes for providing essential medicines and paying incentives to health workers. This ultimately created a challenging sector for the MoH to oversee. Within these programmes there are further divides across health verticals such as immunisation, nutrition, family planning, and humanitarian services.
National GRSS investment, leadership, and political will for health is insufficient	Throughout HPF implementation, GRSS lacked capacity and political will, and did not prioritise domestic resources to deliver health services independently. Despite consistent pressure by the UK and other donors for GRSS to spend more on health we have yet to see improvements on in-year disbursement of allocated funding to the MoH. / The GRSS takes on little responsibility for health service delivery and expects that donors will continue to fund the sector. HPF and CERHSP operated largely independently of the GRSS, through third-party led models, creating a false dependency on donors to meet the population’s health needs. Some capacity was built in County Health Departments (CHDs) through support from implementing partners, but they are some way from being able to coordinate services on their own, with significant geographic variations in capacity. / When HPF3 support was withdrawn from over 200 primary health care facilities and eight State Hospitals over the 2022/23 financial year due to reduced UK ODA budgets, despite GRSS agreeing to pick up these costs, there was no increase in domestic financing. Following the transition from HPF2 to HPF3 in 2018, GRSS agreed to take on responsibility for payment of HCW salaries from donors. They have not delivered on this commitment. As of February 2025, health workers last received a salary payment for August 2023 in February 2024. Salary values, even if paid, have been eroded by inflation. Current donor modalities have not helped incentivise the Government to take on more responsibility and provide additional financing impacting on sustainability.
Health systems strengthening in South Sudan is challenging	The context necessitated that HPF focus on delivering essential health services through third-party contractors, as opposed to directly strengthening GRSS systems. For example, the supply chain system was managed by a third-party contractor, with supplies kitted outside of South Sudan, and delivered to stores at the county level (without direct involvement of the NMoH and SMoHs). Staff in the NMoH were not paid salaries by GRSS since August 2023 (which were paid in February 2024), which limited their ownership and stewardship of the health sector. Although some capacity was built in CHDs, progress varied across states, and it was downstream implementing partners that were ultimately accountable for delivering services, managing the supply chain, and paying incentives. / Outside of service delivery, other health systems building blocks are at a nascent and weak stage, despite the sustained levels of donor investment into health over the past decade. This limits the efficiency and responsiveness of the health system to meet population needs. Going forward, investment in health system strengthening will be critical to lay the foundations for transitioning to a more sustainable health system in the future that relies less on donors. A key lesson learnt from HPF is that we need to test and better understand what systems strengthening and sustainability means in a fragile and conflict affected state (FCAS) without an elected government, and how it differs from global frameworks.
Low demand for RMNCH services at the community level impacts coverage of services	Despite the expansion of BHWs under HPF’s investments, utilisation of RMNCH services remains extremely low. UNFPA estimates at a population level, only 19% of births are attended by skilled health attendants, and the contraceptive prevalence rate for all methods is only 6%. It is important to recognise the difference between population-level estimates based on historic survey data, and the activity-level data collected by HPF3, which indicated that within HPF3 facilities, 554,397 institutional deliveries were recorded, of which 86.1% were attended by a skilled birth attendant. / A change in tack is needed away from focusing only on delivering RMNCH services in facilities, to increasing access, awareness, trust, and confidence in services at the community-level, particularly targeting for girls under 15 at risk of pregnancy and children under five. Tackling wider determinants of health such as distance to facilities and patriarchal social norms needs to happen through listening to communities, and hearing and valuing their solutions to critical challenges such as referral pathways for complicated pregnancy cases, malaria prevention, sexual reproductive health and rights (SRHR), and GBV awareness raising. / South Sudan’s changing political and conflict dynamics necessitates a service delivery approach which provides primary healthcare within communities, since they face extraordinary and often dangerous obstacles to reach health facilities. This is key to unlocking increased demand and utilisation, and in turn coverage, and saving lives in an FCAS.
South Sudan’s health system risks being overwhelmed by infectious disease outbreaks and wider health threats	Infectious diseases pose a major public health threat in South Sudan. Malaria is the leading cause of mortality and morbidity, affecting approximately half of the population. There have been recurrent outbreaks of yellow fever, measles, and cholera in recent years which threaten to overwhelm the health system with high caseloads. Active case finding and surveillance systems are constrained by a lack of funding, with a reliance on field officers under the Global Polio Eradication Initiative to support management of all infectious diseases. / Limited infrastructure and diagnostics, such as isolation chambers, infection prevention and control kits and laboratory capacity, hamper the ability of facilities to provide appropriate care. Disease outbreaks disrupt routine service delivery and contribute to maternal and child deaths.

### A6: FCDO’s investments and diplomatic priorities in South Sudan

The primary focus of the UK’s diplomatic efforts in South Sudan is to avoid a return to civil war. The BE Juba’s Country Plan is built on the premise that the best way to do this is through credible elections. The UK’s diplomatic engagement emphasises the need for government to urgently establish the conditions for peaceful, credible and inclusive elections by creating civic and political space, completing work to unify forces into a single army, ensuring that electoral institutions are resourced, and seeking commitments from all political parties not to use violence as a political tool. We use the breadth of our diplomatic, policy and technical engagement to clearly communicate our expectations of the South Sudanese state to establish stability, respect human rights, and take actions to lay the foundations for economic development and poverty reduction, with a particular focus on the most vulnerable – women and girls.

The UK, as a member of the Troika (Norway, US, UK), has political access to influential government interlocuters and acts as a convener within the international system. As a permanent member of the Security Council, the UK has a close and influential relationship with the UN Mission to South Sudan (UNMISS) and is able to engage and support UNMISS on the broader peace process, elections, constitution, and security. Using our technical and programmatic expertise, we lead conversations in priority sectors, influence multilateral decisions, build international consensus on key priorities and create a united front when engaging GRSS.

We continue to integrate our diplomatic, humanitarian and development activities to target the most vulnerable. We use the UK’s influencing, expertise and ODA resources to deliver humanitarian assistance to those most in need; reduce conflict; support the establishment of democratic and accountable institutions; tackle the impacts of climate change; and provide essential services. The ODA programmes listed below will complement and support this business case.

- South Sudan Humanitarian and Resilience Programme (SSHARP, 2024-2028) will support the humanitarian response and help communities to build resilience, with a particular focus on food security and nutrition, livelihoods, and providing protection services especially for women and girls.
- Education For All South Sudan (EFASS, 2025-2030) will support girls and children with disabilities to access, stay in, and complete school through direct financial support, provide accelerated learning for adolescent girls previously excluded from education, improve the quality of education and support school infrastructure through operational grants.
- Gender Based Violence Prevention South Sudan (GBVPSS, 2024-2029) will pilot effective approaches to tackle harmful norms that support GBV and strengthen the evidence base in conflict contexts. The programme will complement support for women and girls across the FCDO portfolio.
- South Sudan Peacebuilding Programme (SSPP, 2023-2026) builds the capabilities of communities in conflict hotspots to manage, reduce and prevent violent conflict, strengthens capabilities to spur action to implement the peace agreement and provides demand-driven conflict and political analysis to inform UK policy and programming in South Sudan.
- Monitoring and Learning in South Sudan (MLSS, 2024-2029) will provide BE Juba with better evidence on which to base policy, programming and strategic decisions. MLSS will increase accountability of partners through verification of results and ensuring agreed upon standards are being maintained throughout the delivery chain while also ensuring accountability to beneficiaries through a more systematic approach to beneficiary feedback.

### A7: The future of health programming in South Sudan

A key priority for the UK and other donors – alongside responding to the health needs of the population - is ensuring that GRSS commits to stronger investment in, and leadership of the health sector. As per the Health Sector Strategic Plan (HSSP) 2023-27, donors have agreed to harmonise and align support in the health sector in accordance with aid effectiveness principles.

The Health Sector Transformation Project: The sustainability agenda is already being spearheaded by the World Bank (WB). On 20 December 2023, the WB’s Board approved the Health Sector Transformation Project (HSTP) for South Sudan. The HSTP supports the delivery of a basic package of essential health services to all ten states and three administrative areas in South Sudan. The WB Board set the total project cost at USD$369.5m over three years (2024-27), which includes approximately a $117m contribution from the International Development Association (IDA). USD$242.5m is expected to be co-financed by other donor contributions. The finance agreement for HSTP became effective on 20th September 2024. UNICEF as the Management Organisation (MO) for service delivery, started implementation across the country in July 2024, following the closure of HPF. The UK has indicated its intention to contribute to HSTP on the basis of an approved Concept Note.

The GRSS Ministry of Finance and Planning (MoFP) signed a co-financing letter committing to fund USD$10m of domestic resources, in addition to its budget allocation for health, to support HSTP over the life of the programme. All HSTP donors, including the World Bank, understand that achieving the USD$10m contribution will be difficult given economic and political instability. In addition to advocacy for government financing, HSTP will deliver systems strengthening interventions, and implement governance mechanisms that aim to strengthen other elements of GRSS leadership, responsibility and accountability to health.

1. UK health advisers have inputted in and shaped the design of HSTP through discussions with the WB, UNICEF, WHO, and other donors over the past year. A particular focus has been minimising disruption to services during the transition from HPF to HSTP and ensuring that valuable experience and lessons from HPF were captured and taken forward in HSTP. The UK supported HPF Implementing Partners (IPs) at the county level to mentor incoming HSTP IPs on roles, responsibilities, and the local context, to support transition.
2. HSTP will facilitate the operationalisation of One Programme, One Budget, One Package of Services and One Reporting mechanism, with donors agreeing to consolidate their financial support and management approach alongside GRSS co-financing commitments. This approach aligns with FCDO’s objectives under the Lusaka Agenda, as well as deliverables under the Foreign Secretary’s priority outcomes for health. BE Juba will maximise FCDO’s central investments in Gavi, the Global Fund to Fight TB, Aids, and Malaria, and WHO, to ensure alignment with HSTP and GRSS’ priorities for systems strengthening. The project aims to:
- expand access to health services for host communities, refugees, remote and rural populations, women, and other marginalised groups through facility- and community-based interventions.
- incorporate climate-sensitive planning and service delivery to mitigate the health impacts of climate change.
- enhance the pharmaceutical supply chain, improve health information systems, and improve the quality improvement of health services.
- strengthen South Sudan’s health system for better access to services.
- improve the stewardship capacity of the MoH.
- enhance the health system’s ability to prepare for and respond to health emergencies and control disease outbreaks.

Outside of HSTP, various donors and partners are continuing to support different aspects of the health sector in South Sudan through both development and humanitarian programming, including:
- ECHO and US Centres for Disease Control and Prevention’s invests in Integrated Disease Surveillance and Response (IDSR) processes and laboratory systems. It is unclear whether CDC support will continue post 2025.
- Global Fund, USAID, and PEPFAR’s supports prevention and management of HIV and Tuberculosis. It is unclear whether PEPFAR and USAID support will continue post 2025.
- USAID supports the provision of family planning commodities through UNFPA and increased access to basic water and sanitation. It is unclear whether this support will continue post 2025.
- Global Affairs Canada is also supporting UNFPA to train midwives.

### A8: Why should the UK continue to invest in reproductive, maternal, neonatal, child, and adolescent health (RMNCH) in South Sudan?

As set out in the approved Concept Note, this programme will focus on investing in strengthening South Sudan’s health system to drive improved RMNCH outcomes. Most maternal, newborn and child deaths are preventable. We have proven, cost-effective interventions that could prevent about two-thirds of child deaths, half to two-thirds of newborn deaths and many maternal deaths.62 Access to contraceptives through family planning represents high value for money and brings concrete benefits to maternal, newborn, child and adolescent health, poverty reduction, and gender equality. Spacing between births increases newborn and child survival.63

Investing in maternal, newborn, child and adolescent health makes economic sense and benefits individuals, households, communities, and society. Households with healthier and better nourished mothers and children spend less on healthcare. Reducing catastrophic out-of-pocket expenditure on health care prevents families being pushed further into poverty. Preventing illness and promoting good health helps to reduce the cost of treating people when they are sick. In many places, every dollar spent on family planning saves four or more dollars that would otherwise have been spent to address complications of unplanned pregnancies (in later years the savings are even higher).65 However, the benefits of good health transcend costs; they also generate huge economic returns as healthy people work more productively improving their own lives and contributing to the economy. USAID estimated that maternal and newborn mortality leads to US$15 billion in lost potential productivity globally every year.66

Investing in RMNCH supports women and girls to achieve their full potential. Early marriage and pregnancy are the main causes of school dropout, can be life-threatening to the mother and increase the likelihood of poor outcomes for children. Tackling early pregnancies, reduces the impact on young mothers and their children and enables girls to stay in school and reach their full potential. Targeted investment in Sexual Reproductive Health and Rights (SRHR) and the unmet need of adolescents for integrated SRH services and information, including comprehensive sexuality education, will maximise effectiveness and secure life-long and intergenerational impact. Having a healthier, better educated society is also likely to contribute to the growth of the national economy and individuals’ and communities’ capacities to manage conflict and other shocks.

Investing in maternal, newborn, and child health has political benefits, including social stability and human security. UK funding for health is needed now more than ever to maintain stability and minimise needless deaths in the country. The confluence of rising political insecurity in South Sudan, the escalating conflict in Sudan, as well as the severe impacts of ODA cuts on the ability of humanitarians to provide essential services is affecting health outcomes. Conflict impacts individuals’ health and access to health services. Conversely a lack of, or unequal access to health and essential services can lead to grievances and feelings of exclusion, which are major drivers of conflict and violence, particularly in South Sudan. In some circumstances, lack of access to essential services can also lead marginalised groups to seek to renegotiate access for themselves, their families, and communities through armed violence. Delivering context specific and conflict sensitive health care can help to prevent this vicious cycle and contribute to stability. Health care can be a vehicle to improve trust and communications between citizens and the state; build collaboration on health governance and delivery; and improve social cohesion at the local level through community healing or inclusive health promotion initiatives.67 Donor investment in health services can be used to leverage GRSS leadership, responsibility and investment in the health sector.

### A9: What are the implications on health outcomes in South Sudan if the UK did not continue to invest in the health sector?

Withdrawal of UK donor support from health service delivery in the absence of increased GRSS investment and capability would result in increased maternal and child morbidity and mortality. Significant reductions in services would likely drive further breakdown in the nascent social contract between GRSS and communities, in turn fuelling conflict. Should the UK end bilateral support to the health sector in South Sudan, other donors’ resources would enable the continuation of some level of essential services. However, given the scale of UK funding, as the lead donor over the past decade, compounded by USAID cuts to health and humanitarian services, a withdrawal would create a substantial gap. It would risk eroding some of the health gains made under HPF and could weaken the health facilities and systems that our investment has supported. It would likely increase pressure for increased humanitarian-led health delivery, which is relatively more expensive and less sustainable and would compete for resources within an already over-stretched and underfunded humanitarian response. It would also deny the UK the opportunity to influence at the technical level through programme funded posts. In turn, this would reduce the effectiveness of FCDO’s contributions to Global Health Initiatives (GHIs) and centrally managed programmes in South Sudan.

Under HSTP, donors are already collectively testing a deliberately different but cautious approach to transitioning to greater GRSS leadership and responsibility for health service delivery. This business case sets out how UK bilateral health programming in South Sudan will evolve as part of that multi-donor approach. The chances of success are likely to be constrained if support does not align with – or undermines – political and financial interests of ruling elites. This change in approach will take time and programming will need to continually be backed up with policy engagement and diplomatic lobbying, not just within the health sector but across government more broadly. Any change we can positively influence will be incremental and will occur over the long-term. We expect that continued donor support will be required following the end of this programme.

### A10: Key considerations
Development Act: This programme will comply with the UK International Development Act 2016. It will provide lasting benefits for the population by increasing access to and the quality of health services. All IPs will be expected to incorporate “do no harm” principles in their approach, particularly when engaging with vulnerable people.

Gender Equality Act: The Gender Equality Act 2014 will be embedded within the programme. Women and girls will be prioritised through the provision of RMNCH services, GBV and nutrition services. The programme will also seek to challenge harmful gender norms held by community and household decision makers that increase maternal and child deaths. A ‘Significant’ Gender Equality marker will be applied to the programme and progress against results will be monitored through gender and disability-disaggregated results reporting where feasible, and annual reports. Finally, this programme will aim to strengthen the collection of data on gender equality dimensions within national information systems.

Public Sector Equality Duty (PSED): Compliance with PSED is assessed as strong. There are likely to be significant positive impacts on equality through delivering essential services to the population, and against the protected characteristics (most notably, disability, sex/gender, race, and ethnicity).

1. Disability: There is limited data on the prevalence of disability in South Sudan. It is highly likely that conflict and climate-related disasters have led to higher incidence of disability than the global average of 15%. Persons with disability (PWD) are more susceptible to the compounding effects of severe malnutrition, poverty, displacement, protracted violence, extreme weather events, and macro-economic crises. An International Organisation for Migration (IOM) survey in Malakal in 2021 found that 75% of PWDs are perceived to be at a disadvantage when accessing services, especially women and children.[49] The programme will strengthen the health system’s support to those with disabilities through requiring implementing partners to disaggregate data by disability where possible, and to strengthen health information systems to include disability indicators. Although it is not feasible for specialist disability services to be provided within this programme, all options will strengthen services to prevent disability, particularly at primary and secondary levels. The Alma-Ata Declaration calls for primary healthcare (PHC) systems that ‘address the main health problems in the community, providing promotive, preventative, curative and rehabilitative services’. Primary prevention of disability includes routine immunisation for polio and measles; and secondary prevention involves management of injury or malnutrition. The programme will also support community engagement and awareness-raising about disability to tackle discrimination and stigma.
  [49] IOM Disability Access and Inclusion Survey Findings, Aweil South County, February 2023
2. Conflict and Fragility: Intercommunal violence caused by ethnic tensions and disputes over resources such as land and cattle, is increasing, particularly in Abyei, Jonglei, Unity, and Upper Nile. In the last three months of 2023, UNMISS reported 233 incidents of violence across the country with 862 victims affected (406 killed, 293 injured, 100 abducted, and 63 subjected to conflict-related sexual violence).[50] Design of the programme will be informed by conflict sensitivity analysis and the expertise of BE Juba Conflict Advisers. We will encourage partners to draw on the UK funded conflict sensitivity and resource facility under the SSPP. Conflict data will be applied to ensure the selection and distribution of supported health facilities at sub-national level is guided by conflict-sensitive approaches. Partners will be required to integrate local conflict analysis into activity design and implementation to ensure context specific dynamics and risks are addressed.
  [50] UNMISS Quarterly Brief, March 2024

Safeguarding: South Sudan’s FCAS context increases the vulnerability of local populations to sexual exploitation, harassment, and abuse (SEAH). Although health facilities should be protective spaces, we also know that they can be sites of abuse and exploitation. This programme will support vulnerable people including children, victims of sexual and gender-based violence, people with disabilities and mental health challenges. All IPs will need to demonstrate zero-tolerance for inaction or mishandling of SEAH, through investing in structures to prevent, report and act on suspicions, and support survivors and victims. This will be codified in FCDO funding arrangements with partners (i.e. accountable grants, memorandums of understandings, and contracts).

All partners will undergo due diligence assessments of their safeguarding policies and procedures, including assessment of how they are implemented in South Sudan. If Partners are large multilateral organisations that FCDO has a bilateral framework agreement with, we will draw on a Central Assurance Assessment (CAA). BE Juba will not partner with any agencies without comprehensive safeguarding assurances. We will draw on our experience during HPF of putting in place robust procedures for monitoring and reporting, to proactively manage safeguarding risks in all components and ensure that the World Bank and other partners have substantive mitigations in place to manage fraud and SEAH. The programme will draw on expertise from Social Development Advisers, Safeguarding Champions, and the Safeguarding Unit to ensure that safeguarding policies, procedures and risk management are robust and effectively implemented during programme delivery. We will encourage IPs to utilise context specific resources, tools and guidance developed by the Safeguarding Resource and Support Hub (RSH) in South Sudan, to ensure that approaches to safeguarding are context appropriate.

1. Climate and Environment: South Sudan is highly vulnerable to intense flooding and drought, as a result of climate change. This has both direct and indirect implications for the health sector and health outcomes. Procurement and distribution of pharmaceutical commodities, an essential component to the programme, may contribute to climate emissions. IPs will be required to manage disposal of clinical waste in workplans at facilities in climate sensitive ways to reduce the risks to human and environmental health. Community level health education will include the promotion of safe water sanitation and hygiene practices, and the safe disposal of household refuse.
2. Counter Terrorist Financing and anti-money laundering: The risk of this programme funding terrorism is extremely low. The programme will comply with domestic law, particularly the Terrorism Act 2000, the Proceeds of the Crime Act 2002 (POCA), and the Money Laundering, Terrorist Financing and Transfer of Funds Act 2017. Strong financial controls and risk management will be implemented. FCDO will carry out due diligence assessments and compliance checks on suppliers, drawing on CAAs where relevant, who will cascade this to downstream partners to prevent aid diversion in high-risk delivery areas. Where FCDO contributes to a multilateral, we will delegate due diligence assessments of downstream implementing partners to the multilateral, having first sought confidence in its systems and controls through its CAA. All agreements will set out the expectation for partners to detect and report suspected cases.
3. Medicines Licensing Requirements: In line with FCDO’s MHRA medical license, this programme will comply with Good Distribution Practice (GDP). This stipulates that partners should be compliant with rules and regulations associated with the distribution of medicines in their respective territories. South Sudan’s Drugs and Food Authority has weak capacity and limited oversight powers. UNICEF and UNFPA, the key agencies which procure and distribute medicines engage with the Food and Drug Authority on how medicines meet international safety and quality standards. Procurement and distribution of medical commodities for this programme would be managed by UNICEF and IPs, not directly by FCDO.

Partnership Principles: The programme will inform, and be informed, by BE Juba’s Partnership Principles Assessment. It is anticipated that principle one on poverty reduction and delivering the SDGs, and principle three on strengthened financial management and accountability will be especially relevant. These directly relate to our high-level priority to see GRSS progressively increase its budgetary execution for quality essential services for its population.

Under the options outlined in the appraisal case, this programme would provide a very small amount of indirect financial aid to GRSS by contributing to the World Bank multi-donor trust fund (MDTF) to support this project. The World Bank HSTP has been designed as a government-led programme with third party implementation so that the large majority of funds will be channelled through third-party implementers (in this case UNICEF and WHO) which safeguards both service delivery and systems strengthening results (against low government capacity) and project finances (against mismanagement and or misuse by government). Nonetheless, a very small proportion (~1%) of project funds would be under GRSS management to support a Project Management Unit (PMU) which will provide oversight of the programme and build MoH capacity. Financial support required for the PMU would be safeguarded using the World Bank’s extensive fiduciary controls, including the use of a designated and separately maintained account with specific signatories, and which would require World Bank approval for all PMU withdrawals. Under this option, a Partnership Principles Assessment would not be used to manage this programme as the UK’s agreement would be with the World Bank not the GRSS. The funds delivered to the PMU would be minimal, and donor and government funds would not be mixed.

Aid Effectiveness: The UK has championed aid effectiveness in South Sudan through political, technical and programmatic fora. The programme will align to the South Sudan Health Sector Strategic Plan (2023-27) and deliver the Basic Package of Health and Nutrition Services (BPHNS) in GRSS health facilities. The programme will aim to harmonise donor investment and increase mutual accountability through strengthened co-financing arrangements and governance processes. It will also strengthen data for results and decision making. Investment in MoH capacity for oversight and policy development will enhance the effectiveness of future investments.

Risk: The overall programme risk level is major which reflects strategic, contextual, delivery, financial and safeguarding risks. All identified risks are within BE Juba’s risk appetite for all categories. South Sudan is a high-risk environment for fraud, losses, corruption, and safeguarding issues. Whilst we accept a high-risk appetite, we equally place strong importance on designing and implementing strong risk mitigation and management measures and in ensuring our partners understand our zero-tolerance approach to fiduciary and safeguarding risks. The Management Case includes a risk appetite statement for this programme.

### A11: Why should the UK intervene?

The UK is well placed to contribute towards the needs identified in this Strategic Case.
- Service delivery: We have over 10 years of experience leading, managing and learning from HPF to share with and apply to future RMNCH programming. The programme will maximise opportunities for advancing the immunisation, and malaria, TB, and HIV focuses of FCDO’s core investments into Gavi and GFTAM. We will also share learning from the WISH-Dividend SRHR programme.
- Health System Strengthening (HSS): The UK is a leader on HSS and has access to expertise on several of the six pillars of the health system across His Majesty’s Government (HMG). FCDO’s Health System Strengthening for Global Health Security and Universal Health Coverage Position Paper is a useful guide.[51]
  [51] Service delivery; health financing; supply chains; health workforce; health information systems; and leadership and governance.
- Technical Advice: FCDO’s substantial bilateral support to health has been complemented by BE Juba’s programme-funded technical advisory capacity. This technical advice has been valued by like-minded donors in South Sudan and GRSS. The UK currently co-chairs the Health Sector Donor Group. We are supported by UK-Public Health Rapid Support Team (PHRST) in our response to infectious disease outbreaks.

We will bring together our wider UK programme portfolio including centrally managed programmes (CMPs) and multilateral investments:
  1. WISH-Dividend will support SRHR by scaling up access to comprehensive SRH and family planning services, targeting the poorest women and girls, adolescents, and people with disabilities (PWDs), in addition to providing family planning commodities in HSTP facilities.
  2. Healthy Women, Children and Newborns: A Coordinated Approach to Ending Preventable Deaths (HCWN) will provide short- and long-term technical assistance (TA) to tackle key bottlenecks in reducing preventable deaths of mothers, babies and children. South Sudan is an HCWN flagship country, which gives BE Juba access to TA.
  3. Our investment in Gavi, the Vaccine Alliance will continue to expand coverage of core routine immunisation and outreach campaigns for vaccine preventable diseases, thereby reducing the number of zero-dose children, and likelihood of disease outbreaks.
  4. Our investment in the Global Fund to Fight AIDS, TB and Malaria (Global Fund) has supported prevention and treatment of HIV, TB and malaria in South Sudan. We will ensure that the Global Fund’s significant investments in South Sudan aligns with wider systems and PHC strengthening at the country level, in line with the Lusaka Agenda.
  5. Ensuring Quality Access and Learning for mothers and newborns in conflict-affected contexts (EQUAL) works to generate evidence on effective approaches for delivering life-saving maternal and newborn health care in countries affected by conflict, including South Sudan.
  6. Education For All South Sudan (EFASS) programme and the planned BE Juba Gender Based Violence Prevention South Suan (GBVPSS) programme seek to shift harmful social norms, reduce acceptance of GBV and promote safer environments for women and girls. We will leverage potential synergies with the health portfolio, to drive stronger outcomes for women and girls.

The UK is a major health donor and influential actor in South Sudan. The UK remains a major donor despite the total UK bilateral investment in health as a proportion of the total HPF budget falling year-on-year since FY2019/20. As co-chair of the Health Sector Donor Group we play a key influencing and coordination role, supported by our health advisory capacity. In addition to our bilateral investment in health, significant UK multilateral investments contribute to budgets and policy at the country level. These investments and our expertise mean that we play a leading role in the health sector within the international community, with the South Sudanese public, and with the GRSS. This health investment underscores the UK’s commitment to the people of South Sudan and gives the UK more weight and influence in discussions with the GRSS about implementation of R-ARCSS and wider stability priorities.

This programme will be a key priority in the UK’s South Sudan Country Plan alongside investments in humanitarian and resilience building, building stability, accountability, and supporting peace, and education service delivery. Better health outcomes underpin long term change by contributing to economic growth and providing opportunities to bridge conflict divides and support peace. Supporting health interventions will build the resilience of people and key institutions making them better able to cope with the worst impacts of conflict, flooding and humanitarian crises.

In summary, South Sudan is one of the most dangerous places in the world to be born, give birth, or fall ill. Access to, as well as the quality of and demand for, health services is impacted by wider determinants of health including conflict, flooding, the influx of refugees/returnees and social norms coupled with weak capacity and investment in the sector. One of the main constraints is the GRSS’ limited capacity and political will to lead the sector and prioritise domestic resources to deliver health services. Over the past decade, HPF and CERHSP have performed well, achieved results, and saved lives but the approach is not sustainable. Small incremental steps are now required to move towards a more sustainable system, with Government taking on increasing leadership responsibility, and a greater focus on system strengthening and community engagement. This will mean taking managed risks to achieve catalytic and transformational impact. This represents the start of a concerted effort to develop South Sudan’s health system, which is especially important now, given the scale of ODA cuts to health and humanitarian services.

### A12: Expected results: impact and outcomes that FCDO could achieve

Impact ambition: The expected impact of the programme is ‘significant reductions in maternal, newborn, and child mortality’.

Outcome ambition: The expected outcomes of the programme are: 1) ‘Better meet the needs of South Sudan’s population through improved coverage of quality RMNCH services’, 2) ‘Improved responsiveness and efficiency of the health system’, and 3) ‘GRSS is more able to lead, manage, and take responsibility for the health system’.

This programme acknowledges that the impact ambition of significantly reducing maternal, newborn, and child mortality is both a cause and effect of wider determinants of health such as poverty, conflict, gender inequality, and climate change. In order to be addressed sustainably, it is necessary that the programme’s interventions be delivered through South Sudan’s national health system, as captured in the outcome ambition statement.

Strengthening each of the six-health system building blocks is necessary to build a resilient and sustainable system that can meet the needs of mothers and their children. We cannot increase the coverage and quality of health services without strengthening the health workforce, information systems, access to medicines, financing, and leadership/governance. The health system needs to be efficient and responsive in order to better meet the needs of the population. Increasing GRSS funding and responsibility for health is embedded within the theory of change and is vital to achieving sustainable RMNCH outcomes in South Sudan. However, given the politics of the R-ARCSS two-year extension, the delay in holding elections, and an unstable economy, we acknowledge that the task of systems strengthening and encouraging GRSS to execute more funding for health is very challenging. This programme will also be agile and flexible to adapt to differing needs and modalities under changing political scenarios in an FCAS context.

SHAPES will deliver the following outputs (complemented by independent learning and evaluation) to achieve the outcome and impact ambition statements:
  1. Improved access to RMNCH services and medicines in health facilities and communities.
  2. Trained and motivated HCWs and BHWs deliver quality health services.
  3. Strengthened use of data for review, planning, and decision-making on RMNCH by GRSS.
  4. Strengthened GRSS coordination of programming, policy, and resources in the health sector, including commitment of its own domestic financing for health.
  5. Health emergencies responded to rapidly, minimising impact on the health system.

The outputs and outcomes will be achieved through providing a basic package of RMNCH services in health facilities and the community; distributing essential medicines and commodities; paying incentives to healthcare workers; targeted technical assistance to develop core health systems building blocks, community engagement to build knowledge, ownership, and agency for health at the community level thereby bridging the long distances to health facilities, and advocacy and diplomacy to develop GRSS capacities for leadership and coordination of the sector.

Appraisal Case

The appraisal case explores the range of interventions that the programme could take to achieve the impact and outcome ambitions outlined in the Strategic Case and the delivery options for the preferred interventions.

Excluding the ‘do nothing’ option (counterfactual)

As outlined in the strategic case, if FCDO were to stop funding health in South Sudan, it is almost certain that maternal, newborn, and child mortality rates would increase. FCDO has been the lead donor to the health sector in seven of South Sudan’s ten states over the past twelve years under HPF. HPF delivered essential health services through building capacity within CHDs and at the community-level via BHI. Withdrawing UK bilateral support would leave a substantial gap in the health sector could reverse gains, weaken systems, institutions and structures which we have helped build, and undermine the UK’s reputation as a ‘patient partner’.

The South Sudanese population has considerable health needs and is dependent on a donor-led basic health system, focused on primary and community healthcare. Even if other donors maintained their levels of support, withdrawal of UK bilateral support would leave a significant funding gap. This would likely render many health facilities non-functional. Service delivery in State Hospitals was disrupted for over a year when UK ODA reductions in 2022/23 necessitated withdrawal of HPF support at the tertiary level. The impact of any cuts would disproportionately affect the most vulnerable and would require more costly and unsustainable humanitarian programming to plug the gap, countering wider FCDO objectives in South Sudan.

The BE Juba recognises that continuing to provide ODA for the provision of health services in South Sudan’s health sector, particularly the payment of incentives for HCWs by donors could disincentivise GRSS to finance the health sector and undermine accountability, and South Sudanese citizens’ expectations of GRSS to meet their basic health needs. However, the risk of needless lives lost through disruptions to service delivery is a more important priority to address. Without paying incentives to HCWs, we cannot deliver essential services. The BE Juba will mitigate this risk through implementation of the principles outlined in the Foreign Secretary’s priority for ‘genuine respect and partnership’, as well as the Development Review’s focus on ‘better supporting governments’ own systems and efforts to deliver services’. We will advocate strongly to GRSS, using all diplomatic levers, to execute financing for health, implement catalytic interventions that strengthen South Sudan’s health system with a strong focus on governance and leadership, as well as drive strategic thinking across donors to agree a long-term approach for gradual transition towards government paying salaries for HCWs.

Withdrawal would also weaken the UK’s leverage and influence in the health sector by depriving ourselves of a seat at the table with the MoH, thus limiting our ability to drive progress on health system strengthening. BE Juba would lose programme-funded health advisory capacity in country and would therefore not be able to influence priorities at the national and subnational levels. UK support would be limited to our global investments through the Global Fund, Gavi, the WHO, and UNFPA, and our centrally managed programmes.

Therefore, not intervening, or the ‘counterfactual’, has been discounted from further appraisal. It is the basis against which other options will be appraised.

### B1: Options Appraisal
The options appraisal takes a two-stage approach:
  1. First stage: reviews which public health interventions we should prioritise, and how we should weight them to achieve the outcome ambition statement.
  2. Second stage: appraises two feasible options for delivering the preferred interventions identified under the first stage.

#### First stage appraisal – Evaluation of public health interventions against the WHO HSS framework
The section below evaluates which public health interventions under each of the WHO’s HSS building blocks (health workforce, financing, health information systems, access to essential medicines, leadership/ governance, and service delivery) would be most impactful in reducing maternal, newborn, and child mortality in South Sudan over the next five years.

It aims to identify which interventions should be prioritised and how they should be weighted within the programme. The review considers findings from published literature, and situates these within the political economy of South Sudan, lessons learnt from HPF, and what works best in an FCAS context.
Building Block 1: Health Workforce (Input)

The health workforce is the bedrock of delivering quality services and is a key input across each of the HSS building blocks. The WHO defines the health workforce as ‘all people engaged in actions whose primary intent is to enhance health’.[52] South Sudan has limited trained healthcare workers, particularly specialists in surgery, paediatrics, and non-communicable diseases. Global evidence highlights that there are many interventions that can be implemented to strengthen the health workforce, dependent on context, availability of resources, and education capacities. These include:
[52] World Health Report 2006: Working together for health. Geneva: World Health Organisation; 2006 (http://www.who.int/whr/2006/en/)
  1. Regularly compiling and using validated statistics on human resources for health to support decision-making.
  2. Increasing the size and capacity of the national health workforce, which may include recruitment and training of community health workers.
  3. Increasing the capacity of health professions educational institutions, including increasing the quantity and quality of instructors and auxiliary staff.
  4. Strengthening recruitment and deployment systems including incentive schemes to ensure that primary health-care facilities meet their nationally recommended staffing norms.
  5. Effective interaction with or regulation of the private sector requiring accurate knowledge of the numbers, types and qualifications of private sector providers.

It is important to evaluate any intervention into South Sudan’s health workforce with the lens of political economy analysis. Increasing the capacity and size of the workforce is critical to improving the quality of services, and in turn saving lives. However, in the context of GRSS not paying government salaries, any expansion in the size of the workforce would necessitate donors to pay salaries and continue an unsustainable political and financial pathway. Under HPF and CERHSP, incentives were paid to healthcare workers in facilities and Boma health workers in the community (BHWs). Training for HCWs on key areas such as vaccine and stock management are already provided by other Global Health Initiatives (GHIs) such as Gavi and UNFPA.

Priority level: Medium - incentives. This building block is of a medium policy priority because in an FCAS context our levers and capacity to deliver interventions to strengthen the workforce are limited by challenges relating to resourcing, retention, and sustainability. However, in South Sudan, where GRSS has not paid government salaries in over a year, it remains a priority for donors to provide incentives to HCWs, in order to motivate staff to deliver services. Donors need to use all levers to advocate for GRSS to pay HCWs’ salaries, so that donors can reduce support for incentives over time, and in turn increase GRSS commitment to the health sector. This will need to be phased in line with political economy analysis and diplomatic engagement. Expansion of care in the community is critical given the number of obstacles mothers contend with to reach facilities. Continued training and supervision of HCWs is also key to ensure adequate quality of care (QoC) standards. Without GRSS leadership, accountability, and commitment to the healthcare workforce, further interventions such as compiling statistics on human resources and increasing the size of the health workforce would not deliver the desired outcomes.

Building Block 2: Financing (Input)

1. Health financing is of course the most significant overarching input into the health system. It not only concerns mobilising funds to meet the needs of the population but also ensuring that citizens can access services without risk of severe financial hardship. GRSS has not met this responsibility since independence, with only 0.5% of total government expenditure spent on health in 2022/23. The health sector in South Sudan is littered with co-financing agreements between donors/ GHIs and GRSS, and often GRSS secures waivers or simply does not uphold these agreements. Not only does the GRSS continue to invest woefully little in its health system, but when funds are made available, they are not spent on priority, cost-effective interventions and/or are mismanaged within weak PFM systems.
2. Reviews of HPF have shown that some facilities charge patients for services to fill the gap in operating expenses provided by GRSS. Interventions to strengthen financing include improving financial transparency and management and carrying out National Health Accounts to combine data on all expenditure sources.
3. Priority level: High – advocacy. This building block is of a high priority. Diplomatic and political advocacy for national investment in health, aligned to implementation of R-ARCSS, is vital, and will remain a key priority for our engagement with GRSS at all levels. Interventions to strengthen government financing for health in South Sudan will need to be adapted with consideration of its FCAS context and political economy. We will conduct further political economy analysis on different interest groups in South Sudan, and BE Juba’s levers to influence GRSS financing for health outside of the sector. We will also carry out analysis on the prevalence of user fees within the government-run health system, and why they are being introduced by some health facilities. This will inform interventions that minimise financial costs placed on mothers, thereby increasing utilisation of services, particularly amongst the vulnerable.

Building Block 3: Information Systems (Input)

The health information system provides the underpinnings for national decision-making and priority-setting. It has four key functions: (i) data generation, (ii) compilation, (iii) analysis and synthesis, and (iv) communication and use. South Sudan’s DHIS2 system is paper based at the facility level, and reliant on over-burdened HCWs to record data. The system is therefore subject to data inaccuracies and is not sufficiently used or trusted by decision-makers at county, state, and national levels to inform priority-setting. There are four main time periods within which interventions to strengthen data quality and quantity are most effective: improving data collection in facilities, improving monthly tallying during data aggregation, improving quality control during data entry in CHDs, and correcting for data shortcomings post-hoc by the MoH. [53]
[53] Farnham, A., Loss, G., Lyatuu, I. et al. A roadmap for using DHIS2 data to track progress in key health indicators in the Global South: experience from sub-saharan Africa. BMC Public Health 23, 1030 (2023). https://doi.org/10.1186/s12889-023-15979-z

Creating a culture for recording, valuing, and using data at all levels of the health system is critical to engendering the MoH with the evidence-base to understand the population’s needs and deliver policy to address these. As a result of GRSS’ lack of leadership and financing, data systems are fragmented across health verticals, donors, geographies, and implementing partners. Planning for health is hampered by the dearth of population data. South Sudan does not have a CRVS, meaning that the country relies on surveys for the denominator of key RMNCH indicators, which are both costly and infrequent. Interventions to strengthen information systems include:
  1. Developing standard operating procedures (SOPs) and clear accountability for recording, compiling, analysing, and communicating data, particularly for disease outbreaks, and maternal and child health outcomes.
  2. Investing in and training M&E teams at the subnational and national levels.
  3. Setting up working groups to regularly meet and discuss data within the MoH.
  4. Creating dashboards to make the data user-friendly for decision-makers.
  5. Increasing interoperability between key systems such as District Health Information System 2 (DHIS2), Integrated Disease Surveillance and Response (IDSR), Early Warning and Response System (EWARS), and electronic Logistic Management Information Systems (eLMIS).

Priority level: Medium – data culture. This building block is a medium level priority, because it requires multi-pronged, incremental, and longer-term approach to build from the low baseline capacity. Strengthening accountability for existing systems, even if paper-based, across the data chain is of a higher priority than new technical tools for interoperable systems. Generating, compiling, analysing, and using data will be critical to ensuring that GRSS can identify populations most in need of RMNCH services, and target delivery. Registering births and deaths in CRVS systems is a fundamental building block of state building. Embedding a stronger culture for using data will enable GRSS and partners to make evidence-based decisions on responding to disease outbreaks, allocating resources, and procurement of medicines.

Building Block 4: Access to essential medicines (Input)

1. Ensuring equitable access to essential medical products, vaccines and technologies of assured quality, safety, efficacy and cost-effectiveness is critical to meeting RMNCH needs in South Sudan. South Sudan, like many other low and middle-income countries (LMICs), does not have the capacity to set and negotiate prices for medicines, nor have effective procurement, supply, storage and distribution systems. HPF contracted third-party contractors to procure and manage distribution of medicines.
2. In South Sudan’s FCAS context, with limited GRSS financial transparency and investment in health, donor-led supply chain management is the strongest system to ensure that the population receives the safe and effective RMNCH essential medicines that it needs. UNFPA already provides reproductive health supplies, and GFTAM provide anti-malarial commodities. Essential RMNCH medicines include, but are not limited to condoms, emergency contraception, oxytocin, amoxicillin, oral rehydration solution, and long-lasting insecticidal nets (LLINS). Procurement of medicines should ideally be informed by service delivery, consumption, and logistics data to ensure that each county receives adequate supply of medicines based on needs. Outside of the supply chain, there is a gap in policies on the essential medicines list and guidelines on donations of medicines.

Priority level: High – supply chain. This building block is of a high priority because without donor led procurement and distribution of medicines, HCWs will not be able to treat patients. Stock outs of essential medicines increase the risk of maternal and child mortality. Building and sustaining HPF success in procuring, supplying, storing, and distributing essential medicines nationwide is vital.

Building Block 5: Governance/ leadership (Process)

As outlined in the strategic case, GRSS has limited accountability for meeting the health needs of its citizens. The health sector has been led by donors since independence through financing, policy development, contracting of implementing partners, and monitoring and evaluation. Given the FCAS context, strengthening GRSS governance of the health sector is a long-term agenda, and is contingent on financing. This will require stronger advocacy in the political sphere. At the technical level, developing a stronger data culture will provide the MoH with a clearer evidence-base to steer internal and external financing to be based on needs.

Governance and leadership interventions need not be confined to the national level. There is strong evidence from other LMICs such as Kenya and Cameroon on the importance of leadership at the subnational level – in SMoHs and CHDs. In Cameroon for example, accountability for funding of health sits at the regional level (the equivalent of South Sudan’s states). Leadership at the subnational level is critical when responding to infectious disease outbreaks. UK-PHRST analysis of a yellow fever outbreak in South Sudan in 2023 highlighted accountability gaps at the facility, county, state, and national levels in identifying cases, communicating information, and responding rapidly.

Priority level: Medium – accountability. This is of a medium priority, because we can only deliver incremental changes due to South Sudan’s political economy, and wider post-independence challenges. Health is one of many sectors lacking necessary governance, financing, and leadership at the national level. A key projected outcome is to strengthen the sustainability of South Sudan’s health system. To do this, incremental interventions are needed at all levels of the health system to strengthen accountability and governance structures, mirrored by the R-ARCSS pathway.

Building Block 6: Service Delivery (Output)

The UK’s investments in HPF over the past decade have demonstrated the importance of prioritising service delivery in South Sudan’s FCAS context, where health systems are weak and domestic financing is constrained. HPF’s delivery of essential services in PHCUs, PHCCs, County and State Hospitals has filled the substantial gap in GRSS’ capacity and commitment to the health sector. The humanitarian plus model for service delivery, spearheaded by HPF, and now by the WB’s HSTP, can reach the population nationwide, through providing BPHNS in government-run health facilities and the community. UK support to this humanitarian plus model would enable us to save more lives at a population level, through providing essential lifesaving services at scale.

RMNCH service delivery in South Sudan encompasses the delivery of interventions to reduce child newborn, and maternal deaths from communicable diseases, particularly malaria, diarrhoea, and pneumonia. FCDO ‘Health Best Buys’ recommend interventions that support countries to expand coverage of the highest priority package of effective health interventions, focussing on prevention, rather than vertical initiatives and disease-specific interventions.[54][55]
[54] FCDO Health Best Buys, 2022.
[55] FCDO Health Best Buys, 2022.

Packages of care are more cost-effective than single procedures, and are also more feasible in terms of programme implementation.[56] Evidence from LMICs highlights that we should prioritise a strong focus on preventive health services which offer high returns on investment across the life course, such as family planning, periconceptual nutrition, routine ANC and care for labour and childbirth, immunisation, PHC check-ups (e.g. mid-upper arm circumference measurements (MUAC)) and infectious disease prevention.[57] Published literature from LMICs highlights the importance of integrating nutrition within maternal, newborn, and child services package at the PHC level. The cycle of malnutrition is impacted by a range of factors from weight of child at birth, maternal nutrition, gestation at birth, mother’s age, feeding practices, recurrent illness and poverty. It is critical that the health system intervenes to break the cycle of malnutrition.
[56] Stenberg K, Watts R, Bertram MY, Engesveen K, Maliqi B, Say L, Hutubessy R. Cost-Effectiveness of Interventions to Improve Maternal, Newborn and Child Health Outcomes: A WHO-CHOICE Analysis for Eastern Sub-Saharan Africa and South-East Asia. Int J Health Policy Manag. 2021 Nov 1;10(11):706-723. doi: 10.34172/ijhpm.2021.07. PMID: 33904699; PMCID: PMC9278381.
[57] FCDO Health Best Buys, 2022.

1. Immunisation is often a child’s first touch point with the health system. In South Sudan, coverage of DTP1 is 76%, and DTP3 is 72%, meaning that if screening using MUAC was delivered at the same time, the strong coverage of immunisation could be leveraged to also expand coverage of nutrition interventions and other maternal interventions.
2. Published literature and the WHO’s technical definition of service delivery underlines that investments in service delivery alone are inefficient and would reduce the impact of the programme. As the WHO highlights, ‘service delivery is an immediate output of the inputs into the health system, such as the health workforce, procurement and supplies, and financing’.[58] It is only through increasing such inputs that we can improve service delivery and enhance access to services. This reflects our experiences and lessons learnt from implementing HPF over the past decade. In addition to service delivery, under HPF the UK supported:
  [58] WHO, Monitoring the building blocks of health systems: a handbook of indicators and their measurement strategies, 2010
  1. the provision of essential medicines to all supported facilities and BHWs;
  2. payment of incentives to health workers in line with the harmonised incentive scale to support retention of staff;
  3. in-service training for facility and BHWs;
  4. support to the State MoHs and CHDs for oversight and supportive supervision; and
  5. investment to improve water, sanitation and hygiene (WaSH) within facilities.

1. Developing health infrastructure, such as health facilities and hospitals, is of course crucial to delivering essential services. However, there is already significant health infrastructure in South Sudan, even if it is in varying degrees of disrepair due to the civil war. Therefore, it would be most cost effective and efficient to prioritise restoring existing facilitates, as compared to developing new health infrastructure.
2. Priority level: High. Service delivery interventions need to be prioritised with the strongest weighting in South Sudan’s FCAS context. GRSS lacks the capacity and commitment to be able to provide services on its own, and requires substantial external support without which, increases in maternal and child mortality would be inevitable. Delivery of services must happen at all levels of the system to ensure that the population has access to healthcare. Strengthening the quality and coverage of primary healthcare is critical to meeting the needs of the population, and there needs to be a focus on improving referrals systems to ensure mothers can access BeMONC and CeMONC services in a timely and safe manner, in order to reduce maternal mortality rates. The focus on improving service delivery must be balanced with recognition that targeted catalytic investments in the other building blocks are necessary to be able to deliver RMNCH services in South Sudan’s FCAS context.

Cross-cutting: Community engagement (CE) (Process/Input)

A key lesson learnt from HPF is that implementing supply-side interventions alone is insufficient to increase coverage and equity. Community engagement (CE) is needed to address the wider determinants of health in South Sudan, such as harmful sociocultural norms, violence, conflict, poverty, distance to facilities, user-fees, limited road-density, climate shocks, and limited education. The evidence highlights that the combined impact of wider determinants of health prior to conception, in utero, and in early childhood, from neglect, to poor nutrition, or a dearth of opportunities to learn and play, shapes how an individual’s genes are expressed, which in turn affects their health, behavioural, and development outcomes across a lifetime, and potentially even future generations.[59]
[59] WHO, United Nations Children’s Fund, World Bank Group. Nurturing care for early childhood development: a framework for helping children survive and thrive to transform health and human potential. Geneva: World Health Organization; 2018.

CE is central to tackling determinants of health through building trust, understanding, and knowledge of health services and rights to health. CE can be defined as ‘collaborating with communities and stakeholders to work together on issues in order to improve health outcomes and well-being in the community’.[60] There is substantial evidence from LMICs on CE’s ability to contribute towards increased knowledge of health services, behaviour change, and strengthened accountability at the community level.[61] Community health workers (CHWs) are a vital tool in advancing CE. The WHO states that CHWs have ‘enormous potential to extend health care services to vulnerable populations, such as communities living in remote areas and historically marginalised people, to meet unmet health needs in a culturally appropriate manner, improve access to services, address inequities in health status and improve health system performance and efficiency’.[62]
[60] WHO, WHO community engagement framework for quality, people-centred and resilient health services. Geneva, Switzerland: World Health Organization; (2017)
[61] Pilkington G, Panday S, Khatib MN, Kotas E, Hill RA, Simkhada P, Jones L, (2017), The effectiveness of community engagement and participation approaches in low- and middle-income countries: a review of systematic reviews with particular reference to the countries of South Asia. London: EPPI Centre, Social Science Research Unit, Institute of Education, University of London
[62] WHO, What do we know about community health workers? A systematic review of existing reviews [Internet]. Geneva: WHO; 2020 p. 88. (Human Resources for Health Observer Series;19)

Given the accelerating conflict dynamics in South Sudan, it is ever more challenging and dangerous for individuals, particularly women and girls, to travel and receive care in health facilities. Community engagement by BHWs is critical to delivering services directly in communities, as the first point of contact with the health system. Under HPF’s BHI programme in South Sudan, donors provided incentives to CHWs, known as Boma Health Workers (BHWs), to deliver services in their own communities, supplementing services provided in primary healthcare centres and units. Similarly, in Nigeria, CHWs perform task-sharing and task-shifting activities, demand generation, and respond to infectious disease outbreaks.[63] A 2020 WHO meta-review reported that CHWs perform a variety of tasks across six main roles: ‘(1) delivering diagnostic, treatment or clinical care, (2) encouraging uptake of health services, (3) providing health education and behaviour change motivation, (4) data collection and record-keeping, (5) improving relationships between health system functionaries and community members, and (6) providing psychosocial support’.[64]
[63] Whenayon Simeon Ajisegiri, David Peiris, Seye Abimbola, Olumuyiwa O Odusanya, Azeb Gebresilassie Tesema, Rohina Joshi, Blake Angell - It is not all about salary: a discrete-choice experiment to determine community health workers’ motivation for work in Nigeria: BMJ Global Health 2022;7:e009718.
[64] WHO, What do we know about community health workers? A systematic review of existing reviews [Internet]. Geneva: WHO; 2020

The evidence also highlights that multi-component programmes, operating across individual, community, county, state, and national levels perform better than single-component programmes and often produce multiple and reinforcing outcomes.[65],[66] A multisectoral programme in Uganda, which combined peer mentoring in school clubs, financial skills training, awareness raising on SRHR, and engagement with girls’ parents and communities found significant reductions in teenage pregnancy, sexual violence and early marriage.[67] The WHO, World Bank, and UNICEF’s ‘Nurturing Care Framework’ further highlights the importance of multisectoral interventions across health, nutrition, education, and social protection sectors in improving health outcomes. Children need adequate nutrition, responsive caregiving, security and safety, and opportunities for early learning to achieve their health and development potential. One example of a cost effective multisectoral Early Childhood Development (ECD) intervention is kangaroo mother care (KMC), whereby mothers are encouraged to care for low-birth-weight and preterm infants through skin-to-skin contact with their baby. It's an evidence-based practice that can reduce mortality, improve the health of newborns, and increase breastfeeding rates.
[65] Haberland, N. A. (2018) A Systematic Review of Adolescent Girl Program Implementation in Low- and Middle-Income Countries: Evidence Gaps and Insights, Journal of Adolescent Health 63(1), pp. 18-31.
[66] Yount, K. M et al. (2017) Preventing gender-based violence victimization in adolescent girls in lower-income countries: Systematic review of reviews, Volume 192, 2017, pp. 1-13.
[67] Bandiera, O. et al. (2018) Women’s Empowerment in Action: Evidence from a Randomized Control Trial in Africa.

Priority level: High. CE is critical in South Sudan’s FCAS context, with a high proportion of rural communities who struggle to access PHC in health facilities due to conflict dynamics, socio-cultural norms, user fees, and long distances with limited road density. There needs to be tailored programming to deliver services in the community, engage communities, build trust, and knowledge of health rights, in conjunction with other multisectoral interventions which reduce the perverse effects of wider determinants of health.

Cross-cutting: Responding to health emergencies and infectious disease outbreaks

1. Responding to health emergencies and infectious disease outbreaks is a continued priority in South Sudan that cuts across each of the building blocks. Disease outbreaks hamper essential service delivery and contribute to South Sudan’s high maternal and child mortality rates. Severe flooding and droughts limit access to health facilities and impact malnutrition and the transmission of diseases such as cholera, malaria, and dengue. Each of the building blocks contributes towards the effectiveness of emergency preparedness and response. Data on cases and wider population prevalence via EWARS and IDSR is critical for management of disease outbreaks; surveillance officers and HCWs play a vital role in identifying cases; financing of National Action Plans for Health Security enable strengthening of International Health Regulations (IHR) capacities, and leadership/governance is needed to coordinate multisectoral responses. As highlighted in the above sections, in South Sudan, each of the building blocks that underpin preparedness and response are at a nascent level.
2. Under HPF, the UK had limited financial flexibility to support national responses to outbreaks. Our support was limited to technical advice from BE Juba Health advisers and UKPHRST, as well as a small fund for health emergencies, which constrained our influence with partners and government, and our ability to respond to outbreaks rapidly.

Priority level: High – rapid response. This cross-cutting intervention is of a high priority. Health emergencies and disease outbreaks are intensifying, and threaten to overwhelm the health system, and delivery of RMNCH services. Flexibility in rapidly responding to emergencies and disease outbreaks, while protecting funding for service delivery is critical to safeguard RMNCH services.

#### Preferred weighting of interventions to deliver the outcome ambition
The review of public health interventions under each of the six WHO building blocks in South Sudan’s health system has exposed their interlinkages: although service delivery is the most important priority to save lives, this cannot happen without baseline capacity levels in the health workforce, information systems, financing, leadership/ governance, access to essential medicines, and addressing wider determinants of health through community engagement.

The priority level of interventions within the programme has been informed by what is needed in South Sudan over the next five-year period (2025-2030), considering its FCAS context and political economy, to build incremental steps towards strengthening the health system over the next ten to twenty years, aligned with our diplomatic objectives for peace and stability. Achieving the impact ambition of significantly reducing maternal, newborn, and child mortality rates is a long-term agenda, and will require a well-functioning and resilient health system across all the building blocks. The table below outlines interventions that will be most catalytic and impactful over the next five years under each building block, ranked by priority level.

Table 4: Priority level of interventions across Health System Building Blocks and crosscutting areas
HSS Building Block/ cross-cutting priorities	Public health interventions	Priority level within the programme / 2025-2030
Service Delivery	Delivery of essential RMNCH services in health facilities at all levels – PHCUs, PHCCs, County and State Hospitals.	High – delivery of quality essential RMNCH services at all levels of the health system, is critical to saving lives.
Access to essential medicines	Third-party led supply chain of medicines: procurement, supply, storage and distribution systems / Normative guidelines: essential medicines list and donations	High – ensuring equitable access to essential medicines is a vital input for service delivery.
Financing	Advocacy for increased GRSS investment in health / Co-financing agreements / Flexible funding support for rapid responses to infectious disease outbreaks	High – GRSS investment in health is negligible. Stronger advocacy is needed to build a pathway towards sustainability.
Cross-cutting - / Community engagement (CE)	CE through delivery of services and referral at the household and community levels via BHWs. / Build trust and knowledge of health rights through BHWs and community governance mechanisms. / Deliver multisectoral interventions at the Boma level to advance early child development, through linkages with nutrition, social protection, and education sectors.	High – CE is vital in an FCAS context to building confidence, trust, and agency at the community level, and in turn increased utilisation, and coverage of services.
Crosscutting - Responding to health emergencies	Ability to rapidly respond through financing and technical support to health emergencies and infectious disease outbreaks / Mainstream a focus on emergency preparedness and response across all HSS interventions	High – health emergencies and infectious disease outbreaks threaten to overwhelm the health system and disrupt RMNCH service delivery.
Information system	Strengthen accountability for collection, analysis, and use of data for decision-making by the MoH / Mobilise momentum to develop a CRVS that can provide population data for health statistics, as well as future elections	Medium – information systems and CRVS are weak, and data is not valued or used for decision-making. Focus needs to be on strengthening existing systems, instead of introducing new tools.
Health workforce	Payment of incentives to healthcare workers / Training on core RMNCH skills / Expansion of BHI	Medium – GRSS health workers last received a salary payment for August 2023 in February 2024. Incentives, core training, and expanding the BHI are the only feasible interventions in the current context.
Leadership/ governance	Strengthen ownership of and accountability for health at all levels (community to national MoH) / Establish clearer governance of health by GRSS.	Medium – Interventions to strengthen leadership and governance need to be situated within challenging political economy.

The preferred approach is to support a comprehensive package of interventions across the building blocks. The package will focus predominantly on service delivery interventions, to meet the population’s significant RMNCH needs. This will be complemented by targeted catalytic interventions across the health system building blocks from the table above, particularly within access to medicines, financing, community engagement, and responding to health emergencies.

Our ability to increase coverage of service delivery and save lives is entirely dependent on the effectiveness of investments in other building blocks: the sum of all the interventions is greater than its parts. For example, we cannot reduce South Sudan’s high rates of malaria mortality without stronger data on incidence at the subnational level, quantification of anti-malarial commodities based on population need defined by data, delivery of diagnostics and treatment through the health workforce in health facilities and the community, and clear governance at county, state, and national levels to prioritise action, and regularly review data to inform cyclical decision-making. Combining these interventions into a package of support will increase our chances of achieving the outcome ambition.

The pie chart below visually illustrates the weighting of each building block, based on the resources needed to implement interventions. Service delivery, procurement and distribution of medicines, and incentives to HCWs, require greater financing than other interventions such as advocacy for increased GRSS financing. Although each of the HSS building blocks have different resourcing requirements, this does not predetermine the UK’s priority level and focus.

Figure 4: Resource weighting of HSS Building Blocks within SHAPES resources
Without specific support to strengthen the health system, there is no clear pathway out of the current dependence on donors to support basic health service delivery. ODA cuts have underlined the risks of donor dependence, and the need to rapidly increase resilience within health system. It is important to start to lay the foundations of a transition towards GRSS ownership now. This will also help to shift the expectations of citizens from donors to MoH for the provision of essential services, which may have positive impacts on sectors aside from health.

This package of interventions complements the plans of other health donors and programmes in South Sudan and will take advantage of the UK’s strengths and comparative advantage in these areas. Investing in this package of interventions is supported by the available evidence. This business case will also seek to build the evidence base through including a learning and evaluation element.

#### Second stage appraisal – Delivery Options

The second part of the Appraisal Case considers how best to deliver the preferred package of interventions identified in stage one. The overall objective is to determine which delivery mechanism is most likely to achieve the outcome ambition statement: to 1) ‘better meet the needs of South Sudan’s population through improved coverage of quality RMNCH services’, 2) ‘improved responsiveness and efficiency of the health system’, and 3) ‘GRSS is more able to lead, manage, and take responsibility for the health system’.

Excluding options that are not feasible

Excluding continuation of the Health Pooled Fund Programme
The service delivery component of the HPF3 programme ended at the end of June 2024. Through UK-led transition planning, HSTP, the new WB-led MDTF programme picked up the baton from 1 July 2024. UNICEF, the HSTP MO responsible for service delivery, has already contracted IPs to implement services from the Basic Package of Health and Nutrition Services (BPHNS), and supply essential medicines to selected health facilities across all of South Sudan’s ten states. On 20th September, the WB and Ministry of Finance and Planning also agreed a formal finance agreement for HSTP. Their goal is to harmonise fragmented health programmes across different states into one nationwide service delivery platform and strengthen ownership of health by GRSS including through a co-financing agreement.

Continuing HPF is not feasible, nor value for money in a HSTP-led health sector. A standalone UK programme to support service delivery would run parallel to the WB’s multi-donor approach under HSTP, would minimise our impact, and further fragment the health system. All key health donors in South Sudan, including those that previously supported HPF, namely Canada, the EU, Gavi, the WB, and the Global Fund have confirmed that they will support HSTP. The second extension of R-ARCSS in September 2024 and continued lack of investment in essential services by GRSS, has highlighted the need to push for stronger ownership and accountability, which was difficult to achieve through the largely third-party led HPF. The HSTP is explicitly targeting this by taking a hybrid approach to implementation by safeguarding health service delivery through third-party implementation arrangements whilst providing a targeted amount of support to, and under the management of, government (with WB safeguards applied), to leverage stronger government leadership and accountability. The BE Juba is supportive of this approach which takes the initial steps to a more resilient and sustainable health system. For these reasons, a further phase of a FCDO-led HPF is not possible nor desirable and is thus discarded from further consideration.

### B2: Identification of Feasible Options: Advantages and Disadvantages

Two feasible options have been identified to deliver the comprehensive package of interventions across the health system building blocks, informed by their priority level. The choice of options examined draws on published literature, our understanding of South Sudan’s political economy, lessons learnt from previous HPF programming, and what works best in an FCAS context. The table below outlines the seven success criteria which will be used to rigorously analyse which of the delivery options offer the strongest case for achieving the impact and outcome ambitions outlined in the strategic case.

	Success Criteria to inform analysis of delivery options
All six-health system building blocks (reflecting priority levels)	Improved utilisation and coverage of RMNCH health services for the poorest and most vulnerable in South Sudan
	Potential to significantly increase maternal, newborn, and child lives saved for the duration of the programme and beyond
	Potential to advocate for increased accountability, leadership and domestic financing in health by GRSS
Disease outbreaks/Climate/ conflict	Ability to rapidly respond to health emergencies and disease outbreaks
Diplomatic/ Political	Aligned to and supports wider UK priorities in South Sudan on peace, stability, security, and strengthening government accountability
Programme management	Provides the best value for money (VfM) for UK Government and minimises administrative, management and overhead costs
	Fiduciary probity

The two identified options are:
  1. Option 1 – HSTP: Channel UK funding into HSTP plus the capability to respond to emergencies
  2. Option 2 - HSTP+: HSTP and additional UK-led targeted HSS and CE interventions, plus the capability to respond to emergencies

Option 1: HSTP - Channel UK funding into HSTP plus the capability to respond to emergencies

Under the first option, the UK would support the WB-led HSTP for three years or over five years. HSTP is covering all ten states and three Administrative Areas, supporting up to 1,158 health facilities over the life of the project using a phased approach. The proposed budget for HSTP over five years is an appropriate burden share, commensurate to our role as a leading donor to the health sector. HSTP has been approved by the WB Board as a three-year project, but there is an expectation by all partners including the WB, that it will be implemented over a longer time-period. This programme would use the likely break point in year three to consider whether to provide support for year four and five based on performance against outcomes.

UK support to HSTP would deliver four elements: 1) UNICEF-led humanitarian plus health service delivery in health facilities and the community; 2) WHO-led health systems strengthening; 3) monitoring and evaluation and project management; and 4) a contingent emergency response component (CERC).

Service Delivery: The service delivery component would be managed by UNICEF and delivered by downstream IPs, with UNICEF entering into an output agreement with the National MoH. Delivery would focus on the distribution of essential medicines and commodities to health facilities and the community; paying facility health and community workers monthly incentives; in-service training; and expansion of the BHI to increase coverage in the community. Delivery of services would focus in large part on primary healthcare through Primary Healthcare Units and Centres and Boma Health Workers. There are a limited number of tertiary hospitals (33 County, 7 State, 4 Teaching) which are critical to support mothers who face obstetric complications and may need tertiary-level surgery or blood transfusion.

HSS: WHO would implement HSS interventions that have been selected through engagement with the national MoH and donors. The bulk of the budget would focus on strengthening emergency preparedness and response to infectious diseases, such as surveillance and laboratory capacities. The WHO, as per its comparative advantage, would also support the MoH to develop key normative guidelines and SOPs for quality of care, information systems, the essential medicines list, and standard treatment guidelines, operational plans, and M&E technical working groups.

Project Management and Monitoring and Evaluation (M&E): A PMU would be established at the MoH to manage health service contracts, supervise project implementation, and monitor progress on results. The PMU would report directly to the MoH Undersecretary and establish clear coordination mechanisms with the relevant departments at the national and state Ministries of Health. With guidance from the WB, the PMU would also contract third-party monitoring (TPM) for M&E. TPM would provide critical assessment and survey data, to complement routine data through DHIS2, in support of the country’s overall health management information system.

Health emergencies: The WB CERC would enable reallocation of uncommitted funds to support national responses in the event of a health emergency or disease outbreak. CERC funds do however come at an opportunity cost, given that they would likely be taken from budget allocated for delivering HSTP services. Disbursements would be subject to WB procedures such as the declaration of emergency, a formal request from GRSS, and preparation of an ‘Emergency Action Plan’. This option would also hold budget headroom via an Internal Risk Facility (IRF) of up to 10% of the total programme budget (in line with HM Treasury guidance), to increase UK health spending rapidly in the event of a health emergency or disease outbreak. This output would only be activated when needed and subject to funding availability. The IRF is designed to provide additional flexibility by allowing us to make use of resources made available via underspend or reprioritisation across the BE Juba portfolio and/or FCDO Africa Directorate, or to draw down resources from the FCDO central crisis reserve subject to approvals at the appropriate levels.

This option would include two programme funded posts: one HEO Programme Manager and one Grade 7 Health Adviser. The HEO Programme Manager role would work closely with the WB to transfer knowledge and experience from managing the HPF3 programme while supporting the WB to provide the assurances FCDO requires as part of HSTP delivery. It is expected that this position will be particularly important during the early stages of the programme and could be phased out during the later stages of implementation. The Health Adviser role would focus on cross sectoral coordination and technical oversight and would be required throughout the lifetime of the programme.

The outputs would include:
- Delivering humanitarian plus services in health facilities and the community by BHWs focusing on BPHNS[68]
  [68] BPHNS interventions that will be delivered include child health; immunisation; nutrition; maternal and neonatal health; BEmONC and CEmONC; family planning and sexual and reproductive health services; GBV services; infectious and noncommunicable diseases; and emergency and surgical services.
- Paying HCWs and BHWs staff incentives
- Managing nationwide pharmaceutical and medical supply chain for health facilities and BHWs, including last-mile logistics
- Conducting in-service training for HCWs
- Strengthening emergency preparedness and response capacities
- Developing normative guidelines, standards, and SOPs for information systems, quality of care, essential medicines, and standard treatment
- Capacitating the MoH with the skills to take on a stronger coordination and leadership role through the PMU
- Making available financing in the event of health emergencies or disease outbreaks

The table below evaluates the strengths and weaknesses of this option, against the success criteria, with particular reference to the health system building blocks.
Table 5: Option 1 - HSTP, success criteria analysis
Success criteria areas		Strengths	Weaknesses
All six-health system building blocks (reflecting priority levels)	Service Delivery / (High)	Continuity of approach - Enables continuity of FCDO’s proven approach under HPF through contracting IPs, influencing via programme funded posts, and ensuring minimal disruptions to service delivery. / Increased access – HSTP aims to support up to 1,158 HFs nationwide, has increased staff levels at the primary healthcare level, and is expanding BHI at the community level. This will increase access to RMNCH services. / Value for money – HSTP’s humanitarian plus model provides a basic package of services nationwide for host communities and displaced populations from Sudan, including in locations which humanitarian actors are unable to reach or have limited presence.
	Access to Medicines (High)	Proven approach – UNICEF is experienced in supply chain management and has largely followed the proven HPF model for procurement and distribution of medicines.	‘Push’ vs ‘Pull’ system – UNICEF is initially relying on a ‘push’ supply chain system, without using national data on demand to inform procurement. This could lead to stock outs if there are insufficient supplies. This approach should change over the lifetime of HSTP. Additional TA to analyse historical DHIS2 data would accelerate progress in this area through improved drug quantification and procurement.
	Financing (High)	Co-financing – The MoFP has signed a co-financing agreement to commit USD$10 during the programme. / Increased harmonisation: Pools donor resources across the whole country, thereby reducing fragmentation, harmonising the package of services and maximising impact.	Political economy – Finance interventions under the HSS component focus on technical areas such as a National Health Account and Health Financing Strategy. Impact would be maximised with additional interventions addressing specific issues of public financial management and accountability within the sector, as well as political economy pinch points (oversight, conditions, and advocacy).
	Information System (Medium)	Build capacity – The WHO-led training for staff on data entry and analysis will strengthen the skills of staff in CHDs and the national MoH.	Data culture and accountability – Although training will certainly build capacity, on its own it will not create a culture of accountability for valuing and using data. Additional interventions covering supervision and governance could increase impact.
	Health Workforce (Medium)	Incentives – Expansion of HCWs in primary care, and BHWs in the community will increase access. Incentives will motivate staff, in the face of GRSS not paying salaries.
	Leadership/ Governance (Medium)	Build capacity – Leadership training at national and state levels will strengthen skills and behaviours.	Political economy – Leadership training will not address institutional challenges within the political economy, or wider governance, political, and legislative challenges related to the health sector (e.g. sufficient salaries not being paid to government workers).
Community Engagement (CE)			Community engagement – Although HSTP is focused on service delivery interventions, there is insufficient focus on community engagement, and delivering multisectoral interventions that reduce the perverse effects of wider determinants of health in South Sudan. Although there will be support for BHWs under HSTP, the policy focus is on ensuring they have essential medicines and supplies, and incentives to motivate them to work. BHWs need further support and training to target communities most in need, facilitate referral pathways for complicated cases, and build confidence, trust, and knowledge of health to save lives.
Disease outbreaks/Climate/ Conflict		Responsive –The CERC and IRF enables unallocated funds to be used for responses to emergencies. Under the IRF, BE Juba would be able to coordinate with other rapid response mechanisms including SSHARP, which also includes an IRF, and the centrally managed Africa Rapid Response to Outbreaks (ARRO) Fund. A programme funded Health Adviser would enable stronger UK leadership and coordination to outbreaks.	Speed of disbursement - Given the need for an official announcement of an emergency and the development of plans by GRSS, disbursement under the WB CERC may not be rapid enough to be made available by the WB in the early stages of a response. The CERC will also draw on financing allocated for service delivery, which may come at an opportunity cost. This risk would be mitigated by the FCDO IRF. / It is important to recognise the higher marginal costs of IRF funds. We would mitigate this risk through only drawing on the IRF in the event of an emergency threatening to overwhelm the health system and would focus first on reprioritising underspend from within the embassy.
Diplomatic/ Political		Supports stability - Provision of services is a critical input to our goal of building a safe and stable country. Co-financing pushes for stronger GRSS commitment to the health of its population, aligned to spirit of R-ARCSS.	Reduced influence - Without UK programming, our influence with the government on essential services priorities may decrease, as compared with the decade under HPF. Engagement on health would be largely through WB coordination mechanisms although the PF Posts would engage in the sector more broadly.
Programme management		VfM - Offers strong VfM through pooling funds with other donors and delivering services at scale to the whole population, reducing fragmentation. / Risk - Pooling UK funds with other donors will help to mitigate the risks (including reputational) and cushion potential impacts to delivery and results should there be continued unpredictability in UK ODA budgets. / Fiduciary - A small, targeted amount (~1% of project funds) of financial support would be provided to GRSS for the PMU to build MoH capacity. This will be safeguarded by the WB’s extensive fiduciary controls. / Programme funded posts (PF posts) – In the longer term, given that the WB will be leading programming, BE Juba may not need a programme funded post for programme management. A Health Adviser would continue to be funded to lead technical influencing.	Fiduciary - FCDO would have less direct oversight over delivery under a WB-led HSTP than in previous UK-led programming (though this now not a feasible option). This would be mitigated through the WB’s assurances and systems and a PFP HEO programme manager sharing knowledge and providing oversight in the early stages of programme implementation.
Evidence rating: Strong

Option 2: HSTP+ - Additional FCDO-led targeted CE and HSS interventions plus the capability to respond to emergencies

1. As with Option 1, under Option 2 the UK would support HSTP for three years or up to five years if HSTP were expanded. In addition to HSTP, FCDO would deliver three additional elements through separate delivery mechanisms. The UK’s burden share in HSTP would be the same under Option 1 and Option 2, with Option 2 being more expensive due to the additional FCDO-led elements.
2. The three additional FCDO-led elements would deliver: 1) Community Engagement; 2) HSS Technical Assistance (TA); and 3) Learning and evaluation.

Community engagement: FCDO would conduct targeted, context-specific community engagement interventions to increase access to primary healthcare services in the community and address wider determinants of health, including conflict, that hinder demand for and utilisation of RMNCH services. Given the novel approach to programming and limited evidence base in South Sudan, it would initially be piloted in specific counties with a strong focus on learning and evaluation to inform and adapt programming and build the evidence base. Interventions could include upskilling female BHWs, providing care to mobile populations affected by conflict, advancing community-led early child development outcomes such as Kangaroo Mothercare, strengthening awareness and knowledge of health rights, and/or increasing accountability for health within community governance structures. This option could potentially provide multisectoral impacts through connections with BE Juba’s EFASS education programme, and the nutrition arm of the SSHARP programme. With stronger evidence to inform delivery, this intervention could have the potential to be delivered at scale within HSTP.

1. FCDO-led HSS TA: FCDO would provide additional TA, to complement the WHO’s HSTP HSS component. The TA would focus on priority interventions identified in the strategic case under the health system building blocks, focussing on those outside WHO’s comparative advantage as a technical and normative partner of government on health. The strategic case offered examples of interventions that could be explored under the Leadership/ Governance, Information Systems, and Access to Medicines building blocks. The TA would deliver targeted incremental and high-impact steps in the next five years, towards the decades long agenda of strengthening an FCAS’ health system. FCDO would consider and prioritise interventions that would contribute towards our wider diplomatic priorities for implementation of the R-ARCSS Peace Agreement and state building. This would be informed by conflict sensitivity and political economy analysis, as well as BE Juba’s SSPP and GBV programmes.
2. Learning and evaluation (L&E): FCDO would conduct L&E to monitor and evaluate the programme, as well as test the evidence base around the more novel aspects such as community engagement and HSS. There would be a strong focus on building the evidence base for what works best in an FCAS context, and how HSS interventions need to be tailored based on South Sudan’s political economy. FCDO-led L&E would complement the HSTP third-party monitoring through sharing lessons from FCDO-led approaches.
3. IRF to rapidly respond to health emergencies: As with Option 1, FCDO would hold budget headroom via an Internal Risk Facility (IRF) of up to 10% of the total programme budget (in line with HM Treasury guidance). The WB-led CERC would also be available via our contribution to HSTP.

Two Programme Funded Posts to support management, oversight, technical advice and cross sectoral coordination. As with Option 1, FCDO will require one Grade 7 Health Adviser and one HEO Programme Manager to manage coordination across the sector and to share learning generated from the programme. Under this option, the HEO Programme Manager will be required for the full duration of the programme.

The table below evaluates the strengths and weaknesses of Option 2 against the success criteria.

Table 6: Option 2 - HSTP+, success criteria analysis
Success criteria areas		Strengths	Weaknesses
All six-health system building blocks (reflecting priority levels)	Service Delivery / (High)	Same strengths as option 1 (continuity of approach, and the humanitarian plus model offers increased access at scale, and value for money).
	Access to Medicines (High)	Same strengths as option 1 (proven approach). / Move to a ‘pull’ system: FCDO-led HSS TA could support HSTP to accelerate progress to move from a ‘push’ to ‘pull’ system’, thereby reducing stock outs, and strengthening quality of care.
	Financing (High)	Same strengths as option 1 (co-financing and increased harmonisation) / HSS TA - FCDO-led HSS TA could supplement technical-focused WHO HSTP interventions (Health Financing Strategy, National Health Accounts) with political economy and conflict sensitivity analysis informed interventions (oversight, accountability, conditions, and advocacy). It could also ensure there is a clear link between HSS interventions and the service delivery component. / If FCDO did not conduct its own approaches to CE or HSS, we would risk them being deprioritised by the WB, the MoH, and other donors. If we provided the same funding directly to the WB, we would not be able to earmark or guarantee that the funding would be used for CE and HSS, minimising the opportunity for piloting and evidence-building.	Working outside of HSTP - FCDO-funded HSS and CE activities outside of HSTP could introduce a further layer of donor fragmentation compared to only investing through HSTP and introduces more partners for cross-sector coordination by MoH. The MoH currently has limited absorptive capacity to engage with various strands of policy development, which we would aim to address through HSS. Other donors and the MoH have supported FCDO’s plans, and we would coordinate closely with others, particularly the WHO, to minimise risk of fragmentation.
	Information System (Medium)	Same strength as option 1 - (build capacity via training). / HSS TA - FCDO-led HSS TA could unblock data culture and accountability challenges through building the evidence base, and piloting interventions – e.g. increased supervision of data collectors.
	Health Workforce (Medium)	Same strength as option 1 - (incentives).
	Leadership/ Governance (Medium)	Same strength as option 1 - (building capability). / HSS TA: FCDO-led HSS TA could explore how to strengthen governance of health at all levels, with consideration of the pathway towards R-ARCSS and state building.
Community Engagement		FCDO-led CE: Additional FCDO-led CE could pilot an approach to increase the coverage of services provided by BHWs, and target communities most in need. This would allow for tailoring to wider determinants of health in South Sudan, and the political economy. It builds the evidence base for increasing coverage (outcome indicator), beyond simply access to services in health facilities.	Delivering a FCDO-led CE component outside of HSTP risks fragmenting the health system. This would be mitigated through FCDO ensuring alignment with HSTP and gathering clear lessons learning for future implementation under BHI.
Disease outbreaks/Climate/ Conflict		Same strengths as option 1 - (responsive)
Diplomatic/ Political		Retain influencing levers outside the WB - Additional components outside of HSTP affords BE Juba Health Advisers, the SRO, and Development Director with an additional lever for influence outside of HSTP, thereby providing more entry points to drive our priorities. The programme funded Health Adviser would play an important convening, coordinating and influencing role across the wider health sector.
Programme management		Same strengths as option 1: (VfM, risk, fiduciary). / PF Posts - Programme funded Health Adviser and Programme Manager posts would strengthen UK influence and oversight in the health sector.	Burden - Increasing the number of FCDO-led components increases the burden on the BE Juba programme management team. Even so, this is a much lower burden than that sustained throughout twelve years of HPF, and so is manageable.
Evidence rating: Medium/Strong

### B3: Conclusion of the Options Appraisal – preferred delivery option

The options appraisal followed two stages.
  1. Firstly, we identified the need for a comprehensive package of high priority public health interventions across the six health-system building blocks. Our key objective is ensuring that service delivery is effective – this is the primary vehicle to saving lives. The service delivery building block requires the bulk of SHAPES’ resources in an FCAS context, alongside provision of essential medicines. We also recognised that in order to deliver services, phased targeted interventions are needed across each of the other building blocks such as access to medicines, advocacy for GRSS financing, strengthening information systems, the health workforce, and GRSS leadership and governance. Service delivery cannot be strengthened without building capacity under each of the other building blocks. For example, data from information systems is needed to inform supply chain procurement decisions, and catchment populations for facilities, incentives and/or government salaries are needed to motivate staff and ensure quality of care, and clear governance and leadership is necessary to coordinate services at all levels of the health system.
  2. Secondly, we discounted the ‘do nothing’ option and any continuation of HPF due to the extent of needs in South Sudan, and the strength of support for HSTP across the health sector. We proceeded to evaluate two feasible options, HSTP and HSTP+, against seven success criteria, rigorously analysing each of their strengths and weaknesses to decide which option could best deliver the comprehensive package of interventions and achieve the stated outcomes.

HSTP+ (option 2), with its additional FCDO-led targeted interventions in CE and HSS, demonstrated a more comprehensive package of strengths across the six building blocks, when compared with only investing in HSTP (option 1), and the counterfactual (‘do nothing’). HSTP+’s piloting of CE interventions addresses a critical bottleneck identified in the strategic case – without building knowledge, trust, and value in services at the community and household levels we cannot significantly improve the coverage of services in fragile and conflict affected South Sudan. HSTP+’s additional HSS component overcomes any risk of duplicating the WHO’s existing HSS programming under HSTP, through complementing the WHO’s focus on addressing immediate bottlenecks that impede service delivery, with catalytic interventions that strengthen the health system’s responsiveness and efficiency in the longer-term.

An FCDO supplemented HSS approach would complement the HSTP HSS component through BE Juba’s comparative advantages in the health sector; our understanding of the political economy, and conflict sensitivity analysis. Investing in HSTP will ensure the UK is engaged in the main instrument for harmonising health donors in South Sudan, giving us the best opportunity to deliver impact via service delivery at scale nationwide. Although HSTP+ would certainly bring a higher programme management burden when compared with HSTP’s entirely WB-led processes, it was assessed that the potential benefits of these additional components outweighed the programme management costs and were necessary for achieving the intended outcomes. HSTP+ will enable BE Juba to build the evidence-base for CE and HSS in South Sudan, and test new ideas for what works best in an FCAS context.

The HSTP+ approach outlines a balanced, interconnected and complementary package of support to address bottlenecks in South Sudan’s health system, summarised in Figure 5 below:
  1. We will provide essential health services and commodities through our support to HSTP and encourage increased domestic investment in health by GRSS;
  2. We will increase access to primary healthcare through our community engagement geographic pilots; and
    Deliver essential RMNCH services
    Engage with communities to strengthen knowledge, confidence, and agency at the community level
  3. We will strengthen the health system by drawing upon targeted, flexible TA to address specific blockages and our support to WHO under HSTP to progress towards a stronger, more sustainable and resilient system that moves beyond a reliance on donors; and
  4. We will also respond to health emergencies as these arise and whilst the longer-term work of strengthening the health system progresses to reduce maternal, newborn, and child mortality.
    Respond rapidly to health emergencies
    Strengthen health system building blocks to maximise lives saved and GRSS’ stewardship of the health sector

This analysis has uncovered that on balance, HSTP+ is the preferred option and is recommended as the option to be taken forward to cost effective analysis; as well as the financial, management, and commercial appraisal cases.
Figure 5: HSTP+ approach visualised

### B4: Summary of Theory of Change for the preferred option

The theory of change (ToC) outlines the proposed interventions and the proposed causal pathway from inputs to impact. It covers the five-year period for the continued provision of RMNCH essential services, health systems strengthening, enhancing community engagement, and responding to health emergencies. Achieving our impact statement of significant reductions in maternal, newborn, and child mortality will be a long-term agenda in South Sudan, towards which this five-year programme will take the first steps.

There is no single-entry point or clear pathway for strengthening health systems, particularly in FCAS. Therefore, our approach is built on investment in proven cost-effective interventions for maternal, newborn, and child health across the health system building blocks. We are piloting new approaches for health systems strengthening and community engagement to address long-standing challenges in South Sudan which we experienced during HPF programming.

In line with research by Nobel Prize winning economists Acemoglu, Johnson, and Robison, HSTP+ will aim to ‘increase incentives of political institutions’ in South Sudan to support growth and poverty reduction through co-financing and Government-led governance structures.[69]
[69] Robinson, James A, and Daron Acemoglu. 2012. Why Nations Fail: The Origins of Power, Prosperity, and Poverty

The ToC is: IF mothers, newborns, and children have access to quality and safe essential health services, and IF the six health system building blocks are strengthened, and IF communities become more accepting of preventive health services and demand for these increase, and IF health emergencies are responded to appropriately and rapidly, AND with strengthened linkages to peacebuilding, humanitarian and diplomatic approaches AND the GRSS assumes greater responsibility, leadership, and accountability for the health system, making it more responsive and efficient, THEN coverage of health services will increase, the health system will be better able to provide services, respond to health threats and rely less on donors for financing, incidence of ill health will reduce, ultimately leading to a healthier population with significant reductions in maternal, newborn, and child mortality.

There are two programme funded posts: one HEO Programme Manager and one Grade 7 Health Adviser. This builds on current practice under HPF, through which the UK have been able to engage and influence the programme, wider sector, and bring UK central investments together. The HEO Programme Manager will have an important role to play in partner coordination working with the L&E provider to share learning generated. It will be especially important to share the learning generated by the novel aspects of the programme, namely the community engagement component, with external partners. The FCDO has at least twelve years of experience managing health service delivery programmes on behalf of other donors. It will be important for the Programme Manager to share this expertise across the sector. The Grade 7 Health Adviser will have a critical leadership role in the wider sector focusing on cross sectoral coordination and providing capacity building, technical advice and oversight. The two programme-funded posts will work together, and we are exploring the potential to have these seconded into the World Bank to support HSTP on a part-time basis, thereby increasing our influence and access to reporting. Even if not fully seconded to the WB, the two roles will work closely with their project team. The two posts will also work together to support transition across the sector from a largely humanitarian focus to providing essential services.

Figure 6: SHAPES Theory of Change
The evidence for the theory of change is strong. It is based on over a decade of supporting and managing health service delivery programmes in South Sudan, as well as other relevant programming. It is informed by FCDO’s internal evidence review on the Best Buys for health, as well as a vast body of global evidence on RMNCH programming, health system strengthening and community-engagement for behaviour change evidence.

The programme will have the most significant impact within the health sector under the following conditions:
  1. GRSS increases its health budget allocation and expenditure, including the successful execution of this budget down to the subnational level, with continued support from the ongoing World Bank PFM programme.
  2. Progress made on public financial management by GRSS. For the health sector, this means regularly paying sufficient salaries to health workers and civil servants, with reduced ‘leakage’ of funds and improved accountability of spending at all levels from payam to national MoH.
  3. The other major health donors within South Sudan continue their financial and political support for health service delivery programming, allowing a strong and reliable multi-donor partnership.
  4. Planned CMPs, especially the new WISH-DIVIDEND programme provides support on comprehensive and inclusive SRHR, including support for service delivery to health facilities in targeted locations in South Sudan that complement service delivery and CE.
  5. FCDO’s ODA budget remains stable for the full duration of the programme, without in-year budget reductions necessitating a reduction to the scope of FCDO-led HSS and community engagement components,
  6. MoH is collaborative and seeks to positively and constructively engage on all aspects of the programme, particularly those relating to HSS.
1. The unpredictability of the South Sudanese, global, and UK contexts, particularly in terms of the global reduction in ODA, conflict, instability, political economy, delayed R-ARCSS implementation and elections, and the accelerating climate crisis, mean that the operating environment will be fluid and programme flexibility will be essential to success. SHAPES, by design, has been set up to be adaptable and flexible to a changing FCAS and global context. We have worked with the World Bank to put in place mitigations for continuing service delivery if conflict were to increase. We have mapped how the programme’s indicative milestones would adapt to different political scenarios in Annex D. Annex E details how SHAPES would specifically manage risks under a political scenario of deterioration, which could be all-out conflict, a climate shock that overwhelms the health system, or an infectious disease outbreak with high case-fatality. Our core priority under each scenario will be to manage and minimise all risks to service delivery, since this is vital to saving lives. We will manage SHAPES’ response to the changing context at each stage of the programme cycle through careful risk management and continuous dialogue with collaborating partners. There is a risk that the World Bank programme does not continue beyond three years. We assess this risk to be unlikely and would mitigate through engagement and planning with all donors, and where needed and in a timely way, rigorous prioritisation. These overarching risks affect all UK funded programmes in South Sudan and are manageable within the programme and wider BE Juba portfolio risk appetite, as demonstrated by the delivery of HPF programmes during previous periods of conflict.
2. Below is a summary of programme components and corresponding outputs for the recommended option.
Table 7: Programme components and outputs
Component	Corresponding Output
Component 1: Support to the World Bank HSTP - From 3 and up to 5 years	Output 1 (Improved access to RMNCH services and medicines in health facilities and communities). / Output 2 (Trained and motivated HCWs and BHWs deliver quality health services). / Output 3 (Strengthened use of data for review, planning, and decision-making on RMNCH by GRSS). / Output 4 (Strengthened GRSS coordination of programming, policy, and resources in the health sector, including commitment of its own domestic financing for health). / Output 5 (Health emergencies responded to rapidly, minimising impact on the health system).
Component 2: FCDO-led Health System Strengthening -	Output 3 (Strengthened use of data for review, planning, and decision-making on RMNCH by GRSS). / Output 4 (Strengthened GRSS coordination of programming, policy, and resources in the health sector, including commitment of its own domestic financing for health)
Component 3: Community engagement -	Output 1 (Improved access to RMNCH services and medicines in health facilities and communities).
Component 4: IRF to Respond to Health Emergencies (up to 10% of programme)	Output 5 (Health emergencies responded to rapidly, minimising impact on the health system).
Component 5: Learning and Evaluation -	Cross-cutting component that will benefit all outputs.
Component 6: Programme-funded Posts	Cross-cutting component that will contribute to all outputs.

### B5: Economic Appraisal/Cost benefit analysis

Approach
This appraisal monetises the health benefits of the programme, though there will also be spillover impacts on other areas such as education, productivity, the economy and stability. There are three main avenues to consider monetised benefits of the programme. Further details are available in Annex C.
  1. Impact on the health of mothers (e.g. maternal mortality impacts, life improvement)
  2. Impact on the health of under-5s (e.g. child mortality, stunting)
  3. Improvements for anyone accessing health services covered by the programme.

Data for RMNCH in South Sudan is incredibly poor. There is substantial uncertainty around the likely impact of health interventions, and therefore this appraisal uses highly conservative assumptions to compare monetised costs and benefits. If the intervention breaks even from a monetised perspective, when the conservative assumptions are relaxed, it will be good value for money. This appraisal uses the approach of Disability Adjusted Life Years (DALYs) in line with other economic appraisals of health interventions.

Options
Option 1 - Counterfactual
This assumes that FCDO ends bilateral support to the health sector and that other donors continue their support to sustain a basic level of health services. Given the lack of capacity and political will of the GRSS for the health sector, it is likely that a withdrawal by the UK would leave a substantial gap in the services available, rendering more health facilities non-functional. This option would result in a rise in mortality and morbidity rates, especially for vulnerable populations (mothers newborns, and people with disabilities). This would have severe humanitarian consequences, weaken institutions and cause a reputational risk to FCDO. This option is not recommended and is therefore not appraised.

Option 2 – Combined delivery of service delivery, health system strengthening, community engagement, and a rapid response fund
This option includes components 1-6 as set out in Table 7. For the appraisal, only components 1 and 2 are monetised. Component 3 focuses on CE for health services. Given the complex and political economy-shaped nature of this work and limited evidence base in South Sudan (although this is well evidenced in other contexts) the benefits of this option are not monetised, however the evidence suggests that these interventions are effective at increasing access and uptake of health services, though further learning and evaluation is needed to test these approaches in the South Sudan context. Furthermore, the benefits of this option are likely to be realised over the longer-term and outside the life of this programme. Component 4 is only expected to be utilised in an emergency situation. Given the uncertainty around the nature of any health emergency in South Sudan the benefits are not monetised. Components 5 and 6 underpin the delivery of the other components and so are not assessed in isolation. The costs of all components are however included in the final appraisal of value for money for the option.

Component 1- Invest in service delivery to save the lives of mothers, babies and children
Component 1 provides medicines and incentives for health workers that improve outcomes for mothers and under 5s, which would improve early years of health and give children a better start, but to keep modelling conservative it is assumed these benefits stop once service delivery stops in the programme. Benefits are monetised initially assuming 3-years of HSTP, but the additional 2-years of implementation is also considered in the summary table. A major focus of the health service delivery is on women and under 5s. However, we expect to see enormous benefits coming from a general improvement in health service delivery as a result of our support. Better trained health workers, cleaner and better maintained facilities with a more stable supply of electricity, water, sanitation and hygiene, and availability of essential medicines provides benefits for all South Sudanese accessing treatment, not just mothers and babies. Component 1 also includes a degree of health system strengthening. See Annex B for the detailed methodology.

Component 2 –Health system strengthening (HSS)
Component 2 focuses on enabling GRSS to lead, manage and take responsibility for a stronger health system in the future. The impact of this option will be realised over the long-term and will be less transformative on its own. Therefore, the impact is quantified by assuming a share of the benefits of service delivery persist for two years. To keep the assessment conservative, we assume the same DALY benefits per individual benefiting from the programme as component 1, although in reality we would expect this to be higher. See Annex B for the detailed methodology.

UK share of benefits
1. For both component 1 and 2, the UK will be contributing alongside other development partners. We claim benefits proportional to our share of the cost, equating to 19% and 31% for component 1 and 2 respectively. In reality, the UK through providing technical support, coordinating impact, and advocacy, will contribute more than just money. However, this is difficult to quantify in this appraisal. We assume the UK share of the costs and benefits is consistent throughout the lifetime of the programme.
2. To monetise the benefits this analysis uses the IMF’s 2023 estimate of South Sudan’s GDP per capita of $400. However, this estimate is heavily skewed by the impact of the oil sector in South Sudan which produces few jobs and the proceeds of which rarely remain in the country. If oil is stripped out of GDP per capita we get a more realistic figure for GDP (although the most conservative one for the full impact of a DALY) for a typical South Sudanese person of $80 (£64).

Non-monetised benefits
1. One of the key non-monetised benefits, which interacts with other UK Government interventions in South Sudan, is the impact on education. Healthier children are better able to learn, and healthier mothers are better able to teach their children. Not only does better health reduce absenteeism, but it also reduces presenteeism (physically being at school/work but not being productive). Better education in turn improves health, generating a positive feedback cycle. A healthier population can be more productive, increasing the average South Sudanese output (though this impact will be muted in the short term by the lack of employment opportunities). A healthier, better educated, more productive population also leads to strengthened peace outcomes, including through greater resilience to conflict shocks and by directly addressing some of the socio-economic drivers of conflict.
2. Better health services usually mean illnesses can be prevented, detected and responded to earlier, reducing costs to families that can be spent in more productive ways for the economy. Reduced mortality and morbidity improve the dependency ratio as parents are better able to support families. These are substantial benefits that should be considered as bolstering the case for this business case.

Component 3 provides additional non-monetised benefits since community engagement activities will increase access to and uptake of health services thereby multiplying the aforementioned non-health benefits.

Conclusion
The economic appraisal concludes that using incredibly conservative assumptions about the programme's impact and reach, the benefits of delivering components 1 in isolation and together with component 2 outweighs the respective programme costs (column A). In addition, the monetised benefits of delivering components 1 and 2 together outweigh the costs of the entire programme (column B). This holds true regardless of whether support to HSTP lasts for 3 or 5 years. When the conservative assumptions are relaxed and non-monetised benefits of all components included, the programme will represent good value for money. Whilst supporting HSTP in isolation is cost effective, delivering a comprehensive package of support with stronger emphasis on health system strengthening provides even better value for money. Delivering component 1&2 for either 3 or 5 years of HSTP is ‘extremely cost effective’ as the cost per DALY is less than the GDP per capita (a WHO[70] approved measure of cost effectiveness).
[70] WHO 2001 ‘Commission on Macroeconomics and Health’

South Sudan is a high-cost location for service delivery programming with areas of need often inaccessible due to conflict, flooding, and poor infrastructure. Air transport is often required to move supplies, including medicines, to health facilities due to poor road networks and flooding. This highlights trade-offs between meeting equity value for money targets and those of economy and efficiency, with those most in need often living in the most expensive to reach locations.

1. The economic appraisal demonstrates that the programme is expected to represent a good return on UK taxpayer’s money and is robust to a range of conservative assumptions, thereby achieving high VfM. Experience from over a decade of health service delivery programming in South Sudan provides a strong evidence base of service delivery interventions achieving VfM. Evidence/best-buys support the effectiveness of other components.
2. As with data in general in South Sudan, the availability of robust VfM data is limited. Baselines are available from previous programmes including HPF3 for some VfM measures (see Annex C). These programmes covered a smaller number of states, and a different package of services compared to HSTP and so will only be indicative but can help to benchmark VfM. We will strengthen the collection of quantitative and qualitative data across VfM indicators to better assess VfM. We will use the HSTP and SHAPES governance structures to discuss VfM and to inform decisions on trade-offs and choices within the available budget. Programme-wide VfM indicators may include:

Table 11: Potential VfM indicators
VfM Measure	Indicator
Economy / Input / Quantitative	% of budget allocated to management fees of implementing partners. / Direct cost of health service delivery (broken down by cost of commodities and distribution, HCW incentives, training, warehousing and HF rehabilitation).
Efficiency / Input to output / Quantitative and qualitative	% of output indicator milestones meeting targets within agreed timelines. / % of incentive payments received by eligible health workers within agreed timelines. / Evidence of coordination between programme and sector stakeholders. / Cost per service output (HPF3 provided data on antenatal care, skilled delivery, family planning, OPD consultations, vaccination and BHW consultations) / Cost of drug delivery per CHD and per Health Facility / Cost per health worker for training delivered.
Effectiveness / Output to outcome / Quantitative and Qualitative	Adolescents and community members demonstrating increased acceptance of and demand for preventive health services, namely SRHR and family planning. / Drug stockouts/drugs expired. / Community feedback on quality of care. / Strengthened Health Management Information Systems are used to inform decisions on service delivery e.g., quantification of medical supplies.
Cost-effectiveness / Input to impact / Quantitative	Cost of reducing maternal/ child mortality. / Cost per DALYs averted / Cost per Couple Years of Protection (CYPs) provided.
Equity / Input, output, outcome, impact / Quantitative	Number and state distribution of functioning health facilities per 10,000 population / Efficiency and effectiveness indicators by state. / Distribution of health workers by specialisation, state and sex / Proportion of women to receive ANC 4 visit amongst the total number of pregnant women expected for the year per state. / Proportion of women to have skilled delivery amongst the total number of pregnant women expected for the year per state. / % and number of female BHWs trained and recruited. / % of women of reproductive age using modern family planning methods. / Proportion of patients treated with disabilities.

The Internal Risk Facility (IRF), should it be deployed, will support interventions that are early or anticipatory action. We recognise that marginal costs and risks are higher for IRF than core programme spend, but evidence demonstrates that the benefits outweigh the costs. Several studies demonstrate the benefits of early action in humanitarian contexts. For example, modelling in Kenya, Somalia and Ethiopia in the context of drought and food insecurity, illustrates that timely action saves up to US$1.6 billion in humanitarian aid costs over 15 years compared to a late emergency response. Similarly, UN research on emergency preparedness and value of rate of return on investment for six countries indicates on average every US$1 spent saves US$2.60. Given the challenging context in South Sudan, we require a mechanism to access funding to respond to shocks that threaten to overwhelm the health system e.g., disease outbreak or climate related. In doing so, we will help prevent the diversion of funds away from service delivery to a health emergency response.

The challenge lies in shifting efforts from a focus on improving the economy and efficiency of existing, well-established interventions to testing the effectiveness of new interventions, namely HSS and community engagement interventions. This will require rewarding innovation and using monitoring and evaluation to test new approaches and to learn. The shifts we seek to incentivise, and reward include:

  1. From a reliance on donors for providing essential RMNCH services and medicines and incentive payments to healthcare workers, to GRSS taking greater responsibility for the health sector, including through increased domestic investment.
  2. From hesitancy, misinformation and lack of uptake for preventive health services to greater awareness of, trust in, and access to these services at the community level.
  3. From a reliance on humanitarian partners to respond to health emergencies when these occur to a greater focus on prevention and preparedness through a more resilient health system.

Cutting across all of these shifts is a focus on equity. We will look to optimise the trade-off between the equity dimension of VfM and other dimensions, namely economy and efficiency, which may mean reaching fewer people since we will prioritise reaching those most marginalised and in need. For example, HSTP aims to ensure refugees and host communities can access health services.

Where possible, we will build VfM measurements into agreements to incentivise partners.

Management Case

### E1: Overview
The six components of the programme will be delivered through different modalities and partners. FCDO will use a range of governance and management structures and approaches at national and subnational levels. FCDO will ensure at programme level to undertake assessments to manage partners and the programme, including due diligence for each component, as well as delivery chain mapping and risk assessments. In line with the requirements of the PrOF, FCDO will have representation on programme level governance structures and sector level oversight structures to monitor the operational, technical, and strategic implementation of the programme.

The health team within the BE Juba Essential Services Team will manage supplier performance while overseeing technical, delivery compliance and assurance. The overall responsibility for the programme will sit with a G6 Team Leader Senior Responsible Owner (SRO) (0.6 FTE), with technical advice from SEO (0.7 FTE) and Grade 7 (0.8 FTE) Health Advisers. Programme Management will be resourced with a SEO Senior Programme Manager (Programme Responsible Owner (PRO)) (0.4 FTE), HEO Programme Manager (0.8 FTE) and EO Programme Officer (1.0 FTE). The SRO will be accountable for the design, mobilisation, delivery, completion, and closure of the programme, as well PrOF compliance and managing risk. Paragraph 282 sets out the PFP’s roles and responsibilities.

The BE Juba Results Adviser will provide support to the BE Juba Health Team to provide advice on the log frame, monitoring plan and coordination of the SHAPES L&E, MLSS and HSTP TPM suppliers, including monitoring reports, learning products and evaluations. Each evaluation report will be published and followed by a management response which will set out how the programme will be adapted to respond to recommendations and findings.

The programme will further benefit from the BE Juba Conflict Advisers, Social Development Adviser, Economist, Climate Adviser, Humanitarian Advisers, Livelihoods Adviser, Education Advisers, Governance Adviser, Finance Manager and Political Counsellors. The Ambassador is formally accountable for the ODA portfolio in South Sudan but delegates the management and oversight responsibility to the Development Director in line with PROF.

Coordination across the BE Juba teams is critical for the successful delivery of this programme. This includes escalating programme issues to the Development Director and Ambassador; cross-Embassy coordination of high-level messages for the Development Director and Ambassador; joining up on humanitarian, livelihoods and resilience programming with the Humanitarian and Livelihoods Team; and working with the Building Stability and Open Societies team to ensure health work is informed by wider political and political economy considerations and is coherent with peace building and governance programmes. Teams will work together sharing advisory inputs and convening cross-team meetings as appropriate. This will be especially important for Component 1 to lay the foundations for the transition from humanitarian to HSTP supported health facilities and Component 3 for potential complementarities with the EFASS and GBVPSS programmes on community engagement and service access. BE Juba will also periodically conduct joint partner days and sessions to bridge links and synergies across programmes. Joint field monitoring will be undertaken, and learning will be shared. Teams will work to bring other development and humanitarian donors into fora that allow a more strategic approach to allocating resources, particularly in the humanitarian and nutrition sector.

SHAPES will be subject to cross-office management, including:
  1. Deep dive discussions with the Development Director on programme performance, risk, financial and partner management on a six-monthly basis.
  2. Escalating risks outside appetite and severe risks to the Development Director.
  3. Reporting to the Quarterly Assurance and Compliance Board which considers results, risk management, financial progress and cases of fraud/loss and safeguarding.
  4. Informing development of policy and political engagement across BE Juba e.g. through the ODA Delivery Group, BE Juba Country Board, and Senior Leadership Team.

Within FCDO, SHAPES will engage with relevant CMPs and core funding contributions as well as office-wide priority campaigns. As an HWCN Flagship country, progress and results generated from SHAPES will be reported to the FCDO HWCN Hub within Human Development Department as part of regular results monitoring to consolidate multi-country reporting to assess FCDO’s progress towards the Healthy Women, Children and Newborns initiative.

### E2: National Health Sector governance
Despite a plethora of coordination structures in South Sudan, effective governance and oversight of the health sector remains weak. The most effective dialogue with the MoH over the past year has been through the structures used to design and mobilise HSTP which has proved a channel for engagement and influence with the MoH. These have morphed into the formal HSTP committees, explained in paragraph 267, which the MoH is also keen to leverage wider sector coordination. The PFPs will play a critical role in engaging with the HSTP committees and the structures set out below to help strengthen oversight and coordination across the sector.
  1. South Sudan’s Revitalised-National Development Strategy (R-NDS) 2021-24 outlines the GRSS’ priorities for driving progress on development, peace and the economy.[71] The governance structures underpinning the R-NDS were to include a Cross-Sector High Level Committee, chaired by the MoFP, supported by Sector Working Groups to improve alignment between ODA and R-NDS priorities, and lay the foundation for a progressive shift towards a more sector investment-focused programmatic approach. The GRSS has not progressed this initiative and neither the Sector Working Group nor high level committee function.
    [71] The Revised National Development Strategy for South Sudan – 2021- 2024 | United Nations Development Programme (undp.org)
  2. The Health Sector Steering Committee, which is chaired by the Minister of Health to direct the strategic development of the health sector, has met once in the last year.
  3. An Advisory Committee, chaired by the Undersecretary bringing together MoH, donors and the Fund Managers of the two main health service delivery programmes was supposed to meet to discuss progress, direction and any key issues on a quarterly basis but has not met in the past year.[72] With HSTP now effective, it is no longer relevant.
    [72] The Health Pooled Fund III and the South Sudan COVID-19 Emergency Response and Health Systems Preparedness Project. From November 2022 the programmes led service delivery in seven and three of South Sudan’s 10 states, respectively.
  4. The Health Development Partners Group (HDPG) brings together donors, multilaterals and key implementers monthly to align and coordinate support against national health priorities. This is currently co-chaired by two UN agencies, WHO and the World Bank, and rotates annually. Development-humanitarian coordination is facilitated through attendance of the Health Cluster coordinator.
  5. The Health Sector Donor Group (HSDG) meets monthly, often ahead of the HDPG, to coordinate donors on key priorities and develop joint advocacy positions to lobby GRSS and advise/ instruct development partners. Attendance is generally limited to likeminded, major health donors (USAID, Canada, SIDA, EU, GAVI, GFATM, CDC/PEPFAR, World Bank and FCDO). This is co-chaired by two donor organisations, currently FCDO and the World Bank, and the chair rotates annually.
  6. There are dozens of Technical Working Groups, generally led by the MoH. However, only a small number meet regularly. Sub-national coordination is predominantly conducted through the State level Health Cluster meetings chaired by WHO.
### E3: Programme governance and management arrangements

Different governance structures are required for the WB/GRSS led HSTP (Component 1), compared to those directly managed by FCDO (Component 2-5) and the PFPs (Component 6). The BE Juba team will be responsible for ensuring coordination, coherence and synergies between the different components through representation on both structures at all levels. The World Bank HSTP governance structures have been set out in the approved World Bank Project Appraisal Document and TORs have subsequently been agreed for different governance bodies. For FCDO directly managed components, the governance arrangements will be finalised during the inception and mobilisation phase through a detailed TOR based on the approach set out below.

Governance arrangements - Component 1 – Support to the World Bank HSTP

FCDO will allocate the largest portion of the SHAPES resources (75%) through the World Bank’s HSTP. Donors will engage the World Bank through Standard Administrative Agreements (SAAs) either to a MDTF or a Single Donor Trust Fund (the former will be used by most donors, including FCDO). The World Bank has signed a Financing Agreement with the MoFP for the HSTP resources to clearly identify government responsibilities and contribution.

The World Bank is using a hybrid implementation approach for HSTP to incentivise GRSS to take greater responsibility and accountability for the delivery of development projects and results, while protecting health service delivery and system strengthening through engaging UNICEF and WHO as MOs’. This includes a small, targeted amount of Government led implementation which will test government commitment and management capacity while providing for managed conditions to create an entry point for pushing the government to deliver against a set of enabling commitments including co-financing. The BE Juba is supportive of this approach as a first step towards a more resilient and sustainable health system.

The World Bank and MoH has established a High-Level Steering Committee (HSC) to provide strategic direction, overall coordination and policy guidance on the sectoral challenges and future steps on service delivery, HSS and ultimately transforming the health sector. The HSC currently meets on a quarterly basis with membership at the Ministerial and Heads of Cooperation level. An Operational Steering Committee (OSC) has also been established to provide routine oversight and technical guidance during project implementation. The OSC is responsible for ensuring that the implementation of the project is carried out efficiently, is evidence-based and with the necessary technical quality. The OSC meets monthly, and membership consists of technical level officials from MoH, World Bank, MOs, and donors. The OSC reports to the HSC with decisions flowing from the HSC down to the OSC and the PMU serves as the Secretariat to both. Figure 7 below provides a diagrammatic description of the HSTP governance structures. In addition to these steering committees, the World Bank has convened a Donors Committee to support the implementation of HSTP through improved coordination and alignment of HSTP donors to influence higher decision-making structures more effectively. A version of this governance structure was in place during HSTP design and mobilisation and has now transitioned into more formal structures. A full list of partners and their roles and responsibilities on HSTP can be found at Annex F.

        Figure 7: HSTP governance structure
As part of the hybrid approach of HSTP, the MoH will be responsible for establishing, recruiting and hosting a Project Management Unit (PMU), to manage health service contracting and the day-to-day engagement with the GRSS, MOs, and donors. The PMU will include qualified and capacitated government and non-government staff covering the skill mix required for project management, financial management, procurement and contract management, M&E and environmental and social risk management. Note that some of the key positions have already been recruited. The PMU will also be staffed with technical experts (PSEA, Climate, Gender, conflict, etc.) who will be responsible for ensuring these areas are considered within the programme approach and ensure assurance safeguards are in place.

The PMU will report directly to the Undersecretary of Health and will establish clear coordination mechanisms with the relevant departments at the national and State MoHs. Progress reports prepared by the PMU will be shared with MoH, donors and the World Bank as per the financing agreement every quarter. Figure 8 below provides a diagrammatic description of the PMU structure. The World Bank will manage the day-to-day program engagement with the PMU, MoH, MOs and the TPM supplier.

Figure 8: Project management unit
Funds for the project interventions and procurement of supplies will flow directly from the World Bank to UNICEF, WHO, and the TPM supplier. The funds required for PMU salaries and operating expenses will flow from the World Bank to the project designated account, which will be established and managed by the GRSS, expenditure from which will be dependent on the World Bank approving a Withdrawal Application submitted by the PMU. Figure 9 below shows the flow of funds within HSTP.

Figure 9: Flow of HSTP funds

The PMU, UNICEF, and WHO will submit to the World Bank quarterly financial and technical progress reports as per the required World Bank templates which will cover areas such as technical and operational progress, financial management, procurement, social and environmental risk management, visibility and communication, and evaluation on IP performance and corrective actions. FCDO will receive bi-annual reports produced by the World Bank. The TPM agency will provide monitoring reports on a quarterly basis. Additionally, all HSTP partners including donors will be invited to participate in quarterly missions to monitor project activities in the field. These missions will be followed by both OSC and HSC meetings to discuss progress, results and course corrections, if needed.

BE Juba will apply FCDO’s standard routes for managing programme performance of the World Bank and its selected MOs, including through a SHAPES logframe, which will include jointly agreed indicators to track HSTP performance, annual reviews, engaging in HSC, OSC and the Donors’ Committee, field missions and WB HQ monitoring missions and reviewing programme reports. The World Bank and GRSS, with inputs from all partners, has established a results framework for HSTP, which can be found in the approved PAD[73], with a sample provided in Annex C. The HSTP TPM provider will give further oversight and assurance.
[73] World Bank Document

FCDO directly managed components (components 2-5)

It will be necessary for FCDO to have separate governance arrangements in place for the components and partners we are directly managing, as set out in Figure 10.

        Figure 10: Governance arrangements for components 2-5

Governance arrangements
Level 1
The programme will be overseen by a SHAPES Steering Group which will drive programme delivery and performance improvements. This will meet quarterly and be chaired by the EST Team Leader who is also the SRO for the programme and will consist of the PRO, health advisers and programme team, Education, Social Development and Statistics Advisers and other advisers as relevant from BE Juba, and the FCDO HQ Healthy Women, Children and Newborns Hub lead. Each lead delivery partner (including the L&E supplier and MLSS TPM partner) will be members and present on progress, challenges, lessons learned and future plans. From GRSS, the MoH DG International Cooperation will be invited to participate and the World Bank, UNICEF and WHO, representatives, as HSTP partners, will be invited to attend as observers. The core activities will include:
- Providing oversight and reviewing overall programme performance and evidence generated and advising on any changes to the programme activities and focus to ensure the programme delivery and VfM.
- Approving workplans.
- Driving programme coherence, including with HSTP and other FCDO instruments and related donor programming,
- Guiding and reviewing policy work undertaken to support the programme’s objectives.
- Managing risks and opportunities.
- Driving innovation and learning.

The PRO will assume the role of the secretariat, by working with each of the delivery partners and bringing in the lead advisers, to ensure quality and timely submissions to the Steering Group. A detailed TOR for the Steering Group will be developed during inception. As the PFP HEO programme manager will support the WB in the HSTP governance arrangements, they will ensure linkages between all SHAPES components, together with the PFP health adviser.

The L&E provider will play a key role in coordinating monitoring and learning products across the different components to inform the Steering Group and recommend adaptations to programme workplans as relevant to maximise effectiveness. High-level findings from the MLSS TPM programme will also be discussed at the Steering Group.

Level 2
Monthly Technical and Programme Management Meetings: will take place on individual components to ensure FCDO compliance standards and technical requirements are being met, and to review progress and course correct. These will be chaired by the PRO with advisers and programme managers also attending. The meetings will focus on the delivery of the workplan, risks, financial performance, compliance and issues that require escalation to the SRO and/or the Steering Group. The meetings will present opportunities to review technical progress reports against workplans and performance indicators, and review risks and mitigation measures.

Additional Management arrangements components 2 and 5
Health System Strengthening component (2): will procure flexible TA to unblock specific bottlenecks across the various health system building blocks. The programme will need to flex to ensure the support best meets need and capitalises on opportunities where there is the most potential for success. We will ensure that the flexible TA is in line with the objectives of this Business Case. The TA will be agreed on an annual basis prior to the start of the FY but will be reviewed quarterly to ensure relevance. The process for agreeing the TA will include:
- Setting criteria for selecting TA during the programme inception period and reviewing on an annual basis.
- Assessment of need by the health advisers in consultation with BE Juba cross-cutting advisers, and other health sector partners including GRSS, HSTP partners and other donors.
- Development of options: The health advisers will provide a range of viable options including the rationale for support, alignment with Business Case objectives, the risks and opportunities to delivery, complementarity with other system strengthening activities by other development partners, the results expected to be achieved and value for money.
- Once ODA allocations are confirmed, the options will be presented to the Steering Group for discussion and approval by EST Team Leader/SRO.

Internal Risk Facility (IRF) component (5) to respond to health emergencies: will be activated if a rapid and flexible response to a health emergency is required, and subject to funding availability. The SRO will make an initial assessment, against a set of criteria which will be developed during the inception phase, regarding the need for additional financing. If there is a case, the SRO will make a request to the BE Juba Development Director for approval, setting out a clear rationale. Depending on the emergency, BE Juba may look to allocate additional resources by proactive reprogramming across the existing BE Juba portfolio; absorbing any underspend; escalating to Directors to explore the possibility of absorbing Directorate area underspend; or requesting an allocation from centrally held resources, such as a Crisis Reserve, in order to fund the response.  Should funds be made available they will be managed by the SRO.

If additional funding is made available, the IRF would be activated using the following process:
- Programme teams suggest partners and activities, ensuring alignment with the rationale sent to the Development Director. Cross-cutting advisors will be consulted, depending on proposals.
- The PRO would invite proposals from potential partners based on needs, geographical location, capacities and technical expertise. Ideally, these would be existing partners to SHAPES or existing partners on other BE Juba programmes and will have undergone due diligence assessments enabling them to respond rapidly. This may not always be feasible and new to SHAPES or BE Juba arrangements may need to be put in place.
- IRF proposals would need to comply with rigorous approval and accountability measures. IRF allocations will only be made after the internal appraisal process has established need, intervention effectiveness, risk and value for money.
- The SRO would approve proposals from partners within delegated authority limits using criteria that will be determined based on the emergency.
- Following SRO approval, additional funding would be communicated and disbursed to partners and agreements would be signed where these do not yet exist. The SRO will note disbursements in updates to the quarterly BE Juba Monthly Finance Meeting and the ODA Delivery Group.
- The SHAPES Steering Group will be kept informed of activities mobilised through the IRF.

While under FCDO agreement, the IRF partners would be part of the FCDO directly managed Governance Structures with reporting requirements set out in signed agreements or before additional funding is agreed. The SRO will also ensure the finance manager is updated on disbursals at monthly finance meetings.

We recognise the risks to activating the IRF component including the time and transaction costs in accessing funding, the additional programme management requirements, and the uncertainty that funding will be available. Nevertheless, given the challenging context in South Sudan, we require a mechanism to access funding to respond to shocks that threaten to overwhelm the health system e.g., disease outbreak or climate- related. By doing so, we will help prevent the diversion of funds away from service delivery to a health emergency response.

Programme Funded Posts
Two Programme Funded Posts (PFP) component (6) are critical to delivery of programme objectives. They will provide technical advice, oversight and management of the programme. The Grade 7 Health Adviser will focus on cross sectoral coordination and technical advice/oversight of the programme and health sector more broadly, ensuring synergies with SHAPES. The HEO Programme Manager will focus on coordinating across components, sharing learning and evidence from the L&E provider across the sector, and working closely with the World Bank on programme management of HSTP. The performance of each PFP will be managed by the EST Team Leader in line with the job descriptions and agreed ToRs, through FCDO’s performance management system and processes. The two programme-funded posts will work closely together, and we are exploring the potential to have these seconded into the World Bank to support HSTP on a part-time basis to increase our influence and access to reporting.

Management across the components.
It will be important that the distinct components and implementing partners of SHAPES align where relevant, explore synergies to improve VfM and learn from each other. The BE Juba team at all levels will be responsible for ensuring coherence and synergies between HSTP and the other programme components through various governance structures. The HEO Programme Manager will play a key role in coordinating the various FCDO directly managed partners working closely with the SHAPES L&E provider to facilitate the sharing of monitoring, learning and evidence generated across the components.

To further encourage collaboration and alignment between components and across relevant BE Juba programmes, the programme team will carefully design the logframe, exploring the potential for indicators shared between partners and programmes; this could be especially important for Component 3 – Community engagement for increased access to RMNCH health services and the EFASS and GBVPSS programme logframes.

### E4: Approach and Timeframe
The programme will be implemented over five years with the approach split into two phases – mobilisation /inception and delivery. The HSTP (component 1) started on 1st July 2024, and BE Juba has engaged closely with the World Bank and UNICEF on the inception activities and handover from HPF3 with the intention to contribute financially from 2025/26. Components 2-4, project preparation will take place in the first year e.g., proposal development, EME’s and ITTs publication, to allow for a phased approach to implementation in the second year. The inception phase for these components is estimated to take up to 6 months, during which time partners will be onboarded and management tools and procedures will be established. Tools, protocols and templates for the IRF will be established at the start of the programme to be ready for implementation as needed.

Mobilisation/Inception
All partners will need to understand FCDO’s zero tolerance approach: This means that we have zero tolerance to evidence that the necessary risk mitigation and fraud prevention activities have not been implemented, that the appropriate response, investigation and learning activities have not occurred when SEAH, fraud and aid diversion incidents occur, and that FCDO reporting requirements are not being met. All first-tier partners, including the WB, will be subject to rigorous due diligence assessments and most will be required to undertake delivery chain risk mapping before agreements are signed. Comprehensive country level due diligence assessments of implementers will either be undertaken as part of the contracting process, by the BE Juba programme team, or if a common supplier to FCDO, drawn from a Central Assurance Assessment or recent relevant due diligence assessment.

During inception, SHAPES programme team will work with partners to refine the Theory of Change, risk management strategy, VfM framework and metrics, and logframe, including setting milestones for each year of implementation. The time will also be used to further develop the governance structures, set the criteria for the IRF and system strengthening activities, develop partner reporting templates and to further explore with partners policies and processes for PSEAH safeguarding, fraud prevention, gender, disability, conflict sensitivity and climate aspects. The suppliers that FCDO engages directly will be required to provide FCDO with detailed annual work plans and an indicative plan covering the outer years for agreement with satisfactory performance assessed by FCDO. Due to the dynamic context and the high likelihood of sudden onset events (flooding, conflict, political instability) FCDO will work with partners to ensure budgets have flexibility to reallocate resources based on need and ability to deliver. This will ensure the programme continues to reach the maximum number of beneficiaries and allow partners to operate safely.

Implementation
From Q1 FY25/26, FCDO will contribute to HSTP implementation (component 1) and fund the 2 PFPs (component 6) as these are the priorities for implementation. The IRF (component 5) will be activated only when required to respond to a health emergency. The start date for all other components will depend on funding availability but it is expected that they will be phased in during the second year of the programme. Throughout programme implementation, partners that FCDO directly manages, will be expected to:
- provide quarterly detailed progress/results reporting, risk reporting and financial reporting. Partners will be responsible for all financial aspects of the programme namely: due diligence assessments of downstream partners, supply chain management, and verification of funds disbursed to downstream partners.
- record and maintain registers for all assets purchased using programme funds. These will be regularly monitored as part of monthly meetings with BE Juba. All assets under the programme will be owned by FCDO and maintained by the programme partners. Partners will be required to seek FCDO’s approval for all asset disposal plans. The disposal of assets will need to be done in compliance with requirements set out in FCDO’s agreement.
- have a comprehensive understanding and ability to analyse the evolving security situations and deliver on their duty of care responsibilities for their staff and downstream partners (see the commercial case for further information).
- undertake annual audits – each implementing partner will be required to undertake an annual audit. This should be tailored and proportion to both the size of the funding and the recommendations of the relevant due diligence assessment.

FCDO will align with the World Bank’s work plans, timelines and programme procedures for HSTP as agreed in the SAA and the Project Implementation Manual. The World Bank plans to provide annual audited statements.

Table 17: SHAPES programme set up and implementation timeline
Component	2025/26 Q1/Q2	2025/26 Q3/Q4	2026/27	2028/29
1 – Support to World Bank HSTP	Sign AA and agree payment schedule in Q1 2025/26	Implementation for five years
2 – FCDO-led HSS		TORs developed/ITT published/ / Proposal development and due diligence / TORs developed/ITT published	Inception/Implementation
3 – FCDO-led Community Engagement			Inception/Implementation
4 – L&E			Inception /Implementation
5 - Internal Risk Facility	Establish protocols and templates	Implementation as needed
6 – Programme-funded posts		Recruitment and implementation on a rolling basis

### E5: Measuring progress – monitoring, evaluation and results

Throughout the life of the programme, BE Juba will continuously review activities to ensure appropriate and necessary inputs are secured to support testing, learning, adapting and scaling up as relevant. BE Juba will work with partners to develop systems that capture lesson-learning and feedback mechanisms to improve effectiveness and scale up of successful interventions, whilst quickly identifying and scaling down, stopping, or adapting interventions that are not delivering results. The team will use rigorous processes to track issues and monitor the pace and efficiency of delivery. The Essential Services Team will proactively manage delivery and, where required, strategically allocate funds to activities and areas where delivery can be scaled up or pause/drop activity based on the context and risks. We will use qualitative results assessments and cost-benefit and cost-effectiveness analysis to ensure the programme is targeted in its approach and focuses its efforts where it can reach the greatest number of beneficiaries and have the greatest impact.

Results
The Theory of Change will be monitored by programme staff and the programme logframe will be developed as the scope of the programme is finalised. As mentioned above, the World Bank and GRSS, with inputs from all partners, has established a results framework for HSTP, with a sample provided in Annex C. Implementing partners will be required to develop their monitoring plans including specifying expected results and data sources. Key data sources may include routine information reported through DHIS2; additional routine programme generated data; regular surveys; feedback from community groups; and evidence from programme field visits.

FCDO will develop a draft logframe setting out the intended impact, outcome and outputs of the programme aligned to the ToC and drawing on the HSTP results framework. During the inception phases for the different components, partners will undertake detailed design work. The process will include the development of a joint logframe and monitoring plans (including field trips and liaison with the SHAPES L&E, MLSS and HSTP TPM providers) as well as agreement on reporting frequency and content. The BE Juba programme team will develop the programme’s delivery plan which will be the main programme management and monitoring tool, and this will be updated monthly. The Learning and Evidence Partner will be responsible for bringing together the results, VfM reporting, and annual reports from across the programme to consolidate the information and identify lessons and learning from across the portfolio.

Directly managed partners will provide detailed results reporting on a quarterly basis in line with the programme logframe. FCDO will agree reporting templates with implementing partners during the inception phase. The results reported will feed into the cross-Embassy MLSS TPM provider as well as SHAPES L&E provider and be discussed at the SHAPES Steering Group. Annual self-assessments will be done by implementing partners prior to scoring of the programme at the Annual Review stage.

Annual Reviews will be conducted each year and will be informed by findings of the SHAPES L&E provider, field visits, and partner reporting. A Project Completion Report (PCR) will be conducted by the BE Juba programme team at the end of the programme. Year 1 (inception) and end of Year 3 will be important points during which the BE Juba programme team will take stock of progress and results achieved to inform decisions on adapting programme plans as appropriate.

Monitoring, Evaluation and Learning
Given the high-risk context, the scale of the investment, the geographic spread across the country, and limitations the BE Juba programme team faces on travel across South Sudan, mainly due to concerns for staff safety, it is crucial for risk mitigation, learning and adaptive programming, to have independent verification of programme activities.

For Component 1, an independent TPM provider will analyse monitoring data and undertake verification where required. Biannual reporting of results to all donors will support the SRO, health advisers and programme team to monitor performance and identify areas of underperformance to inform decision-making. Output and outcome monitoring data will be used to inform discussions in the quarterly OSC meetings and biannual HSC meetings.

For Components 2-5, SHAPES will benefit from the cross BE Juba MLSS TPM provider, which will be procured and managed by the BE Juba Delivery Excellence Team and will complement the internal monitoring for this programme. The MLSS TPM will use cross-BE Juba field visits, partner reporting, mobile assessments (for example through photographic evidence) and data triangulation, to track progress against logframe indicators and milestones.

The SHAPES L&E provider will have a key role in providing necessary monitoring, learning and evaluation for Components 2,3 and 5 including testing the evidence base round the more novel aspects of the programme. This is necessary in addition to the MLSS TPM provider, which will focus on results verification, finance and compliance checks and portfolio level learning and evaluation, but not the in-depth learning needed on SHAPES. The SHAPES L&E provider will collate the learning and results of all SHAPES programme partners and facilitate the sharing of information across them. It will develop learning products on what works to improve RMNCH outcomes in South Sudan with a particular focus on the HSS and CE components, for the which the evidence base in FCAS contexts is limited. These will be vital to ensure the programme can learn and adapt while building the knowledge base across the health sector in South Sudan. The SHAPES L&E provider will also deliver mid-term and endpoint evaluations for the programme to assess its viability and effectiveness in delivering the ToC. This will be particularly important since this programme will be expanding from a focus on service delivery to support health system strengthening and behaviour change; both complex areas with a less developed evidence base. During inception, the SHAPES L&E provider will develop a monitoring, evaluation and learning plan for components 2-5 of the programme ensuring read-across to component 1.

Beneficiaries
FCDO recognises the strategic role of communities in the implementation, and monitoring of programmes. Beneficiary participation is important in this programme to ensure vulnerable groups are engaged, activities are improved through feedback from beneficiaries and that the programme meets beneficiary needs as effectively as possible. The programme’s deliberate approach of working at the community level allows for the identification of community mobilisation volunteers and mentors who will drive the agenda of behaviour change. Monitoring through the MLSS and World Bank TPM providers, by delivery partners and by the BE Juba programme team, will include qualitative and quantitative engagement with beneficiaries and stakeholders. For component 1, the World Bank TPM providers will carry out beneficiary experience assessments twice yearly to assess patient-reported experiences to better understand the patient experiences and the quality of services as reported by patients. They will also conduct a baseline and endline household-level survey to examine community level perceptions of the local health system including perceptions on health service availability, accessibility, quality and acceptability. For components 2-5, the approach to engaging beneficiaries will be further developed as part of the monitoring, evaluation and learning plan.

Transition and Exit plans
This programme has been designed to begin the process of gradual transition to GRSS leadership with a focus on building the MoH’s capability to lead, manage and take responsibility for a stronger health system while maintaining provision of key maternal, newborn, child and adolescent health interventions. Annex D sets out milestones for the incremental progress we would expect to see during the programme lifetime according to different political economy scenarios.

The key mechanisms and tools to drive sustainability include:
1. Influencing: Advocating, measuring and monitoring progress on health outcomes and health sector investment and reform. The forum for influencing is through our relationships with Government officials across the Ministries of Health and Finance, State Ministries of Health, and the Public Financial Management Oversight Committee. By joining with the other major health donors in South Sudan by convening through HSTP (High-Level Steering Committee and Operational Committee), our influencing abilities will be maximised.
2. Building Systems: Health system performance will be in-built into the logframe and technical expertise areas, using the six building blocks of health systems as a basis.
3. Capacity of NGOs and CSOs: Strengthening the capacity of NGOs and CSOs to support delivery of health services and to support community behaviour change.

Towards the end of Year 4, the programme will develop a transition plan to ensure activities are sustained in future programming or wound down responsibly. This will be guided by i.) agreements on future multi-donor health programming; (ii) the potential to further mainstream activities into government provision; iii.) support for knowledge transfer around activities that have achieved their objective iv.) discontinuation of activities that have proven not to be effective or cost-effective, ensuring lessons learnt are documented and shared. We expect that the World Bank model for support service delivery nationwide will continue in some capacity beyond its current anticipated end date of June 2027 with Additional Financing and into a second phase beyond the life of SHAPES. We do not anticipate the health system in South Sudan will be ready to graduate from donor support in the medium to long term and that FCDO funds will still be needed at the end of SHAPES.

### E6: Risk Management
Overall risk assessment
The programme will operate in a challenging and high-risk environment with insecurity in conflict hotspots, possibility of non-cooperation by local authorities and community leaders, fraud, losses, corruption, and safeguarding issues, all combined with very low levels of institutional capacity and political commitment across the Government. Given this context, and the change in approach to Government-led service delivery, robust risk management will be an essential means to ensure that SHAPES delivers on its objectives.

The programme risk appetite by risk category is set out and justified in the table below. The SHAPES risk appetite is within that set for the BE Juba as a whole. The risk appetites are relatively high reflective of both the need for BE Juba overall to accept risk to deliver humanitarian and development programming, as well as the need for a high-risk appetite specifically for SHAPES which is considered warranted to test and lay the foundations for a gradual transition to a more sustainable health sector in the longer-term and meet Country Plan objectives.

The risk appetites for the different categories are set drawing on the learning and understanding of risk drivers from HPF3 and our wider programme portfolio, as well as learning from other similar contexts. BE Juba takes setting a high-risk appetite seriously with robust risk mitigation and management in place at the portfolio and programme level. We expect our partners to do the same and will discuss key risks and mitigation with them at monthly programme management meetings with the expectation that any risks outside appetite are escalated immediately to BE Juba.

Table 18: Risk appetite
Risk Category	BE Juba risk appetite	SHAPES risk appetite	Justification
Strategy and Context	Eager	Eager	The SHAPES programme has an eager risk appetite for strategy and context risks. This reflects our acceptance of the risk to deliver objectives in a highly challenging and dynamic context in South Sudan including high levels of violence, limited governance, a severe humanitarian situation, high levels of corruption, disease outbreaks, cross-border movements and climate shocks.
Policy and Programme Delivery	Eager	Eager	The risk appetite for policy and programme deliver risk is eager. This reflects our acceptance of a high level of strategic and context level risk to deliver programme objectives together with additional risks of working with poor capacity Government-run health facilities, the lack of GRSS investment in the sector including the failure to pay salaries and implementing partner capacity to deliver.
Public Service Delivery and Operations	Receptive	Cautious	The risk appetite for public service delivery and operations is cautious. This reflects our unwillingness to accept weaknesses in duty of care processes, support services for staff, or compliance with HMG corporate procedures and processes given that South Sudan is a Conflict and Fragile State Post which involves delivering policies and programmes in a high-risk environment.
People	Cautious	Cautious	The risk appetite for people risks is cautious. The team is sufficiently resourced and has the relevant technical and programme management expertise. The team also has dedicated time of cross cutting advisers and will draw on them as needed. The risk appetite demonstrates our unwillingness to accept a high degree of risk to the welfare, capacity and development of our staff.
Safeguarding	Receptive	Receptive	The safeguarding risk appetite is receptive. Sexual exploitation, abuse and harassment are heightened due to high levels of vulnerability and opportunities for exploitation. The programme will work with some of the most vulnerable groups in South Sudan in an inadequate protective environment. The conflict and insecurity risks impact on the safety of implementing partners and health workers, and environmental risks related to medical waste are being managed but remain. There will be safeguarding cases but there will be a zero-tolerance policy to inaction on preventing, reporting and investigating cases.
Financial and Fiduciary	Receptive	Receptive	The financial and fiduciary risk appetite is receptive with safeguarding of development funds a priority. Corruption, patronage, looting and theft are endemic across South Sudan. A culture of impunity and weak accountability mechanisms is the context in which the programme operates. There will be cases of fraud, theft, loss, corruption and destruction of assets but there will be a zero-tolerance policy to inaction on prevention, reporting and investigation.
Reputational	Receptive	Receptive	The reputational risk appetite is receptive. This reflects the high level of context and delivery risks we accept but our caution in other areas. There are heightened risks related to health service delivery, safeguarding and fraud which if realised are likely to impact negatively on the UK’s reputation. However, it also reflects that for health service delivery (the major component of the programme), the World Bank will be the main partner working with the GRSS and MOs meaning that the UK will be one step removed from reputational risks.

The overall programme risk rating is assessed as Major[74], which is within the risk appetite set above. The key risks to the programme include strategy and context, policy and programming, fiduciary and safeguarding risks.
[74] HPF 1, 2 and 3, had the same risk rating, and have been able to operate in most of the country over the past decade, in both government-held and opposition-held areas.

Developments in the political economy will impact on the delivery of programme objectives. Annex D outlines how SHAPES’ milestones would shift under three political scenarios for the next five years: 1) status quo (no elections and limited social contract), 2) deterioration (conflict or a climate shock), and 3) improved stability and leadership from government (elections/political change). The mapping of these scenarios highlights how BE Juba will prioritise maintaining delivery of HSTP services at all costs, and this would shift our outcome and impact ambitions. Annex E sets out how risks will be managed in a deteriorating political situation to protect service delivery.

The programme risk register with full risk descriptions and mitigation measures can be found at Annex G. This will be further developed and updated during the inception phase based on discussions with implementing partners and cross-cutting advisory inputs, experience from HPF3, and recommendations from due diligence assessments. It will be embedded into the programme’s delivery plan and reviewed quarterly with programme partners. The key risks are:
Strategy and context: Insecurity, climate, the humanitarian context, economic risks alongside other factors affect the operating environment and have the potential to impact on the programme’s ability to deliver. In the most severe scenario, this could mean donors and/or partners drawing down from South Sudan and that the programme is unable to operate. Annex E sets out how the risks would be managed in this scenario. The political cycle including deteriorating relationships between donors and GRSS could lead to GRSS disengaging with the programme and/or the UK no longer deeming it acceptable to engage with the GRSS. This would impact on the HSTP’s effectiveness, especially the transformational objectives of the project with the HSS component, which depends upon MoH engagement, compromised. A disease outbreak has the potential to overwhelm the health sector directing all resources to respond. The 90-day pause, and potential cut, in USAID funding, as well as wider ODA cuts are likely to have a destabilising impact in South Sudan. Cuts to humanitarian funding will increase demand in already overstretched government-run HSTP supported facilities, from which the US is suspending its $30m planned contribution. Mitigation measures include closely monitoring the situation, strengthening the health system through SHAPES to be resilient to shocks and pivoting SHAPES to rapid response through activating the IRF and HSTP CERC if required, close coordination with other actors involved in the sector to maximise efficiencies and effectiveness of response, and using diplomatic levers to influence GRSS.

Policy and programming risks: Limited commitment to improving the health system by GRSS including low levels of domestic spending and minimal engagement on health system strengthening efforts. Key mitigation measures include co-financing agreements with GRSS, coordinating with other donors to advocate for increased spend on health services and building the MoH’s capability to lead, manage and take responsibility for a stronger health system. Other risks include insufficient capacity of delivery partners to deliver the programme, delivery partners unwilling to collaborate to maximise resources and minimise duplication and to cooperate with L&E and TPM providers, and insufficient uptake of health services. The programme-funded posts will play a critical role in coordinating donors and delivery partners across components. They will work closely with delivery partners on technical and capacity issues including behavioural and attitude change towards RMNCH at the community level to increase uptake of services.

Fiduciary risks: Funding is diverted either through poor financial management, weak controls or fraud. The GRSS and local organisation involved in programme delivery under the HSTP component increases the risk of diversion of funds due to capacity challenges resulting in the mismanagement of funds and opportunities for corruption, such as procurement, incentive payments, and siphoning off drugs. The WB and UNICEF’s controls are in place to mitigate this risk; UNICEF procedures are being followed for procurement and WB for PMU activities. A biometric system for payment of incentives to health workers and TPM are additional measures to manage this risk. The mitigation measures reduce the risk rating, but it remains major due to the complexity of the programme.

Safeguarding risks: Working with vulnerable communities, in difficult environments with a range of partners, with varying levels of expertise, increases the programmes exposure to safeguarding risks. The GRSS does not have adequate mechanisms in place to prevent and respond to safeguarding concerns and it is possible that victims will not be protected if they report concerns. The disposal of medical waste and expired drugs being prescribed will also require careful management and the BHWs and Health Facility staff sufficiently trained so as to avoid doing harm. Extensive environmental and social safeguard policies are in place under HSTP with the WB monitoring implementation.
Risk Management approach

SHAPES will have policies, procedures, and controls in place to identify, mitigate and manage the risks, which are in line with BE Juba and wider FCDO risk management policies. Early warning, timely escalation, and implementation of mitigation strategies to avert or manage the risks will be at the centre of programme’s risk management approach. Internally, the SRO will be responsible for escalating risks outside of programme appetite, or severe risks even when within appetite, to the Development Director, who in turn will inform HMA and escalate to the Director Africa – West, Sahel, Sudan and South Sudan as appropriate. The SRO will consult with the BE Juba risk lead as the risk is managed and escalated and to ensure it feeds into portfolio level risk discussions/assessments. The programme team will develop risk escalation protocols in consultation with implementing partners. All implementing partners will be expected to provide updated risk registers as part of progress reports and risks will be thoroughly reviewed at the HSC/OSC (component 1) and SHAPES Steering Group meetings (components 2-5) and updated or closed if required. The MLSS TPM provider, beneficiary feedback, field visits and the SHAPES L&E provider will be other avenues to assure that risks are being managed well by implementing partners. The risk management strategy will be further developed during inception in consultation with implementing partners.

While partners understand FCDO’s ‘zero tolerance to inaction’ approach including the need for robust mitigation measures and action on all potential or actual cases, there will almost certainly be incidents of fraud, loss, corruption and SEAH. All partners will be subject to rigorous due diligence assessments and required to undertake, and provide to the FCDO, delivery chain risk mapping. Safeguarding assurances and mitigating safeguarding risks will be mainstreamed across all partners. As with our current programming, we believe these risks – with appropriate mitigation – are justified by the benefits of providing critical health services to those in need, in a country with some of the worst health indicators in the world.
## Annexes
### Annex A. Possible options that the IRF could support.

- Rapid deployment of UK specialist expertise
- Targeted funding to partners on the ground
- Surveillance and data systems and tools
- Epidemiology and modelling
- Contact tracing and testing
- Laboratory capacity, including mobile capacity
- Vaccination, diagnostics and therapeutics – alongside other equipment and supplies, including personal protective equipment (PPE)
- Case management, treatment facilities
- Infection Prevention and Control (IPC)
- Mental Health and Psychosocial Support (MHPSS)
- Preventing and responding to sexual exploitation, abuse and harassment (PRSEAH)

### Annex B. Economic Appraisal

Approach
The benefits of service delivery and health system strengthening are both monetised considering the impact on the health on mothers (e.g. life improvement), impact of health of under-5s (e.g. child mortality, stunting) and the general improvements for anyone accessing health services covered by the programme.

Impact on health of mothers and children
The analysis makes an assumption that having access to health services for a pregnant woman confers a benefit of 1 DALY on average. To calculate the number of pregnant women per year, the analysis considers the birth rate (live births) as estimated by the World Bank, and applies it to the total population, giving an estimate of 316,390 births per year. If better data were available on maternal mortality rates, we would look at the pre- and post- widescale health programmes and derive a benefit from the decreased mortality rate. Given the limitation, instead we consider only an additional DALY per birth, keeping our estimate conservative.

In terms of Under-5 mortality, we do have a reasonable data point to use. In 2010, before independence and the arrival of widespread international health programmes, South Sudan was estimated to have an Under-5 mortality rate of 109 per 1,000 live births. In 2021, after years of donor health programmes this had been cut to 99 per 1,000. As such we make an assumption that health programmes have cut child mortality accordingly. As the life expectancy in South Sudan is around 55 years old, we assume that every Under-5 life saved is worth 55 DALYs.

Our programme will not only save children’s lives, but it will also improve them as the services provided, such as childhood immunisation, confer benefits throughout individuals’ lives. We therefore also add a benefit of 1 DALY per child helped in the programme.

Improvements for anyone accessing health services covered by the programme
Evidence from 2022 suggests there were over 5m outpatient consultations in South Sudan across just seven of its ten states. We do not have an estimate for the total number of consultations across the whole country and take the estimate for seven states to be conservative. It is likely some of these consultations were individuals making a repeat visit. We assume that an individual seeks treatment three times per year if they sought a consultation once (sensitivity analysis included in the annex).

Many of these individuals would also use health facilities in the second year, so we introduce a factor to account for these repeat visitors of 50% (again see sensitivity). This means in the second year we expect 842,000 unique individuals to attend a health facility and so on. We assume that each of these individuals receives a benefit of 1 DALY as a result of attending a facility at least once during the programme. Due to the HSS interventions we believe that there would be an additional DALY increase per unique visitor, however in the interest of conservative estimates this is not included in the central analysis.

Sensitivity
This sensitivity analysis focuses on the assessment of healthcare facility improvements since 40% of monetised benefits are derived from this component and there is little data on two key assumptions.

There is no data available on the number of unique patient consultations per year in South Sudan. The appraisal model assumes a patient seeks medical attention 3 times per year on average and the effects of varying this assumption is shown in the table below for the preferred achievement option assuming 3 years of service delivery. Similarly, there is little data on the proportion of patients who receive treatment in year 1 and do not visit the health facility again in year 2. The central assumption in the appraisal model is 50%, but this is assessed in the table below.

The present value cost benefit ratios and cost per DALY estimates are sensitive to both of these assumptions. However, the option 2 still represents good value for money and is highly cost-effective even when these assumptions are adjusted.

Sensitivity Analysis 1 – Adjusting consultations per patient per year and number of repeat patients for option 2.

	Assumptions	Present Value Cost Benefit Ratio	Present Value Cost/DALY
Consultations per patient per year	1	3.10	£20.67
	3	1.54	£41.43
	6	1.16	£55.32
Proportion of patients in year one also accessing health facility in year two	25%	1.99	£32.15
	50%	1.54	£41.43
	75%	1.30	£49.14

Detailed assumptions

Assumption	Value
GDP per capita	$400 (IMF 2023)
GDP per capita without oil	$80/£64
DALY value	GDP per capita w/out oil
Life Expectancy	55
Infant Mortality averted	10/1,000 live births (2011 rate minus 2022 rate)
Maternal Deaths averted	0 (due to data)
Births per year	316,390
DALYs per Mother (life improvement)	1
DALYs per U-5 (life improvement)	1
DALYS per U-5 (deaths averted)	1
Outpatient consultations (7 states)	5,050,000
Outpatient consultation scale up to 10?	No
Consultations per patient per year	3
Proportion of patients in year one also accessing health facility in year two	50%
Residual Maternal/U-5 Benefits	25%
Residual Healthcare Facility Benefits	50%

### Annex C: Example logframe and VFM indicators

VfM baselines

VfM Measure	Indicator	HPF 3 data at end of programme
Economy	Direct cost of health service delivery (broken down by cost of commodities and distribution, HCW incentives, training, warehousing and HF rehabilitation).	21% of budget for centrally purchased medicines and diagnostics, 59% for health workers incentives.
Efficiency	Cost per service output (HPF3 provided data on antenatal care, skilled delivery, family planning, OPD consultations, vaccination and BHW consultations)	Antenatal care (ANC4): £11.73 / Skilled delivery: £18.81 / Family planning: £2.79 / OPD consultations: £1.25 / Vaccination: £0.31 / BHW consultations: £0.68
Effectiveness/ / Cost Effectiveness	Cost per Couple Years of Protection (CYPs) provided. / Cost per DALYs averted	CYPs: £2.37 / DALYs: £17.99
Equity	Efficiency and effectiveness indicators by state.	Cost per DALY: ranged from £8.79 in Wau (WBeG) to £55.87 in Kajo-Keji (CES). / Cost per death ranged from £692.04 in Wau (WBeG) to £4,341.97 in Kajo-Keji (CES).

HSTP agreed results framework

Expand access to a basic package of health and nutrition services
No	Indicator	Baseline / - Sept 2023	Period 1 - Jul 24 - Jun 25	Period 2 - Jul 25 - Jun 26	Closing Period / - Jul 26 - Jun 27	Means for data collection* (frequency - Data source - data collection method; responsible & verifying entity
1	Percentage of Bomas covered by the Boma Health Initiative	16%	20%	25%	32%	Quarterly - DHIS2 - Quarterly Health Facility Assessment (HFA); TPM report - TPM & PMU
Improve health sector stewardship
2	Percentage of MoH budget executed	30%	50%	75%	99%	Quarterly - MoFP/MoH Quarterly Expenditure Report - PMU & WB; PMU & TPM
Strengthen the health system
3	General service availability score (Percentage)	30.4%	35%	40%	46%	Quarterly - DHIS2 - Quarterly HFA; TPM report - TPM & PMU

Component 1:  Provision of basic health services nationwide
No	Indicator	Baseline / - Sept 2023	Period 1 - Jul 24 - Jun 25	Period 2 - Jul 25 - Jun 26	Closing Period / - Jul 26 - Jun 27	Means for data collection* (frequency - Data source - data collection method; responsible & verifying entity
1	Percentage of Gender-Based Violence Services provided (Percentage)	0%	10%	20%	45%	Quarterly - DHIS2 - MoH & UNICEF report; MoH & UNICEF, verify TPM
2	Percentage of pregnant women receiving four ANC visits	20%	30%	40%	52%	Quarterly - DHIS2 - MoH & UNICEF report; MoH & UNICEF, verify TPM
3	Coverage of birth registration notification	0.4%	4%	8%	10%	Quarterly - DHIS2 - MoH & UNICEF
4	Number of health facilities with climate friendly minor rehabilitation and water and sanitation improvements completed (Number)	0	50	100	200	Quarterly - UNICEF & TPM - UNICEF & TPM Reports; UNICEF & TPM
5	Percentage of deliveries attended by skilled health personnel	19%	25%	35%	43%	Quarterly - DHIS2 - MoH & UNICEF
6	Percentage of children who have received 1st and 3rd dose of pentavalent vaccine	75%	80%	85%	90%	Quarterly - DHIS2 - MoH & UNICEF
7	Percentage of facilities reporting stock out of tracer medicines	27%	26%	24%	22%	Quarterly - HFA, Pharma Agency Distribution reports -; (TPM, Pharma Agency & PMU)
8	Percentage of children aged <59 months receiving Vitamin A supplements twice a year	66%	70%	80%	89%	Quarterly - DHIS2 & Survey - MoH & UNICEF
9	Percentage of children under 5 years who are wasted	16.1%	14%	12%	11%	Annually -DHIS2 & Household Survey (HHS) - TPM & PMU
10	Proportion of infants who have received first dose measles (MCV1) vaccine	72%	75%	80%	85%	Annually - DHIS2 & HHS - TPM & PMU
11	Under five years’ mortality rate (per 1000 live births)	98.69%	80%	70%	60%	Annually - HHS; TPM & PMU
12	Percentage of Intermittent prevention of malaria during pregnancy (IPT>3)	11%	50%	60%	75%	Quarterly - DHIS2 & HHS; TMP, MoH & UNICEF
13	Maternal mortality ratio	1,222	1,000	900	843	Annually - HHS - HHS; TPM & PMU
14	Contraceptive prevalence rate (any method)	6%	8%	9%	10.5%	Annually - HHS - HHS; TPM & PMU
15	Proportion of patients with suspected malaria who received a parasitologic test (RDT/Microscopy)	0%	80%	90%	95%	Quarterly - DHIS2 - HMIS; UNICEF & MoH
16	Proportion of health facilities that have a core set of relevant essential medicines and commodities available and affordable	73%	75%	78%	81%	Quarterly - HFA - HFA reports; TPM & PMU
17	BHI training material revised to include refugee sensitive health interventions. (Yes/No)	No	No	Yes	Yes	Quarterly - HFA - HFA reports; TPM & PMU
18	Number of health and nutrition services provided to refugees and host communities	0	1,300,000	3,700,000	5,940,000	Biannual - DHIS2 & Survey - HMIS & Survey reports; MoH & UNICEF

Health system strengthening
No	Indicator	Baseline / - Sept 2023	Period 1 - Jul 2024/5	Period 2 - Jul 2025/6	Closing Period / - JUL 2026/7	Means for data collection* (frequency - Data source - data collection method; responsible & verifying entity
1	Percentage of SMoH/CHDs with work plans aligned to the HSSP	0%	30%	60%	70%	Quarterly - WHO - WHO report; PMU & TPMA
2	Proportion of health alerts investigated in 48 hrs	81%	84%	86%	88%	Quarterly - WHO database – TPM reports; PMU & TPMA
3	Percentage of disease outbreaks in refugee areas that are adequately addressed as per WHO guidelines	0%	100%	100%	100%	Quarterly - WHO & DHIS2 - WHO report; PMU & TPM
4	Coverage of maternal death review	0%	25%	35%	55%	Quarterly - WHO database - TPMA reports - PMU & TPM

Monitoring and Evaluation, and Programme Management
No	Indicator	Baseline / - Sept 2023	Period 1 - Jul 2024/5	Period 2 - Jul 2025/6	Closing Period / - JUL 2026/7	Means for data collection* (frequency - Data source - data collection method; responsible & verifying entity
1	Percentage of health facilities receiving quarterly supervision visits (disaggregated by visits by CHDs, SMoH and IPs)	0%	30%	60%	85%	Quarterly - DHIS2 - QSC reports - PMU & TPM
2	Percentage of complaints to Grievance Redress Mechanisms satisfactorily addressed in a timely manner	0%	35%	50%	70%	Quarterly - UNICEF - Progress reports; UNICEF, PMU & TPM
3	Percentage of completeness of reporting by facilities	41%	60%	70%	80%	Quarterly - DHIS2 - HMIS reports - PMU
4	Percentage of states that conducted quarterly coordination meetings with a review of data and documented with minutes including action items and follow-up	0%	30%	50%	70%	Quarterly - MoH & WHO - WHO report; WHO, PMU & TPM

### Annex D. SHAPES’ milestones according to different political scenarios

Political scenario (2025-2030)	5-year milestones	10-year milestones
Status Quo (limited political opportunity for change: no elections and minimal GRSS financing)	Higher % of completeness of reporting by facilities. / Lower % of the population (rural, poor) residing more than 5 km from a health facility who are covered by outreach services / Stronger positive qualitative feedback on the effectiveness of MoH operational and high-level steering committee meetings from partners. / Higher % of health facilities that have a core set of relevant essential medicines available and affordable on a sustainable basis / Higher % of children who have received 1st and 3rd dose of pentavalent vaccine / Higher % of pregnant women receiving four ANC visits / Higher existence of formal linkages between facility-based and community-based service delivery / GRSS meets its $10m co-financing commitment by 2027.	Targeted reduction in maternal, newborn, and child mortality rates. / GRSS pays regular HCW salaries. / Lower % of population (rural, poor) living within 5 km of a facility offering specific services (e.g., obstetric care, a package of essential primary health care services, family planning and immunisation outreaches) / Higher budget execution for health. Data from DHIS2 is used to inform government health budget allocations for states and counties. / Higher % of health workers at primary care levels trained in community engagement and risk communication / Health system is more responsive and efficient on key areas – e.g. higher % facilities using community voice to inform service planning, higher % of counties submit timely, complete, accurate reports to the national level, and higher % of facilities providing outreach according to community needs.
Improvement (Improved political opportunity)	Targeted reduction in maternal, newborn, and child mortality rates / GRSS pays a contribution to HCW salaries. / Lower % of the population (rural, poor) residing more than 5 km from a health facility who are covered by outreach services / Higher % of counties that submit timely, complete, accurate reports to national level to inform timely data analysis / Higher % of facilities providing outreach according to community needs / Stronger referral pathways between the community and health facility levels. / Health system building blocks are strengthened to enable service delivery to run smoothly and meet different sub populations’ needs. E.g. – data use for decision-making, moves towards a pull supply chain system, and community engagement is embedded within the health system. / E.g. higher % facilities using community voice to inform service planning and availability and sufficient numbers of qualified personnel and infrastructure to compile and analyse information	Significantly lower maternal, newborn, child, mortality rates. / Significantly higher budget allocation and execution for health. / Higher number of doctors per 1,000 population / GRSS pays HCWs a regular and sufficient salary. / Significantly higher % of government health budget executed. / Significantly lower % of population (rural, poor) living within 5 km of a facility offering specific services (e.g., obstetric care, a package of essential primary health care services, family planning and immunisation outreaches) / Potential withdrawal of some INGOs at the county level. / Evidence and needs based budgeting for health / Open and transparent budgeting processes. higher % of government recurrent health budget spent on health
Deterioration (An emergency that threatens to overwhelm the health system – all-out conflict, a climate shock, or infectious disease outbreak)	Maintain numbers of lives saved through maintaining access to RMNCH routine services and essential medicines in health facilities and communities wherever possible. / Contingency or service continuity funds are accessible to the facility / HCWs and BHWs are protected as much as possible through continued payment of incentives to deliver health services. / Higher % facilities with prepositioned essential supplies / Roster of rapid response teams available to support response / Health sector policy defines roles of health services for emergencies / Higher % facilities with plans or service delivery models for hard-to-reach populations	Preventing a deterioration in maternal, newborn, and child mortality rates. / Build steps towards health system recovery and strengthening resilience if the political economy allows.

### Annex E. Managing risks in a ‘deterioration’ scenario (2025-2030)

### Annex F. HSTP partners and roles and responsibilities

Stakeholders	Role	Responsibility	Forums
MoH	Governance, oversight, leadership and strategy	Set sector policy and direction; pay health worker salaries; provide programme management function; coordinate health development partners; ensure implementation of the HSSP.	Health Sector Steering Committee. / HSTP HSC. / HSTP OSC. / Technical Working Groups / Health cluster (national and state)
MOFP	GRSS commitment and financial contribution / PFM reforms to support more efficient service delivery	Establish financial agreement with WB and dedicated banks accounts; ensure co-financing agreement is upheld; engage in strategic oversight forum; ensure state transfers made.	HSTP HSC. / PFM Oversight Committee
World Bank	Lead organisation for oversight of programme design and delivery	Contribution of resources; lead management and oversight of programme design and implementation; technical capability; establish financial agreement with GRSS; lead engagement with MoFP and MoH; monitoring and evaluation; coordinate donors.	HSTP HSC. / HSTP OSC. / HDPG. / HSDG
Donors	Financing and strategic input	Contribution of resources; strategic input to design and implementation; ensure programme alignment to sector priorities and needs; influencing and advocacy.	HSTP HSC. / HSTP OSC. / HDPG / HSDG
Management Organisations	Manage programme implementation	Contracting, management and oversight of IPs; procurement and distribution of commodities and equipment; payment of incentives; sector engagement and coordination with MoH and other partners; technical leadership; HSS activities.	HSTP HSC. / HSTP OSC. / HDPG
Implementing Partners (NGOs)	Lead implementation of service delivery within allocated ‘Lot’. A Lot if a geographical area used for health service delivery.	Ensure delivery of agreed services within health facilities and community; support and build capacity of CHD and SMoH;	Technical Working Groups. / Health Cluster (national and state); / HDPG.

### Annex G. SHAPES’ Risk Matrix

Name	Risk Description	Gross Likelihood	Gross Impact	Gross Risk Rating	Mitigation Strategy	Residual Likelihood	Residual Impact	Residual Risk Rating	Within Appetite?
Strategy and Context – Risk Appetite - Eager
Strategy and Context	A deterioration of the security situation in South Sudan from increases in sub-national violence or nationwide civil war results in damage to infrastructure, population displacement and disruption to supply chain routes resulting in SHAPES being unable to deliver health services at scale.	Likely	Severe	Severe	Diplomatic action to press government to stop/manage violence. / Close coordination with other donors and partners to maximise synergy of interventions. / Pivot SHAPES to rapid response including through activating the IRF and the HSTP CERC.	Likely	Major	Major	Yes
Strategy and Context	Economic instability and potential collage due to lack of oil revenue causes resources to be squeezed with even less money spent on health services. Local currency, South Sudanese Pound depreciates further, and health sector workers are not paid.	Almost certain	Major	Severe	BE Juba Economic Adviser to monitor the economic situation closely and provide advice to programme teams and engage centrally with GRSS. / Advocacy through engagement with Public Financial Management Oversight Committee and push for transparency surrounding the oil sector.	Highly likely	Major	Major	Yes
Strategy and context	Flooding and other climate shocks impact infrastructure, supply chain routes, displaces populations and increases outbreaks of infectious diseases, impacting the ability of SHAPES to deliver its objectives and for people to access health services.	Highly likely	Severe	Severe	Pivot SHAPES to rapid response through activating the IRF and HSTP CERC. / Strengthen the BE Juba and implementing partner understanding of climate risks and early warning systems available for use and potential adaptations to implement drawing on the BE Juba Climate Adviser. / Strengthen the climate resilience of the health system through supporting minor climate-sensitive rehabilitation to health facilities. / Pre-position medicines and commodities ahead of rainy season. / Draw on the UK Public Health Rapid Support Team to support response to health emergencies.	Possible	Major	Major	Yes
Strategy and context	Humanitarian context within South Sudan or regionally leads to influx of refugees, returnees or IDPs creating pressure and unmet need for health services, overwhelming the health sector and increasing outbreaks of infectious disease.	Likely	Severe	Severe	Work with BE Juba SSHARP programme team to monitor ongoing humanitarian crises and use early warning systems to track potential new crises to build preparedness. / Work with other donors, development and humanitarian partners to agree joined up response to crises. / Draw on UK Public Health Rapid Support Team to support response to outbreaks. / HSTP expands support to more health facilities in the future to bolster the resilience of the health system to such shocks.	Possible	Major	Major	Yes
Strategy and context	The pause and potential withdrawal of USAID funding, wider ODA cuts, and a reduced HSTP budget leads to an increased demand on government-run health facilities and services, overwhelming an already overstretched health system.	Likely	Major	Major	Closely monitoring situation and improving understanding on implications for INGOs/NGOs implementing HSTP. / Improving coordination and identifying efficiencies across the sector. / Transparent decision making on HSTP budget discussions and trade-offs. / Liaising with the BE Juba Humanitarian and Livelihoods Team and humanitarian donors on the knock-on impact of the pause to humanitarian funding on the health sector. / Escalating risks of the impact of USAID funding cuts, especially to WHO, to HQs. / Pivoting WISHDIVIDEND to help address gaps in family planning/SRHR funding.	Possible	Major	Major	Yes
Policy and Programme Delivery – Risk Appetite – Eager
Programme and Delivery	Continued lack of commitment to the health system by GRSS including lack of domestic spending and lack of engagement on health system strengthening efforts, impacts on wider enablers for SHAPES impacting on serviced delivery and limiting health sector transformation and system strengthening potential.	Highly Likely	Major	Major	Pooling UK funds through World Bank HSTP with other health donors to create a single voice working together to lobby GRSS. / Co-financing agreement between World Bank and GRSS agreeing to $10m domestic investment to HSTP and UK conditional financing to further encourage full execution of this. / UK lobbying on increased spend on health services. / Payment of incentives to health workers directly involved in service delivery. / Engage MoH early to make them aware of our HSS plans to increase chances of MoH engagement when this is operational.	Likely	Moderate	Moderate	Yes
Programme and delivery	Insufficient World Bank, MO and IP capacity to implement HSTP objectives resulting in medicines not being distributed to health facilities, health workers not receiving incentive payments and capacity building plans stalled.	Likely	Major	Major	UK and other donors working with the World Bank and UNICEF to ensure sufficient resource in country. / HSTP to follow World Bank or UNICEF procurement rules to ensure selected IPs have necessary experience to deliver. / Influencing HSTP budget to ensure IPs and Unicef have sufficient resource to fulfil objectives. / Pivot SHAPES to rapid response through activating the IRF if needed.	Possible	Major	Major	Yes
Policy and Programme delivery	SHAPES fails to increase access to quality preventive health services resulting in continued low uptake of RMNCH services e.g. family planning, SRHR and immunisation.	Possible	Major	Major	Separate component within SHAPES to protect budget for community engagement interventions to ensure budget not fully consumed by support essential health service delivery. / BE Juba team to influence World Bank HSTP community health plans by BHWs to focus more on community health education, awareness raising to generate demand for health services. / Use SHAPES L&E provider to capture lessons on engaging communities in South Sudan to enable programme to adapt.	Possible	Moderate	Moderate
Public Service Delivery and Operations – Risk Appetite – Cautious
Public Services	Increasing insecurity in Juba poses a threat to BE Juba ability to maintain Duty of Care leading to further movement restrictions and potentially drawdown impacting our ability to implement SHAPES or undertake field visits.	Possible	Major	Major	BE Juba has crisis planning in place with clear plans on how to ensure the safety of BE Juba staff should a crisis occur. / BE Juba will use our networks in Juba and the region to monitor early signs of potential increases to contextual risks. / BE Juba staff follow security procedures and complete TRAs. / SHAPES implementing partners will be delegated duty of care for their staff and contractors and will be required to share their duty of care plans with BE Juba ahead of agreements being signed. / Work with Mos and IPs who are less likely to have the same level of restrictions in place.	Possible	Moderate	Moderate	Yes
Safeguarding – Risk Appetite – Receptive
Safeguards	Environmental and Social Standards: Risk breaches in compliance with environmental and social safeguards (ESS) standards result in significant ESS harm by the HSTP, including unsafe medical waste disposal creating environmental harm and physical harm from sharps, expired drugs not being disposed of safely resulting in these being prescribed to patients.	Likely	Major	Major	ESS documents in place that all HSTP implementing partners need to adhere to throughout the life of HSTP / MO and IP agreements clearly set out responsibilities on ESS. / HSTP TPM provider monitors implementation.	Possible	Moderate	Moderate	Yes
Safeguards	Lack of sufficient safeguarding policies for implementing partners, limited implementation and inadequate local reporting mechanisms to address allegations of SEAH and other forms of abuse exposing vulnerable people to increased risk in health facilities and communities.	Likely	Major	Major	Due diligences for all partners. / Social safeguards and policies in place. / Agreements clear on partners PSEAH responsibilities. / TPM monitors implementation of policies.	Possible	Major	Major	Yes
Financial and Fiduciary – Risk Appetite – Receptive
Financial and Fiduciary	No or limited funding available for IRF, and limited implementing partner capacity to scale up support at short notice.	Likely	Major	Major	Repivot funds from across the BE Juba portfolio in the first instance, liaising with the finance manager. / Identify potential funding sources from across FCDO. Put strong case to HQs based on need. / Use existing BE Juba or HSTP partners to deliver based on capacity.	Possible	Moderate	Moderate	Yes
Financial and Fiduciary	ODA budget does not cover commitments to HSTP WB MDTF and other project components.	Likely	Major	Major	Understanding profile of other donor funding and WB commitments to minimise impact. / Spacing commitment over longer time period, if HSTP is implemented over a longer timeframe. / Assess where best to focus resources across components to minimise impact on results/VfM.	Possible	Moderate	Moderate	Yes
Financial and Fiduciary	Exchange rate fluctuations and inflation and a deterioration in purchasing power, leading to limited access to cash for programme delivery.	Likely	Major	Major	BE Juba Economic Adviser to monitor the economic situation closely and provide advice to programme teams and engage centrally with GRSS. / Ensure majority of disbursements in GBP/USD.	Possible	Major	Major	Yes
Financial and Fiduciary	Funding is diverted, either through poor financial management, weak controls or fraud, impacting programme results and VfM.	Likely	Major	Major	WB controls in place for PMU and GRSS designated bank account. / TPM for all projects. / Field visits to check on programme delivery and assets. / Biometric system for payment of incentives to health workers	Possible	Major	Major	Yes
Reputational – Risk Appetite – Receptive
Reputational	UK faces criticism due to transition from HPF to HSTP, transition from humanitarian to HSTP support for health facilities, mismanagement of UK funds, systematic environmental or safeguarding failure and/or disruption to services leading to criticism by NAO and ICAI, negative coverage from the media and civil society.	Likely	Major	Major	Close monitoring of different programme including through TPM / Active engagement with the WB and MOs on HSTP implementation through governance structures to ensure risks are escalated as they arise. / Implementation of environmental and social safeguards. / Defensive lines developed jointly with other donors on transition from HPF to HSTP and humanitarian to HSTP funded health facilities, and separately if required.	Possibly	Moderate	Moderate	Yes
People – Risk Appetite – Cautious
People	Staffing: FCDO has insufficient staff resource or expertise to manage different components, perform adequate oversight and deliver objectives	Possible	Moderate	Moderate	Work with the Head of Profession to get a pipeline of health advisers interested in the role. / Keep the size and skillsets of the core team under review and assess the case for additional resources as required. / Ensure all programme team members have awareness of different aspects of the programme to provide cover and gap fill where necessary.	Unlikely	Moderate	Minor	Yes