## Girls Education and Skills Partnership Annual Review

Title: Girls’ Education Skills Partnership (GESP)
Programme Value £ (full life): £8 million		Review date: 22 June 2025
Programme Code: [AMP ID#} / 301437	AMP start date: / 06/04/2022	AMP end date: / 31/12/2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	B	B	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	D0003320.odt (live.com)
DevTracker Link to results framework:	D0003321.xlsx (live.com)

Programme Scoring

The Annual Review assesses and rates outputs using the following scale. The Aid Management Platform (AMP) and the programme scoring calculator will calculate the overall output score, taking account of the weightings and individual output scores.

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

A. SUMMARY AND OVERVIEW

Description of programme

The Girls’ Education and Skills Partnership (GESP) aims to boost girls’ access to education and address the skills deficit in Bangladesh, India and Nigeria. GESP provides high-quality and market-relevant skills training to girls and young women, enabling them to become entrepreneurial and employable in sectors such as information technology, manufacturing, and other STEM-related fields. It is an innovative programme which combines the resources of the private sector with the development knowledge and experience of the FCDO and UNICEF’s Generation Unlimited (GenU). Generation Unlimited act as the overall lead/coordinators for GESP, but deliver through UNICEF country offices in Bangladesh and Nigeria (hence references to both GenU and UNICEF as primary delivery partners through the annual review).

The UK’s contribution to GESP is made up of two primary components, Passport to Earning (P2E) and the Challenge Fund (CF). The bulk of our financial support goes towards the CF. P2E is Generation Unlimited’s free digital skilling platform, the CF is a competitive grant scheme which allocates financial support to innovative skilling and employability projects focusing on women and girls. Together these two streams comprise a holistic and integrated approach that aims to provide both scale in terms of the reach in number of girls skilled, but also depth of impact in the provision of market-relevant skills training to young women, which should support their transition to employment. There has also been a secondary component in GESP, of Private Sector in-kind donations, which Price Waterhouse Cooper (PWC) has been supporting a matching process with CF projects. The private sector contribution also includes their market expertise and network. The GESP Advisory Board is an integral part of GESP governance mechanism for private-public-youth partnership (including the Girls' Advisory Panel).

Supporting narrative for the overall score in this review

This annual review will focus on the UK FCDO investment in GESP, which includes progress of P2E (in Bangladesh and Nigeria) as well as the implementation of CF projects. FCDO’s contribution to P2E is modest, however we are the primary donor to the CF, which represents the majority of our investment. Beyond FCDO’s financial investment, we see GESP as a broader partnership.

This year GESP scores an A. This reflects good progress made across a number of projects, exceeding expectations in some areas, as well as underperformance and revised targets in a small number of areas. Overall therefore we think GESP is performing at A: Outputs Met Expectation.

The reasons for this assessment are:

- Consistently meeting set targets, and communicating more than 6 months in advance of the annual review where targets needed revision
- Projects moving from inception into delivery, and exceeding targets in some areas
- Agile programme management: overcoming challenges such as civil unrest in Bangladesh, and the fragile context in Nigeria including unexpected levels of inflation
- Collaboration with Government as well as Private Sector
- Proactive approach to upscaling and future programme sustainability
- Delays in contract signing for one of the projects (Technoserve) - have meant revised targets were necessary and pushed milestones into the final year of delivery
Key outcomes achieved during the Annual Review period:
- 5,499 adolescent girls and young women have been enrolled in formal and informal skilling, employment readiness, or leadership programmes with the support of 255 female mentors
- 3542 adolescent girls and young women have accessed learning to earning opportunities
- 454 public and private sector partners have been engaged in support services to adolescent girls and young women on areas such as employment, entrepreneurship support, employment transition services or workplace readiness support
- There is a marked improvement on previous years, particularly in Bangladesh where inception was challenging due to civil unrest, however projects managed to resume operations successfully once the political situation stabilised. Currency fluctuation in Nigeria also impacted day to day implementation, but all projects are now delivering well. There were initially delays in signing the contract for the Technoserve project in Nigeria, but overall, there has been a strong performance of delivery across CF projects in both countries up to May 2025.
- On private sector in-kind donations, PwC conducted matching and information sessions, in the form of virtual engagement events, to encourage engagement from private sector partners in the CF projects. Based on this continuous matching exercise, we now have a clear picture of those private sector partners that have not responded to communications and those who remain engaged as in-kind contributors. The UNICEF partnerships team have fully explored and ruled out the possibility of partners converting to cash donations.
- Private sector engagement was a cornerstone of GESP’s success, companies like Unilever, Accenture, Vodafone, PWC and Cognizant providing in-kind contributions, training, and mentorship.
  - In-Kind Contributions and Capacity Building
    - Cognizant: Delivered Training of Trainers (ToT) sessions on CV writing, interview preparation, and social media profiling for instructors in Bangladesh and Nigeria. These sessions directly enhanced the employability skills of both trainers and learners.
    - Vodafone: Through Vodafone Women in Business UK, led mentoring sessions at Yaba College of Technology (YCT), Nigeria, focusing on leadership, public speaking, and networking. These sessions inspired confidence and career ambition among young women.
    - PwC: Coordinated the in-kind contribution matching process, helping align private sector offers with the needs of Challenge Fund (CF) partners.
  - Digital Skilling and Curriculum Development
    - Microsoft: Supported the development and localisation of digital skilling content on the Nigeria Learning Passport (NLP), enabling access to courses like digital literacy and data science.
    - Accenture: Provided the “Skills to Succeed” curriculum, which was used by Sightsavers to train 254 young women with disabilities in Nigeria on employability and soft skills.
    - Coursera and Pearson: Although engagement was limited, they were part of the original in-kind partner group, with potential for future collaboration.
  - Entrepreneurship and Livelihood Support
    - Unilever: Partnered with Sightsavers to provide entrepreneurship training and business kits to 170 young women with disabilities in Nigeria, enabling them to start small businesses in retail sales.
    - Standard Chartered Bank: Played a strong advocacy role, promoting the shared-value partnership model and encouraging broader private sector engagement.
  - Impact of Private Sector Involvement
    - Enhanced Quality and Relevance of Training
    - Private sector partners brought real-world expertise into curriculum design and delivery, ensuring that training was aligned with market needs.
    - Their involvement helped bridge the gap between education and employment, especially in male-dominated sectors like ICT and retail.
  - Expanded Access and Reach
    - Airtel Nigeria provided internet connectivity to schools, improving access to online learning.
### Strengthened Public-Private Collaboration
    - GESP’s model of shared-value partnerships exemplifies how public and private sectors can co-create solutions for systemic challenges.
    - The programme’s success in integrating private sector actors into national skilling ecosystems (e.g., through job placements, internships, and mentorships) demonstrates a scalable and sustainable approach.
  - Why This Matters:
    - Innovative Model: GESP is a leading example of a public-private partnership that goes beyond funding to include technical expertise, mentorship, and advocacy.
    - Sustainability: By embedding private sector engagement into national systems and curricula, GESP is building long-term capacity and resilience.
    - Equity and Inclusion: Private sector partners have helped ensure that even the most marginalised—such as girls with disabilities—are included in the learning-to-earning journey.

Key achievements specific to the five projects that make up the Challenge Fund are:

POWER Project – Save the Children International (SCI)
- Locations: Kishoreganj, Bangladesh
- Focus: Tailoring, caregiving, beautician training
- Achievements:
  - 1,806 girls enrolled
  - 1,474 accessed employment or entrepreneurship support
  - 137 female mentors trained
  - 51 partnerships with employers and training centres
Shopner Sharothi – Jaago Foundation Trust (JFT)
- Locations: Cox’s Bazar and Bandarban, Bangladesh
- Focus: Retail sales, food & beverage, basic computer skills
- Achievements:
  - 735 girls enrolled
  - 221 accessed employment or entrepreneurship support
  - 18 female mentors mobilised
  - 474 family/community members sensitised
Skills in Demand for Girls’ Employment in Nigeria – Yaba College of Technology (YCT)
- Locations: Lagos, Nigeria
- Focus: ICT skills (web/mobile development, hardware repair), gender-responsive pedagogy
- Achievements:
  - 1,058 girls enrolled
  - 436 accessed employment or entrepreneurship support
  - All-Women Tech Hub established
  - 325 instructors trained
SABI-Woman – Sightsavers
- Locations: Lagos and Kano, Nigeria
- Focus: Disability-inclusive life skills, entrepreneurship, and employability
- Achievements:
  - 854 girls with disabilities trained
  - 170 started small businesses
  - 254 completed Accenture’s Skills to Succeed programme
  - 128 parents engaged in dialogue sessions
SAYWEE (Skilling Adolescents and Young Women for Entrepreneurship and Employability) – TechnoServe

- Locations: Kano and Lagos, Nigeria
- Focus: Entrepreneurship and employability training
- Achievements:
  - 1,046 girls enrolled
  - 74 trainers trained
  - Digital economy curriculum developed with MindTheGap
Key Features Across Projects
 - Curriculum Development: 31 gender-responsive curricula and teaching materials developed or revised.
 - Capacity Building: 585 instructors trained in inclusive pedagogies.
 - Mentorship: 255 female mentors engaged.
 - Community Engagement: 2,368 family and community members reached to shift gender norms.
 - Employment Linkages: 3,542 girls accessed employment or entrepreneurship opportunities.

We are pleased to see good progress overall with several targets exceeding expectations, however this there are a few areas of underperformance/adequate performance and some targets that currently remain at N/A or 0. It is our expectation that a strong performance complemented by agile programme management this year has set GESP CF projects up for successful delivery across all projects next year.

Communications between GenU and FCDO have met expectations this year, with bi-monthly programme meetings supplemented by ad-hoc communications on specific topics, meetings between FCDO and GenU senior leadership in New York and programme monitoring visits in Bangladesh and Nigeria. Communications around finances have been broadly satisfactory, and underspend has been communicated with FCDO along with a clear demonstration of how total budget spend will be achieved by the end of 2026.

Major lessons and recommendations for the year ahead

Major Lessons and Recommendations for 2025-2026
The Challenge Fund's implementation across Nigeria and Bangladesh in 2024 highlighted critical lessons in resilience, adaptability, and inclusive programming. In Nigeria, inflation and currency devaluation significantly increased operational costs, prompting UNICEF and partners to adopt cost-saving strategies such as leveraging local facilities and enhancing coordination with the Harmonized Approach to Cash Transfers (HACT) team to manage risks and reduce transaction costs. Security risks and infrastructure limitations, especially in rural areas, underscored the importance of strong local partnerships and flexible implementation models, including digital support and alternative energy solutions.
Political unrest and natural disasters delayed activities but also spurred innovation in planning and delivery. In Bangladesh, cultural and environmental challenges affected participation and access. Responsive measures—like relocating training to safer venues, revising transportation allowances, and deploying mobile outreach—proved effective in maintaining engagement.
Across both countries, inclusive targeting—especially of young women with disabilities—was strengthened through mapping, collaboration with disability networks, and adaptive outreach. Delays in partner agreements, such as with Technoserve, emphasised the need for timely coordination and contingency planning.
The transition to spending 0.3% of GNI on ODA will require significant shifts, as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect. ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. All GESP partners will need to work collectively to mitigate the impact of any reductions in overall resourcing for the programme once the FCDO’s resource allocation process has concluded, and in the context of overall ODA cuts.

Recommendations for the year ahead include:
- Continue robust risk management and contingency planning to mitigate delays and disruptions (April 2026).
- Continue partner coordination through regular forums and enforceable delivery deadlines to improve accountability (April 2026).
- Continue cross-learning among partners, especially on cost-efficiency and inclusion strategies (April 2026).
- Expand local engagement to build trust, ensure safeguarding processes are understood, and sustain programme delivery in challenging contexts (April 2026).
- In-Kind: Now that conversion to cash has been fully explored and deemed not possible for private sector partners,continue to strengthen existing offer on shared value partnerships – mentorships, work opportunities etc (April 2026).
- Resource planning for 0.3 transition: All GESP partners will need to work collectively to mitigate the impact of any reductions in overall resourcing for the programme once the FCDO’s resource allocation process has concluded, and in the context of overall ODA cuts

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summary of the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The overall goal of the programme is to have more employable, entrepreneurial and better skilled adolescent girls and young women moving into employment, venture creation or further education. The programme aims to improve the quality of skilling systems and training providers, making them more responsive to girl-centred skills development and relevant to meeting the needs of industry. It also aims to improve young women’s access to employment and entrepreneurship services that facilitate their transition to earning opportunities. To do so the programme will focus its key outputs around (i) Curriculum development and teaching and learning materials; (ii) Capacity of instructors (iii) Skills training and certification and (iv) Learning to earning transitions.

There have been updates made to the theory of change set out in the original business case to make outputs more targeted to the five CF projects and progress against them easier to measure. The last 12 months of the CF side of GESP have seen continued focus on project and budget refinement, due diligence processes, contract signing and implementation of projects, as well as progress against outputs demonstrated more recently. We are happy with the progress that has been made this year, and that clear milestones are in place with progress made against said milestones.

As noted in last year’s annual review, the programme would have benefited from a longer inception phase as part of the design process, given the innovative and complex nature of GESP. However, the overall outcomes and impact as set out in the business case theory of change have not materially changed.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Although CF progress in the last year suffered delays, the solid planning of the processes preceding implementation instils confidence that the programme will be on track to meet its overall target numbers of beneficiaries by the end of 2026.

GESP is delivering well with all projects contributing to cumulative targets over the programme’s lifespan and are on track to reach the target number of beneficiaries. P2E has been fully established in Nigeria and Bangladesh and has achieved good numbers of course registrations and completions. As a direct result of FCDO contributions 18,296 (31.7% of all P2E registrations) adolescent women and girls have completed a minimum of one course that have been FCDO funded.

CF projects in Bangladesh and Nigeria are performing well and are on track. The results matrix has been adjusted for Technoserve outputs not achieving the numbers forecasted due to late contract signing; however, mitigations are in place to achieve full delivery in the upcoming year.

FCDO are content with adjustments to the programme’s in-year budget and accuracy of forecasting to avoid underspend.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

GESP should continue based on its unique offering of skills-based education, specifically targeting girls and young women in line with the ambition of FCDO International Women and Girls Strategy. The 5 CF projects are on track to deliver skills to around 80,000 girls and young women by the programme end date. Through GESP links to the private sector we can showcase the value of investing in girls’ education and skilling around the world through a public, private and youth partnership approach, paving the way and developing the case for similar innovative partnerships in the future.

Now that the Challenge Fund projects are operational, we are assured that they are delivering good VfM. Due to the solid foundations laid during the set-up period, it is expected that GESP will deliver well against outputs in the 20 months remaining of the programme.

Project key:
JFT – Jaago Foundation Trust
SCI - Save The Children International
YCT - Yaba College of Technology
SS - Sightsavers
TS - Technoserve

## C. DETAILED OUTPUT SCORING

Output Title	Curriculum development and teaching and learning materials. Skills and development and training programmes have improved skills-driven curricula and teaching and learning content/materials (TLM) relevant and responsive to the needs of young women and the local labour markets
Output number:			1.1	Output Score:		A
Impact weighting (%):			15%	Weighting revised since last AR?		N/a
Indicator(s)		Milestone(s) for this review			Progress
1.1.1: Number of relevant public and private sector actors engaged in skills driven and gender responsive curriculum or TLM revision/development (disaggregated by type of actor)		Total: 185 / CF: 185 / • 30 (JFT) / • 15 (SCI) / • 60 (YCT) / • 75 (SS) / • 5 (TS)			Total: 226 / CF: 226 / • 30 (JFT) / • 31 (SCI) / • 61 (YCT) / • 75 (SS) / • 29 (TS) / Met
1.1.2: Number of curricula and TLM (including P2E course courses) developed/revised with a gender equality perspective to avoid perpetuating inequalities and biases (disaggregated by subject / type of skilling provision		Total: 28 / CF: 28 / • 3 (JFT) / • 13 (SCI) / • 8 (YCT) / • 2 (SS) / • 2 (TS)			Total: 31 / CF: 31 / • 3 (JFT) / • 16 (SCI) / • 8 (YCT) / • 2 (SS) / • 2 (TS) / Met

Output activities and supporting narrative for the score.

- Save the Children (SCI) developed 16 content resources to support skilling interventions, including bilingual task catalogues (English and Bangla) and thematic content on social-emotional learning, growth mindset, green mindset, digital literacy, and leadership.
- JFT created three market-aligned, gender-sensitive curricula and course modules.
- YCT produced one course on gender-responsive pedagogy, three job-hunting skills courses, and four TVET materials covering computer/mobile repairs and web/mobile applications.
- Sightsavers designed two resources: a disability-inclusive life-skills package and a training manual for vocational instructors.
- TechnoServe developed a digital economy curriculum and revised an existing one to enhance market relevance, gender responsiveness, and disability inclusion.

ON TRACK: 31 curricula and teaching and learning materials (TLMs) were developed, revised, or adapted—surpassing the target of 28. These materials were designed with a strong focus on gender equality and market relevance. A total of 226 public and private sector actors (target: 185) contributed to the review process. As a result, 6,054 students and trainees (target: 2,291) are now being taught by trained personnel using these resources.

Output Title	Capacity of instructors / Teachers/trainers/instructors, and relevant actors have increased capacity to ensure gender-friendly work and learning environments and/or apply responsive pedagogies and tools to equip adolescent girls and young women with market-relevant skills
Output number:		1.2		Output Score:		A
Impact weighting (%):		20%		Weighting revised since last AR?		N/a
Indicator(s)			Milestone(s) for this review		Progress
Number of teachers/trainers/instructors trained in learner centred teaching, active learning approaches and capacitated on how to use gender-responsive teaching and learning materials and implement gender responsive curricula (disaggregated by gender)			Total: 445 / CF: 445 / • 40 (JFT) / • 75 (SCI) / • 200 (YCT) / • 100 (SS) / • 30 (TS)		Total: 585 (women: 36%) / CF: 585 / • 53 (JFT) / • 73 (SCI) / • 325 (YCT) / • 60 (SS) / • 74 (TS) / Met
Number of education and skilling personnel, mentors, employers and other relevant actors capacitated in gender-friendly workplaces and learning environments (disaggregated by gender and type of actor)			Total: 770 / CF: 770 / • 65 (JFT) / • 105 (SCI) / • N/A (YCT) / • 600 (SS) / • 0 (TS)		Total: 1,173 (women: 66%) / CF: 1,173 / • 79 (JFT) / • 313 (SCI) / • 155 (YCT) / • 626 (SS) / • 0 (TS) / Exceeded

Output activities and supporting narrative for the score.

- Save the Children (SCI) trained 73 instructors, including master craftsperson, and empowered 313 individuals through platforms like Young Women’s Clubs to advocate for gender equality and safe workplaces.
- JFT delivered Training of Trainer (ToT) sessions for 53 instructors from TVET institutes and private providers, trained 22 staff on PSEA, and conducted two inclusive workplace workshops for 57 HR professionals.
- YCT trained 325 TVET instructors, master craftsperson, and facilitators in gender-responsive pedagogy and quality assurance standardisation.
- Sightsavers trained 626 individuals, including Unilever Shakti instructors and staff from TotalEnergies and IHS Towers, on gender- and disability-inclusive workplace practices.
- TechnoServe trained 74 trainers in Kano and Lagos, enhancing their capacity to deliver quality training in formal education and TVET settings.

ON TRACK: 585 teachers, trainers, and instructors (target: 445) were equipped with gender-responsive and disability-inclusive pedagogical skills and tools. Additionally, 1,173 relevant stakeholders (target: 770) received training on fostering gender-friendly workplaces and inclusive learning environments, exceeding the set targets and reinforcing the project’s commitment to equitable and accessible education and employment pathways.

Output Title		Skills training and certification / Adolescent girls and young women build foundational, digital, STEM-related, job-specific (inc. vocational and entrepreneurial), and/or transferrable/21st century skills through formal or non-formal skilling, employment readiness and/or leadership programmes.
Output number:			2.1	Output Score:		P2E outputs: A++ / CF outputs: A+ / Overall: A+
Impact weighting (%):			35%	Weighting revised since last AR?		N/a
	Indicator(s)	Milestone(s) for this review			Progress
	Number of adolescent girls and young women (aged 13-24 years) enrolled in formal and non-informal skilling, employment readiness and/or leadership and empowerment programmes (disaggregated by age, type of skilling and % of those disabled)	Total: 4,269 / CF: / • 600 (JFT) / • 1,569 (SCI) / • 500 (YCT) / • 600 (SS) / • 1,000 (TS)			Total: 5,499 / CF: / • 735 (JFT) / • 1,806 (SCI) / • 1,058 (YCT) / • 854 (SS) / • 1,046 (TS) / Exceeded
	Number of adolescent girls and young women (aged 13-24 years) who are enrolled in a course on P2E (disaggregated by age)	Total: 22,000 / P2E: / - 22,000 (Bangladesh) / - N/A (India) / - N/A (Nigeria)			Total: 114,565 / P2E: / - 31,660 (Bangladesh) / - N/A (India) / - 82,905 (Nigeria) / Exceeded
	Number of female mentors, counsellors or role models supporting girls with gender-responsive career counselling, peer support, leadership development, STEM learning or coaching (disaggregated by gender and type of support)	Total: 155 / CF Target: / • 15 (JFT) / • 90 (SCI) / • NA (YCT) / • 50 (SS) / • 0 (TS)			Total: 255 / CF: 255 / • 18 (JFT) / • 137 (SCI) / • 8 (YCT) / • 92 (SS) / • 0 (TS) / Met

Output activities and supporting narrative for the score.

Challenge Fund

- Save the Children (SCI) enrolled 1,806 adolescent girls and young women through seven tailored pathways, including Mentor-Mentee, Referral, Career Guidance, Recognition of Prior Learning, Entrepreneurship Development, Outreach Centres, and a blended classroom/on-the-job training model.
- JFT enrolled 735 adolescent girls and young women in vocational training through two centres in Bandarban and Cox’s Bazar.
- YCT launched an All-Women Tech Hub, enrolling 1,058 participants—436 trained in-person on ICT skills like web and mobile app development, and 622 accessed flexible online learning.
- Sightsavers supported 854 adolescent girls and young women with disabilities: 350 through life-skills coaching, 250 in entrepreneurship training, and 254 via the Accenture Skills to Succeed programme.
- TechnoServe enabled 1,046 adolescent girls and young women to participate in entrepreneurship and employability training across Kano and Lagos.

P2E Platform
- In Bangladesh, 31,660 young women enrolled on the P2E platform, with 23,348 completing at least one course.
- In Nigeria, 82,905 young women registered, and 34,368 completed P2E courses during the reporting period.

ON TRACK: A total of 5,499 adolescent girls and young women (target: 4,269) enrolled in formal and informal skilling, employment readiness, and leadership programmes. This progress was supported by 255 female mentors, counsellors, and role models (target: 155), who provided gender-responsive career guidance, peer support, leadership development, STEM learning, and coaching—demonstrating strong momentum in empowering girls through inclusive and supportive learning environments.

Output Title	From learning to earning (community engagement and industry links) / Communities, family members and public and private sectors contribute to better access, support services and more inclusive transition to employment and entrepreneurship for adolescent girls and young women.
Output number:			2.2	Output Score:		P2E outputs: A+ / CF outputs: A / Overall: A
Impact weighting (%):			30%	Weighting revised since last AR?		N/a
Indicator(s)		Milestone(s) for this review			Progress
Number of partners (private sector, government or other) providing any of the young women: employment; entrepreneurship; employment transition services; or workplace readiness support (disaggregated by type of actor and type of support provision)		CF: 78 / • 12 (JFT) / • 35 (SCI) / • 31 (YCT) / • 0 (SS) / • 0 (TS) / P2E: 90 / 90 employers (Bangladesh)			CF: 123 / • 38 (JFT) / • 51 (SCI) / • 31 (YCT) / • 3 (SS) / • 0 (TS) / Met / P2E: 331 / 331 (Bangladesh) / Exceeded
Number (&%) of young women accessing any of the below: a) employment opportunities; internships, on-the-job work experiences, apprenticeships, job placements, other. b) entrepreneurship opportunities: incubation, business advisory services, mentorship, after-care services, other. c) employment transition services: job matching, career counselling, etc/ (disaggregated by age and type of support)		Total: 3,115 / CF: 2,615 / • 180 (JFT) / • 1,835 (SCI) / • 500 (YCT) / • 100 (SS) / • 0 (TS) / P2E: 500 / 500 job placements for women (Bangladesh)			Total: 3,542 / CF: 2,301 / • 221 (JFT) / • 1,474 (SCI) / • 436 (YCT) / • 170 (SS) / • 0 (TS) / Progress made but slightly short of target / P2E: 1,241 / 1,241 (Bangladesh) / Exceeded
Number of family members, guardians, community/local leaders reached with activities to promote change in negative gender norms and stereotypes and awareness raising regarding the benefits of skilling and work for women (disaggregated by gender and type of actor)		Total: 1,390 / CF: 474 / • 694 (JFT) / • 376 (SCI) / • 20 (YCT) / • 250 (SS) / • 50 (TS)			Total: 2,368 / CF: 2,368 / • 474 (JFT) / • 1,428 (SCI) / • 303 (YCT) / • 128 (SS) / • 35 (TS) / Met / Despite over-performance by SCI, there is further work required by JFT, SS, and TS.

Output activities and supporting narrative for the score.

Challenge Fund

- Save the Children (SCI) facilitated employment for 656 young women who completed skilling programmes.
- JFT supported 221 young women in accessing employment services—including mentorship, internships, and job placements—through collaboration with 38 employers in Cox’s Bazar and Bandarban.
- YCT connected 106 graduates to internships, supported 254 in launching businesses, and provided employment transition services to 76, with backing from 31 partners.
- Sightsavers enabled 170 young women with disabilities to start small businesses during the reporting period.

P2E Platform
In Bangladesh, through a partnership with Shomvob, 1,241 young women secured employment, supported by engagement with 331 private sector partners.

Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets. Make sure you highlight any significant challenges, issues or underperformance.

ON TRACK: During the reporting period, 454 public and private sector partners at country level (target: 168) were engaged in delivering support services to adolescent girls and young women (these private sector partners are distinct to GESP’s in-kind private sector partners. These services included employment assistance, entrepreneurship support, transition-to-work programs, and workplace readiness training. As a result, 3,542 adolescent girls and young women (target: 3,115) were able to access opportunities that support their journey from learning to earning.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

The Challenge Fund (CF) projects in Nigeria and Bangladesh faced significant challenges due to economic, infrastructural, and socio-political factors. In Nigeria, inflation and currency devaluation raised implementation costs, prompting UNICEF and partners to adopt cost-saving strategies and enhance risk management. Delays in finalising agreements, such as with Technoserve, disrupted project timelines, while security threats in Katsina State curtailed training activities. Infrastructure limitations, including unreliable electricity and internet, hindered digital literacy efforts, which were mitigated through partnerships with local authorities and telecom providers. In Bangladesh, cultural barriers and environmental disruptions like floods and political unrest delayed activities and limited access, especially for young women. UNICEF and partners responded by relocating training sessions, revising transportation allowances, and establishing mobile outreach to ensure continued participation.

Despite these challenges, the projects yielded valuable lessons and positive outcomes. Sightsavers improved outreach to young women with disabilities by engaging disability networks, while PwC and FCDO worked to strengthen communication with private and charity partners, although attendance and support issues persisted. Participants in training programs expressed empowerment and appreciation for the inclusive and engaging learning environments. These testimonials highlight the transformative impact of the initiatives, reinforcing the importance of adaptive strategies, community engagement, and cross-partner collaboration to overcome barriers and drive meaningful change.

FCDO will need to work collectively with all GESP partners to mitigate the impact of any reductions in overall resourcing for the programme once the FCDO’s resource allocation process has concluded, and in the context of overall ODA cuts.

## D: VALUE FOR MONEY

Key cost drivers and performance
As of May 2025, FCDO has contributed $4,258,337.86 to GESP. Of this, $3,203,689.41 (75%) has been spent through the country offices in Bangladesh and Nigeria, primarily supporting the implementation of the five Challenge Fund projects. A further $738,638.16 (17%) has been spent by the Programme Division on global coordination, programme development, and support functions including UNICEF’s standard 8% recovery cost. The remaining 8% of funds were committed but unspent at the time of GESP’s Annual Report submission (which covered the period 1st May 2024-30th April 2025).

VfM performance compared to the original VfM proposition in the business case
The original VfM proposition included limited quantitative benchmarks, but the programme now provides sufficient data to assess performance across the 5E framework:

Economy
UNICEF’s procurement systems and long-term agreements continue to support cost control. No cost overruns are reported, and the programme benefits from in-kind contributions from private sector partners, although the financial value of these has sometimes been limited. Financial donations focussed on financial support rather than ‘in-kind’ which have additional costs to administer, would likely have had greater positive impact on GESP. There has been significant benefit to the Challenge Fund projects from local in-kind support such as facilities and staff.
Efficiency
The programme is now delivering through both P2E and the Challenge Fund. In FCDO-funded countries, 57,716 adolescent girls and young women have completed Passport to Earning (P2E) courses—23,348 in Bangladesh and 34,368 in Nigeria. FCDO provided 31.7% of the funding in these regions, accounting for 18,296 beneficiaries reached.

Effectiveness
There is evidence of progress against key outcome indicators, including increased enrolment in skilling programmes and improved perceptions of employability among participants. However, quantified data is not provided on employment or income outcomes, which limits the ability to assess long-term effectiveness at this stage.

Equity
GESP maintains a strong focus on gender equality and inclusion. All reported beneficiaries are adolescent girls and young women, with disaggregation by age and disability status embedded in the monitoring framework. Community engagement activities are also underway to address harmful gender norms, though specific reach figures are currently unclear.

Cost-Effectiveness
The cost per P2E beneficiary in FCDO-funded countries is low, and the programme is leveraging digital platforms to reach scale. While cost-effectiveness of the Challenge Fund component cannot yet be fully assessed, forecasts predict strong cost-effectiveness.

Assessment of whether the programme continues to represent value for money

Overall, GESP is representing good value for money. The programme has moved beyond early-stage investment and is now delivering tangible results across multiple components. While some outcome-level data is still emerging, the scale of delivery, particularly through digital skilling, and the programme’s strong equity focus support a positive VfM assessment.

Challenge Fund
The Challenge Fund has now moved into full implementation, with $3.2 million disbursed across Bangladesh and Nigeria. As the Challenge Fund represents 75% of the total funding FCDO has committed, this is where we would like to see the greatest impact. While outcome data on employment or income is not yet available, the fund has supported a wide range of skilling and empowerment activities. The cost per beneficiary cannot yet be calculated, but the scale of investment and the diversity of interventions suggest that the Challenge Fund is on track to deliver value. Continued monitoring will be essential to assess its long-term impact and cost-effectiveness. Significant investment has been made thus far and should be continued in order to maximise return on this investment, particularly as GESP enters its final year of delivery.

Passport to Earning
Passport to Earning (P2E) remains a core component of GESP’s digital skilling strategy. It offers a low-cost, scalable platform for reaching adolescent girls and young women with foundational and employability skills. In FCDO-funded countries, 57,716 girls and young women have completed P2E courses—23,348 in Bangladesh and 34,368 in Nigeria. FCDO provided 31.7% of the funding in these regions, accounting for 18,296 beneficiaries reached. With an investment of $400,000, this translates to an estimated cost of $15 per beneficiary. The infrastructure is in place, suggesting that the cost-effectiveness of P2E will continue to improve as more learners are reached. Working with GenU should, along with the economies of scale, improve value by pooling donor contributions.

E: RISK

Overview of risk management
Over the past year, the GESP programme has operated within the FCDO’s corporate risk appetite, with residual risk levels remaining broadly stable across most categories. We are confident that the mitigation strategies we have devised ensure that programme risks can be effectively managed and will remain within FCDO’s risk appetite, these are regularly re-assessed. The programme has matured from early-stage implementation to active delivery which has marked a shift from design and setup risks to delivery and results-based risks. As implementation has scaled up, especially in Nigeria and Bangladesh, the focus has moved to ensuring quality, inclusion, and safeguarding in delivery. The programme has not reported any major incidents. No changes to the programme’s formal risk appetite are proposed at this stage.

Equality and Inclusion
There is no evidence that assumptions made in the original Equalities Impact Assessment have changed, but continued monitoring is needed to ensure that marginalised groups—including girls with disabilities—are not excluded from access to skilling and employment pathways.

Safeguarding and SEAH
Safeguarding remains a priority area. GESP operates in contexts where risks of sexual exploitation, abuse, and harassment (SEAH) are elevated. GenU/UNICEF have undertaken significant work to address these risks, Dedicated meetings have happened this year to explain GenU/UNICEF’s reporting process to FCDO staff and we are keen to see this effort continue given the direct impact it is having on the success of the programmes.

Climate and Environmental Risk
The programme’s digital-first approach and localised delivery models suggest a relatively low carbon footprint. However, no formal emissions assessment or shadow carbon pricing has been conducted. A basic environmental risk screening should be undertaken in the next year to confirm this assessment and identify any opportunities for climate co-benefits (e.g. green skills training).

Due Diligence and Partner Risk
UNICEF, as primary implementing partner, provide a high level of fiduciary assurance. A refresh of due diligence assessments for delivery partners may be warranted, particularly where there have been material changes in delivery arrangements or partner performance.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance Summary of partners and FCDO, notably on commercial and financial issues.

Top level GESP budgets have been received multiple times across the reporting period to account for iterations in the programme. Financial reporting is improving and has become more consistent and more accurate across the course of the annual review period. The FCDO doesn’t monitor programme level CF budgets and requires high-quality reporting from GenU to ensure that the funding is being utilised effectively and efficiently. FCDO continues to work with GENU to ensure accurate forecasting to avoid underspend.

Programme and risk management has improved. Communication to FCDO around timelines and emerging risks has been clear, with agile programme and risk management demonstrated in response to the changing context in Bangladesh. GenU/UNICEF have held sessions with FCDO to update on GenU/UNICEF risk management and approach to managing SEAH.

GenU have delivered a better performance compared to last year, with stronger engagement from FCDO in-country officers which was observed during FCDO country visits. Private sector partners have received more details of project outcomes in the form of virtual engagement events, to encourage engagement from private sector partners who haven’t responded to communications, and we now have a clearer picture of those partners who remain engaged.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
1. Field Visits and Stakeholder Engagement
- Joint Missions: FCDO and GenU conducted field visits to Nigeria (Nov 2024) and Bangladesh (Mar 2025).
- Community Engagement: Over 2,300 family and community members were reached through sensitisation events, promoting gender norm change and support for girls’ skilling.
2. Monitoring, Evaluation, Research, and Learning (MERL)
- MERL Strategy Operationalised: Each CF project implemented a tailored monitoring plan
- Learning Products: A learning brief and blog were published to share insights on digital skilling
- Tracer Study: Planning initiated for a tracer study to assess long-term impact of GESP.

Evidence
During the 2024–2025 review period, GESP made significant strides in strengthening its evidence base through enhanced monitoring, participatory research, and adaptive learning, including:
- Updated Logframe and KPIs: In November 2024, GESP revised its logframe to reflect more accurate targets and milestones, based on updated data.
- Learning Briefs and Blogs: Two knowledge products were published, focusing on digital skilling and course completion strategies, informing course design and delivery improvements.
2. Implications for Programming
- Target Adjustments: Based on improved data quality and disaggregation, targets for several indicators were increased (e.g., number of girls taught with gender-responsive curricula, number of mentors, and community engagement figures).
- Enhanced Inclusivity: Evidence from Sightsavers highlighted the need for more tailored approaches for girls with disabilities. This led to the development of disability-inclusive curricula and training manuals
- Community Engagement: Data showed that engaging male community members and family influencers is critical to shifting gender norms. This has led to expanded community outreach.
3. Quality and Breadth of Evidence
- Mixed Methods: GESP uses both quantitative (e.g., KPIs, tracer studies) and qualitative (e.g., testimonials, PAR) approaches, enhancing the robustness of its evidence.
- Real-Time Learning: The establishment of a Community of Practice and quarterly learning exchanges ensures that evidence is not only collected but actively used to inform decisions.

Learning
GESP has employed a range of structured learning processes to capture and share lessons:
Participatory Action Research and Evaluation (PARE):
1. Workshops in Bangladesh trained young women to conduct research and contribute to programme monitoring and advocacy.
2. Youth researchers developed and implemented research plans, contributing to programme learning
1. Learning Briefs and Blogs: Two learning briefs were published on digital skilling
2. Community of Practice: a platform was established to facilitate peer-learning sessions among partners.
3. GESP Advisory Board and Girls’ Advisory Panel (GAP):
1. The GAP brought youth voices into governance and learning.
2. The Advisory Board reviewed progress and shared strategic insights.
Monitoring, Evaluation, Research, and Learning (MERL) Strategy: A comprehensive MERL guidance document was developed to standardize learning and evidence generation across countries.

What are the key lessons identified over the past year for (i) this programme (ii) wider FCDO and development work?
(i) For This Programme (GESP):
- Digital skilling must be localised: Tailoring P2E content to local labour markets and learner needs increases relevance and uptake.
- Community engagement is essential: Involving families and male champions helps shift gender norms and sustain participation.
- Disability inclusion requires targeted strategies: Sightsavers’ work highlighted the need for tailored outreach, accessible materials, and inclusive pedagogy.
(ii) For Wider FCDO and Development Work:
- Shared-value partnerships work: Collaboration with private sector actors (e.g., Unilever, Accenture, Vodafone) enhances programme reach and sustainability.
- Flexibility is critical in fragile contexts: Political unrest and environmental shocks in Bangladesh required adaptive planning and rapid response.
Do you have any learning aims for the programme for the coming year?
1. Evaluate long-term impact through the GESP tracer study.
2. Strengthen the Community of Practice to foster cross-country learning and innovation.
3. Deepen understanding of what works in shifting gender norms through community engagement.

Date of last narrative financial report	31st March 2025	Date of last audited annual statement