## Annual Review Template

Title: Girls’ Education Skills Partnership (GESP)
Programme Value £ (full life): Up to £9m		Review date: 22 June 2026
Programme Code: [AMP ID#] 301437	AMP start date: 06/04/2022	AMP end date: 31/12/2026

Summary of Programme Performance
Year	2023	2024	2025	2026
Overall Output Score	B	B	A	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case and Summary (D0003320) 301437 (Published - July 2023)
DevTracker Link to results framework:	Logical Framework (D0005321) 301437 (Published - June 2024)

A. SUMMARY AND OVERVIEW
Description of programme
The Girls’ Education and Skills Partnership (GESP) programme (up to £9m, 2021-2026) aims to support adolescent girls and young women to transition from learning to earning by improving access to market-relevant skills and livelihood opportunities.

1. The primary component under the GESP programme is an £8m multi-country project implemented by UNICEF’s Generation Unlimited[1], that operates across Bangladesh, Nigeria, and India. The programme addresses both supply-side constraints (limited access to quality skills provision) and demand-side barriers (weak labour market linkages and gender norms). Delivery is structured around two initiatives:
  [1] Generation Unlimited (Gen U) is UNICEF’s global partnership platform for turning education into employment outcomes for young people—by aligning governments, donors, and the private sector at scale.
  1. The Challenge Fund (CF) supports targeted, in-country interventions to strengthen skills systems, improve training quality, and support transitions into employment and entrepreneurship.
  2. The Passport to Earning (P2E) provides a scalable digital platform offering flexible, market-relevant training, increasingly linked to job platforms and employer networks. This combined approach has enabled delivery at scale while testing models for system integration, although converting reach into sustained labour market outcomes remains a key challenge.

1. A smaller, complementary component is delivered through an Accountable Grant Agreement (up to £200,000) with the International Initiative for Impact Evaluation (3ie). This component supports FCDO to strengthen the global evidence base on what works in skills and learning to earning interventions, by mapping and assessing existing research across low and middle income countries. It aims to inform policy, programme design, and investment decisions, ensuring GESP and wider programmes are grounded in the best available evidence.
2. A unique part of GESP’s operating model is its emphasis on public–private partnerships, which bring together government, private sector actors[2], and civil society to strengthen pathways from skills development to employment. Partnerships have provided training content, mentoring, digital platforms, and employment opportunities.
  [2] Including Accenture, Cognizant, Coursera, Microsoft, Pearson, PwC, Standard Chartered Bank, Unilever, and Vodafone

Summary supporting narrative for the overall score in this review
The programme has demonstrated strong delivery performance over the reporting period, with most outputs on track or exceeding cumulative targets across both Challenge Fund and P2E components. It scores an A overall. A major achievement includes large scale reach of adolescent girls and young women through skills provision and digital platforms, with over 1.6 million enrolments on P2E and more than 66,000 girls reached through in-person training.

Progress has also been made in strengthening pathways from learning to earning. Early evidence of transitions is emerging, including job placements and transition support through P2E in Bangladesh, expanded mentoring networks (over 750 mentors), and increased engagement with employers. At the system level, there are positive signs of sustainability, including integration with national skills frameworks and scaling of programme approaches through government systems. However, while delivery at output level is strong, confidence in outcomes remains moderate due to limited evidence on sustained employment, income, and longer-term economic empowerment. More progress based on self-reported data and tracer findings is still emerging. The final year will therefore be critical to consolidate results, strengthen the evidence base, and demonstrate value for money.
Major lessons and recommendations for the year ahead
The programme closes in December 2026, so the recommendations are proportionate and focus on synthesising, distilling and disseminating lessons learned.
Output #	Lesson	Recommendation	Who / When
Cross cutting (Outcomes)	The lack of robust outcome-level evidence remains a key limitation. The programme has delivered at scale and exceeded many output targets. However, this reporting period reinforces that high activity levels (training, enrolment, outreach) do not automatically translate into sustained outcomes such as employment, income, or economic empowerment.	To prioritise completion and rapid synthesis of the tracer study and any available outcome data into a short evidence note focused on sustained transition outcomes. This should clearly set out what can be evidenced on employment, entrepreneurship, and longer-term change, and where evidence gaps remain.	Gen U Team, by December 2026
Cross cutting (ToC)	The programme model is strongest where interventions are integrated. The clearest lesson from delivery is that training alone is insufficient. Results appear strongest where skills provision is combined with mentoring, employer engagement, job placement support, and community sensitisation. However, this integrated learning to earning pathway is not yet consistently articulated across all components.	Produce a short end-of-programme synthesis on the GESP delivery model, identifying the core intervention package that appears most effective in supporting girls’ transitions from learning to earning. This should distil practical lessons across Challenge Fund and P2E components for future programme design.	Gen U Team, by December 2026
Cross cutting (VfM)	Private sector partnerships are a core strength, but their added value is not yet well evidenced. Private sector partnerships have clearly supported delivery through mentoring, training content, job placement pathways, and in-kind support. However, the programme does not yet systematically capture which partnerships delivered the greatest value, how they contributed to outcomes, or whether they improved value for money.	Produce a short learning brief on private sector partnerships, focusing on their contribution to programme reach, transition outcomes, and value for money. This should identify which partnership types were most useful and what lessons should inform future shared-value model.	Gen U Team, by December 2026
Cross cutting (Equity)	Reaching the most marginalised requires differentiated delivery models. GESP shows that different barriers require different adaptations: disability-inclusive coaching and employer engagement for young women with disabilities; childcare and safe learning spaces for young mothers; and mobile delivery, transport adjustments and community mobilisation for girls in remote or socially conservative areas. These adaptations are central to participation and progression, but require stronger local partnerships, more intensive delivery support and realistic budgeting from the outset.	Produce a short learning brief documenting the main adaptations used to reach marginalised girls and summarise the operational implications for future programming, including any additional delivery requirements or costs.	Gen U Team, by December 2026
Cross-cutting (evidence)	Generating policy-relevant evidence requires early and sustained engagement with stakeholders to ensure outputs are aligned to decision-making needs.	Ensure the 3ie evidence gap map is used as a strategic tool to engage and influence key actors (e.g. World Bank, CGD) to drive uptake in programme design and system-level decision-making.	FCDO Team, by October 2026
Cross-cutting (targets)	Indicator targets have not consistently reflected programme maturity. Across outputs and intermediate outcomes, the majority of indicators have been significantly exceeded, suggesting that some targets were set conservatively or not adjusted as implementation scaled. This limits the extent to which the logframe can meaningfully assess performance or distinguish between strong delivery and exceptional performance.	Undertake a light-touch review of the logframe for the remaining implementation period. This should confirm that remaining targets are appropriate for close-out, align with end-of-programme priorities (including evidence synthesis), and clarify expectations for final reporting and learning outputs.	FCDO and Gen U, by June 2026
Cross-cutting (learning and dissemination)	The programme has generated significant learning but this needs to be distilled and shared. With a substantial body of delivery experience and emerging evidence, the final phase presents a critical opportunity to consolidate lessons learned and ensure they are effectively captured and communicated.	Produce learning briefs (see output section) and develop a light-touch dissemination plan, informed by stakeholder mapping, to ensure findings reach priority audiences (including FCDO and wider sector actors) and support sustainability beyond the programme period.	Gen U (supported by FCDO), by December 2026

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The programme’s Theory of Change (ToC) is based on improving the quality and relevance of skills provision, alongside strengthening access and transition pathways, to support adolescent girls and young women to move from learning to earning. This is delivered through curriculum reform, capacity building, expanded access to skills programmes (including P2E), and stronger linkages to employment and entrepreneurship. Together, these address both supply-side constraints (quality of provision) and demand-side barriers (labour market access and social norms), with the aim of enabling sustainable livelihood outcomes.

No updates were made to the ToC during the reporting period. The past year has focused on accelerating implementation. This has led to improved alignment between activities and intended results. The programme has also demonstrated that its integrated learning to earning model linking skills, mentoring, and transition support is critical to achieving outcomes. This pathway is not yet, however, consistently evidenced across all components.

While the ToC remains valid and relevant, evidence to fully demonstrate the causal pathways is still developing. Outputs are being delivered at scale, but the link to sustained labour market outcomes is only partially evidenced, and reliant on self-reported indicators and limited longitudinal data. As the programme enters its final phase, the priority is to validate how improvements in provision translate into sustained employment, income, and empowerment outcomes drawing, on emerging tracer and programme evidence.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact Assessment

No	Impact	Indicator	Milestone	Progress
1	More employable, entrepreneurial, and better skilled adolescent girls and young women moving into employment, venture creation, or further education.	Percentage of targeted young women who report an improvement in their career trajectory (new job, promotion or raise, self-employment, or entering/staying in education (within 6 months of course completion) (disaggregated by type of career trajectory, age, and % with disabilities)	59%	Exceeded. 86%

At impact level, the programme shows positive but still emerging evidence of impact. A high proportion of targeted young women (86% against a target of 59%) report improvements in their career trajectory within six months of course completion. This includes movement into employment, self-employment, or continued education. This suggests the programme is successfully supporting initial transitions from learning to earning and that its integrated approach is beginning to deliver results. However, this evidence is primarily self-reported and short-term. There is limited data on the quality and sustainability of these outcomes, particularly in terms of stable employment, income gains, and longer-term economic empowerment. As a result, overall confidence remains moderate, and the extent to which these changes are sustained beyond the programme period is not yet clear.
Outcome Assessment[3]
[3] Cumulative targets are to be achieved by the programme end date – 31st December 2026

No	Outcome	Outcome Indicator	Milestone	Progress
1	Improved quality of skilling systems and training providers responsive to girl centred skills development and relevant to meeting the needs of industry	1.1 Number of students/trainees being taught by education and skilling personnel using gender responsive and teaching and learning materials and curricula (disaggregated by gender and age)	32,519 / Cumulative target: 60,920	Exceeded: 62,922 / Cumulative total: 68,976
		1.2 Number (& %) of teachers/trainers/instructors who report an increase in their knowledge and awareness of relevant market needs and gender-sensitive pedagogies and tools (disaggregated by gender)	87% / Cumulative target: 92%	Exceeded: 96% / Cumulative achievement: 92%
2	Increased equitable access to market-driven skills provision as well as employment and entrepreneurship opportunities for adolescent girls and young women	Number (& %) of targeted adolescent girls and young women who, at the end of the skilling programme, believe they are a) more likely to find employment, or b) more prepared to start an enterprise, or c) more likely to / go/stay in education	81% / Cumulative target: 97%	Exceeded: 97% / Cumulative total: 97%
		Number of adolescent girls and young women who complete course content on P2E	Target: 5700 / Cumulative target: 858,750	Exceeded: 28,553 / Cumulative Total: 949,259
		Number of employer policies and practices that are supportive of inclusive female employment as a result of GESP interventions.	Target: 205 / Cumulative target: 420	Exceeded: 272 / Cumulative Total: 323

Overall, performance at outcome level is positive. The programme is showing strong progress in expanding access to skills provision and improving the quality and relevance of training. Outcome indicators on participation, exposure to gender-responsive delivery, and perceived readiness are largely on track or exceeded. However, the evidence is stronger on access, reach, and self-reported progress than on sustained economic outcomes. While there are encouraging early signs that the programme is supporting girls’ transitions from learning to earning, confidence in the extent to which these changes will translate into lasting employment, income, and empowerment outcomes remains moderate. Key evidence such as tracer study findings is still emerging.

There has been good progress on Outcome 1, (62,922 learners reached and 96% of instructors reporting improved knowledge) with both indicators exceeding cumulative targets ahead of time and demonstrating substantial progress in improving the quality and relevance of skills provision. This reflects the programme’s ability to deliver at scale, including through partner-led expansion of training models. However, results are primarily measured through reach and self-reported improvements. There is limited evidence on whether these changes have translated into consistent improvements in teaching practice or learning outcomes. While there are early signs that gender-responsive approaches are being embedded within delivery systems, the extent to which these represent sustained system-level change beyond the programme period remains uncertain.

Progress under Outcome 2 indicators is strong on access and perceived readiness. It is, however, more mixed in demonstrating sustained transitions into employment and entrepreneurship. High levels of self-reported confidence (97%) and significant scale-up of P2E completion (over 28,000 in-year) suggest that participants are benefiting from integrated support, including training, mentoring, and transition services. However, these results are similarly based on short-term, self-reported outcomes, and evidence on sustained employment, income gains, or job quality remains limited. While initiatives such as job platform linkages in Bangladesh demonstrate promising models for strengthening school-to-work pathways, employer engagement results remain below cumulative expectations and provide limited insight into the depth or durability of changes in employer practices. As a result, while early signals are positive, overall confidence in sustained labour market outcomes remains moderate.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme should continue through to completion, as it is delivering strongly at output level and demonstrating credible pathways to impact. GESP has achieved significant scale and shows early evidence of improved career trajectories (86% vs 59% target). However, value for money and impact are not yet fully demonstrated due to limited evidence on sustained employment and income outcomes. With only six months remaining, continuation is justified to consolidate delivery, capture outcome evidence, and maximise the return on the existing investment.

## C. DETAILED OUTPUT SCORING

Output Title	Skills and development and training programmes have improved skills-driven curricula and teaching and learning content/materials (TLM) relevant and responsive to the needs of young women and the local labour markets
Output number:		1	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
1.1: Number of relevant public and private sector actors engaged in skills driven and gender responsive curriculum or TLM revision/development (disaggregated by type of actor)	Target: 20 / Cumulative target: 213	Milestone exceeded. 329 / Cumulative total: 555
1.2: Number of curricula and TLM (including P2E courses) developed/revised with a gender equality perspective to avoid perpetuating inequalities and biases (disaggregated by subject / type of skilling provision)	Target: 16 / Cumulative target: 63	Milestone exceeded: 22 / Cumulative target: 72

This output assesses whether the programme has improved the quality and relevance of skills training by aligning curricula and teaching materials with labour market needs and the needs of young women. Performance is strong, scoring an A, with both indicators exceeding targets and demonstrating substantial progress at scale. However, across the output, there is limited evidence on the quality, uptake, and consistent use of revised curricula in practice. The extent to which these improvements are contributing to better learning outcomes and labour market transitions is not yet clear.

Indicator 1.1 has significantly exceeded both annual and cumulative targets, largely driven by the programme’s partnership-based delivery model and aggregation across multiple partners and countries. A substantial share of results is driven by Sightsavers, which engaged a wide range of stakeholders through consultation and validation processes. In practice, the indicator captured a wide range of participation, rather than only direct contribution to curriculum reform. Combined with a relatively low initial target and faster delivery as the programme progressed, this helps explain the high result.

Indicator 1.2 has marginally exceeded targets for this reporting year. Challenge Fund delivery has focused on context-specific adaptations, embedding gender-responsive elements such as life skills, safeguarding, and inclusive approaches into training provision, while aligning content to local labour market needs. This includes, for example, SCI’s development of modules on employability skills, digital skills and AI-powered career guidance. P2E has been a key driver of scale, producing a large volume of modular courses across digital, entrepreneurial, and employability domains, with gender considerations integrated into design. Together, these approaches demonstrate consistency with the programme’s theory of change and a clear emphasis on improving both relevance and inclusivity.
Case study: Jaago Foundation Trust (JFT) Skills on Wheels gender-responsive curriculum for hard-to-reach girls in Bangladesh. JFT developed seven gender-responsive curricula and teaching and learning materials (TLMs), including six modules for its mobile Skills on Wheels model, to reach girls in remote areas where mobility, safety and social norms limit access to fixed centres. The curriculum process engaged 41 public and private sector actors and applied a gender-inclusive lens to address barriers faced by girls. Through mobile delivery, the model has expanded access to skills training for previously excluded groups and supported early livelihood gains, while also helping to increase community acceptance of girls’ participation. It demonstrates how tailored curriculum design and flexible delivery can improve inclusivity, though evidence on the sustainability of income gains remains limited.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no material changes during the reporting period, and given the programme is entering its final six months, no further design changes are proposed.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned
Broad stakeholder engagement and partnership-based delivery can scale curriculum reform, but the key challenge is evidencing what leads to adoption in practice. The programme has successfully integrated gender-responsive approaches into curricula and TLMs, supporting more inclusive and labour market-relevant skills provision. However, there is limited evidence on whether reforms have contributed to improved learning or employment outcomes.
Recommendations[4]
[4] No recommendations were made at output level last year. Given the programme has only six months of implementation, new recommendations are limited to focusing on disseminating and sharing lessons learned,
Consolidate and document the curriculum model, focusing on which elements of stakeholder engagement and curriculum reform led to adoption in practice, to inform future programming and scale-up.
Output Title	Teachers/trainers/instructors, and relevant actors have increased capacity to ensure gender-friendly work and learning environments and/or apply responsive pedagogies and tools to equip adolescent girls and young women with market-relevant skills
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
2.1 Number of teachers/trainers/instructors trained in learner centred teaching, active learning approaches and capacitated on how to use gender-responsive teaching and learning materials and implement gender responsive curricula (disaggregated by gender)	Target: 832 / Cumulative target: 5592	Milestone exceeded: 1822 / Cumulative total exceeded: 6578
2.2 Number of education and skilling personnel, mentors, employers and other relevant actors capacitated in gender-friendly workplaces and learning environments (disaggregated by gender and type of actor)	Target: 585 / Cumulative target: 3810	Milestone exceeded: 2084 / Cumulative total exceeded: 4736

This output assesses whether the programme has strengthened the capacity of trainers and wider stakeholders to deliver gender-responsive, learner-centred skills training and support more inclusive learning and work environments for young women. A teacher in Bangladesh remarked “The Micro Skills School Package training brought a significant change in my teaching approach. Previously, it was difficult to keep students engaged, but now they participate with enthusiasm”.

Performance is strong, with both indicators exceeding cumulative targets and the output scoring an A, reflecting the programme’s ability to scale delivery through Challenge Fund partners across trainers, employers, mentors and other actors. However, evidence remains stronger on participation than on whether this capacity building has led to sustained changes in teaching practice, workplace conditions, or improved learning and labour market outcomes.

Indicator 2.1 has reached 1,822 teachers/trainers against a target of 832. This reflects the use of cascade training models and partner-led delivery, enabling rapid expansion across multiple geographies. Training has been embedded within implementation and has focused on learner-centred pedagogy, active learning, and gender-responsive practices, including inclusive facilitation, safeguarding, and life skills. This includes large-scale delivery by partners such as TechnoServe (over 780 trainers trained) alongside system-linked initiatives such as training 380 teachers to implement the Micro Skills School Package in Bangladesh. However, while scale is clear, the indicator provides limited insight into training quality or whether improved teaching approaches have been consistently applied in practice.

Indicator 2.2 has been significantly overachieved, reflecting strong delivery across a broad ecosystem beyond trainers. This is driven by the programme’s partnership model, with Challenge Fund partners embedding gender sensitisation across employers, mentors, and service providers to promote more inclusive learning and workplace environments. However, as above, this indicator captures participation but provides only limited evidence on whether actors have implemented sustained improvements in workplace practices or expanded opportunities for young women, leaving its contribution to labour market outcomes only partially evidenced.

Case Study on Sightsavers - strengthening capacity for inclusive skills delivery Sightsavers has played a key role in building capacity for gender and disability-inclusive training, contributing to a large share of results under this indicator (over 2,000 actors reached cumulatively). It has trained a wide range of actors, including instructors, administrators, and partner organisations on inclusive teaching practices, safeguarding, and workplace accessibility, with a focus on supporting young women with disabilities. This approach has gone beyond individual training to influence systems, for example through the development of an inclusive vocational instructor guide and engagement with a broad ecosystem of stakeholders. As a result, institutions are better equipped to create more inclusive learning and workplace environments. While performance is strong in terms of scale, evidence on how these capacity gains translate into sustained employment outcomes remains limited, consistent with wider programme findings.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no material changes during the reporting period, and given the programme is entering its final six months, no further design changes are proposed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned
Partner-led capacity building can reach large numbers quickly, but stronger evidence is needed on whether training changes practice. The programme has successfully embedded gender-responsive and learner-centred approaches across both training and wider labour market engagement. However, monitoring remains focused on participation rather than application, with limited evidence on whether capacity gains have translated into sustained changes in teaching practice or workplace environments.
Recommendation:
Produce a small number of focused case studies showing how training has changed teaching practice or workplace environments in practice, to address the evidence gap between participation and application.

Output Title	Adolescent girls and young women build foundational, digital, STEM-related, job-specific (inc. vocational and entrepreneurial), and/or transferrable/21st century skills through formal or non-formal skilling, employment readiness and/or leadership programmes.
Output number:		3	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
3.1. Number of adolescent girls and young women (aged 13-24 years) enrolled in formal and non-informal skilling, employment readiness and/or leadership and empowerment programmes (disaggregated by age, type of skilling and % of individuals with disabilities)	Target: 42,228 / Cumulative target: 76,620	Milestone exceeded: 60,604 / Cumulative total: 66,103
3.2 Number of adolescent girls and young women (aged 13-24 years) who are enrolled in a course on P2E (disaggregated by age)	Target: 6000 / Cumulative target: 1,390,000	Milestone exceeded. 35,356 / Cumulative total exceeded: 1,624,194
3.3 Number of female mentors, counsellors or role models supporting girls with gender-responsive career counselling, peer support, leadership development, STEM learning or coaching (disaggregated by gender and type of support)	Target: 614 / Cumulative Target: 2435	Milestone exceeded: 757 / Cumulative total moderately exceeded: 2481

This output assesses whether the programme is reaching adolescent girls and young women with market-relevant skills training, alongside mentoring and other support to strengthen readiness for employment or entrepreneurship. Performance is strong, scoring an A, with accelerated delivery across both in-person and digital models and most indicators on track or exceeding targets. Training spans a wide range of sectors aligned to labour market demand, reflecting a diverse and adaptive delivery model. However, performance remains strongest on enrolment and reach, with more limited evidence on learning quality.

Indicator 3.1 has performed well during the reporting period with plans in place to reach the cumulative target by programme end date. Enrolment levels indicate strong demand and accelerated delivery across partners. As an input-level indicator, however, it provides limited insight into progression, completion, or transition into employment and livelihoods. Some evidence of inclusion is available, including 1,962 girls and young women with disabilities reached and differentiation between in-school (11,830) and not in education, employment and training (NEET)/out-of-school young women (2,454). However, this is not consistently disaggregated across the portfolio, limiting the ability to assess whether enrolment gains are systematically reaching the most marginalised.
Case study: SAYWEE (TechnoServe, Nigeria) – scaling enrolment into market-relevant training and entrepreneurship pathways. The SAYWEE project has been a major driver of enrolment. reaching over 37,000 adolescent girls and young women during the reporting period through structured training in entrepreneurship, employability, and sector-specific skills. Delivery combined outreach through schools, technical and vocational education and training (TVET) institutions, and community networks with targeted mobilisation of out-of-school young women, contributing to rapid scale. Training content focused on practical, demand-led skills (e.g. small business development, financial literacy, and job readiness), supported by 135 female mentors providing guidance and career coaching. A distinguishing feature is the programme’s emphasis on early linkage to income-generating opportunities, including internships and business start-up support, enabling participants to apply skills quickly. For example, participants developed micro-enterprises in areas such as retail, with some reinvesting profits to expand their businesses. This case highlights how large-scale enrolment can be achieved where outreach, flexible delivery, and labour market-aligned training are combined.

Indicator 3.2 has been significantly exceeded, driven by the scalability of the P2E digital platform. Large numbers of young women have enrolled in courses across a range of domains, including digital, entrepreneurial, and employability skills, with localisation and flexible access supporting uptake across contexts. This reflects strong demand for digital learning opportunities and the programme’s ability to deliver at scale without proportional increases in cost. However, as with other digital platforms, enrolment does not equate to completion or outcomes, and there is limited evidence on course completion rates, learning gains, or transitions into employment.

Indicator 3.3 has marginally exceeded its cumulative target and championed a growing network of female mentors and counsellors supporting programme participants. Mentorship and peer support have been a key feature of programme delivery, contributing to improved engagement, confidence, and retention, particularly for marginalised girls. These support systems help bridge the gap between training and employment by providing guidance, role modelling, and practical advice. However, while the number of mentors has increased, there is limited systematic evidence on the quality, intensity, or effectiveness of mentoring relationships, and how these translate into improved outcomes for participants.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no material changes during the reporting period, and given the programme is entering its final six months, no further design changes are proposed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons Learned
Blended delivery models can expand access rapidly, but enrolment alone is not enough. The programme has successfully combined in-person delivery with P2E to reach large numbers of girls, demonstrating strong demand. However, high enrolment does not automatically translate into completion or progression.

Progression depends on linking training to mentoring, employer engagement, and follow-up support. The model is most effective where girls are supported through the full pathway from skills acquisition to employment or entrepreneurship, rather than training being delivered as a standalone activity.

Mentorship and support systems are important enablers of retention and confidence. They help girls overcome barriers to participation and progression, particularly those who are more marginalised, but evidence on the intensity and effect of this support remains limited.
Recommendations
Prioritise close-out evidence on completion, progression, mentoring and transition outcomes. Capture a small number of clear examples, alongside available data, to demonstrate not only reach but whether girls moved through the full pathway from enrolment to livelihoods.
Output Title	Communities, family members and public and private sectors contribute to better access, support services and more inclusive transition to employment and entrepreneurship for adolescent girls and young women.
Output number:		4	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
4.1 Number of partners (private sector, government or other) providing any of the young women: employment; entrepreneurship; employment transition services; or workplace readiness support (disaggregated by type of actor and type of support provision)	Target: 226 / Cumulative target: 735	Milestone exceeded: 860 / Cumulative total exceeded: 1314
4.2 Number (& %) of young women accessing any of the below: a) employment opportunities; internships, on-the-job work experiences, apprenticeships, job placements, other. b) entrepreneurship opportunities: incubation, business advisory services, mentorship, after-care services, other. c) employment transition services: job matching, career counselling (disaggregated by age and type of support)	Target: 11,905 / Cumulative target: 24,571	Milestone exceeded: 17,367 / Cumulative total: 20,727
4.3 Number of family members, guardians, community/local leaders reached with activities to promote change in negative gender norms and stereotypes and awareness raising regarding the benefits of skilling and work for women (disaggregated by gender and type of actor)	Target: 13,004 / Cumulative target: 32,115	Milestone exceeded: 85,644 / Cumulative target exceeded: 88,012
4.4. Number of evidence products produced that strengthen the evidence base on effective, scalable and cost-efficient skills and TVET interventions.	Target: Deliver planned evidence products (including Evidence Gap Map, Report and Presentation	Milestone met

This output assesses whether the programme is improving the wider enabling environment for girls. This is achieved by engaging families, communities, employers, and partners to expand access to opportunities, support services, and more inclusive pathways into employment and entrepreneurship. Performance is strong, scoring an A, with indicators meeting or exceeding targets and particularly strong results on partnerships and community engagement. The output also reflects effective use of public–private partnerships to strengthen transition pathways and support sustainability. However, evidence remains stronger on reach and activity than on the quality and durability of employment outcomes, with continued reliance on proxy indicators.

Indicator 4.1 has significantly exceeded both annual and cumulative targets. This reflects the programme’s success in mobilising a broad ecosystem of private sector actors, government institutions, and service providers to support transitions into employment and entrepreneurship. For example, partners in Bangladesh have strengthened employer engagement through job matching and structured follow-up, increasing demand for trained participants, while collaboration with corporate partners has enabled internships and placement opportunities. However, while the number of partners is a clear strength, the indicator primarily measures breadth of engagement rather than depth or effectiveness, with limited evidence on the quality of partnerships or their direct contribution to sustained employment outcomes.

Indicator 4.2 has performed well during the reporting period with plans in place to reach the cumulative total by programme end. The programme has supported large numbers of young women to access employment opportunities, entrepreneurship support, and transition services, including job matching, business advisory support, and mentoring. In Bangladesh, partners reported a shift toward actively managing transition pathways, resulting in improved placement outcomes and stronger employer engagement. Several private sector partners proactively returned to request additional cohorts of young women for future recruitment cycles, signalling satisfaction with previous hires and growing demand for female talent.

However, overall progress reflects the challenges of translating skills into livelihoods, particularly in constrained labour market contexts. While access to services has improved significantly, evidence on the quality and sustainability of outcomes is still limited, including job retention, income generation, and business success, which constrains assessment of impact.

Case study: Private sector partnerships linking digital skills to employment (Bangladesh). In Bangladesh, GESP has demonstrated how private sector partnerships can strengthen pathways from learning to earning through integration of the Passport to Earning (P2E) platform with the Shomvob[5] job-matching system. During the reporting period, this partnership engaged over 438 private and public sector actors and supported 1,205 job placements across sectors including sales, customer service, and entry-level digital roles. The model provides end-to-end support, from course enrolment and completion through to job matching and employer engagement, helping address a key gap in digital learning programmes. This demonstrates how combining digital skills provision with active labour market intermediation can translate high participation into tangible employment outcomes.
[5] Shomvob is a digital job-matching platform that connects trained young people to employment opportunities by managing candidate profiles, matching them to vacancies, and facilitating employer engagement and placements

Indicator 4.3 has significantly exceeded targets, with over 88,000 community members and stakeholders reached cumulatively, driven by a major scale-up in outreach as delivery matured. Partners in Bangladesh, particularly Jaago Foundation Trust (JFT), expanded campaigns, social media and local events. SCI and TechnoServe also increased community dialogues on barriers such as early marriage, unpaid care and women’s economic participation. However, the sharp increase appears to reflect intensified delivery and a broader definition of reach, rather than a fundamental shift in programme design. The indicator therefore measures exposure to norm-change activities more than demonstrated shifts in attitudes or behaviour, and evidence of sustained norm change, or labour market effects remains limited.

Indicator 4.4 has met its target through delivery of the 3ie Evidence Gap Map and related outputs, which strengthen the evidence base on skills and TVET and expose important gaps, particularly on labour market outcomes. The work exceeded initial expectations in scope and was shaped by advisory group input to improve policy relevance. While there are early signs of interest amongst stakeholders such as the World Bank and the Center for Global Development (CGD), the indicator measures production rather than uptake. Its contribution to policy or programming is therefore still unproven, making dissemination and use the main priority for the final phase of the programme.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 4.4 was added to the logframe during the reporting period to reflect the Accountable Grant Agreement with 3ie.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons Learned
Transitions to work depend on a wider enabling environment, not training alone. Strong engagement with employers, government, service providers, families, and communities has expanded access to opportunities and support for young women, demonstrating the value of a whole-system approach.

Community engagement is important for participation and progression, but current evidence is stronger on reach than norm change. Large-scale outreach appears to have improved support for girls’ participation, yet results are primarily measured through exposure rather than sustained shifts in attitudes or behaviour.

Evidence on the quality and sustainability of transition outcomes remains limited. While access to services and opportunities has increased, there is still limited evidence on whether partnerships and outreach are translating into durable improvements in jobs, income, and entrepreneurship outcomes.
Recommendation
Focus final reporting on demonstrating how partnerships, transition services, and community outreach contributed to concrete changes for girls. Prioritise a small number of clear examples and available data so evidence goes beyond counts of actors reached to show actual transition outcomes.
D: VALUE FOR MONEY

Key cost drivers and performance, VfM performance compared to the original VfM proposition in the business case

Economy. Key cost drivers include delivery (curriculum, mentoring, job placement), staffing, and digital platforms. Costs are actively managed through established UN/UNICEF financial controls (e.g. Harmonized Approach to Cash Transfers [HACT], competitive procurement, and partnership agreements), and mitigation strategies in response to external pressures such as inflation and fuel costs (e.g. use of existing government facilities). However, the assessment remains largely narrative, with no benchmarking of unit costs against market rates. Private sector contributions are also not consistently monetised, limiting visibility on cost offsets. We recommend developing a short learning brief on private sector partnerships to systematically assess their contribution. This would strengthen the VfM case and help inform future programme design.

Efficiency. The programme shows strong evidence of delivering outputs at scale and frequently exceeding logframe targets (e.g. substantial overachievement across most output and intermediate outcome indicators). Efficiency gains are further supported by a delivery model that integrates digital platforms (P2E), partnerships, and government systems, enabling high reach without proportional increases in delivery infrastructure. The use of public-private partnerships has also expanded outputs (e.g. training, mentoring, placements) without equivalent increases in programme spend, indicating strong leveraging effects. However, these claims are not supported by clear efficiency metrics (e.g. cost per beneficiary, cost per training completion), nor is there analysis of whether rapid scale-up has affected quality or sustainability of delivery. As such, while output delivery is strong, the absence of unit cost analysis constrains a rigorous assessment of whether efficiency has improved over time or relative to alternatives.

Cost effectiveness. There is emerging evidence that programme investments are contributing to intended outcomes, particularly in terms of skills acquisition, participation, and initial transitions into employment or entrepreneurship (e.g. job placements via P2E, high levels of reported transition readiness). Emerging benchmarking data from Bangladesh are helping strengthen the VfM case. The Alternative Learning Pathway (ALP) programme typically costs $380–400 per learner, compared with under $100 for GESP skills training, while achieving similar employment transition outcomes. This suggests GESP may be delivering comparable results at lower cost by leveraging existing systems, partnerships and tailored delivery. However, robust cost effectiveness cannot yet be demonstrated. Outcome measurement relies heavily on self-reported indicators (e.g. perceived readiness, confidence), with limited data on sustained employment, income gains, or long-term economic outcomes. The tracer study is expected to strengthen this evidence base and will be reported on in the Project Completion Review (PCR).

Equity. The programme demonstrates a strong and credible commitment to equity, with VfM explicitly incorporating a focus on reaching marginalised adolescent girls and young women. This includes targeted interventions for girls with disabilities (e.g. Sightsavers), delivery models for hard-to-reach populations (e.g. Skills on Wheels), and large-scale engagement with communities to address social norms barriers. The scale of outreach (e.g. community engagement and targeted inclusion approaches) suggests that resources are being directed towards those furthest behind. Data disaggregation is also present in parts of the results framework.
Assessment of whether the programme continues to represent value for money

Overall, the programme represents moderate VfM, with strong performance on delivery and clear evidence of leveraging partnerships, systems, and digital platforms to achieve scale. The integrated learning to earning model and emphasis on equity suggest resources are being directed towards high-priority outcomes and underserved groups. However, the VfM case is only partially demonstrated. The assessment is constrained by a lack of quantitative cost metrics and limited robust evidence on sustained employment and income outcomes. Strengthening outcome evidence and linking this to costs particularly through the tracer study will be critical to demonstrating whether scale translates into durable value.
E: RISK

Overview of risk management
The overall risk rating for the programme remains moderate, reflecting strong delivery performance but ongoing risks associated with the final phase of implementation and the ambition to translate outputs into sustained outcomes. Risk management is embedded within programme governance arrangements, with regular monitoring by UNICEF and FCDO, including oversight of delivery, financial performance, safeguarding, and partner capacity. As the programme draws to a close, risk management will focus on demonstrating robust outcome-level results and sustain pathways from learning to earning and ensuring effective close-out, including sustainability and institutionalisation of programme approaches.

Strategy and Context Risks: Moderate to Major. Programme delivery in Nigeria and Bangladesh is exposed to fragile and changing operating environments. These include economic volatility (inflation, currency fluctuations), political transition, and access constraints These factors have the potential to disrupt delivery and increase costs. Mitigation measures include adaptive delivery approaches (e.g. mobile training, digital platforms) and close engagement with country partners to maintain implementation continuity. An underlying strategic risk in the GESP portfolio is that there is very limited high-quality synthesis of this evidence of skills and TVET interventions. This is limiting the sector’s ability to draw clear conclusions on what works. Mitigation measures include the 3ie evidence gap map (see Section G for more details), funding the GESP longitudinal studies, and FCDO’s role in convening stakeholders (World Bank, CDG) to build partnership and consensus on this work.

Policy and Programme Delivery Risks: Moderate. While output delivery remains strong, there is a risk around translating high levels of activity into sustained outcomes, particularly employment and income gains for beneficiaries. Outcome-level evidence remains limited, and there is a risk that rapid scale-up may compromise quality or sustainability of interventions. Mitigation measures include strengthening labour market linkages, continued partner performance management, and ongoing investment in tracer studies and evaluation to better evidence results.

Financial and fiduciary: Moderate. Financial and fiduciary risks remain moderate, reflecting the complexity of multi-partner delivery and reliance on in-kind contributions. Risks include challenges in forecasting under changing external conditions, and difficulties in consistently valuing and aligning in-kind contributions with programme objectives. Cost pressures, particularly inflation and currency depreciation, have affected delivery planning. Risks are mitigated through UNICEF financial controls, oversight, though transparency and alignment of in-kind contributions remain areas for improvement, and future lessons learned on the impact of public-private sector agreements.

People Risk: Moderate. As the programme closes alongside the FCDO2030 restructure there is a risk around capacity challenges during the final phase of the programme. Risks include reduced institutional memory and delivery continuity; and potential gaps in FCDO capacity over the next six months. Mitigation measures include active succession planning and knowledge transfer; close monitoring of delivery partner staffing against critical milestones; and ongoing FCDO engagement to maintain sufficient oversight capacity.

Safeguarding Risks: Moderate. The programme engages vulnerable populations, including adolescent girls and young women, some of whom face heightened risks of gender-based violence, exclusion, and exploitation. Safeguarding systems are in place, including prevention of sexual exploitation and abuse (PSEA) policies, safeguarding training including for downstream partners, and established reporting mechanisms.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Over this review period partners have remained focused on project delivery despite the uncertainty of future funding from FCDO as a result of the reduction in UK ODA to 0.3% GNI. Partners have demonstrated resilience and pragmatism through re-profiling budgets and adjusting delivery plans.
MoU with UNICEF
Generation Unlimited have delivered timely bi-annual reports during the reporting period, supplemented by monthly programme management meetings covering delivery, risks, safeguarding, finance, and contractual issues. Delivery against output remains strong, however, as highlighted in Sections B and D, more evidence is needed against achieving programme outcomes. Generation Unlimited co-ordinate delivery across multiple partners and countries. Co-ordination at the country level has been strengthened during the reporting period through regular programme review meetings and Community of Practice sessions.

Financial management and forecasting. Financial oversight is conducted by monitoring expenditure and assessing downstream partner financial reports through UNICEF systems. Pre-payments are made to UNICEF in line with FCDO’s operating requirements. Of FCDO’s £8 million contribution (approximately $9.7 million), 92% of funds received had been committed or spent, indicating strong budget utilisation and limited risk of underspend in the final phase. Partners have demonstrated flexibility in financial management to respond to contextual risks.

Commercial considerations. The commercial model remains a strength, with private sector partners contributing expertise, content, mentoring and employment pathways that expand reach without equivalent increases in spend, particularly through P2E. However, these in-kind contributions are not consistently quantified, and their additionality and impact are not yet well evidenced.

Accountable Grant with 3ie: Payments are made in arrears against verified expenditure, in line with FCDO grant requirements. A short time extension was given to 3ie until June 2026 to enable completion of outputs. Reporting is proportionate with performance assessed on delivery and quality of final evidence products.

FCDO management and oversight. FCDO has maintained active engagement through programme oversight, participation in governance structures, and collaboration with UNICEF and partners (including advisory board engagement and joint planning processes). As the programme enters its final phase, FCDO management will focus on strengthening outcome-level evidence, and supporting effective programme close-out and sustainability planning.

G: MONITORING, EVIDENCE AND LEARNING

### Monitoring
Monitoring processes are well established under the GESP programme, with downstream partners reporting against aligned results frameworks, supported by UNICEF oversight and regular reporting processes. Monitoring draws on a mix of quantitative and qualitative data, including routine data collection, partner reporting and monitoring visits.

This Annual Review used a blended approach, combining desk review of core documents with interviews with in-country project leads, government counterparts, and Generation Unlimited HQ staff. These pointed to strong progress in linking skills delivery to employment and system-level change. In Bangladesh, for example, delivery has shifted towards active management of transition pathways, including job matching and employer engagement. Innovative models such as Skills on Wheels have expanded access for marginalised girls’; while mentoring and community engagement have supported participation. Challenges remain around sustaining participation, managing expectations on income generation, and supporting progression to higher-level skills. Overall, findings suggest strong output-level delivery, improving transition pathways, and growing sustainability potential.

FCDO’s Higher Education Adviser in Nigeria undertook a monitoring visit to delivery sites in Lagos, including Yaba College of Technology and Sightsavers implemented activities, alongside UNICEF colleagues. The visit enabled direct engagement with partners and beneficiaries and observation of delivery in practice. At Yaba College of Technology, facilities were of a high standard and participants demonstrated strong engagement, including through ‘hackathon’ presentations that showed clear links between skills development and emerging employment pathways. Participants presented with confidence and technical ability, suggesting good training quality, although examples observed were limited to competition winners and may not be representative of the wider cohort.

At Sightsavers supported activities, delivery showed strengths in reaching marginalised young women and building partnerships with government and private sector actors. Beneficiaries demonstrated familiarity with training content and entrepreneurial activities, indicating progress in skills acquisition. However, there was less clear evidence of translation into improved business performance or sustainable livelihoods, with income generation appearing limited in many cases. This highlights the need to strengthen pathways from training to earning, including deeper engagement with employers, markets, and financial institutions.

Overall, the visit reinforces wider programme findings: strong output-level delivery and engagement, but more limited and uneven evidence of sustained outcomes, particularly in relation to employment and income. Strengthening transition pathways and evidencing longer-term outcomes will be critical in the final phase.

Evidence
FCDO is investing in strengthening the evidence base through the programme. Early findings from the 3ie evidence gap map show a large and growing body of impact evaluations on skills and TVET (over 500 studies), but a lack of high-quality synthesis limits clear conclusions on what works. Evidence remains concentrated on direct training and labour market outcomes, with less coverage of system-level reforms and emerging areas such as green skills.

This work complements key evidence streams under the Generation Unlimited component by strengthening understanding of how gendered barriers shape girls’ transitions from learning to earning. These include the tracer study (tracking longer-term outcomes), youth-led research (e.g. Youth Participatory Action Research and Evaluation [YPARE]), and Communities of Practice and learning briefs that capture delivery insights. Together, they enhance programme learning, although further synthesis will be needed to translate this evidence into practical guidance for policy and investment.

Learning
As the programme enters its final months, the priority is to distil, synthesise and disseminate learning so that evidence on what worked, for whom, and under what conditions can inform future policy and programming. Emerging lessons include:
1. Strong output delivery does not yet equate to demonstrated impact. The programme has delivered at scale, but high levels of activity do not yet translate into robust evidence of sustained employment, income, or economic empowerment outcomes. This will be unpacked further in the PCR.
2. Integrated learning to earning approaches are most effective. Results are strongest where skills training is combined with mentoring, employer engagement, and transition support, highlighting the importance of full pathway approaches.
3. Private sector partnerships are critical but under-evidenced. Partnerships play a key role in enabling transitions into work, but their contribution to outcomes and value for money is not yet systematically captured.
4. Addressing social norms is essential for outcomes. Community engagement is critical to enabling participation and transition to employment, particularly for the most marginalised girls.
5. Digital delivery enables scale but requires complementary support. Platforms such as P2E have driven reach, but outcomes depend on combining digital learning with mentoring and labour market linkages.
6. Learning needs to be actively distilled and shared in the final phase. The programme has generated substantial implementation experience and emerging evidence, but this now needs to be synthesised into a small number of clear, high-quality outputs and shared with priority audiences to maximise uptake and sustainability beyond programme close.

Date of last narrative financial report	23rd May 2026	Date of last audited annual statement	23rd July 2025