Programme Completion Review

Title: Catalytic Climate Action in Iraq – Nationally Determined Contributions, Energy, Water and Drought Management
Final Programme Spend £ (full life): £3,909,746.40	Review Date:	29 June 2025
Programme Code: 301442	Start Date: 16/01/2022	End Date: 29 June 2025

Summary of Programme Performance

Year	Year 1	Year 2	Year 3 (15 months due three months of No-Cost-Extension)
Programme Score	97.5 (A)	100 (A)	105 (A)
Residual Risk Exposure Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/D0001023.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0001022.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

Iraq is one of the most vulnerable countries in the world to climate change. This includes its effects on the country and the economic risks to its hydrocarbon-dependent economy from the global transition towards clean energy. The three-year programme, with a £5m resource envelope, aimed to accelerate climate resilient and low carbon development in Iraq. It worked with the Government of Iraq (GoI), across the multilateral system and with international partners to promote transformational, long-term change in line with International Climate Finance Key Performance Indicator 15. It built the capacity of the Government of Iraq to mitigate and adapt to climate change with support for energy sector transition, fiscal sustainability, water governance and drought management.

Specifically, it was expected to support the GoI to:
1. Diversify the energy sector from fossil fuels,
2. Ensure fiscal sustainability with less exposure to cyclical risks;
3. Negotiate effectively with neighbouring countries to secure water supply; and
4. Manage droughts in highly vulnerable areas.

The Catalytic Climate Action in Iraq (CCA) programme has worked closely with ministries in the Government of Iraq and been a driver of climate action. As a result of the mix of challenges and successes CCAI faced throughout the previous years (2022-2024), the programme has scored A. The programme annual review for 2024-2025 was exempted as it was due within three months of the programme’s planned end date 30 June 2025.

The programme adopted a whole of government approach to mainstream climate action and promote inter-governmental coordination. Policy advocacy has been a strong avenue for enabling change within Iraq and has contributed to communicating key messages to governorates, providing technical assistance, and facilitating Iraq’s membership to the UN Water Convention.

The CCAI Programme faced an ODA budget reduction, which resulted in a reduction of the planned outputs. To accommodate delivery, the programme was granted a one-year no-cost extension, followed by an additional three-month no-cost extension to allow for the finalisation of the one output (weather stations). In total, the programme was extended by 15 months.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.

Major lessons learned, evidence generated:
- The catalytic delivery approach proved highly effective in maximising limited resources, enabling rapid response to GoI reform priorities, and amplifying UK political influence in the climate sector.
- Working with UNDP as lead implementer provided access and credibility with GoI institutions, but more consistent information-sharing and reporting would have improved the FCDO’s ability to fully showcase results and lessons in real time.
- Evidence-based diplomacy was a strong enabler, technical studies and informal Track 2 (non-governmental) dialogues created trust and opened pathways for formal agreements on transboundary water, demonstrating the value of combining political access with credible technical inputs.
- Programme-funded expertise is vital during closure as well as delivery. The loss of embedded expertise due to budget uncertainty constrained effective exit planning and finalisation of lessons learned.
- Sustainability requires ongoing engagement. While pilots (e.g. renewable energy financing, drought-resilient crops, community-level water solutions) showed uptake, tackling the challenges around weak government ownership, fragmented donor coordination, and limited market access required continued effort.
- Monitoring and evaluation could have been stronger to help demonstrate the programme’s transformational change. Outputs could have been more stretching with reporting linked more clearly to the logframe targets.
- Equity and inclusion had positive examples (e.g. women and young professionals engaged in water diplomacy and technical teams), but there was scope to more fully integrate broader vulnerability dimensions (e.g. marginalised farmers and communities).
- Adaptive management helped the programme navigate political instability and budget fluctuations, but there could have been greater focus on risk from the outset.
Recommendations for Future Programming
- Embed sustainability from the outset by requiring government co-financing, accountability mechanisms, and market-driven approaches to ensure interventions endure beyond donor funding.
- Strengthen monitoring, evaluation and learning (MEL) systems: ensure logframes are stretching, reporting is milestone-linked, and risk registers are in place from inception, with lessons captured iteratively rather than only at closure.
- Plan for exit early: ringfence resources for programme-funded expertise during closure to ensure continuity, capture lessons, and produce high-quality PCRs.
- Invest in strategic communications and branding to amplify UK visibility, mobilise partnerships, and attract co-investment in Iraq’s climate sector.
- Deepen donor coordination by establishing structured climate and energy platforms that align international support and enhance UK political leverage with GoI.
- Advance systemic change in priority sectors:
  - Energy Transition: support NDC fiscal modelling, renewable energy financing (including the Central Bank of Iraq’s initiative), and coordinated engagement with the Ministries of Electricity, Oil and Environment.
  - Water Diplomacy: sustain Track 1 (governmental) and Track 2 (non-governmental) dialogues and support Iraq’s operationalisation of the Water Convention.
  - Drought Preparedness: expand support for market linkages for resilient crops and integrate water-efficient agriculture into Ministry of Agriculture policies.
- Integrate equity and vulnerability analysis systematically, ensuring interventions address the differentiated impacts of climate change on women, youth, and marginalised communities.
- Ensure suitable staffing is available to build and maintain personal relationships with Iraqi stakeholders throughout the programme and to amplify the project internally.

How this report was conducted

This Programme Completion Review was developed through a comprehensive review of evidence from multiple sources. The assessment draws on quarterly and annual progress reports, monitoring and evaluation data submitted by the implementing partner, and independent verification of outputs and outcomes where available. It also considers evidence from stakeholder consultations, including engagement with government counterparts, local authorities, and beneficiary communities, to ensure the programme’s contribution to national climate priorities was captured. Financial data, including audited statements, were reviewed to confirm compliance with FCDO requirements and alignment with agreed budgets. Lessons and insights documented in narrative report, further informed this review.

Actions following approval of this report

Confirming financial closure with the implementing partner.
- Receipt and filing of the final audited financial statements as part of closure documentation.
- Verification of asset disposal in line with FCDO rules and ensuring no programme-funded activity continues beyond the contractual end date.

To ensure sustainability, the programme’s tools, knowledge products, and lessons will be shared with national stakeholders and integrated into ongoing initiatives, supporting Iraq’s climate resilience agenda beyond the life of this programme.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£5,000,000	£3,909,746.40
Timeframe	3 years (10/2021-03/2024)	4 years (10/2021-06/2025)
Outcomes	The GoI is on a growth trajectory toward a climate resilient and low carbon economy.	The GoI has taken strong steps to build climate change, sustainable energy and environmental considerations into its policies. It is early, but the GoI appears to be on the right trajectory.

Overall assessment of programme outcomes and sustainability

The programme aimed to address barriers to climate resilience and low-carbon development to achieve transformational change and catalyse climate action in Iraq. It combined targeted interventions with UK diplomatic assets and convening power, and partner resources to achieve the intended outcome. It also contributed to building the evidence base for climate interventions addressing data deficits and building analytic capacity in Iraq. It was designed to be 100% Investment Climate Financing (ICF) eligible, contributing to ICF Key Performance Indicator (KPI) 15 (transformational change).

The theory of change remained valid, and evidence from implementation supports this. Delivery of CCAI was challenged from the UK-side by a budget reduction in FY22-23, leading to the cancellation of three output indicators and the need for UNDP to reassess their staffing of the programme, and staff drawdowns that impacted management and oversight. There were also challenges presented by the complex political economy in Iraq, inter-ministerial co-ordination and data sharing were prime examples, and the delay caused by attempted intervention in the procurement of weather stations by the DG of Iraqi Meteorological Organisation and Seismology (IMOS) Department.

Despite these challenges, CCAI has performed well. Most Output Indicators have scored either an A (met expectations) or an A+ (moderately exceeded expectation), with only two scoring B (moderately did not meet expectation). This has largely been due to UNDP and GoI making greater use of the programme outputs and products than was initially expected.

This bodes well for sustainability of impact and, following completion of CCAI, the Government of Iraq has continued to focus on delivering climate resilient approaches. GoI is increasing the unconditional emissions reduction target in Iraq’s NDC3.0 and has taken an active position in international fora focused on climate and environment issues. They have been particularly active regarding water and desertification.

Value for Money (VfM)

Assessing the VfM of a catalytic programme like CCAI is challenging, however we assess the VfM of the programme has been good. For the full VfM explanation please see Section D: Value for Money.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The steps outlined in the theory of change (ToC) remained valid. Given the catalytic focus of the programme, a recommendation from the first Annual Review was a discussion between UNDP and FCDO on the theory of change and results framework to better understand indicative results. It also provided an opportunity to refine and contribute to other KPIs. A review of the logframe took place in November 2023 and a review of the Iraq Country Plan was competed in autumn 2023 when our Climate Change activities and results were reviewed. This led to the outputs being enhanced and more tangible products to be added.

The Iraq Country Plan was updated in 2024 and again in 2025 during the No Cost Extension to reflect the priorities of the new UK Government and the decision to reduce ODA to 0.3% of GNI. In both reviews the importance of climate resilience and energy transition were highlighted as a factor in reducing instability and fragility in Iraq, and the benefits to the UK of increasing our security, reducing migration, and providing opportunities for growth. The ToC and logframe targets fitted well with these objectives and the No Cost Extension to June 2025 allowed us to continue influencing the GoI without any amendments.

The delivery of the programme theory of change was impacted by contextual changes in Iraq, driven by the complicated political economy. Data and information sharing between Ministries was a challenge, especially when drafting the multisectoral water study, and the Inter-Ministerial Climate Information Group was delayed due to internal GoI dynamics. Uncertainty around ODA funding for Iraq in 24/25 impacted decision making on the duration and expansion of the programme. These difficulties, along with issues around the procurement of the Weather Stations, led to a no cost extension to ensure effective completion of CCAI.
## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Output Number and Title		Output Number 1 (GoI is supported to facilitate energy transition in Iraq)
Output Score		A
Impact weighting (%)		35%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1: Energy transition framework (ETF) developed and approved	Project design and planning. CCAI programme procured the Regional Center for Renewable Energy and Energy Efficiency (RCREEE) to conduct a review and analysis of the legal and regulatory settings, and policy reform actions required to address barriers to energy diversification. A technical inception report has been completed and assessments of policy and regulations has been completed.		Energy transition policy framework developed and approved	Moderately exceeded expectation (A+): / The ETF was launched at Iraq’s COP29 pavilion securing international visibility. The Prime Minister’s Office endorsed it as a national technical study to support future policy development. It has been published by the Ministry of Environment and UNDP. / In addition, Geospatial information Systems training for energy professionals (22 participants, 27% female) enhanced technical capacity in spatial analysis and energy planning. / Renewal of four software licenses ensured the Ministry of Electricity retained access to advanced solar simulation tools
1.4: Nationally Appropriate Mitigation Activity (NAMA) proposal development.	The starting target was scoping analysis underway		Draft NAMA project is consulted with all stakeholders. / NAMA project developed	Moderately did not meet expectation (B): / In collaboration with the Central Bank of Iraq, CCAI supported a national initiative on renewable energy for Small and Medium-sized Enterprises in Iraq. A comprehensive proposal was submitted to the Mitigation Action Facility to seek international funding. Ultimately the proposal was not funded.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output met expectation and scored (A). Over the lifetime of the programme, substantial progress was achieved in support of Iraq’s energy transition, primarily through the development of Iraq’s first Energy Transition Framework (ETF). The process was anchored in stakeholder engagement, technical training, and iterative policy drafting.

The complex dynamics between Iraqi government ministries meant the Embassy had to engage GoI directly to support timely publication and adoption of the ETF. This was completed in time to be a formal background document for Iraq’s NDC3.0 and will influence Iraq’s future energy transition. This process was a milestone in Iraq’s energy transition journey and effective collaboration between Iraqi institutions, development partners, and international technical agencies. The ETF is published on both MoEn and UNDP platforms.

In parallel, UNDP supported the MoEl in building its technical capacity by renewing four photovoltaic software (PVsyst) licenses in January 2025, extending access through January 2026. These tools are vital for simulating and planning solar photovoltaic projects, ensuring that MoElc can continue predict the amount of energy produced linked to the ETF.

Output 1.4, while not successful in securing international financing, enhanced GoI’s capability to develop and deliver bids for climate finance. On reflection, the inclusion of securing international financing in the target, was probably over-ambitious given the well-recognised challenges of these competitive bidding processes.

CCAI faced a budget reduction in 2023 meaning two planned outputs were cancelled. While the programme managed to deliver its core objectives, these constraints limited the scope of activities and reduced overall flexibility to address political and institutional challenges. The cancelled outputs were:
- Indicator 1.2: (# of NDC-aligned fiscal frameworks for Iraq developed and approved by GoI)
- Indicator 1.3: (# of Grid-wide assessments completed on renewable energy (RE) absorption capacities)

Monitoring and assessment of this output relied on a combination of implementing partner reporting (from UNDP and RCREEE), feedback from workshop and training participants, direct government engagement, and regular coordination meetings. These sources consistently confirmed progress against planned deliverables, though they also highlighted institutional and political barriers that slowed the ETF’s formal adoption. Importantly, no significant contradictions were found across different data sources.

Lessons learned through this output, and recommendations for future programming

Lessons Learned
- Institutional Coordination is Critical but Fragile: The late involvement of the Climate Directorate within the MoEnv highlighted weaknesses in intra-ministerial coordination. Although broad consultations were conducted, the absence of one key technical actor delayed progress and created duplication of review processes. This shows that stakeholder mapping at the outset of programming must go beyond ministries to include relevant directorates, units, and technical offices.
- Political Buy-in from the Highest Levels is Essential: The Prime Minister’s Office (PMO) directive requiring clearance before the publication of policy frameworks fundamentally altered the trajectory of the ETF, reducing its status from a formal policy to a study. This demonstrates that even strong technical products and inclusive consultations cannot overcome political hurdles without early and sustained engagement from the PMO and other high-level decision-makers.
- Capacity Building Delivers Tangible Impact: The GIS training delivered in May 2024 was highly effective in enhancing the skills of government staff, particularly young professionals and women in the MoElc. Positive feedback confirmed that such technical training builds institutional ownership and provides tools that are immediately applicable. The renewal of PVsyst licenses also demonstrated the value of continuity in technical support, preventing the loss of institutional knowledge.
- Budget Reductions Limit Delivery and Flexibility: The 2023 budget reduction directly led to the cancellation of two output indicators, narrowing the scope of activities and weakening the programme’s ability to respond flexibly to emerging needs and political shifts. This experience underscores the risk of reduced funding in complex governance environments, where sustained and predictable investment is often required to maintain momentum.
- Linking National Efforts to International Platforms Increases Impact: The launch of the ETF during COP29 significantly raised Iraq’s visibility and credibility in global climate dialogues. This demonstrated that connecting national outputs to international processes can create external incentives for governments to sustain progress, even when internal challenges slow formal adoption.

Recommendations for Future Programming:
- Ensure Early PMO Engagement: Future programmes should seek to involve the PMO from the design phase, ensuring political backing for strategic frameworks. This could include joint inception workshops, formal letters of engagement, and targeted technical assistance to PMO units.
- Strengthen Inter-ministerial Coordination Mechanisms: Establishing a structured coordination platform or working group across MoElc, MoO, MoEnv, and MoP at the outset of programming will prevent gaps like those encountered with the Climate Directorate. Regular joint meetings, co-signed TORs, and agreed review protocols would provide clarity on roles and responsibilities.
- Embed and Institutionalise Technical Capacity: Building technical skills (e.g. GIS, PVsyst) should be paired with institutional reforms to ensure sustainability. This could include integrating tools into ministry planning processes, establishing government-owned training modules, and embedding capacity within civil service training academies.
- Plan for Financial Contingencies: Given the impact of the 2023 budget reduction, future programmes should design activities with clear prioritisation, contingency measures, and phased delivery plans. Where possible, leveraging co-financing from other donors or GoI budgets would provide resilience against unexpected funding cuts.
- Link Outputs to International Frameworks and Dialogue: Future initiatives should intentionally connect Iraqi outputs to regional and global climate platforms (e.g. COP, UNFCCC processes). This creates incentives for Iraq to maintain momentum, enhances international credibility, and provides a platform for accountability.

Output Number and Title		Output Number 2 (Improved knowledge and capacity of Iraq for transboundary water negotiations)
Output Score		A
Impact weighting (%)		35%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1 Multisectoral analysis report on Iraq's water needs, availability, gaps ad impact of water scarcity on different sectors (including climate change impacts).	Relevant data and info collection		Multisectoral analysis collected and produced	Moderately exceeded expectation (A+): / The study “Towards Climate-Resilient Transboundary Water Arrangements in Iraq” were produced and, alongside the story boards produced by Geneva Water hub, has been used by the MoWR to train staff and as a resource for the negotiation team.
2.2 Number of guidelines for transboundary negotiations produced	Analysis of international laws, / conventions, principles of international law, / bilateral agreements, protocols and minutes / of Iraq		Three guidelines based on the analysis and negotiation vision agreed by all stakeholders / Iraq vision on transboundary negotiations developed	Moderately did not meet expectation (B): Two negotiation guidelines were developed for Iran and Türkiye. The GoI decided against developing the third proposed guideline intended for Syria.
2.3 Number of Iraqi officials trained on a) negotiation skills and b) laws and treaties on transboundary water basins management	Transboundary vision and recommendations for negotiations are designed		Two training courses conducted to train 50 officials	Met expectation (A): / 51 officials were trained.
2.4 Number of global platforms on transboundary water, where GoI has attended / Attendance of Government of Iraq in the UN Water Convention and Meeting of Parties. Specifically 1 platform of Integrated Water Resource Management (IWRM) working group.	Arrangements for one Water Convention events		GoI attended two strategic events under the Water Convention working group by Dec/2023 / Two strategic events to increase position of Iraq on water diplomacy 2024	Moderately exceeded expectation (A+): / Two strategic events under the Water Convention working group by Dec/2023 / And during 2024-2025, two additional strategic events were supported to increase Iraq's position on Iraq's water diplomacy. One was in COP29, and another was in 5th Baghdad International water conference.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output met expectation and scored (A) over the course of the programme. Output 2 successfully delivered against its end-of-programme targets, with all planned indicators’ activities achieved except for the Syrian-specific guideline, which was deprioritised by GoI. Overall, CCAI has made a substantial contribution to strengthening Iraq’s institutional preparedness for transboundary water negotiations. This included developing the resources to inform, train and direct Iraq’s water negotiation teams, and helped Iraq set a vision for its negotiation aims and present its narrative and approach internationally. The products of CCAI have been used far in excess of what we originally anticipated in training Ministry of Water Resources (MoWR) staff.

Despite these successes, the output also encountered systemic challenges in ensuring long-term sustainability of digital platforms and institutional resourcing, reflecting broader constraints in Iraq’s public administration, especially in the digital sphere.

Monitoring of this output relied on implementing partner reporting, direct engagement with MoWR, Ministry of Foreign Affairs (MoFA), and Prime Minister’s Office (PMO) stakeholders, documentation of training sessions, and observation of Iraq’s participation in international fora. The consistency of these sources provided robust evidence of progress, with no major conflicts identified, although sustainability challenges were noted in relation to digital infrastructure.

Lessons learned through this output, and recommendations for future programming

Lessons learned
The delivery of this output demonstrates that Iraq has both the political will and institutional interest to advance structured, evidence-based transboundary water negotiations, but continues to face financial, technical, and institutional barriers that limit sustainability. A key lesson is the importance of combining high-level political engagement with practical, technical capacity support. The adoption of negotiation guidelines and the creation of the storytelling platform were clear milestones, but embedding these tools within government systems requires predictable funding, stronger IT infrastructure, and dedicated institutional arrangements.

Another lesson is that regional and international visibility matters: Iraq’s convening role at the Baghdad International Water Conference (BIWC) not only elevated its profile but also created leverage for sustaining domestic reform momentum. Linking domestic capacity-building with regional and global platforms is therefore a valuable strategy for ensuring that outputs translate into long-term influence.

Recommendations for future programming:

- Institutionalise Digital Tools: Provide sustained technical and financial support to ensure platforms like the storytelling tool are fully transferred to and maintained by Iraqi institutions, including dedicated GoI budget allocations for hosting and software licenses.
- Strengthen Inter-ministerial Coordination: Build structured coordination between MoWR, MoFA, and PMO on water negotiations, supported by joint working groups with clear roles and responsibilities.
- Deepen Negotiation Capacity: Expand tailored training and mentoring programmes for negotiators, with simulations and scenario planning for different negotiation tracks (Iran, Turkey).
- Leverage Regional Platforms: Continue to support Iraq’s role as a convener of regional dialogue (e.g. through the BIWC and link outputs to international fora to strengthen Iraq’s credibility and bargaining power.
- Safeguard Output Delivery from Budget Cuts: As with Output 1, future designs should differentiate between “core” and “secondary” indicators to ensure critical activities are protected during financial constraints.
- Disseminate Lessons Broadly: Lessons from Output 2 should be shared through internal FCDO boards, regional water diplomacy networks, and participatory beneficiary feedback with Iraqi institutions to inform both future UK programming and wider donor strategies.

Output Number and Title		Output Number 3 (Drought preparedness and risk reduction capacities strengthened in Iraq)
Output Score		A+
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
3.1 Build capacity of the Iraq Meteorological Organisation and Seismology (IMOS) to enhanc production of high-quality drought forecasts in user friendly language. Development of (i) capacity needs assessment, (ii) tailored curriculum, and then (ii) trainings	As starting target was deliver training for 25 participants and they trained on EWS		50 Participants	Moderately Exceeded expectations (A+): / 19 participants were trained in person and an additional 20 were trained online in the first reporting period. 25 trainings were delivered during the second reporting period. The cumulative total at March 24 was 64
3.2 Establishment of national committee for drought warning	Institutional needs assessment completed		ToR of the Committee designed	Moderately exceeded expectations (A+): / ToR for the Inter-Ministerial Climate Information Group, established in collaboration with the World Food Programme (WFP) and successfully completed its activities under the project. / Following establishment the Committee developed a routine workflow producing drought outlooks to support early warning. This laid a strong foundation for continued collaboration with WFP and the Ministry of Environment. / The Committee produced guidance on the provision of advisory services, the development of user-centric warnings, and the formulation of guidelines, strategies, and procedures for drought warning reports.
3.3 Drought contingency plans developed - conducted by concerned ministries and provinces	Design of drought contingency planning training package		2 drought contingency planning workshops at the federal and provincial levels	This activity was cancelled due to the budget reduction.
3.4 Number of farmers trained in/equipped for drought resilient technologies to minimise the impact on their livelihoods.	Identifying the targeted communities for the training		250 farmers	Met expectation (A): 251 farmers were trained.
3.5 Number of weather stations set up and handed over to GOI for climate preparedness and readiness	Procurement process		5 stations purchased, installation begun and handed over to GOI (Aug 2025)	Moderately exceeded expectation (A+): / Five weather stations were procured and delivered to the Iraqi Meteorological Organization and Seismology (IMOS). They were deployed at sites in Nineveh (Tel Abta and Al-Ba’aj), Anbar (Al-Nukhayb), Muthanna (Al-Salman), and Basra. / Additionally a Central Data Unit (CDU) was established at Baghdad International Airport to serve as the primary hub for data reception, processing, and archiving. Each station has GSM communication. / IMOS supplied with spare parts, including GSM communication modems and antennas, to support system redundancy and long-term operational sustainability.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output moderately exceeded expectations and scored (A+) over the course of the programme. Output 3 has made strong progress in strengthening Iraq’s national and community-level capacity to anticipate, prepare for, and respond to drought. This has included building technical capacity, access to data, and understanding.

At the institutional level, the Inter-Ministerial Climate Information Group established in collaboration with the World Food Programme (WFP) played a pivotal role in operationalising early warning mechanisms. Through regular meetings, the group developed guidance on user-centric warnings, advisory services, and procedures for drought reporting, thereby laying the foundation for a more coordinated national system of climate risk management.

At the technical level, capacity was enhanced through sustained engagement with the Climate Information and Technical Working Group. This built a solid knowledge base that is being used to generate routine drought outlooks and feed into Iraq’s early warning system. Complementing this, a national workshop on anticipatory action and disaster risk reduction was held in August 2024, producing concrete recommendations for future action.

At the community level, substantial progress was achieved with the successful implementation of resilience measures in northern Iraq. A total of 251 farmers, of whom 40% were women, completed training through Farmer Field Schools in Erbil, Kirkuk, and Sulaymaniyah. These sessions provided practical skills in climate-smart agriculture, water efficiency, and greenhouse management.

Alongside training, more than 500 dunums (a unit of land of 2,500 square metres/0.25 hectare) were brought under drip irrigation, 14 solar-powered irrigation systems were installed, and farmers were equipped with drought-tolerant seeds and climate-resilient tools. This has strengthened community resilience and fostered stronger linkages with government extension services to support sustainability.

Despite strong overall achievements, the programme faced two key challenges. The first was the cancellation of planned drought contingency plans due to budget reductions, which prevented completion of Indicator 3.3. The second was the delay to installing the weather stations due to attempted political interference in the process.

Lessons learned through this output, and recommendations for future programming

Lessons Learned
- Training must be institutionalised to endure. The success of the Climate Information and Technical Working Group (CITWG) showed that technical capacity is most valuable when embedded into routine processes (e.g., regular drought outlooks).
- Infrastructure requires early administrative clearance. Delays in the Basra weather station highlighted how approvals, site changes, and institutional volatility can undermine progress even when equipment and civil works are ready.
- Community structures strengthen resilience. Farmer Field Schools (FFS) and Community Drought Committees (CDC) worked best when supported by government extension services, demonstrating that local ownership is key to sustainability.
- Gender balance improves uptake. With 40% of FFS graduates being women, the programme showed that inclusive participation not only promotes equity but also improves adoption of climate-resilient technologies.
- Forecasts need to be translated into actions. Technical early warnings are useful, but farmers and ministries require practical, impact-based advisories to guide planting, irrigation, and other decisions.

Recommendations for future programming:

- Formalise inter-ministerial mechanisms. Establish clear Terms of Reference and formal mandates for the CITWG to ensure continuity of drought outlook production and climate risk analysis.
- Adopt a “permits-first” approach for infrastructure. Secure site selection, legal approvals, and operational agreements before procurement, and ensure operation and maintenance plans are budgeted from the outset.
- Scale up community resilience models. Replicate the FFS and CDC model in other governorates through costed toolkits, ensuring continued collaboration with extension services.
- Maintain sex-disaggregated monitoring. Track women’s participation systematically to sustain inclusive access to training, inputs, and technologies.
- Develop impact-based advisories. Co-design actionable, user-friendly advisories with agriculture and water ministries, and test dissemination channels such as SMS, radio, and CDC noticeboards for last-mile delivery.

Output Number and Title		Output Number 4 (Knowledge and learning is generated and informs improved design of climate resilience and low carbon programming in the future)
Output Score		A
Impact weighting (%)		10%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
4.1 Hire Climate and Energy advisor within FCDO. / Hiring of Climate Advisor to support implementation of program and seek for further opportunities	Recruitment process		Climate and Energy advisor within FCDO was hired	Met expectation (A): Climate Adviser recruited and role has been baselined into Embassy staffing.
4.2 Development of Monitoring, Evaulation & Learning for wider climate activities within FCDO Iraq office (in alignment to country strategy) and for overall programme engagement. / Monitoring of programme activities to capture wider qualitative outputs and outcomes.	Recruitment process		MEL lead was hired	Met expectation (A): Monitoring and evaluation process and Evaluation Report has been done last year (December 2024)
4.3 Number of international and national climate events organised or attended to promote progress of this programme. - transformational change of climate action in Iraq, Improved climate change knowledge sharing across GOI and stakeholders.				The ‘permanent’ cross-GoI negotiating team built expertise and experience quickly and effectively. / Iraqi pavilions at COP28 and COP29 demonstrated leadership internationally and highlighted CCAI outputs at events. / Water officials understood transboundary water issues better and negotiations became more efficient. / UNDP Climate Information Group help build cross-GoI connections.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output met expectations and scored (A) over the course of the programme. The expansion of climate and energy expertise within British Embassy Baghdad has supported the mainstreaming of these issues into wider work, including political and growth efforts. Moving the role from programme funding to baseline staffing has increased the sustainability of this expertise and approach. Continuity of the role will allow for expert input to Country Business Planning, programme and project development, and provide links into central expertise and funding opportunities. It will also allow for continued engagement with GoI and external stakeholders.

Domestically we have seen better co-ordination between some GoI ministries and departments. UNDP’s creation of a Climate Information Group was important for bringing Iraqi ministries and stakeholders together, even if they could have handled the process more sensitively. There have been political challenges with this and the election in November 2025 may change these dynamics for the future. This is one reason a continued Climate Adviser presence in Post will be important.

In addition to the scored outputs, the GoI was supported to be active internationally. They created a ‘permanent’ UNFCCC negotiating team to help develop experience and expertise. Iraq hosted a Pavillion at both COP28 and COP29 holding a series of events demonstrating their efforts on climate and energy, including building on the outputs and outcomes from CCAI – on energy transition, drought resilience, and regional water sharing. CCAI’s transboundary water outputs underpinned aspects of Iraq’s presentations at the Fifth Baghdad International Water Conference in April 2025.

Lessons learned through this output, and recommendations for future programming

Lessons learned
- Continued engagement is necessary to ensure climate and energy issues remain on the political agenda and programme work does not stall. Personal relationships are essential for this in the Iraqi context.
- Iraq is active internationally when the benefits are clear. It is important for different departments to coordinate their efforts to avoid duplication and maximise impact.
- Continued engagement with Post and the UK system is important to ensure the objectives of the programme are understood and mainstreamed into wider work of the embassy ensuring that political and economic levers can be used when needed and the successes can be amplified.

Recommendations
- Ensure there is suitable bandwidth for Programme Manager/SRO available to both build personal relationships with Iraqi stakeholders to maintain momentum and to engage broadly enough to provide an understanding of what different Iraqi ministries are doing where there are overlapping remits.
- Ensure there is suitable bandwidth in the programme team to engage internally to maximise understanding of where the programme fits into wider Embassy and HMG work, and to support development of colleagues to take advantage of the programmes work.
- Ensure lessons learned are fed into new programme designs were appropriate.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

Assessing the VfM of a catalytic programme like CCAI is challenging. The business case for CCAI noted the VfM was compelling, but not absolute, and that the economic benefits of this programme were uncertain. The last AR indicated CCAI was delivering good VfM given its alignment with the Country Plan, its ability to influence the GoI on issues linked to climate and wider insecurity, and Iraq’s broader development pathway. However, the real outcomes of CCAI, and therefore its true VfM, will only be evident and measurable as GoI implements these policy changes.

At this point, the outputs and products appear to be influencing GoI’s approach and shaping keystone policies like ‘Vision 2050’ and Iraq’s NDC3.0. Both policies were published shortly after the closure of CCAI. Vision 2050 integrates sustainable initiatives to provide 70% of Iraq’s water, food and energy. The NDC3.0 increases Iraq’s existing unconditional emissions reductions target for 2030 and sets a new target for 2035. The Energy Transition Report, a core outcome of CCAI was published by GoI as a formal technical study in support of the NDC3.0. Iraq has also published a country programme with the Green Climate Fund and developed a national Climate Investment Plan. Following through and implementing these policies should help deliver sustainability of action towards climate resilience and clean energy. They should also create trade opportunities for UK PLC.

Climate change disproportionately affects marginalised groups and communities, so CCAI sought to target poor and women farmers to improve food security and maximise climate resilience. Through community drought committees, community leaders, farmers, workers and agriculture directorates were able to create a forum for community grievances, mediation and input into local operational and project decisions. A tailored gender plan was designed and incorporated into Output 3 sensitised to the needs and capacities of women for drought preparedness. As a result, women were directly targeted for training in farmer field schools.

The cost of operating in Iraq is high and the security situation affected the efficiency of delivery. This is a wider challenge of delivering in a fragile state. Despite this, all outputs were delivered to budget and, apart from the weather stations, to time. Installation of the weather stations necessitated a No Cost Extension to the overall programme as the final output to be delivered. A budget cut part-way through the project necessitated UNDP to cut some management resource and remove three sub-outputs in consultation with the GoI. However, overall, we still assess the CCAI programme provided good VfM.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

Various risks were identified and mitigated over the life of the programme. The major risks related to the capacity, and political will, of the GoI to deliver on its climate and energy transition agenda given the complect political economy in Iraq. These were mitigated through consistent lobbying and building relationships with key individuals, as well as aligning with national and PM-level commitments such as ending routine gas flaring.

We initially considered there was a moderate fiduciary risk given the overall risk of fraud and corruption in Iraq. To mitigate this, UNDP conducted due diligence assessments of delivery partners and maintained robust procurement approaches.

We also considered there was a moderate risk of reputational damage for spending ODA in an Upper Middle Income Petrostate. This was mitigated by having a clear rationale on the importance of reducing emissions, to the benefit of all.

With programme delivery now complete, we only retain two minor risks around delivery, linked to the potential for UNDP staff and institutional memory to be lost before the programme is archived, and reputation, given the potential for our support to still be criticised for political or activist purposes. These will be mitigated though resumption of Post climate capacity and robust information management processes.

Current level of fiduciary risk and direction of travel since last ASP	Minor / Improving
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

The programme was administered and delivered by UNDP. As the programme administrator, UNDP was responsible for the management of the programme, execution of legal agreements, and ensuring fiduciary oversight and compliance with central UNDP policies and procedures.

UNDP was responsible for the overall work programme and its daily operations and management. We maintained a regular rota of meetings in addition to regular formal reporting. They gave FCDO a formal progress update on the programme every 6 months, as set out in our Framework Arrangement and a project report on the status of the programme every year for the duration, within 6 weeks after the end of the relevant period, and a final report summarising programme performance and results within 3 months of completion.

UNDP worked in close partnership with the GoI and supported the development of the original and revised NDCs, as well as supporting technical work underpinning them. UNDP worked mainly with the Ministry of the Environment but also strengthened the capacity of the Ministry of Water Resources and supported the development of a National Water Council. UNDP has also assisted the Ministry of Water Resources in developing Local Water Committees to improve water governance at the sub-regional level.

We had some challenges with UNDP where delivery issues were not communicated in a timely matter because they felt they could manage them on their own. These cases usually resulted in being cleared by intervention from the Embassy with only minor delays. However, flagging these issues earlier could have mitigated these delays entirely. Changes in staff, and staff absences were also not communicated effectively occasionally leaving us without points of contact.

Programme-level approach to monitoring and evaluation

This programme was not expected to be formally evaluated. Learning and evidence was mainstreamed through the programme. Individual projects will collect relevant data to assess performance. Members of the Development Team have undertaken monitoring visits where tangible outputs have been delivered. For more catalytic aspects of the programme, BEB has ensured senior engagement at policy launch events to demonstrate political support for GoI’s approach.

The programme was monitored quarterly through Post-led structures and formally monitored during the FCDO Annual Reviews from the date of implementation. We do not deem it appropriate to procure a formal evaluation.

Date of last narrative financial report	28 August 2025	Date of last audited annual statement	N/A