## Annual Review Template

Title: Humanitarian Action and Recovery after Crisis programme (DRC) – Translated: Action Humanitaire et Relèvement après Crise
Programme Value £ (full life): 209 million		Review date: 18 July 2025
Programme Code: 301448	AMP start date: 18/04/2023	AMP end date: 15/12/2027

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	HARC Business Case DevTracker / Addendum 1
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The Democratic Republic of the Congo (DRC) is one of the largest and most complex humanitarian crises in the world. Over 24 million people needed humanitarian assistance and protection in 2024, of which 7.3 million people were displaced.

Over the course of 2024, the conflict in North Kivu between the Mouvement du mars 23 (M23) and government forces intensified, resulting in increased fighting and heavy artillery positioned around displacement sites near the provincial capital of Goma. Between November 2023 and February 2024, 1.5 million people were newly displaced and another one million mid-way through the year, as the conflict spread into neighbouring South Kivu. Displacement sites around the provincial capital of Goma multiplied rapidly, outpacing the capacity of the humanitarian system to deliver. In January 2025, M23 forcibly took control of significant territory in North and South Kivu, including the provincial capitals, and dismantled displacement sites. Key supply routes, including the airports, were closed and remain out of service. The humanitarian community was forced to temporarily withdraw to safety and to evacuate non-essential staff. An estimated 1 million displaced people were forced to flee again. Although many displaced people have returned to their places of origin, they are finding their land and houses destroyed, occupied or inaccessible.

In the province of Ituri, many thousands of people were affected by conflicts with other armed groups, such as Allied Democratic Forces (ADF), the Coopérative pour le Developpement du Congo (CODECO) and Zaire. The impact of the conflict and access of humanitarian organisations to those in need has worsened this year, as armed groups take advantage of a focus on North and South Kivu.

The events in early 2025 have vastly altered the humanitarian context in eastern DRC, adding to an already desperate food, health and protection crisis.

Throughout the reporting period, the Humanitarian Action and Recovery after Crisis (HARC) programme provided urgent life-saving assistance to populations in need, responding at pace to meet new needs and assuming a lead role in responding to dramatic changes in context.

Between 2023 and 2027, the Humanitarian Action and Recovery after Crisis (HARC) programme, will deliver £209 million of lifesaving humanitarian assistance to approximately 4 million people, primarily in the conflict affected provinces of North Kivu, South Kivu and Ituri. The programme includes:

1. International Committee of the Red Cross (ICRC) which delivers humanitarian assistance and protection activities in some of the hardest to reach areas, including through capital investment in water, sanitation and hygiene (WASH) infrastructure.
2. Strategic Assistance for Emergency Response in DRC (SAFER) a consortium of non-governmental organisations (NGO) led by Mercy Corps, which delivers rapid multipurpose cash and voucher assistance and emergency WASH services to newly displaced populations.
3. World Food Programme (WFP), to deliver multipurpose cash and voucher assistance, including mitigating risks to women and girls.
4. United Nations Children’s Fund (UNICEF), which tackles cholera in regions with high levels of displacement including through capital investment in WASH infrastructure and provides child protection.
5. Enabling Affected Communities to Survive and Thrive (EAST) an NGO consortium led by Concern Worldwide, which delivers longer-term support to build resilience, focused on those affected by sexual and gender-based violence (SGBV), by restarting livelihoods, developing income generating activities and treating Severe Acute Malnutrition (SAM).
6. United Nation Population Fund (UNFPA) to strengthen health systems for improved gender-sensitive sexual and reproductive health and rights (SRHR) services in humanitarian settings.
7. Strategic Partnerships through targeted interventions on key areas of focus, namely rapid response, cash assistance, civil-military relations, prioritisation and information management
8. United Nations Humanitarian Air Service (UNHAS), administered by WFP, a critical enabler of the humanitarian response, allowing access to otherwise inaccessible areas.
9. Independent third-party monitoring and strategic research by the NGO, IMPACT Initiatives.

This Annual Review of the HARC programme covers the period from January 2024 to March 2025. It was originally intended to cover the 2024 calendar year, but a three-month extension was received due to the crisis in eastern DRC from January 2025 (see below). Two addendums to the HARC Business Case were approved during the reporting period. In May 2024, the budget was increased by £16 million to facilitate increased capital expenditure on emergency water and sanitation and delivery of sexual and reproductive health services. In October 2024, a further increase of £95 million was approved to extend the programme from three years to four. WFP and UNICEF were added as partners in January 2024 and UNFPA was added in November 2024. Due to the timing of the contribution, UNFPA’s performance will be assessed in the next Annual Review.

Summary supporting narrative for the overall score in this review

The programme has scored an A in a complex and demanding operating environment. Humanitarian assistance was provided to almost two million people in the reporting period with double the programme resources than the year before (and approximately 60% more than anticipated).

The programme provided rapid response to newly displaced people through multipurpose cash assistance at scale, invested in more effective delivery of humanitarian assistance through water and sanitation infrastructure and delivered livelihoods assistance to help build community resilience to shocks.

In response to the dramatic contextual shifts in 2025, partners quickly pivoted activities to scale up delivery of urgent assistance.

Major lessons and recommendations for the year ahead

The programme successfully responded flexibly to severe changes in context providing proof of concept in modalities used, the expertise and strength of relationships held by key partners with the capacity to deliver urgent lifesaving support.

The recommendations arising from last year’s Annual Review have been implemented. Combining advocacy with our programme activities, per the recommendations of last year’s annual review, continues to be impactful. During the reporting period, programme focus areas, namely rapid response, cash response and humanitarian access were reinforced by strategic partnership support and policy engagement to influence the enabling landscape in these areas.

Following the recommendation for multi-year programming, the HARC Business Case obtained a one-year extension until March 2027. Budgets will be confirmed with partners in due course.

There was an increased emphasis on programme conflict sensitivity. British Embassy Kinshasa’s (BEK) conflict adviser reviewed key components of the HARC programme, connecting partners with the BEK-funded Conflict Sensitivity Hub where technical support was available.

New Recommendations

Build on progress to improve prioritisation of assistance: In response to new and more complex vulnerabilities and given the challenging global funding context by enhancing information management and analytical capacity for the humanitarian system through IMPACT’s research and analysis initiative (known as REACH). The analysis was used in the preparation of the inter-agency Humanitarian Needs and Response Plan (HNRP). In the coming year, we will support needs assessments to improve prioritisation of populations with the most severe humanitarian needs, accompanied by enhanced beneficiary decision making.

Flexing funding to context changes: We have maintained flexible funding options by building strong relationships with partners who have the capacity to respond to the changing context of increased fighting and to deliver urgent emergency lifesaving support. Alongside, the HARC programme incorporated a greater focus on more efficient, longer lasting emergency assistance, replacing water trucking with capital investment in the water network. These changes create greater efficiencies and have significant value for money, while providing people what they need. In the coming year, BEK should consider obtaining the services of infrastructure specialists to ensure the integrity of these programmes.

Adapt the HARC programme. The HARC programme represented over 60% of BEK annual spend in financial year 2024/25. The HARC programme should be adapted to ensure that the number and complexity of partnerships ensure balance between providing life-saving support, partnerships and policy engagement.

Linking advocacy to programming and technical assistance: Combining advocacy with our programme activities continues to be impactful, focusing attention on DRC, e.g. lobbying for system wide scale up, persuading others to effect system change, for example improving prioritisation, and the use of third-party monitoring. In the coming year, these predominantly local efforts should be augmented with dedicated support and more efforts should be taken to inform global advocacy and programming with the DRC experience, notably multilateral system reform and the humanitarian reset underway. During the reporting period, BEK continued to actively contribute to advocacy efforts leveraging senior leadership and engaging in key humanitarian forums. With full humanitarian advisory capacity in the coming year, BEK should extend this engagement to the technical working groups focussing on prioritisation, efficiency, and speed.

Focus on Preventing Sexual Exploitation and Abuse and other safeguarding ​measures: In October, BEK fielded a dedicated programme management visit to eastern DRC to meet with partners and discuss their safeguarding approach and concerns. The visit made recommendations about how to improve BEK support in this area. The visit is considered a best practice to be replicated annually, if the security situation allows. Quarterly meetings and dedicated safeguarding meetings will be used to test partner internal controls.

Update the HARC programme theory of change (by October 2025). Since the inception of the HARC programme conflict dynamics, humanitarian needs, the operating context and available funding have changed significantly. Given the change in operating context and in the range of partners, the HARC logical framework does not sufficiently reflect the achievements of the programme. Whilst programme objectives will remain broadly similar (prioritise, protect and prevent), emphasis, modalities and partners should be informed by the reality on the ground. An updated analysis of the context and the capacities of the humanitarian system should, where appropriate, inform a revision of the theory of change before the next Annual Review.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The theory of change aims to provide the humanitarian assistance necessary to ensure that men, women and children’s lives are saved and that cycles of humanitarian crisis are prevented, civilians' rights are protected, and suffering is reduced. This is achieved by meeting the immediate needs of displaced and vulnerable households with multipurpose flexible cash grants; supporting those households to recover from the effects of violence and to access humanitarian assistance in a dignified manner, including by focusing on sexual and gender-based violence; and to improve household food security and nutrition situation by supporting them to restart livelihoods and treat malnutrition, and improving their ability to cope with future shocks. BEK supports these outcomes by helping the enabling logistical and analytical capacity of the humanitarian system and by influencing the humanitarian sector and its engagement with the government of DRC at every level. These outcomes were initially driven by the four programmatic components (SAFER, a UN agency, ICRC, EAST), monitored through a third party.
Since the theory of change was approved in 2023, there have been three significant shifts in the humanitarian context: 1) the emergence of M23 and increased conflict in 2023, leading to the growth of displacement sites around the provincial capital of Goma and the subsequent declaration of a system wide scale up of the humanitarian system by the United Nations; 2) the intensification of the fighting between M23 and government and regional forces in 2024, and the use of heavy artillery, which caused rapid growth of the underserviced camps; and, 3) in 2025, the expansion of M23 territory across North and South Kivu, the forced closure of displacement sites and a new returnee population of over one million people. These shifts have radically altered the operating context, surfacing new, compounded vulnerabilities, with difficulties reaching those in need, and with working within an area controlled by a non-state authority. A global and local decrease in humanitarian funding has required a new focus on seeking prioritisation and efficiencies.
The HARC programme responded promptly and well to these shifts, but the new operating environment necessitates a reassessment of the assumptions underpinning the programme. At this mid-way point in the programme’s four years, it is an opportune moment to take stock of the theory of change and to adapt as needed.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

HARC is on track to achieve its outcomes, meeting the immediate needs of displaced people, enabling people to recover from violence and access assistance in a dignified manner, while building people’s resilience to future shocks.

Outcome 1: Displaced and vulnerable household’s immediate needs are met.

HARC achieved the outcome of meeting displaced people’s immediate needs during the reporting period. Monitoring showed that cash, food and immediate water and sanitation assistance were effective in helping people recover from displacement and avoid its worst consequences.

SAFER assistance was found to be appropriate, with 67% of households reporting that at least some of their household’s needs for the first month were met by SAFER assistance. This exceeds the target of 60% and was reinforced by third party monitoring (TPM) visits, which found this figure ranged from 95% to 100% % for assistance provided by SAFER and WFP (across 11 visits).

Women reported that they were able to participate actively and safely in decision making about the use of assistance. 97% of female respondents said this was true after receiving SAFER assistance, against a baseline of 80%. TPM visits to SAFER project locations found that between 75% and 91% of households reported that decisions were either made jointly or by females. These figures ranged from 73% to 93% for TPM visits to WFP project locations.

Beneficiaries reported a reduction in negative coping strategies following HARC interventions. For SAFER, the average household ‘reduced coping strategies index’ (rCSI) fell by 76.3% during the reporting period, exceeding the target of 60%. For WFP, rCSI fell from an average score of 18 to 13 by the end of the reporting period, a drop of 28%.

Outcome 2: Vulnerable households recover from the effects of violence and are able to access humanitarian assistance in a dignified manner.

The change expected from the programme are being successfully delivered as measured by the percentage of people satisfied with the protection services provided by the programme, their ability to access protection services such as psychosocial support, and whether they believe their safety and security has improved.

Partners took measures to ensure that assistance was delivered safely and did not exacerbate protection risks. SAFER found that 94% of beneficiaries reported that humanitarian assistance is delivered in a safe, accessible, accountable and participatory manner, against a target of 80%, and this indicator was also 94% for EAST’s beneficiaries. TPM visits provided independent confirmation of beneficiary satisfaction with protection measures, with satisfaction rates of between 92% and 99% at SAFER distribution sites, and between 90% and 100% for WFP.

ICRC expanded the availability of protection services, focussing on those who had no other access to assistance, particularly people in rural areas and those deprived of their liberty. EAST and SAFER provided individualised protection assistance, including psychosocial support, and referrals to survivors of gender-based violence. EAST also provided cash to people facing protection risks and assistive devices to people with disabilities.

Finally, 93% of SAFER beneficiaries sampled reported an improvement in the sense of safety and security at the end of the project, against a target of 80%.

Outcome 3: Household's resilience to food and nutrition shocks is improved.

This outcome was on track by the end of the reporting period. During 2024, EAST’s resilience activities were being designed and implemented so there is limited outcome level data from 2024. However, in January to March 2025, 81% of vulnerable households that participated in EAST’s training and capacity building programmes reported an increased capacity to respond to shocks and absorb their impacts (against a target of 60%). 83% of target households had an improved and acceptable food consumption score at the end of the action (against a target of 80%). Further, WFP reported that food consumption scores increased from a baseline of 15.7 to 27 by the end of their intervention (against a target of 25.7) highlighting the contribution that cash and food assistance makes to resilience.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The HARC programme continues to address urgent humanitarian needs and persistent challenges. The proof of concept has been validated through demonstrated impact, with clear delivery against programme goals in a challenging operating environment. In the reporting period the UK was able to significantly scale up assistance, being one of the first donors to do so following the crisis in January 2025 and addressing critical gaps to sustain the humanitarian system. The UK is well positioned to sustain this work given its impact as a significant donor, the technical leadership demonstrated through critical co-ordinator forums; and the breadth of capable partnerships.

## C. DETAILED OUTPUT SCORING

Output Title	Quality, timely and adequate assistance is delivered to areas of greatest humanitarian need.
Output number:		1	Output Score:	A
Impact weighting (%):		45	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of people receiving humanitarian assistance to meet immediate needs through UK funding (including rapid response), disaggregated by modality: in-kind, cash, vouchers, & mobile money	1,044,956	1,085,773 / (104%)
1.2 Percentage of interventions started within 9 weeks from the alert (SAFER)	75%	94% / (125%)
1.3 Number of individuals with access to sufficient quantities of clean drinking water for domestic use	507,651	540,402 / (106%)
1.4 Number of cholera cases treated and of people receiving prevention services	119,870	946,103 / (789%)

Briefly describe the output’s activities and provide supporting narrative for the score.

This is the emergency response component of the programme, aiming to save lives. It includes results from the NGO rapid response consortium, SAFER, the International Committee of the Red Cross (ICRC), the World Food Programme (WFP) and the UN Children’s Fund (UNICEF). This output scores an A as a balance of the indicators were all achieved.

The SAFER consortium sought to meet new needs resulting from large-scale displacement within twelve weeks of a UN alert. SAFER delivers cash, food and water and sanitation assistance. ICRC’s country appeal, to which the HARC programme contributes, includes provision of cash, food, essential supplies, water and sanitation assistance and healthcare in hard-to-reach areas.[1] WFP provides multiple rounds of cash or food assistance to food insecure households, for up to 6 months, at USD 15 per person per month. WFP conducts rapid protection assessments to help mitigate sexual exploitation and abuse risks when distributing cash assistance. Finally, UNICEF responded to urgent cholera and child protection needs from January to April 2024.
[1] Due to ICRC’s reporting timeframe, this Annual Review uses ICRC’s targets and results data from their 2023 appeal, with targets and results reported in the last Annual Review removed.

Output 1.1: The number of people provided with food, cash or vouchers.

All partners over-achieved against their targets, in response to increased largescale displacements due to the intense fighting in 2024. SAFER assisted over 370,000 people against a milestone of 340,000, and ICRC reached almost 18,000 people compared with a milestone of 3,200. WFP reached 700,000 people with multipurpose, flexible cash grants, meeting their target for the year.

Output 1.2: Percentage of interventions started within nine weeks of the alert.

SAFER began interventions within nine weeks of an alert 94% of the time, exceeding the target of 75 per cent. This indicator previously set a target for inventions started within 12 weeks of an alert. During the reporting period, SAFER partners piloted and implemented proposed changes to the response methodology, improving response times to nine weeks from July 2024 onwards, while retaining quality of response and safety of staff.

Output Indicator 1.3: the number of individuals with access to a sufficient quantity of clean drinking water for domestic use.

As part of its rapid response, SAFER provided clean drinking water, decent sanitation and hygiene kits. Given the growing levels of displacement, HARC augmented SAFER’s water and sanitation response with a capital investment contribution for the construction of water points, latrines and sanitation facilities, including in health centres. SAFER delivered drinking water to 188,000 people through its rapid response work, less than the planned target of 215,000 as a result of the disruption to delivery from January 2025. However, the infrastructure funding enabled over 270,000 people to access drinking water against a target of 235,000.

ICRC moderately underachieved their WASH targets, reaching 32,000 people compared with a target of almost 38,500. This was due to a decision to reprioritise funding for life-saving healthcare due to the escalating conflict and scaling back water projects.

Output 1.4 the number of cholera cases treated and of people receiving prevention services.

In 2024, DRC was facing one of the worst cholera outbreaks in six years. The HARC programme contributed £3 million to the UNICEF cholera response to reduce morbidity and mortality of cholera in eastern DRC through targeted health and water and sanitation interventions supporting almost 950,000 people, well in excess of their target of 120,000 people. The cholera outbreak was supressed, though cholera remains endemic in DRC.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In 2024, HARC funded the position of an inter-agency Rapid Response Co-ordinator to strengthen the displacement alert system and co-ordinate the response among different rapid response mechanisms. This support provides an enabling environment for the SAFER component, while also contributing to the wider response environment.

Output 1.4 will not be reported on in the next Annual Review as the cholera response was limited to January – April 2024.

Progress on recommendations from the previous AR

Continued incidence of large-scale displacements are anticipated, given conflict dynamics, validating continued support of the SAFER rapid response mechanism and the delivery by WFP of multipurpose cash at scale. We are exploring the use of mobile money transfers where feasible and safe to overcome liquidity constraints. ICRC remain a critical actor to reach vulnerable populations.

Using the UK’s influence our funding of the Rapid Response Co-ordinator, and to IMPACT we will continue to seek improvements in the alert system to ensure the most vulnerable are prioritised and reached quickly and safely.

Output Title	Protection assistance is provided to enhance safety, dignity, and rights of people in areas of greatest humanitarian need and survivors of abuse and SGBV are supported.
Output number:		2	Output Score:	B
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1.1 Number of people receiving or referred to protection services	26,350	26,520 / (101%)
2.1.2 Number of people receiving mental health and psychosocial support	2,771	2,106 / (76%)
2.2.1 Percentage of men, women, girls and boys targeted who reported receiving information on PSEA services	75%	70% / (93%)
2.2.2 Number of SGBV/PSEA cases receiving holistic care	2,889	1,502 / (52%)

Briefly describe the output’s activities and provide supporting narrative for the score.

The EAST consortium seeks to prevent sexual and gender-based violence and responded to the needs of survivors through psychosocial support, referrals for healthcare, case management and cash assistance. It delivers other protection interventions, such as assistance to people living with a disability. Targets for protection and Protection from Sexual Exploitation and Abuse (PSEA) services were met, and at a vital time given the context in eastern DRC. However, EAST experienced start-up delays in targeting their activities, staff training, and validating Standard Operating Procedures (SOPs) for the consortium. It was agreed with FCDO that implementation would be paused to allow sufficient time for consortium alignment. SOPs were validated in June 2024, followed by training sessions in Tanganyika, North Kivu, and Ituri, with implementation of individual protection assistance from August 2024. As a result of these delays, this output underachieved the indicators on mental health and psychosocial support (MHPSS) and provision of SGBV care to survivors.

For these reasons this output scored a B. More positively, EAST has worked hard to overcome these challenges and is now delivering as planned. Between January and March 2025, EAST achieved or exceeded its targets, for example a 50% overachievement in the number of people provided with MHPSS.

Through HARC’s contribution to the ICRC country appeal, the programme funds ICRC’s protection activities. In addition to MHPSS and assistance to SGBV survivors, these include visits to detainees, advocating for compliance with International Humanitarian Law and reuniting unaccompanied children with their families. ICRC overachieved its indicators during the reporting period.

Output indicator 2.1.1: Number of people receiving or referred to protection services.

The milestone for this indicator was exceeded with ICRC providing protection assistance to over 5,300 people with HARC funding, exceeding the target of 3,300 due to higher than anticipated demand. EAST provided protection assistance to 1,500 people, missing the target of 2,500.

Two other partners contributed to this indicator. UNICEF provided 19,400 people with protection assistance as part of their response to the cholera outbreak in eastern DRC (slightly less than the target of 20,000 people). This included medical care and psychosocial support, family reunification, case management for children in foster care and released from armed groups and SGBV response. SAFER provided cash to 350 people assessed as in need of protection assistance, compared with a target of 550.

Output indicator 2.1.2: Number of people receiving mental health and psychosocial support.

ICRC has provided mental health and psychosocial support (MHPSS) including to survivors of sexual based violence. ICRC overachieved its target of 250 people, reaching 290 people with HARC funding. EAST supported 1,800 people, compared with a target of over 2,500 between January 2024 and March 2025. EAST overachieved their target for this output in January to March 2025 by 50%, demonstrating successful delivery following delays in starting implementation.

Output indicator 2.2.1: Percentage of men, women, girls and boys targeted who reported receiving information on PSEA services

FCDO partners are required to take all reasonable and adequate steps to prevent Sexual Exploitation, Abuse and Harassment. This includes providing information to beneficiaries on PSEA services. HARC’s TPM provider, IMPACT, collects data on the proportion of sampled beneficiaries who have received this information. An average of 70% of beneficiaries received this information, slightly underachieving against a benchmark of 75%. The figures varied by partner with WFP achieving 75% across 7 visits and SAFER achieving 61% across 5 visits. No TPM visits were done for EAST during the reporting period, though one visit in April 2025 has a result of 93%, providing some assurance of EAST’s processes. The programme team has engaged partners to encourage progressive improvement on PSEA.

Output indicator: 2.2.2: Number of SGBV/PSEA cases receiving holistic care.

The HARC programme funded ICRC to provide care to 38 SGBV survivors (mostly within 72 hours of the incident) at primary-health-care centres. This represented an overachievement on ICRC’s target of 29 people. As above, EAST underachieved because of delays, providing only 1450 people with care, compared with a target of over 2,800. So far in 2025, this output has been overachieved.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

UNFPA was added as a partner to the programme in November 2024 to provide sexual reproductive health services. Their contribution will be assessed under this output in the next Annual Review.

We will review the description of Output indicator 2.2.2 as some elements of holistic care, such as legal assistance, are not provided through HARC.

Output Title	Malnourished households receive appropriate support and households receive cash to restart livelihoods
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1.1 Number of cases of Global Acute and Severe Acute Malnutrition (in areas of nutrition crisis) provided with treatment.	3,907	4,845 / (124%)
3.1.2 Cure rate for the treatment of Severe Acute Malnutrition	80%	97% / (121%)
3.2.1 Amount of cash distributed for livelihood support.	1,237,400	763,383 / (62%)
3.2.2 Number and types of livelihoods re-established.	82,692	78,291 / (95%)
3.2.3 Number of people supported to better adapt to the effect of climate change as a result of International Climate Finance	471,842	748,773 / (159%)

Briefly describe the output’s activities and provide supporting narrative for the score.

The EAST consortium seeks to prevent people from being in need of, or dependent on, humanitarian assistance through addressing malnutrition and enabling people to be less dependent on humanitarian assistance through livelihoods assistance. ICRC also provides supplies, equipment and training to enable people to produce food and provides training and conditional grants for people to start small businesses.

The output has scored an A overall, the result of nutrition indicators being overachieved and in spite of EAST’s livelihood activities failing to reach their targets as a result of a lack of cash suppliers, limited bank capacity in the provinces, and security concerns delaying the completion of infrastructure work and to transport cash.

Output 3.1.1 Number of malnutrition cases treated and 3.1.2 Cure rate for Severe Acute Malnutrition (SAM).

EAST’s malnutrition work includes preventative actions, such as ante-natal care, and identifying and treating cases of malnutrition. EAST supported health centres and the community health system, for example ensuring a regular supply of medicines and nutritional inputs. Emergency referrals were also facilitated with the provision of free transport and food assistance. During the reporting period, EAST treated over 4,800 cases of malnutrition, against a target of just over 3,900, reflecting the high incidence of malnutrition in targeted areas. The cure rate for SAM was 97%, well over the target of 80%, demonstrating the quality of treatment provided through EAST’s facilities.

Output indicator 3.2.1: Amount of cash distributed for livelihood support and Output indicator, 3.2.2: Number and types of livelihoods re-established.

EAST delivers a number of livelihoods interventions, including training and kits to enable people to begin a trade, setting up village savings and loans associations to generate investment in local businesses, and cash for work programmes. EAST was delayed in delivering these activities due to a lack of cash suppliers, limited bank capacity in the provinces, and security concerns delaying the completion of infrastructure work and to transport cash. As a result, USD 760,000 was transferred compared to a target of over USD 1.2 million and EAST supported 62,500 people, having targeted over 76,000. As with other EAST indicators, they overachieved in the first quarter of 2025, suggesting that implementation is now on track.

ICRC reestablished 15,700 livelihoods with contributions from the HARC programme, exceeding the target of 6,400. This was possible due to the relative stability of some areas of eastern DRC in the relevant period.

Output indicator, 3.2.3: Number of people supported to better adapt to the effect of climate change as a result of International Climate Finance (ICF).

We have considered 30% of the HARC programme beneficiaries to have become better able to adapt to the effects of climate change by reducing their dependency on climate-related resources. It is composed of other indicators, and the overachievement is primarily driven by UNICEF reaching more people during the response to the cholera outbreak.

## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

Economy: All partners conducted competitive and transparent tendering processes to ensure the economy of inputs is promoted. The experience of BEK partners in the DRC ensures good pricing of inputs and services relevant for the calculation of cash-based interventions. The HARC programme team reviews partner financial reports to ensure costs are eligible and demonstrate good economy.

Efficiency: HARC uses interventions where there is strong evidence of their efficiency. SAFER and WFP deliver flexible cash assistance to enable people to meet their needs. SAFER has also improved the speed of their response to alerts, enabling them to reduce their target from beginning implementation 12 weeks after an alert to within 9 weeks, without sacrificing security. Speed is a crucial dimension of value for money (VFM) in emergencies (where VFM is a function of speed, cost and quality).

Effectiveness: The HARC programme is effective, as evidenced by the achievement of its outcome indicators. It has enhanced its effectiveness through its influencing and funding strategic roles within the humanitarian coordination architecture. As chair of the Good Humanitarian Donorship (GHD) group and one of the largest humanitarian donors in DRC, BEK is able to use its technical and political expertise and work with partners to support a more efficient and effective response. The HARC programme has also funded the Rapid Response Mechanism co-ordinator in Goma to strengthen the co-ordination and timeliness of rapid response mechanisms in eastern DRC, a position in the Cash Working Group to support the scale-up of this modality and a Civilian-Military Co-ordinator with WFP in Bukavu to strengthen coordination with defence and security forces to enable unimpeded delivery of humanitarian assistance. HARC also expanded its funding to IMPACT to cover their needs assessment activities to support the prioritisation of the whole humanitarian system – to ensure assistance is provided to those most in need.

Equity: HARC aims to target the most vulnerable communities and the most marginalised. Partners target beneficiaries at the project design stage, though SAFER uses UN alerts followed by its own needs assessment to identify those in greatest need. Partners are expected to implement the Core Humanitarian Standards and respect the principles of humanitarian aid. Partners disaggregated data by age and gender and several partners include gender-specific output indicators (particularly for protection activities). The following table summarises the performance of partners in reaching female beneficiaries.

Partner	Indicator	% female
SAFER	Total beneficiaries	53%
WFP	Total beneficiaries	52%
UNICEF	People suspected to have cholera responded to within 48 hours.	50%
EAST	People participating in income generating activities	76%
EAST	Number of under 5s with Severe Acute Malnutrition treated	53%
EAST	Number of people receiving Individual Protection Assistance	85%

SAFER also conducted a rapid gender analysis of Kanyaruchinya displacement site, Goma, in March 2024 following increased displacement to this location to support the gender sensitivity of their intervention.

WFP and EAST provided some data disaggregated by disability status. Only 1.6% of WFP beneficiaries were people living with disabilities. For EAST, 30% of the people participating in income-generating activities and 14% of people receiving Individual Protection Assistance were living with a disability. During the next year we will encourage more partners to disaggregate data by disability status and explore opportunities to overcome barriers to disabled people accessing assistance.

Cost Effectiveness and whether the programme continues to represent value for money.

The HARC modalities and design maximises cost effectiveness across the programme. Cash assistance is cheaper than in-kind assistance and is judged by recipients to be the preferred and most effective form or assistance, as verified by post distribution and TPM monitoring. It helps ensure flexibility to meet beneficiaries needs, and to restore and boost local markets and production. The emphasis on rapid response is of proven cost effectiveness in reducing further deterioration or the adoption of negative coping mechanisms. HARCs innovative funding water and sanitation infrastructure projects through SAFER, UNICEF and ICRC, are more cost-effective and sustainable methods of meeting needs than emergency modalities such as water trucking. Similarly, community prevention management of malnutrition is of proven cash effectiveness.

The programme is currently representing good value for money. It was able to scale up during the reporting period to deliver urgent assistance at a critical time for people in eastern DRC and works to improve the efficiency and effectiveness of the wider humanitarian system.

E: RISK

Overview of risk management

Risk appetite
HARC is consistent with the DRC Portfolio risk appetite, approved in January 2025. The programme (and portfolio) have a greater risk appetite than the FCDO Corporate risk appetite, given the operating context and likely positive return against risk for the FCDO.

FCDO continues to take a proactive and structured approach to risk management, ensuring that both strategic and operational risks are identified, monitored, and addressed through appropriate channels. Sanctions and other high-level risks have been effectively managed and escalated in line with established protocols. The risks associated with conflict escalation, increasing shortfalls in international humanitarian funding, and ensuring adequate programme management capacities have all been escalated and are monitored closely. This reflects the FCDO’s commitment to maintaining high standards of accountability, responsiveness, and resilience in a rapidly evolving global context.

Risk trends
The main implementation risks for the HARC programme include the deteriorating security situation in North and South Kivu, increased threats to humanitarian actors, and high staff turnover in partners, affecting Mercy Corps and Concern, which have struggled to retain key consortium staff. Access constraints and resource gaps also remain critical challenges.

In light of increased need and disruptions to partner operations, the programme team operates under the assumption that risks of aid diversion and safeguarding incidents remain high. The BEK team reinforced financial oversight through field visits, emphasising key compliance messages and strengthening financial reporting practices. Fraud awareness and reporting protocols were reiterated. Internal and external controls—including quarterly financial reviews, annual audit submissions, and fraud prevention systems—were consistently applied to mitigate risks of financial loss or diversion. A dedicated safeguarding visit to Goma in October 2024 examined partner controls and led to several recommendations to strengthen their approaches:
- IMPACT to conduct ex-poste assessments at distribution sites
- Partners to review functionality of reporting mechanisms
- Partners to adapt awareness raising on PSEA, ensuring language adapted to local context.
- Conduct deeper analysis on the impact of multipurpose cash assistance on SGBV risks.
- Greater proportion of budget allocation towards safeguarding mitigation
With the deteriorating security situation, certain partners have conducted rapid reviews of their reporting mechanisms. The FCDO programme team will review internal safeguarding controls to ensure minimum safeguarding standards are still in place, and activities still within the current risk appetite concentrating on functionality and confidentiality; survivor-centred response protocols; and regularity of safeguarding audits.

M23 has been designated under the UN’s and UK’s sanctions regimes. Since January 2025 BEK has taken the following steps with all our relevant partners: 1) formal notification of the UK sanctions regime for DRC and associated requirements for aid organisations; 2) regular engagement with partners to ensure that they have undergone the necessary internal processes to fulfil their compliance responsibilities; and 3) a partner refresh of key programme management frameworks to ensure that sanctions risks remain within the FCDO risk appetite and are regularly monitored.

Risk management processes
Risk is managed on an ongoing basis as issues emerge and escalated to the Senior Responsible Officer as required, then escalated further as required in line with FCDO’s risk management policies. The programme team conducts quarterly reviews of the risk register. Partners report on risk through regular communications with the programme team and through their quarterly reports. Risk is discussed with partners at quarterly project meetings and ad hoc partner consultations.

Climate risk
In line with our Paris Agreement commitment, the HARC business case identified the programme’s level of climate risk as moderate. By supporting the most vulnerable households to improve their ability to cope and manage their natural resources we will increase their resilience to future climate impacts.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Across the portfolio, delivery partners demonstrated strong commitment to humanitarian outcomes in a highly volatile and resource-constrained environment. Most partners adapted effectively to operational challenges, including insecurity, access constraints, and staff turnover. Financial performance was generally sound, with improvements in reporting quality and responsiveness to FCDO oversight. Flexibility was a key strength, particularly in response to the evolving crisis in eastern DRC and the implications of MONUSCO’s withdrawal from South Kivu.
- ICRC delivered consistently high-quality assistance, reaching hard-to-access areas. BEK provided £11.6 million in 2024, with funding scaled up in response to worsening needs.
- SAFER, led by Mercy Corps, received £18.5m from HARC in financial year 2024/25. It significantly improved financial reporting and responsiveness. Despite leadership turnover and access issues, the consortium-maintained delivery momentum and adapted well.
- WFP achieved strong value for money, with 69% of its £20m budget in 2024/25 being delivered as cash assistance to beneficiaries.
- UNICEF received £3m for its cholera response. The original 3-month contribution was extended by an additional month to fully utilise the contribution. A further contribution was made for water infrastructure, to be reported on in the next Annual Review.
- EAST, led by Concern Worldwide, had a delayed start but is now delivering effectively following initial coordination and mobilisation challenges, as discussed above. It spent £12.6m in FY 24/25.
- Standby Partnerships provided critical surge capacity to the humanitarian response. HARC funded the following roles:
  - Sexual and Gender Based Violence Sub-Cluster Co-ordinator (UNFPA): Strengthened co-ordination and advocacy on gender-based violence, supporting the UK-led Call to Action initiative.
  - Civilian-Military Coordinator (WFP): Facilitated co-ordination between WFP and security and military forces to enable unimpeded delivery of humanitarian assistance. This was particularly essential during MONUSCO’s withdrawal form parts of eastern DRC.
  - Rapid Response Mechanism Co-ordinator (OCHA): Improved rapid response systems by developing alert tools and enhancing inter-agency co-ordination.
- UNHAS remained a vital enabler of humanitarian access, transporting over 44,000 passengers and nearly 600 tonnes of cargo. Through an almost £4m contribution from HARC, it maintained cost-effective operations.
- UNFPA began implementation of its SRHR programme in late 2024, aiming to reach 200,000 women and girls with essential services; while delivery is still in early stages, the team has shown flexibility and responsiveness to FCDO recommendations, with a full performance review planned for the next Annual Review.
- IMPACT provided independent third-party monitoring across multiple partners, offering timely insights, practical recommendations, and ‘flash’ safeguarding and fraud reports where issues were identified.
Due Diligence assessments
All partners under the HARC programme’s humanitarian portfolio have undergone Due Diligence Assessments (DDAs), evaluating their capacity and capability with respect to governance, financial stability, programme delivery, downstream partner management, and safeguarding. An action plan is in place to monitor progress against identified findings and recommendations.
In 2024, the programme team refreshed DDAs for Mercy Corps (SAFER), IMPACT, and WFP. Additionally, delivery chain maps have been developed for each partner—or for each intervention where delivery chains vary by location or activity—ensuring clear visibility and accountability throughout the implementation process.
Asset management

The HARC funded assets within SAFER, EAST and IMPACT components. Partners provided updated asset inventories through their annual reports. They are also informed of the mandatory requirement to inform FCDO of any plans to procure new assets. In June 2024, BEK staff undertook a physical asset inventory for SAFER and recommendations have been made to the partner. As most EAST consortium members had only recently begun procuring assets at the time of the visit, the BEK team did not undertake an inventory for the project.

Financial performance

The HARC budget increased during the period under review as a result of the two Business Case Addendums. The Foreign Secretary announced £14.6m in additional humanitarian funding for eastern DRC following the expansion of M23 control from January 2025. As a result, HARC spent £32.5m in FY 23/24 and £83.6m in 2024/25.

Most of partners have managed finances with rigor and with good monitoring and adaptive capability and highlighting possible reprogramming in good time to allow reviews, discussions, and approvals for any changes in the short period the project was implemented. Financial reports were submitted in a timely manner by all implementing partners. Each report was carefully scrutinised, with the team assessing financial management capacity by analysing the ratio of actual expenditure to forecasted budgets, alongside the implementation status of planned activities. Overall, the programme has spent in line with budget and forecasts over the past year, with the exception of the EAST project which underspent against its forecasts due to delays in implementation discussed above. As project implementation is now fully underway, financial accuracy has improved as well.

Fraud and Safeguarding

FFCDO systematically collaborates with partners, strengthening their ability to identify, prevent, and respond to safeguarding and fraud concerns more effectively. Through rigorous due diligence processes, regular reviews of safeguarding and fraud reports, and proactive engagement such as Safeguarding Week and field visits, the FCDO has fostered a culture of continuous learning and accountability. These efforts have enhanced transparency whilst empowering partners to implement stronger safeguarding measures. Through joint initiatives, training programs, and open dialogue, the FCDO has ensured that safeguarding is not only a priority but a shared responsibility, creating safer, more resilient programmes.

G: MONITORING, EVIDENCE AND LEARNING

Third Party Monitoring

HARC funds IMPACT to provide third party monitoring of its delivery partners. 19 assessments were conducted in the reporting period, of which 7 were of SAFER, 7 of WFP and 5 of EAST. The 5 EAST visits were to collect baseline data for an evaluation of EAST’s livelihoods activities. The remainder were verification of partners’ registration of beneficiaries and delivery of assistance. During the reporting period IMPACT changed its approach and now conducts visits of beneficiary registration, in addition to its previous monitoring of distribution. This provides useful insights into both processes. Lessons learned workshops were conducted with SAFER and EAST, looking at the findings of all visits to date. Their findings will be discussed in the next Annual Review.

Evidence and Learning

All HARC projects are designed using the best available evidence, as set out in the Business Case, drawing on robust needs assessments and proven response modalities, for example the SAFER rapid response mechanism and cash assistance through WFP. Implementing partners are required to integrate monitoring and evaluation into their delivery, contributing to a broader evidence base on programme effectiveness through regular reporting and independent third-party monitoring. A key focus in the coming year will be the assessment of resilience programming, with IMPACT undertaking baseline and mid-term data collection of the EAST consortium’s activities to inform delivery. UK support to IMPACT/REACH has further strengthened system-wide evidence generation, enabling more refined and co-ordinated prioritisation across the humanitarian response in DRC. These efforts ensure that UK-funded interventions remain responsive, accountable, and strategically aligned with the needs of affected populations.

Date of last narrative financial report	SAFER: 22 January 2025 / ICRC: 30 June 2025 / WFP: 22 May 2025 / EAST: 2 May 2025 / UNICEF: / Emergency Cholera Response: 30 July 2024 / WASH: 1 July 2025 / UNFPA: 14 April 2025IMPACT: 25 April 2025	Date of last audited annual statement	SAFER: 8 November 2024 / ICRC: / WFP: 10 June 2025 / EAST (Concern): 9 April 2025 / UNICEF: 13 May 2024 / UNFPA: N/A / IMPACT: 26 June 2024

.