## Annual Review

Title: Ukraine Good Governance Programme
Programme Value £ (full life): £38m		Review date: 1/04/23 – 31/03/25
Programme Code: 301455	AMP start date: 10/03/22	AMP end date: 31/03/26

Summary of Programme Performance
Year	1 - 12/2022	2 - 12/2023	3 - 03/25
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	D0003120.odt
DevTracker Link to results framework:	D0004764.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Ukraine Good Governance Fund (GGF) is a British Embassy Kyiv (BEK) programme (2022-26, up to £38m) designed to support Ukraine’s reforms through a mix of targeted technical support to the Government of Ukraine (GoU) delivered through a technical assistance contract (Managed Fund), and a series of accountable grants/MoUs through international and Ukrainian NGOs in priority governance reform areas.
[note] TA under GGF has been focused on research, strategy development and provision of specialist technical expertise to track and support policies changes and reforms across key sectors that are priorities for GoU. We have also facilitated technical advisory support to SMEs and research institutions, technical support for preparation of investment projects for war-affected communities, and technical advice on legislation and procedural reforms.

GGF’s impact statement is to contribute towards ‘an open and resilient and democratic Ukraine with stronger rule of law, more effective, transparent, and accountable institutions, and an economy that is competitive and inclusive’. The programme builds on progress made under its predecessor –the regional Good Governance Fund– since 2014 and it was designed prior to Russia’s full-scale invasion of Ukraine in February 2022 but began work in April 2022 and therefore rapidly pivoted to support GoU’s most pressing war-related needs as long as they aligned with the programme’s agreed economic and governance reform mandate.

During the review periods, the programme delivered key results across GGF’s focus areas of judicial reform and anti-corruption, and economic inclusive policies. Examples include:

- Regional recovery: Updated the 2024-2027 State Regional Development Strategy, trained 200+ community representatives on designing recovery projects, developed regional recovery strategies for Dnipropetrovsk and Ivano Frankivsk regions. This workstream will transition to Triggering Investment, Growth and Economic Resilience (TIGER economic recovery) Programme.
- Business revitalisation: Developed the Online Entrepreneur’s Cabinet to be integrated into the Diia ecosystem, aggregating all state and donor-funded opportunities for SMEs, matching entrepreneurs with relevant grant, loan, or capacity-building opportunities. Developed the 2024-2027 SME Strategy adopted by the government of Ukraine in September 2024. This workstream will transition to TIGER (economic recovery) programme.
- Energy: Drafted, updated and extended the Ukraine Energy Strategy out to 2050 with an implementation roadmap. This workstream has transitioned to URES (energy stability) programme.
- Innovation: Drafted sectoral sections of the Win-Win Innovation Strategy adopted by GoU in January 2025. Developed a concept for the establishment of the Science Park of the Kyiv Aviation Institute. Parts of this workstream have transitioned to Governance Reform Programme (GRP).
- Judicial Integrity: Helped establish the Disciplinary Inspectors Service (DIS) of the High Council of Justice and to select its members on the basis of an open and merit-based competition. DIS are hearing complaints on judges’ integrity and applying disciplinary sanctions in an impartial and independent way, working their way through an extensive backlog. This workstream will transition to GRP.
- Anti-Corruption: Developed the databases and digital interfaces to support compensation mechanisms for war damage, facilitated cross-border traffic into the EU via e-queueing and digitalised licensing for seafarers, eliminating corruption opportunities. Launched the Local Government Integrity Alliance providing support to 75 local government entities in increasing transparency in governance and reconstruction. Key parts of this workstream will transition to GRP (governance reform)
- State Owned Enterprise Reform: Worked with GoU to develop and secure adoption of legislation on improved transfer and management of state property. Helped GoU operate the electronic auction system that enabled them to hold 882 successful auctions since November 2022, of which 47 were for SOEs. We will exit from this workstream.
The previous annual review (March 2023) was the second for the programme and focused on assessing GGF’s performance in the context of that rapid pivot and responsiveness to GoU asks. There have been a number of changes since that reflecting the challenging context that GGF continues to operate in:

- USAID Freeze and annual review delay: This Annual Review was delayed while the team dealt with the implications for governance programming of the USAID pause in January 2025 and subsequent cuts. For GGF projects that use the April-March FY, this has enabled us to extend the review to cover a second year of programming, using the AR to harvest recommendations to support the current year’s plans. For projects that use the (USAID) October – September FY, we will cover only one year to September 2024. As a result of the USAID freeze, payments to USAID’s State Owned Enterprise Reform Programme and ProIntegrity due in Jan/Feb 2025 were not released. USAID has now closed these programmes, along with the USAID Digital Transformation Activity.
- Programme extension: In November 2024 the programme was given a one year no-cost extension to 31 March 2026. This was intended to increase flexibility on timing for transitioning GGF elements to other programmes in the portfolio.
- Programme closure and transfer of initiatives: As new Ukraine FCDO bilateral ODA programmes have come online, it was decided in March 2025 to close GGF early. Closure timing will vary for different components, but the most significant change is closure of the Managed Fund by the end of June 2025. From January 2025, projects in GGF portfolio also began to move across into the Governance Reform Programme – while the exact timing was uncertain, the transition had been planned for some time.
For this third annual review we have focused on the relevance, impact, and value for money of GGF’s constituent projects. Given the decision on early closure, and the drive to maintain portfolio strategic coherence, this review also looks at lessons we can take into successor programmes and lays the foundations for the Programme Closure Review. For a mapping of the transition of GGF elements to other programmes, see Annex I.

For this reporting period, GGF comprised 6 outputs outlined below. We have been pragmatic in selecting the natural review period for each component to get the best data we can on delivery and impact. Also in this reporting period, on the basis of a recommendation made in last year’s Annual Review to take a different approach to GESI across GGF, we closed early our support to NDI on Promoting political & civic participation of Women & LGBTQ+ Communities. A detailed performance review was concluded at the time and, given the timing, it has not therefore been covered as part of this review.

Project	Implementing Partner/ modality	Output	Review period	Value for review period	% weighting /output score
UK-FY aligned programmes (April-March)
Managed Fund	Alinea & Abt Associates/ contracts	1	Apr23 – Mar25	£12m (£6m/year)	40%/A
Resilient Institutions, Society and Elections (RISE)	IFES (International Foundation for Electoral Systems)/AGA	2	Apr23 – Mar25	£4m (£2m/year)	20%/A+
Supporting judicial administration reform	IDLO (International Development Law Organisation)/MoU	3	April23 – Mar25	£0.7k (£0.35m/year)	5%/A
US-FY aligned programmes (October-September)
Pro-Integrity	DAI Global LLC/DCA through USAID	4	Jan24 - Sept24	£3.4m (9 months)	25%/A+
Digital Transformation Activity (DTA)	Eurasia Foundation/ DCA through USAID	5	Oct23 – Sept24	£0.5m* (year)	5%/B
State Owned Enterprise Reform Activity (SOERA)	Deloitte/ DCA through USAID	6	Oct23 – Sept24	£0.75m* (year)	5%/B

*Payments in arrears to SOERA (£1.5m) and DTA (£2m) not completed in Q4 FY24-25 due to USAID freeze

Summary supporting narrative for the overall score in this review
GGF has continued to perform at the level of A – met expectations. Individual components have delivered as intended, reflecting continuity on the governance reform side and careful selection of priorities on the Managed Fund side. The use of GGF has changed significantly over its lifetime. Year 1 (2022-23) was characterised by a fast-moving pivot to support Ukraine to sustain its reform efforts in the new context of the full-scale invasion. GGF’s broad mandate, flexible set-up and the fact that its Managed Fund was already active, all enabled it to respond at pace to new urgent asks from GoU, including helping set up an approach to macroeconomic forecasting in the war context, support to design components of the first WB-GoU Rapid Damage Needs Assessment (RDNA), and a range of time sensitive strategy development elements. Year 2 (2023-24) began as a period of consolidation but toward the end of the year and into Year 3 (2024-25) much more emphasis was put on targeted catalytic support for development of the Ukraine bilateral ODA portfolio, supporting key piloting and gathering of evidence, incubating components until ready to move to new programmes, working hard to ensure responsible exit and transition from key components, and refocusing on key initiatives intended to bolster other parts of the portfolio.

Examples of project incubation include technical assistance provided to the Ministry of Energy, including drafting the 2050 Energy Strategy and National Action Energy and Climate Plan for 2025-2030, which grew into a dedicated TA component under the URES energy programme. A number of other projects were launched and successfully continued by the Recovery and Economic Growth team, including FIRE, which continued GGF’s work on DREAM in public investment management, and TIGER, which is taking over the City UK project in its 3rd phase. Finally, the entire Governance and Reform Programme is a successor to successful GGF projects, including TAPAS/DTA and GGF’s rule of law work. GGF allowed to explore new areas for interventions, such as innovation and research, informing wider HMG’s approach and allowing to gather lessons learnt of programming in these novel areas.

All while not losing sight of GGF’s added value as a programme with a clear reputation for responsiveness to GoU asks. Externally, the pace of decision making has shifted too, and while the need for what GGF has to offer remains high, there is now more emphasis on strategy and planning rather than rapid response to a highly volatile external environment. As it is being closed down, all its elements are being carefully transitioned to other programmes (GRP/TIGER), and many elements allowed an exit altogether as they became self-sufficient (strategies for Ivano-Frankivsk and Dnipropetrovsk regions were adopted, with reform owners continuing the follow-up work).

The team’s task in Year 3 was complicated by uncertainty over longer-term programming, leading to several further in-year partial pivots and changes to the planned end-date for the programme, including a 1 year No Cost Extension to March 2026 followed soon after by the decision to close the Managed Fund from June 2025.

The resulting range of components in the review period has been vast but many workstreams have either already transitioned or are close to doing so, leaving the GGF in its final year (2025-26) focused on consolidating achievements, supporting the remaining transitions or exits from its various workstreams, and bringing its experiences to bear in supporting the wider UK portfolio in Ukraine.

Major lessons and recommendations for the year ahead

Some of the lessons and recommendations outlined below were identified early in the review period and are already in implementation. We have captured them here to document our decisions, to draw together lessons for future programmes delivering in an uncertain or rapidly changing context, and to provide a basis for the Programme Closure Review. Lessons will be shared with BEK at the Post Programme Board in June 2025 so that other programmes can learn from GGF.

Lesson 1: Plan early for succession/exit: For smooth transition, plan for programme closure and clearly delineate mandates between different programmes, especially where there is not a single “successor” programme.

GGF has delivered a huge amount of appreciated and impactful work across a range of areas and the decision to close by June 2025 reflected confidence that new programmes were now in place to pick up key GGF components in ways that would support more in-depth, strategic approaches. Programme closure planning for the GGF’s flagship Managed Fund began formally in March 2025 but GGF teams have been working steadily to prepare for transition of elements to new stand-alone programmes since even before they began to come online in 2024, and by January 2025 had already hived off substantial reform programming in anti-corruption, judicial reform and state owned enterprise reform into the new Governance Reform Programme.

Having an increasingly clear plan for programming after GGF helped us target either to areas where we were confident we would continue to invest, or to carrying out scoping for areas of interest for new programmes. In a few areas less certain trajectories or inconsistency in understanding across the wider team led to overenthusiastic promises or even to reversal of decisions already communicated, with associated reputational/relationship risks.

Lesson 2: Avoid dependency on implementing partners for key relationships with government counterparts – the FCDO should have a consistent role and independent channels of communication

A key question in GGF’s succession planning was around whether the UK could remain sufficiently responsive to GoU requests without GGF’s flexible resource, and whether this would in turn affect UK relationships with GoU. After discussions with beneficiaries and programmes across the Embassy, it was agreed that BEK would be able to remain responsive to all key GoU stakeholders through new programmes. However it was also noted that the GGF’s Managed Fund configuration coupled with staffing shortages and limited in-country access had led to overreliance on implementing partners for key relationships with Gou counterparts. It was also agreed that shifting key BEK-GoU relationships over to programmes with clearer thematic focus and the right advisory expertise would help BEK engage more directly with GoU on shaping work on areas of mutual interest/priority, and would increase our ability to shape programming and make more strategic decisions without undermining our responsiveness to GoU asks.

Recommendation 1: GGF SRO should consider how best to share relevant learning for a programme of such diversity (GGF SRO should use the June PPB and plans for a closing event on lessons learning to ensure sharing of lessons and should ensure that the PCR is commissioned in a way that will gather and disseminate relevant learning): In the final phase of GGF it will be important to work closely with other programmes and teams across the FCDO, within the donor community in Ukraine, with GoU, and with CSOs and other Ukrainian organisations, to pass on learning, relationships and knowledge. The programme should focus on drawing out and sharing its relevant lessons to support the fast evolving Ukraine bilateral ODA portfolio, and will have additional relevance globally for teams operating in a fast changing fragile/conflict context and/or thinking about managing a major programme pivot. The broad range of areas covered by GGF across its history and still into its final year increases the challenge for the team to share learning effectively, and also risks reinforcing the perception of GGF as a flexible funding mechanism rather than a programme that has been used strategically for a key period and is now handing over the baton.

Recommendation 2: Sustainability, impact, and VfM should be key considerations for future Technical Assistance. The PCR should further analyse how best to do this, and disseminate learnings to other TA programmes within the BEK Portfolio (by the completion of the PCR): MF performance has been very consistent but with hindsight, some outputs lack ambition on sustainability, which is generally reliant on GoU ability to implement strategies and policies, and on securing funding for follow-up to pilots. There is huge potential for catalytic impact but some elements of programme design (notably annual project cycles) and the level of ambition set do not lend themselves to driving or tracking longer-term impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Good Governance Fund aims to help Ukraine become a resilient country with effective and transparent institutions and competitive and rules-based economy. It seeks to achieve this through three workstreams: judicial reform and anti-corruption measures, economic inclusive policies, civic participation and civil society. These efforts are mutually reinforcing, contributing to a positive cycle of government accountability to citizens and enforcement of economic rules by strengthened institutions.

See Annex A for the GGF Programme Map and Annex B for the GGF Theory of Change.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

GGF is on track for expected outcomes and impact. Across each of the outputs there are examples of GGF projects directly supporting the government to deepen understanding of international best practice, draft strategies/reforms/legislation, and implement them to see reform embedded into the GoU. The breadth of support and delivery is impressive.

In light of the challenging operating context, we adjusted our ambition and timelines in 2022 and we continue to review and refresh every time we bring a new initiative online. Rather than change the ToC (which broadly holds) this change is reflected in the indicators and milestones we are reporting against, some of which are more modest than they might otherwise have been. In other areas (e.g. some of our reform agendas) we have been able to achieve significantly more than we might have done in a pre-full scale invasion context, drawing on the windows of opportunity opened up by EU Accession and IMF conditionalities, the Ukraine Plan, and US conditionality and dependence on donor funding.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Individual GGF components demonstrably add value and the team has been rigorous in selection of priorities, balancing poverty reduction, country plan, and relationship interests and paying attention to feasibility and windows of opportunity. However GGF has struggled to become more than the sum of its parts so to improve VfM and future impact it makes sense for GGF to close as early as feasible and shift key workstreams into more specialist programmes. We cannot afford to have gaps in delivery against any of the three pillars of the Theory of Change given key relationships and the relationship between GGF work and the wider portfolio so we will continue with GGF until all elements are successfully transitioned. The last of these is likely to be work on elections/democracy.

## C. DETAILED OUTPUT SCORING

Output Title	GGF Managed Fund
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	Yes - down

Due to the timing of GGF’s Annual Reviews (March 2024 and June 2025), reporting under this Output covers a full two year period from April 2023 to March 2025. Spend over that period was £12m

The Managed Fund (MF) Technical Assistance component, implemented by Portfolio Management Unit operated by Alinea and the Technical Assistance Facility operated by Abt Global, supports GoU by running a series of individually identified economic and governance reform projects that respond to opportunities for reform or unblocking progress on reform that will benefit Ukraine. The MF provides rapid, responsive, catalytic support that is intended to pave the way for other donors, actors, and GoU to build sustainable solutions. Each of the projects delivered by the MF –of which there were 5 in this reporting period– have their own Results Framework. The key results have been compiled into the MF Results Framework – see Annex C.

Briefly describe the output’s activities and provide supporting narrative for the score.

The Managed Fund demonstrated good delivery across all indicators, maintaining its consistent performance as a reliable mechanism to provide:

1. High quality technical assistance to support the GoU in defining strategic frameworks for the country’s economic recovery for years to come.
2. Initiating pilot projects to support practical implementation of the policy documents it designed and sharing best practice.
3. Continuing to build and maintain strong relationships across government, enabling GGF to identify and respond to requests flexibly.
The 7 projects delivered by the Managed Fund are described below along with the headline assessment of their performance against output indicators:

MF Project	FY23-24	FY24-25
Business Revitalisation: Support private sector-led recovery, improve SME support policies, strengthen the Export and Entrepreneurship Promotion Office under the Cabinet of Ministers of Ukraine and upscale programmes to help businesses maintain their operations and boost exports. Identify the challenges and needs of women entrepreneurs provide tailored training and support.	Spend: £1.3m / Key results: / • Developed the 2024-2027 SME Strategy; / • Developed the concept of the Syhnivka Industrial Park (Lviv region). / • A - Output met expectations.	Spend: £0.83m / Key results: / • Developed the Online Entrepreneur’s Cabinet aggregating all state and donor-funded opportunities for SMEs, matching entrepreneurs with relevant grant, loan, or capacity-building opportunities, to be integrated into the Diia ecosystem. / • Export promotion to Poland for 50 Ukrainian SMEs. / A - Output met expectations
Inclusive Economy: Technical assistance, including policy advice, research, needs identification, and capacity-building to support gender equality, inclusion, integration of vulnerable groups (women, veterans) into the labour market	Previously part of Business Revitalisation	Spend: £0.74m / Key results: / • Entrepreneurship training for 250 women, career guidance for 40 veterans. / • Policy-oriented research on gender gap in labour market and entrepreneurship. / • A - Output met expectations
Economic Hub: Technical assistance in fiscal policy and public finance management, including the Ukraine Plan development, macroeconomic forecasting, policy evaluation, and recommendations to sustain economic resilience amidst war pressures, and enhancing transparency and efficiency in financial institutions.	Spend: £1.1m / Key results: / • 12 sectors were prioritised for sectoral strategies and endorsed by Ministry of Economy. / • A - Output met expectations.	Spend: £0.88m / Key results: / • Monitored investment indicators and reporting under the EU’s Ukraine Plan, which unlocked billions in EU funding – provided bridging support until EU support could come online. / • Closed tax loopholes through new legislation that brought £270 million in additional revenues to Ukraine’s budget. / • A - Output met expectations
City UK: / Technical assistance aimed at unlocking private sector investment, including the reform of the investment promotion agency, improving business regulatory environment, financial ecosystem, and capital markets	Previously part of the Economic Hub	Spend: £0.5m / Key results: / • Developed a concept for reforming Ukraine’s investment promotion agency. / • Trained 25 civil servants from across GoU on investment promotion in Cambridge / • A - Output met expectations
Regional Recovery: Advisory and coordination support to the Ministry for Communities and Territories Development to update the State Regional Development Strategy and the Transport Strategy, support to local communities on developing recovery plans and designing projects and concepts for recovery projects.	Spend: £0.99m / Key results: / • Drafted the updated version of the Regional Development Strategy / • Drafted the Kyiv City recovery framework, recovery frameworks for 10 hromadas, and 4 regions. / • Trained 200+ community representatives in designing recovery projects / • A - Output met expectations.	Spend: £0.8m / Key results: / • Developed economic strategies for Dnipropetrovsk and Ivano Frankivsk regions. / • Developed recovery strategies and investment projects for 5 communities in the South, East, North, and Centre of Ukraine. / • Provided training to 150 entrepreneurs and management consulting advice to 10 SMEs from regions. / • A - Output met expectations
RePower Ukraine: Expert support to develop the Energy Strategy of Ukraine 2050 and implementation roadmap, and 3 feasibility studies for investment-ready projects in renewable energy sectors.	Spend: £0.42m / Key results: / • Updated Energy Strategy 2050 implementation roadmap, and four feasibility studies in renewable energy. / • A - Output met expectations.	Transition of work to URES
Innovation Ecosystem: Support for Ukraine’s innovation promotion policy, including the 2030 Innovation Strategy of Ukraine, developing business-enabling regulations and policy measures to boost innovations and the development of innovative sectors of economy, increase synergies between research, higher education institutions and private sector	Spend: £0.45m / Key results: / • Contributed to the preparation of the Win-Win Innovation Strategy by developing sector specific reports for three sectors and providing policy recommendations / • A - Output met expectations.	Spend: £1m / Key results: / • Developed a concept and a communication strategy for launching the science park of the Kyiv Aviation Institute. / • Helped develop 7 sectoral innovation strategies (GreenTech, HealthTech, AI, etc.) / • A - Output met expectations

MF performance has been consistent, with only few initiatives missing significant milestones or significantly exceeding expectations. With hindsight, some outputs lack ambition on sustainability, which is generally reliant on GoU ability to implement strategies and policies, and on securing funding for follow-up to pilots. There is huge potential for catalytic impact but some elements of programme design (notably annual project cycles) and the level of ambition set do not lend themselves to driving or tracking longer-term impact. Sustainability and impact should be key considerations for future Technical Assistance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While a number of change requests were submitted by the Managed Fund to the FCDO in FY23/24, they did not materially change the scope of work or budget and output indicators did not change materially over the reviewed period.

As MF indicators are set by project there are no changes specifically triggered by this review but we anticipate adding an indicator to the GGF results framework for the coming year that will capture MF closure.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Status
The overall results framework for the MF should be discontinued and individual results frameworks for the different projects used for assessment.	Done
More focus on the effects of MF inputs to help tell the story of the MF impact, perhaps through quarterly outcome change stories.	Partially done. MF has produced good comms examples of its work, which have been amplified by Ministries, but these are usually activity- rather than impact-based. This reflects wider limitations to the MF results framework.

Lessons:
1. The GGF team at BEK should ensure they communicate the lesson that future TA should focus more on sustainability, feasibility, and scale of impact, reflecting this in the targeting of activities, results frameworks, MEL, and comms. (to share learning in June 2025 Post Programme Board).
2. Future BEK TA should ensure that it implements in close coordination with other donors’ technical assistance projects, as well as with other UK-funded projects. (to share learning in June 2025 Post Programme Board).
3. The FCDO should play a role in the relationships with GoU consistently, where we can help support the sustainability of the impact and coordination. (to share learning in June 2025 Post Programme Board).
4. The GGF team should ensure the results framework strikes a better balance between quantitative and qualitative indicators, moving beyond activity-based reporting toward assessing quality/relevance/likelihood to make real-life impact. (to share learning in June 2025 Post Programme Board, and to implement within Q1 for final phase of GGF).
5. Programmes with significant digital spend, which is likely in actively digitalising countries such as Ukraine, should engage early on the Spend Control Assurance Team and seek guidance on the implementers’ compliance with FCDO’s Digital Spend rules and Technology Code of Practice. (to share learning in June 2025 Post Programme Board)

Output Title	Resilient Institutions, Society and Elections (RISE) (IFES)
Output number:		2	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	Yes - down

Due to the timing of GGF’s Annual Reviews (March 2024 and June 2025), reporting under this Output covers a full two year period from January 2023 to December 2024. Spend over that period was £4m.

Briefly describe the output’s activities and provide supporting narrative for the score

The Resilient institutions, Society and Elections project (RISE) is a three-year £5.55m project that contributes towards making Ukraine's electoral processes more effective, inclusive and resilient, with a focus on pressing developments around elections and political processes in Ukraine as the war has progressed. RISE is implemented by IFES and began in June 2022. IFES delivered across 3 Outcomes. See Annex D for the detailed output table.

IFES Workstream	FY23-24 (A)	FY24-25 (A+)
1. Ukraine’s election administration has strengthened skills, tools, and capacity to administer elections utilising the reformed legal framework.	Key results: / • District Distribution Modelling study, for internal and external voter displacement completed May, 2023 to inform electoral modification needs. / • Roadmap for Electoral Reform in Ukraine – 2023 Wartime Edition jointly presented by IFES and OPORA in Oct. 2023; / • Needs Assessment of Civic and Political Rights for Veterans with Disabilities study presented in Oct. 2023 / • MoC between IFES and the Ministry of Digital Transformation in November 2023 to strengthen Ukraine’s cybersecurity and digital transformation, assisting the Ministry of Digital Transformation protecting citizen data; / • Webinar series for 580 State Voter Register representatives on cybersecurity and tackling disinformation on social media in Nov.-Dec.2023 / • Trainings on Cybersecurity and Disinformation to prepare the Central Election Commission (CEC) to combat Russian disinformation in post-war elections conducted in Sep. 2023 with 49 CEC representatives (27 women; 22 men); / • A- Outputs met expectations.	Key results: / • Out-of-Country Voting (OCV) Roadmap Research findings presented CEC in May 2024; / • Policy paper published on Adapting EU AI Regulations for Electoral Processes: A Path for Ukraine in cooperation with the NGO Institute of Innovative Governance (IIG) in Sep.2024; / • The civil society Working Group on Postwar Elections (includes CPLR, OPORA, and IFES) finalised Part II of the White Book on Preparing and Conducting Postwar Elections in Nov.2024. / • IFES presented its Crisis Communication and Combating Disinformation Playbook for election management bodies to the CEC Oct.2024 / • A+ – Outputs moderately exceeded expectations
2. Ukrainians, particularly those from historically excluded populations, have better access to and are more engaged in the political and electoral process.	Key results: / • All Ukrainian Forum for Civic Educators held in May 2023 to facilitate dialogue among civic educators 39 educators (27 women; 12 men) / • A discussion and CSO statement in September 2023 on the risks of elections being held in Ukraine during all-out war; support for the 7th Ukrainian Women’s Congress including a panel discussion on political participation of Women, in November 2023; / • Opening of the Center of Electoral Law Yaroslav Mudryi National Law University, Kharkiv on Dec. 2023. established through a subaward to the All-Ukrainian Civic Network OPORA at the beginning of 2022. / • A - Outputs met expectations.	Key results: / • IFES Assessment on the Needs of Veterans with Disabilities in Ukraine presented and launched Programme for Veterans with Disabilities at the Western Rehabilitation Centre in Yavoriv, Lviv Oblast in Apr. 2024; / • Launched the first part of the “Leadership in Times of War” - Leadership Programme for Internally Displaced Women Apr.2024; / • IFES civic education course “Democracy: From Theory to Practice” in universities and vocational schools in Sep.2024 / A+ – Outputs moderately exceeded expectations
3. Systematic efforts by civil society, official institutions, and legal and political stakeholders to identify and address gaps in political finance and electoral justice systems are increased.	Key results: / • Strategy support for the National Agency on Corruption Prevention (NACP) Department for Building Integrity in Political Finance in April 2023; / • Dispute Resolution Course: university course on “Electoral Disputes Resolution” to CEC representatives Apr. 2023; / • Political Finance Training for Judges: regional training on adjudicating political finance cases for active judges (13 women; 5 men) from northern Ukrainian regions organised on Nov. 2023 in cooperation with the National School of Judges (NSJ) / • B- Outputs moderately did not meet expectations.	Key results: / • Training for Journalists on Investigation and Analytics in Political Party Finance in June 2024 (18 participants - 14 women; 4 men) from national and regional media outlets across Ukraine); / • Training Initiative with the National School of Judges (NSJ): conducted between April 23-May 25). The events gathered 40 participants for interactive training / • First conference of the European Network for Oversight and Regulation of Political Contributions and Expenditure (ENFORCE) Dec.2024 with 37 representatives from 16 countries, including 14 representatives of the NACP and CEC. / A+ – Outputs moderately exceeded expectations

Overall, we are happy with IFES’s work. The UK has been supporting IFES in Ukraine since 2016. The organisation has demonstrable expertise on elections, including in countries that have had post-conflict elections and required out of country voting arrangements. In addition to broader institutional knowledge, they draw in national expertise and make effective use of it, while also balancing direct support to the Government of Ukraine and carrying out supportive work on inclusion and political engagement of vulnerable populations.

IFES works to an ambitious set of broad-ranging targets. In FY23-24 they largely met expectations, receiving an A, and in FY24-25 they received an A+. A couple of areas were below expectations, including viewership of informational campaigns and capacity building to electoral justice actors, but others significantly exceeded expectations, reflecting the challenges, uncertainty and fast-moving politics in Ukraine’s democracy space – and the range of areas exceeding expectations increased into FY24-25.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Our grant agreement with IFES –and the accompanying workplans, budgets and results– were updated in March 2025 to provide additional support to both IFES and its key downstream partner OPORA when USAID funding to them was frozen and then cut in order to continue delivery of key UK objectives. The interim arrangement was extended to June 2025 and discussions are now underway about plans for the rest of FY25-26 with both IFES and OPORA. Revised plans will review VfM, take into account any relevant political changes and ensure reporting is directly aligned with FCDO processes now USAID is no longer a partner.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Status
Light-touch revision of the results framework to a) get a better balance between quantitative and qualitative indicators (too often the number of processes are being counted, rather than their quality or effectiveness) and b) to move beyond disaggregated gender data to capturing more effectively the how men and women, boys and girls benefit from the activities undertaken.	Not done: Not taken forward formally by the GGF team but we note significant improvement in reporting quality between the first and second year of this reporting period. The team has also updated its approach to tracking progress on AR recommendations.

Recommendations and Lessons
1. FCDO to seek clarity on donor initiatives and reporting: IFES has had a successful partnership with several donors alongside the UK (including USAID and Canada), with good quality reporting that has met FCDO requirements. However, joint reporting has made it difficult to distinguish between donor activity and related results. As USAID is no longer a funding partner, looking ahead to future donor engagement, it will be important to agree clarity and coordination between donors so that we are able to track results, VfM and priorities, while benefitting from joint engagement. (by July 2025).
2. FCDO should ensure periodic engagement with downstream partners: IFES works successfully with a number of downstream partners and NGOs, which has strengthened UK engagement and brought Ukrainian experience, expertise and voices into UK programming. To further strengthen this, particularly in a time of heightened pressure on elections, it is recommended to create more regular partners-FCDO engagement. FCDO will also set up a separate AGA with a Ukrainian NGO to support elections monitoring and oversight and to benefit from Ukrainian expertise and regional presence (by September 2025).
3. FCDO to engage regularly with Central Election Commission: IFES currently works directly with the CEC, where they support capacity building, reform work and support on issues including voter registration. To further support Ukraine’s administrative capacity and reforms on election preparations and given the significance and pressure on Ukraine’s first post-war elections, it is recommended that the FCDO meet directly with the CEC on a regular basis to continually review priorities and support (July 2025).

Output Title	IDLO - Building Institutional Capacities of the Reformed Judicial Administration Bodies in Ukraine
Output number:		3	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	No

In July 2023 GGF began a new project with IDLO that built on a previous phase of GGF support to IDLO that concluded in March 2025. The focus remains on strengthening the transparency and accountability of Ukrainian judiciary and improving the efficiency of adjudication in Ukrainian courts of law.

Due to the timing of GGF’s Annual Reviews (March 2024 and June 2025), reporting under this Output covers the period from the beginning of the new agreement in July 2023 to March 2025. Spend over that period was c.£0.7m.

Briefly describe the output’s activities and provide supporting narrative for the score.
Our support to IDLO is driven by the principle that a more transparent, apolitical and accountable judiciary will have a positive effect on systemic corruption and will help rebuild public trust in justice sector institutions and the government more broadly. It is also likely to have a positive effect on investor confidence. The project is founded upon recommendations made by the Council of Europe’s European Commission for Democracy through Law (the Venice Commission) to assign international members of the Selection Commission and the Ethics Council a meaningful role in the selection/vetting process and to provide international experts with a prevailing vote in case of a tie vote. These recommendations were accepted and adopted by the Ukrainian Parliament. It works most closely with the two entities that govern Ukraine’s judicial administration system: the High Qualification Commission of Judges (HQCJ) and the High Council of Justice (HCJ), focusing in particular on provision of international support for selection and vetting of judges, efforts to fill vacant positions for judges and support for Disciplinary Inspectors to clear the extensive backlog of complaints cases against judges.

Over the reporting period, IDLO made progress towards all outcomes, working both independently and in close cooperation with the EU ‘Pravo-Justice’ project and the USAID ‘Justice for All’ project. See Annex E for the detailed output table. Key achievements in this period were:

Workstream	FY23-24 (July-Mar)	FY24-25
Legal frameworks and Selection	• Produced legal memoranda on optimisation of judicial selection and appointment as well as qualification assessment, re-launch of the Public Integrity Council (PIC), and establishment of the High Council of Justice (HCJ) Disciplinary Inspectors’ Service (DIS). / • Helped establish a new system of transparent sanctioning of judges by facilitating the work of the Selection Commission aimed at conducting a transparent and merit-based competition for vacant leadership and other positions in the DIS.	• Assisted the HQCJ with the development of the concept for the competition to first instance courts. / • In cooperation with the National School of Judges (NSJ), IDLO contractors (independent experts) produced 300 test questions on the History of the Ukrainian Statehood for judicial competitions. / • Finalized the ToRs for the customisation of a digital platform to administer multiple-choice tests for judgeship competitions and qualification assessments. / • Contributed to the development of a plan to reorganise the Public Integrity Council (PIC) and improve its business processes and overall performance.
Disciplinary Inspectors Service (DIS)	• Following the adoption of legislation that restored the disciplinary function of the HCJ, supported the HCJ with establishment and operationalisation of a hybrid (national-international) DIS Selection Commission. / • Drafted Regulation and Rules of Procedure of the DIS Selection Commission, together with the EU “Pravo-Justice” and USAID “Justice for All” projects.	• Following an open and merit-based competition and appointment of 21 disciplinary inspectors, the new Service of Disciplinary Inspectors (SDI) of the High Council of Justice (HCJ) was operationalised and began work. / • At SDI’s request, provided training on international standards on judicial ethics and conduct, as well as gender equality and social inclusion (see below).
GESI	• Thematic reviews on gender equality and social inclusion completed and improvement recommendations produced.	• Organized and conducted a two (2)-day workshop on the Bangalore Principles of Judicial Conduct and Gender Equality, Disability and Social Inclusion (GEDSI) for SDI inspectors. / • Organized an online workshop on the Bangalore Principles of Judicial Conduct and GEDSI for the PIC.

Overall we have been satisfied with IDLO’s work. IDLO occupies a clear niche between EU and USAID judicial reform efforts and coordinates well with all other major stakeholders – including Ukrainian NGOs. It engages with sensitivity on politically sensitive issues and is generally a trusted partner for key counterpart/beneficiaries which positions it well to provide advice and inject comparative global perspectives and expertise. It has continued to make incremental progress despite significant resistance in some areas. In addition, we are pleased to see that IDLO has clearly taken on board lessons from the previous phase (notably on gender perspectives).

Ambition was set high for IDLO’s work. At the point of project launch the HQCJ had been fully renewed and HCJ was 75% renewed but we underestimated the challenges of restarting work after 4 years of being non-operational and progress was later slowed down back by obstacles including an investigation that alleged corruption in judicial appointments, by the process of securing longer-term buy-in for recommendations (in a context of differing views), and by leadership changes. As a result, and because of our selection of indicators and milestones, the review assessment of results does not capture IDLO’s work effectively, and IDLO has scored a B.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made during the year. IDLO’s work under this project concluded in March 2025, so this output will not be active next year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Status
Bring in expertise on best practice to understand some of the gendered barriers to entry to the justice sector, and how these have been overcome in other programmes.	Done: A thematic review was carried out in close collaboration with FCDO on gender equality and social inclusion in the project. This was followed by GESI-focused trainings linked to broader ethics training.

Lessons/Recommendations
1. FCDO to be clearer about IDLO’s tasking vs joint work with other initiatives: It is a strength of the project that the IDLO has been able to work closely with the EU and USAID projects in this same space, whilst retaining its own voice, but at times it has been challenging to clearly define responsibility and therefore also VfM for the UK. IDLO’s work under this GGF project concluded in March 2025 and the donor landscape has changed significantly with the closure of USAID’s Justice for All project in early 2025, creating concerns about significant gaps in critical work but also making it easier for IDLO and the EU’s Pravo-Justice both to deconflict and to cooperate effectively. (August 2025)
2. Revise our results tracking approach: With hindsight, the output assessment framework we developed and the indicators we selected for assessment were insufficiently within IDLO’s gift and overdependent on reform beneficiaries' uptake. Delays to key processes have had a significant negative impact on the assessment. As we anticipate working with IDLO under the Governance Reform Programme in future, we will take away the recommendation to review the limitations of the current approach and look for a way to retain ambition (and avoid activity-driven assessment) but with more recognition of the complex policy environment IDLO operates in. More regular review of indicators and milestones should be an important part of our process. (August 2025)

Output Title	ProIntegrity
Output number:		4	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	Yes - up

The review for this output runs from January 2024 (ProIntegrity start date) to September 2024 in line with the USAID reporting year. Spend over this period was £3.4m

Promoting Integrity in the Public Sector Activity (ProIntegrity) was set up as a 5-year programme equally co-funded and co-branded by USAID and the UK and implemented by DAI Global. The project was designed to be a comprehensive response to anti-corruption needs in the resilience, recovery and reconstruction landscape, working to strengthen national level anti-corruption institutional capacity, strengthen anti-corruption compliance and control in local governance, and advance transparency and accountability in recovery and reconstruction. We played an active role in co-design and in shaping its workplans. Prointegrity began work in January 2024 until its freeze and then closure by USAID in January/February 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.
As the review period was the first year of the project's operation, ProIntegrity focused on set-up including registering and recruiting staff, identifying civil society partners and establishing key working relationships with counterparts and interlocutors. See Annex F for detailed Output scoring.

Workstream	FY24-25 (Jan-Sept 2024)
Set-up	• Initial contract deliverables (MEL plan, workplan, GESI strategy, communications strategy) were all developed and finalised jointly with USAID and the UK. / • Pivoted to respond to some emerging needs including increased focus on analysis and research into customs system reform, and support to Central Election Commission licencing (which we later took on through IFES when ProIntegrity was frozen). / • 8 technical CSO partners identified through an Annual Program Statement (call for proposals) and brought on board, supporting the project’s technical components.
Technical Advice	• ProIntegrity contributed to adoption of 34 anti-corruption measures; improved or developed 11 anti-corruption tools, and conducted 9 oversight actions, including integrity checks of candidates for key / judicial and anti-corruption institutions or processes. / Areas in which the project delivered technical inputs include: / Judicial Integrity Checks / Legislation on Lobbying / Financial investigation / Legal analysis of inconsistencies – Customs / Changes to the Criminal Code of Ukraine and the Criminal Procedure Code regarding Liability of Legal Entities / Ukrainian Customs Issues and Reform / Legislation to reform ARMA (concept note) / Recommended Priorities for the Ministry for Communities and Territories Development and State Agency for Restoration and Development of Infrastructure to ensure transparency and accountability of the Restoration Process
Subnational and Inclusion	• The project launched the Local Government Integrity Alliance providing support to 75 local government entities across 10 regions in enhancing transparency of governance and reconstruction.
External engagement	• Supported Ukrainian and international events, mainstreaming the topic of integrity and helping Ukrainian officials (esp local government) participate, including URC 2024 (Berlin), OECD Integrity Forum, 451E IT Forum, Integrity Day of the annual Richelieu Forum of the National Agency of Ukraine for Civil Cervice (NAUCS).

Overall ProIntegrity moderately exceeded expectations (A+), moving faster than anticipated to set up and become actively involved in anti-corruption reform efforts. Its production of anti-corruption knowledge products was prodigious. However, its performance on GESI indicators was disappointing.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes to this output occurred once indicators were agreed at the start of the Prointegrity programme. While ProIntegrity’s work continued after this reporting period until January 2025, as the programme was then frozen/closed, USAID has since withdrawn from work on anti-corruption and any future anti-corruption work will be picked up under the Governance Reform Programme, there will be no further reporting under this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons:
FCDO should ensure the appropriate level and area(s) of advisory support to programme components. Our joint working with USAID on Prointegrity right from the outset was highly effective and allowed us to shape the programme to reflect areas of priority for us including on subnational governance, civil society accountability and aspects of inclusion. This level of effort requires substantial advisory time. For co-funded projects where we did not have adequate advisory support we were not able to achieve the same levels of influence and engagement. (to be shared in the June 2025 Post Programme Board).
Output Title	Digital Transformation Activity (DTA)
Output number:		5	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	Yes - down

The review period for this component runs from January 2024 to October 2024 in line with the USAID reporting year.

Briefly describe the output’s activities and provide supporting narrative for the score.

Transparency and Accountability in Public Administration Services (TAPAS) was a USAID-led project co-funded by the UK since 2016 and funded through GGF in 2022-2023. When it closed in January 2024, it was replaced by the successor programme Digital Transformation Activity (DTA). We intended to fund DTA through GGF also but when USAID froze and then closed it in early 2025 we were then unable to disburse our first payment to DTA of £2m in January 2025. We have still included the DTA reporting here as we invested significant staff time and energy in supporting and shaping DTA through its transition from TAPAS and first months, but the impact weighting has been reduced.

DTA tackles corruption via the introduction of e-services, ensuring transparent public procurement and usage of open data, improving citizens day-to-day lives and increasing trust in the state. The main GoU stakeholders are the Ministry of Digital Transformation and the Ministry of Economy, but the team also works closely with Ukrainian civil society organisations such as Transparency International and Kyiv School of Economics, delivering a broad range of support on digitalisation and anti-corruption. See Annex G for detailed output scoring.

DTA delivered against three core objectives, as well as a cross-cutting inclusion objective:
1. Digitalisation for Economic Revitalisation: digitalisation of business-related permits and licensing services. Outputs substantially did not meet expectation.
2. Digitalisation for Transparent Recovery: civic oversight and scrutiny of reconstruction projects. Outputs met expectations.
3. Digitalisation for Good Governance: eServices implemented in corruption-prone sectors and improving Ukraine’s score in the Online Service Index within the UN E-Government Development Index. Outputs met expectations (with some not meeting and some substantially exceeding).
4. Cross cutting inclusion: Project training programmes to provide new knowledge and skills for women and representatives of vulnerable groups. Output moderately exceeded expectations.
Due to delays in the process of transition from TAPAS to DTA, some of the indicators were not met and this output has scored B. The progress achieved during the reviewed period built a solid foundation for the start of DTA’s work and it was then very frustrating to the team when the USAID freeze put a halt to activity.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicators were agreed in advance and were not changed but the Annual Review found that the selection was insufficient to develop a clear picture of DTA’s work and recommended a broader basket of indicators in future.

In practice, while DTA’s work continued for a further 4 months until January 2025, as the programme was then frozen/closed, USAID has since withdrawn from work on anti-corruption and any future anti-corruption work will be picked up under the Governance Reform Programme, there will be no further reporting under this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR	Update
Ensure Eurasia Foundation include updates on any areas of government legislation they are supporting that is deemed politically sensitive or more high risk.	Starting from last year TAPAS and then DTA has included updates on the draft legislation their teams are working on in weekly updates.
BE Kyiv to undertake a stocktake of the UK’s procurement support and work more closely with the Eurasia Foundation procurement team to understand what upgrades are being prioritised and what progress is being made in order to raise the profile of UK contributions internally and whether any and what additional UK support could do.	There have been number of discussions within BEK, including with DBT on participation of the British Businesses in Prozorro tenders and non-price criteria. DBT recently ran an inward visit to the UK with Nadiia Bihun, Deputy Minister of Economy, part of which involved exchange of experiences on how to include non price criteria in tenders in Ukraine.
BEK to conduct a mapping and deconfliction exercise to ensure that the Digital Transformation Activity aligns to existing and planned BEK programmes, particularly on business revitalisation and economic recovery.	DTA’s activities were aligned and deconflicted with FIRE and REG teams and regular updates were provided through the Governance and Democracy Delivery Groups and less formal internal communication.
BEK to work with the Eurasia Foundation team to ensure that DTA’s log frame is set up to capture high-level outcomes and impact.	This feedback will be taken into future work with Eurasia Foundation.
BEK to monitor the absorption capacity of the GoU and downstream partners and consider sustainability in view of the uplift in the size and scale of the programme as it transitions to DTA.	DTA continued to come under considerable pressure to spend beyond absorption capacity over the past year (until funding was abruptly stopped). USAID mitigated some of this pressure by using DTA to create a Digital Resilience Fund and hold a competition for GoU stakeholders to procure hardware. UK funds were not used for this initiative.

Lessons
FCDO should be mindful of GoU capacity when expanding programmes, and ensure we remain aligned. DTA was designed to be a much larger programme than its predecessor TAPAS. It is a huge challenge for Ukraine to lose USAID funding, but it was becoming clear that the scale of resources that USAID was offering up ($130+m over 5 years) was stretching the programme beyond GoU absorption capacity, reducing appetite for more challenging work that couldn’t be guaranteed to spend on time, and leading to broad mandates that were increasingly difficult to track. (to be shared in the June 2025 Post Programme Board).

Output Title	State-Owned Enterprises Reform Activity (SOERA)
Output number:		6	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	Yes - up

The review for this output runs October 2023- September 2024 in line with the USAID reporting year.

Briefly describe the output’s activities and provide supporting narrative for the score

The State-Owned Enterprises Reform Activity (SOERA) is a USAID-led programme that focuses on improving State-Owned Enterprises (SOE) and Municipal Owned Enterprises (MOE) corporate governance in Ukraine by increasing effectiveness, transparency, accountability, on management of SOEs and MOEs in the country, and on advancing SOE and MOE privatisation. Over the review period SOERA worked to transfer and manage state property at the national and subnational level, improve the performance and transparency of SOEs, and respond to war-related needs. There were six components to this activity.

Workstream	FY23-24 (Oct-Sept)
1. State Property Transfer.	Key results: Prepared the groundwork for improved transfer and management of state property. Worked with GoU to roll out the electronic auction system for state property. Since 2022, GoU has helped GoU hold 882 successful auctions, of which 47 were for SOEs. Worked with the Deputy Minister of Economy to begin mapping the State Property Fund of Ukraine’s (SPFU) thousands of SOEs, which will be a launchpad for further state property transfer.
2. State Property Management.	Key results: Started creating a centralised digital public property register for the SPFU; developed an organisational transformation concept to expand the duties of the SPFU; helped the SPFU design and launch its Digital Transformation Office.
Support to Individual SOEs.	Key results: Completed a preliminary assessment report of risks to Ukrainian Railways and supported the corporatizing of Energoatom, Ukraine’s nuclear power plant SOE.
Subnational Support	Key results: Facilitated two webinars to municipalities to increase their awareness of privatization and lending legislation; interviewed 20 CSOs to understand how to use them to monitor corruption; developed a concept to merge two utility companies in Vinnytsia oblast that can be scaled next year.
Direct Budget Support	Key results: Conducted 541 spot checks of Direct Budget Support funds and found the GOU’s accountability systems to be working effectively. [Links to WB loan guarantees]

On balance, outputs moderately did not meet expectations. A lot of relevant work was delivered towards the objectives of the programme but several key results fall short of where they should be at this stage. See Annex H for the detailed outputs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes to this output occurred during the past year. As USAID froze then closed SOERA in early 2025 there will be no further reporting under this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A

## D: VALUE FOR MONEY

Key cost drivers and performance
The top cost driver for the GGF is driven by the Managed Fund and is fees for international experts. Despite the significant challenges posed by the operating context, particularly the security situation and the shortage of in country expertise, the GGF programme team continues to drive down costs where possible, while ensuring high standards of delivery are maintained. The team is currently focusing on using the silver lining opportunity generated by USAID’s withdrawal of funding from IFES to push for lower overheads and reduced salaries for international experts from July 2025 onwards.

VfM performance compared to the original VfM proposition in the business case

GGF was designed prior to the full-scale invasion in February 2022, so although VfM was explored extensively in the business case, the Programme pivoted dramatically its first months to respond to the new context and continue to offer VfM. These changes are captured in the first and second Annual Reviews. Three years in, the most important VfM consideration across the full GGF portfolio remains the question of whether delivery of outputs is driving progress towards outcomes – and our challenges in measuring the associated changes.

Much of GGF’s work –and in particular the Managed Fund’s contributions– has the potential to be catalytic, whether designing new strategies to deliver reform in government or bringing in expertise for training to better understand GESI integration in judicial reform policies and processes. But not all metrics bring out the sustainability of interventions and the fast-changing and volatile environment at presents unexpected shifts that undermine even well thought through interventions. Thought should be given to how technical assistance can best deliver sustainable impact in a war time context, and how we best measure that.

We also acknowledge the risk that we replace, rather than enhance, GoU functions, and the need to design interventions either that we are confident can avoid this or that recognise this side effect as a trade off we are willing to tolerate. This is very much on our minds in the Embassy as we bring online two new programmes that will support our efforts to improve: the Governance Reform Programme which will include a Political Economy Analysis function, and the Monitoring Programme, VERITAS, which also includes cross-portfolio research.

In the meantime, GGF has done well to adapt to the context and provide meaningful contributions to the economic and governance reform of the country. Future programmes in the portfolio should build on the lessons learned from a programme that had to adapt fast and embed mechanisms that will facilitate this need for flexibility. There is still room to demand better Value for Money for (international) expertise, and the team should continue to push partners on this, especially in light of recent USAID cuts that have changed the parameters for several key partners.

Assessment of whether the programme continues to represent value for money
GGF continues to represent VfM for the Embassy as it supports transition of priority programming into successor programmes, retains critical elements through transition periods and focuses on disseminating learning from the GGF experiences to programmes in design and mobilisation phases. Its closure in June 2025 also represents a VfM decision (made possible by the expanded portfolio and annual ODA allocation) focused on maximising strategic impact with the shift to specialist programmes.

E: RISK

Overview of risk management

The operating environment remained complex and volatile throughout the review period, carrying considerable risks. The GGF risk appetite was updated in Summer 2022 as part of the Theory of Change update process and remained the same during the review period.

GGF Risk App.	Strategy & Context	Policy & Programme Delivery	Public Service & Delivery Operations	People	Financial Fiduciary	Reputational	Safeguarding
Receptive/ Major	Receptive / Major	Receptive / Major	Cautious/ Moderate	Cautious/ Moderate	Cautious/ Moderate	Cautious/ Moderate	Cautious/ Moderate

The programme maintained its strong approach to risk management. Risks were monitored and updated on a quarterly basis. A central GGF risk register was maintained and focused on a sensible selection of risks, with targeted mitigation measures reviewed quarterly, although more effort is needed to integrate risks specific to the programme rather than portfolio-wide risks. Implementing partners also provided their own risk assessments in their quarterly reporting, and highlighted potential adaptations in response to risks identified. Top risks monitored and mitigated include:

Programme delivery: insufficient staff capacity and increasing demands on their knowledge as the portfolio of UK programmes in Ukraine expanded. This risk was discussed in the previous annual review and mitigated by limiting the team’s involvement in other programmes, recruiting a new programme and project manager and shifting the SRO role to a member of the team who could be more active.
- Conscription: Staff members of implementing partners may be conscripted to the war effort, leaving implementers unable to deliver as planned. This risk was mitigated through careful planning and maintaining plans to ensure capability critical for project delivery.
- Travel restrictions impact on monitoring: Managed Fund programme staff were working in various locations including outside of Ukraine for security reasons. In addition travel and security restrictions limit both FCDO staff and implementation partners ability to monitor projects delivered by downstream partners in Ukraine as the war is in its active phase. This risk was mitigated through close engagement of the GGF team, partners’ detailed reporting and regular communication with GoU partners. The need to further mitigate the risk informed the design the Embassy’s new third party monitoring programme, VERITAS.
Reputational: Unpredictability of budget allocations and late decisions on annual funding were mitigated by timely and transparent communication with the Managed Fund and with GoU counterparts, and by maintaining strong working relationships and open communication with implementing partners.
We had considered the possibility of USAID decision-making adversely affecting our portfolio and had introduced and agreed principles for co-funding and working together with USAID. We were unprepared, however, for the scale of impact in January 2025, which brought three co-funded USAID programmes to a halt (SOERA, DTA, ProIntegrity), closed down a judicial reform programme that was coordinating closely with IDLO, and had a major impact on our key elections partner IFES and its downstream Ukrainian NGO partners. The newly approved Governance Reform Programme was also badly affected as we had planned to shift our funding to two of the three (DTA and ProIntegrity) over to GRP from January 2025. The team has worked hard to pivot plans and, in some cases, to provide bridging funding but the longer-term reconfiguration process is still underway.

Key trends in risk exposure remained in the area of programme delivery, related to the ability of BEK, GoU and implementing partners to navigate a complex environment with multiple stakeholders. A prominent risk affecting programme delivery was high turnover of senior leadership in reform owners' teams (within GoU). For instance, RePower was faced with a change of Deputy Minister overseeing its work in September 2023. The Managed Fund worked on addressing this risk by developing relationships with new teams and onboarding them and being responsive to the changing agendas of leadership teams. Working in spaces where multiple other donor actors are present also carries risks of duplication. During the review period we tested approaches to coordination and learning lessons, that will feed into the next stages of the programme. These include increased investment in donor coordination, including separate to joint donor discussions with implementing partners, clearer templates and higher frequency for reporting and updates, and quarterly review meetings bringing in a broader range of FCDO stakeholders.

The programme was able to deliver within risk appetite, with key risks effectively mitigated. The work to update the risk register and provide a more nuanced and detailed account of GGF-specific risks is underway – this is a priority going into GGF’s final year.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The operating context continues to be challenging and uncertain in Ukraine, and close and constructive relationships have been important for the continued successful delivery of GGF. Delivery and reporting has been timely for all partners, and communication channels have been proactive and honest. This has enabled continued smooth delivery and the ability for GGF to flex in response to the changing context. However there remain limitations in the design and vehicles of delivery. Most notably:
1. The Structure of the Managed Fund: The two-contract structure (Project Management Unit and Technical Assistance Facility), which was originally set up for a regional GGF programme, is overly complex which can create unclear lines of communication and accountability, and hamper its ability to be flexible and to provide sustainable support. The annual cycle of projects (which originates with FCDO systems) does not always encourage VfM and is disruptive both for GoU and delivery partners. This structure is not recommended for future programmes.
2. Relationships in government: Limitations on platform space in Kyiv and a fast-changing political landscape have led to overreliance on implementing partners. It would be beneficial for the GGF team to have their own relationships with key counterparts in GoU. This would help us make decisions about when to flex to support the needs of GoU, and would improve cross-UK government join up, better drawing on different parts of HMG’s expertise as needed.
3. Delivery through other donor programmes: The model of delivering our anticorruption and digitalisation work through USAID programmes has offered VfM in a programme with GGF’s breadth and enabled the UK to punch above its weight in key arenas. However it has come with trade offs on levels of control over programming decisions and in areas where the UK has different policy positions to the US. With USAID cuts to work in key governance areas, as we mobilise the Governance Reform Programme, a successor to GGF, we should now consider other models that enable the UK to have a separate voice to the US in this space and offer more autonomy.
4. Outer years certainty: given ongoing uncertainty it can be challenging to commit to outer years budgets but this has significant implications for our partners. The more certainty that FCDO can give to partners, the better VfM they can provide for the FCDO.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
GGF team closely monitored the performance of the programme, engaging on a weekly basis with many of the components of the programme such as the Managed Fund, regularly attending high-level and working level meetings with downstream partners, conducting quarterly discussion with government counterparts, reviewing documents and reporting. The team was broad, with a number of programme managers leaning into different components, enabling this level of monitoring. This array of activities offered a sufficient diversity of sources of information to verify findings and ground programme decisions in evidence. For the future, it is recommended to have more direct interaction with government counterparts, especially at the inception and mobilisation stages of the projects. We were also specifically hampered by our lack of economic advisory expertise in the team, but were able to draw on support from political and economy team colleagues.

We were able to draw on the SOERA mid-term evaluation to support a Governance Reform Programme decision on whether to continue funding SOERA in future and we had anticipated being able to draw on evaluations from USAID projects as they closed –notably TAPAS, which closed in 2024– but these evaluations were halted along with USAID funding.

Evidence: There has not been significant change to the core evidence base underpinning the programming but individual projects have invested in expanding the evidence base to support GoU decision-making. Evolving external environment necessitated continuous evidence review in the unique context of Ukraine, with its martial law in place, war-caused demographic crisis, and very active donor environment. It is recommended that the GGF programme and other similar programmes make a consistent effort to engage relevant advisors to evaluate and advise on the choice of interventions and policies for the programme.

Learning: As an adaptive TA facility, GGF’s strong feature was adjusting its programming to the context, quickly learning about GoU’s evolving needs, maintaining close relationships with key government counterparts. The insights about political currents informed the programming and contributed to GGF’s flexibility. For example, the Managed Fund organised workshops to socialise results of the PEA and needs assessments with the Embassy teams. Dedicated sessions were organised on cross-sectoral topics, such GESI, to bring together different implementing partners working with the Managed Fund. But it has also come from the engagement of cross-cutting advisers in the FCDO, as we have used GGF to better understand and respond to the context and Ukraine’s needs.

Stronger systems of self-assessment, reflection and openness to lessons learnt would have strengthened Manage Fund delivery, as would more explicit feedback loops. The timeframes for projects were a partial obstacle to this, but in several cases projects were continued for more than one year and iterative review and learning could have been stronger. Catch-ups between the programme team and the implementing team should provide an opportunity for substantive updates rather than procedural planning of cooperation, and we have now introduced quarterly reflection and review meetings to create more space for these exchanges. In addition the complex double contract structure for the Managed Fund made it harder for the Portfolio Management Unit to provide detailed updates to the GGF team as implementation was carried out by the Technical Assistance Facility separate from the PMU – essentially it divorced brain from body.

The key lessons of the programme for the wider organisation are:

1. The importance of an appropriate results frameworks for all programmes, including a “Fund”: It is important to design, maintain, and update an appropriate format for the programme’s results framework. The absence of coherence across the programme complicates consistency in MEL. A consistent approach to all parts of the programme should be agreed at its start. (lesson to be shared in the June 2025 Post Programme Board).
2. FCDO should give more consideration to the sustainability of interventions: a lot of the focus of the interventions has been on the generation of strategies and reports. These are often in response to GoU requests and are highly relevant. However, in themselves they do not always deliver change, and the programme would benefit from going beyond strategies in into embedding sustainable and catalytic change. There are elements of the portfolio that did do this – it was just not consistently applied. (lesson to be shared in the June 2025 Post Programme Board).
3. FCDO should ensure TA bolsters Government capability: There is a risk that Technical Assistance replaces government functions rather than bolstering them. More careful thought and explanation needs to go into how TA will complement GoU, with clear sustainable exit plans from the outset within the finite resources agreed with FCDO.
4. FCDO should consider how its programmes can be agile in rapidly changing contexts: GGF has been agile in responding to needs following the full scale invasion on February 2022. But it has not stepped back to assess whether it remains the right vehicle to deliver what is needed in this context. More thought needs to go into how FCDO programmes balance immediate responsiveness with the capacity to plan a longer term portfolio, and taking early decisions on what that transition of programmes should look like – and when. (lesson to be fed back to the FCDO Centre for Delivery, and shared in the June 2025 Post Programme Board)

The next review will be the GGF Progamme Closure Review. This should focus on the above 4 lessons, making recommendations for future programmes across FCDO.

Date of last narrative financial report	[Varies by component – all components report monthly]	Date of last audited annual statement	[Varies by component – all compliant]

Annex A – GGF Programme Map

Good Governance Fund Map FY23-25
GGF IMPACT STATEMENT (3–15 yrs)	An open and resilient Ukraine with stronger rule of law, more effective, transparent, and accountable institutions, and an economy that is competitive and rules based.
OUTCOMES (3 years): Fixed	Judicial reform embeds rule of law, selected state institutions are more effective, transparent and accountable, reducing corruption; increased ability to deliver reconstruction and services.	Ukraine adopts and implements economic reforms that create a more inclusive economy, enhancing trade opportunities with the UK.	Citizens and civil society, including those currently disadvantaged, are better able to engage in politics, hold government to account, and access economic opportunities.
Delivery Groups	Governance / Reconstruction	Economic	Governance
Country Plan Objectives and Relevant Delivery Group Objectives (TBC): Flexible	Country Plan Goal 5 Democracy & Governance / Governance DG outcomes: 1-4 Reconstruction DG Goal:4	Country Plan Goal 3 Economic stability/recovery / Economic Goals:1,2,3	Country Plan Goal 5 Democracy & Governance / Governance DG outcome:4
GGF Projects	IDLO-Judicial reform / TAPAS anti-corruption to July24 / Pro-integrity anti-corruption wef FY24/25 / IFES - election reform / MF-Regional Recovery planning	MF-Economic Hub / MF-Business Revitalisation / MF-Business Inclusion / MF-Tech/Innovation hub / MF-CityUK/Financial Services / SOERA -SOEs Reform / EBRD Multi Donor Account-Reform and Business Ombudsman / IFC Financial Inclusion OECD Secondments wef FY24/25	NDI-Inclusion in Political and Civic life to June 24 / IFES- Post war elections preparation. / MF-Business Inclusion

Annex B – GGF Theory of Change

Annex C – Managed Fund 2023-2025 Results Frameworks

Indicator(s)	Milestone(s) for this review	Progress
UA2012 – Business Revitalisation (incl. Inclusive Economy) (2023-2024)
Status of the set of policies to revitalise business operations of SMEs during the war	September 2023: Outline of standardised frameworks to strengthen SMEs competencies in business planning, talent retention and innovative business practices. / October 2023: Report* on the set of policies to improve business enabling environment for SMEs during the war.	A: Output met expectation / 1) Draft SME Development Strategy, with an Action Plan and KPIs, was updated to account for the context of the war and post-war periods, and based on the previous reform owner feedback was developed and presented to the Ministry of Economy for public consultations. / 2) Report on roll-out of two policies to improve the business enabling environment for SMEs during the war was presented to the reform owner: on the Entrepreneur’s Account Platform and EntreComp+- based surveys for entrepreneurs to assess their skills.
# additional SME support services launched in Diia.Business centres which received legal and TA from the project, including those aimed at the export of goods or services	October 2023 – 3.	A: Output met expectation / 10 SME support services were launched (integrated consulting service, complex solution zone, pop-up store, coworking, coffee-place, event service, professional training service, grant support service, podcast services, piloting a new service for SME support in Diia.Business Warsaw centre). Their contribution to solving SMEs’ essential problems varies greatly.
Status of a set of guidelines for the extension of services by authorised partners of the Diia.Business Association	September 2023 - Policy stipulating key requirements and criteria for the extension of the services offered by the EEPO with the involvement of partnership model. / October 2023 - Guidelines enabling the extension of services provided by the SME support infrastructure with the involvement of partnership model.	A: Output met expectation / The team delivered a Policy Guideline and a set of documents for the heads and employees of Diia.Business centres, with comprehensive guidance on new services, including an additional four new services, were developed.
Status of a package of measures to strengthen export potential of SMEs during the war, based on best international practice.	September 2023 - Research on key hurdles for women entrepreneurship conducted. / October 2023 - 1) Report on Export Laboratory expansion; 2) Report on the progress and results of the development of the industrial park "Sygnivka".	A: Output met expectation / The final report on the results of the research “Needs of and Challenges Faced by Ukrainian Female Entrepreneurs in the Conditions of Full-Scale War” was prepared. Several reports were prepared: a report on the Export Laboratory’s expansion results and an assessment of its potential; a report on enabling additional services (startup incubator) for SME residents at IP Syhnivka; and a report on the conducted SME Possibilities Forum (held on 25 January 2024).
UA2017 – Business Revitalisation (2024-2025)
1.1. Status of the set of policies and supporting instruments to revitalise business operations of SMEs during the war	August 2024 1) SME Development Strategy 2024-2027 adopted by GoU 2) A draft of the MEL framework for SME Development Strategy 2024-2027 developed / October 2024 - SME Development Strategy 2024-2027 Forum held in Kyiv	A: Output met expectation / The target has been achieved. The SME Development Strategy 2024-2027 Forum, titled "Economic Policy of Ukraine: Reconstruction During the War", was held in Kyiv to vitalise the coalition of internal and external stakeholders.
1.2. Number of state and non-state stakeholders engaged in public consultations regarding the SME Development Strategy 2024-2027	August 2024 - 100 / 40 / 60	A: Output met expectation / 113 state and non-state stakeholders were engaged in public discussion regarding the SME Development Strategy 2024-2027, including 37 state stakeholders, including GoU agencies, regional authorities, donors, and representatives of the international community, and 76 non-state stakeholders, including NGOs, business associations, and experts. Slight underachievement of state body target is compensated by overachievement of non-government stakeholders target.
2.1. Upgrades in services offered by EEPO and Diia.Business to promote Ukrainian SMEs exports	September 2024 - Additional needs and gaps of Diia.Business centres personnel to support SMEs analysed and 7+ events for SMEs held in Diia.Business Centres aimed at providing additional services for SMEs / January 2025 - Evaluation of Diia.Business Warsaw's progress to serve Ukrainian SMEs domestically and internationally completed and recommendations developed	A: Output met expectation / The project team analysed the operational efficiency and internal capacity of Diia.Business Centre in Warsaw, updated key documents, and addressed any legal or operational deficiencies. Following this analysis, the project team presented relevant recommendations to the Diia.Business team, that were subsequently implemented. As a result, Diia.Business Centre in Warsaw has gained tools for the consistent and sustainable development and securing capacity to serve Ukrainian SMEs.
3.1. Status of a package of measures to strengthen the export potential of SMEs during the war, based on international best practice	July 2024 - Panel discussion on gender mainstreaming and women’s leadership in Ukraine's recovery at URC 2024 in Berlin. Participation of Ukrainian governmental and non-governmental stakeholders in London Tech Week side event. Recommendations based on the results of both events prepared / October 2024 -Recommendations on land usage for industrial park initiatives and opportunities to scale this initiative across Ukraine based on international best practice developed / February 2024 - Report on the continuing direct support to selected SMEs via Diia.Business Warsaw including Export Laboratory results	A: Output met expectation / The panel discussion “Gender Mainstreaming and Women's Leadership: Ensuring Gender-Sensitive and Inclusive Recovery” was held on June 12, 2024, at URC 2024 in Berlin. / Tech Unity: UK & Ukraine event was held in London on October 23, 2024, bringing together government and business representatives from the UK and Ukraine. The recommendations based on the results of both events were prepared. / The financial outcomes of various municipal land transfer mechanisms were assessed and compared, leading to the development of financial models for each mechanism within Formatsia.Lviv IP. These models outline the advantages and disadvantages of each approach, drawing on both global best practices and local experience. / This in-depth analysis offers municipalities clear guidance on aligning land transfer strategies with financial, developmental, and community objectives, ensuring more informed decision-making for future land management projects. / A comprehensive report was developed based on the Pilot Programme results, including key insights and general recommendations for SMEs seeking entry into foreign markets.
4.1. Status of the development and roll-out to production of the Online Entrepreneur’s Cabinet Platform	September 2024 - Technical specifications to develop the Online Entrepreneur's Cabinet are finalised and a set of documents* required to launch the Online Entrepreneur's Cabinet is approved by the Ministry of Digital Transformation / March 2025 - The Online Entrepreneur's Cabinet was developed and integrated to the Diia ecosystem	B: Outputs moderately did not meet expectation / The Online Entrepreneur’s Cabinet is developed, but not fully integrated in the Diia ecosystem.
4.2. Additional opportunities for SMEs owned/managed by representatives of marginalised groups in the Online Entrepreneur’s Cabinet	September 2024 - Questionnaire to identify representatives of marginalised groups added to the Online Entrepreneur's Cabinet technical specifications. / March 2025 - SMEs owned/managed by representatives of marginalised groups can be matched with specific existing support programmes in the Online Entrepreneur’s Cabinet.	A: Output met expectation / Achieved. The Online Entrepreneur’s Cabinet system allows users who are SMEs owned/managed by representatives of marginalised groups to pick “the targeted programme option” to avoid scrolling through the whole list of programmes. Additionally, the system administrator has the ability to prioritise certain support programmes for these groups.
UA2021 – Inclusive Economy (2024-2025)
1.1. # governmental and non-governmental stakeholders participated in and contributed to the meetings of the Steering Group in the field of support and development of female entrepreneurship	November 2024 - 10/2/8* / February 2025 - 16/4/12* / * total participated/government stakeholders/NGO stakeholders (incl. international organisations and donors, civil society organisations).	A: Output met expectation / 16/4/12
1.2. Conducted research serving a database for recommendations on policy development to foster an inclusive economic environment	November 2024 - Sociological research on the existing problems among employers during the employment of war veterans, especially those who have been disabled, and problematic aspects of support provided by employment centres to war veterans in the process of their employment, is conducted and recommendations on the inclusive working environment for war veterans are developed / January 2025 - Adult Population Survey and National Expert Survey on entrepreneurship in Ukraine are conducted, and Ukraine’s National Report for the Global Entrepreneurship Monitor (GEM) 2024/2025 is prepared and presented to the Ukrainian and foreign stakeholders	A: Output met expectation / The sociological research “Inclusive Employment and Workplace Environment for War Veterans” was conducted by the Kyiv International Institute of Sociology. The research identified challenges faced by the employment centres’ specialists in providing job search services to war veterans. It also outlined the types of support needed by HR specialists and employers to implement inclusive practices successfully in their workplaces. / The Adult Population Survey and National Expert Survey on entrepreneurship in Ukraine were conducted, and Ukraine’s National Report for the Global Entrepreneurship Monitor (GEM) 2024-2025 was prepared and presented to the foreign stakeholders (at the Global GEM Conference 2025, held on February 17-19, 2025, in Bilbao) and to the Ukrainian stakeholders (during online presentation, held on February 28, 2025).
2.1. Level of awareness/ knowledge on guiding war veterans through career selection acquired by the representatives of the SES through awareness-raising workshops	December 2024 - At least 70% of workshop participants for SES specialists report an improvement in their understanding of ways how to guide the war veterans through choosing a career path	A: Output met expectation / 75% of SSE specialists report an increase in their knowledge on guiding war veterans through career selection.
2.2. # HR specialists in Ukrainian companies who have enhanced their professional skills in trauma-informed management and war veteran-inclusive business practices	December 2024 - 10	А++: Outputs substantially exceeded expectation / 20 HR specialists (19F: 1M) in Ukrainian companies who have enhanced their professional skills in trauma-informed management and war veteran-inclusive business practices.
2.3. # war veterans who have completed the course “Career guidance and counselling guide for war veterans”	January 2025 - 50	B: Outputs moderately did not meet expectation / 36 war veterans (12F: 24M) completed the Career Guidance and Counselling Guide for War Veterans course. This number includes 20 participants who completed the course in the online format (7F:13M).
3.1. % women who participated in the programme report an increase in their knowledge and skills in entrepreneurial activities, addressing the gaps identified in the needs assessment	February 2025 - At least 70% of female entrepreneurs trained report improved/gained knowledge and skills	А+: Outputs moderately exceeded expectation / According to the results of the final programme evaluation, over 84% of participants of the programme “Grow 2.0” reported an increase in the overall level of knowledge and skills in entrepreneurship.
3.2. % women from marginalised groups (incl. women on maternity leave, women from rural areas, internally displaced women, female war veterans, women with disabilities, and mothers with many children or single mothers) who participated in the programme	February 2025 - 25% of women from marginalised groups out of the total number of participants in the programme	А++: Outputs substantially exceeded expectation / 31% – IDPs, 34% – single mothers, 8% – mothers of children with disabilities, 12% – mothers of multiple children, 9% – women with disabilities, 7% – national minorities (communities), and 4% – families of fallen (deceased) defenders (male and female) of Ukraine.
UA2013 – Economic Hub (incl. CityUK) (2023-2024)
1.1 Status of creation the framework (GESI sensitive and environmentally sound) and identification of key areas of the Strategy of Economic Growth of Ukraine	August 2023 - At least 5 strategic sectors are prioritized for sectoral strategies. A vision of the development of 5 strategic sectors of the economy was formed and provided to the responsible stakeholders. / October 2023 - Strategy sector presentations approved by the Ministry of Economy. / March 2024 - At least 7 strategic recommendations endorsed by the Ministry of Economy and taken on board for the implementation.	A+: Outputs moderately exceeded expectation. / 12 strategic recommendations, which were endorsed by the Ministry of Economy and taken on board for implementation.
1.2 # consultations with Office of the President, GoU, line ministries, export environment on recovery strategy and economic growth	August 2023 - 8 / 5 / 3*. / October 2023 – 12 / 8 / 4*. / March 2024 - 15/10/5*. / * consultations/stakeholders consulted/ stakeholders representing IDPs, children, women, other vulnerable groups	А++: Outputs substantially exceeded expectation / As a result of the series of working groups created / and the increased number of consultations at the request of the Ministry of Economy, this target was overachieved: 99/706/211. The significant number of consultations and diverse representation, particularly from marginalised groups, indicates the thorough and impactful involvement of stakeholders in shaping the recovery strategy and economic growth initiatives.
2.1 Updated in 2023 macroeconomic and fiscal forecasting scenarios and analysis based on data gathering from a wide spectrum of state and non-state stakeholders (including CSOs, IFIs, donors, think-tanks, anticorruption watchdogs and vulnerable groups representatives)	August 2023 - Draft updated macroeconomic scenarios and analysis based on data gathering from a wide spectrum of stakeholders submitted to MoF for feedback. / October 2023 – Macroeconomic scenarios and analysis based on data gathering from a wide spectrum of stakeholders approved by MoF and a at least 2 policy briefs on relevant issues focused on social and fiscal policy prepared (to be agreed with MoF at the implementation stage). / March 2024 - Macroeconomic scenarios and analysis reviewed and at least three scenarios for the national economy submitted to MoF. The scenarios include the assessment of the impact during the period January-March, as well as relevant assumptions and challenges to affect the macro forecast, budget and financial needs for the next year.	A: Output met expectation / An updated macroeconomic forecast and macroeconomic scenarios used for the development of the state budget 2024 by GoU, as well as policy recommendations approved by the reform owner for further policy cycle developments. As a result, at least several recommendations were endorsed by MoF and taken on board for implementation. The presented updated macroeconomic forecast and macroeconomic scenarios were used for the development of the state budget 2024 by GoU. A presentation on the developed policy recommendations and two analytical policy briefs on relevant issues focused on the budget deficit and post-war economy were submitted to the reform owner.
2.2 # policy briefs* on fiscal and social policy issues prepared at the request of the reform owner and direct beneficiaries.	October 2023 – 3/1. / January 2024 – 6/3. / March 2024 – 8/5. / * # of policy briefs /# of policy briefs with GESI impact analysis of budget policy options	B: Outputs moderately did not meet expectation / 6/5 reports were provided, slightly below the initial target.
3.1 Level of integration of analysis and best practice of social services provision into the GoU policymaking aimed at protecting marginalised groups	August 2023 - A tentative list of the issues for policy analysis prepared, analysis conducted and suggested solutions based on international best practice presented to RO. / October 2023 - A presentation on the results of the analysis and recommendations on specific issues of social policy and demographic impact delivered. / March 2024 - The procedures for social services provision to marginalized populations are reviewed and new effective and efficient approach is suggested.	B: Outputs moderately did not meet expectation / At the project close, the data on various social payments is being collected by the Data Analytics team in the Ministry of Social Policy and the project team and combined with data on social services in each territorial community in order to prepare a detailed understanding of integrated social packages (cash + care). The dashboard development is ongoing and will be tested / and finalised by 01 May 2024.
3.2. # scenarios of demographic situation in Ukraine, its economic impact and recommendations	September 2023 – 1. / December 2023 – 2. / March 2024 – 3.	A: Output met expectation / Three scenarios were developed.
4.1 # public servants (central and local governments and regional authorities), who passed the training	March 2024 – 30.	А++: Outputs substantially exceeded expectation / 106 participants due to a change in the training format and applying online training in a three-day intensive format.
4.2 Status of legal/reporting changes and educational course implementation for local communities to raise capacities at local and municipal levels.	September 2023 - Completed preliminary evaluation of the targeted local communities’ capacity and developed preliminary recommendations on educational activities for targeted local communities' capacity increase. / December 2023 - Finalised draft legal/reporting changes and educational course outline and content for local communities submitted to RO. / February 2024 - Legal/reporting package, capacity building, local communities’ educational activities, provided trainings and communication support approved by RO	A: Output met expectation / Finalised draft legal/reporting changes and educational course outline and content for local communities submitted to RO / Legal/reporting package, capacity building, local communities’ educational activities, provided trainings and communication support approved by RO
5.1. Conformity of the developed set of recommendations aiming at modernising the Ukrainian financial and related professional services sector to UK best practices, wartime and early recovery Ukrainian context and GESI	29 February 2024 - Two capital markets working group meetings and two working group meetings to establish priorities and discuss feedback conducted. / 15 March 2024 - Developed initial set of recommendations aiming at modernising the sector and facilitating Ukrainian private sector-led economic recovery (including capital markets / development) considers UK best practice, Ukraine's wartime, and early recovery context, and GESI.	A: Output met expectation / 3 of the 4 meetings conducted. However, a contingency plan was implemented and additional activities allowed to achieve the goals of the 4th meeting. / Recommendations were developed and shared with reform owners.
5.2. Status of preparation of the corporate twinning initiative for UK-Ukraine collaboration	29 February 2024 - Twinning initiative ToR prepared and included links of the corporate twinning initiative with other initiatives/ platforms / 15 March 2024 - Preparation for the pilot phase of the corporate twinning initiative is finalised	A: Output met expectation / The project delivered corporate twinning initiative ToRs and finished preparations for the pilot phase of the twinning initiative.
6.1. Materials developed for educational activities to build the GoU and its dedicated agency(s) capabilities to reach investors and secure new partnerships	15 January 2024: Training needs analysis conducted / 18 February 2024: GoU training curriculum based on the results of the training needs assessment developed	A+: Outputs moderately exceeded expectation / Training needs analysis was conducted. Training curriculum was developed.
6.2. Percentage of officials trained who report an increase in knowledge to attract private investments to support the reconstruction of Ukraine and commitment to use in their work the knowledge and skills gained in the FDI training	31 January 2024 - Training materials for the FDI training developed / 15 March 2024 - At least 70% of officials who were trained report an increase in knowledge and at least 70% of officials who were trained report commitment to use in their work the knowledge and skills gained in the FDI training	A++: Outputs significantly exceeded expectation / 100 per cent of participants vs targeted 70 per cent reported improvement in their knowledge, as a result of the training, and they indicated that they would use the newly acquired knowledge and skills in their day-to-day work.
UA2019 – Economic Hub (2024-2025)
1.1. Development status of the framework for monitoring and control of the Ukraine Plan investment component implementation by Ministry of Economy as the National Coordinator of the Ukraine Facility	August 2024 - The set of documents for monitoring and control of the Ukraine Plan capital expenditures is endorsed by GoU. / October 2024 - The set of materials (documents, processes, templates aligned with GESI and green agenda requirements of EU) for GoU coordination on the Ukraine Plan investment component is endorsed by GoU. The Investment Pipeline database is available for public review. / March 2025 - Blueprint for financing instruments and compliance requirements for IFI investments under the Ukraine Facility and other financial instruments available for Ukraine are submitted to the Ministry of Economy and approved.	A+: Outputs moderately exceeded expectation / The following set of documents were prepared by the project team and endorsed by the GoU: / Stakeholder map for each investment indicator / Analysis of the required budget funding for the implementation of indicators of the Ukraine Plan. / Proposal of the mechanisms to provide 20% non-repayable financial support under Pillar I of the Ukraine Facility. / The set of materials for GoU coordination on the Ukraine Plan investment component was endorsed by GoU (this set includes documents, processes, and templates aligned with GESI and green agenda requirements of the EU). / Blueprint for Financing Instruments and Compliance Requirements related to IFI investments under the Ukraine Facility and other financial instruments available for Ukraine were submitted to the Ministry of Economy and approved.
1.2. Development status of a methodological framework for evaluating the economic impact of reforms outlined in the Ukraine Plan and other respective existing and/or forthcoming bilateral and multilateral documents for 2024-2027.	July 2024 - Economic analysis and modelling to assess the impact of the reforms on key economic variables is conducted. / September 2024 - Paper on the economic evaluation of the reforms in the Reform Matrix for 2024-2027 and respective visualisation on the analytical dashboards of the monitoring results and economic estimates is endorsed by GoU.	A: Output met expectation / A paper on the economic evaluation of the reforms in the Reform Matrix for 2024-2027 and respective visualisation on the analytical dashboards of the monitoring results and economic estimates was endorsed by the GoU. Economic evaluation of reforms considered the following factors: economic importance of reforms, harmonisation with EU legislation, priority for international partners, and impact on the EU accession process.
1.3. # consultations with key stakeholders during the development of the framework for monitoring and control of the Ukraine Plan investment component implementation and framework for evaluating the economic impact of the reforms in the Reform Matrix for 2024-2027	September 2024 - 8 / 5 / 3* / October 2024 - 12 / 8 / 4* / March 2025 - 15/10/5* / * # consultations / # stakeholders consulted (including business associations, NGOs, IFIs, GoU agencies) / # stakeholders representing women and marginalised groups.	А++: Outputs substantially exceeded expectation / 84 / 190 / 28 consultations conducted.
2.1. Status of creation of data-driven economic development strategies for preselected frontline regions of Ukraine	July 2024 - Kharkiv economic revitalisation strategy concept is developed, based on an analysis of the economic situation and potential economic, social, and security impacts of proposed regulations and presented to the Ministry of Economy. / September 2024 - Economic revitalisation strategy concepts for preselected frontline regions are developed based on analysis of the economic situation and potential economic, social, and security impacts of proposed regulations and submitted to the Ministry of Economy.	A: Output met expectation / Kharkiv economic revitalisation strategy concept developed and submitted to the Ministry of Economy, considering the economic situation, key risks for the economy of Kharkiv, the impact on the economic structure during the war and including recommendations for the GoU regarding business stimulation and compensatory mechanisms for the population. / Economic revitalisation strategy concept for all preselected frontline regions – Chernihiv, Sumy, Kharkiv, Luhansk, Donetsk, Dnipropetrovsk, Zaporizhzhia, Kherson, Mykolaiv, and Odesa – were developed and submitted to the Ministry of Economy
2.2. # policy briefs* on the implementation of the National Revenue Strategy (NRS), public finances, and transparency issues prepared at the request of the reform owner and direct beneficiaries	October 2024 – 2/1 / January 2025 – 3/2 / March 2025 – 4/3 / # of policy briefs /# of policy briefs with GESI impact analysis of budget policy options	A: Output met expectation / 4 / 3 policy briefs prepared.
2.3. # consultations with stakeholders	October 2024 - 10 /5/3/1 / January 2025 - 20/10/8/2 / March 2025 - 30/20/17/5 / * # of consultations / # of stakeholders consulted / # of non-governmental stakeholders, including business, expert society / # of stakeholders representing women and marginalised groups.	C: Output substantially did not meet expectation / 16 /8 / 5/ 1 consultations conducted (underperformance due to a change in ministerial priorities)
3.1. # public events with GoU and other key stakeholders (non-governmental, CSOs/NGOs, business, marginalised groups, international) on coalition building to support evidence-based public finance policy and pension reform implementation (including GESI lens)	September 2024 – 1 / November 2024 – 2 / March 2025 – 5	A: Output met expectation / 5 events held
3.2. # communication products / (articles, posts, presentations, analytical notes, etc.) on pension system reform and NRS implementation developed, including products prepared on request and on behalf of the reform owner	September 2024 – 20 / December 2024 – 50 / March 2025 - 100	А++: Outputs substantially exceeded expectation / 310 communication products prepared.
4.1. # analytical supporting documents on economic security issues and implementing obligations under the Ukraine Plan prepared at the request of the Committee on Finance, Taxation and Customs Policy	October 2024 – 5 / December 2024 – 10 / March 2025 - 20	A+: Outputs moderately exceeded expectation / 29 analytical documents prepared.
4.2. Level of enhancement in inclusivity and gender-sensitive analytical capacity in Parliamentary oversight	October 2024 - At least 50% of analytical and communication materials developed for the Committee on Finance, Taxation and Customs Policy oversight practices include a specific section on GESI impacts and considerations / December 2024 - The developed analytical materials including GESI impacts and considerations are discussed with governmental and non-governmental stakeholders / March 2025 - The developed recommendations suggesting specific measures to enhance gender equality and social inclusion in the legislative and oversight processes approved by the Committee on Finance, Taxation and Customs Policy.	A: Output met expectation / The developed recommendations suggesting specific measures to enhance gender equality and social inclusion in the legislative and oversight processes were approved by the Committee on Finance, Taxation and Customs Policy.
UA2020 – City-Ukraine Hub (2024-2025)
1.1. Incorporation of GESI principles into the developed recommendations on the single-window investment agency establishment	March 2025 - Developed recommendations on a single-window investment agency establishment consider the interests and needs of women and marginalised groups	A: Output met expectation / Developed recommendations on the SWIA establishment took into account the interests and needs of women and marginalised groups and were approved by the UkraineInvest Supervisory Board.
1.2. # consultations with governmental and non-governmental stakeholders on establishing a single-window investment agency	November 2024 - 1/ 4/ 3/ at least 50% of stakeholders are represented by women* / March 2025 - 3/ 10/ 3/ at least 50% of stakeholders are represented by women* / * # of consultations / # of stakeholders consulted / # of non-governmental stakeholders	B: Outputs moderately did not meet expectation / 9/20/11 consultations were conducted. Gender disaggregated data not provided.
2.1. Alignment of the developed expert recommendations on Ukraine’s financial ecosystem modernisation and corporate governance with the EU acquis and relevant Ukraine’s obligations	December 2024 - Developed legal and regulatory recommendations and solutions to improve arbitration and dispute resolution in Ukraine (to improve investor protection and attract private sector investment) and developed recommendations and solutions on green and sustainable finance (namely, on infrastructure for the future, a just transition and the move to net-zero, impact investments) – are aligned with the EU acquis and relevant Ukraine’s obligations / February 2025 - Developed digital solutions in Anti-Money Laundering (AML) to address investor confidence – are aligned with the EU acquis and relevant Ukraine’s obligations / March 2025 - Developed solutions on improving Ukraine's financial ecosystem to attract FDI, improve exports and develop human capital – are aligned with the EU acquis and relevant Ukraine’s obligations. Developed recommendations on enhancing Ukraine’s corporate governance regime and framework – are aligned with the EU acquis and relevant Ukraine’s obligations.	A: Output met expectation / Developed legal and regulatory recommendations and solutions to improve arbitration and dispute resolution in Ukraine, along with developed recommendations and solutions on green and sustainable finance – were aligned with the EU acquis and relevant Ukraine’s obligations. / Developed digital solutions in AML to address investor confidence – were aligned with the EU acquis and relevant Ukraine’s obligations.
2.2. # businesses that established business-to-business linkages/ increased exports/ received assistance to access finance through the project	March 2025 - At least 5 partnerships established/ companies assisted	A+: Outputs moderately exceeded expectation / The project team supported nine businesses and developed respective case studies for each of the nine partnerships.
3.1. # public servants (central and local governments and regional authorities), who passed the specially prepared training	March 2025 - 12/7/5* / # of public servants educated/ # Male / # Female	А++: Outputs substantially exceeded expectation / 108/47/61 / Some certified training programmes take up to six months to complete, and the project team expects at least an additional 34 participants to complete their training within the next six months.
3.2. # private sector firms’ representatives and individuals (including government officials, professionals, representatives of the workforce, and marginalised groups), who passed the specially prepared training and workshops	December 2024 – 40 / March 2025 - 100	A+: Outputs moderately exceeded expectation / 220 / Some certified training programmes take up to six months to complete, and the project team expects at least 100 additional participants to complete their training within the next six months.
UA2014 – Local Recovery (2023-2024)
1.1 Institutionalization of the Updated State Regional Development Strategy 2024- 2027 and set of supplementary documents (the Strategy implementation roadmap, budget assessment, list of functional types of territories, recommendations for adopting the Strategy, tools to monitor, review and report the implementation of the Strategy)	November 2023 - Final draft of the updated State Regional Development Strategy 2024-2027 and set of supplementary documents (the Strategy implementation roadmap, budget assessment of the policies/ programmes and the Strategy implementation, list of functional types of territories, along with the criteria and principles for classifying hromadas into the identified types, recommendations for adopting the Strategy at the regional and local levels, tools to monitor, review and report the implementation of the Strategy) that include integrated feedback from key stakeholders – have been endorsed by the Ministry for Communities and Territories Development which commits to submit the document for the GoU approval.	A: Output met expectation / The final draft of the updated State Regional Development Strategy 2024-2027 and set of supplementary documents (including a list of functional types of territories along with the criteria and principles for classifying hromadas into the identified types, recommendations for adopting the Strategy at the regional and local levels, tools to monitor, review and report the implementation of the Strategy) that include integrated feedback from key stakeholders were endorsed by MfR (were uploaded on the website of MfR for public discussion).
1.2 Inclusion of GESI principles to the updated State Regional Development Strategy 2024- 2027 and supplementary documents	November 2023 - The final draft of the updated State Regional Development Strategy 2024-2027 and the supplementary documents include GESI-oriented goal and recommendations.	A: Output met expectation / The final draft of the updated State Regional Development Strategy 2024-2027 and the supplementary documents include complemented and expanded GESI-oriented goal and involve the input from stakeholders representing women and marginalised groups.
1.3 # consultations with key government and nongovernment stakeholders (local communities, regional administrations, representatives of the business community, civil society, marginalised groups, donor-funded projects) on the updated State Regional Strategy 2024-2027 and supplementary documents.	November 2023 - At least 4 per type of stakeholder* / * # of consultations / # of stakeholders consulted / # of local community representatives / # of regional administration partners / # of representatives of business community / # of representatives of civil society / # of stakeholders representing IDPs, veterans, people with disabilities, elderly individuals, other marginalised groups / # of donor funded projects.	A: Output met expectation / The total number of written comments received was above 3000, 58 stakeholders provided their comments, including 4 local community representatives, 4 regional administration partners, 4 representatives of the business community, 28 representatives of civil society, 6 stakeholders representing IDPs, veterans, people with disabilities, elderly individuals, other marginalised groups and 12 representatives of donor-funded projects.
2.1 Existence of Recovery Plan Methodology (which considers the Resolution of the Cabinet of Ministers of Ukraine No.731 ‘On Approving Procedures for the Recovery and Development of Regions and Territorial Communities’, dated July 18, 2023; incorporates GESI considerations and the best global practices of local recovery planning) and set of materials for methodology training sessions	December 2023 - Finalised Recovery Plan Methodology which incorporates recommendations based on actual government regulation documents, GESI considerations and best global practices and a set of materials for training which consists of at least one training focused on capacity building for women and marginalised groups accepted by MoR.	A: Output met expectation / Recovery Plan Methodology incorporates GESI considerations and / provisions of the Resolution of CMU No.731 and other national laws and regulations, as well as global practices of local recovery planning. The developed set of training materials contains trainings for capacity building of women and marginalised groups. Both the Methodology and a set of training materials are accepted by MfR.
2.2 Institutionalization of developed Comprehensive Recovery Plans at the local level	January 2024 - At least 10 developed Comprehensive Recovery Plans, which are based on the approved Recovery Plan Methodology and reflect inputs from the consultations with key stakeholders, accepted by MoR.	A: Output met expectation / 10 Comprehensive Recovery Plans for hromadas incorporating inputs from working group coordination meetings have been developed and accepted by the MfR.
2.3 # conducted consultations with key government and non-government stakeholders(local communities, regional administrations, marginalised groups, donor-funded projects) on the Recovery Plan Methodology and Comprehensive Recovery Plans	Target 31st January 2024 - At least 2 per type of stakeholder* / * local community representatives; regional administration partners’ civil society; IDPs, veterans, people with disabilities, elderly individuals, other marginalised groups; donor-funded projects.	B: Outputs moderately did not meet expectation / In total, 12 consultations were conducted with 10 stakeholders / representatives, including 3 local community representatives, 1 regional administration partner, 3 representatives of civil society, 2 stakeholders representing IDPs, veterans, people with disabilities, elderly individuals, other marginalised groups, 1 representative of donor-funded / projects.
3.1 # developed recovery project design concepts for selected local communities (hromadas)	March 2024 - Three recovery project design concepts developed per hromada, resulting in a total of at least 30 recovery project design concepts which incorporate the GESI criteria/principles defined in the Recovery Plan Methodology and Recovery Plans. One of the three developed project design concepts per hromada includes a detailed cost breakdown (design and estimate documentation), accepted by MoR.	A: Output met expectation / Three recovery project design concepts were developed per / community, resulting in a total of 30 recovery project design concepts, including 10 with design and estimate documentation, and accepted by MoR.
3.2 # local community authority representatives (involved in the project) who reports increased knowledge on how to design recovery projects, obtain recovery funding, manage and report against recovery projects based on funding requirements	March 2024 - At least 4/2/2* per selected hromada. / * # of local community representatives trained / # female / # male.	А++: Outputs substantially exceeded expectation / 204 local community representatives were trained (129F: 75M). Bobrovytska hromada Chernihiv oblast: 19/13/6; Gogolivska hromada Poltava oblast: 24/20/4; Dubovyazivska hromada Sumy oblast: 32/18/14; Karolino-Bugazka hromada Odesa oblast: 9/6/3; Ladyzhynska hromada Vinnitsya oblast: 12/8/4; Mykhailo-Kotsubynska hromada Chernihiv oblast: 10/8/2; Novobuzka hromada Mykolaiv oblast: 15/10/5; Novopokrovska hromada Kharkiv oblast: 21/8/13; Romenska hromada Sumy oblast: 51/31/20; Sosnytska hromada Chernihiv oblast: 11/7/4.
UA2018 – Regional Recovery (2024-2025)
1.1. Alignment of the State Regional Development Strategy Action Plan with EU accession requirements	July 2024 - Draft Action Plan of the State Regional Development Strategy 2024-2027 is aligned with requirements outlined in the Ukrainian Plan, Chapter 9 "Decentralisation and Regional Policy"	A: Output met expectation / Draft Action Plan of the State Regional Development Strategy 2024-2027 is aligned with requirements outlined in the Ukrainian Plan, Chapter 9 "Decentralisation and Regional Policy", submitted to the MTU.
1.2. Inclusion of GESI principles to the Action Plan of the Updated State Regional Development Strategy 2024-2027	July 2024 - Draft Action Plan of the Updated State Regional Development Strategy 2024-2027 includes GESI-oriented recommendations	A: Output met expectation / Draft Action Plan of the Updated State Regional Development Strategy 2024-2027 includes GESI-oriented tasks and actions.
1.3. # consultations with key government and non-government stakeholders (local communities, regional administrations, representatives of the business community, civil society, marginalised groups, donor-funded projects) on the Action Plan of the updated State Regional Strategy 2024-2027	July 2024 - At least 4 per type of stakeholder* / * local community representatives / regional administration partners / representatives of the business community / civil society / stakeholders representing IDPs and other marginalised groups/ / donor-funded projects.	A: Output met expectation / The project team engaged over 30 stakeholders, with at least four representatives per category: representatives of the business community, representatives of civil society, stakeholders representing IDPs and other marginalised groups, and representatives of donor-funded projects.
2.1. Status of institutionalisation of Regional Development Strategies for 2 regions	December 2024 - Drafted Regional Development Strategies for 2 regions are developed based on consultation sessions with regional stakeholders and take into account the current socio-economic conditions of the regions and their recovery needs / March 2025 - Developed Regional Development Strategies for 2 regions are accepted by the heads of the regional administrations and the reform owner	A: Output met expectation / Developed Regional Development Strategies for 2 regions were accepted by the directors of the economic departments of the relevant regional administrations.
2.2. Status of institutionalisation of Local Development Strategies for 5 hromadas	July 2024 - Drafted Local Development Strategies are developed for 5 hromadas based on updates of corresponding Local Recovery Plans and consultation sessions with local stakeholders / August 2024 - Developed Local Development Strategies are accepted by hromadas' local authorities	A: Output met expectation / Developed Local Development Strategies are accepted by hromadas' local authorities.
2.3. # consultations with key government and non-government stakeholders (local communities, regional administrations, marginalised groups, donor-funded projects) on the Local and Regional Development Strategies	March 2025 - At least 1 per type of stakeholder* per strategy document / * local community representatives / regional administration partners / representatives of civil society / stakeholders representing IDPs and other marginalised groups/ donor-funded projects	А++: Outputs substantially exceeded expectation / The number of consultations with key stakeholders on five Local Development Strategies includes: / 92 working group members, including residents, business representatives, and civil society. / 695 residents surveyed. / 14 entrepreneurs engaged through questionnaires. / Regional administrations engaged during the approval process of Strategic Environmental Assessment (SEA) and strategies, along with the Ministry of Environmental Protection and Natural Resources. / The number of consultations with key stakeholders on two Regional Development Strategies: / 5,331 residents and 158 representatives of local self-government bodies surveyed. / 25 online consultations with local authorities, universities, clusters, CSOs, agencies, and associations. / Four representatives of marginalised groups engaged (two per region). / Four donor-funded projects involved (two per region). / The representatives of the MTU and the expert community engaged. / One strategic session per region, led by the MTU, gathering input from diverse stakeholders.
3.1% of trained entrepreneurs who report increased knowledge on how to design business models and launch social entrepreneurship activities (disaggregated by gender)	November 2024 - At least 70% of entrepreneurs trained report increased knowledge	A+: Outputs moderately exceeded expectation / c.85% of the programme participants rated their knowledge improvement following the programme as at least 8 out of 10. Among them: / Men (20%) gave an average rating of 8.6. Women (80%) gave an average rating of 8.8.
UA2015 – RePower (2023-2024)
1.1. Progress in support of GoU regarding communication of Ukrainian energy recovery policy to a global audience	June 2023: The presentation for the Ukraine Recovery Conference, as well as supplemented communication package, including a list of specific investment projects, accepted by the Ministry of Economy. / July 2023: The presentation that includes a list of key potential investment projects (not less than 35 projects) with detailed information for investors accepted by the Ministry of Economy.	A+ – Outputs Moderately Exceeded Expectation / The Ministry of Energy communicated the vision for energy sector development to international stakeholders and Ukrainian market / players at the Ukraine Recovery Conference using the prepared communication package. / The presentation of over 50 investment projects took place, with the key areas for investment in the energy sector outlined. / The Ministry of Energy provided a letter of acceptance for these outputs.
2.1. Status of the Energy Strategy until 2050 implementation roadmap	August 2023; Draft updated and extended the Energy Strategy until 2050 implementation roadmap based on / the URC results submitted for feedback to the Ministry of Economy. / September 2023: Updated and extended the / Energy Strategy until 2050 implementation roadmap, / based on the URC results accepted by the Ministry of Economy.	A: Output met expectation / The Ministry of Energy accepted the updated and detailed implementation / roadmap for the Energy Strategy 2050, which also received approval / from all central government authorities.
3.1. Status of pre-feasibility / and/or feasibility studies developed for selected projects*	September 2023: Draft version of prefeasibility and/or feasibility studies for the selected projects (list of projects approved by the Ministry of Economy), submitted for feedback to the Ministry of Economy. / November 2023 Completed pre-feasibility and/or feasibility studies for selected projects	A: Output met expectation / The Ministry of Energy has accepted the results of the four pre-feasibility studies for wind energy projects, solar energy projects, geothermal energy, and electric charging stations developed.
3.2. Status of developed draft legal acts to introduce green investment / mechanism in Ukraine	November 2023 / Draft legal acts required to introduce green investment mechanism in Ukraine (based on the developed concept of green investment mechanism), submitted for feedback to the Ministry of Economy. / November 2023: Draft legal acts to introduce green investment mechanism (green taxonomy and verification) in Ukraine, accepted by the Ministry of Economy.	A: Output met expectation / Draft legal acts necessary to implement a green investment mechanism in Ukraine (laws, resolutions, concept papers) have been submitted to the Ministry of Energy for feedback and accepted by the Ministry of Economy.
UA2016 – Tech Ecosystem (2023-2024)
1.1. Progress in support of the GoU and the Ministry of Digital Transformation with organised consultations to explore and discuss / the GoU Innovation Strategy	February 2024 Conducted three sector specific events in an online/offline format / March 2024: Reports on the outcomes of the sector specific events accepted by the Ministry of Digital Transformation	A: Output met expectation / The project team conducted three sector-specific events on the topics of AgroTech, BioTech, and GovTech in a hybrid online-offline format and prepared reports on their outcomes.
2.1. Evidence-based recommendations to promote development in defined Innovation and Tech Sectors	February 2024: Developed informed recommendations and a list of policy options to foster innovation development in the defined sectors, / including impact assessments, submitted for feedback to the Ministry of Digital Transformation / March 2024: Reports on three sectoral assessments for Innovation and Tech Sectors, including evidence-based recommendations, accepted by The Ministry of Digital Transformation	A: Output met expectation / The project team has prepared reports on three sectoral assessments of / the innovation and tech sectors, which include an international experience / review, an overview of the state of the sector in Ukraine, evidence-based / recommendations, and a detailed description of one top priority project for / development and implementation in each sector
2.2. Consideration of GESI perspective in sectoral assessments for Innovation and Tech Sectors	February 2024 Developed informed recommendations and a list of policy options to foster innovation development in the defined sectors considering GESI perspective / March 2024: Reports on three sectoral assessments for Innovation and Tech Sectors include consideration of GESI perspective	A: Output met expectation / The project team took into account GESI aspects in all reports on the three sectoral assessments of the innovation and tech sectors (separate sections on this topic were included in each report)
3.1. International best practice / consideration in feasibility study for / Establishing a Governmental / Innovation Agency	February 2024: Drafted concept of establishing an Agency outlining the functions of the Agency and general setup, including a review of international best practices from similar institutions, submitted for feedback to the Ministry of Digital Transformation / March 2024: Developed concept of establishing an Agency outlining the functions of the Agency and general setup, including international best practices / from similar institutions, accepted by the Ministry of Digital Transformation	A: Output met expectation / The project team developed two potential concepts for establishing / an Agency, outlining the functions of the Agency, including international / best practices from similar institutions, and submitted these for feedback to the Ministry of Digital Transformation.
4.1. Level of awareness / knowledge gained by Ukrainian tech sector / stakeholders about challenges in / selected sectors, along with the most / relevant solutions, through awareness raising workshops	March 2024 Average level of awareness/ knowledge of Ukrainian tech sector stakeholders who joined the workshops is at least 4 / 5* / * (1 - Unacceptable, 2 – Marginal, 3 – Satisfactory, 4 – Good, 5 - Excellent.)	A+ – Outputs Moderately Exceeded Expectation / The level was reported to be 5/5.
UA2022 – Innovation Ecosystem (2024-2025)
1.1. Set of developed supplementary documents for the State Innovation Strategy	January 2025 - Developed drafts of the State Innovation Strategy Action Plan and Communication Plan are presented and discussed with the Ministry of Digital Transformation and relevant stakeholders / March 2025 - Set of developed supplementary documents for the State Innovation Strategy developed, consulted with a wide spectrum of relevant stakeholders, and accepted by the Minsitry of Digital Transformation.	A: Output met expectation / Summary materials of the State Innovation Strategy have been developed, presented, and discussed with the the Ministry of Digital Transformation and relevant stakeholders. / The finalised seven sectoral strategies for innovation development in AUV, AI, AgriTech, BioTech, GovTech, MedTech, and GreenTech, have been developed. These materials were thoroughly consulted with a wide range of relevant stakeholders, presented to the Ministry of Digital Transformation, and formally accepted by the Ministry of Digital Transformation
2.1. Results of the implementation of an evidence-based approach in producing recommendations to intensify the development of tech clusters in defined tech sectors (EdTech, Agrifood Tech, Health Tech, and Energy & Environment Tech	January 2025 - Developed four reports for defined tech sectors, containing the results of the sectoral assessment and outcomes of conducted stakeholder consultations (including defined gaps in the innovations ecosystem and stakeholders’ needs) – submitted to the Ministry of Digital Transformation. The reports contain mapping and research materials, outlining current trends, challenges, value chains, and opportunities within each defined tech sector. / March 2025 - Developed four reports for defined tech sectors, containing targeted recommendations (in particular, based on outcomes of conducted cluster-specific events) to foster effective collaboration between the GoU and technology stakeholders, and accompanied by cluster strategic development plans – accepted by the Ministry of Digital Transformation.	A: Output met expectation / Four reports of sectoral assessments and the outcomes of consultations for the EdTech, AgriFood Tech, Health Tech, and Energy & Environment Tech sectors have been developed. Gaps in the innovations ecosystem and stakeholders’ needs within defined sectors have been identified. Reports containing sector-specific mapping and research materials, outlining current trends, challenges, value chains, and opportunities within each defined tech sector have been prepared. / Four reports on the defined tech sectors – EdTech, AgriFood Tech, Health Tech, and Energy & Environment Tech – featuring targeted recommendations to enhance collaboration between the GoU and technology stakeholders have been prepared. These recommendations were developed based on insights gained from sector-specific cluster events and were complemented by strategic development plans for each cluster. These results were presented to representatives of the Ministry of Digital Transformation and a broader audience at the Tech Clusters Conference 2025 and were officially accepted by the Ministry of Digital Transformation.
2.2. Consideration of GESI perspective in sectoral assessments of EdTech, Agrifood Tech, Health Tech, and Energy & Environment Tech and in specific tech cluster development plans	January 2025 - Developed four reports with the results of sectoral assessment for tech sectors include the GESI perspective / March 2025 - Developed informed recommendations and a list of options to foster innovation development in the defined sectors include the GESI perspective	A: Output met expectation / Reports for EdTech, AgriFood Tech, Health Tech, and Energy & Environment Tech sectors include GESI considerations. Informed recommendations and a list of options to foster innovation development in the defined sectors, including the GESI perspective, have been developed.
3.1. Development status of the institutionalisation framework for the Innovation Scientific Park of the Kyiv Aviation Institute (KAI)	December 2024 - Developed draft concept of Innovation Scientific Park of the KAI, including scientific park's goals, operational strategies, and development roadmap, accompanied by drafted scientific park’s legal framework and governance structure / March 2025 - Finalised concept and strategic plan including developed roadmap and legal framework for the development of the institutionalised Innovation Science Park of the KAI – accepted by KAI.	A: Output met expectation / Draft concept of the KAI Science Park, including strategic goals and options for operation strategy, as well as drafted legal documents have been developed, presented, and discussed with KAI / In close cooperation with KAI, the project team finalised the concept of the KAI Science Park and developed a detailed roadmap for its strategic development until 2030. Additionally, the project team also equipped KAI with a set of legal framework documents required for the Science Park operation. The finalised concept, development plan and legal framework were presented to and accepted by KAI
3.2. Developed materials to showcase and promote the Innovation Scientific Park of the KAI among relevant stakeholders	March 2025 - Developed marketing materials (including pitch presentations, and portfolios) to attract public and private partners / March 2025 - Developed materials to support the KAI in organising and participating in defined international events to promote the Scientific Park	A: Output met expectation / The project team developed a comprehensive set of branding materials, including a brand book with the logo and brand identity created from scratch, as well as supporting visual, promo and information materials (pitch presentations, teasers, portfolio, etc.) to prepare the Science Park to participate in relevant international events for further promotion of the KAI Science Park
4.1. Level of knowledge gained by six selected Ukrainian Deep Tech startups about industry engagement, data access and utilisation, staff training and development, and commercialisation strategies	October 2024 - The average level of knowledge of selected programme participants before the programme’s start is at least 2/5* for each module – based on pre-test results / March 2025 - The average level of knowledge of selected programme participants at the programme’s end is at least 4 /5** for each module.	A: Output met expectation / The average level of knowledge of selected programme participants at the programme’s end is 4.22/5**. / The level of knowledge for each module is at least 4/5 for 7 out of 8 participants – based on post-test results.
4.2. # potential investors engaged in the presentations of capstone projects developed by programme participants	March 2025 - At least 5 potential investors (including venture capital firms’ representatives, private investors, and institutional investors) participated in the presentation	A: Output met expectation / 7 potential investors (including venture capital firms’ representatives, and private investors, and institutional investors) joined the Demo Day and participated in the presentation of the participants’ pitches
4.3. Share of female representation and representation of marginalised groups in the acceleration programme	October 2024 - At least 50% of the programme participants are represented by women and representatives of marginalised groups / March 2025 - At least 30% of capstone projects are presented by women and representatives of marginalised groups	A+ – Outputs Moderately Exceeded Expectation / 65% of selected participants of the acceleration programme were representatives of women and marginalised groups / 37,5% of capstone projects were presented by women and representatives of marginalised groups

Annex D – IFES 2023-2025 Results Framework

Output (s)	Indicators	Milestone(s) for FY23-24 and Progress	Score
Output 1.1 Technical assistance to legal reform efforts	# laws, amendments, or strategic documents to ensure credible elections/referenda or improved political processes drafted with IFES technical assistance.	Target: 1 / Actual: 1	A
	# analytical materials with recommendations for improving the electoral, referenda, or political process developed with IFES support.	Target: 5 / Actual: 18	A+
Output 1.2 Comprehensive technical assistance provided to EMBs and key stakeholders, including on outreach, electoral technology, cybersecurity, modernization and decentralization	# election officials and other stakeholders trained with IFES assistance (disaggregated by sex, training topic, and audience)	Target: 1000 / Actual: 304 (143M;161F)	B
	# initiatives that support/work towards the full institutionalization of the joint CEC-IFES Training Centre.	Target: 1 / Actual: 0	C
Output 2.1 Support to Ukrainian civil society organizations on advocacy and outreach to improve access to the electoral and political process	# materials/outreach tools targeting historically excluded groups developed by IFES and IFES-supported CSOs (disaggregated by type, target audience).	Target: 10 / Actual: 75	A++
	% trainees who indicate utilizing knowledge and skills gained from IFES-led trainings/curriculum in their advocacy and outreach efforts.	Target: 45% / Actual: 91%	A+
Output 2.2. Targeted civic and voter education provided to support citizen engagement in political and electoral processes	# students and teachers participating in IFES' civic education programs and initiatives (data disaggregated by audience, gender, new teachers and university) (2000 students, 60 teachers)	Target: 2000 Students, 60 teachers. / Actual: 3794 Students (1949M; 1845F); 59 Teachers (16M; 43F)	A++
	# viewership from IFES-supported informational and voter education campaigns, including national media sources, social media, and other channels (disaggregated by communication channel and audience and gender, where possible)	Target: 1 million / Actual: 220,735	C
Output 3.1: Technical assistance provided to political finance oversight institutions and political stakeholders to address political corruption	# people trained on political finance and abuse of state resources (disaggregated by audience, sex)	Target: 50 / Actual: 182 (119F; 54M)	A+
	# materials on political corruption and abuse of state resources developed by IFES and IFES-supported CSOs (disaggregated by target audience, topic)	Target: 50 / Actual: 33	B
Output 3.2 TA and capacity building provided to electoral justice actors, including the judiciary and police	# judicial and law enforcement personnel trained with FCDO assistance.	Target: 100 judges, 1500 law enforcement staff. / Actual: 58	C
	# educational/guidance materials developed for judges, law enforcement staff, and other stakeholders.	Target: 3 / Actual: 7	A+

Output (s)	Indicators	Milestone(s) for FY24-25 and Progress	Score
Output 1.1 Technical assistance to legal reform efforts	# laws, amendments, or strategic documents to ensure credible elections/referenda or improved political processes drafted with IFES technical assistance.	Target: 1 / Actual: 6	A++
	# analytical materials with recommendations for improving the electoral, referenda, or political process developed with IFES support.	Target: 7 / Actual: 15	A+
Output 1.2 Comprehensive technical assistance provided to EMBs and key stakeholders, including on outreach, electoral technology, cybersecurity, modernization and decentralization	# election officials and other stakeholders trained with IFES assistance (disaggregated by sex, training topic, and audience)	Target: 200 / Actual: 255 (84M;169F)	A+
	# initiatives that support/work towards the full institutionalization of the joint CEC-IFES Training Centre.	Target: 1 / Actual: 2	A+
Output 2.1 Support to Ukrainian civil society organizations on advocacy and outreach to improve access to the electoral and political process	# materials/outreach tools targeting historically excluded groups developed by IFES and IFES-supported CSOs (disaggregated by type, target audience).	Target: 30 / Actual: 70	A++
	% trainees who indicate utilizing knowledge and skills gained from IFES-led trainings/curriculum in their advocacy and outreach efforts.	Target: 70% / Actual: 85%	A+
Output 2.2. Targeted civic and voter education provided to support citizen engagement in political and electoral processes	# students and teachers participating in IFES' civic education programs and initiatives (data disaggregated by audience, gender, new teachers and university)	Target: 2000 new students, 50 teachers / Actual: 4654 new students / (2,346M:1,308F); / 49 teachers (15M, 34F)	A++
	# viewership from IFES-supported informational and voter education campaigns, including national media sources, social media, and other channels (disaggregated by communication channel and audience and gender, where possible)	Target: 250 000 / Actual: 8 226 217	A++
Output 3.1: Technical assistance provided to political finance oversight institutions and political stakeholders to address political corruption	# people trained on political finance and abuse of state resources (disaggregated by audience, sex)	Target: 200 / Actual: 243 (F161; M61; Identified as other 21)	A
	# materials on political corruption and abuse of state resources developed by IFES and IFES-supported CSOs (disaggregated by target audience, topic)	Target: 30 / Actual: 65	A+
Output 3.2 Technical assistance and capacity building provided to electoral justice actors, including the judiciary and police	# judicial and law enforcement personnel trained with FCDO assistance.	Target: 60 / Actual: 164 (M71; F93)	A++
	# educational/guidance materials developed for judges, law enforcement staff, and other stakeholders	Target: 1 / Actual: 3	A+

Annex E – IDLO 2023-2025 Results Framework

Indicator(s)	Milestone(s) for FY23-24	Progress
Legislation underlying the role of HCJ Inspectors amended in line with issued recommendations	Changes in legislation are adopted by the Parliament.	A: Output met expectation / Two (2) draft laws No. 9261 and No. 9483-2 aimed at restoring the disciplinary function of the HCJ were developed and adopted by the Parliament. IDLO’s recommendations on strengthening independence, improving and safeguarding integrity and improving and maintaining efficiency of the DIS were included.
Number of HQCJ procedures improved or adopted	3 procedures improved or adopted	A: Output met expectation / Advised HQCJ on organizing testing for judgeship candidates in times of war, developing a new pool of legislation knowledge tests for judgeship competitions and providing HQCJ with a digital platform for administering tests. Developed a training course on testing judgeship candidates’ skills and knowledge, for which the first part was organized in December 2023. Assisted HQCJ with an IT needs assessment, produced a report on HQCJ IT needs and issued optimization recommendations. Contributed to developing unified indicators for the assessment of integrity and professional ethics of judges.
Open and merit-based competition for vacant judgeship positions carried out	2000 candidates admitted to the judgeship competitions under new legislative framework by April 2024.	B: Output moderately did not meet expectation / IDLO commenced peer reviewing legislative knowledge test questions and respective multiple-choice answers to be used in the merit-based competitions in the Judiciary.
Service of HCJ Disciplinary Inspectors established and disciplinary hearings resumed	Established by April 2024.	B: Output moderately did not meet expectation / Established on 28 November 2024. High Council of Justice appointed 21 disciplinary inspectors and a deputy head of the service.
Indicator(s)	Milestone(s) FY24-25	Progress
HCJ and HQCJ Secretariats restructured in line with issued recommendations	Restructuring happens	B: Output moderately did not meet expectation / While full restructuring was not delivered, IDLO provided meaningful expert inputs into the process. It monitored developments with the HCJ Strategy for 2024-2027 and Action Plan, which has been put on hold until the State Strategy on the Reform of the Judiciary is approved by the President.
Number of HQCJ procedures improved or adopted	10 HQCJ’s procedures are changed following IDLO advice.	B: Output moderately did not meet expectation / IDLO analysed and provided recommendations on improving a number of HQCJ procedures, but not all of them were incorporated by HQCJ. For instance, the regulation on the SDI adopted by the HCJ on 19 December 2024 did not incorporate IDLO’s recommendations.
Open and merit-based competition for vacant judgeship positions carried out	HQCJ assisted with designing open and merit-based competition for vacant judgeship positions and transparent qualification assessment procedure for sitting judges	B: Output moderately did not meet expectation / IDLO provided expert advice and support to the HQCJ with judgeship competitions, including processing survey data, outlining critical parameters for each stage of the competition, developing test questions on the History of Ukrainian Statehood, helping administer cognitive ability tests. However, at the time of the project completion, all the competitions have not yet been carried out yet.

Annex F – Pro-Integrity 2023-2024 Results Framework

Indicator(s)	Milestone(s) for this review	Progress
# anti-corruption measures proposed, considered, adopted or implemented due to / USG/UK Govt assistance, to include laws, policies, or procedures	5	А++: Output substantially exceeded expectation / During FY1 (2024), Pro-Integrity supported 34 anticorruption measures, including laws, policies, and procedures.
# anti-corruption tools and mechanisms improved or developed with Pro-Integrity support	5	А++: Output substantially exceeded expectation / 11 anti-corruption or integrity promotion tools and mechanisms were improved or developed with Pro-Integrity support in FY1 (2024).
# partnerships and coalitions for effective corruption prevention, detection, and deterrence / supported with Pro-Integrity technical assistance	3	C: Output substantially did not meet expectation / No progress has been observed in establishing international partnerships or coalitions with Pro-Integrity's support. No partnership has been established.
# oversight actions taken by non-government organizations receiving Pro-Integrity assistance	5	А++: Output substantially exceeded expectation / 9 oversight actions were conducted focusing on integrity-check of the candidates for key judicial and anti-corruption positions.
# organizations pursuing their own performance improvement priorities in anti-corruption with USG/UK Gov-t capacity strengthening support (CBLD-11)	1	А++: Output substantially exceeded expectation / Pro-Integrity exceeded the year target by actively engaging 6 national organizations to increase their performance in anti-corruption and integrity promotion.
# anti-corruption knowledge products produced with Pro-Integrity support	2	А++: Output substantially exceeded expectation / In FY1 (2024), Pro-Integrity almost reached the Life of Activity (LOA) target, producing 32 products.
# Pro-Integrity supported measures designed to promote or strengthen the participation of marginalised groups in the anti-corruption field	3	C: Output substantially did not meet expectation / 0 measures were designed to promote or strengthen the participation of marginalised groups.

Annex G – DTA 2024 Results Framework

Indicator(s)	Milestone(s) for this review	Progress
Objective 1: Digitalisation for Economic Revitalisation
Number of business-related permits and licensing services digitized	3	C: Outputs substantially did not meet expectation / The transition from paper-based to digital systems required in-depth process re-engineering to simplify and standardize workflows. This demanded extensive coordination among government agencies and stakeholders to ensure compliance and usability, as well as substantial legislative and regulatory updates to enable their digitization. The delays made it impossible to complete in time.
Objective 2: Digitalisation for Transparent Recovery
Percentage of reconstruction projects substantively improved relative to those closely monitored as the result of civic oversight and scrutiny	15% of projects substantively improved	A: Output met expectation / 15% (74 projects monitored and 11 improved) / In total, the TI-U team analysed 74 recovery projects and related procurements, sent 11 appeals on the detected overpricing to supervising entities, controlling and law enforcement bodies.
Objective 3: Digitalisation for Good Governance
Number of eServices implemented in corruption-prone sectors	4	B: Output moderately did not meet expectation / 2 services were introduced. / The target was not met as the transfer of responsibilities and resources from TAPAS to DTA took longer than anticipated to align workflows, secure approvals, and onboard new team members.
Ukraine's score in the Online Service Index within the UN E-Government Development Index (EGDI). EGDI considers factors such as online services, telecommunications infrastructure, and human capital.	0.82	A++: Output substantially exceeded expectation / In September 2024 the UN released its eGovernment Survey 2024 (https://publicadministration.un.org/egovkb/en-us/Reports/UN-E-Government-Survey-2024), ranking 193 countries based on the UN’s eGovernment Development Index (EGDI). Ukraine ranked 30th with an EGDI index score of 0.8841 out of 1, up from 46th in 2022.
Cross-cutting
Number of women and representatives of vulnerable groups empowered with new knowledge and skills through project training programs	2,000	A+: Outputs Moderately Exceeded Expectation / 2,202 representatives of vulnerable groups, including: / - 1,581 women / - 74 persons with disabilities / - 6 veterans / - 81 IDPs / - 393 persons living in rural areas / - 51 persons living in conflict-affected areas / - 16 persons over 65 y.o.

Annex H – SOERA 2023-2024 Results Framework

Performance Indicators	Unit of Measure	Y3/ FY23 Target	Y3/FY23 Actual Total
# SOEs in the database with up-to-date and accurate information (Custom)*	# SOEs	20	0
# trainings on SOE reform or public property management as a result of USG assistance (Custom)	# trainings	2	7
Percentage of participants who demonstrate increased knowledge of SOE reform strategies and policies after training or capacity building interventions.	%	90%	100%*
# new participants engaged in SOE reform or public property management webinars (Custom)	# participants	500	2196. Measured annually
# laws, policies, regulations, or procedures proposed, adopted, or implemented in accordance with international standards to advance SOE reform or public asset management as a result of USG assistance (disaggregated by policy target area) (Custom)*	# measures	12	62
# large SOEs privatized as a result of USG assistance (Custom)*	# SOEs/MOEs	1	0
# small SOEs/MOEs privatized as a result of USG assistance	# SOEs/MOEs	85	70
# state and municipal assets leased as a result of USG assistance (disaggregated by state and municipality) (Custom)	# assets	1,500	1,065
# privatization, leasing, and communications trainings (Custom)	# trainings	4	1
# new conditions, systems, and procedures implemented (disaggregated by national/municipal) (Custom)	# new tools	4	1 plus 43 subsystems
# building and land property rights registered with USG assistance (disaggregated by small and large buildings) (Custom)	# buildings	50	100
# SOEs prepared for liquidation as a result of USG assistance (disaggregated by small and large SOEs) (Custom)	# SOEs	5	0
# CG practices implemented at SOEs such as completed supervisory boards (SBs), new independent SBs, appropriate internal control systems as a result of USG assistance* (disaggregated by CG practice type) (Custom)	# CG practices	2	1
# SOEs with significant improvements in operational performance, as measured by year-on-year increases of 5% or more in their operating profit, as a result of USG assistance (Custom)	# SOEs	2	0
Level of SOE compliance with international standards on disclosure and financial reporting (Custom)	Scaler 1/ below	Level b	Level b
# trainings for CSOs on oversight of SOEs (Custom)	# trainings	2	0
# supported enterprises that institute one or more new management or corporate governance mechanisms, in accordance with OECD principles or international leading practices, to enable enhanced performance as a result of USG assistance. (Custom)	# SOEs	1	1
# supported SOEs that maintain operations at or above pre-wartime levels	# companies	4	3

Annex I: Transition of GGF components to other programmes
Component	Policy area	GoU Counterparts	Post-GGF status
Managed Fund Projects
Business Revitalisation	Support for private sector-led recovery, improving state services for businesses, promoting SME’s export activities	Ministry of Economy, Ministry of Digital Transformation, Export and Entrepreneurship Promotion Office	Transitioned to TIGER. TA will be complemented by enhanced access to finance through IFIs.
Inclusive Economy	TA and capacity-building to support gender equality, inclusion & integration of vulnerable groups into the labour market	Ministry of Economy, Ministry of Veterans	Transitioned to TIGER, fostering integration measures within the private sector development activities.
Economic Hub	TA in fiscal policy and public financial management, including the Ukraine Plan development, macroeconomic forecasting, policy evaluation, and recommendations on economic resilience and transparency in financial institutions.	Ministry of Economy, Ministry of Finance, Parliament’s Temporary Investigative Commission on Economic Security, Ministry of Social Policy	Exit from fiscal policy. Targeted component on PFM will continue under GRP focused on meeting key needs of the MoF.
City UK	TA aimed at unlocking private sector investment, including the reform of the investment promotion agency, improving business regulatory environment, financial ecosystem, and capital markets.	Ministry of Economy	Transitioned to TIGER.
Regional Recovery	TA to the Ministry of Communities and Territories Development to update the State Regional Development Strategy and Transport Strategy, and support to local communities on developing recovery plans and designing recovery projects.	Ministry of Communities and Territories Development, regional and local authorities	Transitioned to TIGER, with a focus on building local capacity to design recovery investment projects.
RePower Ukraine	TA to the Ministry of Energy, including helping update the 2050 Energy Strategy and feasibility studies for renewable energy investment projects.	Ministry of Energy	Transitioned to URES and scaled up.
Innovation ecosystem	Supported Ukraine’s innovation promotion policy, including the 2030 Innovation Strategy of Ukraine.	Ministry of Digital Transformation	Transitioned to GRP’s DIGIT project. Will explore opportunities to maintain innovation work through economic programmes.
Other components
Elections preparation	Contributes towards making Ukraine's electoral processes more effective, inclusive and resilient	Central Election Commission, National Agency on Corruption Prevention	Currently retained in GGF until its close. New programme under design.
Women & LGBTQ+ political participation	Focused on networks and skills for political and civic participation for women and LGBTQ+ communities.	Central Election Commission, Ministry of Communities and Territories Development.	Closed in 2024. Some elements may be reflected in a new programme under design.
Judicial Integrity	Focused on strengthening judicial transparency and accountability and improving the efficiency of adjudication in Ukrainian courts of law.	High Council of Justice, High Qualification Commission of Judges	Transitioned to GRP.
Pro-Integrity - anti-corruption	Designed to be a comprehensive response to anti-corruption needs in the resilience, recovery and reconstruction landscape.	Ministry of Communities and Territories Development and State Agency for Restoration and Development of Infrastructure	Transitioned to GRP as part of DIGIT, with some reduction in ambition due to USAID exit.
DTA - digitalisation	Tackles corruption via the introduction of e-services, ensuring transparent public procurement and usage of open data, improving citizens day-to-day lives and increasing trust in the state	Ministry of Digital Transformation, Ministry of Economy	Transitioned to GRP as part of DIGIT project, with some reduction in ambition due to USAID exit.
State-Owned Enterprise Reform	Focused on improving State-Owned Enterprises (SOE) and Municipal Owned Enterprises (MOE) corporate governance in Ukraine.	Ministry of Economy, Ministry of Communities and Territories Development, State Property Fund	USAID closed the programme and UK has exited from SOE privatisation work.