## ANNUAL REVIEW

Title: Freedom and Resilience Programme
Programme Value £ (full life): £30m		Review date: August 2025, covering July 24-June 25
Programme Code: 301457	AMP start date: / 22/09/2022	AMP end date:31 March 2025 / No-cost extension to 31 March 2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	D0003956.odt (live.com)
DevTracker Link to results framework:	D0005187.xlsx (live.com)

A. SUMMARY AND OVERVIEW
Description of programme

The six countries of the Western Balkans (Albania, Bosnia & Herzegovina, Kosovo, Montenegro, North Macedonia, Serbia) continue to face challenges related to conflict legacies, social and ethnic divisions, political instability and democratic backsliding. These create the conditions for interference of Hostile State Actors (HSA) and infiltration of Serious Organised Crime (SOC) actors. The UK’s objectives in the region are to support a more stable and prosperous Western Balkans that is more resilient to malign influence, and better able to contribute to Euro-Atlantic security.

The Freedom and Resilience Programme (FRP) is the FCDO Overseas Development Assistance (ODA) baseline programme managed by Westen Balkans Department (WBD) that supports programme interventions across all six countries of the region. It complements the department’s other programmes: Western Balkans Security Programme (WBSP); the Democratic Empowerment Programme (DEP), WBD’s support to the Office of the High Representative in Bosnia and Herzegovina (BIH); and the Albania focussed Unlocking Change programme.

The FRP began in April 2022 and builds on past successes of the FCDO’s Good Governance Fund (GGF, 2015-2022) and Stability Programme (2018-2023). It was originally planned to run until March 2025. A no-cost extension to 31 March 2026 was agreed in March 2024.

As set out in the original Business case, the FRP was set up to complement more tactical programming by addressing long-term, structural issues across the region, including ethno-nationalist divisions, gender inequality and gender-based violence (GBV), and a lack of transparency and accountability in government, which create the vulnerabilities that hostile state actors and organised crime groups exploit, and that contribute to political instability and conflict risks. The Programme has interventions in three outcome areas: i) reconciliation and peacebuilding in conflict-affected communities; ii) empowering women and girls and tackling Conflict Related Sexual Violence (CRSV) and gender-based violence; and iii) strengthening government capacity, transparency and accountability. The scope of the FRP allows programme teams at Posts in each country to focus on different areas to align with their specific challenges and policy priorities. Gender equality is strategically considered throughout all three outcomes.

Summary supporting narrative for the overall score in this review

The programme is generally meeting expectations, and the overall score is therefore A. This score is based on a review of individual sub-project results which are submitted to inform a programme level results framework. Results at the programme level are tracked on a quarterly basis.

Projects are achieving their objectives, often in challenging political contexts, and contributing effectively to HMG policy aims. Some projects have encountered obstacles to their smooth running. For example, planned workshops in schools in Serbia were impacted by strikes and protests; and in Montenegro work on merit-based recruitment identified some duplication in activities with other donors, requiring a refocus of the FRP project activities. In these instances, project teams have taken steps to address the challenges. Overall, the level of disruption has not impacted negatively on the delivery of FRP at a Programme level. Regular (6 weekly) catch ups with project teams at Posts ensure that project issues are raised promptly and mitigating actions are in place and agreed.

Major lessons and responses to recommendations from 2024:
FRP is broad in scope and is less restrictive than other programme funding streams on what activity can take place under it. This has positive and negative consequences. On the one hand it allows enables flexibility for Posts using the fund to further activities relevant to their objectives. On the other hand, this can limit the focus of the programme. As WBD begins to think about a successor programme to FRP it should consider the balance between narrow, targeted programming vs greater flexibility in use of a fund. As FRP goes into its final year the number of projects has been reduced by 20%.

One of the challenges faced by FRP has been uncertainty of year-on-year funding, which has restricted opportunities for long-term project planning. The prospect of a 3-year spending review settlement could be an opportunity for WBD to address this through a successor programme.

The last Annual Review noted that FRP was challenging to manage by some Posts and the centre. It recommended reviewing the processes for managing FRP. Over this reporting period, systems and processes have been streamlined, by reducing the number of programme boards and approval layers and delegating more responsibility to Posts. Through this the centre has retained management of the strategic fit of projects under FRP and the overall budget allocations. It has not been considered that these efficiencies have led to a lowering of quality or essential oversight. But this should remain under review. In addition to this a new online reporting system has been developed over this reporting period to streamline results reporting at a programme level. This was not online during the review period but is now in place.

The last Annual Review noted that to improve Social Inclusion outcomes across the programme, the FRP should improve the collection and use of disaggregated data in accordance with the Leave No One Behind agenda. This remains outstanding and should be considered for any successor programming. Lots of activity on this agenda happens across the programme, and it would be beneficial to more systematically capture it.

It was recommended last year that donor coordination should continue and seek a complementary approach to EU accession work and new EU funding mechanisms.
Donor coordination has been impacted over the reporting year with reductions in donor funding across the region. This has made understanding the wider donor environment ever more important and efforts have increased in this area. For example, when USAID paused its ODA programming WBD ran exercises with Posts to map programming impacts and gaps. The centre should further consider its role in donor coordination. With a reduction in development spend, it is important to consolidate relationships with other development partners and maximise the opportunities under the wider EU-UK reset, including the role of the EU-UK Strategic Consultations.

The previous review recommended that WBD and Posts should ensure that changes to the programme over the next 18 months are well communicated and managed and there should be further discussion between WBD and Posts on the future direction of the FRP. Since then, Board level discussions took place to agree the future direction of FRP and any successor programme. Also during this timeframe the UK Prime Minister took the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget is being gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition. This has impacted to some extent how future programming will evolve. WBD remains in close contact with Posts to update them on this process.

The reporting and strategic management of regional interventions was recommended to be reviewed, noting that regional work does not have a distinct tab on the results framework. A regional tab has been added to the Results Framework and the remaining regional projects have involved wide consultation with relevant Posts across the region.

The sustainability of interventions across the programme including exit strategies of activities and dependency of public sector and civil society organisations on UK funding was highlighted last year, recommending that sustainability is embedded into future project cycles. Sustainability remains a core consideration for each FRP sub-project as part of their inclusion under the programme. As FRP has now entered its final year teams have been specifically instructed to focus on sustainability of projects or projects which would yield learning outcomes to support development of a successor programme.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s Theory of Change, including any changes to outcome and impact indicators from the original business case.

The following regional-level Theory of Change (TOC) has not changed since the Business case for the programme was agreed in 2022.This is a high-level TOC for the FRP, and project interventions have their own project specific TOCs which link into one or more of the three outcome strands. As set out in the Business Case, the TOC has been designed as a “Framework for Action” to address the three contributing themes of reconciliation and peacebuilding in conflict-affected communities; empowering women and girls and tackling CRSV and gender-based violence; and strengthening government capacity, transparency and accountability. Each sub-project’s TOC is specific to that project’s intervention and context, with Posts using Country Business Plans (CBPs) to drive strategic programming and ensure programme-policy alignment in their respective countries, utilising the strong contextual knowledge held at Posts. The programme level TOC and assumptions are set out below.

Assumptions (summarised) / 1a Russia’s aggression in Ukraine has been accompanied by malign interference across the Western Balkans, seeking to undermine reforms and countries’ Euro-Atlantic ambitions through increasing disinformation and support for secessionists and those who threaten sovereignty and territorial integrity in the WB. A socially cohesive society fosters the ability and willingness of its members to undertake collective action and improve the societal well-being of all. / 1b UK support and strategic engagement with state institutions, civil society and multilaterals will influence, promote and protect democratic values. UK interventions are do no harm and track positive and negative short-term changes through potential displacement of actors that create “stability” in the region. / 2a Legacies of conflict, contested historical narratives and societal/political extremism exacerbate risk of conflict – manifestations of structural and cultural violence continually put communities at odds with each other and exacerbate societal divisions. By fostering inter-group cooperation across divisions through community initiatives, the foundations of divisive narrative around the conflict will erode – resulting in increased community and societal resilience to divisive narratives. / 2b There is evidence that gender inequality is a conflict driver in the patriarchal world of the Western Balkans and that GBV can fuel instability and conflict; and growing evidence that it can be a driver (and impact) of violent extremism and serious and organised crime. Tackling harmful social norms, building media capacity, promoting accountability, security and justice and strengthening multi-sectoral service provision can all have a positive impact on preventing and responding to GBV. / 3a The UK has committed to putting women and girls at the heart of its work on conflict and stability. When women participate meaningfully in political life, policymaking is more inclusive, with the needs and concerns of women better represented. Increasing women’s meaningful and representative participation in decision-making processes, including conflict prevention and peacebuilding will contribute to strategic outcome 1 of the current UK NAP on WPS. / 3b There is strong evidence to suggest that preventing and responding to GBV supports the promotion of gender equality; as well as women’s political, economic, social and digital inclusion. Holistic and multi-sectoral approaches to GBV are more likely to have impact: coordinated interventions operating at multiple levels, across sectors and over multiple timeframes are more likely to address the various aspects of and therefore have a greater impact on tackling GBV. / 4a Institutionalisation of citizen engagement and civil society networking are important in securing government accountability and transparency. By engaging civil society in governmental dialogue, accountability will be improved. This also contributes to building trust between state institutions, civil society and citizens. / 4b State institutions that are agile and responsive to deteriorating living conditions for citizens will maintain public support for reform. This forms a virtuous circle of responsive to citizen needs, improved services, trust in institutions, and demand for improved services.

The assumptions are considered to remain valid but have not been specifically tested for the purposes of this annual review.

The broad outcome areas of the TOC remain valid in the region. Rising tensions (northern Kosovo and southern Serbia, and ongoing political deadlock in Bosnia and Herzegovina) have demonstrated the continuing relevance of peacebuilding and reconciliation, conflict prevention, and the need to address deep-rooted structural challenges.

The outcome pillar relating to women and girls remains of particular importance. Within the WBD portfolio, FRP is well placed for long-term work on gender equality and social inclusion (GESI) including dedicated interventions with the specific aim of contributing to gender equality, as well as mainstreamed best practice.

The last Annual Review recommended further consultation and consideration the pros and cons of using a more directive, centrally held, TOC vs TOCs specific to individual WB country contexts. This remains an issue for discussion for successor programming once FRP closes.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

FRP has three outcome areas as stated in the business case:
1. Improved reconciliation and peacebuilding outcomes for conflict-affected communities, with a focus on building connections across conflict divides and strengthening access to transitional justice processes.
2. Empowerment of women and girls through tackling CRSV, GBV and promoting women’s meaningful participation in decision-making processes.
3. More transparent and accountable governance through building state capacity and strengthening civil society.

The impact is: Western Balkans Six (WB6) countries are more stable, inclusive and resilient to the risk of violent conflict.

FRP is making definite contributions across its three outcome areas. As described below, each Post using the programme to fund a project will link that project’s success directly to one, or more, of these outcome areas, and use their own TOCs to govern the logic of the intervention.

Examples of projects contributing to broader change (e.g. government policy/ societal change) relating to these outcome areas include:

In North Macedonia FRP support has led to the development of gender equality and social inclusion analysis methodology to review governmental policies and regulations. It has also produced six corresponding policy briefs, including the topic of increasing women in executive positions in central and local public administration.

In Kosovo a project supporting the Kosovo Rehabilitation Centre for victims of Torture’s (KRCT) advocacy efforts have contributed meaningfully to the extension of the mandate of the State Commission for recognising and verifying the status of sexual violence victims of the Kosovo conflict, enabling hitherto unknown survivors to come forwards and assert their legal and other rights.

The Mostar project on inclusive spaces in BIH concluded this year after a 3-year implementation period. It has helped deliver a marked increase in community interest, activism, and ownership, which has catalysed further investment in both indoor and outdoor spaces across the city. Crucially, attitudes have shifted with citizens and local authorities now more active in maintaining and utilizing public spaces. Marginalised groups, particularly persons with disabilities, women and youth have benefited significantly, and public spaces are more accessible, safe and inclusive. According to the endline survey, one of the most telling indicators of change is the decrease in the percentage of youth expressing a desire to leave the city, suggesting a strengthened sense of belonging and hope for the future. The City of Mostar has submitted a joint application with FRP’s implementing partner to the Federal Government for continued investment in project activities, demonstrating good sustainability and endorsement of the project’s activities.

FRP has supported the Macedonian National Development Strategy (NDS). On 29 October, the Macedonian Parliament adopted the Law on the 2024-2044 National Development Strategy (NDS) and the Law on the implementation of the NDS for the period 2024 – 2028.

In BIH FRP has supported the Srebrenica Memorial Centre which is now an internationally recognised research centre, developing global links to further atrocity prevention and peacebuilding tools (including with the UK Defence Academy), including narratives and memorialization of diverse groups of war victims, such as Roma and women from Eastern parts of BiH and helping deliver the 2024 UNGA resolution.

In Montenegro, FRP support enabled reforms to the Criminal Code and training for judges, resulting in landmark 40-year sentences for femicide cases in 2025. A draft definition of femicide has also been developed for future inclusion in law. These changes strengthen judicial responses to gender-based violence and help ensure justice for GBV survivors.

Nevertheless, one of the challenges for FRP is that it is difficult for projects operating in 12-month cycles (with often no more than a 10-month implementation phase) to demonstrate meaningful contributions towards outcome level results. The examples cited above refer to projects that have been able to operate across multiple years.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

FRP is delivering effective results for FCDO in the WB region and should continue until its planned end date. Final project work has been agreed following the recent confirmation of funding for FY 25/26. The type of programming activity which FRP, as an ODA baseline programme, can achieve continue to remain relevant – particularly around stability and reconciliation, and gender equality. As such it remains a significant programming tool within the wider WBD programming portfolio.

## C. DETAILED OUTPUT SCORING

FRP is a regional programme supported by a number of sub-projects delivered through the six Western Balkans Posts. Each sub-project has a logframe which is used to report up at the programme level. Each sub-project contributes output level activity under each of the three Programme level Outcome areas: Reconciliation and peacebuilding; Women and girls are empowered; Strengthened state institution accountability and transparency. On the Programme level Results Framework these are divided into sub-outcome and output areas (see Table 1 below). Previous reviews have reported against the stated output levels of Engagement, Coordination and Capacity in that table.

However, each output level activity that is reported back by Posts for each sub-project links directly to one of the three relevant Outcome Areas, regardless of how it is sub-categorised under the Sub-Outcome or Outputs in the table below. So, this review will report against the different activities that support the Outcome Areas, using these Outcome Areas as Output headings. This will simplify the organisation of the report while maintaining an analysis of what is, in practice, output level activity in support of the programme’s outcomes.

While numbers have varied in-year, FRP has apportioned programme activity broadly as 50% on activity supporting women and girls, 25% on State Institution Accountability and Transparency, and 25% on Reconciliation and Peacebuilding. As such outputs will be weighted in line with these percentages. There is inevitable overlap where sub-project outputs are contributing to more than one outcome area. In these cases, rather than duplicate, the contribution has been allocated to one outcome area only.

This approach responds to a recommendation last year that suggested reviewing output areas, specifically noting that many interventions contain coordination elements across the programme, so it could be superfluous as a dedicated output area.

Table 1

Outcome Areas	Sub-Outcome Areas	Outputs
A. Reconciliation and peacebuilding in communities and states	Social Cohesion	Engagement
B. Women and girls are empowered	GBV prevention and response	Coordination
C. Strengthened state institution accountability and transparency	Transitional Justice	Capacity
	Women's participation
	Civil society promotion of democratic values
	State institution reform initiatives
	Oversight

Output Title	Reconciliation and peacebuilding
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	Yes – see text above

Number of sub-project outputs contributing to programme output. See annex for individual projects.	Project progress	Overall score
14	All sub-projects met their programme level output contributions	A

Briefly describe the output’s activities and provide supporting narrative for the score.

Fourteen FRP sub-project outputs contribute to the programme level output relating to Reconciliation and Peacebuilding. These have remained on track throughout the reporting period. Examples of specific contributions are as follows.

Through FRP’s work with the Srebrenica Memorial Centre (SMC) an inter-religious dialogue committee was engaged in five different activities and visited more than 10 sites. This is significant because it shows the increasing capability of the SMC’s ability to engage with and influence key stakeholders. The SMC also produced a comparative study on investigating and prosecuting genocide denial in Germany and in BiH, resulting in an in-depth legal analysis and recommendations that was presented and delivered to PO offices and ministries of justice in BiH. This is significant as it demonstrates SMC capacity to expand its mandate from a memorialisation institution to an organization that can positively influence different levels of decision makers.

The Government of the Federation of BiH (FBiH) adopted a new Law on civil victims of war that recognizes children born of war as civilian victims or war and grant them access to rights and services and include new services for CRSV survivors. This included integration of three suggestions for improvement that were submitted by the FRP project ‘Ensuring CRSV Survivors rights on Justice and Redress’. Advocacy towards the implementation of this new legislation across FBiH is part of an ongoing FRP project.

A study was produced on the Roma’s specific traumatic experiences from the war in BiH. No available research on Roma sufferings from the Podrinje district during the 92-95 conflict has existed to date. The study has now concluded and will result in a new project under FRP that will support meaningful Roma participation in transitional justice, reparations, and reconciliation processes. The new project will have a strong focus on needs of Roma survivors of conflict related sexual violence and will draw on the experiences and outcomes of other FRP-funded projects that have made progress in the area of reparations for conflict-related sexual violence (CRSV) survivors in BiH.
A two-year project into the interests of Kosovo-Serbs in the EU Dialogue Process held a series of community forums, expert panels, and opinion polls which engaged a diverse cross-section of Kosovo-Serb citizens. Policy proposals were finalised as planned and produced in line with the project’s objectives, both in terms of thematic focus and professional presentation. The completed papers were shared with relevant institutional and international actors and presented during a dedicated public event in Pristina which brought together a wide range of key stakeholders, including international diplomatic representations, UN agencies, the Kosovo government, civil society organisations, and media outlets.

A total of twenty journalists from Kosovo and Northern Ireland participated in a project which focused on Peace Journalism skills. Through, exchange visits, mentoring and workshops, the project developed a network of journalists in Kosovo who are able to apply the principles of “peace journalism” to their work, enabling them to report in an ethical matter that promotes understanding and reconciliation.

The missing persons project in Kosovo made notable progress in empowering civil society and families of missing persons. By February 2025, the Missing Persons Resource Centre held extensive outreach and legal awareness sessions, reaching over 120 family members and resulting in more than 2,000 free legal aid applications and filed 700+ court cases. Collaborations with institutions and awareness campaigns fostered dialogue between communities and improved trust, including cross-community efforts with Serbian family associations.

A project which aims to address the challenges faced by the Albanian minority in Serbia to achieve Serb-Albanian socio-political integration and representation in state institutions met its objectives, including setting up youth caucus groups and organising internships in relevant ministries such as the Ministry for Human Rights and Social Dialogue. A further project aimed at bringing together representative constituencies of boys and girls of high school age from the Serb, Bosniak, and Albanian communities in order to break down barriers of separation and build new, positive relationships was initiated in the latter part of the reporting year.

Over this reporting period FRP’s work with the International Commission on Missing Persons (ICMP) successfully concluded with ICMP taking positive steps to ensure the sustainability of the Missing Person’s Group.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year. There are no changes planned, and FRP is in its final year of implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous year:
No recommendations specific to this area from last year’s review.

Recommendation for the year ahead:
FRP’s work on drivers of instability, including in conflict risk areas such as Kosovo/Serbia and Bosnia and Herzegovina, remain particularly relevant and should be considered for future programming. Learning should be taken from FRP to inform new project design.

Output Title	Women and Girls are Empowered
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	Yes

Number of sub-project outputs contributing to programme output. See annex for individual projects.	Project progress	Overall score
19	Most sub-projects met their programme level output contributions, with one project unable to complete planned activities due to strikes (outside of the project’s control)	A

Briefly describe the output’s activities and provide supporting narrative for the score.

Nineteen FRP sub project outputs contributed to the programme level output relating to women and girl’s empowerment. These have remained largely on-track over the reporting year. Notable achievements include the following:

In Albania our work through FRP has engaged experts to develop a module for the faculty of journalism in Albania to mainstream gender equality. A pool of women experts has been created to be contacted by media outlets for expert opinions in various professional fields. 40 women entrepreneurs and project beneficiaries were engaged in an EXPO for Women entrepreneurs, wherein they were able to exchange experiences as well as acquire training on digital tools, business management training, establish a relationship with financial institutions for potential business loan opportunities, and build their network.

FRP’s project in Kosovo which addresses long-term effects of sexual violence and ending stigmatisation of survivors of sexual violence and their family members during the war met targets including 50% of 49 first-time clients reporting improvements in emotional well-being, self-stigmatisation, physical health, and social interactions. Clinical observations also indicated a 45% improvement in symptoms and 35% of survivors reporting stronger family relationships. The project also made significant progress in supporting survivors’ status recognition. A total of 45 survivors submitted applications to the State Commission, and 5 regained their status through court proceedings, including one from the Court of Appeals.

A planned assessment to establish a foundational understanding of how minority rights and gender considerations are integrated within Kosovo's legal and institutional landscape was completed over the reporting year.

In Kosovo capacity-building trainings were conducted for journalists to enhance their understanding and reporting of gender-based violence (GBV) with greater sensitivity and adherence to ethical standards. A total number 70 journalists were trained. These trainings placed a strong emphasis on recognizing and addressing stigma related to GBV, challenging harmful narratives, and promoting survivor-centred reporting practices.

Integration of domestic violence (DV) cases into the Ministry of Justice database in Pristina, Dragash, Gjilan, and Gjakove exceeded expectations, with a 13.09% increase - surpassing the project’s 8% target. Operational GBV Community Task Forces were established in four municipalities, engaging in outreach such as awareness sessions with high school students and collaborative activities, enhancing local coordination and responsiveness to gender-based violence. Additionally, support services were provided in partnership with Safe House Gjakova and Liria Gjilan, offering psycho-social and legal counselling to 56 women survivors. Also, 156 service providers—well beyond the initial goal of 25—were trained using tailored training to detect and eliminate gender stereotypes, with pre- and post-tests confirming increased knowledge and capacity.

In North Macedonia FRP’s work supported the Ministry of Social Policy, Demography and Youth to complete the evaluation of the Istanbul Convention National Action Plan. It mapped all local GBV services, secured support to local CSOs to deliver services, proposed a plan to have nation-wide GBV service coverage, and drafted the Stratcom on GBV which is now agreed with the ministry. Targeted interventions and policies were also aimed at promoting gender equality and addressing gender-based challenges in judiciary. The working group at the Ministry of Justice that is considering updates to judicial Laws is taking on board the recommendations from the project.

In North Macedonia over 1,100 high school girls across 53 schools nationwide were provided with mentorship sessions, conducted in collaboration with local mentors, focused on career guidance, academic development, and personal empowerment

Across the Western Balkans, FRP’s project on increasing access to justice for the victims and survivors of GBV through increased understanding amongst the judiciary led to 450 judges completing specialised training on handling femicide cases. Post-training assessments revealed a marked improvement in participants’ self-assessed knowledge, with all reporting increased understanding of legal and procedural aspects of femicide cases.

Over the reporting period progress on planned workshops in schools in Serbia has been limited due to school strikes and protests. A no-cost extension was approved, allowing the project to continue until the end of July to provide additional time for implementation.

Through its work supporting feminist change agents 19 women’s rights organisations across the Western Balkans were directly supported. Twelve of the organisations have produced reports, research and articles that contribute to a better understanding of the anti-gender movement, GBV, LGBT+ issues, and gaps in relevant legislation/policy/procedures. Ten organisations, along with the primary project implementer, Kvinna till Kvinna, have engaged in thirteen awareness-raising activities. A comprehensive set of services and support was provided by nine partner organisations to more than 1,200 women. This support helped them make informed decisions and take control of their lives. Partners organised 28 training sessions and 18 workshops across the Western Balkans region, nineteen of which empowered rights-holders in different ways.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year. There are no changes planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous year
Continue to ensure engagement and cooperation with Civil Society Organisations as an element of future work, given that this is a proving to be a key area of FRP success in FY 2023-2024 across the region, and a key practice to ensure sustainability following programme closure.
Response
Engagement with civil society organisations has continued, particularly through FRP’s Democracy and Resilience in the Western Balkans: Supporting Feminist Change Agents. This project directly supports local women’s rights organisations.
Recommendation for the year ahead
- The Western Balkans Thematic Review: Gender Equality Progress in Action (2022–2025) conducted this year has a number of relevant recommendations to be taken into consideration for FRP. These include:
- Leveraging research and evidence to inform policy, programming, and donor coordination.
- Continuing hands-on and diplomatic support to CSOs and WROs, especially in hostile or volatile contexts.
- Sharing successes and lessons with other donors to mobilise additional funding and scale impact.

Output Title	Strengthened state institution accountability and transparency
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	Yes

Number of sub-project outputs contributing to programme output. See annex for individual projects.	Project progress	Overall score
18	Most sub-projects met their programme level output contributions. Due to duplication with another donor one project had to redesign its approach.	A

Briefly describe the output’s activities and provide supporting narrative for the score.

Eighteen FRP sub project outputs contributed to the programme level output relating to strengthened state institution accountability and transparency. These have remained largely on-track over the reporting year. Notable achievements include the following.

In Albania the project which seeks to increase parliament’s responsiveness to citizens’ concerns demonstrated success through a public hearing on disability issues which showcased clear articulation of ten citizen-generated recommendations on accessibility and inclusion. Crucially, responses from key ministries demonstrated a willingness to assess and integrate these proposals into existing or future policies, indicating a growing responsiveness to citizen input within parliamentary processes and policymaking.

In Kosovo FRP’s work to improve public procurement has supported development of a digitised case management system to provide an open and transparent process allocation and data capture thus reducing the risk to corruption. This is now in use for all procurement review board decision making. 78% of procurement board decisions were in line with expert recommendations, just below the 80% target for Q4. However, the number of decisions was much higher than previously so in terms of absolute numbers there was a much higher alignment with expert recommendations. Substantially, though the project managed to convince the Board to provide justification why they do not agree with expert recommendations, and this has been incorporated in the case management system.

The project which supports Kosovo’s public oversight and accountability in public institutions did not meet all its stated objectives, but reported positive results including, advancing institutional accountability by engaging directly with three of state institutions. A total of 15 recommendations were submitted across the three institutions, addressing systemic gaps such as the lack of access to inspection reports, unstructured licensing procedures, and the absence of transparency in decision-making. Some responded positively by publishing seven new Board decisions and acknowledging the project’s recommendations during internal discussions. One, however, was unresponsive. The project also monitored 12 recruitment processes, exceeding the target number of five.

In North Macedonia our project to support improved governance helped development of a portal to communicate the use of KPIs in monitoring of the Government’s work. Over this year the portal became active, and the data is being used by the media to report on governance issues and to hold government to account.

In Montenegro our work on merit-based recruitment is split between two projects: one with an NGO on the demand side of merit-based recruitment, and one supporting the supply side with government. On the demand side amendments were initiated to the Law on Civil Servants and Employees through a working group and public discussion. Analytical work on service contracts, the appraisal process, the acting mandates and the new legislative changes, provided evidence-based findings and insights into improvements that can be made in state institutions. A long-standing recommendation was adopted, namely the elimination of discretionary authority in the selection of candidates for executive, expert and expert-managerial positions. Due to an overlap of work with another donor under the supply side of the project, implementation of results in this area have slowed while new workstreams were agreed. The project is now focused on support to the Administrative Inspection and Appeals Commission where a functional analysis of the work of commission’s work has been developed. Ten control checklists for key areas under their jurisdiction have been developed for more efficient oversight and a streamlined method has been put in place for monitoring the implementation of corrective measures, in line with recruitment related laws at both central and local levels. Cooperation with the Agency for Prevention of Corruption, focusing on the protection of whistleblowers within the public sector has been initiated.

Also in Montenegro, FRP’s work on strengthening legislative processes and inclusive policymaking began its pilot phase in which it completed a needs assessment of women MPs. This gave an insight on their position and needs. It is now being used for creating a tailored mentorship programme for women MPs.

FRP’s project in Serbia which strengthens citizen engagement and participation in public policy processes in local communities enabled 38 activists from selected organisations to enhance their advocacy and communication skills, develop structured advocacy plans, and strengthen their collaboration with local decision-makers. In parallel, eight civil society organizations successfully implemented advocacy campaigns with measurable results at local and national levels. These included the co-financing of clean energy infrastructure in schools (Kraljevo), institutional steps toward the declaration of a new nature reserve (Vojvodina), and new municipal bylaws enabling civic use of public spaces (Ćićevac).

Through a programme to help end discrimination and promote equality in Serbia a planned Equality Impact Assessment (EIA) methodology reflecting perspectives of women and people with disabilities has been finalised, and a guide for CSOs and activists engaging in anti-discrimination support at a local level has been drafted. This provides an explanatory and CSO adapted review of antidiscrimination legislation, knowledge on how to recognise and record acts of discrimination and how to offer advisory support to potential victims. After the development of the EIA, the project engaged with 102 stakeholders and 12 local self-governments in EIA capacity development training and introducing the methodology—more than double the initial targets.

FRP’s work on ensuring open data in Serbia becomes a strategic tool for achieving public goals in a participatory and transparent manner led a range of results across different ministries including: Power BI and advanced data training to 18 State Audit Institution (SAI) employees; support to the Ministry of Justice for improving domestic violence data quality; developing a support map for persons with disabilities for the Ministry of Labour; and established the Government’s Open Data Working Group (ODWG) resulting in 600+ new datasets published. A guide for promoting gender-sensitive, data-based reporting for the media was also produced. This will be further used in training to media and journalists.

Following the tragic nightclub fire in the Macedonian town of Kočani which left more than 60 dead and over 150 severely burned, UK medial staff from the NGO UK-Med deployed to Skopje to provide capacity building support to the national clinicians in addition to specialist burns rehabilitation support to the victims. In lieu of a specific humanitarian funding stream for WBD it was agreed that this should take place and be funded through FRP due to the capacity building activity of the support. Following the successful completion of the burns rehabilitation trainings, according to the pre- and post- training knowledge tests and self-assessments, all participants showed a significant positive improvement, both in their practical knowledge of how to manage and treat burns patients, and also in their own self confidence in doing so.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from previous year:
During the previous review DEP was a new project coming on stream within the Western Balkans Portfolio. Several projects moved from FRP to DEP during this process. The previous review noted that this caused some confusion for reporting because project results became split between the two programmes, recommending that this be clarified by this review.
Response
All projects have finished moving between the two programmes and reporting for this year only includes projects delivered under FRP.
Recommendation for the year ahead:
This is a broad outcome and programming area. For any future programme design the team should consider how best to focus its activities.

D: VALUE FOR MONEY

Key cost drivers and performance

FRP is comprised of sub-projects managed by Posts across the region. These sub-projects are primarily delivered through NGOs and multilateral organisations. Cost drivers across the portfolio will typically include operational costs, such as implementer staff time and administrative costs for running projects, sub-granting to local organisations, delivering workshops and training events. FRP does not deliver any capital/infrastructure spend. Teams have fed back that more budget certainty, enabling multi-year planning, could help drive costs down by broadening the supplier base that is available. Some of the larger delivery partners can manage donor budget uncertainty better but tend to have higher overheads than working directly with smaller local NGOs.

Prior to project proposal approval, budget lines are agreed with the Programme Responsible Officer before being finally agreed by Post Programme Boards.

VfM performance compared to the original VfM proposition in the business case

Economy
Management of input costs is largely devolved to Posts delivering each intervention, with initial project budgets reviewed prior to project approval. Consultant fees and salaries remain the highest cost driver. In previous years budgets were reviewed both by Posts during project development and again at headquarters. In a move to improve internal efficiency the secondary review has now been dropped.
Efficiency
- At a programme level, capturing the speed/ ease at which the programme produces outputs is complex to measure because of the diverse number of projects feeding into broad output areas. However, at a project-by-project level, programme teams continue to ensure efficient programming through arranging regular meetings with sub-partners and ensuring adherence to regular reporting procedures.
- Standardised proposal forms for each sub-project have ensured a consistent and considered approach, for example by being endorsed by the relevant country programme board to confirm how projects will contribute to achieving Country Business Plans and the FRP programme.

Effectiveness
- In the original business case, outcome level results were to include instances when partners translate technical assistance or capacity building into substantive policy commitments by host governments. FRP has shown some evidence of this, such as through the City of Mostar submitting a joint application with the implementing partner to the Federal Government for continued investment, and also, ownership of the National Development Strategy in North Macedonia. There remains concern, though, that some other work will be harder to sustain without donor funding. Wider reductions in donor support and internal politics which, in some instances, have also led to government budgets being stalled, will also impact on this.
- The impact of one year funding cycles has also impacted on the ability to develop programmes that lead to longer term change. It is noticeable (see above) that the FRP projects which seem to contribute most to longer term change are those that have been able to run uninterrupted over a number of years.

Equity
- FRP is the strongest programme in the portfolio on promoting gender equality, with a specific work strand on women’s empowerment, and several projects focused on addressing and responding to GBV, including historical CRSV.
- Several projects have a strong focus on youth, and the project in Mostar includes disability rights.
- A number of projects are focussed on minority rights across ethnic divides.

Overall Cost-Effectiveness
FRP remains a significant pillar of the Western Balkans department programming portfolio. It’s work on conflict prevention and reconciliation remains particularly relevant within the overall portfolio. It also adds value in projecting values and complementing the policy work of Posts.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money. This is particularly evident on a project-by-project basis where individual projects have their own VFM approach articulated in project proposals, monitored at Post. At the Programme level, sub-project ideas are discussed prior to approval to ensure that they are a strategic fit within FRP’s three output strands. This facilitates best use of the fund by ensuring that programming money and activity remains aligned with the priorities agreed in the Business Case.

E: RISK

Overview of risk management

For the FRP, each project has a risk register which is managed by the respective Posts. The programme-level risk register (based on the detailed risk register annex in the Business Case) is reviewed regularly by the programme team. Programme risk is discussed between the programme team and Posts at six-weekly meetings. Additionally, Western Balkans Department has a central risk register which covers both policy and programmes and this is reviewed every six weeks.

A significant risk over this reporting period has been uncertainty around future budgets and planning for the final year of the programme. This has been managed well by teams at Posts who have worked closely with implementing partners on mitigations such as no-cost extensions.

There has been no change to risk appetite.

Update on Partnership Principles

Partnership Principles are not formally assessed in project design under FRP.  Projects are designed at each Post across the region.  Decisions on project design are informed by Post’s understanding of the local context on a case-by-case basis.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

As noted in previous Annual Reviews FRP has had challenges with budget clarity since its inception. Teams have consistently managed this well.

At the last annual review FCDO’s new finance system had been causing challenges for teams to navigate. Support from FRP’s central finance team has helped navigate this. Teams are now all on the same finance system.

It was reported last year that quarterly reporting of FRP projects to FCDO centre had been patchy due to staff shortages, but this has been on track for this reporting period.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Last year the FRP annual review was conducted by two independent consultants. The review team also included a member of the FRP programme team working in an independent capacity. The review included field visits to Belgrade, Mostar, Sarajevo and Pristina. As such it was deemed that a lighter-touch desk based annual review was justified for this year’s annual review. Each project has an individual logframe which teams use to monitor progress. Select indicators from these are used to inform the programme level logframe. This is updated each quarter with highlights presented to the WBD Programme Board, ensuring internal scrutiny and transparency in the programme’s operation.

A new online results reporting system using Power BI has been developed over this reporting period. It is now operational but was not in place for the purposes of this review. This will, hopefully, make results reporting and reviewing of results more efficient for the remainder of FRP.

The external MEL partner (Ecorys) has been supporting UK programming in the Western Balkans since 2019. Ecorys is permitted to spend 20% of its time on FRP to ensure that cross-portfolio (i.e. with ISF) synergies can be identified and evaluated.

Evidence

Due to the annual cycle of programme funding projects which would ordinarily have a 2-3 year implementing period are often extended once funding is secured. Teams will make choices whether, and how, to extend projects based on prior performance.

Over the reporting period a Western Balkans Gender Equality in Action thematic review was conducted, covering four programmes in the region, including FRP. The review provides clear evidence of FRP’s contribution to Gender Equality and Social Inclusion (GESI) and Women, Peace and Security (WPS) outcomes. Specific FRP results highlighted include fostering inclusive dialogue platforms in North Macedonia to challenge harmful gender narratives, supporting survivors of historical conflict-related sexual violence in Kosovo and Bosnia and Herzegovina, and enabling women’s rights organisations to counter the anti-gender movement. The review evidences improved coordination and survivor-centred services for GBV and CRSV survivors, legal reforms recognising children born of wartime rape, and increased women’s participation in public life. Lessons from the review emphasise the importance of longer-term programming to achieve sustainable outcomes, and the need for targeted technical support to GBV implementing partners to strengthen their capacity. These findings demonstrate FRP’s adaptability and effectiveness within the broader Western Balkans portfolio, while underscoring the value of sustained investment and tailored support in complex and challenging environments.

Some projects have had formal evaluations. The Mostar project and Gender Mainstreaming at Universities project in Bosnia and Herzegovina have had final evaluations, with the Mostar evaluation feeding into potential new project design. A final evaluation on the Recruitment project in Kosovo was submitted by the in June 2024.

In the last Annual Review it was noted that FRP’s results data could be better disaggregated against variables identified in the Leave No One Behind agenda. This remains an area for improvement.

Learning

The following forums for sharing learning are used:

- Fortnightly meetings of Heads of Programme with Western Balkans Department.
- Monthly meeting of the Western Balkans Programme Network (open to all).
- 6-weekly meetings of London team with teams from each country.
- Regular meetings of the Gender Focal Point network, including quarterly meetings with FCDO Europe Director for Mediterranean and Western Balkans and Senior Gender Champion.
- Ecorys Helpdesk.

Date of last narrative financial report	Because FRP is made up of projects led by Posts, there is no overall Financial Report or Audited Statement. These are held by programme teams for their projects.	Date of last audited annual statement	See comment in previous box.

Annex A – Breakdown of Projects under FRP for the reporting period July 2024 – June 2025

Location	Project ID	Project Title
Albania	301457-415	Increase parliament's responsiveness to citizens' concerns – Albania
Albania	301457-443	Invest in Women: Accelerate Progress towards gender equality in Albania
Bosnia and Herzegovina	301457-413	Ensuring CRSV Survivors rights on Justice and Redress in BiH are advanced in accordance with International Standards
Bosnia and Herzegovina	301457-419	Improving public space and public discourse in Mostar – BiH
Bosnia and Herzegovina	301457-434	Srebrenica Memorial: Truth, Dialogue, Future – BiH
Bosnia and Herzegovina	301457-440	Peacebuilding: supporting marginalised (Roma) communities in BiH
Bosnia and Herzegovina	301457-457	Srebrenica Outreach Project
Bosnia and Herzegovina	301457-458	Fighting impunity and promoting transitional justice in BiH
Bosnia and Herzegovina	301457-448	Secondment to OHR Sept 2024-March 2025
Bosnia and Herzegovina	301457-418	University and Gender Mainstreaming – UNIGEM – BiH
Kosovo	301457-412	Supporting institutions and communities building an inclusive society in Kosovo
Kosovo	301457-439	Support civil society to increase public oversight and accountability of Kosovo public institutions
Kosovo	301457-444	Strengthening of public procurement system in Kosovo
Kosovo	301457-454	Secondment for the Head of the OSCE Mission in Kosovo
Kosovo	301457-411	Dealing with Conflict Legacy in Kosovo
Kosovo	301457-441	Reflecting interests of K-Serbs to formulate policy proposals – Kosovo
Kosovo	301457-447	Improving the capacities of journalists in Kosovo on peace journalism
Kosovo	301457-428	Addressing effects of sexual violence and ending stigma that survivors face in Kosovo
Kosovo	301457-438	Addressing effects of gender based violence in Kosovo and empowering survivors to fight stigma – Kosovo
Montenegro	301457-431	Enabling Merit Based Recruitment in Public Administration (Montenegro)
Montenegro	301457-432	Strengthening Demand for Merit Based Recruitment
Montenegro	301457-452	Strengthening legislative processes and inclusive policymaking
North Macedonia	301457-406	Reinventing Governance in North Macedonia
North Macedonia	301457-404	Gender gap action – enabling equal opportunities for girls and young women in North Macedonia
North Macedonia	301457-424	Prevention Against Gender Based Violence in North Macedonia
North Macedonia	301457-445	United Voices for Gender Equality: Building support for Gender Inclusive Policies - North Macedonia
North Macedonia	301457-446	Bridging Gender Bias in Judiciary - North Macedonia
North Macedonia	301457-456	Emergency Medical Team response to nightclub fire
Regional	301457-442	Regional Missing Persons phase 2
Regional	301457-410	Fight Against Gender Based Violence and Femicides in the Western Balkans
Regional	301457-433	Democracy and Resilience in the Western Balkans: Supporting Feminist Change Agents
Regional	301457-453	Strengthening Access to Transitional Justice processes
Regional	301457-455	In-House delivery roles under FRP ODA programme
Serbia	301457-409	Strengthening citizens engagement and participation in public policy processes in Serbia
Serbia	301457-435	Open Data for Open Societies – Serbia
Serbia	301457-436	Leave No One Behind: Fostering Equality and Protection against Discrimination – Serbia
Serbia	301457-437	Empowering Albanian Youth and Enhancing Integration Into Serbian Society – Serbia
Serbia	301457-450	Skilled Youth, Empowered Communities Serbia ('Spark')
Serbia	301457-449	Serbian Equality Commission