Title: Building Resilience, Inclusion and Diversity through Girls’ Education (BRIDGE)
Programme Value £ (full life): £39.9m		Review date: November 2025
Programme Code: [AMP ID 301459]	AMP start date: 31/08/2022	AMP end date: 31/10/2026

Summary of Programme Performance
Year	2023	2024	2025	2026
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003448.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004779.xlsx
DevTracker Link to Addendum to the Business Case	https://iati.fcdo.gov.uk/iati_documents/D0006692.odt

## A: SUMMARY AND OVERVIEW

Description of programme

Jordan continues to face multiple crises: economic, stability, social, and climatic. This past year has been marked by several significant events, most notably the fall of the Assad regime; continuation of the Israel/Gaza crisis; aggression between Israel and Iran; and a change in US leadership and subsequent reductions in aid.

With a high debt-to-GDP ratio of 91.5%[1], Jordan’s fiscal space continues to narrow; there is limited capacity to invest in services and infrastructure for its current population, let alone the significant refugee population it hosts. Jordan’s modest economic growth, estimated at 2.5%[2], has constrained industrial competitiveness and contributed to persistently high unemployment, which stands at 21.3%[3] overall and approximately 46%[4] among youth.
[1] Jordan’s debt hits JD 35 billion, now 91.5% of GDP public_debt_quarterly_report_-q1_2025_.pdf
[2] International Monetary Fund. (2025, October 7). Jordan — IMF reaches staff-level agreement on the fourth review under the Extended Fund Facility and the first review of the Resilience and Sustainability Facility arrangement. Retrieved from https://www.imf.org/en/News/Articles/2025/10/07/pr-25331-jordan-imf-agreement-on-4th-rev-under-eff-and-1st-rev-of-resil-and-sfa [imf.org] International Monetary Fund. (2025). IMF DataMapper: Jordan profile. Retrieved from https://www.imf.org/external/datamapper/profile/JOR [imf.org]
[3] Department of Statistics (Jordan). (2025, June 16). Unemployment rate reached 21.3% in Q1 2025. Retrieved from https://dosweb.dos.gov.jo/unemp_062025/ [dosweb.dos.gov.jo]
[4] World Bank. (2025, April 15). On the job: Expanding economic opportunities for youth, women, and refugees in Jordan. Retrieved from https://projects.worldbank.org/en/results/2025/04/15/on-the-job-expanding-economic-opportunities-for-youth-women-and-refugees-in-jordan [projects.w...ldbank.org]

The Government of Jordan has demonstrated generosity in hosting refugees, expanding services at the detriment of quality and taking the burden share of the costs (estimated currently at 73% in the education sector[5]). Political support for hosting refugees has been challenged, leading to a reduction in benefits for refugees, which have contributed to increased levels of vulnerabilities and food insecurity[6]. Refugees are increasingly resorting to negative coping mechanisms such as involvement in illicit activities, early child marriage and child labour[7]. These are key factors which affect school attendance and learning outcomes.
[5] AAI MoE Reporting
[6] Socio-economic Survey of Refugees in Host Communities 2024
[7] World Bank and UNHCR. (2023). Supporting Refugee Education in Jordan: Financial and Social Impacts. World Bank Publications.

The fall of the Assad regime has enabled many Syrian refugees to return (167,000 registered refugees between February and July), however as of August 2025, 481,116 remain in Jordan (20.3% in camp settings). While many initially indicated that they would return to Syria at the end of the school year, due to a rise in instability in Daraa and Sweida and lack of basic services available across Syria, intention surveys have indicated increased hesitation and delay. The International Community recognises that Jordan will require support while Syrians residing in Jordan continue to have refugee status, and that some refugees will chose never to return to Syria.

The Building Resilience, Inclusion and Diversity through Girls’ Education programme (BRIDGE) supports the Government of Jordan (GoJ) and the international community in delivering on the Jordan Compact’s[8] commitment to provide access to quality education in a safe, inclusive, and tolerant environment for all children in Jordan, regardless of nationality. Through a combination of financial aid and technical assistance, BRIDGE helps the GoJ provide education to the most marginalised children, including refugees, enabling continued access to the national education system, a cornerstone of the Jordan Compact. This investment in human capital is essential for Jordan’s economic development and long-term stability, while promoting social cohesion and resilience among vulnerable groups. Ensuring equality in education access aligns with the Humanitarian, Education and Resilience goal of the Jordan Business and Country Plan (BCP).
[8] The Jordan Compact was an agreement between the GOJ and the international community to combine humanitarian aid with long-term development support in response to the Syrian refugee crisis. Since the signing of the Jordan Compact in 2016, 160,000 refugee children have accessed the national education system on an annual basis.

Following the 2024 Annual Review, a Business Case (BC) Addendum was approved to:

1. Increase financial aid to the Ministry of Education (MoE) through the Accelerating Access Initiative (AAI), ensuring continued support for refugee and out-of-school children.
2. Extend the programme timeline to better align with the academic calendar and support the third and final year of AAI implementation.
3. Ensure funding for camp school operational costs and provision of assistive devices and transportation for children with disabilities in camp settings.
4. Reprofile the programme’s financial allocations, including a reduction in technical assistance funding.

As a result of the BC Addendum, the total financial value of the BRIDGE programme increased from £30 million to £39.9 million.

Summary supporting narrative for the overall score in this review

This is the third Annual Review of the programme, covering the period from April 2024 to September 2025. The third year of BRIDGE aligned with the second year of AAI 3.0 operating from August 2024 to July 2025.

During the past year, the focus has been on strengthening the efficiency and effectiveness of the AAI mechanism, ensuring camp school operations were fully supported, as well as strengthening FCDO’s coordination and technical leadership on refugee education. Significant steps were made in all three areas:

  1. Strict adherence by MoE and donors to an agreed schedule of progress meetings, submission of reports, prioritisation exercises, and joint monitoring visits.
  2. UNICEF was fully funded by FCDO, EU and Switzerland to maintain camp school operations in Zaatari and Azraq, ensuring that 35,000 children continued to have access to learning.
  3. Improved coordination between MoE and donors due to the inclusion of a Senior Donor Coordinator in the DCU (Development Coordination Unit in the MoE) structure (programme-funded role) and FCDO technical leadership of the AAI donor group.

The reduction in Technical Assistance funding has been offset through successful utilisation of the centrally managed programmes, including ERICC (Education Research in Conflict and Crises), INSPIRE (Inclusion Support Programme for Refugee Education) and K4DD (Knowledge for Development and Diplomacy). This has included extended research on the efficiency and effectiveness of support to refugee education, which has enabled evidenced discussions between the Ministry and donors on the way forward. The remaining BRIDGE TA has been used to fund the Senior Donor Coordinator role and a Fiduciary Risk Assessment (FRA).

While challenges remain with capacity in the MoE, there is now a clear pathway to address any capacity deficits. Given global reductions in ODA and lack of clarity in future allocations, plans to shift towards a more harmonised financing model have also been put on hold. The FRA highlighted the importance of reviewing the pros and cons of off-budget vs on-budget support and ensuring that off-budget support was captured in the GFMIS if practical.

Despite a volatile and challenging year, BRIDGE has maintained progress across indicators and subsequently scored an A.

Major lessons and recommendations for the year ahead

Detailed recommendations can be found throughout the report, particularly under the outputs, and are consolidated in Annex A. Key lessons from this review and recommendations for the year ahead include:

  1. The fall of the Assad regime in Syria has provided scope for some refugees to return. However, continued instability in Syria (due to internal and external actors), lack of livelihood opportunities, and limited access to basic services, make safe and voluntary return challenging for others. It will therefore be important to ensure that the GoJ continues to receive support in hosting refugees and allowing access to the national education system, while factoring in the unpredictable returns environment. As this is the final year of the programme, UK education support for refugees will need to be continued in the successor humanitarian business case. A sudden exit would be detrimental to those refugee children remaining in Jordan. Intention surveys have indicated that returns are strongly linked to both the school year and availability of education services in Syria. This highlights the role that provision of education plays in irregular migration.

  1. During the final year of BRIDGE, it is recommended that we utilise some of the remaining technical assistance funding to support the MoE to develop the successor programme to AAI. The first stage will be to present a set of costed options to the MoE, which could include providing support which would enable the GoJ to support the reconstruction of the Syrian education system (e.g. training Syrian teachers or support on curriculum development). Areas of possible support were identified through ERICC funded research, however activities have not been costed or agreed with the GoJ. This stage should also consider opportunities to expand the current donor pool and explore opportunities to move away from solely grant financing (investments, public-private partnerships etc).

  1. The numbers of students in the camp continues to decrease and education services will require rationalising. Operational costs are expected to reduce as numbers decrease, and this presents an opportunity to restart conversations around transition of camp school operations from UNICEF to the MoE, which offers far greater VFM and more longer-term stability for refugee children. Depending on costs involved and policy decisions by the GoJ regarding the future of the camps, transition may need to be a staged process. BRIDGE should also continue to influence strategies that address inequality in provision as well as support for the most vulnerable children: the new Education Strategic Plan (2026-2030) presents an opportunity to set revived targets on refugee children.

  1. There remains a challenge in Jordan with data on out of school children due to delays in conducting a new census and disagreements and sensitivities around current population data. This has meant it has not been possible for UNICEF to conduct a study on out of school children as planned. While it will be impossible for a study to now be conducted during the lifetime of BRIDGE, we will continue to utilise enrolment data to highlight early drop-out of Syrian refugees (especially boys), from Grade 7 onwards. Meanwhile, UNICEF has been able to undertake work in creating early warning systems in schools which help identify and retain at-risk students. Despite delays, largely due to the sensitivity of the topic, UNICEF have now initiated the social and behaviour change study on drug usage amongst school aged children. This will provide useful direction going forward, that can be utilised effectively in FCDO’s work on protection, security and stability.

  1. DCU programme management of AAI has improved over the last year, most notably with the addition of the programme funded role who has enabled a stronger coordination link between the MoE and donors. Having consistent and on-time progress updates, as well as the opportunity to participate in annual joint donor-MoE monitoring visits, has enabled a shift from focusing predominantly on inputs and outputs, to outcomes and using evidence for better prioritisation and decision making. However, accessing timely data remains challenging and this sometimes limits evidence-based decision making when prioritisation is necessary. Priorities for this next year will be to strengthen financial and grant management (in line with FRA recommendations), revision of consultancy contracts so assessment of staff is based on performance, improving capability for fundraising, and strengthening data analytics through use of better statistical applications, such as Power BI.

  1. The UK should continue to prioritise its leadership role on refugee education and system strengthening in the MoE. This should continue to not only target programme management and planning in the DCU (as set out above) but also support the MoE on technical and policy leadership on refugee education, enabling the GoJ to make evidence-based decision-making. The MoE has appreciated all the technical work FCDO has led over the past year, as this enabled them to plan and prioritise for this year, however moving forward the MoE should have their own capacity to conduct technical and policy work. This is more critical than ever to ensure that those refugees remaining in Jordan receive equitable services and have increased learning opportunities. Continued technical leadership and coordination of the donor group has also grown in demand due to reductions in technical expertise in respective donor agencies,

How will the programme respond to changes in UK development policy?
Firstly, the UK will look to more efficiently leverage innovative financing, exploring opportunities such as the International Finance Facility for Education (IFFEd). IFFEd effectively multiplies the impact of donor dollars so middle-income countries that house large numbers of refugees, like Jordan, can make critical investments in quality education and skills.  Aligned to this, the UK will also support the MoE to strengthen public-private partnerships, through offering technical expertise and mechanisms to enable effective collaboration.

Secondly, the UK will provide increased levels of in-house technical expertise to drive forward system strengthening, enabling the MoE to more efficiently and effectively respond to changes in refugee demographics, ensuring that the system can respond in an equitable and cost-effective way, and that drives up quality for all.

Third, the UK will look at how it can further leverage connection to UK expertise, including working with universities and the edtech sector to support Jordan modernise the education sector, including through the use of AI to support teaching and learning. FCDO will engage more strategically with the British Council and the Department of Business and Trade (DBT) to identify opportunities, such as the Education World Forum, to strengthen connections and access UK expertise.

Finally, just as FCDO has done with the locally engaged programme funded role and engagement of the MoE in the series of refugee education workshops and research pieces, the UK will look at how it can strengthen internal MoE capacity to drive forward the direction on refugee education, strengthening their use of evidence to inform policy making and strategy.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change (ToC) for the BRIDGE programme, outlined in the Business Case, was updated following the last Annual Review and approval of the Business Case addendum to refocus on relevant activities (this was a key recommendation). This is set out below:

The inclusion of the accountable grant to UNICEF enabled not only camp schools to remain open through covering salaries to Syrian Assistant Teachers (SATs) and Incentive Based Volunteers (IBVs), but provided additional opportunity to improve the infrastructure, provide support on menstrual health and hygiene, and school-based violence prevention activities. These additional activities directly targeted inequities which currently exist in camp settings as opposed to schools in host communities.

Flexible technical assistance has focused on two key activities: the inclusion of a programme funded role in the DCU, aimed at improving coordination between the MoE and the donors, and management and reporting of the AAI programme; and a Fiduciary Risk Assessment, enabling further tranches of funding to be made to the MoE. FCDO CMPs have also been effectively utilised to support broader technical work, evidence generation and policy dialogue.

The assumptions underpinning the ToC were also revised following the last AR and continue to remain relevant.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

As per the programme logframe, the impact will be measured through Jordan’s ranking in international assessments, namely the Programme for International Student Assessment (PISA)[9] and Trends in International Mathematics and Science Study (TIMSS)[10]. Data collection for the next PISA assessment will be undertaken in 2025, with results available in 2026. The most recent TIMSS assessment took place in 2023, and results were published in December 2024. The results demonstrate improvements, however Jordanian students at both 4th and 8th grades were still below international averages.
[9] PISA measures the ability of 15-year-olds to use their reading, maths and science knowledge to meet real-life challenges. PISA is conducted every four years. The 2022 results for Jordan indicated a decline in learning outcomes in mathematics compared to 2018, and similar levels in reading and science. In both cases, the results were less that the average across OECD countries.
[10] TIMSS assesses grade 4 and grade 8 students’ performance in maths and science. TIMMS is also carried out every four years.

Data from PISA and TIMMS enables us to determine whether learning outcomes have improved at a national level. Although the programme has had to reduce interventions that focus on quality (due to overall donor cuts), a key argument for maintaining donor support to refugee education is that it brings additional resources into impoverished host communities. It is also important to measure as many of the strategies that Jordan has implemented to accommodate the refugees are generally considered to have a negative impact on quality. Therefore, utilising PISA and TIMMS results provides some high-level indication of the impact.

The outcome indicators specified in the logframe, and progress against them (where applicable), are set out in the below table:

#	Outcome Indicator	Progress
Sub-outcome 1: More vulnerable children in school and learning
1.1	Net enrolment rate in AAI schools (KG2 - 12)	2022/23 – 80.3% / 2023/24 – 80.4% / 2024/25 – data available in 2026 / National target - 84.9% / The breakdown above highlights that while rates at primary remain high, access to KG remains constrained and boys are continuing to drop out earlier than girls.
1.2	Completion rate-basic level	2022/23 – 96.1% / 2023/24 – 95.4% / 2024/25 – data available in 2026 / While the aggregate completion rates remain high, disaggregation by gender shows that a higher completion rate for female students (97.4% vs 93.4%).
Sub-outcome 2: More efficient and effective education system for the inclusion of vulnerable children, including refugees
2.1	Successful transition of camp-based activities to MoE	This year’s milestone for the transition of camp-based activities to MoE was for 25% of activities to be transitioned. Plans developed with the GoJ in 2023 were halted in 2024, initially pending key decisions on whether Syrian assistant teachers and other incentive-based volunteers could be formally employed, or whether, like teachers, would need to be substituted with Jordanians. Compounded by further reductions and delays in funding from other AAI partners (notably the US) and reduction in UNICEF capacity, transition of activities has not progressed with the GoJ. During AR meetings this was raised with both UNICEF and the Minister of Education. / With the growing reductions in numbers of refugees in camps, it may be more possible to transition activities in years ahead, especially if numbers of refugees reduced substantially. Transition to the MoE would offer better VFM than working through UNICEF as the overheads would be lower.
2.2	Number of BRIDGE recommended policy or administrative changes on improvements in education outcomes adopted by MoE allowing access to the national education system for refugee students.	Access has been maintained for refugees through MoE’s annual waiver of documentation requirements. Support for refugees has in part been due to FCDO’s leadership on AAI, secondment of an FCDO staff member to the MoE to support coordination and planning, as well commissioning and running a number of workshops to support prioritisation, review lessons learned from the past 6 years, and identify areas for improved efficiency and effectiveness of support to refugees.
2.3	Percentage of schools evaluated as acceptable or better in accordance with the standards of the Quality Education & Accountability Unit	2022/23 – 39% / 2024/25 – 84% (all schools) / Type I (Camp Schools): Only 33.3% of schools were rated “acceptable or better,” and none reached the “good” level, and 33.3% rated acceptable / Type II (Double Shift Schools): 83% of schools achieved “acceptable or better” ratings, including 8% rated “good” and 75% rated “acceptable.” / These variations highlight continuing equity challenges, with camp schools constrained by higher teacher turnover, limited facilities, and resource scarcity. Targeted support and differentiated interventions remain essential to ensure equitable improvement across all school contexts.

The outcome indicators were revised following the approval of the Business Case Addendum which refocused BRIDGE on maintaining access to the national education system for refugees.

1. The following changes are now recommended for the final year of the programme under sub-outcome 2:
  1. Indicator 2.1 on transition should remain but also include rationalisation of services, especially where there is reduced demand for services going forward. Should transition remain politically or financially untenable, focus will be on improving efficiency and effectiveness of camp school operations.
  2. Indicator 2.2 should capture both qualitative and quantitative influence of FCDO leadership on refugee policy.
  3. Indicator 2.3 should revise targets to focus on Type I and Type II schools to drive forward progress in these schools in line with national level improvements.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme should continue. Progress against outputs is either in line with, or exceeding, expectations, ensuring continued access to education for the most marginalised. Through FCDO’s leadership on AAI, the GoJ has been able to maintain access to the national education system for refugees, and fulfil commitments set out in the 2016 Jordan Compact. The inclusion of UNICEF in the programme has enabled camp schools to remain open, ensuring access for refugees in camp settings. The business case addendum also enabled the inclusion of a programme funded role (as part of the flexible TA), which has supported the delivery of improved management, reporting and coordination of AAI. FCDO CMPs have been effectively utilised to generate timely evidence generation and support policy dialogue on refugee education. Education continues to underpin key outcomes of the UK’s Country Business Plan, including inclusive growth, gender equality and inclusion, resilience of vulnerable refugees and Jordanians, and stability.

This is the final year of the programme. Looking ahead, although the fall of the Assad regime has allowed some refugees to return to Syria, the country is still not considered stable enough to trigger the cessation of refugee status and returns continue to be on a solely voluntary basis. In excess of 110,000 registered refugee children are predicted to need access to the education system for at least the next academic year. Should stability in Syria be sustained, and the education system gradually recovers, the expectation is that this number will progressively decrease over the next 5 years. However, with current assessments from Syria showing a challenging baseline with over 40% of schools destroyed and many functioning schools now triple-shifting, it is recognised that a return to pre-conflict status will take time. There will be some refugees who also decide never to return. Additional to this, just as the GoJ required support to expand education services to meet the demographic surge caused by the refugees, it will need support to contract and rationalise services in an equitable and efficient way if the demand declines significantly. There is an opportunity to reduce or end policies that have had a negative impact on quality – such as double shift schools or temporary contract teachers. Support to these areas should be prioritised in the successor humanitarian business case, as well as a more clearly articulated an exit strategy, should circumstances allow.

## C. DETAILED OUTPUT SCORING

Output Title	Increased access to education for vulnerable children in AAI schools
Output number:		1	Output Score:	A
Impact weighting (%):		50	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress	Achievement
1.1 Cumulative number of children including refugee in NFE centres	5472 / a. dropout: 4,200 / b. catch-up: 1,272	5368 / a. dropout: 3765 / b. catch-up: 1,603	Achieved / dropout: 90%, catch-up: 126%
1.2 Number of students with disabilities enrolled in AAI 3.0 schools, (Grades 1-10)	4,100	4,932	Exceeded / 120%
1.3 Number of refugees (Syrian, non-Syrian refugees) in Type I, II, and III schools whose tuition fees are paid for through AAI 3.0 support.	158,054 / a. Syrian : 154,668 / b. Non-Syrian : 3,386	159,374 / a. Syrian : 155,779 / Non-Syrian : 3,595	Achieved / 101%
1.4 Number of Syrian students have access to formal schools (aged 6 to 17 years), KG2 centres (aged 5 years) and non-formal education centres (aged 12 to 18 for boys and 12 to 20 for girls) in refugee camps in Jordan.[11]	37,090	37,381[12] / (49% Female)	Achieved 100%
[11] These numbers are already calculated within the overall total number of refugees
[12] United Nations High Commissioner for Refugees, Operational Data Portal – ‘Total Registered Syrian refugees’ https://data.unhcr.org/en/situations/syria/location/36, accessed 21 September 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 focuses on improved access to formal and non-formal education for all vulnerable children, regardless of nationality. This output is delivered through the UK’s contribution to the AAI). Overall, this output scores A. Indicator milestones were increased following the previous AR and have been achieved or exceeded.

1. Indicator 1.1 measures the provision of non-formal education (NFE). Overall, 5,368 children have been supported with NFE, either through the dropout or the catch-up programme.
  1. The dropout programme aims to equip children who have dropped out of school with a range of skills to support them on their pathway back to education, or towards training and employment. 3,765 children were supported under the drop-out programme.
  2. The catch-up programme targets younger children aged 9-12 who have been out of the education system for at least one academic year. In total there are 76 catch-up centres through which 1,603 students were supported.

Indicator 1.2 focuses on the inclusion of children with disabilities, in alignment with the National Three-Year Action Plan for Inclusive Education. A total of 4,932 students with disabilities have been enrolled in AAI schools from grades 1-10, significantly exceeding the initial target of 4,100 and reflecting the strong demand from parents.

Indicator 1.3 records refugee tuition fees covered through AAI funding. AAI aims to ensure that all refugees in AAI schools have their tuition fees covered by the programme (the same for textbooks).

Lessons learned:

  1. AAI has enabled MoE to support the most vulnerable regardless of nationality and refugee status. 49% and 36% of students supported by the dropout and catch-up programmes, respectively, were Jordanian. This indicates vulnerabilities among host communities are also being addressed by AAI, in line with a conflict sensitive approach. Widening inequality or failure of the government to deliver for one marginalised group and not another, has the potential to damage social cohesion and lead to instability.

  1. It remains difficult to assess quantitatively whether NFE offers good VFM. Although field visits highlighted many positive stories of the NFE programme, understanding of long-term impact and whether the programme is effectively reaching all children out of school requires robust longitudinal data and analysis, which is not currently available. It is therefore recommended that one of the 4 TA positions identified under US funding to AAI focuses on NFE to support the MoE in addressing the effectiveness and efficiency of the approach.

  1. The MoE continues to rely on AAI to support inclusion of children with disabilities. The demand for services in communities has increased significantly, however limited GoJ funding for inclusion has restricted widespread scale up. FCDO has been working with the MoE and other partners to strengthen inclusion within the new ESP. It will be difficult to increase the allocation for children with disabilities in AAI without cutting core costs, such as teacher salaries or tuition fees, which are deemed essential.

  1. Differences in MoE support on inclusion in AAI were observed during field visits. Regional differences were noted particularly in regard to support for children with disabilities. Teachers in Aqaba were particularly vocal about the challenges they were facing. Likewise, there continues to be significant differences between the quality of education in boys’ schools vs girls’ schools.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

An additional indicator (1.4) was added following approval of the Business Case Addendum to reflect support to UNICEF to maintain camp school operations, and the numbers of children who will be affected if the camps school closed.

Progress on recommendations from the previous AR and recommendations for the year ahead.

Progress on recommendations from the previous Annual Review is outlined below:

Recommendations from last year	Progress
1. Non-Formal Education (NFE): / FCDO should strengthen NFE indicators in the logframe (e.g., graduation and dropout rates) and assess how many catch-up students transition to formal education to better evaluate value for money and impact.	An additional indicator was added under output 2 to capture the number of children graduating from catch-up classes and the drop-out programme who successfully transition back to formal education. / Field visits highlighted numerous success stories from the NFE programme. Students expressed deep appreciation for the opportunity to return to learning, describing the centres as safe and supportive environments where they not only received academic help but also found a new community and made friends their age. Many students requested the introduction of a fourth cycle to extend learning, enabling children to transition to Tawjihi levels. / Teachers in formal schools who are caregivers of children with disabilities (CWD) also advocated for the inclusion of their children in NFE cycles, emphasizing the importance of accessible education for all.
2. Out-of-School Children: / FCDO should use findings from the new study to guide strategic engagement with MoE and partners, addressing both supply and demand barriers and informing a broader strategy linked to NFE.	Despite timely planning, UNICEF were unable to progress on the out of school children study due to significant differences between the census data and the MoE data. It was agreed that the study would need to be conducted following the next census (2026/27), however due to timing, this would now not be possible under BRIDGE. This activity should be included in the successor programme given it’s importance.
3. Dropouts / Protection: / FCDO and partners should investigate dropout causes and enhance prevention and retention efforts. Emerging concerns include the link between drug trafficking and school withdrawals among refugee children.	A contribution arrangement way established with UNICEF Jordan to address school dropout among vulnerable children, especially Syrian refugees. UNICEF are working at the school-level to identify and retain at-risk students. It also integrates harm reduction and behaviour change strategies to tackle emerging issues such as drug use and trafficking, aiming to shift community norms and promote safer, more inclusive learning environments.
4. Costing: / FCDO and partners should explore covering full refugee education costs, develop robust policy and budget analysis, and better understand tuition fee structures and their impact on schools.	This has been a priority of the ERICC workshops which have engaged the MoE on the efficiency and effectiveness of AAI and encouraged more transparent discussion around costings.

Recommendations for the year ahead:

Expansion of Dropout Programme Options: One of the key recommendations to the MoE is the addition of a fourth cycle to the dropout programme. This new cycle will offer an extended learning pathway for students who have successfully completed the initial three cycles, providing them with a grade 10 certificate and increased ability to transition to Tawjihi courses (upper secondary).

Expansion of the NFE programme to include children with disabilities: Field visits highlighted that not all NFE centres were currently accessible by children with disabilities.

Increased focus on addressing gender and regional differences: Regional differences have not been observed before (focus had been largely on camp schools vs host community schools). Future monitoring visits must continue to monitor differences and identify strategies to address any inequities in support.

Output Title	Improved teaching and learning of children in Type I, II, and III schools, enabling children to catch-up and progress through the system
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

*No target for MDTs was included in the logframe.
Indicators	Milestones for review	Progress	Achievement
2.1 Provision of special education (Learning Support Teachers (LST) and Multidisciplinary Team (MDTs members)	360 LSTs / 168 MDTs	360 LSTs (95% Female) / 157 MDTs (94% Female)	Achieved / 100% / 93%
2.2 Provision of assistive devices for children with disabilities (UNICEF)	878	898	Achieved 102%
2.3. Absolute number of contracted (a) teaching and (b) nonteaching staff supported by AAI in Type I, II schools.	(a) 6,369 / (b) 1,824	(a) 6,141 / (b) 1,651 / (52% female)	Achieved / (a) 96.4% / (b) 91%
2.4 Number of primary or secondary textbook or other teaching and learning materials (TLM) provided with AAI assistance.	158,054 / a. Syrian : 154,668 / b. Non-Syrian : 3,386	159,374 / a. Syrian : 155,779 b. Non-Syrian : 3,595	Achieved / 100% of refugee children
2.5 Number of children who graduate from the NFE catch-up programme that successfully transition back to formal education	700	1050 (490 catch-up / 560 dropouts)	Exceeded 150%

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 focuses on support for teaching and learning, including for children with disabilities. This output is also delivered through the UK’s contribution to AAI. Overall, this output scores an A.

Indicator 2.1 relates to staffing for inclusive education in both public schools and NFE centres, specifically through the deployment of Learning Support Teachers (LSTs) and Multidisciplinary Teams (MDTs). 360 LSTs (95% female), were assigned to 138 AAI schools, in line with the original target. In addition, 157 MDTs were assigned to schools. The MDTs are comprised of various specialists including occupational therapists, speech therapists, physical therapists, and vision and hearing rehabilitation therapists. Although the target for the LSTs was met, specialised human resource shortages were reported to have delayed recruitment processes.

Indicator 2.2 relates to the provision of assistive devices for children with disabilities. Overall, 898 children were provided with assistive devices following screening.

Indicator 2.3 focuses on Type I (camp) and type II (double shift) schools having the necessary human resources to support vulnerable children. Overall, 6,141 and 1,651 teaching and non-teaching staff were supported with renumeration. These results were in line with the targets.

Indicator 2.4 measures the provision of teaching and learning materials. All refugee children whose tuition fees were covered received free textbooks, in line with the target in the AAI results framework.

Indicator 2.5 is a new indicator, as recommended during the last AR. The number of children who transitioned back to formal education was significantly higher than expected, indicating that the positive impact of the NFE programme.

Lessons learned:

  1. Assistive devices are often reusable. Assistive devices have been provided over several years and while many stay with children for their entire learning journey, many are only used for a limited time and are reusable. It would be useful to better understand the impact of this provision in terms of VFM.

  1. There is a significant gender issue in recruitment of LSTs. There are very few male LSTs, and it remains a challenge to recruit them in the public education system. Informal reporting from the MoE suggests that the majority of male trained LSTs are employed in the Gulf, where there is a strong demand for their expertise and salaries are considerably higher. AAI focuses in-school support for children with disabilities from Grade 1-6, where schools are largely mixed, and so the impact is limited. However, older boys with disabilities in segregated systems are less likely to receive ongoing support due to lack of male LSTs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 2.2 which tracked the number of students with disabilities accessing educational tools, support devices, and assistive technology in schools, was changed to reflect the exclusion of this indicator from AAI by the MoE and the inclusion of a more targeted approach by UNICEF. Also, as many of the assistive devices are reusable and remain in schools for use with other children, it would be better to have an indicator which showed percentage of children with disabilities with improved learning outcomes as a result of these devices. This will be explored with UNICEF to assess whether this is possible.

Progress on recommendations from the previous AR (if completed) and recommendations for the year ahead

Progress on recommendation from the previous Annual Review are outlined below:

Recommendations from last year	Progress
Ensure appropriate analysis to assess the viability and sustainability of diversity of learning resources (particularly through technology).	This recommendation was deprioritised given the narrower focus of AAI 3.0. However, more recently FCDO have started to engage with the Edtech Hub and AI observatory to identify where support may be useful.
Address challenges that emerged during the inclusive education pilot before any scale up.	As noted above, inclusive education continues to remain a challenge due to insufficient funding and budgetary allocation by the MoE. The field visits highlighted regional differences which can now be addressed in terms of support for children with disabilities. Ambition on inclusion and where it should sit have formed part of the discussions for the new ESP. FCDO have engaged with GIZ who have more expertise on inclusive education and lead on discussions on inclusion with MoE.

Recommendations for the year ahead:

  1. Inclusion: While AAI has contributed to enhancing inclusion, there remains a challenge with scaling up support to children with disabilities. Inclusion will be mainstreamed through the four domains of the ESP, and it will be important to collectively advocate with other AAI donors and the EPDG that sufficient resources are allocated for this to ensure equitable scale up across the country.

  1. Shift the focus to more quality improvement for the most marginalised schools: Should reductions in numbers of refugee students free up any budget resources, focus should shift to interventions that can strengthen the quality of teaching and learning. For example, this could include ensuring that the most vulnerable schools are able to effectively benefit from the MoE digitalisation plan and new AI tools designed to support learning.

  1. Consider providing LSTs and MDTs in NFE centres: It is recommended that if NFE classes are to open up to children with disabilities, LSTs and MDTs will be necessary to support their full inclusion.

Output Title	MoE at national and sub-national levels have capacity to generate, analyse and use data and evidence of decision making on vulnerable children
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicators	Milestones for review	Progress	Achievement
3.1 Number of research pieces on direction setting on refugee education that inform MoE and donor decision making.	1	7 research pieces completed; 2 workshops undertaken with MoE and donors; 1 webinar	Exceeded
3.2 DCU effectively and efficiently utilising evidence in AAI decision making as evidenced by reporting and prioritisation workshops	Quarterly reports /prioritisation workshops demonstrate use of evidence	Reporting demonstrates increasing use of evidence	Achieved

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 aims to ensure data and evidence inform policy making. It was added at the start of the review period to ensure that BRIDGE measures the impact of the flexible technical assistance component, the support to UNICEF, and effective utilisation of FCDO CMPs. It also recognised the need to increase focus on system strengthening, especially in light of declining sectoral aid. Through the deployment of a programme funded role into the MoE, technical capacity to utilise data and evidence has improved significantly. Unfortunately, due to ongoing discrepancies between the census data and MoE EMIS data, the out of school children’s study was not able to progress. This was out of UNICEF’s control and therefore not reflected in the score. This output has met expectations on the first two indicators and therefore scores an A.

Indicator 3.1 focuses on improving MoE evidence-based policy and programming with regards to AAI. In absence of large-scale TA (which was reallocated to financial aid under the approved Business Case Addendum), FCDO has effectively collaborated with other actors including WB, UNICEF and UNHCR to tap into the helpdesk functions under ERICC, INSPIRE and K4DD. This includes:

  1. Evidence reviews:
- Drugs, youth and education in MENA.
- Investment in refugee education and stability, security and migration.
- The role of education in countering mis- and dis-information in MENA.
  1. Skills mapping of refugees in Jordan.
  2. Poverty swift survey, which included a module on school drop-out.
  3. Support to Syrian refugee education:
    1. Two-part study looking back and forward, examining the efficiency and effectiveness of donor support through AAI
    2. Two workshops reviewing findings and discussing priorities moving forward.
    3. Webinar to share findings with education sector partners (including MoE, NGOs, UN, DPs)

Indicator 3.2 refers to the improved technical capacity in DCU to utilise data and evidence in decision-making on AAI. Throughout the year there have been a series of notable improvements that have strengthened the delivery of AAI. These include:

Joint monitoring visits with MoE and donors. This enabled the DCU to see the real-world impact of the interventions and gather qualitative evidence which is not always visible in the quantitative data. This evidence was utilised to make a number of changes to the AAI programme, including the addition of the fourth cycle of NFE, as described above.

Quarterly reporting and quarterly meetings to discuss emerging challenges and priorities. The quality of these meetings and reporting has been significantly enhanced by the FCDO programme funded role. Feedback from AAI donors has been highly positive around the addition of this role.

MoE engagement and participation in a Wilton Park event on inclusion of refugees in national education systems. This provided an opportunity to learn from other countries facing similar challenges and apply this learning in Jordan.

Lesson learned:

FCDO is effectively deploying centrally funded resources to complement BRIDGE and support overall response efforts. Under ERICC, FCDO Jordan has been able to utilise £0.5m of support, reducing the need to tap into BRIDGE’s budget and further reduce financial aid.

The deployment of the programme funded role has been extremely effective, offering significant VFM benefits over contracted technical assistance. The relationship between FCDO, donors and the MoE has been strengthened due to the improved quality of reporting and collaboration on prioritisation of activities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 3.3 (which focused on UNICEF’s out of school children study) was removed before this AR due to the reasons set out above.

Progress on recommendations from the previous AR (if completed) and recommendations for the year ahead

This was a new output, therefore there are no recommendations from the previous Annual Review.

Recommendations for the year ahead:

1. Continue to utilise FCDO CMPs, but expand this engagement with other CMPs, such as SCALE and the Edtech Hub. ERICC should continue to be utilised in developing the successor programme to AAI, building on the research reports and workshop findings conducted this year.
2. Expand technical capacity in the DCU through managing the US Government to Government grant which has an allocation for up to 4 roles. The programme funded role, based in the DCU, is in a position to manage and deploy this additional technical capacity. Focus should be on policy development and data and grant management.
## D: VALUE FOR MONEY

FCDO uses the “5 Es” Value for money (VFM) framework (cost-effectiveness, economy, efficiency, effectiveness, equity) to ensure that UK Aid maximises impact.

Cost-effectiveness
It currently costs the GOJ approximately £200m per annum to educate 160,000 refugees through the national education system under the AAI programme. 27% of this cost was covered by donors during the 2024/25 academic year, demonstrating the strong burden sharing arrangement.

Allowing refugees to access the national education system avoids the need for a parallel education system.  Parallel education systems for refugees offer limited advantages, especially where the language of instruction is the same in the host and home countries and there are no significant cultural differences that may impact integration.  This aligns with Jordan’s strategic preference for inclusive service delivery that supports long-term stability and development.

Funding through the national system has also attracted development funding, which typically has provided longer term commitments than humanitarian funding and enabled investment in sustainable infrastructure. This has maintained more long-term security for refugees in their learning journey.

Cost-effectiveness data comparing parallel and integrated systems is limited due to the challenge of quantifying the long-term benefits to refugee students as well as the specific interventions needed to support the integration of refugees in host country education systems where the language and culture is significantly different.  However, longitudinal data comparing the experiences of refugees in Lebanon (emergency education – no integration), Turkey (transitional-gradual integration) and Australia (long-term integration) highlighted significant student level advantages of inclusion in national education systems including: improved learning outcomes; lower levels of drop-out; reduced disruptions to schooling and educational continuity (between education levels); and reduced discrimination.

Economy
The unit costs for tuition fees and textbooks continue to be limited to 20 JOD per child per year (40 JD in total for both) under the AAI agreement. These nominal costs were set at the start of AAI and have not increased, despite the MoE raising the costs to non-Jordanians outside of AAI to between 60 JOD and 120 JOD depending on academic level). Positively, this reflects the strong burden sharing arrangement that exists between donors and the MoE as it has shifted the burden further to the GoJ, however, given inflation and rising operational costs, a review of these rates may be necessary to ensure sustainability without compromising quality.

Field visits highlighted that assistive devices provided in the early phases of the programme are now being reused as children no longer need them or grow out of them (e.g. wheelchairs). The reuse of devices is a positive cost-saving measure; however, the programme should consider tracking the impact of these devices on learning outcomes to better assess cost-effectiveness

Efficiency
Support to camp school operations has been shared with the EU and Swiss, with shared reporting. This has reduced the administration burden and programme management costs of UNICEF, demonstrating efficiency.

The reduction in BRIDGE Technical Assistance funding (under the BC addendum) has been offset through the following:

  1. Recruitment of a programme-funded CBS HEO to be seconded and support MoE DCU to improve coordination and delivery efficiency. From a value for money perspective, the insourced CBS HEO is significantly more cost-effective, with an annual cost of £42,000, compared to £85,000–£100,000 for an outsourced consultant and £170,000 for an overseas FCDO staff member. This represents up to a 50% cost saving, while maintaining high service delivery standards and promoting long-term institutional capacity building.

  1. Effective utilisation of CMPs to provide TA (described in more detail above under output 3). As well as a cost saving for BRIDGE, there is also a reduced management burden as contracting and payments are managed centrally. Research also contributes more effectively to central learning and global public goods.

Effectiveness
AAI has supported access to education for the most vulnerable children. The net enrolment rate for grades KG2-12 in AAI schools is now 80.4% compared to the previous year of 80.3%. The results reflect a 95% correspondence with the national target of 84.9%. While slightly below the national target, this result indicates that the programme has been able to maintain student access despite operational challenges, particularly those related to school capacity, socio-economic constraints, and displacement. The programme continues to be most effective at the level of primary education with dropouts steadily increasing from Grade 7 onwards. Future programming should look more closely at addressing these dropouts, recognising that causes are often beyond the direct control of the education system.

Broader evidence from the UNHCR and WFP skills mapping exercise of all working age refugees aged 18-65 (including people with disabilities) highlighted that the skills of refugees educated in Jordan were at a higher level than of those who were educated in Syria. This indicates the potential positive impact that refugees can play on the Jordanian economy while they remain in the country and on return to Syria.

Equity
The total number of children with disabilities in AAI schools has increased from 4,029 to 4,932. This would indicate AAI investments have succeeded in increasing access to formal education for the most marginalised. However, regional disparities (e.g., in Aqaba) suggest the need for targeted resource allocation and teacher training to ensure equitable service delivery.

In terms of gender, a higher proportion of boys (60%) are supported across both the drop-out and catch-up programme. This is expected as out-of-school rates are higher for boys than for girls due to child labour impacting boys at an earlier age than child marriage (cause of female drop out).

Assessment of whether the programme continues to represent value for money:

The programme continues to represent value for money. There remains a strong burden sharing relationship between the GoJ and donors to support the education of refugee students. This highlights the strong political support for ensuring all children, regardless of their status, have access to education. Reductions in technical expertise in the US and EU has led to increased reliance on FCDO technical expertise and the programme funded role will have oversight of US TA going forward. While refugee children remain in Jordan it will be important to ensure they receive equitable education, not only for the benefit of Jordan’s stability and economy but also to support reconstruction in Syria as many who graduate are likely to return. Moving forward the programme will also seek to work with the MoE to increase focus on quality, and where possible, reduce double shifting.

While support to UNICEF has been efficient and equitable in terms of maintaining access to refugee children in camp settings, it would be more cost-effective to transition services to the MoE. There would be reduced overhead costs and increased sustainability of operations. Current allocations made to UNICEF could also be shifted to the MoE, increasing their budget for AAI activities. A review of the roadmap for transitioning services is necessary and dialogue on this with the MoE should be prioritized.

E: RISK

Overview of risk management

The overall programme risk rating remains Moderate. While the operating environment in Jordan continues to be complex, recent risk exposure has been shaped by funding delays, refugee returns, and capacity constraints within the Ministry of Education (MoE) and DCU.

Over the past year, the programme has faced several critical risks:

Risk	Mitigating Action
a. USAID Funding Suspension and Delays / In early 2025 USAID paused disbursement under its G2G agreement with the MoE, creating uncertainty for the Accelerated Access Initiative (AAI). This delayed tuition, textbook procurement, and transportation services for Syrian students, including teachers’ transport in Zaatari Camp and other activities. Despite activities restarting in mid-2025 under the US Regional Foreign Affairs Office, there is some cautious concern that they may be stopped in the future.	Continuous engagement with US Regional Foreign Affairs Office to clarify timelines and emerging issues. / Adjustment of implementation timelines to align with funding availability. / Programme funded role took over responsibility for G2G in DCU
B. Syrian Refugee Returns to Syria / The return of Syrian refugees from Jordan to Syria has introduced unpredictability in student numbers, affecting enrolment and funding allocations. This has made it more challenging for the MoE to prioritise activities.	Ongoing monitoring of refugee movements and intentions (UNHCR, UNICEF and the Jordanian Government).
C. Risk of Camp School Closures / In February 2023, the Government of Jordan (GoJ) committed to assuming the operational costs of schools in refugee camps from UNICEF. However, this decision was paused due to a decline in donor funding, resulting in UNICEF retaining responsibility for camp school operations. Declining levels of funding and no new agreement for the take-over of camp school operations means this poses a risk for continued access for refugee children in camp settings.	BC Addendum approval enabled a contribution arrangement to be established to support UNICEF to cover costs. This was done together with the EU and Switzerland to ensure full costs were covered and reducing the burden on the UK alone.
D. Technical capacity in DCU to manage AAI / Weak technical capacity in data presentation and analysis, coordination and financial management presents a risk to the delivery of the programme.	BC Addendum approval enabled the deployment of a programme funded role in DCU to improve coordination and management of AAI.
E. Availability of data / Differences between census and MoE data limited the ability of UNICEF to conduct the out of school children survey.	Various options were explored with UNICEF and MoE, however it was agreed that the study should be deferred until census data is available, given the importance of having accurate data to inform policy responses for out of school children.

 Update on Partnership Principles
The BRIDGE Business Case outlines how disbursement of financial aid to MoE will be dependent on maintenance of the four Partnership Principles (i. Poverty reduction and attainment of SDGs, ii. Respecting human rights, iii. Strengthening financial management and accountability, and iv. Strengthening domestic accountability).

While the last formal assessment was in September 2023, no new concerns have emerged since, and ongoing monitoring suggests continued alignment. The September 2023 assessment was based on a comprehensive literature review and peer consultation and concluded there was sufficient evidence of GoJ’s commitment to the principles. There have been no notable concerns in the education sector that have warranted further discussion with the GoJ on the principles. The policy of allowing refugees to access the national education system has remained. Providing financial aid to GoJ, including in the education sector, therefore remains an appropriate and effective aid modality.

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Moderate / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable
Is a full FRA update required?	Yes, Completed Sep 2025. The FRA confirmed moderate fiduciary risk, with vulnerabilities around off-budget flows and fraud through overcounting of students or misallocation of tuition fees.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

FCDO works through two key partners: the MoE and UNICEF. UNICEF has been a partner since November 2024.

MoE
Over the past year, FCDO has disbursed £9,000,000 in off-budget support to MoE via the JFA. This accounted for 62.3% of the total JFA budget for the academic year 2024/25.

The primary team responsible for AAI is situated within the DCU. AAI supports three full-time positions within the DCU, comprising a Project Coordinator, a Monitoring and Evaluation coordinator, and a Finance coordinator. Since May 2025 these positions have been under the FCDO programme funded role who has strengthened the monitoring of their performance and identified remedial actions. Engagement with the DCU Director has been positive. There is a monthly high level with DCU and AAI donors to discuss programme progress and any issues.

Reporting has shown significant improvements with the addition of the programme funded role. AAI donors and the DCU director have provided very positive feedback on the programme funded role and are keen to see this position is continued going forward.

UNICEF
FCDO has disbursed £6,400,000 to UNICEF through a contribution agreement, supporting camp school operations during the 2024/25 academic year. Camp school operations are co-financed by EU and Switzerland. During the period November 2024-March 2025, 1,836 Syrian volunteers (46 per cent female) were engaged as Syrian Assistant Teachers and Incentive-Based Volunteers and provided assistance in classroom, administration, outreach to parents and communities, as well as daily support to school operations (this includes regular and generator maintenance, cleaning, and security). 1,805 are attributed to FCDO. During the period April 2025 to August 2025, a total of 2,181 Syrian volunteers were engaged as Syrian Assistant Teachers and Incentive Based Volunteers in refugee camps, of which 371 are attributed to FCDO. This demonstrates effective alignment with donor disbursements and consideration of different donor financial years.

FCDO has met with UNICEF on a quarterly basis, in accordance with the agreement. Additional follow-up or urgent meetings are convened as needed. Field visits to both Azraq and Zaatari camps to monitor the implementation of school operations were undertaken. Reporting remains high quality and informative.

UNICEF were unable to undertake the out of school children study due to ongoing challenges with census data. FCDO are waiting for a formal request to reallocate the resource allocation to supporting more Syrian incentive-based volunteers in camps to support children’s learning.

UNICEF has seen staff loses following overall reduction in global funding. There has been a notable drop in communications around broader issues impacting refugees and strategic engagement on the transition of services to the MoE has stopped. This has been raised with UNICEF during the AR meeting.

Coordination
FCDO has continued to lead the AAI donor group, chairing both quarterly standing meetings and calling ad hoc meetings as necessary. Several of the AAI donors have become increasingly reliant on FCDO’s expertise following cuts to their own technical expertise.

FCDO has also recently assumed a leadership role in co-chairing the Education Development Partners Group (EDPG), as part of its broader coordination responsibilities in the education sector. This role enables a deeper and more influential engagement with the MoE, and step reflects FCDO’s continued commitment to fostering effective collaboration among development partners and supporting strategic alignment with national education priorities.

Compliance
Over the reporting period, the programme manager completed a due diligence assessment of UNICEF, and assured compliance by ensuring regular review of the logframe, consistent monitoring of risks, and robust financial management. The programme is fully compliant across all key areas.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Monitoring and evaluation activities for the BRIDGE programme were conducted regularly throughout the review period, with a strong emphasis on field engagement and stakeholder feedback. Field visits were carried out across the north, middle, and south of Jordan, including joint donor and MoE visits to AAI-supported schools and NFE centres. These visits facilitated group discussions with principals, teachers, parents, and students, enabling the collection of valuable feedback on programme implementation and impact.

Additional monitoring visits were conducted in collaboration with UNICEF to follow up on camp school operations. These engagements included direct conversations with beneficiaries to assess the relevance and effectiveness of the education services provided. High-level visits by FCDO senior management to camp schools also took place, with a specific focus on education programming and strategic priorities.

Feedback gathered during these visits was systematically reviewed and discussed with donors, MoE, and UNICEF. This collaborative approach informed key programming decisions and recommendations, including the recommendation of an additional cycle of the NFE programme.

The AR process was underpinned by comprehensive data collection, updates to the risk register and logframe, and consultations with all donors, MoE, and UNICEF. The process also incorporated revisions and advice from relevant FCDO advisors, ensuring that the review reflected both field realities and strategic priorities.

Evidence
Significant evidence has been generated throughout the review period, as set out above under Output 3.

Due to the sensitivities associated with drug use, UNICEF required a longer timeframe to reach agreement to undertake the Social and Behaviour Change (SBC) study on substance abuse. This study has now been agreed and the implementing partner – NUDGE Lebanon – have recently embarked on the data collection process. Due to the delays, UNICEF have informed FCDO that they will be requesting a no-cost extension to complete activities.

Learning
Over the past year, learning has been driven by continuous field engagement, stakeholder consultations, and evidence gathered through programme implementation. Following the fall of the Assad regime, the programme has utilised intention surveys to help the MOE understand potential impacts on enrolment. While these initially indicated that there would be high levels of returns at the end of the academic year, many of the children who collected their papers have re-enrolled. This is partly due to the political situation in Sweida and Daraa, as well as increased awareness of the challenges faced by those who have returned. This highlights the need for flexible and responsive education planning that can adapt to shifting refugee dynamics going forward.

Another critical learning point is the need to increase support to facilitate the transition of operational leadership and financial responsibility from UNICEF to the MoE. As noted above, this has been limited in recent months due to a drop in technical capacity in UNICEF.

Based on the above, recommendations on monitoring, learning and evaluation include:
1. To continue with regular monitoring visits, joint with the MoE and AAI donors where possible. These should cover all the regions and equal numbers of girls’ and boys’ schools. These are important for collecting qualitative data to inform decisions.
2. Continue to utilise FCDO CMPs to support evidence and data on refugee education, as well as support for designing the new iteration of AAI.

Date of last narrative financial report		Date of last audited annual statement

Annex A: Summary of Recommendations
CMPs: Continue to utilise FCDO CMPs for technical assistance and evidence generation, but expand this engagement with other CMPs, such as SCALE and the Edtech Hub. ERICC should continue to be utilised in developing the successor programme to AAI, building on the research reports and workshop findings conducted this year.
Technical capacity in MoE: Expand technical capacity in the DCU through managing the US Government to Government grant which has an allocation for up to 4 roles. The programme funded role, based in the DCU, is in a position to manage and deploy this additional technical capacity. Focus should be on policy development and data and grant management.
Transition of services: Continue to work with the MoE and UNICEF to develop a staggered roadmap for transition of services. This may be more possible if the numbers of refugees in camp settings significantly decreases.
Financial management: FRA recommendations adopted: strengthen internal audit; introduce third-party monitoring; review pros and cons of off-budget vs on-budget support.
Inequality: Increased focus on addressing gender and regional differences: field visits must continue to monitor differences and identify strategies to address any inequities in support.
Children with disabilities: While AAI has contributed to enhancing inclusion, there remains a challenge with scaling up support to children with disabilities. Inclusion will be mainstreamed through the four domains of the ESP, and it will be important to collectively advocate with other AAI donors and the EPDG that sufficient resources are allocated for this to ensure equitable scale up across the country. NFE should be accessible to children with disabilities.
Quality education: Should reductions in numbers of refugee students free up any budget resources, focus should shift to interventions that can strengthen the quality of teaching and learning. For example, this could include ensuring that the most vulnerable schools are able to effectively benefit from the MoE digitalisation plan and new AI tools designed to support learning.
Expansion of Dropout Programme Options: One of the key recommendations to the MoE is the addition of a fourth cycle to the dropout programme. This new cycle will offer an extended learning pathway for students who have successfully completed the initial three cycles, providing them with additional support for reintegration into formal education.