Business Case – March 2024

Summary Sheet

Portfolio/ Business/Country Plan Summary:

Africa Strategy Objective 3 – Cleaner, Greener Planet
Outcome 3.4 - Nature: Biodiversity safe-guarded and improved through restoration; land, water and natural resources management; scaling the role of nature-based solutions and ecosystem services; and strengthened conservation of endangered species.
Outcome 3.6 - Science & Innovation: Strengthened understanding of weather, climate and natural resource risk through regionally led research and cutting-edge innovation.

Title: Congo Basin Forest Action (CBFA) Programme
Programme summary: / The Programme will address the primary driver of deforestation across the Congo Basin - small-scale agricultural practices by local communities. This will be achieved by working directly with beneficiaries to support transitions to income generated through more sustainable activities - effective community forests, improving agricultural efficiencies, and encouraging sustainable agroforestry. / Reinforced through helping local communities to secure and operationalise land tenure rights, whilst building local and regional capacities and knowledge, with a focus on equipping beneficiaries to continue sustaining activities beyond the programme period. / Co-design and co-ownership at its core. This means ensuring beneficiaries form a key part of the design of programme activities. This reduces the risk of such activities failing once programme funding ends. / These activities will be focused on areas of active deforestation as a result of human activity. These are primarily unprotected forest frontier zones where local populations are encroaching on the forest for economic reasons.
What is the rationale for UK Aid spending?: / CBFA is 100% International Climate Finance. It is principally both a climate and development programme. It aims to support low-income communities through enabling sustainable development practices, strengthening capacities, and enhancing knowledge. / The 2023 White Paper on International Development focused on the need to address extreme poverty, climate change, and biodiversity, highlighting the importance of protecting and restoring nature whilst driving a just transition through sustainable economic transformation. These objectives are at the heart of CBFA. / The 2023 Integrated Review Refresh reiterated the close interaction between development and climate change, stating “climate change and biodiversity loss are important multipliers of other global threats, and are guaranteed to continue to worsen over the next decade. This programme principally addresses this challenge. / The International Development Strategy thematic priority of climate & nature is addressed by CBFA through developing innovative approaches to tackle climate change and protect nature. Programme has the potential to contribute to three of the seven priority initiatives for UK Development Leadership: Delivering lasting solutions to food and nutrition insecurity, including sustainable agriculture; open science for global resilience; and reforming and greening the global financial system. / The UK has a comparative advantage due to the significant leadership role played in the major regional institutions on forests. The UK also has a strong reputation on successful climate programming across Central Africa. This builds upon the leadership demonstrated on forests across the international stage since COP26, which saw the UK financially committing to pledges on nature, forests, IPLCs, and the Congo Basin itself. CBFA validates all of these pledges.
Programme Value: £90m (2024-31)	Country/ Region or Sector: / Congo Basin (including DRC, RoC, Cameroon, and Gabon). Forests, climate, and sustainable livelihoods.
Department/Country Office confirmation of review processes	Africa Programmes & Expertise Department (APEX), Africa Directorate, FCDO
Contact name	Andrew Carr, Central Africa C&E Adviser – Andrew.carr@fcdo.gov.uk
Threshold for final approval of Business Case: Junior Minister (Min for Development & Africa)
Date of Approval of Concept Note	Nov 2021	Name and role of Approver: Vicky Ford, Minister for Africa
Date of Approval of Business Case	dd/mm/yyyy	Name and role of Approver: Andrew Mitchell, Minister for Development & Africa
Programme Code: 301464	AMP Start Date: 06/12/21	AMP End Date: 30/09/32
Overall programme risk rating:	​​Major​

## Contents

## List of Acronyms

AFD – French Development Agency
AG – Accountable Grant
ALIGN – Advancing Land-based Investment in Governance Programme
APEX – Africa Programmes & Expertise Department
ARCAN – Africa Regional Climate & Nature Programme
BB – Best Buy
BC – Business Case
BCR – Benefit-Cost Ratio
BE – British Embassy
BHC – British High Commission
BLF – Biodiverse Landscapes Fund
CAFI – Central African Forest Initiative
CAR – Central African Republic
CBFA – Congo Basin Forest Action Programme
CBFP – Congo Basin Forests Partnership
CDEL – Capital Departmental Expenditure Limit
CF – Community Forest
CFE – Community Forest Enterprise
COMIFAC – Central African Forests Commission
COP – Conference of the Parties
CO2 – Carbon Dioxide
CSF – Critical Success Facts
CSSF – Conflict, Stability & Security Fund
CSO – Civil Society Organisation
C&E – Climate & Environment
Defra – Department for Environment, Food & Rural Affairs
DESNZ – Department for Energy Security & Net Zero
DRC – Democratic Republic of the Congo
EB – Executive Board
ECCAS – Economic Community of Central African States
EME – Early Market Engagement
EQG – Equatorial Guinea
FAO – UN Food & Agriculture Organisation
FCDO – Foreign, Commonwealth & Development Office
FCLP – Forests & Climate Leaders Partnership
FCPF – Forest Carbon Partnership Facility
FGMC – Forests, Governance, Markets & Climate Programme
FPIC – Free, Prior & Informed Consent
FTE – Full-time Equivalent
GDP – Gross Domestic Product
GEMFA (Global Evaluation & Monitoring Framework
GESI – Gender, Equality & Social Inclusion
GHG – Greenhouse Gas
GIBEC – DRC Inter-Donor Group on Environment & Climate
GIZ – German Agency for International Cooperation
GLG – Global Land Governance Programme
Ha - Hectare
HMG – His Majesty’s Government
HMT – His Majesty’s Treasury
ICF – International Climate Finance
ICRAF – International Council for Research in Agroforestry
IFSLU – Investing in Forests & Sustainable Land Use Programme
IIED – International Institute for Environment & Development
ILLUCBF – Improving Livelihoods & Land Use in Congo Basin Forests Programme
INGO – International Non-Governmental Organisation
IPLC – Indigenous Peoples & Local Communities
ITMOS – Internationally Transferred Mitigation Outcomes
KPI – Key Performance Indicator
LoI – Letter of Intent
MCA – Multi Criteria Assessment
MEL – Monitoring, Learning and Evaluation
MOU – Memorandum of Understanding
NBS – Nature Based Solutions
NGO – Non-Governmental Organisation
NPV – Net Present Value
NRM – Natural Resource Management
NTFP – Non-Timber Forest Product
PCD – Procurement & Commercial Department
PCR – Programme Completion Review
PES – Payments for Ecosystem Services
PRO – Programme Responsible Officer
PrOF – Programme Operating Framework
PSED – Public Sector Equality Duty
ODA – Official Development Assistance
OFAC – Observatory of Central African Forests
OGD – Other Government Department
RDEL – Resource Departmental Expenditure Limit
REDD+ - Reducing Emissions from Deforestation in Developing Countries
RFUK – Rainforest Foundation UK
RoC – Republic of Congo
SDGs – Sustainable Development Goals
SEAH – Sexual Exploitation, Abuse & Harassment
SES – Social-Ecological System Framework
SMEs – Small & Medium Enterprises
SMP – Simple Management Plan
SRO – Senior Responsible Officer
TACT – UK Terrorism Act 2000
ToC – Theory of Change
ToR – Terms of Reference
UK – United Kingdom
UN – United Nations
UNDP – United Nations Development Programme
UNFCCC – United Nations Framework Convention on Climate Change
VCM – Voluntary Carbon Market
VfM – Value for Money
WWF – World Wildlife Foundation

## Strategic Case

### i. The Context

Urgent action is needed to halt and reverse deforestation, and the UK is playing a leading role in the international response. Action to protect forests was a central element of the UK COP26 Presidency, including through the establishment of the Forest and Climate Leaders Partnership (FCLP) and a commitment of £3bn in International Climate Finance (ICF) for nature, and £1.5bn specifically for forests. The importance of the forest agenda is reinforced by the Integrated Review (2023) and the 2030 Strategic Framework on International Climate and Nature Action.

The Congo Basin region is the second largest tropical forest basin in the world and is of continental and global significance. Covering an area of roughly 3.7 million km2, it’s the second-largest river basin in the world after the Amazon, and one of the last remaining major terrestrial carbon stores on the planet. These forests make up almost 70% of Africa’s forests overall, including 91% of Africa’s moist forests, and are home to an extraordinary level of biodiversity that represents immeasurable potential for regional socio-economic development.

The Congo Basin forests provide valuable ecological services at local and regional levels across six core countries across Central Africa (Gabon, Cameroon, Republic of Congo, the Democratic Republic of Congo, Equatorial Guinea, and the Central African Republic). On a local level, these forests sustain the hydrological cycle and provide flood protection in high rainfall areas. These forests also directly regulate the regional climate, acting as the primary driver of rainfall patterns across Central Africa, whilst providing a major source (17%) of moisture for West Africa and generating much of the rainfall in the Sahel. The drying trend in the Congo Basin suggested by some scientific papers may impair this “water pump” service, increasing regional socio-economic stresses. Such dependencies on these forests span most of the Sub-Saharan continent, with farmers many thousands of miles away in the Horn of Africa relying on the rainfall the Congo Basin forests provide through regulation of weather patterns and climatic conditions.
[note] Bergen, M (2019) Congo Basin Deforestation Threatens Food and Water Supplies Throughout Africa. WRI. https://www.wri.org/insights/congo-basin-deforestation-threatens-food-and-water-supplies-throughout-africa
[note] Gong, C., and Eltahir, E. (1996), Sources of moisture for rainfall in West Africa, Water Resour. Res., 32(10), 3115–3121, doi:10.1029/96WR01940.
[note] Cadet, D.L. and Nnoli, N.O. (1987), Water Vapour Transport Over Africa and the Atlantic Ocean During Summer 1979. Q.J.R. Meteorol. Soc., 113: 581-602. https://doi.org/10.1002/qj.49711347609
[note] Rudi J. van der Ent, Hubert H. G. Savenije, Bettina Schaefli and Susan C. Steele‐Dunne (2010) Origin and fate of atmospheric moisture over continents Water Resources Research, vol. 46. https://agupubs.onlinelibrary.wiley.com/doi/full/10.1029/2010WR009127
[note] Zhou, L., Tian, Y., Myneni, R. et al. Widespread decline of Congo rainforest greenness in the past decade. Nature 509, 86–90 (2014). https://doi.org/10.1038/nature13265
[note] Rudi J. van der Ent, Hubert H. G. Savenije, Bettina Schaefli and Susan C. Steele‐Dunne (2010) Origin and fate of atmospheric moisture over continents Water Resources Research, vol. 46. https://agupubs.onlinelibrary.wiley.com/doi/full/10.1029/2010WR009127

As current precipitation in the Congo Basin is close to the minimum required for a rainforest to thrive, Réjou-Méchain et al. found that large areas of Central Africa’s forests have high vulnerability to climate change. The most vulnerable areas are the rainforest margins in the north and south, the coastal forests near the Atlantic seaboard, and most of DRC’s forests, threatened by a combination of climatic and anthropogenic pressures.
[note] Réjou-Méchain M, Mortier F, Bastin JF, Cornu G, Barbier N, Bayol N, Bénédet F, Bry X, Dauby G, Deblauwe V, Doucet JL, Doumenge C, Fayolle A, Garcia C, Kibambe Lubamba JP, Loumeto JJ, Ngomanda A, Ploton P, Sonké B, Trottier C, Vimal R, Yongo O, Pélissier R, Gourlet-Fleury S. Unveiling African rainforest composition and vulnerability to global change. Nature. 2021 May;593(7857):90-94. doi: 10.1038/s41586-021-03483-6. Epub 2021 Apr 21. PMID: 33883743. https://www.nature.com/articles/s41586-021-03483-6

At the global level, the outlook for this carbon sink the Congo Basin provides a critical line of defence against climate change and in meeting the goals of the Paris Agreement. It is estimated that the forests and peatlands of the Congo Basin combined store up to as much as 60 billion tonnes of carbon – equivalent to nearly six years of global human-induced emissions, of which approximately half is contained in the peat swamp region of DRC and RoC. The Basin as a whole absorbs nearly 1.5 billion tons of carbon dioxide a year – nearly 4% of annual CO2 emissions. Large areas of these forests have a high vulnerability to climate change, and their sequestration function might decline by around 10% until the middle of the next century, reducing the rate at which they absorb CO2 from the atmosphere and store carbon. It is estimated that forests up to 50o north latitude deliver benefits at a global scale that cumulatively keep the planet cooler by 1o Celsius. Destroying rainforests in the 10o band just south of the equator could warm the planet by 0.5o Celsius, and restoring forests in the 10o band just north of the equator would deliver 25% more global cooling than expected based on CO2 sequestration alone.
[note] Dargie, G., et al Lawson, I., Rayden, T., Miles, L., Mitchard, E., Page, S., Bocko, Y., Ifo, S. and Lewis, S., 2018. Congo Basin peatlands: threats and conservation priorities. Mitigation and Adaptation Strategies for Global Change, 24(4), pp.669-686. https://link.springer.com/article/10.1007/s11027-017-9774-8
[note] Dargie, G. C., Lewis, S. L., Lawson, I. T., Mitchard, E. T. A., Page, S. E., Bocko, Y. E., & Ifo, S. A. (2017). Age, extent and carbon storage of the central Congo Basin peatland complex. Nature, 542 (7639), 86-103. https://doi.org/10.1038/nature21048
[note] Galford GL, Soares-Filho BS, Sonter LJ, Laporte N (2015) Will Passive Protection Save Congo Forests? PLoS ONE 10(6): e0128473. https://doi.org/10.1371/journal.pone.0128473
[note] Hubau et al (2020) Asynchronous carbon sink saturation in African and Amazonian tropical forests. Nature 579, 80–87. https://doi.org/10.1038/s41586-020-2035-0
[note] Lawrence D, Coe M, Walker W, Verchot L and Vandecar K (2022) The Unseen Effects of Deforestation: Biophysical Effects on Climate. Front. For. Glob. Change 5:756115. doi: 10.3389/ffgc.2022.756115. https://www.frontiersin.org/articles/10.3389/ffgc.2022.756115/full

The Congo Basin forests are a critical economic asset for a large and growing population. An estimated 40 million people live within them, with 80 million people directly reliant on them for food, nutritional, health, and livelihoods needs. These populations are hugely diverse, representing over 150 distinct ethnic groups. Robust economic growth has slowed in recent years, with progress on poverty reduction stagnating. GDP values per capita in the region vary widely between countries, ranging from US$493 in CAR to $7,143 in Equatorial Guinea in 2020. Two of the poorest countries in the world, CAR and DRC, account for almost 60% of the region’s population, with over 70% of people living below the World Bank’s international poverty line (less than USD 2.15/day), and the same amount being defined as food insecure.
[note] World Bank (2022) ‘World Development Indicators DataBank’, https://databank.worldbank.org/source/world-development-indicators

Source: Tyukavina, A. et al. (2018). Congo Basin forest loss dominated by increasing smallholder clearing. Science advances, 4(11),
Table 1 - Development-related Indicators for Congo Basin Countries

Increasing domestic social and economic development needs must be met to fulfil the Sustainable Development Goals (SDGs). National development visions and strategies lay out ambitious plans to meet these needs and, at the same time, supply and benefit from a wide range of global commodity markets, extractive industries (oil, gas, mining) and infrastructural expansion. Higher returns on investment and sustainable economic development from natural assets will depend on utilisation and extraction that prioritises long-term growth over short-term gain, taking into account the local ecosystem services provided by natural assets, including for adaptation and resilience.
[note] Acworth, J & Douard, P (2021) The role of land use planning in Central Africa. Congo Basin Forest Partnership Report. https://pfbc-cbfp.org/actualites-partenaires/Package-%C3%A9tudes-PFBC.html?file=files/docs/key_docs/Publications%20du%20PFBC/2021_CBFP_LUP%20in%20CongoBasin_Report.pdf

### ii. The Problem

The forests remain under climatic and anthropogenic pressure from various drivers and underlying causes. Congo Basin countries lost a total of 17.9 million ha of forest in the period 2000-2019, 5.45% of its forest area. Trends vary by country, but most nations have seen a relative stabilisation of rates of forest loss over the past 6 years, as illustrated in figures 1 and 2.
[note] FGMC Basic statistics on trade from Congo Basin countries (2020). Internal UK Government document.

Figure 1 - DRC Primary Forest Loss Rate, 2002-21
Figure 1 - Congo Basin Primary Forest Loss Rates, 2002-21
Source: What Happened to Forests in 2021? | Global Forest Watch Blog

Drivers of forest disturbance within the region vary between countries and are highly complex, but an estimated 84% of forest disturbance across the Congo Basin is currently driven by subsistence and small-scale semi-commercial farmers clearing forests to feed themselves and residents of nearby towns and cities, with industrial scale clearing representing only a small fraction of all forest loss . In addition, the slow, but progressive building of road networks in the forest is providing access and increasing the risk of deforestation.
[note] Terminology and definitions differ between sources: deforestation, forest degradation, forest loss, forest disturbance etc. The use of ‘forest disturbance’ here is based on the reference from which the 84% figure was sourced, and is defined as, “complete or partial removal of woody vegetation from areas with at least 25% tree cover” and includes primary and secondary forest and plantations.
[note] Molinario, G., Hansen, M.C., Potapov, P.V., (2015) Forest cover dynamics of shifting cultivation in the Democratic Republic of Congo: a remote sensing-based assessment for 2000–2010. Environ. Res. Lett. 10, 094009. https://doi.org/10.1088/1748-9326/10/9/094009
[note] Alexandra Tyukavina et al., Congo Basin forest loss dominated by increasing smallholder clearing. Sci. Adv.4, eaat2993 (2018). https://doi.org/10.1126/sciadv.aat2993

Table 2 - Congo Basin Forest Disturbance Drivers (Adapted from )
[note] Alexandra Tyukavina et al., Congo Basin forest loss dominated by increasing smallholder clearing. Sci. Adv.4, eaat2993 (2018). https://doi.org/10.1126/sciadv.aat2993
Direct Driver	Rounded Estimated % Forest Disturbance
	DRC	Gabon	Cameroon	Republic of Congo	Regional Total
Small-scale Agriculture	92	30	58	48	84
Industrial Agriculture	1	3	16	1	1
Commercial Forestry	1	61	22	46	9
Infrastructure Expansion	1	4	2	1	2
Fire	5	2	2	4	4

Informal primary production dominates economic activity across much of the Congo Basin. This includes timber, non-timber forest products, and small-scale, rain-fed agriculture. Within these sectors, communities do not all have access to the resources, finance or markets to ensure full value is gained from forest products. In particular, slash and burn agriculture and charcoal production provides food and fuel for forest communities and adjacent towns, but also perpetuates unsustainable pressure on natural resources. Factional governance and the prevalence of elitism enables significant exploitation by better-resourced local and international enterprises such as logging interests, as communities have poor negotiating positions and lack sufficient collective representation.

Source: Tyukavina, A. et al. (2018). Congo Basin forest loss dominated by increasing smallholder clearing. Science advances, 4(11).
Figure 2 - Drivers of Congo Basin Forest Loss

Deforestation and forest degradation trends are closely linked to population growth and urbanisation. Whilst the global population has grown by 0.9% between 2012-2021, Congo Basin countries have seen considerably faster growth rates during the same period (DRC, 3.3%; Gabon, 3.07%; RoC, 2.5% & Cameroon, 2.7%) adding over 30 million to the regional population. Urbanisation rates are climbing, with 2012-2022 seeing an increase in DRC from 41% to 46.5%, Gabon from 86.5% to 90.5%, RoC from 64% to 68.5% and Cameroon from 53% to 58.5% . Related to this is expanding and upgrading of road networks which lower the costs of extracting natural resources. Such developments are important to enhancing the prosperity of these nations, introducing new economic opportunities at national and local scales, however there is also strong evidence indicating that these endeavours, without support for more sustainable options, are enabling further deforestation across the region as previously inaccessible areas are opened up .
[note] World Bank (2022) Urban Population DRC. Urban population (% of total population) - Congo, Dem. Rep. | Data (worldbank.org)
[note] World Bank (2022) Urban Population Gabon. Urban population (% of total population) - Gabon | Data (worldbank.org)
[note] World Bank (2022) Urban Population Republic of Congo. Urban population (% of total population) - Congo, Rep. | Data (worldbank.org)
[note] Urban population (% of total population) - Cameroon | Data (worldbank.org)
[note] Mosnier, A., Mant, R., Pirker, J., Bodin, B., Makoudjou, A., Awono, E., Bokelo, D., Tonga, P., Ndinga, R., Havlik, P., Bocqueho, G., Maukonen, P., Obersteiner, M., Kapos, V., Tadoum, M., (2015) Modelling future land use changes in Central Africa 2000-2030. A report by the REDD-PAC project. UNEP-WCMC, IIASA, COMIFAC. https://doi.org/10.22022/REDD/08-2018.13773
[note] Kleinschroth, F., Laporte, N., Laurance, W.F., Goetz, S.J., Ghazoul, J., (2019) Road expansion and persistence in forests of the Congo Basin. Nat. Sustain. 2, 628–634. https://doi.org/10.1038/s41893-019-0310-6
[note] Pacheco, P., Mo, K., Shapiro, A., Dudley, N., Aguilar-Amuchastegui, N., Ling, P.Y., Anderson, C., Marx, A., (2021) Deforestation Fronts: Drivers and responses in a changing world. WWF International, Gland, Switzerland. https://www.researchgate.net/publication/348548442_Deforestation_fronts_Drivers_and_responses_in_a_changing_world
[note] Rubaba et al. (2015) Road Improvements and Deforestation in the Congo Basin Countries. https://elibrary.worldbank.org/doi/10.1596/978-1-4648-0654-4_ch5
[note] Laurance et al. (2017) Road Expansion and the Fate of Africa’s Tropical Forests. Frontiers in Ecology and Evolution, vol. 5. https://doi.org/10.3389/fevo.2017.00075
[note] Kleinschroth et al. (2019) Road Expansion and Persistence in Forests of the Congo Basin. Nat Sustain 2, 628–634 (2019). https://doi.org/10.1038/s41893-019-0310-6

Forest dependence in the Congo Basin is higher among marginalised groups, such as indigenous people and women, and so deforestation and degradation often have the greatest impact on these groups in terms of livelihoods, culture and health. Women in forest-dependent communities are primary users of forest resources and are particularly affected by deforestation. Women and Indigenous Peoples, and forest communities in general, often lack equal rights to land ownership and other resources essential for their effective participation in forest management and have no legal rights to compensation when deforestation takes place. Even where rights are protected by legislation, challenges remain in its implementation.
[note] World Development Report 2008: Agriculture for Development. https://openknowledge.worldbank.org/server/api/core/bitstreams/8d8ad2dd-5c98-5042-8aad-744fdd7b034f/content
[note] World Bank Gender Portal: Land Owned by Women (%). https://genderdata.worldbank.org/indicators/sg-own-ld/
[note] Boketa, R. (2023) Securing Women’s Property Rights. Sustainable Development Goals Action. https://sdg-action.org/securing-womens-property-rights/

Research suggests that climate change could further drive vulnerability and fragility, posing a threat multiplier and exacerbating environmental degradation, highlighting variations in rainfall driving small-scale conflicts over natural resources, with climate shocks to agricultural production contributing towards regional instability . Noting the varying levels of regional stability; linkages between climate mitigation & adaptation, environmental degradation, natural resource stress and vulnerability dynamics are context-specific and greatly influenced by local and national, formal, and informal governance structures. For the Congo Basin, one of the most significant risks is precipitation variability, particularly given the majority of agricultural practices across the region are rainfall-fed. Less seasonal predictability, increased chance of drought conditions, and increased frequency of intense rainfall events combine to directly threaten the livelihoods of millions across Central Africa .
[note] Maslin, M., (2018). Climate change not the key driver of human conflict and displacement in East Africa, https://www.ucl.ac.uk/news/2018/apr/climate-change-not-key-driver-human-conflict-and-displacement-east-africa
[note] Raleigh and Kniveton, (2012) Come rain or shine: An analysis of conflict and climate variability in East Africa, Journal of Peace Research. https://doi.org/10.1177/0022343311427754
[note] Raleigh and Urdal, (2007) Climate change, environmental degradation and armed conflict. Political Geography 26(6). https://doi.org/10.1016/j.polgeo.2007.06.005
[note] Buhaug et al., (2015) Climate variability, food production shocks, and violent conflict in Sub-Saharan Africa. Environmental Research Letters 10 (2015). https://iopscience.iop.org/article/10.1088/1748-9326/10/12/125015
[note] von Uexküll, (2014) Sustained drought, vulnerability and civil conflict in Sub-Saharan Africa. Political Geography, 43(SI), 16–26. https://doi.org/10.1016/j.polgeo.2014.10.003
[note] Mosello, B. L. Ruttinger and L. Sauerhammer (2019) ‘Climate-Fragility Research Paper: The Climate Change-Conflict Connection: The Current State of Knowledge’, Climate Security Expert Network. https://climate-security-expert-network.org/sites/climate-security-expert-network.com/files/documents/csen_research_paper_-_the_climate_change-conflict_connection_the_current_state_of_knowledge_0.pdf
[note] Angelina A, Gado Djibo A, Seidou O, Seidou Sanda I, Sittichok K (2015) Changes to flow regime on the Niger River at Koulikoro under a changing climate. Hydrol Sci J 60(10):1709–1723. https://doi.org/10.1080/02626667.2014.916407
[note] Nicholson S., et al (2022) Environ. Res. Lett. 17 054052
[note] Kamitewoko, E. (2021) Impact of Climate Change on Food Crop Production in Congo Brazzaville. Modern Economy, 12, 1686-1702. doi: 10.4236/me.2021.1211085.

Table 3 - Development-related Indicators for Congo Basin Nations
	Fragility		Development
Country	World Bank, 2023 List of Fragile and Conflict-affected Situations	OECD, States of Fragility 2020	OECD, DAC List of ODA Recipients 22/23
Cameroon	Conflict	Fragile	Lower Middle-Income Country
CAR	Conflict	Extremely fragile	Least Developed Country
DR Congo	Conflict	Extremely fragile	Least Developed Country
Eq. Guinea	Not Listed	Fragile	Upper Middle-Income Country
Gabon	Not Listed	Not Listed	Upper Middle-Income Country
Rep. Congo	Fragile	Extremely fragile	Lower Middle-Income Country

Households in poverty are typically more exposed and vulnerable to the hazards that destroy assets and income streams. These include waterborne diseases and pests that become more prevalent during floods or droughts, spikes in food prices that often follow local and international production failures, and crop failure and livestock mortality caused by increasingly erratic rainfall patterns. Related climate migration is expected to increase rapidly due to such increased stresses on agricultural production as climate shocks continue to both keep people in and push people back into poverty.
[note] Met Office (2023) Climate risk report for the Central Africa region (2023). Internal UK Government Document.
[note] Rigaud, Kanta Kumari; de Sherbinin, Alex; Jones, Bryan; Bergmann, Jonas; Clement, Viviane; Ober, Kayly; Schewe, Jacob; Adamo, Susana; McCusker, Brent; Heuser, Silke; Midgley, Amelia. (2018) Groundswell: Preparing for Internal Climate Migration. World Bank, Washington, DC. http://hdl.handle.net/10986/29461
[note] Met Office (2023) Climate risk report for the Central Africa region (2023). Internal UK Government Document.

Table 4 - Food Insecurity across Congo Basin Nations
[note] FAO Sustainable Development Goal Two Indicators. https://www.fao.org/sustainable-development-goals-data-portal/data/indicators/212-prevalence-of-moderate-or-severe-food-insecurity-in-the-population-based-on-the-food-insecurity-experience-scale/en
Country	Prevalence of severe food insecurity in the total population (%) 2019-2021	Number of severely food insecure people (millions) 2019-2021	Percentage of people unable to afford a healthy diet (%) in 2020
Cameroon	26.7	7.1	60.7
CAR	61.8	3.0	95.1
DR Congo	39.2	35.1	90.0
Eq. Guinea	N/A	N/A	N/A
Gabon	N/A	N/A	36.3
Rep. Congo	55.5	3.1	92.4

Economic prosperity, social development and maintenance of the natural environment are challenged by market failures and weak governance. Driving these three objectives collectively is a significant challenge in the Congo Basin, where often unsustainable practices used for extractive processes such as slash and burn agriculture and charcoal production provide livelihoods for millions, whilst widespread poor governance hinders development efforts. Alternative sustainable approaches must be able to increase income and wealth to allow an enabling environment for behavioural change, but this requires a holistic and prolonged approach, tackling the diverse range issues faced by local communities simultaneously over the long-term.

Despite substantial international pressure and funding to support sustainable development and mitigate climate change (c.US$2 billion to central Africa since 2008), the state of the forest in the Congo Basin has generally deteriorated, although there are examples of success with respect to supporting enduring sustainable practices which this programme will seek to learn and from. These will focus on where approaches have ensured effective transferral of benefits to local communities, such as the landscape interventions in Yangambi carried out over the past twenty years by CIFOR, and REDD+ best practice seen in the Republic of Congo .
[note] Eba’a-Atyi, R. and Guizol, P. (2019). International financial flows to support nature protection and sustainable forest management in Central Africa (OFAC Brief Series No. 3). https://www.cifor.org/publications/pdf_files/brief/7392-OFACBrief.pdf
[note] Cerutti, P. (2021). Yangambi: A Proven Model of Engagement. https://www.cifor-icraf.org/annualreport2021/yangambi-a-proven-model-of-engagement/
[note] Bosquet, B (2017) World Bank Blog. https://blogs.worldbank.org/nasikiliza/a-balancing-act-exploring-how-the-republic-of-congo-can-use-forest-resources-sustainably-for

The Congo Basin is the subject of a global market failure in which the commodity markets have been unable to internalise the social and environmental costs to deforestation. This results in skewed incentives for those utilising natural resources. Ultimately, there has been an undervaluing of the benefits of these forests in terms of livelihoods at the local level, biodiversity, and regional and atmospheric climate services at a regional and global level. Market prices, private sector practices and tax and regulatory policy have not reflected the wider economic and societal value of the forest, leading to suboptimal outcomes around land use and allocation of capital.

Weak governance continues to undermine many domestic and international interventions across the region. Congo Basin countries score amongst the lowest on Transparency International’s Corruption Perceptions Index. Laws and policies governing natural resource exploitation and management may lack coherence and often are not enforced, while powerful vested interests are able to influence land use allocations. Indicative of the wider region, DRC presents significant governance challenges which hinder success rates, stemming from ineffectiveness or absence of strategic vision, far-reaching and endemic corruption, the role of natural resources in facilitating this (notably for armed groups), lack of capacity to sustain efforts and secure progress, and persistent conflict and instability. In some regions of the Congo Basin, resource exploitation and efforts to monopolise conservation benefits is driving conflict. This can result in decisions affecting forests and local populations being taken without sufficient transparency or accountability.
[note] Rahmé, M and Walsh, A. (2022). Corruption challenges and responses in the Democratic Republic of Congo. K4D Helpdesk Report. Brighton, UK: Institute of Development Studies. DOI.10.19088/K4D.2022.093
[note] Fagbadebo, O. (2019) Corruption and the challenge of accountability in the post-colonial African states: a discourse. http://dx.doi.org/10.31920/2050-4306/2019/v8n1a1
[note] Schouten, P (2022) Our climate future depends on conflict dynamics in Congo. Climate and conflict. https://www.diis.dk/en/research/our-climate-future-depends-on-conflict-dynamics-in-congo

Issues relating to allocations and rights over land and natural resources are a compounding factor. This is a particular issue at the local level for women and within communities, as well as an issue that extends beyond communities to national systems. Across the region, there are frictions between customary and formal (legal) systems of tenure and land governance. Efforts to recognise or define customary rights into national legal frameworks have been mixed. Even within legal frameworks, lack of communication, consistency and organisation within and between national government Ministries and agencies has the potential to create confusion. It has been frequently observed, for example in Cameroon, that the same location might be the subject of overlapping land use allocations, for example mining, logging and agro-industrial concessions and protected areas. The overarching lack of clarity in forest & land use rights, and lack of transparency, can disincentivise long-term investment in sustainable management of forest resources and engagement by local actors with carbon markets.

Scientific and socio-economic research findings in recent years have been significant, providing a better understanding and quantification of the importance of the Congo Basin for both the climate and livelihoods in the region. However, research capabilities are still severely limited, particularly regarding institutions in the region, which largely rely on Western academia for expertise and funding opportunities – which is also limited. This exacerbates the challenge of autonomising research capabilities in the region to ensure self-sufficient capabilities in the long term.

Past efforts at intervention by international development actors have achieved limited pockets of effective collaboration with stakeholders. Coordination among and between countries, ministries, donors, NGOs, and other institutions working toward reducing deforestation in the Congo Basin has been relatively weak. While national and regional initiatives exist to address this, a mutual distrust persists between the donor community, host country governments and local communities. Points of contention include standards of governance, appropriateness of conditionality, and ownership, quantum and accessibility of funding and difficult trade-offs when valuable minerals, oil or gas are discovered in forest regions.
[note] Green Climate Fund (2022). Forest and Land Use Sectoral Guide. Sectoral Guide Series. https://www.greenclimate.fund/sites/default/files/document/gcf-forests-and-land-use-sectoral-guide-consultation-version-1_0.pdf

Local community buy-in is critical for the success of any programme seeking to reduce deforestation rates across the Congo Basin – these populations must experience prolonged economic benefit from any delivered interventions. However, scoping consultations with local communities have indicated widespread disillusionment with previous programming efforts. Strong grievances emerged suggesting these were poorly thought out without proper consultation and local ownership. This was exacerbated by ineffective channelling of funding to ensure communities are reached, with substantial management fees absorbing significant portions of donor funding, compounded by siphoning of funds at local levels, ultimately resulting in interventions struggling to sustain positive impacts.
[note] T. Gjefsen etl al. (2021) Indigenous people receive little climate funding. Rainforest Foundation Norway. https://www.regnskog.no/en/news/falling-short
[note] Larson AM, Sarmiento Barletti JP. (2020). Designing for engagement: Insights for more equitable and resilient multi-stakeholder forums. CIFOR Infobrief 280. https://cifor.org/library/7593

Interventions which focus on sustainable livelihoods and economically viable alternatives to unsustainable practices targeted at local populations are difficult to establish and maintain but are vital for programme success . Consultations with stakeholders across the Congo Basin have indicated repeated programmatic failures in large part due to limited co-design and lack of both long-term strategic planning and funding. The 2021 ICAI review - International Climate Finance: UK aid for halting deforestation and preventing irreversible biodiversity loss concluded of the UK aid programme that while some programmes are working well with forest communities, including indigenous peoples, consultation with communities during programme design is inconsistent.”
[note] Trefon, T (2017) Forest Governance and International Partnerships. Science & Diplomacy, Vol. 6, No. 3 (September 2017). http://www.sciencediplomacy.org/forest-governance-andinternational-partnerships-in-congo-basin
[note] ICAI (2021). UK Aid Under Pressure: Synthesis of ICAI Findings. UK-aid-under-pressure-synthesis-of-ICAI-findings-2019-23.pdf (independent.gov.uk)

There is extensive opportunity to learn lessons from past engagements efforts on both programming and policy and strategy. A 2022 FCDO scoping exercise in the region, covering DRC, RoC, Cameroon and Gabon, identified widespread dissatisfaction with past efforts at engagement by the international community, including quality and effectiveness of donor-funded development programming.

With some of the lowest GDP Per Capita rates on Earth, it is critical that Congo Basin countries continue to economically develop to reduce poverty rates and move away from chronic instability and fragility. This presents a particular challenge with respect to the region’s natural environment, notably it’s forests and the extensive natural capital these provide. As such, the need for sustainable development across Central Africa has never been greater, something recognised by the international community in recent years, and demonstrated through regional commitments made at COP26.

In this context, and in view of the commitments made by the UK to deliver funding to address these challenges, the decision was taken to design interventions under the title of the Congo Basin Forest Action (CBFA) Programme.

### iii. Intervention Opportunities

Framing

Interventions intended to address population needs and protect, restore, and utilise nature, take place within complex social-ecological systems. A review undertaken in 2022 by FCDO as part of the ‘Best Buys’ output proposes an adapted version of the Social-Ecological System (SES) Framework, illustrated in figure 4 below, as a useful way to conceptualise the core dynamics of these systems.
[note] Cox, M. (2014). Understanding large social-ecological systems: Introducing the SESMAD project - Scientific Figure on ResearchGate. Available from: https://www.researchgate.net/figure/SES-Framework-Ostrom-2009_fig1_284134726

Figure 3 - FCDO adapted SES Framework

One set of potential interventions are actions which directly affect Resource Systems or Resource Units. These include, for instance, Wetland Conservation and Restoration, and Reduced Impact Logging. While of significant potential benefit from a nature conservation perspective, these interventions have proven difficult to reconcile with needs of populations in terms of economic development and poverty reduction. Work in this domain requires extensive buy-in and leadership from the host governments over long periods, for example to establish and maintain protected areas. For these reasons, a UK-funded and managed intervention centred on fortress conservation, i.e., creation and maintenance of Protected Areas where humans are excluded or restricted, was considered and ruled out as an approach to be undertaken through this programme.

Other instruments specifically affect Governance Systems, in turn affecting Actors, who in turn affect Resource Systems or Resource Units. These include, for instance, Community Based Forest Management, or Marine Protected Areas. The distinction between instruments that directly affect Actors, and those that affect Governance Systems, can be blurred in practice. Governance interventions have potential for high impact, or to enable other interventions, and therefore while evidence is still emerging from programmes such as the UK’s Forest Governance Markets & Climate (FGMC) programme, interventions in this category are also considered further in the Appraisal Case.

Systemic interventions can affect broader Social, Economic and Political Settings, with scalable, global level impacts on nature and biodiversity. These could include carbon pricing, improving valuations of natural capital, international legislative change, and major technological innovations. The UK has extensive current and past interventions targeting global impacts within these areas. These include funding the Wealth Accounting and the Valuation of Ecosystem Services (WAVES) partnership, and broad efforts by FGMC to support innovations in the forest space, alongside influencing international law through advocacy and evidence development. CBFA has been designed to complement such efforts by focusing on bottom-up grassroots activities to build sustainable development at the community level, drawing down the successes from macro-interventions to the local level. Partners and stakeholders will be encouraged to consider links to broader activities both within and beyond the UK remit.

Thematic Focus

The thematic focus of the programme is intended to include influencing Actors directly, as well as Governance that indirectly shapes Actors behaviour, based on the framing for interventions within the social-ecological system of the Congo Basin forests. This could include a wide range of intervention types, which will be narrowed down in the first section of the Appraisal Case, considering a number of critical success factors, as well as complementarity and overlap with other UK-funded programming.

There is a perception of a thematic gap for CBFA in grassroots, bottom-up delivery approaches for local communities in non-protected forest areas, addressing informal, subsistence-orientated practices which overwhelmingly constitute the primary drivers of deforestation across the region, most notably in forest frontier zones. This was a consistent consensus from the 2022 scoping exercise, reflected by most civil society organisations and local communities, alongside other donors and both national and international NGOs.

Ensuring sustainable management of the Congo Basin forests for the benefit of local populations will require actions that address both the regional governance and global market failures. In this region, poverty and weak forest & land use governance are major challenges to sustainable management of forest resources. However, there are a number of political and legislative processes underway, including decentralisation, reform of forest & tenure and planning systems, which provide important opportunities to protect rights and livelihoods for forest dependent communities. A 2021 UNECA review of Central Africa offered positive prospects for improved accountability and more inclusive and diverse economic activity resulting changing demographics, digital technology (and payments) and increasing local value chains and markets offering alternatives to exports that tend to be operated under obscure terms.
[note] Swilling, M et al., (2021) Fostering Leadership and transformational change for economic diversification in Central Africa, UNECA. https://www.uneca.org/sites/default/files/SROs/Central-Africa/ice-ca-37/ICE%202021%20Study_Final%20Second%20drat%20on%20%206%20Nov%202021%20-%2002112021%20Final%20%20%28003%29.pdf

Lack of secure tenure can be recognised as a ‘binding constraint’ in forestry, as tenure is an important precondition for motivating people to invest in sustainable forest management. There is evidence that securing community land and resource rights can be foundational in securing economic benefits for local communities whilst tackling deforestation. Across the Congo Basin, virtually all land has been either under the ownership (DRC, CAR) or in the custody (Congo, Cameroon, Gabon) of the State and in the absence of overarching legal frameworks in Congo Basin countries that allow for full collective ownership of land.
[note] Kusters, K. et al. (2022) Formalizing community forest tenure rights: A theory of change and conditions for success, Forest Policy and Economics, Volume 141,102766, ISSN 1389-9341, https://doi.org/10.1016/j.forpol.2022.102766. (https://www.sciencedirect.com/science/article/pii/S1389934122000788)
[note] Centre for International Forestry Research (undated). Forest Tenure Recounted. https://landportal.org/issues/forest-tenure-recounted.
[note] Larson, A. (2012) Tenure rights and access to forests: A training manual for research. https://www.cifor.org/publications/pdf_files/Books/BLarson1201.pdf

Across much of the region, efforts to introduce effective, sustainable community forestry – forested areas managed collectively by local people - have been stymied by limitations in the legislative frameworks or their implementation in the context of local governance or stewardship practices. In Cameroon and elsewhere in the region, challenges have included:
[note] Forest Restoration Research Unit (2008). Research for Restoring Tropical Forest Ecosystems: A Practical Guide. Biology Department, Science Faculty, Chiang Mai University, Thailand http://www.forru.org/PDF_Files/rfrtfpdf/rfrtfappendix.pdf

  1. The limitations to the size of community forests (e.g. at 5,000 ha in Cameroon and CAR), which can preclude sustainable logging practices, or larger scale conservation or payments for ecological services
  2. The high level of technical requirements, which can lead to large upfront costs that favour reliance on an outside actor, which could be a logging company.
  3. Legal tenure rights not being well-fitted to customary systems, which can create uncertainty or conflict at the local level.
  4. Lack of capacity and effectiveness of government and local systems for implementation and administration

In DRC, recent legislative changes – supported by engagement from the UK and international community – have substantially improved the framework for establishing devolved forest rights, providing the basis for effective community forestry. For example, community forests can be at the scale of 50,000ha, ten times larger than Cameroon and CAR. However, challenges remain in translating these de jure rights into de facto benefits to communities entitled to rights, and into effective forest stewardship. Communities would benefit from support in developing simple management plans, as well as being better linked to markets, for non-timber forest products, sustainable timber, and in principle for voluntary or compliance carbon markets or markets for biodiversity offsets or credits. CBFA intends on supporting development in these areas in collaboration with other UK programming, focusing on realising economic benefits to local communities through a grassroots holistic approach, alongside securing these for the long term lasting change.
Without strong institutions able to effectively implement rules and build alliances within a complex political economy, neither land use planning nor tenure reform will yield sustainable change. Administrations must be properly staffed and equipped in order to fulfil expectations, in terms of planning, monitoring and controlling forest resources. Monitoring efforts are ideally performed by regulatory agencies, but strategic partnerships with local communities and NGOs can be established to improve monitoring activities. Transparency can trigger accountability, deter corruption, and empower better-informed decision-making. This is a major focus of the programme, ensuring local organisations and supported communities are effectively empowered to enforce, monitor, and benefit from livelihood activities.

Given the complexity of the sector, actions across all these areas are needed to bring about a change in the way forests are governed. Devolved Forest Rights provide an overarching entry point to work on all these issues and is therefore an expected focus of this programme. Several promising activities have been identified that respond to emerging opportunities in the region. Formalising and securing land tenure rights for local forest communities was ranked ‘High Potential’ in the FCDO Nature Best Buys review. A randomised rollout of a programme formalising customary land rights in Benin showed that it reduced tree cover loss by around 20% (and fires by around 5%) in treated villages, with no evidence of anticipatory deforestation or negative spill-over effects.This is supported by evidence from the Brazilian Amazon, and elsewhere. Community-based Forest Management, meanwhile, was ranked as ‘Low Evidence’ under the Nature Best Buys. While there is local evidence of successful interventions, including through previous UK programming described later in this business case, the context-specificity of community forestry practice has hampered systematic analysis of approaches. This should encourage an emphasis on development of the evidence base through suitable knowledge-focused components and Monitoring, Evaluation and Learning (MEL) systems. CBFA will have a dedicated MEL component which will play a key role in supporting development and implementation of localised evidence, alongside core safeguarding, including proactively tracking performance of interventions to ensure they are delivering economic benefits to local communities.
[note] FCDO Nature Best Buys Review (2022). Internal UK Government Document.
[note] Wren-Lewis, L., Becerra-Valbuena, K., Houngbedji, K. (2020) Formalizing Land Rights Can Reduce Forest Loss: Experimental Evidence from Benin. Science Advances. https://www.science.org/doi/10.1126/sciadv.abb6914

There are innovative mechanisms for mobilising financial flows for standing forests and their dependents that are currently at early stages of development, including Internationally Transferred Mitigation Outcomes (ITMOs) under Article 6 of the Paris Agreement, Voluntary Carbon Markets (VCM – carbon credit transactions not purchased to meet mandatory GHG reductions, in this case typically benefiting smallholders more directly), results-based payments, and Payments for Ecosystem Services (PES – when beneficiaries of an ecosystem service make payments to the providers, in this case, the local communities) models which reflect the value of benefits provided by forests.
[note] UNDP (2021) High Integrity Voluntary Carbon Markets (VCM): Emerging Issues in Forest Countries. https://www.undp.org/publications/high-integrity-voluntary-carbon-markets-vcm-emerging-issues-forest-countries
[note] Fripp, E. (2014) Payments for Ecosystem Services (PES) A practical guide to assessing the feasibility of PES projects. https://www.cifor.org/publications/pdf_files/Books/BFripp1401.pdf

Many of the financial instruments aimed at supporting smallholders and/or leveraging investment into sustainable land use, such as green bonds and impact bonds, are still relatively nascent and there is a lack of evidence of their successful application at scale. The time span of the CBFA programme is sufficient that in a rapidly emerging sector such as innovative finance for environmental outcomes, emerging evidence and the results of pilot projects may be used in the later years of the programme. As such, a phased approach to targeted support will allow the programme to support evidence-building in the initial stage of implementation before considering further interventions in later years. This will be carefully tracked by partners with support from the MEL component to ensure local communities are benefiting first and foremost, noting that CBFA will not force individuals to adopt alternative practices if it reduces their income.

Looking across the donor landscape in the Congo Basin, certain innovative finance approaches – such as PES and biodiversity offsets - have yet to be pursued at scale, in part owing to the complexity of the context relative to jurisdictions where successes have been recorded. PES was ranked as ‘Mixed Evidence’ under the FCDO Nature Best Buys review, however, there is evidence to suggest that impact can be achieved, both in theory and in practice under certain conditions, as demonstrated in Costa Rica and Uganda, with varying levels of lasting impact. CBFA will draw on the lessons from the limited success of PES in Africa , with the definition of PES broadened to include general rewards and incentives for sustainable forestry, including through high value timber products and watershed management.
[note] Arriagada et al. (2012) Do PES Affect Forest Cover? A Farm Level Evaluation from Costa Rica. https://www.jstor.org/stable/pdf/23272587.pdf
[note] World Bank (2018) Evaluating the Permanence of Conversation Following the End of PES in Uganda. https://documents1.worldbank.org/curated/en/867301589223292444/pdf/Evaluating-the-permanence-of-forest-conservation-following-the-end-of-payments-for-environmental-services-in-Uganda.pdf
[note] Achaval-Torre, J. (2021). Paying for Nature & Society: Innovation in Financial Incentives for Farmers to Conserve Nature in the Global South. CoSAI Secretariat. https://www.iwmi.cgiar.org/archive/cosai/news/paying-nature-and-society-innovation-financial-incentives-sustainable-and-inclusive-transition/index.html
[note] Osewe et al (2023) Critical Analysis of Payments for Ecosystem Services: Case Studies in Kenya, Uganda and Tanzania https://www.mdpi.com/1999-4907/14/6/1209

PES, for which early precedents were primarily based in Latin America, has received growing attention from the African Development Bank. While originally narrowly defined as a voluntary transaction for a well-defined ecological service between a single buyer and seller, the broader concept of incentivising and rewarding countries or communities in support of environmental goods and services (including carbon sequestration) has proven more workable. It is the lessons that apply to this broader framework, including watershed management in Kenya and carbon sequestration in Uganda, that will be referenced by CBFA when developing baselines and criteria for success.
[note] Richards, F; Legrand, Tl Garba, L (2015) PES a promising tool for natural resource management in Africa. https://www.afdb.org/fileadmin/uploads/afdb/Documents/Publications/Payment_for_Environmental_Services_-_A_promising_tool_for_natural_resources_management_in_Africa_-_06_2015.pdf
[note] https://www.un.org/waterforlifedecade/green_economy_2011/pdf/session_4_biodiversity_protection_cases_kenya.pdf

In analysing over 25 PES projects in Africa, success was found to be linked to approaches that “bundled environmental services” involved ‘medium to long-term financing” (as opposed to a single upfront payment), “combined transaction types” (cash and in-kind) and adopted a “regional approach”. These are further lessons that will be built into any PES interventions by CBFA. More generally, the programme will ensure success is rewarded incrementally through the lifecycle of any project, with strict conditions tied to deforestation rates. Given the significant financial scales required to deliver PES with lasting impact, and to minimise risk and maximise chances of success, any intervention will seek to collaborate institutions and companies already trialling PES across the continent, e.g., CAFI, World Bank, African Development Bank, WWF, World Resources Institute, Verra.
[note] Osewe et al (2023) Critical Analysis of Payments for Ecosystem Services: Case Studies in Kenya, Uganda and Tanzania https://www.mdpi.com/1999-4907/14/6/1209

Engagement with financial innovations such as PES may be an opportunity to test a new approach to the Congo Basin, capitalising on momentum at the international level and is therefore a potential focus of this programme. The approach of CBFA in this field will be graduated, reflecting the limited evidence and the higher risks – in particular fiduciary risks – associated with the region. Again, an emphasis will need to be placed on developing the evidence base, bolstering research and knowledge work in the relevant field, outlining robust criteria to take forward activities into implementation, and having in place a strong MEL function for the programme itself.

Geographic Focus

At COP26, the UK pledged to support sustainable development specifically with respect to the Congo Basin forests, as part of the $1.5bn Congo Basin Pledge (2021-2025). The below quotation is extracted from the announcement:

We are demonstrating our commitment to this important region today by announcing an initial collective pledge of at least $1.5 billion of financing to support ambitious efforts and results in the region to protect and maintain the Congo Basin forests, peatlands and other critical global carbon stores. We intend to build on this in subsequent years, by seeking increased finance and investment from a wide variety of public and private sources while also improving coordination, effectiveness and accessibility. We also call on other donors to significantly increase their support for the protection and sustainable management of the Congo Basin forests.
[note] National Archives, UK Government (2021) COP26 Congo Basin Joint Donor Statement. https://webarchive.nationalarchives.gov.uk/ukgwa/20230105153550/https:/ukcop26.org/cop26-congo-basin-joint-donor-statement/

At that time a Concept Note was approved for £200m to cover the UK’s commitment to the region, with CBFA being the primary offer within this. As a result, the geographic scope of the programme is defined as limited to the Congo Basin region, with the expectation that most activities would take place in four of the forest countries where needs and delivery practicalities are most suitable – Cameroon, Gabon, Republic of Congo and the Democratic Republic of Congo. These four countries account for 95% of primary tropical forest cover across the Congo Basin.
[note] Global Forest Watch (2020) Forest Coverage by Country, Central Africa. https://www.globalforestwatch.org/dashboards/global/

CBFA is intended to operate and deliver on the understanding that:

1. Regional and multi-country programmes are ideal for tackling cross-border issues and capturing comparative advantages and potential efficiencies of reach and impact by working regionally. Such programmes also afford a degree of regional flexibility where there are politically volatile national contexts.
2. Extractive processes that drive deforestation across the Congo Basin, most notably slash and burn agriculture and charcoal production, currently support the majority of forest-based livelihoods across the region.
3. Economic modelling of any interventions driving towards sustainable development practices by UK programming may display an initial negative impact on beneficiaries. In reality, this will not occur - CBFA will ensure effective sequencing wherein interventions must develop to be economically viable and stable prior to beneficiaries shifting across. No-one will be required or forced to adopt new practices that are not as economically viable. Appropriate safeguarding measures will be taken to guarantee this, and are described in the Programme Approach section of the Appraisal Case.
1. Climate and weather events do not recognise national boundaries; they are both global and regional processes. Many environmental problems, including those facing the forest and water sectors, are either transboundary, influenced by regional processes and markets, or multi-country involvement. Countries coordinating and learning together will provide opportunities to effect large-scale positive change.
2. Natural resources move, legally and illegally, across borders. Policies to manage resources in one country can have consequences for managing that resource and the livelihoods of the people who depend on it in another country. Actions taken to combat illegal activity in one country can displace the problem in a neighbouring country.
3. As a regional entity and a global public good, there is a strong rationale for an overarching regional approach, not least due to the risks of displacing issues and environmental, social, and economic problems if the forest landscapes are not treated in their entirety. The Congo Basin rainforests are national resources for six host countries, each with its own aims, ambitions, opportunities, and development needs. Each has distinct strengths, weaknesses, capacities, and capabilities, with individual cultures, contexts, and challenges.
4. Many key challenges of the Congo Basin are beyond the control of any single programme. As described, significant regional challenges include conflict and governance. Programme interventions will endeavour to work to mitigate risks and avoid exacerbation, but it must be recognised that these are external factors which UK programming has limited influence over.
5. Where possible and appropriate, any programme activity should align with national government policies on development. The nexus of economic development and sustainability is a challenging space across the Congo Basin where extreme poverty persists for large swathes of the population. Access to energy, transport links, and natural resources development are examples of core strategies for governments in the region. These priorities should be worked with where possible.
6. Whilst infrastructure expansion represents a small percentage of forest disturbance in the Congo Basin, there is strong evidence that it is a core enabler of extractive activities, particularly informal deforestation carried out by local communities . It is therefore imperative that any programming considers this multiplier effect and identify opportunities to minimise related negative impacts.
  [note] Rubaba et al. (2015) Road Improvements and Deforestation in the Congo Basin Countries.
  [note] Laurance et al. (2017) Road Expansion and the Fate of Africa’s Tropical Forests. Frontiers in Ecology and Evolution, vol. 5. https://doi.org/10.3389/fevo.2017.00075
  [note] Kleinschroth et al. (2019) Road Expansion and Persistence in Forests of the Congo Basin. Nat Sustain 2, 628–634 (2019). https://doi.org/10.1038/s41893-019-0310-6
7. Provincial government control varies significantly across the Congo Basin, with socio-economic conditions, strength of national identity, and prevalence of conflict all factors in determining effectiveness of the enforcement of national law. A relevant example of this relates to formal government recognition of land tenure rights. Whilst this should generally have a positive impact on the effectiveness of community ownership and reduction of conflict, the lack of capacity to enforce such laws is commonplace across the region, notably in remote areas of DRC, and unstable parts of Cameroon. Other UK programming intends on supporting capacity building at a national scale, whilst CBFA has a clearly defined scope to operate and tackle challenges locally.

### iv. UK Intervention Rationale

Delivery of a significant, new intervention to address challenges in the Congo Basin Forests will advance UK priorities in line with existing UK government objectives and commitments:

The 2023 White Paper on International Development highlighted extreme poverty, climate change, and biodiversity loss as three key priorities for the UK in the coming years, noting that these challenges are interrelated, and must be addressed holistically. It recognises the importance of a just transition in forests and land use to reduce emissions whilst enabling economic transformation, with the ultimate goal of protecting and restoring nature in parallel with driving sustainable development. It focuses on the need to empower IPLCs and women & girls, improve land & forest tenure security, and support farmers to sustainably secure their livelihoods, with particular attention on fragile and conflict affected states. CBFA has all of these objectives built into it’s core narrative and focus, seeking to drive economic development for local communities whilst ensuring nature is protected.

1. The 2023 Integrated Review Refresh reiterated the close interaction between development, global security, and climate change, stating “climate change and biodiversity loss are important multipliers of other global threats, and are guaranteed to continue to worsen over the next decade: six of the top ten risks for the decade ahead identified by the World Economic Forum relate to climate, the environment and nature. The consequences are both acute and chronic, resulting in a sharp increase in global migration and the number of people in need of immediate humanitarian assistance, as well as significant setbacks to progress towards the Sustainable Development Goals (SDGs).” Evidence is clear on climate change as a driver of regional conflict and migration, with Central Africa particularly exposed and vulnerable due to the ongoing conflicts (e.g. East DRC), extremely poor resilience (e.g. natural disasters), and low economic opportunity. Support to livelihoods and knowledge transfer on climate and forests via CBFA can help tackle these issues and provide improved stability to beneficiaries.
2. International Development Strategy: advancing the thematic priority of climate & nature, developing innovative approaches to tackle climate change and protect nature. CBFA has the potential to contribute to three of the seven priority initiatives for UK Development Leadership (delivering lasting solutions to food and nutrition insecurity, including sustainable agriculture; open science for global resilience, reforming and greening the global financial system).
3. International Climate Finance: the UK has committed to double our International Climate Finance (ICF) contribution to at least £11.6 billion between 2021-2026. The full amount of CBFA funding is allocated to International Climate Finance, contributing to this financial target, and to associated pledges described below.
4. The UK’s commitment to Nature, including the £3 billion share of our ICF in development solutions that protect and restore nature. It is anticipated that the Congo Basin Forest Action Programme would also contribute to this pledge.
5. The UK’s contribution to spending on Forests: At COP26, the UK publicly committed £1.5 billion over five years to support the forests pledge. It is anticipated that the Congo Basin Forest Action Programme would also contribute to this pledge.
6. The COP26 Joint Donor Statement on the Congo Basin, pledging at least $1.5 billion between 2021-2025 to support the region to protect and maintain the Congo Basin forests, peatlands and other critical global carbon stores, was signed by: the European Union, Germany, France, Japan, Belgium, the Netherlands, Norway, Sweden, South Korea, the United Kingdom, the United States, and the Bezos Earth Fund. This was the first time a Congo Basin-specific commitment has jointly been made by such an extensive set of donors at this scale. It is anticipated that the Congo Basin Forest Action Programme would also contribute to this pledge.
7. The UK’s commitment to the IPLC Forest Tenure Pledge: At COP26, 22 bilateral and philanthropic donors, including the UK, also committed $1.7bn from 2021-2025 to advance Indigenous Peoples’ and local communities’ (IPLC) tenure rights and forest guardianship. The pledge is intended to increase support directly channelled to IPLCs, including to strengthen capacity building and governance structures that bring greater tenure security, and activities that secure their land and resource rights such as wider tenure reform processes. It includes a commitment to promote the effective participation and inclusion of IPLCs in decision-making and to include, consult and partner with them in the design and implementation of relevant programmes and finance instruments. It is anticipated that the Congo Basin Forest Action Programme would also contribute to this pledge.
  [note] National Archives, UK Government (2021) COP26 IPLIC Forest Tenure Joint Donor Statement. https://webarchive.nationalarchives.gov.uk/ukgwa/20230105153257/https:/ukcop26.org/cop26-iplc-forest-tenure-joint-donor-statement/

The proposed intervention will complement our past and current efforts through both policy and political initiatives, and through UK ODA programmes. The UK is well placed as a member of the international community to play a leading role in efforts to address challenges in the Congo Basin region, in support of partner governments. The UK has held an active presence across the region for many years. These efforts are being built on in the context of our renewed focus post-COP26, which has seen the UK take on influential roles through various Congo Basin institutions, whilst building out a portfolio of programming.

### v. Programme Summary & Strategic Fit

What, Where, and How?

CBFA has been designed to address the primary driver of deforestation across the Congo Basin - small-scale agricultural practices by local communities. It will do this by working directly with these groups to support transitions to more sustainable activities, ultimately reducing deforestation rates, whilst ensuring local economic benefits are realised.

This will be achieved through a broad range of complementary activities. On the ground, these will include establishing and supporting effective community forests, improving agricultural efficiencies, promoting better fuel practices, and encouraging sustainable agroforestry. These activities will be reinforced through helping local communities to secure and operationalise land tenure rights, whilst building local and regional capacities and knowledge, with a focus on autonomising activities and capabilities to promote success beyond the programme period.

An explicit focus will be placed on driving behavioural change, which ultimately poses one on of the most significant challenges to the lasting success of any intervention, even when beneficiaries are offered superior alternative economic incentives. To support this, CBFA will have co-design and co-ownership at its core. This means ensuring beneficiaries form a key part of the design of activities. This reduces the risk of such activities failing once programme funding ends, empowering true proprietorship and lasting economic benefits within local communities. CBFA will have civil society and national NGOs play a key role in delivering this to promote locally led action and drive lasting behavioural change. This will be supported by international organisations who will provide capacity, oversight, and expertise as required.

These activities will be focused on areas of active deforestation as a result of human activity. These are primarily unprotected forest frontier zones where local populations are encroaching on the forest for economic reasons. These areas exist across the nations of the Congo Basin, and so CBFA will aim to deliver locally orientated action whilst retaining regional spread.

CBFA will have local economic development at the forefront of decision-making, with a focus on “multi-level settlements” which offer more value from forest conservation, sustainable forestry and value-chain creation than can be gained from wildlife poaching, illegal logging and slash and burn agriculture.
[note] Swilling, M et al., (2021) Fostering Leadership and transformational change for economic diversification in Central Africa, UNECA. https://www.uneca.org/sites/default/files/SROs/Central-Africa/ice-ca-37/ICE%202021%20Study_Final%20Second%20drat%20on%20%206%20Nov%202021%20-%2002112021%20Final%20%20%28003%29.pdf

In focusing on the connection between climate mitigation through forests, and economic benefit for those across the Congo Basin, CBFA seeks to form an exemplar of an inclusive and just climate transition. It aims to demonstrate that the global effort to protect the world’s forest resources will only succeed if they provide local benefits that exceed those available from extractive processes. Measures are outlined later in the business case which demonstrate how the programme will ensure divergence from this objective is safeguarded against.

These approaches will be delivered across three components, which effectively spread the anticipated fiduciary and timeliness risks associated with these types of activities in this part of the world. Component 1 has been strongly inspired by the success of the Improving Livelihoods and Land Use in Congo Basin programme (ILLUCBF) described further in the appraisal case. This component will lead the co-design approach, working with local communities to tailor activities within the scope set out above.

Beyond this, component 2 will enable FCDO to flexibly respond to proposals from reputable partners which strategically fit with the focus of CBFA. Component 3 will continue our ongoing support for the Central African Forest Initiative (CAFI). A fourth component will provide critical underpinning MEL support for component 1 and 2.

Strategic Fit with other UK-led initiatives

Policy & International Cooperation

The UK led efforts to spotlight the region's importance at COP26 via the $1.5bn Congo Basin Pledge, using strong convening power to secure commitments from 11 other signatories. This culminated in a high-level segment at the World Leader’s Summit in Glasgow, which saw the UK Prime Minister and DRC President sign a CAFI-DRC $500m agreement as part of the Pledge. The UK itself has committed £200m to the region overall, with roughly half anticipated to be spent via CBFA, and remainder allocated through other programmes.

As part of the COP26 Presidency legacy, the UK inaugurated the Forests and Climate Leaders Partnership (FCLP) at COP27, which aims to continue Heads of State level dialogue beyond UK COP tenure. Core to FCLP are nations representing the three major tropical forests, including those within the Congo Basin. The Prime Minister announced CBFA in principle during the FCLP launch event in Egypt, and the UK formally named the programme at COP28, which also saw FCLP convene partners in continued support of the Leaders’ Declaration on Forests and Land Use, whilst supporting DRC announcing a national package for forests, climate, and nature backed by finance from public, private, and civil society partners.
[note] UNFCCC (2023) Summary of Climate Action at COP28 https://unfccc.int/sites/default/files/resource/Summary_GCA_COP28.pdf

The UK has taken over the chairing of the Central African Forest Initiative (CAFI), through which the majority of Congo Basin Pledge donor funding to date has been disbursed. CAFI takes the parallel approach of signing ‘Letters of Intent’, which are MoUs with key milestones related to forest protection, livelihoods improvement, and investing in programming on the ground. The UK has committed £31.75m to CAFI through the Africa Regional Climate and Nature (ARCAN) programme. The UK has been an increasingly influential and trusted member of CAFI, taking over the chair from March 2023-25, led by FCDO. This provides a key opportunity in the region, enabling a stronger position to address and criticisms from regional stakeholders regarding the speed and degree of local ownership of CAFI.

The UK is also a leading member of the Congo Basin Forests Partnership (CBFP) having taken on the role of co-chair of the Donor College with the USA. Alongside the Regional College, which includes governments from Congo Basin nations, the Donor College is the most important forum within CBFP. It is the institutional home for the Congo Basin Pledge, and is generally used to make related collective decisions, alongside progressing CBFP objectives and deliverables. The CBFP holds an annual Meeting of Parties, where it has in the past developed a UNFCCC COP narrative and associated outputs. The UK is in a position to leverage this leadership role to influence and expand the scope of discussion within the Donor College to cover better collaboration on strategy and programming amongst donors.

Specifically in DRC, the UK co-chairs the Groupe Inter-bailleur sur Environment et Climat (Inter-donor group on environment and climate - GIBEC). GIBEC is the primary coordination group for donors in DRC and exists to drive alignment amongst participants for diplomatic and political purposes. The UK is a well-respected and trusted participant of this group and is proactively engaged in discussions and decision-making amongst donors.

UK-funded Programming

There are three other major forests-orientated UK programmes currently operating or planned across the Congo Basin. Listed in more detail below, these focus on conservation and sustainable development associated with protected areas (BLF), private sector development and investment (IFSLU), and governance and market reforms (FGMC). These cover a significant portion of the intervention space, whilst leaving a thematic gap for CBFA to operate and deliver against – grassroots, bottom-up delivery approaches for local communities in non-protected forest areas, addressing informal, subsistence-orientated practices which overwhelmingly constitute the primary drivers of deforestation across the region, most notably in forest frontier zones. CBFA will engage with communities with respect to acquisition, enforcement and operationalisation of devolved forest rights through endeavours such as community forestry. CBFA will also help create the conditions for developmental and financial innovations to reach these communities in support of sustainable forest management, all driven through prioritisation of economic gain for beneficiaries.

The Forest Governance, Markets and Climate (FGMC) Programme is a global forest initiative that includes the Congo Basin as a focus region (Gabon, Cameroon, and the Republic of Congo). Thematically, it focuses on strengthening forest governance using market-based incentives making use of inclusive stakeholder deliberative processes to reach consensus on rules governing forests and the benefits derived from them. This includes focus on ensuring community/IPLC voices and interests are included in national decision-making and governance on forest land use that affect them, and how benefits from the forest sector reach them. FGMC has supported the development of policies and regulations for community forests in a number of countries. It has recently completed a £250m 10-year first phase, and is currently developing its business case for a £500m global phase two to build on these successes, including considerations for inclusion of DRC, to deliver between 2025-35.

The Investments in Forests & Sustainable Land Use (IFSLU) Programme is a further global FCDO initiative that works primarily with the private sector to incubate forest-friendly enterprises, build positive enabling environments for sustainable business, and catalyse investment into sustainable practices along deforestation-linked commodity supply chains. IFSLU has been successful in Eastern and Western Africa yet faced challenges in sourcing private sector partners and projects in Central African countries. IFSLU phase I will come to an end in Summer 2024, with a global business case for the second phase approved for operation between 2024-34. The intention is to include a stronger emphasis on Congo Basin countries in this second phase, with £31.5m allocated to the region within a £195m global envelope for the initial 5 years.

The Biodiverse Landscapes Fund (BLF) is a global development and conservation programme led by Defra which focuses on ecosystem restoration and sustainable development to support biodiversity in transboundary protected areas, including the TRIDOM national parks region spanning Gabon, Cameroon, and the Republic of Congo. BLF will operate between 2024-31 with a global budget of £90m, some £12-15m to be spent across the Congo Basin.

The Improving Livelihoods and Land Use in Congo Basin Forests (ILLUCBF) Programme was the last Congo Basin dedicated initiative by HMG and focused on improving the livelihoods of forest-dependent communities through sustainable interventions to reduce deforestation, delivered with £13m between 2015-20. It reported successful forestry and livelihoods interventions during the programme period, but noted the removal of its Monitoring, Evaluation, and Learning (MEL) component reduced capacity to coordinate and reflect on performance. The focuses and successes of this programme have strongly informed development of CBFA.

British Embassy Kinshasa is leading design of a Green Growth Programme for DRC, which will focus on supporting SMEs on energy and agriculture, which are likely to interact with the forestry sector given DRC’s reliance on charcoal for energy generation, and the challenging relationship between arable space and forested areas as the primary driver of deforestation. This programme is set to spend £38m between 2025-31.

The UK’s Global Land Governance Programme (2020-2030) includes three core components, which operate in the Congo Basin: i) the Land Facility - a central offer to wider HMG programmes and Posts on strengthening land and forest governance reforms and implementation capacity, this will begin implementation in early 2024; ii) FoTeRi - strengthening IPLC forest tenure rights and governance structures through grants, capacity building and technical assistance to forest communities and iii) ALIGN – advancing responsible land-based investment in key sectors including forestry, mining and agriculture.
[note] The Forest Tenure Rights component of the GLG Programme is currently being delivered through the organisations Tenure Facility: Home - Tenure Facility: https://thetenurefacility.org/ and Cadasta: https://cadasta.org/
[note] IIED (2020). ALIGN: Advancing Land-based Investment Governance. https://www.iied.org/align-advancing-land-based-investment-governance

The UK is also supporting forest countries within the Congo Basin to implement their forest conservation efforts and meet the methodological and procedural requirements for generated and transacting forest carbon credits. This is through a £10m contribution to the UN-REDD Technical Assistance Programme, operating in ROC and DRC, and the new UK-funded AIM4Forests Programme (£24.5m) partnering with FAO to support governments strengthen their monitoring of forest sector emissions.

The UK also contributes to multilateral climate financing vehicles, including those incorporating REDD+ approaches. These partners include large-scale climate and nature funds such as the Green Climate Fund, Global Environment Facility and Climate Investment Funds, as well as the Forest Carbon Partnership Facility (FCPF – UK contribution £141.5m) which will provide the governments of Republic of Congo and DRC with readiness payments to reduce greenhouse gas emissions.

### vi. Impacts, Outcomes, Results & Indicators

With £90m across 7 years (2024-2030), CBFA will use UK International Climate Finance to achieve results for poverty reduction and development, climate resilience, forest protection and reduced greenhouse gas emissions. The programme will contribute to the ICF nature and forest finance commitments. Programme funding will contribute towards a low-carbon and equitable transformation of the land and forests sector in developing countries. The Theory of Change, presented in full in the Appraisal Case, draws on evidence of what works to influence outcomes for communities and natural resources, operationalising devolved forest rights, improving the policy and legislative environment with respect to land tenure and forest-relevant markets. It also factors in the scope to use financial innovation to deliver relevant outputs, outcomes and impacts.
[note] Intergovernmental Panel on Climate Change (2019). Climate Change and Land: an IPCC special report on climate change, desertification, land degradation, sustainable land management, food security, and greenhouse gas fluxes in terrestrial ecosystems. https://www.ipcc.ch/site/assets/uploads/2019/11/SRCCL-Full-Report-Compiled-191128.pdf

Impact Statement: Reduced deforestation in the Congo Basin and improved economic outcomes for forest dependent communities.

Outcome Statements:

1. Improved forest & land use governance and forest management solutions that support forest dependent communities.
2. Improved enabling conditions including empowerment of, and economic opportunities for; local actors and cooperation between stakeholders.

Provisional results: The full programme results framework (logframe) will be finalised during the inception phase, once the final set of activities has been selected. However, estimated expected results, based on conservative modelling assumptions (see Appraisal Case), include:

1. Deforestation avoided: 342,041ha.
2. Forest Disturbance avoided (in addition to Deforestation avoided): 342,041ha.
3. Over 100,000 direct beneficiaries in rural communities in forest landscapes, including increased livelihoods and job opportunities for women and girls, with additional 300,000 indirect beneficiaries.
4. Over 100 Community Forests supported by the programme.
5. Over 50 Community Forest Enterprises supported which are economically profitable or have been supported to gain better access to markets.
6. An estimated 99.4MtCO2e of avoided emissions and carbon abatement over the programme lifetime.
7. The programme will also have a demonstration effect, building a body of evidence on innovative interventions in the Congo Basin and putting in place the building blocks to help make future investments more effective. 3x knowledge product outputs will be produced under the Monitoring, Evaluation & Learning (MEL) component during programme implementation.

Potential ICF Key Performance Indicators:
- KPI 6 - Net change in Greenhouse Gas emissions (tCO2e) – tonnes of GHG emissions reduced or avoided as a result of ICF.
- KPI 8 – Ecosystem Loss Avoided (Hectares) as a result of ICF.
- KPI 15 – Extent to which ICF intervention is likely to lead to Transformational Change.
- KPI 17 - Hectares of land that have received sustainable land management practices as a result of ICF.

### vii. Risks and Assurances

Climate Change and Environmental Sustainability: CBFA will satisfy UK government commitments to align programming with the Paris Agreement and nature-proof ODA. All programme spend will be counted as ICF contributing to the nature and forest spending commitments. Relevant ICF KPIs are included in the results framework. The Management Case also outlines how programme management arrangements will ensure sufficient climate and environment expertise and input are accessible throughout programme design and delivery.

In line with the FCDO Programme Operating Framework (PrOF) Rule 5 climate commitments, a formative climate risk assessment found in Annex B was undertaken as part of the business case development process, identifying the risk as major, with climate related risks potentially significantly impacting programme success, thus risk reduction measures have been incorporated in design and operations. The programme is classified as ‘Principle’ under the Rio Markers given its central focus on climate and environment. In line with the Paris Agreement, the programme will not provide any financial or promotional support for the fossil fuel energy sector overseas.

Public Sector Equality Duty: The programme will operate in line with Public Sector Equality Duty (PSED) and the requirements of The UK Equality Act 2010. This includes due regard to the need to eliminate prohibited conduct, such as unlawful discrimination, harassment and victimisation; advance equality of opportunity between people who share a protected characteristic and people who do not share it; and foster good relations between people who share a protected characteristic and those who do not share it. This will be addressed through due diligence on partners, operating policies and monitoring. The protected characteristics most likely to be addressed in this programme include sex, race, age and disability.

Gender, Disability, Inclusion and Leave no one behind: Climate change disproportionately impacts the poorest and most excluded. Women and girls, people with disabilities and Indigenous Peoples and Local Communities (IPLCs) are disproportionately impacted by environmental degradation and typically have less ability to cope with shocks and stresses. The disproportionate impacts of biodiversity loss on women and girls include higher domestic work burdens and exposure to gender-based violence, loss of income and declining health. IPLCs and women & girls are also disproportionately less able to engage in and influence related decisions which affect their lives, reinforcing this cycle.

Although value chain-oriented, community-focused and nature-related interventions have the potential to provide quality opportunities to the excluded, they can also serve to reinforce social inequalities e.g. keep women in low paid work, exclude poor and marginalised groups when land rights are formalised, transfer costs/risk to women, fail to provide Free, Prior and Informed Consent (FPIC). Moreover, interventions run the risk of delivering limited livelihood and poverty reduction benefits; unevenly distributing benefits or enabling benefits to be captured by elite groups; or negatively impacting indigenous rights and cultural resources through land acquisitions.

Given the substantial and disproportionate impacts of climate change and deforestation on women and marginalised groups, this programme has a Gender Equality and Disability Inclusion Marker rating of ‘Significant’, in line with PrOF guidance. CBFA will meet minimum equality commitments and seek to proactively address the inequalities facing climate-affected rural economies.

To comply with UK commitments to gender equality markers, the PSED, and International Development (Gender Equality) Act 2014, CBFA will adopt ‘do no harm’ principles and measures to ensure interventions do not worsen inequality and support the practical needs of potentially marginalised groups. At a minimum, all tier 1 suppliers will need to:

1. Ensure all data are disaggregated by gender and other characteristics, where possible, and investigate ways to include intersectionality (for example class, ethnicity, age, disability, religion, sexuality, parenthood etc) in data collection and analysis.
2. Base their programme design and implementation on sound gender, equality and social inclusion (GESI) analysis, integrating multi-disciplinary expertise and including consultation with affected groups (i.e. ensure FPIC is provided).
3. Analyse visible and hidden power dynamics as part of their foundational GESI analysis and seek to empower and include potentially marginalised groups within project engagement and decision-making structures.
4. Develop credible plans to monitor the engagement of, and impact on, differentiated social groups.
5. Establish mechanisms for ensuring that any adverse impacts of the programme are identified and addressed.
6. Incorporate proactive measures to enable participation from marginalised groups in programme activities and ensure programme benefits are available to marginalised groups.

Conflict, fragility and stability - The programme is likely to operate in fragile, conflict-affected environments or those where there is a potential link between conflict risks and natural resource management. This is most notable in DRC through conflict in the East, where factional groups rely on revenue from natural resource exploitation and seek to monopolise the benefits from international conservation efforts. While conflict has been linked to both accelerated and reduced deforestation in tropical forests around the world, statistical analysis in the DRC suggests conflict as a driver of deforestation.
[note] Butsic, V. et al., (2015) Conservation and conflict in the Democratic Republic of Congo: The impacts of warfare, mining, and protected areas on deforestation https://luclab.berkeley.edu/wp-content/uploads/2015/08/congo.pdf

CBFA recognises the presence of networks that combine state/non-state and civil/military actors seeking to control resources in the basin, and their propensity for violence when changes occur to the existing distribution of wealth and influence. Such issues are present to a lesser extent across the region, and also include challenges faced by environmental defenders and community activists. Through our delivery partners we will continue to assess the context, conflict dynamics and how the programme impacts on the local population to ensure a ‘do no harm’ approach. This will also include avoiding inflammation of localised disputes, e.g., through preferential treatment of groups within a local community – strong ex-ante analyses will be conducted to prevent this. We will also work with Posts to ensure the programme does not contribute to worsening conflict and, with wider Government stakeholders, undertake and share conflict analysis and information. This will be supported by a detailed conflict assessment as part of the programme inception period.

Key safeguarding actions the programme will take include:
- Being deliberate about the regions in which it operates and avoiding what tend to be region-specific hotspots of conflict such as Eastern DRC, and Northern & border regions of Cameroon. CBFA will have a physical presence in an area comprising less than 1% of the Congo Basin and this area will be chosen to minimise the impact of conflict, a strategy that has proven effective in sustainable forestry programmes in the Republic of Congo.
- Ensuring additional benefits are created for governments and forest communities, rather than a reallocation of existing benefits.
- Ensuring programme interventions do not create grievances by undermining people’s livelihoods or access to land. This design principle will avoid situations that have occurred in the past when conservations efforts have seen communities take up arms or support armed groups to protect the benefits they receive from resource exploitation.
  [note] Schouten, P (2022) Our climate future depends on conflict dynamics in Congo. Climate and conflict. https://www.diis.dk/en/research/our-climate-future-depends-on-conflict-dynamics-in-congo
- Being explicit during programme design about withdrawing the programme where members of state agencies are involved in illegal resource exploitation, a threat to programme benefits, or the safety of personnel becomes a risk.
- Being explicit during programme design with regards to the role of respective national militaries. More specifically, being explicit about the programme withdrawal (from the region or the country) where armies or government officials undermine local conservation efforts or are found to support high-level resource extraction.
- Harness the rapidly growing adoption of digital technology to enhance transparency around resource use.
- Link forest resources to more diverse economic activities so as the disrupt existing power networks around commodity extraction. Forest, mining and tourism products can be linked to regional value chains and value addition as CBFA supports economic diversification and improved governance.
  [note] Swilling, M et al., (2021) Fostering Leadership and transformational change for economic diversification in Central Africa, UNECA. https://www.uneca.org/sites/default/files/SROs/Central-Africa/ice-ca-37/ICE%202021%20Study_Final%20Second%20drat%20on%20%206%20Nov%202021%20-%2002112021%20Final%20%20%28003%29.pdf

Social Safeguarding - This programme will engage with governments and at the community level, and is likely to engage with vulnerable populations. The programme will be delivered via third parties that may include multilaterals, I/NGOs and private sector entities. Safeguarding will be considered throughout the programme cycle. We will ensure that safeguarding due diligence checks are in place across each partner and will only work with partners that have sufficiently robust policies and practices in place to mitigate risks and ensure the prevention of sexual exploitation and abuse and harassment (SEAH), harm to marginalised peoples, hard to reach Indigenous Groups, and those affected by forced displacement & resettlement. Partners will be expected to provide this assurance for their downstream partners (assessed through the due diligence processes). Safeguarding risks will be closely monitored through agreed periodic meetings and direct monitoring visits.

Community Leadership – the behavioural characteristics of individuals and groups occupying leadership roles within local communities is important in determining rates of success regarding forest-related interventions. Studies have shown that leaders who prioritise social cohesion, cooperation, and equality saw significantly improved tree cover indicators in their areas of influence. Evidence also indicates a further positive effect from women’s participation in forests user groups. CBFA will ensure social dynamics are assessed within any area of intervention, with emphasis on identifying and engaging with individuals and groups demonstrating a strong track record of trust and reliability within the local community, alongside encouraging participation of women decision-making processes.
[note] Kosfeld, Michael, and Devesh Rustagi. 2015. "Leader Punishment and Cooperation in Groups: Experimental Field Evidence from Commons Management in Ethiopia." American Economic Review, 105 (2): 747-83.
[note] Leone (2019) Women as decision makers in community forest management: Evidence from Nepal. Journal of Development Economics. Volume 138. Pp180-191. ISSN 0304-3878. https://doi.org/10.1016/j.jdeveco.2019.01.002

Safeguarding measures will be designed to mitigate risk and enhance opportunity. Measures will be taken throughout the programme design and management process as well as the more granular project/activity development cycles that will operate under each programme component. For example, in-depth social, environmental and gender analysis will form part of suppliers’ inception phases and screening assessments will be embedded into the project/activity development cycle under each programme component. Disaggregated monitoring and thematic evaluations will be used to assess the performance of these safeguarding measures. In respect to suppliers, safeguarding expectations and responsibilities will be made clear through FCDO reviewed code of conduct terms in commercial contracts and agreed terms in grant agreements. Lastly, all personnel working for suppliers and working in the FCDO team will be made aware of their safeguarding responsibilities and the appropriate reporting channels, and suppliers much provide the training required to fulfil these requirements.

Partnership Principles – FCDO primary partners will be tier 1 suppliers, however, close relationships will be developed and maintained with stakeholders across the region to ensure sufficient trust is built between HMG and those involved and/or benefiting from the programme. Such relationships will be monitored and reported on to understand where challenges and issues exist, and due process carried out on resolving accordingly to manage reputational risk. Whilst not currently planned in the programme, options will be considered for closer working with regional governments to allow greater flexibility and co-ownership over designed interventions. If such an option is pursued, due diligence and process will be followed with respect to FCDO partnership principles.

Counter terrorist financing and anti-money laundering - FCDO does not fund proscribed organisations, nor designated individuals or entities subject to financial sanctions in the UK. FCDO is committed to the prevention, deterrence and detection of terrorist financing and money laundering under the Terrorism Act 2000 (TACT). The programme will apply a zero-tolerance approach towards terrorist financing and money laundering. All funds will be channelled through implementing partners. The risk of funds being diverted to support terrorism is considered to be low and there will be robust mechanism in place to track flow of funds for intended purposes. Comprehensive due diligence assessment, delivery chain map and third-party monitoring will be applied to ensure compliance with this policy.

Risk - Risk rating for the programme overall is Major. This is necessary given the substantial challenges faced across the Congo Basin with respect to governance, intervention success, fiduciary risks, and fragility. There is appetite to take risk in policy and programme delivery, using the programme to help operationalise devolved forest rights, improve sustainable resource management and improve development outcomes for communities. There is appetite to explore innovative, higher-risk approaches such as payments for ecosystem services in a complex high fiduciary risk context. If pursued, such approaches will be subject to thorough due diligence processes to mitigate associated risks as far as possible. There is low tolerance for safeguarding risks and a zero-tolerance approach to both fiduciary and safeguarding breaches. There is willingness to take on and manage reputational risk, so long as that does not harm the overall programme licence to operate. Further information on risk and escalation is set out in the Management Case.

## Appraisal Case

The Strategic Case set out the scope of the proposed intervention, making the case for the geographic and broad thematic focus of the programme on the Congo Basin, and on addressing the central issues affecting deforestation. It arrives at objectives for the halting and reversal of deforestation in the region, and delivery of economic benefits to people and communities, as well as improving overall engagement between international partners and stakeholders in the region. The Appraisal Case will be presented in three parts:

  1. Solution options appraisal – which set of interventions best addresses the issues to achieve the outcomes and impacts specified in the Strategic Case?
  2. Delivery options appraisal – what is the best delivery mechanism and choice of partners for the set of interventions selected?
  3. Preferred option – summary of the planned intervention, accompanied by an evidence-based Theory of Change and Value for Money assessment.

The full analyses underlying these summaries adhere to appraisal guidance set out in the Treasury Green Book and PrOF Guides.

### i. Options Appraisal

Solutions Options Appraisal

In considering the delivery of the outcomes specified in the Strategic Case, we identified five feasible solutions options for the Congo Basin Forest Action Programme scope and activity components:

Option 0: Do no more (the Counterfactual). No funding is allocated for the design and delivery of this new programme. This would mean no additional UK funding to support the Congo Basin Forests as announced at COP26 and COP27, effectively reneging on public announcements for forests, most significantly the £200m Congo Basin Pledge that this programme constitutes almost half of. Beyond this, there would be a negative impact on efforts to reach broader public ICF3 commitments, including the £3 billion for nature, and £1.5 billion for forests. Other UK global programming would continue delivering their footprint across the region, continuing UK presence without a new, regionally exclusive programme.

Option 1: Broad programme scope, extending beyond community level, with a greater emphasis on national level governance and wider architecture for financial innovations, e.g. PES in its broader sense. Consider more expansive programme scope that covers a range of host government priorities. Under this option, the programme would have maximum flexibility to pursue thematic interventions in pursuit of the Impact and Outcome Statements outlined in the Strategic Case. This could re-open interventions related to protected areas, working with communities on livelihoods or private sector initiatives.

Option 2: Tighter definition of local level community forestry work, emphasising securing and operationalising rights, with some livelihoods-related work. This programme scope would be the tightest, closely following past programmatic efforts under the ‘Improving Livelihoods and Land Use in Congo Basin Forests’ (ILLUCBF) Programme. In addition to work on securing land and forest rights as well as management of community-controlled resources, there could be a component that worked on local livelihoods. Under this option, CBFA would be more focused on IPLCs and would work at grassroots level, but would likely exclude higher risk financial innovations, excluding out of scope non-community forests interventions.

Preferred Option
Option 3: Broader local level engagement and applied forest policy, with intervention options extended to more sustainable livelihoods, community level governance including community forests, financial innovations and limited enabling environment work. Under this option, which sits between Option 1 & Option 2 in terms of scope, CBFA could retain a focus on community level interventions on rights, resource management and livelihoods, while also having the scope to consider relevant applied policy interventions that extend beyond direct engagement with those communities, such as on national policymaking or data. Under this option, the programme could seek to scale ILLUCBF and test innovative interventions such as PES or links to voluntary carbon markets. A close link to IPLCs would be retained, but such a component could also take on regional-level efforts at applied research in pursuit of larger scale solutions for the Congo Basin. Work on protected areas is presumed to be excluded, as would interventions that lack a line of sight to community-level impact.

Option 4: Heavier emphasis on private sector development, including the work of larger firms in the region. This would allow the programme to engage with a set of international actors active in the Congo Basin, some of which have obtained and are operationalising land rights – e.g. agricultural industry or extractives actors. Local level engagement would be geared towards livelihoods benefits, rather than focusing on rights and their application, which may exclude work on governance and local communities and Indigenous Peoples rights. Focus on some innovative financial interventions could be retained where these relate to the actions of private sector actors – voluntary carbon markets and offsetting could be a good fit here. This option has a high risk of duplication with other HMG programming with a similar thematic focus, notably IFSLU2 and the DRC Green Growth Programme. CBFA would need to work closely with these programmes to effectively complement activities.

Drawing from Green Book and PrOF guidance, these strategic options were appraised using evidence-based qualitative analysis against the desired programme outcomes set out in the strategic case and a set of Critical Success Facts (CSFs) presented in this Appraisal Case.

Scoring process - Table 5 scores each option above against FCDO Key Success Criteria relating to UK climate change priorities, FCDO operating model requirements and ability to make the biggest impact for the poorest. These criteria are divided into assessments of internal considerations with respect to delivery of the programme, and assessments of a smaller number of more heavily weighted external considerations. The scores range from 5 as the highest (very good) to 1 as the lowest (poor).

Table 5 - Comparison of Key Success Criteria (1 – poor, 5 – very good)
	0: do no more	1: broad scope / do everything	2: only community forests	3: local dev and forest policy	4: private sector focus
Strategic Fit with UK Commitments, including ICF	1	4	5	5	3
Achievability & Ease of Deployment	5	4	2	3	2
Alignment with UK Inclusion Priorities	1	3	5	4	2
Potential Value for Money, including Likelihood to Leverage Other Finance	3	3	2	3	4
Internal Considerations Scores (0.4 Weighted)	4	5.6	5.6	6	4.4
Likelihood of Delivering Transformational Change	1	5	3	5	4
Targeting, Including Reach to the Most Vulnerable	1	3	5	5	3
Legitimacy, Local Ownership and Incorporation of a Regional Dimension	1	3	4	4	3
External Considerations Scores (0.6 Weighted)	1.8	6.6	7.2	8.4	6
TOTAL MCA	5.8	12.2	12.8	14.4	10.4

Strategic fit with UK Commitments: The emphasis here is ICF and the Congo Basin Forest financial commitments and so the speed of mobilisation of programmes matters for the score. All options score acceptably on this other than Option 0, which would be a retreat from previous funding commitments and UK emphasis on the importance of the Congo Basin. Options 1 and 4 lack sufficient emphasis on IPLCs to score as well as Options 2 and 3. While Option 3 has less IPLC focus than Option 2, it has the benefit of enabling work relating to development of high integrity carbon markets.

Achievability and Ease of Deployment: This option is considered again in the context of delivery channels, but some thematic areas will be easier to deliver than others. A tighter programme scope will be more difficult to achieve in practice because of the greater limitations on eligibility of spend. Therefore, more flexible programming options are likely to receive higher scores.

Alignment with UK Inclusion Priorities: Delivery of all options would conform to the required assurance set out in the Strategic Case, however some options are likely to involve improved engagement with marginalised groups, particularly IPLCs. This will depend on how tightly the programme is focused at the local level and therefore how much emphasis is given to consulting these groups and addressing their needs. Option 2 is therefore likely to score most highly, while Option 1 will suffer from breadth in scope and Option 4 will be impacted by private sector practices with regard to inclusion.

Potential VfM: under this row, we consider the likely cost dynamics – economy, efficiency, effectiveness and equity, with an emphasis on the scope to bring in other finance. The latter drives the higher score for private sector related programming, as well as the lower score for the tightly focused community forestry work. This type of intervention is less likely to attract outside finance. VfM is covered in more detail in the assessment at the end of the Appraisal Case, as well as in the Commercial case.

Likelihood of Delivering Transformative Change: here we consider the potential for impact at scale, particularly with regard to potentially systemic changes. Although Option 2 has the potential to deliver effective programming locally, it would rely on replication based on results as it does not engage with national systems nor with innovative financial mechanisms that could have outsized impacts beyond the region. Programmes that consider the use of systems such as PES or carbon markets are recognised separately for each (I.e., Option 4 is likely not to include PES, but would include carbon markets).

Targeting: this criterion is about the reach to vulnerable populations, and therefore the potential of the programme to deliver effective poverty reduction. This is higher for more targeted programmes, with the private sector focused piece difficult to assess owing to the different scales at which private sector operates in the region – SMEs in DRC likely to score better than larger scale logging in Gabon.

Legitimacy, Ownership, and Regional Character: this assesses the degree to which interventions are likely to be seen by populations and host governments in the region as co-owned. It is intended that the programme will include an extended co-design and consultation process with beneficiaries for the majority of the planned spend. However, options that have greater flexibility may warrant higher scores here, as would interventions that are seen to address local needs – with targeting at the community level considered as likely to be well-perceived.

The recommended option is Option 3 i.e., to deliver all components within the programme scope. The five options are appraised in the VfM analysis later in the appraisal case.

Delivery Options Appraisal

Three options were considered for delivering the preferred solution option for CBFA:

Option A: Multilateral delivery - A multilateral partner manages and delivers all components of the Business Case. In the CBFA context, this is highly likely to involve disbursement of funds via CAFI and significantly increasing UK CAFI engagement on an ongoing basis to ensure our thematic priorities are taken forward as we intend.

Option B: Outsourced service contract - To the extent possible, programme management functions will be outsourced to one umbrella delivery partner, which will then manage a combination of grants and contracts to organisations best suited to delivering each component.

Preferred Option
Option C: FCDO management - components of the Business Case will be outsourced and managed by FCDO under a mixture of commercial contracts and grants best suited to delivering each component, including multilateral contributions where appropriate. This option is likely to require greater resource from FCDO to undertake monitoring and risk management, alongside engagement from Posts in the region.

Similar to the strategic options, these delivery options were assessed against CSFs drawn from Green Book and PrOF guidance. The delivery options appraisal concluded that Option C is the preferred option for delivering CBFA, because it will:

- Diversify the risks of the programme away from one partner, whether a bilateral supplier or a multilateral. Addresses stakeholder concerns about previous experiences which saw slow disbursement and reduced grassroots delivery of funding.
- Avoid the additional delivery risks and dependencies associated with delivering the entirety of CBFA through a single large contract with one supplier, including the potential for duplication or higher administration costs associated with longer delivery chains.
- Increase operational control of FCDO over activities and any flexibility required within the programme lifetime, particularly by comparison with a multilateral-only channel where funding priorities are decided by multiple donors, whilst also providing a strong entry point to influence CAFI using programme learning.
- Enable each delivery partner engaged in a set of differing lines of effort to make best use of their unique capabilities and areas of comparative advantage.
- Enable the programme to replicate and scale-up the arrangements that were in place under previous programmes and make use of arrangements that have been used effectively in other interventions focused on communities and devolved forest rights in the Congo Basin, while leaving scope to support promising initiatives that may emerge from new potential suppliers.
- Increases flexibility in the programme design to work with existing central programme offers, for example on land governance. This could improve efficiencies and lower costs as it would utilise an existing offer designed for this purpose, with an existing supplier and established delivery chain.
- Improves ability to capitalise on wider FCDO relationships and political access, taking advantage of established connections, capabilities, and capacities to ensure effective programme delivery. This could range from UK bilateral political relations, to utilisation of internal functionality like FCDO’s MEL capacity.
- Offer stronger potential for flexible and response programme management and a phased approach, in line with plans for the delivery of a long-term programme.

Table 6 - Comparison of options against Key Criteria (1 – poor, 5 – very good)
Criteria	Option A	Option B	Option C
Likely perception of programme as additional support by host governments	2	3	4
Potential Value for Money / Cost drivers	4	2	3
Supplier capacity and capability	3	3	4
Ease of programme management	4	4	2
Control over risk and delivery	2	3	3
Timing and resources	4	2	3
Ability to improve knowledge management and learning	2	4	4
Total	21	21	23

Likely perception by host governments – a key factor for scores here is the extent to which new programming and funding will be perceived as additional by host governments. This is the driving factor behind low score for Option A, given CAFI is perceived as a pre-existing entity, with which governments in the region are already engaging at Board level. Option B introduces another intermediary, and is therefore likely to be perceived less well than Option C, which lends itself more readily to government-to-government engagement.

Potential value for money/cost drivers: this is considered further in the Commercial Case, but a key driver is the need to fund new programme management infrastructure for CBFA. Option A scores well as it would utilise existing CAFI Secretariat architecture and personnel resources, albeit these would need to be expanded. Option C outperforms Option B due to the programme leveraging internal HMG resource and partial benefits of existing CAFI Secretariat architecture, while under Option B there would be more costs associated with outsourced programme coordination and programme management – typically involving a larger team based outside the host country, where day rates for consultancy are likely to range from £400-£900, depending on the seniority.

Supplier capacity and capability: this criterion relates to the combination of expertise likely to be provided by suppliers through each modality. Option C outperforms the other options as it allows for a mix of qualified multilateral agency staff with existing networks, alongside other skills brought in through competitive tenders for bilateral delivery partners. The result is likely to be a greater diversity of capacity and capability.

Ease of programme management: this relates to the ease for FCDO of overseeing the resulting programme. Option C is more complex as it involves multiple delivery channels and therefore multiple governing agreements, e.g. contracts, MOUs or accountable grants. These additional management requirements will be met through the additional capacity afforded by the two project funded staff recruited under CBFA. These staff will allow the programme to operate more efficiently and effectively through being based in the region, managing relationships with partners on the ground, freeing up the core FCDO management team to focus on overall strategic delivery. This structure and approach are discussed further in the management case. Options A and B effectively outsource this programme management to other actors, at a cost. This cost is higher for Option B, as reflected in the Potential VfM score, whereas for Option A would likely see CAFI the primary provider of programme management, reducing the resourcing impact on FCDO at a cost of control over activities.

Control over Risk and Delivery: this programme is operating in a difficult environment, and there are likely to be challenges under all delivery approaches. However, a multilateral or CAFI-only option is perceived as carrying greater risks due to the significant loss of control over how and why funds are spent, and reduced sight to monitor interventions given longer delivery chains. It is also likely that Options B and C would benefit from tighter accountability in a bilateral programming context, where HMG is better placed to set the extent of monitoring and other controls and to adapt these as needed.

Timing and resources: this relates to the likely ability of the delivery organisations to deliver the programme into an implementation phase in a timely manner. This is relevant in the context of the funding commitments that CBFA is intended to contribute to. Under Option A, this is likely to be most accelerated due to the presence of an existing MOU to govern the disbursement of payments, as well as the pre-existing infrastructure of programme management and delivery and the network of CAFI partners. Option B takes the most time to move into implementation due to the need for a long procurement process associated with a large service contract.

Knowledge management and learning: this criterion concerns the potential for additional contribution to the body of evidence on interventions in the relevant thematic and geographic space, forest-related development work in the Congo Basin. Options B and C allow for new bilateral programmes and lend themselves more easily to working with a programme MEL supplier to trial, monitor and evaluate tailored interventions.

The assessment suggests an overall preference for Delivery Option C, combined with Solutions Option 3. This option would see the FCDO team in the UK and across Central Africa managing a regional Congo Basin-focused programme with a mixed delivery modality that can address key themes raised in the Strategic Case, whilst contributing evidence and learning to the global movement to tackle climate change and environmental degradation. This option provides the highest level of interaction in strategic alignment, delivery practicality, flexibility of funding into different themes, and learning between themes and partners.

Importantly, this approach showcases UK commitment to the Congo Basin, increases visibility and provides the potential to flex into different areas based on evidence and in line with the Theory of Change. This approach would enable FCDO to build on past, successful work at the community level through the ILLUCBF programme that concluded in 2020, while also exploring innovative approaches to tackling climate issues in the region such as PES and working with regional efforts on applied knowledge products and potentially research. The retention of a broader piece aligned to the ongoing efforts of CAFI in the region is important as it will allow the programme to build on regional efforts, to plug directly into existing agreements with host country governments, and to move quickly to an implementation phase on at least one strand of the programme. The resulting programme would offer a consolidation of several smaller programmes and partners currently and formerly working with FCDO in this region whilst also maintaining flexibility to respond to future spending review and strategic shifts.

### ii. Programme Approach and Componentry

CBFA will focus on grassroots, bottom-up delivery approaches for local communities in non-protected forest areas, addressing informal, subsistence-orientated practices which overwhelmingly constitute the primary drivers of deforestation across the region, most notably in forest frontier zones. This will be done whilst ensuring economic benefits are effectively transferred to beneficiaries. To support this, the programme will also engage with communities with respect to acquisition, enforcement and operationalisation of devolved forest rights. CBFA will also help create the conditions for developmental and financial innovations to reach these communities in support of sustainable forest management.

Through the preferred option, CBFA will maximise opportunities to:

  - Give greater focus on supporting stronger local ownership of interventions and alignment with national strategies to improve the enabling environment and increase probabilities of solutions enduring beyond the funding period. This will include:
- Use of an inception or co-creation phase to enable better targeting and prioritisation of programme activities with national governments and local communities, particularly marginalised groups (e.g. women & girls, indigenous peoples, those with disabilities)
- Seeking to work with regionally endorsed institutions, as well as national NGOs and civil society where possible, supporting localisation, and building on previous successes.
- Earlier, deeper government engagement on focus and governance of the programme at country level, for example through ensuring representatives are consulted for advice through the entire design and implementation period.
  - Prioritise specific thematic and geographic gaps which are not supported by other UK programmes and donors, including working at the local communities’ level on grassroots support to drive more sustainable practices, improve access to land tenure rights, and promote local and regional knowledge development.
  - Avoid duplication of other UK programmes and donor activities, but seek to strengthen and collaborate on programming through enhanced coordination.
  - Push greater focus on regional learning between countries, engendering state-level South-South cooperation and platforms shifting the focus from learning between NGOs at head-quarter level to exchange between countries.
  - Secure successful impact through also working with established partners, while testing engagement with new stakeholders in a graduated manner.

Design and Delivery Model

CBFA has been developed based on a Theory of Change informed by a thorough assessment of the evidence, lessons and recommendations generated in the delivery of past FCDO programming. The programme design draws from consultation with a range of experts and partners engaged in relevant thematic priorities in the region, assessment and mapping of the wider operating context for the programme, reviews of the peer-reviewed and grey literature, and consultation with FCDO Posts in relevant countries.

The programme sets out to achieve the outcomes articulated in the Strategic Case:
- Improved land & forest use governance and forest management solutions that benefit forest dependent communities.
- Improved enabling conditions including empowerment of local actors and cooperation between stakeholders.

These will be most effectively pursued through a comprehensive delivery of all the components identified in the strategic options appraisal of this Appraisal Case. Moreover, there are holistic benefits to driving coordination alongside a mix of well diversified programming to manage the risks associated with both the operating context and the application of innovative approaches. It is intended that in parallel to the delivery of the core programme activities, UK diplomatic missions in both Yaoundé and Kinshasa will be equipped to engage on relevant policy concerns with host governments, as well as playing a role in monitoring and risk management for the programme. This intention informs the need to consider Programme-funded posts as part of delivery, explored further in the Management Case.

Building on lessons learned, CBFA will consist of four complementary programme components that will work synergistically to catalyse improved forest management solutions that lead to reduced deforestation and improved outcomes for local communities through an overarching intervention approach articulated in the Theory of Change (Figure 5). These four components are:

Component 1: Community Forests – interventions co-designed and co-owned by beneficiaries for lasting legacies.

Component 2: FCDO Partners Facility – flexible support for best practice and innovation, in support of component 1 objectives.

Component 3: Central African Forest Initiative (CAFI) – driving collaboration and collective opportunities.

Component 4: Monitoring, Evaluation & Learning – ensuring effective and agile programming.

The primary focus of the programme is to facilitate, promote and secure forests-orientated sustainable livelihoods and land management for economic gain and reduction of deforestation. This will be achieved through successful delivery of Component 1. However, this component is likely to take some time before operationalisation and major disbursement, thus Component 2 allows for quicker action whilst also providing ongoing flexibility in the programme. Component 3 supports Components 1 and 2 through improving the enabling conditions under which communities operate. The MEL Component (4) seeks to proactively monitor performance, support evidence development, appraise analyses, and facilitate information sharing.

Table 7 - CBFA Component Matrix
Component	1 Community Forests	2 FCDO Partners Facility	3 Central African Forest Initiative	4 Monitoring, Evaluation & Learning
Primary objectives	Increased participation, transparency and accountability in forest land use planning and decision-making processes	Scaling of forestry best practice across the region, and flexible, rapid funding of innovation. Relatively quick mobilisation.	Successful Central Africa Forest Initiative delivery, aligned with UK priorities and core needs of the Congo Basin	Monitoring, evaluation and learning outputs to track performance and improve future interventions with regional legitimacy
Primary outputs	Secured forest rights by communities, evidence of improved economic and environmental outcomes co-designed with stakeholders	Improved economic and environmental outcomes based on external proposals and agile programming	Support to country LoIs and other joint initiatives agreed by CAFI with host governments in Cameroon, Gabon, DRC and RoC. Potential to support results-based payment incentives	Verification of analyses, ongoing reporting, and improved or expanded knowledge outputs covering the Congo Basin region, including regional institution output and programme MEL.
Timeline	Year 1 - inception phase, seeking co-design with stakeholders. Implementation from Year 2.	From Year 1 – rapid commencement of disbursements once approvals process established.	From Year 3 – contributions to existing and planned CAFI interventions in scope.	From Year 1, although likely to involve process that extends into Year 2.
Responsible parties	Delivery partners via lead partner, likely to be private sector or INGO	FCDO managed partners facility for proposal appraisals	CAFI	FCDO to manage contributions or contracts. MEL via independent third party
Budget emphasis	High	Moderate	Moderate	Low
Risk	High	Moderate	Low	Low

Overarching Intervention Approach & Design Methodology

The programme will not force any beneficiaries to change their economic activities. It will focus on collaboratively making alternative livelihoods economically sustainable over time, with the long-term ambition of substantiating enduring behavioural change. Given economic modelling can indicate economic losses for local communities in the immediacy as core extractive livelihood activities are reduced, safeguarding against this will be a fundamental part of the approach and design methodology set out below.

Behavioural change is fundamental to the enduring success of any intervention delivered within CBFA, and presents one of the most significant challenges for the programme to tackle. To ensure impact is being realised, partners will work with the MEL provider to monitor and understand behavioural shifts within the local community, tracking adoption of practices by intended beneficiaries, alongside broader indirect community uptake through exposure to programme activities.

The scope for CBFA interventions is constrained to activities which reduce deforestation and enhance economic livelihoods, including in areas such as community forestry and securing land tenure. These form part of the component specific activities set out later in this business case, however it is important to note that these are deliberately indicative, and do not represent an exhaustive list of what CBFA will deliver. This is to avoid prescribing and restricting approaches ahead of the core co-design phase, which will see bespoke interventions tailored for local communities based on specific circumstances. Given this, it is critically important to substantiate a clear, well-defined approach on how and why these activities will be selected. The below methodology outlines this, and will be the responsibility of the lead delivery partner to implement with oversight from the MEL provider:

Geographies Selection: As part of the selection progress for component 1, partners will identify a long list of potential landscapes across the Congo Basin which may be appropriate for application of CBFA interventions. These will be spread across the four focus countries, and occupy forest frontier zones without protected status.

Analysis: To assess intervention feasibility and likelihood of successful and sustained change ahead of time, these geographies will be subject to rapid ex-ante analyses carried out by relevant expertise amongst selected partners. Analyses will focus on current socio-economic status and need, deforestation rates and associated drivers, localised geographic priorities, conflict sensitivity, current and previous donor programming activities, and viability of monitoring and evaluation activities, with a conclusory recommendation on whether to intervene or not. An independent appraisal of these analyses will be conducted by the MEL provider and a final decision will be made by FCDO.

Co-Design: Geographies which meet the expected criteria applied in the analysis will be taken into the co-design phase. Local communities will be engaged with support from relevant CSOs, NGOs, and local government, with the goal of designing tailored interventions that meet their specific needs. Attention will be paid to the behavioural characteristics of those in leadership roles within these stakeholder groups to minimise risk of dereliction and ensure appropriate knowledge and awareness of local context. Design of interventions will be reported on by partners at set intervals, and will require final approval by FCDO for implementation. Criteria to successfully progress to implementation are as follows:

1. Should clearly demonstrate how proposed activities will support reducing deforestation rates.
2. Must outline how local communities will economically benefit from the interventions proposed ahead of time.
3. Must clearly demonstrate that local communities have been core in the intervention design process.
4. Should have clear positive evidence that local leaders have been appraised for positive behavioural traits.
5. Should set out how beneficiaries will secure ownership of activities through the proposed timeframe of the intervention.
6. Should provide a robust exit strategy that ensures the intervention can succeed once the funding period ends.
7. Should have a deliberate approach that sets the conditions for the activity to be replicable, or for systems to be in place that are internally sustainable.

Performance Monitoring: To guarantee the effectiveness of any intervention during its implementation phase, ongoing monitoring will be carried out by partners, with the MEL provider assuring and augmenting the reporting from tier 1 suppliers through their own primary data collection. This will track both economic and deforestation performance, safeguarding beneficiaries from negative economic impacts, whilst ensuring activities are meeting the objectives of the programme. This will also enable rapid learning to be shared with other interventions under design, whilst enabling partners to quickly identify and act on risks. Reporting checkpoints will ensure discussion and decision making amongst partners, with FCDO oversight.

Evaluation & Learning: During and after each intervention, the MEL component will capture results and actionable learning which will contribute towards the CBFA evidence offer, enabling learning within and beyond the programme, and to the programme-level evaluation.

Component 2 will see application of a similar set of criteria in relation to approval of proposals. Depth of performance monitoring by the MEL component will be assessed and applied on a case-by-case basis dependent on the capacity of the implementing partner, e.g., should a partner have robust M&E capabilities and reporting, the CBFA MEL component will take a less interventionalist approach. This dynamic will be established in parallel to commercial contracting.

### iii. Component 1 – Community Forests

Component 1 will see a novel approach to the design and implementation of grassroots forest interventions, building on a previous very successful FCDO forests & local communities programme delivered across Congo Basin, entitled: Improving Livelihoods and Land Use in Congo Basin Forests (ILLUCBF also known as CoNGOs). Much of the work expected in component 1 will be based on the approaches taken within ILLUCBF, which delivered three principal components:

NGO’s Collaborating for Equitable and Sustainable Community Livelihoods in Congo Basin Forests (CoNGOs) implemented by a consortium of NGO’s led by IIED (£3.43m): Supported communities to secure or initiate securing some 90,000ha of forest lands, supported business models that started yielding both financial and social benefits and strongly influenced legal reform processes across the Congo Basin (Cameroon, Central Africa Republic, DRC, Gabon and Republic of Congo).

The DRC Community Forests Project implemented by a Rainforest UK (RFUK) led consortium (£5.64m): Supported the establishment of 6 community forests, starting from a context of extremely low capacity and knowledge of the approach, and fed into the development of national guidance on a Simple Management Plan for CFs which was implemented in one CF.

Financing Sustainable Community Forest Enterprises (CFE) in Cameroon (DRYAD) led by ICRAF (£5.7m): Demonstrated innovative performance-based finance to CFE’s in Cameroon to ready them for private investments.

At the conclusion of the programme, there had been an intention to include a similar set of interventions in the new, flagship Africa Regional Climate and Nature (ARCAN) programme within FCDO Africa Directorate’s portfolio. However, this was subsequently not pursued, in part as it was judged too complex within a programme with a broad, pan-African scope, already covering multiple climate-related issues. The introduction of this Congo Basin-specific programme, therefore, is an opportunity to build on past efforts.

While the current, large UK programmes in the region work in adjacent areas, including national policy and governance (FGMC), private sector development (IFSLU), land governance (GLG) and biodiversity (BLF), there remains a gap when with respect to engagement at the grassroots community level, which this component of CBFA is intended to fill. This community level engagement piece is consistent with the former work under ILLUCBF, which CBFA will adapt for the current context and is envisioned to focus on direct community support for action, improved governance, securing land rights, accessing sustainable finance and alternative or value-added livelihoods opportunities and capacity development.

Since the design of the ILLUCBF programme, there have been a number of significant developments within the natural resource landscape. There has been increased interest at the international level in the benefits that natural capital, and especially forests, provide to local, national and global systems. There has also been examination of how these might best be captured both within financial and economic systems and for the benefit of those living in and managing the forests. Where applicable and identified as appropriate through the co-design process, these novel interventions, such as Payments for Ecosystem Services (PES), results-based carbon payments, and Voluntary Carbon Markets (VCMs) may be introduced and trialled.

Targeted Barriers and Challenges

The ILLUCBF programme was a successful intervention in a difficult context. The programme’s PCR recorded an overall score of A+. Below are two extracts from the PCR summarising the conclusions of independent evaluations:

1. The RFUK evaluation results indicate that there have been significant positive impacts on sustainable forest use, community solidarity, local income-generating activities, and community-based development initiatives. Previously marginalised community members, such as women and indigenous populations are both integrated and empowered. The project influenced the National Strategy on Community Forestry and Operational Guide.
2. The CoNGO’s evaluation found that the project overachieved against impact, outcome and outputs, supporting communities to secure or initiate securing some 90,000ha of forest lands and demonstrating two major innovations that may be duplicated across the region: The allocation of CF within a forest concession in CAR and a business model that started yielding both financial and social benefits in DRC and Cameroon. The project developed strong collaboration between NGOs across the region, strongly influenced legal reform processes in CAR, DRC and RoC, and contributed to the elaboration of the Brazzaville Roadmap which sets out priority actions needed to strengthen and scale-up community forests in the region.

There were a number of lessons learned identified in the PCR, which can inform this component of the CBFA. The full PCR findings are provided in Annex A but the summary points are:

- The importance of building strong coalitions of partners with strong leadership and a shared collective vision.
- Strong coordination and communication between component leads, aligned with the overarching programme vision and logframe, to facilitate capturing of Synergies between the components
- The importance of improving progress towards gender equality and inclusion of indigenous groups.
- The need to establish and demonstrate Value for money metrics from the outset.
- The need to support communities and enterprises in best practice, and to access new markets and finance to achieve scale and sustainability.
- The importance of consistent and useable Monitoring, Evaluation and Learning.
- The need to integrate CF interventions into broader forest & land use planning / landscape approaches.
- The importance of taking a multi-pronged approach.

Beyond ILLUCBF lessons learnt, CBFA scoping exercises with stakeholders across the region identified the following direct and indirect concerns surrounding community-focused interventions:

1. Short-termism through programmes generally lasting 3-5 years and lacking legacy or, in some cases, making things worse.
2. Lack of co-design of programmes, which are implemented through dictating solutions among communities and their government representatives.
3. Poor performance by multilateral institutions because funding does not reach the ground via disbursement mechanisms.
4. Insufficient national and local capacity, causing unsustainable reliance on external Technical Assistance of varying quality and impact and avoidance of building local skill bases.
5. Poor long-term support, limiting the availability of continued interventions beyond the programme cycle.
6. Monitoring & Evaluation is not emphasised, leading to the implementation of ineffective methodologies causing post-programme failures.
7. Ineffective training methods caused by delivery of inappropriate technical assistance.
8. Limited research causes decisions to be made based on insufficient evidence.
9. Lack of knowledge-management systems causes incoherent understanding of what is being accomplished and what practices should be further supported, modified, or abandoned.
10. Insufficient autonomy of local communities and NGO partners cannot sustain programming legacy once funded activity ceases.
11. Lack of community voice avoiding inclusive representation and misunderstanding of local needs and aspirations.
12. Communities are powerless and unaware of how to affect decision-making. For example, private sector logging and mining impossible deleteriously affecting communities cannot be stopped, even if illegal.

Intervention Strategy, Illustrative Activities and Expected Outputs

1. It is therefore proposed that CBFA undertakes to reengage with the themes of the ILLUCBF programme, including seeking to support communities to secure forest lands and to organise and establish themselves officially as required under the different national jurisdictions in the Congo Basin.
2. The programme will support communities and their representatives to derive financial and social benefit from the resulting formal recognition. In comparison to ILLUCBF, there should be a shift in emphasis from attaining devolved forest rights for communities to operationalising forest rights at community level, achieving value for communities while incentivising environmentally responsible stewardship of the forest. During implementation, the programme and its partners should take into account the ILLUCBF PCR lessons.

It is intended that this component be predominantly carried out by downstream implementing partners under the coordination of a lead partner, with which FCDO anticipates holding a service contract. This will be covered in more detail in the Commercial and Management Cases. The component will begin with an inception phase, during which political economy analysis, stocktake of the varying contexts and analysis of needs will be undertaken. During the phase, the details of activities to be carried out will be worked through in detail. However, we can identify illustrative examples and outputs as including those listed below. It is important to emphasise that the process of running the inception phase, which is anticipated to involve extensive co-design efforts with local stakeholders, will deliver an important, if less tangible, part of what is achieved under Component 1, as well as Component 2.

A comprehensive co-design process involving regional stakeholders to develop a suitable set of interventions with strong local buy-in will inform a diverse suite of activities. These could include, but are not limited to:

- Comprehensive co-design process involving regional stakeholders to develop a suitable set of interventions with strong local buy-in.
- Assessment of local level governance and related institutions to understand failures and challenges to be factored into tailored interventions.
- Local partners and trainers of trainers delivering capacity building to community groups, CFE’s and local officials in a wide range of technical, business, governance and advocacy aspects.
- Participatory livelihoods assessment and planning to understand dependencies and identify where interventions are both most needed and most effective from a longevity perspective.
- Supporting community forestry enterprises with training and access to finance to support diversification, formalisation of access to land & user rights, and improved livelihood impacts.
- Supporting communities directly with processes to secure formally recognised CF titles for communities, including simplified Sustainable Management Plans (SMPs), and local cooperatives.
- The incorporation and integration of relevant and appropriate traditional knowledge into protected area management plans, and into livelihoods systems generally, e.g. churches and schools.
- Improved productivity and efficiencies from existing and planned activities, e.g., agriculture, agroforestry, charcoal.
- Providing communities with technical, governance and business support, and reported performance data through a digital smartphone-based field monitoring system as a condition for continued financing.
- Contributing technical inputs and supporting civil society in making recommendations to legal and forest governance reform processes, by developing advocacy platforms, using lessons learnt from pilots, supporting drafting of laws, submitting position papers and recommendations, sitting on official governance structures roundtables, organising workshops etc.
- Design of potential pilot payment schemes (PES and/or VCM) which could benefit communities working as stewards of the forest.
- Assessment and options analysis for sub-national/local value chains to deliver i) improved sustainability and productivity, ii) reduced pressure on forests, iii) greater added value/income generating opportunities.

Outputs and Outcomes:

- 342,041ha avoided deforestation and forest disturbance collectively.
- 100 Community Forests supported.
- 50 Community Forests economically profitable or viable.
- 100,000 people supported to improve forest tenure rights or engaged in CF.
- At least 50 local organisations able to support CF, advocate for policies, and demonstrate strong organisational financial capability.

### iv. Component 2 – FCDO Partners Facility

Given the need for a comprehensive and meaningful co-design phase within Component 1, and that this will take time, Component 2 represents new lines of complementary effort giving the programme opportunity to deliver results more quickly and the flexibility to pursue innovative approaches bilaterally.

The establishment of an FCDO Partners Facility will allow CBFA to respond to proposals from prospective partners across the region with a strong track record, providing the programme with flexibility and adaptability and facilitating quicker action and results that align with the Theory of Change, with a focus on the validation of specified outcomes and the impact statement.

FCDO staff are cognisant of past and existing projects, have a good understanding of previous and current actors in the region and are well placed to ascertain the reputations, performance and fit of potential partners with CBFA. Indeed, requests for support, to build on, expand and/or transfer past successes are regularly received.

FCDO has already received a number of promising proposals from actors planning on delivering or already doing so across the region. Both these and new proposals submitted during the programme period will be formally appraised using similar criteria to those used to assess interventions co-designed in component 1:

- Should clearly demonstrate how proposed activities will support reducing deforestation rates.
- Must have civil society organisations and/or national non-government organisations included in the implementation plan as delivery partners.
- Must clearly demonstrate that local communities will economically benefit from the interventions proposed.
- Must provide a robust exit strategy that ensures activities can succeed beyond the funding period.
- Should have a deliberate approach that sets the conditions for the activity to be replicable, or for systems to be in place that are internally sustainable.

An example of best practice within the region comprises of a multidecadal suite of landscape interventions in Central DRC, working with the most vulnerable communities and households in and around the Yangambi Reserve and bordering frontier forests along the Congo River, with the aim to reduce pressure on, clearance of and expansion into the forest through successfully:

1. Driving long-term behaviour change within communities through work with local institutions and governance systems.
2. Increasing agricultural productivity to reduce need for expansionist land utilisation approaches.
3. Promoting sustainable practices to enable alternative livelihoods without losing forest cover.
4. Increasing household income through inclusive consultations and utilisation of applied research and best practice to deliver improved opportunities.
5. Diversifying livelihoods strategies to empower local communities in effective development and financial resilience.
6. Increasing the supply of fuel wood from agroforestry and fast-growing tree species which are sustainably managed.
7. Promoting comprehensive supply-chain efficiencies to ensure effectiveness at every stage.

Landscape level interventions, i.e. taking a ‘bigger picture’ approach and considering the heterogeneity of a selected geography, have advantages in being able to address a wide area and multiple, interacting factors contributing to degradation and pressure on natural resources. Operating at the regional or landscape level has potential to generate and build up sustainable gains, but tends to be slow burn, often seeing an acceleration in progress and results over time. The ability to potentially support such approaches would both provide CBFA with a means to enable the continuation of funding to such projects, thus preventing a funding gap, building on existing progress and providing stability and longer-term sustainability of results.

A further example of pioneering best practice resulting in significant positive impacts for the region lies in UK-led policy and action influencing research in the region over the past decade. Key successes achieve here include:

Supporting Gabon in the quantification of its forest carbon sequestration capacities, ultimately resulting in the Gabonese government successfully certifying 90 million tonnes of carbon credits for sale in 2022 – the first ever on the African continent.

Classification and quantification of the largest tropical peatlands on earth spanning the DRC and RoC, resulting in high profile commentary and action from around the world, providing the region with the natural capital to ensure concerns and needs are consistently listened to on the international stage. The evidence from this work also underpinned successful high-level lobbying and pushback from international advocates in response to DRCs oil and gas auctioning, which saw some blocs overlap with this peatlands complex.

Championing of regional capacity building through academic institutions to drive knowledge retention and action within the Congo Basin as opposed to the heavy historical reliance on funds and resourcing from Western academia. Salient knowledge from research forms a key part of the cycle which informs national policymaking and the resulting local level action, and pushing for this to be led and autonomised in-country is key to an enduring legacy which demonstrates self-sufficiency.

Identifying how different ecological systems are responding to climate change, enabling trends to be established, raised as a concern, and subsequently actioned. This includes discovering the significant decline in fruit production observed across the region due to increased drought and water stress, allowing targeted interventions to consider practically what this should mean for their focus and thematic areas.

The limited understanding of the Congo Basin forests, and their associated ecological systems, is a major constraint on the formulation of policy and the design of interventions best able to address underlying causes of degradation, respond to climate change and take into account the complex interrelationships between different elements of the regions biosphere systems.

Within FCDO, this component also accommodates the ability to bid through the FCDO Global Land Governance Programme Land Facility component, a central offer which will become operational early 2024., This is designed as a flexible offer, responsive and adaptive to country-specific political opportunities and context, providing technical support for partner countries to develop and implement land governance reforms with robust land policies, legislation and administrative systems by:

Enhancing political incentives to implement sustained reforms, including through informed political economy analysis to enhance the business case for targeted interventions and fostering the network and relationships to build political consensus.

Increasing government capacity to plan, manage and implement systematic and priority land policy and reforms at national level, through technical assistance and improvements of the processes governing land transactions for investment.

Facilitating coordination across government and development partners for accelerated change, including multilateral and bilateral interventions.

Enhancing forest community tenure rights, working with regional and national stakeholders to ensure this is embedded and addressed through policy reforms, implementation and more inclusive reform processes.

An approach that includes leveraging this central offer will enable CBFA to plug directly into relevant expertise from FCDO partners, deliver certain priorities faster and support FCDO institutional coherence. This will be covered in more detail as part of the Management Case.

Land Facility support complements Component 1 through addressing systemic land and forest governance issues at national and regional levels, facilitating enabling structures for coordination, consultation, and collaboration with wider stakeholders, including forest community stakeholders, for more effective implementation.

Targeted Barriers and Challenges

The practicalities of partner interventions ranging from research to action within the Congo Basin forests pose numerous challenges, such as accessibility – both due to the physical geography and the political economy. Control of access by vested interests, overlapping uses of land, and the absence of functioning forest & land use planning processes render secure experimental control uncertain. There is a lack of coherence across those government agencies that issue permits, and inconsistent application of legal process in some contexts. These challenges are set out with respect to component 1 and remain valid for this component.

Across the components there will be challenges related to finding reliable and capable partners within the region. These may present as more acute in the context of a demand-led component that relies on external proposals. This can be difficult, making paramount the need for a rigorous process to ascertain potential partners with capacity, strong relationships and a proven track record for delivery in complex and challenging environments. Prospective proposals from such partners will also need to be assessed for thematic and timescale fit with the programme and be clearly aligning with and supporting the programme’s objectives and delivering against appropriate indicators.

Partners will also need to be adaptable and flexible, however, as the Congo Basin region is both complex and dynamic: for example, climate change is significantly affecting rainfall patterns and thus requiring the adaptation of the traditional timing of planting and land management operations. Local and national social and political systems also have the potential to change significantly over the programme timeframe. Partners operations and delivery approaches will need to be designed to be able to adapt to changing conditions and environment.

Despite the importance of Central Africa’s forests to people and planet, research into and understanding of the Congo Basin’s forests has been and is limited. Capacity remains relatively weak both in terms of the number of qualified staff and of scientific infrastructure and institutions. There has been limited (although successful when undertaken) support for long-term funding for comprehensive research collaboration.

Intervention Strategy, Illustrative Activities and Expected Outputs

In keeping with the Theory of Change of CBFA, the programme will seek to engage directly with the intervention strategy in order to generate lessons and drive visible impact, but will focus energy on creating the conditions for a more systemic change.

As with Component 1, Component 2 is intended to programme in response to feedback, particularly critical feedback, across the region. Component 2 will support interventions with strong local buy-in and commitment and scale up those found to be successful where appropriate.

Utilisation of the Land Facility and approval of support under the Partners Facility will need to be led by local stakeholders as relevant – calling down TA, capacity strengthening and analysis and building on and adapting proven successful work by strong and trusted partners, as requested and required in response to identified and specified need.

Expected Activities:

- Political Economy Analysis to inform targeting of interventions.
- Network and relationship building events and initiatives to improve political consensus and coordination between local, national, regional and international actors.
- Technical assistance and capacity building for relevant stakeholders at the national and regional level to improve land tenure and land governance systems and procedures.
- Continuation, up-scaling, and transferring of best practice projects by trusted partners, including the piloting of adaptive management and innovative solutions.
- Capacity building of scientific institutions and strengthening of research infrastructure.

Outputs and Outcomes:
- 342,041ha avoided deforestation and forest disturbance collectively (in addition to comp. 1)
- At least 100,000 individuals directly benefiting from capacity building.
- At least 20 local organisations and associates able to support CF, advocate for policies, and demonstrate strong organisational financial capacity.
- At least 10 local processes strengthened to ensure participation of CSOs and recognition of CF approaches.
- 10m ha forest included in research studies.
- 20 research outputs delivered and informing policy and decision making.

### v. Component 3 – Central African Forest Initiative

Component 3 builds on existing engagement by the FCDO Africa Regional Climate and Nature (ARCAN) Programme to support the leading regional multilateral platform for engaging specifically with the Congo Basin Forests, the Central African Forest Initiative (CAFI). At a base level, CBFA will make core contributions to the CAFI Multi-Donor Trust Fund which provides direct investments on the ground and a political negotiation platform that aims to drive high-level policy dialogue. Beyond this, CBFA will consider financing targeted interventions for delivery if possible, during the intended funding phase commencing from 2026 onwards.

Complementary to funding, and enabling, reform and rural development programs, studies, and preparatory grants, CAFI negotiates and encourages high-level commitments that place forests at the centre of countries' development policies. The most recent examples include the DRC commitment, endorsed by DRC President Tshisekedi at COP26 in Glasgow in November 2021, to stabilize forest cover loss at its 2016-2018 levels and restore 30 million hectares of land; and Gabon's commitments to avoid or cap the conversion of forest with high carbon stocks and high conservation value.

CAFI works with six Central African partner countries: Cameroon, Central African Republic, Republic of Congo, the Democratic Republic of the Congo, Equatorial Guinea, and Gabon, with over 30 Ministries engaged and a coalition of donors: Belgium, the European Union, France, Germany, the Netherlands, Norway, South Korea, Sweden, and the United Kingdom.

Targeted Barriers and Challenges

The UK has been a Board member of CAFI since its establishment in 2015. FCDO made the first UK financial contribution to CAFI in 2022, before the UK took on the Chair of the Executive Board in 2023 for two years. In its early years of set up and initial implementation, CAFI has faced a number of delivery challenges. The UK is working with other donors and the CAFI secretariat to improve delivery through our period as Chair. Any future core contribution to CAFI by CBFA should consider current delivery challenges.

Three of these challenges are of particular relevance to the potential engagement of CBFA with CAFI:

Difficulties encountered by CAFI programmes to disburse funding quickly, and to reach communities on the ground.

Higher costs and perceived legitimacy of working through large UN and international cooperation agencies. Host governments have encouraged CAFI to work through local or regionally governed organisations, but this has been difficult due to UN rules and access requirements such as strong levels of fiduciary management and social and environmental safeguards.

As a multi partner trust fund, agreement must be reached between all donors, and between the CAFI board and partner governments before programmes can be implemented, which can lead to delays in approving programs.

Intervention Strategy, Illustrative Activities and Expected Outputs

At country level, CAFI enters phased dialogues that ensure the mainstreaming of climate and forestry objectives into sectoral and development plans. This catalyses a long-term process necessary for the changes required. The below constitute the routine approach taken, which would be complemented by aligning separate bilateral funding:

Partner countries develop their national investment frameworks addressing all drivers of deforestation and forest degradation according to their priorities.

Following a review of the national investment framework and discussions with the partner country, the CAFI Executive Board (EB) agrees to support certain policy reforms and large-scale programmes.

Through a Letter of Intent (e.g. with the DRC in 2016 and in 2021, Gabon and the Republic of Congo) signed between the CAFI EB and by Ministers with coordination mandates (e.g. Minister of Finance) or Heads of state or government, agree on time-bound targets in policy reform and programmatic performance and the corresponding financial support by CAFI.

CAFI and partner countries agree on a programming framework and then partner countries through implementing organisations develop and implement programs (sectoral and landscape/jurisdictional) to achieve the milestones in the Letter of Intent and jointly monitor progress with the EB.

Throughout the process, CAFI offers a framework that allows for a combination of field investments and high-level policy dialogue. Multi-donor coordination strengthens the convening power of the Initiative. CAFI is an opportunity to drive systemic change through whole-of-government approach and donor coordination. Through CAFI, donor countries pool their financial resources, coordinate their policy dialogue and align their bilateral funding and thus multiply the impact of their individual contributions.

There is also a precedent for individual donors providing targeted contributions or co-financing to pursue priority developmental objectives, consistent with the mandate of CAFI. However, this funding can only be spent on agreement with the board and partner countries, with additional work likely needed to ensure earmarked funds are delivered. CBFA will be seek to achieve this, alongside providing core funding where this has not been possible.

The intervention strategy of CBFA with respect to CAFI will be to provide funding that ultimately supports other Components of the programme, where these are consistent with the ongoing policy dialogue with partner governments. In service of achieving milestones in CAFI-partner country LoIs, and in delivering on shared priorities of the UK and partner countries, these could include for example:

1. Security of land tenure for IPLCs (Component 1 & 2)
2. Community-level organisation and land management (Component 1 & 2)
3. Community-level economic valorisation of forest rights (Component 1 & 2)
4. Local implementation of financial innovations (Component 1 & 2)
5. Payments for Ecosystem Services (Component 1 & 2)
6. Regional knowledge and policy work & action-oriented research (Components 2 & 4)
7. Coordination of knowledge and policy work (Component 4)

Whilst the primary function of CBFA funding for CAFI is to supplement UK core contributions, the delivery of programming by CAFI across the Congo Basin provides clear opportunities for synergies and complementarity with this programme. A key connection between both entities will be on knowledge sharing, learning, and value add. Experience and approaches by CAFI in the implementation of the above activities would be considered by CBFA, including on alignment and avoidance of duplication. Where opportunities exist to collaborate, particularly on higher risk activities such as PES, CBFA will seek to do so. The programme retains the option to ringfence funding for targeted interventions should they manifest during the proposed funding period from 2026 onwards.

### vi. Component 4 – Monitoring, Evaluation & Learning

Component 4 will facilitate a critical underpinning quality assurance mechanism for component 1 & 2, whilst developing evidence and learning for use within and beyond CBFA. As previously outlined in the Intervention Approach & Methodology, the MEL component will play a pivotal role in independently assessing ex-ante analyses, appraising co-designed proposals, verifying ongoing monitoring of interventions to safeguard economic and deforestation objectives, and developing high quality evaluations of activity performance to generate important evidence that will feed back into programme activities. These responsibilities will carried out in close consort with delivery partners within component 1 & 2.

Beyond this, and in combination with the delivery components, the MEL piece will assist the programme to retain a regional character through effective knowledge sharing between interventions during and after delivery. This will enable a proactive and responsive approach to emerging best practice within the programme, and ensure early stage mitigation of interventional failures. It will also enable better coordination between various componentry of CBFA, whilst building a strong evidence base for future UK and broader donor programming across the region.

Targeted Barriers and Challenges

Access to areas where interventions would be considered can be a major challenge across the region. Forest frontiers within the Congo Basin forests are generally serviced by long distance road infrastructure, or in the predominant case of DRC – the Congo River. Air access is severely limited and restricted. A major complaint from local communities in recent scoping has been the lack of effective monitoring and follow-up with interventions, and access contributes as a major barrier towards successful delivery of this.

Considerable criticism resounds within the region of donor-led efforts to deliver lasting change through project work. This includes lack of coordination and co-design, but also specifically a lack of monitoring and evaluation emphasis, leading to mistakes being repeated. Moreover, value chain problems arise from a poor understanding of product potential and limited market access. Limited research causes decisions to be made based on insufficient evidence. Lack of knowledge-management systems causes an incoherent understanding of what is being accomplished and what practices should be further supported, modified, or abandoned.

Intervention Strategy, Illustrative Activities and Expected Outputs

To achieve successful delivery of innovative and traditional interventions within this programme and in future initiatives, there is a significant need for detailed and agile MEL to better inform programme design and guide policy decision-making. To achieve this, component 4 will seek to support and drive:

1. Independent monitoring and evaluation of suppliers and activities across each component throughout inception and implementation, particularly during the co-design and implementation phases of component 1, and all pre-designed activities delivered through component 2.
2. Facilitation of agile learning within and between components throughout the programme lifespan. Ensuring that solutions identified through activities are considered and transposed elsewhere where appropriate.
3. Strong evaluation to build a strengthened evidence base identifying which intervention approaches are successful and which have failed, and why, to enable self-learning within the programme whilst providing foundations for future initiatives.
4. Ensuring a holistic and robust approach is carried out by the programme with regards to delivery of objectives, e.g., monitoring of GESI safeguarding.

Part of Component 4’s objective is to set up MEL systems working regionally, nationally and locally; establishing a community of practice intended as a programme legacy. Where possible and appropriate, solutions co-designed and prepared for implementation in the inception phase of Component 1, coupled with learning from components 2 & 3, will ensure interventions speak to each other, and are supported by partners while delineating between both to ensure delivery and oversight are locally owned.

The MEL component will not directly deliver reporting. This will be carried out by deliver partners. This component will independently assess and validate these reports to ensure transparency and effectiveness

A MEL system nested at regional, national, and local levels will involve capacity building tailored for different groups, including implementing CSOs and NGOs, businesses, government agencies, and academic partners.

Through this, CBFA will develop an evidence base to pilot and scale innovative activities through its other components across locally and internationally led interventions, assessing and adapting these according to what works and what does not so that the programme will be guided by a strengthened understanding of:

1. The reason(s) a particular intervention succeeds or fails (and where possible, using lessons from FCDO and other donors gleaned from the regional learning).
2. Where and why to scale success, including understanding how various contexts augment effectiveness.
3. The reason(s) an approach works in one country or sub-national geography and not others, and the implications for further programme work.

Projects under the programme will also baseline existing local group capacity and track their progress and development. Groups will include sector department & district staff, extension services, NGOs, and businesses. The programme will use this information to direct training of trainer support, create trained pools of local “champions” to scale project successes and form a legacy beyond the funding period.

Knowledge and information networking will be hosted at the programme level, potentially supported by the MEL provider under contract. Component 4 will be responsible for delivering outputs that will include:

1. Establishing protocols to assure programme analysis, monitoring and reporting, during inception and implementation, working with different Components of the programme on delivery pathways.
2. Capturing learning across the entire programme, including regional donors’ interactions, national working group experience, and local implementation partners and projects.
3. Designing and implementing a programme-level evaluation, which draws on the ongoing monitoring and learning.
4. Establishing programme website, Facebook, Twitter, and Instagram feeds for information capture, story sharing, highlighting champions and programme participants, and information dissemination.
5. As the programme progresses, implementing a structured learning programme through a Community of Practice, bringing together practitioners virtually and physically across the four countries for academic and practical learning exchanges designed to last beyond CBFA’s programme cycle.
6. Establishing rounds of regional, national, and local Shared Learning Dialogue events aimed at building stakeholder capacity throughout the programme and its partners.
7. Dissemination of information to partners through channels and language that is useful and accessible.
8. Improving peer networks to exchange and learn on behalf of programme partners.
9. Publishing findings in internationally accessible outlets to promote the benefits of FCDO’s CBFA and encourage replication of key successes.

It is anticipated that CBFAs first year will highlight challenges and barriers most relevant to implementation across numerous contexts. Monitoring, evaluation, and learning will be critical features of an adaptable approach to addressing risk and setbacks. The programme will have to adapt to operational challenges as it proceeds.

### vii. Theory of Change

The Theory of Change for the Congo Basin Forest Action Programme is presented in figure 5 below, which includes the assumptions used in forming it, building on the evidence detailed throughout the strategic and appraisal cases. Central to the programme is the assumption that the global benefits of securing Congo Basin forests are contingent upon support for the programme from the countries in the basin, and forest communities; this support will only be forthcoming if the benefits of the programme for these countries and communities outweigh the benefits of that accrue from activities that destroy the forests; finding the best way to transfer and safeguard the required benefits will be demanding given that the evidence base remains thin relative to other areas of intervention undertaken by FCDO. This is due to the:

1. Relative novelty of some of the intervention types proposed, including to co-design the approach, alongside support for PES and VCMs.
2. High level of context specificity of many of the interventions proposed, particularly with regard to community forests and composition and norms among rural communities.
3. Challenges of operating and producing good data and robust analysis in the Congo Basin, which for a number of reasons discussed in the Strategic Case presents a difficult operating environment.

It is intended that during the inception phase there will be an elaboration of the Theory of Change, during which it will be re-examined in the context of ongoing engagement, along with closer scrutiny of assumptions. This fuller analysis of the evidence needs will help the programme MEL component to prioritise building the areas with the weakest existing evidence.

The evidence for the ToC assumptions varies but is informed by just transition principles. The limited availability of data means the programme will be expected to actively assess the validity or otherwise of the assumptions and pull back from actions that rely on assumptions that prove unfounded. Safeguarding of programme value and benefits is built into the design and underpinned by focusing on people, lives and livelihoods in an inclusive manner, as agreed by countries supporting a “Just Transition” at COP28.
[note] UNFCCC (2023) Summary of Climate Action at COP 28. https://unfccc.int/sites/default/files/resource/Summary_GCA_COP28.pdf

Figure 4 - CBFA Theory of Change
Table 8 - Theory of Change Assumptions Evidence
Assumption	Strength of Evidence
Impact / Outcome
Programme success can be extended from one locale to another	The concept here is that successful interventions can be expanded and/or transferred to new areas through acting as a template and having demonstrated results. / There is some evidence of successful scaling up / transfer of pilot interventions related to institutional or market reforms and whilst there is a wealth of literature highlighting major issues (i.e., considering differences between or within physical, socio-economic, cultural and political systems of the locations) there is very little evidence of successful practical scaling up / transfer of NRM pilots. / CBFA in part seeks to build on the successes of the ILLUCBF programme and scaling up / transfer is a key recommendation of the project’s independent evaluation
Deforestation issues will not only be displaced geographically	Leakage is when a project or programme designed to protect forests leads to a shift of deforestation to another area. There are numerous approaches used to try to reduce or prevent this, but they require regulatory authority, enforcement, and standardised incentives (for not deforesting) across whole regions and will therefore be outside the control of the project. / As the dominant driver of forest disturbance within the region, and the focus of the project, is small-scale agricultural expansion into the forest, CBFA participants are less likely to undertake forest disturbance activity in other areas due to limitations on access and community boundaries and resources. Whilst it is highly likely that deforestation will continue, direct leakage from areas under CBFA is less likely.
Trust between partners will support sustainable development	One of the findings from the regional stakeholder consultations informing the design of CBFA was a lack of trust between national, regional and international partners. / The independent evaluation of the ILLUCBF programme found strong evidence of improved trust and co-ordination and lists these as key sustainable legacies of the project. Whilst there seems little doubt that increased trust is likely to be beneficial in a range of ways there is little if any direct evidence that sustainable development would be a direct outcome.
More co-design leads to stronger CB ownership	There is evidence that meaningful engagement of community stakeholders address needs better and can achieve improved results than just a top-down approach / Formal co-design approaches have been viewed increasingly positively in recent years but the literature and studies investigating it are dominated by sectors other than natural resources, in particular health, and/ or are geographically focused on regions other than the Congo Basin. The only Nature Based Solutions study viewed concerns green spaces around cities in the global north. One of the main findings of the regional stakeholder consultations informing the design of CBFA, however, was a wide-spread and strong dissatisfaction with a lack of meaningful co-design in other programmes. / Whilst there is very little formal evidence for the assumption there is also very little evidence countering it as there is a general lack of evidence in relation to the co-design of natural resources interventions in the Congo Basin.
Intermediate Outcome
Ownership at local level will improve stewardship	The rationale for this assumption is that increasing local buy-in and ownership of project activities will engender greater commitment by participating communities to project aims – as these will be aligned with their own priorities – and will result in improved stewardship of the forest resources, including a degree of formal and informal community-based policing and enforcement. / There is good evidence of community owned forestry projects reducing deforestation in other countries and regions / Whilst the independent evaluation of the ILLUCBF programme, on which CBFA seeks to build found that it had exceeded its targets for securing land use rights, overall evidence from the Congo Basin is weak and therefore should be considered a priority for MEL.
National and regional policy coherence coordination will strengthen forest protection	Whilst direct evidence for the assumption is weak there is good evidence that incoherence between sectoral land-based policies is detrimental to forest protection.
Improved knowledge products will be acted upon by policymakers	Evidence for this is weak but can be improved by ensuring that knowledge products are tailored to meet decision makers’ needs, provide useable information and are made consciously accessible.
Output
Improved livelihoods options will reduce pressure on forest resource	There is good evidence that community forestry has had a proven impact on reducing deforestation and improving livelihoods across a range of countries. / There is good evidence, in other African contexts, that improved living standards can both reduce forest degradation and alleviate poverty. / There is medium to strong evidence globally that improved agricultural productivity yields a wide range of benefits, including reduced deforestation and forest degradation. / Within the region, however, evidence is weaker although many programmes advocate such an approach and it is a key recommendation of the ILLUCBF programme evaluation. / A key factor, however, is the disconnect between public good and private incentive. A recent study within the Congo Basin found that financial returns to communities was only assessed in a minority of the studied community forestry projects and that, in DRC and Cameroon, NBS projects were unlikely to develop, “unless local people are guaranteed that it will contribute to improving their livelihoods, notably their financial and physical capital”.
Financial innovations can succeed and scale in the Congo Basin	Given the innovative nature of this component it is not surprising that the evidence base is weak. / CAFI are undertaking work in the field of PES but the main evidence for successful PES comes from Latin America, and it has no record in the Congo Basin. / The issue noted above concerning the realisation of tangible benefits for communities for actions providing a public good, however, renders attempting trialling such or a similar innovation of high importance. The conditions necessary for successful financial innovation are likely to be highly variable across the region and will require diligent assessment and monitoring in each instance.
Political, institutional and economic conditions remain conducive	There is good evidence that political and institutional conditions will remain conducive. All Congo Basin Forest countries are signatories to numerous international commitments for reducing deforestation, REDD+ support and multiple other programmes and funding are present and the formal international and regional narrative supports continued efforts to which the CBFA seeks to contribute. / Local level political and institutional support is intended to be further strengthened through the co-design process. / Evidence for continuing conducive economic conditions is less strong, with financial incentives often working against forest protection.
Economic benefits will precede phase down of extractive livelihoods.	Slash and burn agriculture and charcoal production have both been modelled within the CBFA business case and demonstrate a hypothetical initial net livelihoods loss when scaled down against the model benefits found from Non-Timber Forest Products. / CBFA will ensure economic gains are prioritised throughout any intervention through effective safeguarding measures, and not allow any negative impacts to be passed onto intended beneficiaries at any stage.
[note] AIM 4 Resilience Business Case; FGMC. Internal UK Government Document.
[note] Nkuintchua, T., Enongene, K. and Mbzibain, A. (2019) Independent Evaluation Of the project - CoNGOs: NGOs collaborating for equitable and sustainable community livelihoods in Congo Basin forests. IIED. https://www.iied.org/sites/default/files/pdfs/migrate/13614IIED.pdf
[note] Nkuintchua, T., Enongene, K. and Mbzibain, A. (2019) Independent Evaluation Of the project - CoNGOs: NGOs collaborating for equitable and sustainable community livelihoods in Congo Basin forests. IIED. https://www.iied.org/sites/default/files/pdfs/migrate/13614IIED.pdf
[note] AIM 4 Resilience business case Annex 1. Internal UK Government Document.
[note] Clever Cities (2021). Co-design of Nature Based Solutions with Citizens: Learnings from a Sector Literature Review. https://clevercities.eu/fileadmin/user_upload/Resources/Co-design_NBS_Learnings_from_a_sector_literature_review.pdf
[note] Mayers, J. (2014) Social justice in forests: gains made and tactics that work. A report from the Forest Governance Learning Group. http://pubs.iied.org/13574IIED.html
[note] Pirker, J & Carodenuto, S (2021) Current State, Barriers and Perspectives for REDD+ in the Congo Basin. Congo Basin Forest Partnership Report. https://pfbc-cbfp.org/actualites-partenaires/Package-%C3%A9tudes-PFBC.html?file=files/docs/key_docs/Publications%20du%20PFBC/2021_CBFP_REDD%2B%20in%20the%20Congo%20Basin_Report.pdf
[note] Mayers, J. (2014) Social justice in forests: gains made and tactics that work. A report from the Forest Governance Learning Group. http://pubs.iied.org/13574IIED.html
[note] Defries, R. et al. (2021) Improved Household Living Standards can Restore Dry Tropical Forests. Biotropica. DOI: https://10.1111/btp.12978
[note] Smith et al. (2019). Which practices co-deliver food security, climate change mitigation and adaptation, and combat land-degradation and desertification? Chapter 6 of the IPCC Special Report on climate change, desertification, land degradation, sustainable land management, food security and greenhouse gas fluxes in terrestrial ecosystems. https://hdl.handle.net/10568/105504
[note] Pirker, J & Carodenuto, S (2021) Current State, Barriers and Perspectives for REDD+ in the Congo Basin. Congo Basin Forest Partnership Report. https://pfbc-cbfp.org/actualites-partenaires/Package-%C3%A9tudes-PFBC.html?file=files/docs/key_docs/Publications%20du%20PFBC/2021_CBFP_REDD%2B%20in%20the%20Congo%20Basin_Report.pdf
[note] Nkuintchua, T., Enongene, K. and Mbzibain, A. (2019) Independent Evaluation Of the project - CoNGOs: NGOs collaborating for equitable and sustainable community livelihoods in Congo Basin forests. IIED. https://www.iied.org/sites/default/files/pdfs/migrate/13614IIED.pdf
[note] Lescuyer. G, Kakundika, T. M., Lubala, I. M., Ekyamba. I. S., Tsanga R., and Cerutti, P. O., (2019) Are community forests a viable model for the Democratic Republic of Congo? Ecology and Society. Are community forests a viable model for the Democratic Republic of Congo? on JSTOR

### viii. Value for Money Assessment of Preferred Option

This section evaluates the VfM of option 3 against option 1 through a quantified Cost Benefit Analysis and supporting qualitative evidence. Both options have been outlined earlier in the appraisal case as the ‘preferred’ option and the ‘do no more’ option respectively. The multiple benefits of functional tropical forests are difficult to model in narrow economic or financial terms, but the analysis adopts the available evidence in making its assumptions.

The model juxtaposes the global benefits that arise through CO2 sequestration, non-timber forest and timber products when the Congo Basin is sustainably managed, with the loss of logging and shifting cultivation opportunities for forest communities when short-term extraction livelihoods are curtailed to protect the forest. The Congo Basin is the world’s largest carbon sink. As such, carbon sequestration associated with retaining tropical forests dominate the VfM and BCR assessment.
[note] World Bank (2022) Journey into the Congo Basin: The Lungs of Africa and beating Heart of the World. https://www.worldbank.org/en/news/feature/2022/10/24/journey-into-the-congo-basin-the-lungs-of-africa-and-beating-heart-of-the-world#

Through the proposed programme and investment of up to £90m across 7 years (2024-2030), the impact of this programme will be a reduction in the deforestation and disturbance rates respectively in the Congo Basin.

Following the cost-benefit analysis, the FCDO’s “4Es Framework” is applied to appraise whether CBFA represents an optimal use of resources to achieve intended outcomes on the basis of Economy, Efficiency, Effectiveness and Equity.

Counting the ‘monetisable’ benefits and applying the DESNZ 2023 “central” carbon price of £252/tCO2e gives this project a net present value of £11.4bn and positive BCR of 193:1. This value is lower at lower carbon prices and marginally negative (-£13.1million) if carbon is not valued.

Assuming that CBFA is concentrated on 968,400ha (0.36% of the basin) of the forest that is at high risk and accessible to FCDO, the programme could prevent 342,041ha being lost or disturbed between 2024-2050.

The average programme cost to preserve a hectare of rainforest (with all associated benefits) is modelled to be £170.42.

The key benefit arises from lower rates of deforestation and forest disturbance and continued CO2 sequestration above and below ground, that prevents 99.4MtCO2e from entering the atmosphere between 2024-2050, even when attribution to CBFA is scaled back after 2027 in the model. (If attribution is maintained at 90% over the 27-year period the model shows the programme to prevent 168.9MtCO2e from entering the atmosphere).

The discounted cost of the GHG savings that are attributable to the project over the project’s lifetime amounts to £0.59/ tCO2e.

Other benefits streams altered by CBFA in this analysis are associated improved land management, availability of non-timber forest products, and sustainably harvested timber – all assumed to be positively affected. Charcoal manufacturing and shifting slash and burn cultivation are assumed to be adversely affected given their extractive nature being pitched against the programme’s efforts, however, any intervention aimed at phasing away from these will do so in a manner that ensure economic losses are not incurred for the beneficiary.

The programme CO2 sequestration benefits are immense, but it is critically important to translate these into material livelihood gain for people living areas of intervention. Based on the model used, CBFA must ensure at least£0.29/tCO2e of the carbon benefits can be transferred to forest dependent communities. This will be achieved in a well-managed, monitored, and phased manner, with economic livelihoods safeguarded against any negative impacts as extractive processes are wound down.

There are documented benefits for weather stability, hydrological flows and biodiversity associated with the Congo Basin’s forests . These benefits support the positive VfM finding but are difficult to attribute and are not quantified in this assessment.
[note] Butler, R (2013) Deforestation Rate Falls in Congo Basin Countries. https://news.mongabay.com/2013/07/deforestation-rate-falls-in-congo-basin-countries/
[note] Abernethy, K. et al (2016) Annual Review of Environmental Resources (41) p.1–33. https://www.annualreviews.org/doi/pdf/10.1146/annurev-environ-110615-085415
[note] Wolosin, M and Harris, N (2018) Tropical forests and climate change: the latest science. https://wriorg.s3.amazonaws.com/s3fs-public/ending-tropical-deforestation-tropical-forests-climate-change.pdf

CBFA’s abatement cost of £0.59/tCO2e represents a cost-effective carbon capture and storage option, compared with other global options.

The Benefit-Cost Ratio (BCR) results captured in Table 9 are contingent upon improved land and forest governance that is expected to emerge from the programme. They should not be viewed as expected KPI’s or logframe targets for the programme, nor should the zero carbon BCR be interpreted as an actual negative impact on beneficiaries.

Table 9 - Summary results and value for money for CBFA £90m scenario (central carbon value series)
	Carbon at FCDO (£252/ton)	Carbon at EU market (£49/ton)	Carbon at voluntary market (£10/ton)	Zero Carbon (£0/ton)
Ave annual benefit of the programme (2024-2050)	£422m	£81m	£16m	-£0.48m
Net Present Value (10%)	£11.40bn	£2.21bn	£0.44bn	£-0.01bn
Benefit Cost Ratio	193:1	37:1	7.5:1	0.22:1
HMG cost (actual)	£90m	£90m	£90m	£90m
HMG cost (discounted)	£59m	£59m	£59m	£59m

The modelled livelihoods detailed in table 10 below demonstrate the complex narrative of forest-preserving interventions in regions where local populations are predominantly reliant on extractive processes to meet basic needs. It is important to note that these values represent the theoretical losses and gains only of the variables modelled, and serve as guidance for CBFA regarding the associated safeguarding measures previously described that will ensure no participant will experience negative economic impacts as a result of programme interventions. Beyond the model variables, many direct programmatic benefits are expected through CBFA. These include:
- Enhancing productivity through provision of agricultural and agroforestry materials (e.g., seeds/saplings, pesticides & equipment).
- Construction of basic infrastructure within local communities to support activities.
- Provision of vehicles to support accessibility for civil society and local communities.
- Supporting access to markets for agricultural and agroforestry products.
- Improving efficiencies in various practices (e.g. charcoal production and consumption).
- Provision of effective training to local communities, securing lasting capacities and expertise.
- Supporting development of knowledge across the region (e.g. Gabon’s successful certification of 93m tonnes of carbon credits based off robust evidence).

Table 10 - Summary results and value for money for CBFA £90m scenario (DESNZ ‘central carbon value series’)
Congo Basin Forest Action Programme Modelled Variable	Modelled Outcome
Modelled geographical reach (ha)	968,400ha
Tropical forest preserved per year (ha)	24,210ha
Total tropical rainforest preserved 2024-2050 (with declining attribution) (ha)	346,203ha
Ave. cost of preserving a ha. of rainforest (2024-2050)	£170.42
Ave. cost per hectare of programme	£92.94
Attributable CO2e saving (2024-2050)	99.4MtCO2e
Cost per tCO2e (marginal abatement cost)	£0.59
Charcoal and wood fuel benefit/loss (total)	-£847,350
Slash and burn agriculture benefit/loss Y1	-£1,815,750
Slash and burn agriculture benefit/loss Y2	-£907,875
Slash and burn agriculture benefit/loss Y3	-£453,938
Non-Timber Forest Products benefit/loss Y1	£907,875
Non-Timber Forest Products benefit/loss Y2	£453,938
Sustainable forestry benefit loss (total)	£665,775
Total Modelled Livelihoods Benefits Without Safeguarding	-£2,009,430

The Congo Basin forests support a range of diverse livelihoods through combinations of direct food, fuel and timber harvesting, medical plants, charcoal and freshwater provision and conservation work, with the potential to add carbon offset generation under Article 6 of the Paris Agreement (and the voluntary carbon market) to this list .
[note] Samndong, R.A., Bush, G., Vatn, A., and Chapman, M. (2018) Institutional analysis of causes of deforestation in REDD+ pilot sites in the Equateur province: Implication for REDD+ in the Democratic Republic of Congo. Land Use Policy 76: 664-674. https://doi.org/10.1016/j.landusepol.2018.02.048
[note] White, L et al. (2023) Congo Basin rainforest — invest US$150 million in science. https://www.nature.com/articles/d41586-021-02818-7
[note] White, L et al. (2023) Congo Basin rainforest — invest US$150 million in science. https://www.nature.com/articles/d41586-021-02818-7

Informal wood production (including wood fuels) in the DRC alone has been valued at US$ 1,687m and represents 95.5% of total sector value. Forest stewardship offers opportunities for nature-based mitigation actions and the creation of the type of labour-intensive work that forest dwellers can access and sustain.
[note] Cerbu, G (Ed.). (2016) Central Africa Congo Basin Timber. PROFOR, Washington D.C. https://www.profor.info/sites/profor.info/files/PROFOR_CongoTimber_web_0.pdf

Precedents exist for climate-smart agriculture practices, land restoration, selective logging, and forest protection that provide jobs and revenues to rural households. For example, Brazil’s Bolsa Floresta program offers a monthly payment to low-income households if they commit to zero deforestation and enrol their children in school; in Colombia and Nicaragua, land users receive payments for preserving ecosystems that delivery public good services; in Costa Rica poor households receive payments for reducing deforestation.
[note] Pfaff, A; Robalino, J-A; Sanchez-Azofeifa, A (2007) Payments for Environmental Services: empirical analysis for Costa Rica. Paper For NBER S.I. https://www.researchgate.net/publication/228707178_Payments_for_Environmental_Services_Empirical_Analysis_for_Costa_Rica

While closed canopy tropical rain forests represent a specific biome that is typically incompatible for commercial agriculture, the Central African forests include open forest and savanna. In these areas it is becoming clear that trees can be integrated and used to restore agricultural landscapes to the benefit of both carbon sunk and agricultural productivity.

### ix. Cost Benefit Analysis Assumptions

The programme BCR and VfM assessment is contingent upon a series of modelling assumptions (most notably the carbon price), summarised below in Table 11.

Table 11 - VfM Model Assumptions
Parameter	Assumption
Overall budget	The programme will invest an additional £90 million in the Congo Basin over 7 years. This allocation will be slow (5%) in the first year relying on “existing proven partners” and stepped up (10%) in year 2 and 17% the final 5 years of the programme.
Time horizons	Investment is expected over 7 years (2024-2030) and the benefits of this investment are modelled over 27 years (2024-2050). The benefit stream is subject to an “attribution” factor and a social discount rate which combine to make the model conservative. The attribution factor ensures that the model does not claim benefits that should be attributed to other programmes or interventions (particularly after 2030), and captures the impact leakages that accompany any investment of this nature.
Discount rate	10% per annum
Geographical reach	The Congo Basin is captured as the 269m hectares that span six Central African countries. CBFA expected to target the 968,400ha that most at risk of deforestation and disturbance and where it knows it can be effective.
Size of carbon sink	The estimates vary, but for the purposes of the model it is assumed the Congo Basin stores 30.6bn tonnes of carbon (mostly in peatlands), the equivalent of 224.6bn tCO2e . This is distributed equally above and below ground.
Distinction between deforestation and forest disturbance	The model distinguishes between ‘deforestation’ (total loss of forest) and ‘forest disturbance’ that results from communities making charcoal, collecting fuelwood, defaunation of animals responsible for seed dispersion and pursuing slash and burn agriculture without removing the entire tree canopy. Deforestation results in 100% loss of above ground carbon and 75% loss of below ground carbon. Disturbance results in 50% loss of above ground carbon and 50% loss of below ground carbon.
Reduction in deforestation and disturbance rates	Current levels of deforestation in the Congo Basin are assumed to be 0.3%, but this is not evenly distributed across the 269 million hectares. CBFA will target the 968,400ha that are known to be at risk. Over this area, deforestation will be reduced from 6.5% per annum to 4% per annum due to programme interventions Disturbance of the forest (through charcoal and agricultural activities) will be reduced by the same extent.
Attribution factor for benefit streams	The ability to attribute benefits to CBFA investment is expected to decline over time as the programmes impact declines and new interventions are introduced. Attribution is modelled at 90% year 1-7 while investment is active; 60% year 8-17 and 20% for year 18-27.
Value of carbon	The DESNZ value of a tonne of avoided CO2e in 2023 of £252 is used in the model. This value is not adjusted annually, but the model accommodates, and imputes how VfM changes when CO2e is valued at £49/ tonne (EU prices) and at £10/ tonne (voluntary market prices) and £0/ tonne respectively.
Ave value of unsustainable charcoal and wood fuel	£70 per hectare per year
Ave value of unsustainable slash and burn agriculture	£150 per hectare in year 1 / £75 per hectare in year 2 / £37.5 per hectare in year 3
Mean value of NTFPs	£75 per hectare in year 1 / £37.5 per hectare in year 2
Mean value of sustainable agroforestry	£55 per hectare per year
Baseline	The VfM is modelled relative to the baseline of FCDO’s existing programme. This programme experiences 0.3% deforestation per year and a further 0.3% forest disruption due to unsustainable wood fuel collection and charcoal burning.
[note] WWF (2021) Deforestation Factsheet DRC & CAR. https://wwfint.awsassets.panda.org/downloads/deforestation_fronts_factsheet___drc_and_car.pdf
[note] Harris, N.L., Goldman, E., Gabris, C., Nordling, J., Minnemeyer, S., Ansari, S., (2017). Using spatial statistics to identify emerging hot spots of forest loss. Environmental Research Letters 12(2): 024012. https://iopscience.iop.org/article/10.1088/1748-9326/aa5a2f
[note] Lewis. S. (2009) Nature 457, 933 (2009). https://doi.org/10.1038/7232933a
[note] UNEP (2023). Critical Ecosystems: Congo Basin Peatlands. https://www.unep.org/news-and-stories/story/critical-ecosystems-congo-basin-peatlands#
[note] CAFI (undated) Why Central African Forests. https://www.cafi.org/who-we-are/why-central-african-forests
[note] Abernethy, K; Coad, L; Taylor, G; Lee, M; Maisels, F. (2013). Extent and Ecological Consequences of Hunting in Central African Rainforests in the 21st Century. http://rstb.royalsocietypublishing.org/lookup/doi/10.1098/rstb.2012.0303
[note] Bogaert, J., Bamba, I., Koffi, K.J., et al. (2008) Fragmentation of forest landscapes in Central Africa: Causes, consequences and management. In: Lafortezza, R., Chen, J., Sanasi, G., and Crow, T.R. (eds), Patterns and Processes in Forest Landscapes, pp 67-87. Springer. https://link.springer.com/chapter/10.1007/978-1-4020-8504-8_5
[note] Butler, R (2013) Deforestation Rate Falls in Congo Basin Countries. https://news.mongabay.com/2013/07/deforestation-rate-falls-in-congo-basin-countries/
[note] Mayaux, P; Pekel, J-F; Desclée, B; Donnay, F; Lupi, A; Achard, F; Clerici, M; Bodart, C; Brink, A; Nasi, R; Belward, A. (2013) State and Evolution of the African Rainforests Between 1990 and 2010. https://royalsocietypublishing.org/doi/10.1098/rstb.2012.0300
[note] UK Government (2020) Valuing Greenhouse Gas Emissions in Policy Appraisal. https://www.gov.uk/government/publications/valuing-greenhouse-gas-emissions-in-policy-appraisal/valuation-of-greenhouse-gas-emissions-for-policy-appraisal-and-evaluation#annex-1-carbon-values-in-2020-prices-per-tonne-of-co2
[note] WRI (2021) How Charcoal Industry Threatens DRC Forests. World Resources Institute. https://www.wri.org/insights/how-charcoal-industry-threatens-drcs-forests
[note] OEC (2022) Wood Charcoal Production DRC. https://oec.world/en/profile/bilateral-product/wood-charcoal/reporter/cod
[note] EnDev (2022) Where Charcoal is too Costly: eCooking for Urban Areas in DRC. https://endev.info/where-charcoal-is-too-costly-ecooking-for-urban-areas-in-drc/
[note] Ndinga, J. (2023) Congo-Brazzaville Seeking Alternatives: Slash and Burn Agriculture Mayombe Forest. Rainforest Journalism Fund. https://rainforestjournalismfund.org/stories/congo-brazzaville-seeking-alternatives-slash-and-burn-agriculture-mayombe-forest;
[note] Bogaert, J., Bamba, I., Koffi, K.J., et al. (2008) Fragmentation of forest landscapes in Central Africa: Causes, consequences and management. In: Lafortezza, R., Chen, J., Sanasi, G., and Crow, T.R. (eds), Patterns and Processes in Forest Landscapes, pp 67-87. Springer. https://link.springer.com/chapter/10.1007/978-1-4020-8504-8_5
[note] Tanzito Adjumati, Georges & Ibanda Pembele, Angele & R, Talaguma & M, Lusanga. (2020). Slash-and-burn agriculture, the major cropping system in the region of Faradje in Democratic Republic of Congo: Ecological and socio-economic consequences. Journal of Development and Agricultural Economics. 12. 25-36. https://www.researchgate.net/publication/340105605_Slash-and-burn_agriculture_the_major_cropping_system_in_the_region_of_Faradje_in_Democratic_Republic_of_Congo_Ecological_and_socio-economic_consequences
[note] Butler, R. (2020). Deforestation in the Congo Basin Rainforest. https://rainforests.mongabay.com/congo/deforestation.html;
[note] Saambili, P. K., (2019). ‘Slash-and-Burn’ Agriculture Helps Displaced People in DRC Get Back on Their Feet. But What’s the Long-Term Effect? https://globalpressjournal.com/africa/democratic-republic-of-congo/slash-burn-agriculture-helps-displaced-people-drc-get-back-feet-whats-long-term-effect/
[note] Ingram, V. (2009) Valuation of non-timber forest product chains in the Congo Basin: a methodology for valuation. https://www.cifor.org/knowledge/publication/4617/
[note] Bush et al. (2020). Long-term collapse in fruit availability threatens Central African forest megafauna. Science, 370, 1219-1222. https://www.science.org/doi/10.1126/science.abc7791
[note] Bergen, M. (2019). Congo Basin Deforestation Threatens Food and Water Supplies Throughout Africa. World Resources Institute. https://www.wri.org/insights/congo-basin-deforestation-threatens-food-and-water-supplies-throughout-africa;
[note] Ingram, V. and Bongers, G. (2009) Valuation of Non-Timer Forest Product Chains in the Congo Basin. CIFOR. https://www.fao.org/forestry/24300-062a5a1a9b6119efd64c82838b3eaa379.pdf
[note] Bush et al. (2020). Long-term collapse in fruit availability threatens Central African forest megafauna. Science, 370, 1219-1222. https://www.science.org/doi/10.1126/science.abc7791
[note] Alkire, S. Foster, J, Seth, S; Santos, M-E; Roche, J Ballon, (2015) Multidimensional Poverty, Measurement and Analysis. https://ophi.org.uk/publications/ophi-working-papers/
[note] FSC (2020) Forest Stewardship Standard for the Democratic Republic of the Congo. Available from: www.fsc.org/en/documentcentre/documents/resource/188
[note] Ingram, V. (2017). Changing governance arrangements: NTFP value chains in the Congo Basin. International Forestry Review Vol.19(S1). https://www.cifor.org/publications/pdf_files/articles/AIngram1701.pdf;
[note] African Development Bank (2021). Policy Brief - Economic performance of the Congo Basin’s forestry sector https://www.afdb.org/en/documents/policy-brief-economic-performance-congo-basins-forestry-sector;
[note] Nlom, H. J. (2011) The Total Economic Value of Congo Basin Forests. https://www.researchgate.net/figure/the-total-economic-value-of-Congo-Basin-forests_fig1_49607803;
[note] Nlom, H. J. (2011) The Economic Value of Congo Basin Protected Areas Goods and Services. https://www.researchgate.net/publication/49607803_The_Economic_Value_of_Congo_Basin_Protected_Areas_Goods_and_Services
[note] Fair and Precious (2023) 10 Million Hectares to be Certified as Sustainably Managed in the Congo Basin by 2025. https://www.fair-and-precious.org/en/news/750/10-million-hectares-to-be-certified-as-sustainably-managed-in-the-congo-basin-by-2025;
[note] Interholco (2018) Sustainable Forest Management, the ‘best land-use’ for Congo Basin’s ‘Natural Capital’. https://www.interholco.com/en/rss-feed-en/19-archive-2018/98-sustainable-forest-management-the-best-land-use-for-congo-basin-s-natural-capital

### x. Monetisable & Non-Monetisable Benefits

Monetisable

Carbon: By altering the deforestation and disturbance rates, CBFA safeguards 3.7 MtCO2 above and below ground in the Congo Basin per year. Over the lifetime of the programme (2027-2050) the preferred option would secure 99.4MtCO2e, once the declining attribution rate in the VfM model is considered. The abatement cost for the programme translates to 0.59/tCO2e.

Sustainable forest management and ecosystem services: The programme ensures 968,400 hectares of the most vulnerable forests across the Congo Basin are subjected to improved land and forest management. On half this land the rate of deforestation is reduced from 6.5% per annum to 4% pr annum (a 38% decline). On the other half of this area, forest disturbances are cut by a similar proportion. As a result, 346,203 ha of forest are preserved between 2024-2050, securing habitats for the Congo Basin’s biodiversity as well as the Congo Basin’s role in hydrological mediation and rainfall patterns.

Increased income: The modelled income benefits to people living in the Congo Basin are positive for NTFPs (especially sustainable meat harvesting) and agroforestry and negative for unsustainable charcoal and wood harvesting and for unsustainable slash and burn agriculture. The income increase for beneficiaries relates to carbon sequestration benefits (e.g. Payments for Ecosystem Services & Voluntary Carbon Markets), NTFPs and sustainable logging, all of which are assumed to be positively correlated with investment. Income from charcoal manufacturing and slash and burn agriculture are assumed to be negatively correlated with investment. The analysis suggest that a carbon price of £0.29/ tonne is necessary, or an additional £166 per hectare of agroforestry is required to offset the loss of income from charcoal, wood fuel harvesting and small-scale slash and burn agriculture. These values provide critical guidance for CBFA’s monitoring and safeguarding approach that will be implemented to ensure economic losses are not actualised through programme activities.
[note] Pagiola, S., Rios, A., & Arcenas, A. (2008). Can the poor participate in payments for environmental services? Lessons from the Silvopastoral Project in Nicaragua. Environment and Development Economics, 13(3), 299-325. https://www.cambridge.org/core/journals/environment-and-development-economics/article/abs/can-the-poor-participate-in-payments-for-environmental-services-lessons-from-the-silvopastoral-project-in-nicaragua/78EFE1C043E36008D90B75EDA01125A8

Non-monetisable

Forests are complex ecosystems that generate a multiplicity of public goods, not all of which can be captured in economic models. Evidence is emerging of the biodiversity refuge provided by the Congo Basin as well as the forest’s contribution to year-round hydrological flows and rainfall in Central and West Africa. It is unknown as to how much deforestation would threaten these ecosystem services. As such they have not been quantified or attributed in this analysis. It stands to reason, however, that protecting the Congo Basin habitat, as well as the heritage value that it presents, provides positive outcomes for society through the following known pathways.

Hydrological mediation: The ability of functional forest systems to reduce the impact of both drought and flood in the Congo Basin and further across Sub-Saharan Africa, across rural areas, cities and towns .
[note] Megevand et al. (2013) Congo Basin Forests: Description https://elibrary.worldbank.org/doi/abs/10.1596/9780821397428_CH01
[note] Bergen, M (2019) Congo Basin Deforestation Threatens Food and Water Supplies Throughout Africa, https://www.wri.org/insights/congo-basin-deforestation-threatens-food-and-water-supplies-throughout-africa

Biodiversity refuges: The Congo Forests are home to 10,000 plant species, 30% of which are unique to the basin. A United Kingdom-led team showed that fruit production in a forest in Gabon declined by 81% over three decades. This decline correlated with a warming and drying climate in the region. Less fruit production appeared to affect forest elephants who eat fruit as a key part of their diet: they showed an 11% decline in body condition over the same period. A degradation in biodiversity impacts the resilience and productivity of an ecosystem, which in-turn, affects the livelihoods that depend on them.
[note] WWF (2023) Congo Basin. https://www.worldwildlife.org/places/congo-basin
[note] Bush et al. (2020). Long-term collapse in fruit availability threatens Central African forest megafauna. Science, 370, 1219-1222. https://www.science.org/doi/10.1126/science.abc7791

Weather stability: Forests affect multiple aspects of radiative forcing and accordingly the full weather and climate impact of these forests goes beyond its role as a carbon sink. Through albedo effects, cloud seeding, surface roughness and localised intensity of evapotranspiration, forests affect both global climate and regional weather and forest destruction would almost certainly cause warmer and drier weather in large parts of the continent, alongside less predictable rainfall patterns, something critical for the majority of livelihoods across the region. More generally the Congo basin forests are “key to global environmental health”.
[note] Wolosin, M and Harris, N (2018) Tropical forests and climate change: the latest science. https://wriorg.s3.amazonaws.com/s3fs-public/ending-tropical-deforestation-tropical-forests-climate-change.pdf
[note] Abernethy, K; Coad, L; Taylor, G; Lee, M; Maisels, F. (2013) Extent and Ecological Consequences of Hunting in Central African Rainforests in the 21st Century. http://rstb.royalsocietypublishing.org/lookup/doi/10.1098/rstb.2012.0303.

### xi. 4Es: Economy, Efficiency, Effectiveness, Equity

Economy

Economy refers to the degree to which FCDO or its agents can be expected to buy the inputs required to produce programme outputs at an appropriate quality and cost. Inputs would include staff, third-party consultants, raw materials and/or capital.

Companies and consumers stand to benefit from the certification processes and sustainable timber products envisaged under this programme.

Efficiency

Efficiency refers to the degree to which programme activities are predicted to convert the aggregate inputs into desired outputs.

A total investment of £90 million over 7 years generates an average annual return of £422 million every year between 2024-2050.

A key benefit emerging from this programme involves GHG sequestration at a time when the world desperately needs to remove CO2e from the atmosphere. The low marginal abatement costs for CO2e reduction (£0.59 per tonne), the total cost per hectare (£60.93/ ha.) and the low average cost of preventing a hectare of tropical rain forest from being either lost or disturbed (£170.42/ ha.) provide the UK government with an efficient means of supporting sustainable global development (Sustainable Development Goals 2, 12, 13 and 15).

The VfM analysis reflected on a raft of systemic changes including community custodianship of forests, greening of value chain, evidence development, capacity building and a knowledge economy that in turn will enable greater co-ordination of multi-lateral donations to the region. It is these changes that will convert the public-good value of forests identified in the ‘benefit streams’ into on-the-ground incentives to conserve forests and better decisions around forest stewardship.

Lessons and evidence from the FCDO’s prior engagement in the Congo Basin will inform approaches for delivering supported activities that maximise the likelihood that inputs are efficiently converted into outputs which ‘stick’.

Effectiveness

Effectiveness refers to the rate at which CBFA outputs are predicted to transform into desired outcomes and impacts.

The economic model uses FCDO’s preferred carbon price of £252/tonne. The resulting output suggests an extremely high BCR. To test the robustness of this, a sensitivity analysis was carried out, which showed that a) when the carbon price is reduced stepwise, the BCR remains positive until the per tonne value is £0.29, giving confidence that CBFA will be highly cost effective.

Despite the significant net macro benefits to protect the forests of the Congo Basin, at community level, there are micro incentives not to. The model quantifies this. At zero carbon value, it predicts a £480,000/year loss, driven by reduced extractive livelihoods activities. This will be carefully monitored by the implementing partners and MEL component to ensure that, in reality, this does not happen, with interventions having a core focus on driving economic gains ahead of any transition away from extractive activities.

Programme benefits will be additional. Outputs and outcomes associated with the CBFA represent an expansion of existing initiatives with proven benefit. The additional area covered by this programme, and the reduced rate of deforestation and forest disturbance, ensures the programmes additionality in terms of positive difference that would not have been realised otherwise.

The programme provides a key defence against accelerated deforestation driven by expanded access to the forest as new roads are built and anthropogenic climate change.
[note] Karam, S.; Zango, B.-S.; Seidou, O.; Perera, D.; Nagabhatla, N.; Tshimanga, R.M. (2023) Impacts of Climate Change on Hydrological Regimes in the Congo River Basin. Sustainability 15, 6066. https://doi.org/10.3390/su15076066

Equity

Equity refers to the way in which programme benefits are distributed among target populations and is particularly important considering FCDO’s commitment to ‘leave no one behind’. The model captures both positive and negative impacts on local livelihoods, but shows that where the benefits of greenhouse gas mitigation can be translated into income gains for local residents, the equity contribution will be positive and high.

The programme has “Improved enabling conditions including empowerment of local actors and cooperation between stakeholders” listed as an outcome.

Outputs will assist recipients adopt beneficial practices. The positive correlation between CBFA and the value of non-timber forest products and sustainable forestry will assist local communities in diversifying their livelihood incomes.

The previously mentioned challenge around curtailment of extractive livelihoods processes will be at the forefront of the inception and implementation of CBFA, ensuring that local communities are not negatively affected by the interventions delivered. This will be secured through effective consultation with beneficiaries to co-design appropriate activities, coupled with a proactive and response MEL approach that will safeguard against microeconomic damage.

The Congo Basin Forests represent an “open access resource” more than a “common property resource” in the typology of Ostrom and Hess and creating a regime that might control rights of access, withdrawal, management and exclusion to the forests and their resources is not expected to be easy. All the evidence testifies to the need to convert the macro-economic rationale for protecting these forest landscapes into on-the-ground incentives confronted by a critical mass of local people, to protect trees.
[note] Ostrom, E. and Hess, C. (2007) Private and common property rights. Workshop in Political Theory and Policy Analysis, Indiana University. Research Paper No. 2008-11-01. https://dlc.dlib.indiana.edu/dlc/bitstream/handle/10535/3985/W07-25_Ostrom_Hess_DLC.pdf?sequence=1&isAllowed=y

The benefit streams listed above will only be realised if donor funds are allocated through trusted and accountable partnerships with local agencies and organisations capable of translating the economic benefits outlined into on-the-ground incentives that provide an alternative to the hard-won livelihoods forged in clearing forests for the purposes of human settlements, agriculture, charcoal and artisanal mining purposes. The same reconfiguration of incentives requires a political economy that favours sustainable forest economies over the rents that can be generated through an indiscriminate extension of mining rights and road construction licenses for example, and which is capable of policing cross-border trade in illegal forest products. Any successful effort will necessarily have to be span country borders. An example of this is the long-term partnerships between international scientists and local research institutions that have yielded much of the data on climate change, carbon sinks and biodiversity that has driven policy changes to date.
[note] White, L et al. (2023) Congo Basin rainforest — invest US$150 million in science. https://www.nature.com/articles/d41586-021-02818-7

Programme activities will aim to improve the ability of landholders and land businesses, including women, Indigenous People and other marginalised groups, to extract greater value from forest and land management. For example, CBFA aims to secure higher value forestry and the protection of non-timber forest products to enhance the livelihoods of forest communities.

## Commercial Case

### i. Routes to Market Summary

This section sets out the commercial approach and requirements, proposed funding/performance model and rationale for choice of instruments that will be deployed under the programme to ensure strong value for money. The commercial case has been developed in close collaboration with relevant colleagues and programme teams delivering in the region, Commercial Department, and the design team. This builds on input from consultants, organizations and communities in the region delivering on Forestry initiatives, existing FCDO programmes and central Africa coordination mechanisms in the region.

Primary Market analysis has been undertaken via an in-depth field trip conducted by the programme Senior Responsible Owner (SRO) and a review of previous HMG-funded forestry programmes in the Congo Basin. Feedback from these initial assessments/scoping reviews indicate there is sufficient local expertise and suppliers required to deliver a programme of this nature based in the region at tiers 1 and 2 of the programme through INGOs and the private sector. This analysis has fed into the choice of route to market mentioned in the sections below. Building on this analysis, an Early Market Engagement (EME) will be conducted with interested suppliers in early 2024, to generate market interest, for component 1 and 2 in particular, and to feed into the terms of reference for potential suppliers. Given the scale of this programme, the programme is likely to need to work through National NGOs at tier 3. These organisations do not have the capacity to operate at scale and are unlikely to be able to deliver all the elements of the programme, so multiple funding mechanisms will be used to maximise delivery of the programme objectives.

Building on the appraisal case and preferred option, the programme team therefore intends to utilise a mixed approach to deliver the budget allocation of £90 million against four identified components:

Figure 5 - CBFA Budget Allocations
The table below summarises the proposed approach to delivery against the 4 identified components of the programme:
Table 12 - Component Commercial Approaches
Component	Approach	Comment
Community Forests (£45 million)	Commercial Contract	Competitive procurement
FCDO Partners Facility (£20 million)	AGs, MoUs, Commercial Contract	Competitive procurement for Fund Manager to manage: / Breakdown of funds to be determined but could use one or a mix of the following routes to market: / Direct funding for unsolicited proposals / MoUs with international organisations / Call down within existing FCDO Frameworks
CAFI (£20 million)	MoU	Existing MoU with multilateral – currently UNDP as the host of the CAFI Secretariat
Monitoring, Evaluation & Learning (£5 million)	Commercial Contract	Call down from the GEMFA Framework

### ii. Routes to Market Componentry Details

Component 1 – Community Forests

As set out in the Appraisal Case, this component will seek to support activities that contribute to outcomes related to improved forest & land use governance and forest management solutions that support communities dependent on forests for livelihoods. This component has been designed on the basis of feedback received during the scoping review/concept note stage of this programme and will look to address challenges of having long delivery chains and lack of beneficiary engagement in co-designing interventions. It aims to underpin activities with strong political economic analysis of policies and operational environment related to devolved land rights, forest management and trialling innovative approaches to nature-based solutions in the Congo Basin region. Working directly with communities and aligned to principles of co-design mentioned in the strategic and appraisal case, with a requirement for the lead delivery partner to ensure safeguards are implemented to guarantee that local communities will benefit economically. This component is likely to be a single lead agency that subcontracts the delivery to consortium of commercial entities/not-for-profits/NGOs, with a strong local presence or understanding of context. The lead delivery partner will have to work closely with the MEL provider who will have oversight of activities, tracking economic and deforestation performance including, the safeguarding of beneficiaries from negative economic impacts.

This component will be sourced through a competitive tendering process. An EME will be arranged in early 2024, to help form a terms of reference document that will build on the outline in the Appraisal Case. This ToR will be used to source an implementing partner through a competitive procurement process. Based on the pre-market analysis a contract is best suited for this component given it is of high value, will require significant, sustained management capacity for managing subcontracts that will draw in local expertise. Any contractual agreements with suppliers will have break clauses to ensure flexibility for required circumstances. It is likely that a large private sector supplier will deliver this overall management function for the programme, managing onward, potentially long, delivery chains. A workplan will be developed under the MEL component to monitor progress through the inception and delivery phases.

Component 2 - FCDO Partners Facility

This component will deliver fast mobilising interventions that can contribute to developing longer-term activities under component 1. Example of activities under this component could include working with FCDO’s Land Facility on commissioning action research or working on relevant policy areas or working with specific organisations in-country on regional capacity building initiatives or finding regional academic capacity and links to wider scientific networks.

This component will be sourced through a mixed approach including existing FCDO framework agreements, FCDO Land Facility and responses of unsolicited proposals received from organisations operating in the region that will be contracted via an accountable grant modality. This delivery mechanism is proposed given the anticipated efficacy of working with organisations that are already active in this area. For example, NGOs with an existing local footprint and initiatives may be more likely to successfully deliver given their relevant relationships and experience working with communities to deliver results. There are several INGOs/NGOs that are currently delivering such work at the community level, investing in these will provide FCDO with better VfM, avoiding economic cost of additional management and administrative cost for setting up new entities, leveraging existing partnerships and building on a robust evidence base on what works. The detailed breakdown of the £20 million spend against delivery route is yet to be determined. These delivery routes are best suited to a component of this nature to ensure flexibility, allow for greater control over the interventions to adapt and learn (smaller innovative grants) and faster procurement (helping to mitigate the reputational risk of slow delivery in risk section below). Contracts and accountable grant agreements will have break clauses to ensure flexibility for required circumstances.

Aspects of this approach may be more management intensive than others, particularly with respect to unsolicited proposals without any pre-existing framework agreement. Overseen by the planned project-funded staff, the management requirements of this component will be outsourced to an intermediary tier 1 supplier, who will be responsible for proposals received, including taking them through the approvals process for filtering, assessment, and final consideration by the board. The tier 1 supplier will also manage opportunities that may arise for activities within existing FCDO frameworks which will be significantly less time intensive, given funding mechanisms and central management already be established. Given the tier 1 supplier will take some time to procure, project-funded staff and the core FCDO team will take forward pre-existing unsolicited proposals in the interim.

The criteria for selecting proposals will be based on the programme’s theory of change outcomes and impact. Proposals will need to demonstrate validation of these in the first instance. This will be considered alongside the proposed geographies for intervention to assess feasibility of delivery, assurance that consultation has taken place to ensure the considerations of beneficiaries have been factored in and safeguarding considerations. An appraisal of the delivery partner(s) will also be conducted to ensure reputational and fiduciary risks are effectively mitigated. The full set of formalised criteria will be developed within the FCDO management team ahead of programme inception.

A workplan template for performance management will be established. Each successful proposal and respective delivery partner will be required to work with the MEL component lead with oversight from the FCDO management team and tier 1 supplier to develop and appropriate and mutually agreed structure to follow through the intervention lifespan. This will include KPIs and if appropriate, constitute a Service Level Agreement.

Component 3 – CAFI

Through this component the programme will invest through an existing well-established FCDO funding mechanism (MOU) delivered via the Central African Forest Initiative (CAFI) under the ARCAN programme. The CAFI secretariat is hosted by UNDP and programs are implemented via a range of organisations including the World Bank, FAO, GIZ, AFD. National and International NGOs can also be accredited to the fund. Strengthening coordination across the region, nationally and on a local level on forest management is critical for addressing challenges to deforestation and climate change in the Congo Basin. Working through an existing multilateral channel can help achieve this objective, and provision of this through an existing UK programme will streamline the process. CBFA will align with ARCAN where needed on funding, ensuring UK contributions to CAFI are proportionate.

This component will primarily provide direct investment into a UNDP managed Multi Donor Trust Fund MoU. Any interventions funded by the UK under a contribution to CAFI would be in line with the actions agreed in the letter of intent between CAFI and the host country, designed to address the drivers of deforestation. and made following demonstrable progress by CAFI in addressing MEL challenges during 23/24. This is also in line with FCDO’s COP27 commitments.

Component 4 – Monitoring, Evaluation & Learning

This component of the programme is primarily to drive independent appraisals, monitoring, evaluation, and learning with respect to the programme’s results framework and theory of change.

This independent MEL component will be procured using FCDO’s existing Global Evaluation and Monitoring Framework (GEMFA) that works with pre-selected suppliers to respond to Terms of Reference. The use of a pre-existing framework should result in a faster procurement time drawing in expertise from pre-approved suppliers. In the event this is perceived a risk, restricting the terms of reference for MEL in terms of limited number of pre-approved partners that are unable to deliver against the scope of work, the programme team will look to contract this through a competitive procurement process. This will have an appropriate break clause to ensure flexibility for required circumstances.

Components 1 and 2 contractual arrangements will seek to utilise elements of a design and build approach where feasible, including designing the programme activities based on strong political and economic analysis and an inclusive programme design approach. The inclusivity will be measured via strong engagement and ownership of programme activities by communities, local government, and local/regional stakeholders (such as non-profits, research organizations, small farm holders/private sector). The feedback received from market during the EME will be incorporated into the Terms of Reference and the future programme design. The implementing partner will be expected to build in a programme inception phase, on the basis of which workplans will be adjusted. This business case includes indicative budgets spend for each component, but we will revisit the component level split and further financial breakdowns at the procurement strategy stage (i.e., before tending).

To deliver on the UK commitments of COP26 and COP27 and to minimize reputational risk of slow/delayed delivery this programme will aim to frontload delivery where possible, balancing this against the need for a longer co-design phase elsewhere – timely mobilisation of high priority deliverables in Year 1 (direct awards to partners under component 2) and a thorough procurement process under way for components 1, 2 and 4. The appraisal option makes the case for working with a diverse range of partners (assessment of value for money of FCDO investments) and allowing time for partner and detailed geographic selection to minimize delivery, fiduciary, and other relevant contextual risks. During the mobilisation phase and upon approval of the business case, the programme team along with the Commercial Department will launch a tender process for the main implementing partner for the largest component (1) – the tender process and contract award is likely to take place in FY 2024/25 with inception phase to start in June 2025. The Year 1 spend via direct awards will help to hit the ground running immediately without risking reputational risk of lag in delivery since commitments at COP27. This approach of direct partnership management (MOUs, AGs) as well as a contract (reduced management burden for FCDO) will help to manage risk and ensure good VFM.

### iii. Generating Market Interest

CBFA has been well received by stakeholders as part of the design/consultation phase. There has been interest from a range of partners including INGOs and research institutions, as well as consultation with local communities (based on the field visit conducted by the SRO in 2022). This has reinforced the need for interventions within the defined scope of this programme. The programme’s commercial route to market will start with launching an EME for component 1 & 2.. The EME will be open to a range of potential suppliers, including commercial suppliers, INGOs, local NGOs, and other entities. This will ensure information is shared with the market in an open and transparent way without any competitive advantage given to current stakeholders.

For component 1 and 2, FCDO will launch a commercial route to market. To prevent any perceived bias and encourage a diverse range of bidders, the FCDO will:
- Host an EME in early 2024 to bring together potential partners enabling us to share information on the project direction, as well as discuss challenges to project implementation. This will also enable potential partners to meet and explore partnership options. The EME will inform the final sourcing strategy.
- Share a TOR based on current CBFA programme documents and lessons learnt from earlier Forestry, Livelihoods and Land Tenure related programmes in the Congo Basin area.
- Clearly articulate in the Invitation to Tender and the TOR the design and delivery requirements and expectations of the FCDO for the supplier. The TOR will also require any consortia bidding for the contracts to demonstrate how they will work together to deliver results.

During the first two years, there will not be a proactive call for proposals for component 2. This is because of the high-quality proposals already received, and the anticipation of such a trend continuing over the programme lifecycle. Should there be a significant gap at the end of year 2, the programme will consider issuing a call for proposals and associated promotional events through the tier 1 partner for component 2. In this event, we will follow the UK Government Functional Grant Standards to promote efficiency and effectiveness and follow a competitive grant process.

The Component 4 supplier will, in the first instance, be secured through the Global Evaluation and Monitoring Framework Agreement (GEMFA). However, if no suitable supplier is sourced via this mechanism, an open tender exercise will be conducted, which will be preceded by an EME exercise.

### iv. Payments and Performance Management

The CBFA programme aims to utilise appropriate payment approaches depending on the type of financial modality. The programme team will base the requirements for each contractual arrangement based on advice from Commercial Department and in accordance with the Programme Operating Framework (PrOF). Although the intention is to tie payments closely to workplans and milestones/deliverables, these are yet to be finalised.

Payment linked closely to work plans, reporting and/or results will form the core of the majority of funds executed under the tendered portion of the total programme budget. This will be done to encourage ambitious results and innovation within the programme. The inclusion of Key Performance Indicators (KPIs) on key areas of focus, including poverty and marginalization targets, will push implementing partners to focus attention on high-risk areas (for example growing urbanization and population that are at higher risk to deforestation or targeting Indigenous Populations that are at risk of being left behind) encouraging them to take innovative approaches to delivering against their targets. The payments against KPIs will be based on the context with clear assessment criteria.

The programme team will utilise verification visits, periodic reporting and findings from the MEL provider to ensure robust tracking of results against the KPIs, giving assurance on how FCDO funds are being used and enabling swift and early action should any issues be found.

### v. Contract & Supplier Management

The programme team will use a variety of incentives, metrics and mechanisms to manage performance including:

1. Monthly meetings with suppliers
2. Regular reporting against KPIs
3. Annual Reviews and audits.
4. Engagement of FCDO advisers at post where feasible.
5. Field visits.
6. Steering Committee/Programme Board reporting.
7. Third party independent monitoring (for components 1-3).

All implementing partners will need to successfully meet FCDO’s due diligence requirements and an assessment on their ability to technically deliver and meet the programme requirements ahead of signing the contractual arrangements; All tender processes involved in this programme will seek to evaluate capacity, capability and experience in delivering forestry related programming. The lead implementing partners will also be expected to manage the due diligence of downstream partners and accountability through the delivery chain.

Programme management will ensure minimisation of underperformance risk through robust workplans and appropriate KPIs which align with CBFAs outcomes and impact statement. These will be managed by the MEL provider with oversight from the FCDO project funded staff. These will be coupled with regular meetings outlined above between the internal FCDO management team and external suppliers. This will ensure effective scrutiny of activities, and allow for early indications of issue and consequent swift remediation.

Where the programme is delivered under a contract – e.g. components 1, 2 & 4, if underperformance is sustained or where serious concerns are raised or a contractual obligation is broken suppliers will be required to supply a rectification plan. Depending on the nature of the incident, the FCDO may also seek damages/financial compensation from the supplier. Alternatively, the supplier may be placed on a Performance Improvement Plan. If performance fails to improve, termination of the award will be considered.

### vi. Key Cost Drivers

Expected main cost drivers are listed in the table below:

Table 13 - CBFA Main Cost Drivers
Component	Type of Contract	Cost Drivers
1	Commercial contract	Management and administrative fee of implementing programme, consultants’ fees, travel costs, costs associated with delivery, including potential fund management costs, security costs depending on locations.
2	AGs, commercial contract and MoU	Fee rates, costs associated with delivery – staff, travel, security, cost of livelihood activities, field staff, administrative and management cost, including potential fund management costs.
3	MoU	Results-based payments or other channel of disbursement to regional stakeholders, analysis, administrative and management fee
4	Commercial Contract	Fee rates associated with agreed milestones, Consultant costs. Local/National staff costs. Data collection, travel costs, security costs depending on locations

Where relevant, a competitive procurement process will ensure that we are able to compare proposed costs and achieve greater value for money.

### vii. Value for Money Metrics
VFM indicators will be included in the programme’s results framework and logical framework (“logframe”) to help monitor and assess VFM performance. Table 14 below shows indicative metrics for how to track supplier performance:

Category	Metric
Economy	Costs of follow up and support. / Costs of evidence base creation. / Costs of training. / Costs of investment memorandum.
Efficiency	CF Establishment Cost. / Cost per hectare. / Cost per beneficiary.
Effectiveness	Cost/tCO2 avoided. / CFE revenue % increase.
Equity	% change in income of forest dependent communities. / % of CFE led by women. / % of CFE jobs delivered by women. / % of workshops attendance by women.

Table 14 - CBFA Indicative EEEE Metrics

A set of draft VfM indicators will be included in the ToR for the contracts and agreed during the contracting/granting stage. The implementing partners at the start of the programme will be required to agree a CBFA VfM and results framework with reporting metrics and template that will be used for reporting through programme implementation phase. It is anticipated that the production of the main results framework will be undertaken by the MEL provider and completed within 6 months of the appointment of that supplier. Additional work will be undertaken with implementing partners to ensure their financial systems are better able to analyse VfM per output. This will be supported by the MEL provider. Partners will be expected to regularly report on VfM indicators in periodic reporting and review meetings.
viii. Commercial Risk

The following risks have been identified with regards to the commercial component of the programme:

Risk of fielding capable suppliers for programme delivery – Given the context in the Congo Basin there is a risk of delayed and slow operationalization post-selection of implementing partner across the 4 countries. This risk relates to the ability of the selected partner to run procurement processes, select capable sub-contractors, mobilize teams, set up robust implementation systems and ability to deliver in a timely manner. The selected implementing partner (following competitive tendering) will be required to provide a work plan for commencing activities on the ground and conduct a similar assurance check, provide a delivery chain map and conduct due diligence for all sub-contracted bodies. The work plan will be used to adjust timeframes and provide any support required to setting up the programme presence on the ground.

Contextual complexities with downstream delivery – Limited partner capability to deliver in complex operating environments forms another key commercial risk. Efforts to capacity build local organisations will be carried out as part of validating the programme’s objectives. Due diligence will be carried out prior to award of grants to ensure policies in partner organizations meet FCDO standards such as anti-corruption, fraud and bribery, safeguarding, modern slavery, risk management and procurement capability. Delivery chain mapping and due diligence and monitoring will be used to manage delivery risk during implementation. All first-tier suppliers will be required to carry out similar due diligence checks on downstream partners.

Risk of lack of coordination within programme components - Integrated programme learning – Building on lessons learnt in other FCDO forestry related programmes, an independent MEL component has been built into the programme to provide assurances the programme is delivering against the set scope, driving good VFM and continuing to learn and adapt to the given context. There is a risk the different components of the programme operate in silos. The TOR for the individual contract/MOU/AGs should include data sharing agreements with the MEL facility. More details of assuring coherence across the different components are covered in the management case.

Risk of delayed programme delivery – given this programme relates to COP26 and COP27 commitments there is a reputational risk of being perceived as being slow to deliver. The commercial case and route to markets for each of the components takes this into account and has suggested a proportionate approach to delivery balancing between faster procurement arrangements (where due diligences have been done in advance) vs open tendering processes which could take up to 6-8 months to complete.

Risk of poor exit strategy – this programme will be funded for 7 years. There is currently not any successor programme in the pipeline. This is expected given CBFA has yet to commence, however, there is a risk that as the programme reaches its end point, activities will abruptly cease to the detriment of beneficiaries. The FCDO team will closely monitor and capitalise on opportunities for continuation of activities through internal solutions such as new programming and expansion through other programming such as IFSLU2 which runs for 10 years, alongside liaising with other regional donors to understand potential for collaboration. This will be developed into an engagement plan by the MEL component as the programme progresses. CBFA will be supported by FCDOs standard terms and conditions on Exit Management, where the supplier is obligated to provide an Exit Plan within 3 months of the commencement of the contract. The team are permitted, on giving reasonable notice, to request an update to the Exit Plan.

A detailed risk register and risk strategy is embedded within the management case. This programme is not expected to deliver in conflict affected areas of the Congo Basin, however given the complex operating environment, there might be certain areas that pose a higher delivery, fiduciary and safeguarding risks that will require close monitoring and management. Such geographies may require remote monitoring plans to ensure continuity in performance. All implementing partners will be required to periodically report against this risk, maintain an update to risk register and ensure have robust systems in place to escalate and address any issue that arise through the course of the programme.

## Financial Case

The Congo Basin Forest Action Programme has been conceived as a £90 million, 7-year Business Case. FCDO will provide £90 million of RDEL over a period of seven years from 2024, although options will be explored to deliver some spend as CDEL where appropriate. This will be addressed should opportunities arise. The commitment of £90 million for a specific programme focused on the Congo Basin region was announced by the Prime Minister at COP27, and this amount would contribute to the ICF, ICF nature, forest funding and Congo Basin specific funding commitments.

### i. Financial Summary

Timeline

To best facilitate the mobilisation of the programme’s components in line with current affordability, it is envisaged that the programme will develop as in Figure 7 below. In year 1 funding will be channelled to CAFI, as well as the FCDO Partners Facility and INGOs/NGO or research institutions that are strategically aligned to component 2 and 3 of this programme (for more details please refer to the appraisal and commercial case). It is intended that procurement will begin in year 1 for a lead supplier to deliver Components 1 and 2. Procurement will also begin for a Monitoring, Evaluation and Learning provider using the GEMFA framework. Following the procurement exercise, from Year 2 Component 1 will begin delivery, anticipated to begin with a year-long consultation and co-design inception phase, after which the rate of spend should increase. Component 2 is expected to deliver from Year 1 under interim internal FCDO management. The timeline proposed is subject to Spending Reviews and affordability.

Figure 6 - CBFA Proposed Timeline

Overview of Funding Flows

Funds will flow from FCDO to Tier 1 suppliers for each component and then from those suppliers to downstream Tier 2 and Tier 3 partners engaged in project delivery. Funding is intended to be allocated to programme components broadly as set out below in Figure 8, with the below amounts assigned to components:

1. Community Forests £45 million
2. FCDO Partners Facility £20 million
3. CAFI £20 million
4. Monitoring, Evaluation & Learning £5 million

Figure 7 – CBFA Programme Fund Flow Diagram

### ii. Componentry Financial Details

Component 1: Community Forests

Funds will flow from FCDO to a Tier 1 supplier. This supplier will be selected on the basis of an open procurement for a service contract. The appointed supplier will build an appropriate consortium with international and national partners in order to run the consultation and co-design process with stakeholders in the region as part of an inception phase. They will then run competitive processes to issue grants to Tier 2 suppliers to engage and deliver at the community level as well as with local and national processes. Tier 2 suppliers under Component 1 are likely to be non-government organisations, research organisations, and civil society actors. FCDO will conduct due diligence on the Tier 1 supplier prior to signing the contract, and the supplier will be responsible for establishing due diligence procedures, financial management and risk management systems to ensure good management of public funds and value for money.

Component 2: FCDO Partners Facility

Once procured, funds will flow from FCDO to a tier 1 supplier who will disburse to a selection of specialist organisations, anticipated to be not-for-profits or international organisations through grants to initiatives focused on the same themes as Component 1. This business case has identified examples of best practice in the region that component 2 can build on. Prospective partners may sub-grant to organisations engaged in community-level work. The tier 1 supplier will be expected to conduct due diligence on grantees prior to signing grant agreements and ensure that these grantees have adequate policies and systems in place to manage sub-granting – where this is anticipated – and ensure value for money. During the procurement phase, in order to mobilise funding quickly, the internal FCDO management team will progress pre-existing appropriate proposals, assuming the role expected of the tier 1 supplier to the extent that capacity permits.

Component 3: CAFI

Funds are anticipated to flow from FCDO to the CAFI multi-partner Trust Fund office, who are the fund managers. Funds will flow down to CAFI implementing organisations such as the World Bank and UN agencies, NGOs, and research institutions as Tier 2 suppliers. CAFI beneficiaries are at multiple levels – from communities up to national governments. Specific due diligence processes would need to be assessed by the programme team at the time of awarding funding. Payments will only be made on demonstration of need following assurance that partners can deliver.

CBFA will work with the existing funding mechanism established by ARCAN, adding value through targeted interventions where feasible, and providing core funding where necessary.

Component 4: Monitoring, Evaluation & Learning

Funds will flow to a Tier 1 commercial supplier selected through the Global Evaluation and Monitoring Framework Agreement (GEMFA) and from there to Tier 2 partners, which may include smaller subcontractors, global academic partners, and national service providers.

### iii. Financial Principles & Parameters

Management of Expenditure

For Trust Fund Administrative Agreements or the existing MOU, anticipated for CAFI under Component 3, funds are anticipated to be paid at a maximum of twelve (12) months in advance on cash-basis of commitment. Payment will not be in advance of need and will be in line with FCDO payment rules for Trust Funds. For contracts (Components 1 & 4), funds are anticipated to be disbursed to lead suppliers in arrears against inputs with performance criteria or against output milestones, this will be defined at contracting stage. Contracted suppliers will likely invoice FCDO monthly. There may be exceptions to this where a clear demonstration of need is provided. For grant agreements under Component 2, it is more likely that organisations funded will require payments in advance of activity taking place due their relatively smaller scale, however this will only be implemented where a need is demonstrated, and a preference is retained for payments in arrears where possible.

Costs Directly Incurred by FCDO

Delivery will be largely outsourced, and delivery costs will be incurred via the tier 1 suppliers, with all tier 1 agreements made in GB pound sterling. The costs incurred directly by FCDO are staff costs incurred within Africa Programmes & Expertise Department (APEX), Africa Directorate with FCDO for the programme’s management, oversight, and monitoring. The Management Case provides detail on the expected FCDO staff resources required to manage CBFA. In addition, it is anticipated that the programme may include the provision of two (2) project funded staff positions to be based in the region and working closely with partner organisations. Any decision to add a programme funded component would be taken by the SRO and APEX Management. The costs of these posts would be fully charged to the programme by reducing the relevant theme budget. The cost of each role would depend on the position and location but is expected to be up to £200,000 per annum per post. The position(s) would be in line with HMT rules.

Financial Aid to Governments

Financial aid to governments is not planned under this programme. However, during the inception phase, a thorough review of options to support host government priorities will be undertaken. There may be some cases where targeted funding for discrete activities, such as attending training events, may be needed to support progress. In any cases where funding could be seen as provided directly to host governments, support will be agreed and provided in line with FCDO policies.

Pooling of Resources

1. This programme covers a region within which we currently have two established FCDO Posts – BHC Yaoundé and BE Kinshasa. Working closely with these Posts will help the programme to better deliver, to realise opportunities and to manage risks. CBFA should retain an option for Posts to provide additional finance from their budgets where this is available in order to support deliverables that align with the programme’s objectives and with Posts’ Country Business Plans. In principle, this approach could be pursued through any of components 1,2 or 3.
2. The preferred method for post buy-in is by budget transfer from post to APEX. This represents the best value for money option based on programme management burden for additional components and staff time. This approach will follow agreed provisions for accounting for ICF spend and results at posts, and will only be carried out with Africa Geographic Director approval.

In addition, the CBFA programme intends to retain the flexibility to bid into other FCDO centrally managed programming modalities where appropriate, in particular the Centres of Expertise offer planned under the Land Facility, discussed in the Appraisal Case. In such cases, CBFA will follow processes set out under the relevant business case, seeking to achieve the best value for money and remaining consistent with the PrOF rules.

### iv. Cost Profile & Planning

The cost profile is set out in Table 11 below. Funding for the programme will come from the FCDO APEX. The programme intends to explore the use of both RDEL and CDEL where appropriate. 100% will be classified as Official Development Assistance (ODA) and International Climate Finance (ICF) and will count towards the £3 billion nature funding target, the global forest-related funding target and to the regional pledge for the Congo Basin. Part of the funding is also anticipated to count towards the pledge totals for IPLC-related contributions. The cost profile shown below is tentative and the following assumptions have been made:
- The Business Case is fully approved by March 2024 and runs for 7 years.
- Negotiation on non-contract agreements for selected year 1 components starts as soon as the Business Case is approved, with mobilisation of agreements taking under 6 months.
- Detailed procurement planning for relevant components will start upon approval of the Business Case. TORs will be finalised and issued within 6 months. We expect procurement to take up to 12 months, followed by a 12-month inception period, so the programme will be fully operational by year 3.
- Component 3 CAFI spend will retain inherent flexibility to manoeuvre funds between other components, as well as between financial years. This is needed to remain adaptable to both UK and CAFI requirements, particularly as the current CAFI MoU expires in the FY25/26.
- Procurement for MEL component will be taken forward through GEMFA. We expect procurement to take 6-9 months, followed by a 6-month inception period, so the component would be operational from year 2 onwards.
- The costs of project funded staff would be fully charged to the programme, drawn from the budget of component 1. The cost of each role would depend on the position and location but is expected to be up to £200,000 per annum per post. Due process would be followed as per PrOF guidance, with agreement sought from the FCDO Chief of Staff.

Table 15 - CBFA Cost Profile (*spend is indicative & subject to change)
£ million	FY 24/25	FY 25/26	FY 26/27	FY 27/28	FY 28/29	FY 29/30	FY 30/31	TOTAL
Component 1 / Community Forests	0.2	0.5	5.3	10.0	10.0	10.0	9.0	45.0
Component 2 / FCDO Partners Facility	2.6	5.0	8.0	2.0	1.0	1.0	1.0	20.0
Component 3* / CAFI	0.0	0.0	4.0	4.0	4.0	4.0	4.0	20.0
Component 4 / MEL	0.0	0.8	0.8	0.8	0.8	0.8	1.0	5.0
Total	2.8	6.1	18.0	16.7	15.7	15.7	15.0	90.0
Project Funded Staff (within Component 1)	0.2	0.4	0.4	0.4	0.4	0.4	0.2	2.4

The Component 1 cost profile is based on an extended procurement and inception phase involving extensive co-design with local stakeholders, in line with the lessons learned from consultations in the region. This is also likely to be associated with lower disbursements in the early years. This will be followed by a delivery phase involving the extension of sub-grants, including to mobilise support for local communities. This component will also house the budget associated with two programme-funded positions based in each of the two established UK diplomatic missions in the region, in Yaoundé and Kinshasa. These are discussed further in the management case.

The Component 2 cost profile is based on providing support through grants to established partners in the region working with local communities, or on governance or relevant policy enabling environment issues, along with a small amount for the eventual tier 1 supplier as an intermediary. This is intended to deliver results during the longer inception period associated with Component 1, and it is anticipated that spend will taper off after year 3.

The Component 3 cost profile is indicative, and will depend on a review of UK and CAFI needs ahead of the MoU expiry on FY25/26. Flexibility is retained to a) alter the provisional £4m/year profile as required, both between years, and between components, e.g., should component 2 require additional funds, CBFA retains the right to oblige as needed. Similarly, CAFI funding may increase from other components should requirements necessitate, e.g., for any targeted intervention opportunities previously described. FCDO will make an assessment of CAFI needs and the value of UK contributions ahead of MoU expiry, and negotiate a new MoU if appropriate.

Component 4 includes an ongoing MEL contract, expected to make consistent payments throughout the life of the programme, although with a higher work rate at the baseline, midline and endline points. This is budgeted at approximately 5% of the overall programme budget.

All implementing partners will be required to submit annual budgeted work plans for FCDO approval containing detailed estimates for fees and reimbursable expenses, including disbursements to third party organisations. These will be followed by regular financial reporting containing details of historical spend, forecast spend and estimated total spend for the current financial year including an explanation for any marked deviations from expected spend. These will help FCDO to assess partners’ budget utilisation rates and to further inform our forecasting.

A rolling forecast, updated on a monthly basis, will be used to update projections and monitor their accuracy. We will not seek to earmark funding allocations to the component lines but will maintain flexibility for the SRO to approve the movement of funds between components depending on how well areas are performing and needs changing. The flexible design of the programme will allow FCDO posts (and possibly OGDs) to expand the programme where opportunities and demand for this arise.

### v. Financial Management, Monitoring, and Reporting

As set out in the Commercial Case, funding will be provided via a combination of contracts (anticipated for Component 1,2 & 4) and grants (anticipated for Components 2 and 3). Payments made in accordance with contracts will be based on milestones agreed within the terms of the service contract. Grant funding will be provided with no expectation of the supplier making a financial return, with eligible costs and a schedule of payments being outlined in the grant agreement.

Payment triggers will be defined and agreed as part of the contracts and non-contract agreements with selected suppliers. By default, programme funding will be paid to suppliers in arrears on a quarterly basis. If the supplier makes an exceptional request for an advance payment this will be considered on a case-by-case basis to ensure that it is not in ‘advance of need’ and represents good value for money. Payment claims from the supplier will be checked by FCDO programme team, and funds will only be released if sufficient evidence is provided. Disbursement requests will detail the funding needs, cash balance and liquidity position to avoid payment being made in advance of need. In accordance with any applicable terms in the contract or non-contract agreements, payment may be withheld in instances of failure to meet specific milestones.

As is standard practice for FCDO ODA programming, spend for CBFA will be monitored in line with the payment schedules agreed with suppliers using the established and robust programme management processes used within FCDO. An annual financial reporting regime will be established by FCDO, in consultation with the supplier, and funds managed by suppliers will be held in bank accounts that are tracked. Partners will report regularly to FCDO to account for how funds are being used. Tier 1 partners will need to provide audited financial reports, that separately identify FCDO funding, disbursements, and unspent financial resources.

Payments will be made through the FCDO payment system, so that they can only be made to registered suppliers. All forecast and actual payments will be recorded on FCDO systems so that progress can be monitored and payments to the programme can be easily separated out. FCDO accounts will be monitored to check transactions are actually made to suppliers.

Asset Management

All assets procured through programme funds will be tracked and monitored through asset registers held by each first-tier supplier/partner. Asset management will be in line with FCDO procedures and outlined in the relevant agreements with partners. How the assets are managed will differ depending on the delivery route. For example, where funding is part of a multi-donor fund FCDO will not have ownership of the assets and will provide steers on best practice rather than owning the decisions. Registers will be updated regularly and audited by the external audits and FCDO owned assets transferred or disposed of at the end of the programme according to usual FCDO rules and processes. Due diligence procedures will help enable FCDO to ensure partners have robust mechanisms in place for any asset management and disposal.

Assessment of Financial Risk and Fraud

FCDO has a zero-tolerance policy towards fraud and corruption, money laundering and the financing of terrorism. Delivery partners will take appropriate measures to prevent fraud and corruption in connection with the use of FCDO funding. This means adopting appropriate fiduciary and administrative practices and institutional arrangements to ensure that the funding from FCDO is used only for the purpose for which it was given. This will be managed by the MEL provider and an appropriate independent sub-contractor who shall closely monitor activities through regular engagement with delivery partners as per the standardised meetings outlined earlier in the management case.

FCDO is committed to the international fight against terrorism, and in particular, against the financing of terrorism. Delivery partners must comply with appropriate policies, procedures and controls such as: compliance with applicable national laws and regulations for anti-money laundering and combating the financing of terrorism; a written policy on anti-money laundering and combating financing of terrorism policy; appointment of an anti-money laundering and combating financing of terrorism officer; due diligence requirements; record keeping reporting of suspicious transactions; anti-money laundering and combating financing of terrorism training for all their staff.

Programme funding for contracts and grants will be paid in arrears, or under exceptional circumstances in advance, but not in advance of need, to ensure that disbursements are based on demonstrated need and avoid the build-up of unspent cash balances. Financial reporting and transparency requirements, as well as rigorous due diligence and auditing will help to mitigate the risk of corruption and fraud in the partnership and grants managed by suppliers. Regular in-person and remote monitoring will also help to identify risks and facilitate early corrective action. All beneficiaries of the programme will apply the standards and best practices required by FCDO. The FCDO’s requirements will be codified in agreements and contracts.

The overall financial and fraud risk is assessed to be Major. Based on experience we have identified the following risks and associated risk assessments:

- Procurement (Major) and supplier fraud at every level - Due diligence and monitoring reduce the risk of fraud in procurement of goods and services in the programme. Suppliers will be encouraged to report to FCDO any instances of fraud or potential fraud, in part to demonstrate that their monitoring systems are working.
- Risk at government level (Moderate) - No funding is expected to flow directly to government. The programme will abide by the Partnership Principles.
- Risk of under/overspend (Major) – this programme will deliver major spending components (1 & 2) through bilateral delivery, paying suppliers based on need. This means that any delays in activities due to unforeseen events cascade directly into FCDO’s payment schedule. Component 3 may benefit from the ability to time payments to a Trust Fund with greater predictability. Overall, forecasting is likely to remain a challenge throughout the programme, with particular difficulty in the early years. Monthly expenditure reports and forecasts, quarterly financial reports, and frequent meetings with partners will help mitigate the risk of large over or under spends of this programme.

If fraud is detected, FCDO will require full remedial action including repayment in full if the fraud involves diversion of UK funds. Continued disbursement of funds will be contingent on adequate financial oversight mechanisms.

Financial performance will be monitored through annual reviews and by financial audits to determine the accounting standards and practices put in place. Spot checks for FCDO owned assets and financial spot checks will be undertaken as appropriate, with financial checks dependent on the model being used. The team will also consider undertaking full follow the money exercises. The MEL supplier will work with the programme team to develop a VfM framework with specific metrics for each component and suppliers will be required to report against this every year.

## Management Case

Effective delivery of CBFA will be secured through establishment of external and internal management arrangements, ensuring public funding is utilised appropriately by contracted entities. FCDO has tried and tested programme management approaches, which will be employed to formulate and guide internal oversight and delivery. These will draw upon expertise across the department and beyond through clear governance arrangements throughout the lifecycle of the programme, whilst ensuring a robust MEL approach. Combined, these mechanisms afford CBFA the foundation and framework to underpin efficient management, help drive effective supplier & stakeholder engagement, allow for agile & dynamic programming, promote alignment between components, and ensure responsive risk management.

Comprehensive management approaches, including governance structures, should be established upon programme operationalisation, i.e., once contractual agreements are completed with suppliers. Interim internal structures will be stablished sooner to ensure the programme reaches this stage. In the case of CAFI, work will be carried out with support of current management structures under ARCAN, including our UK CAFI board member. To ensure agility in a changing operating environment, these approaches will retain some flexibility as the programme progresses. This will include the flexibility to hire projected funded staff, with two anticipated to be recruited to support component delivery, most based in both BHC Yaoundé and BE Kinshasa.

### i. Governance Approaches & Objectives

CBFA must be equipped with an appropriate level of flexibility to adjust its resources and activities in response to changing contextual factors. Particularly in Component 1, where a flexible approach to design, delivery, management, and monitoring is essential. This is due to a) beneficiary demands of co-designed and co-owned solutions, b) limited evidence on how best to support beneficiaries at the intended scale, and c) a necessity to adapt programme strategies to the complex political economy of countries across Congo Basin.

Components 2 and 3 build on tested delivery models through existing partners where interventions are likely to be built on a stronger evidence base, but lessons from previous regional programming continue to emphasise the importance of adapting and responding to developments in dynamic forest landscapes.

For CBFA’s MEL component (4), appropriate flexibility remains key in adapting to the rapidly changing landscape across the region. Programme delivery and management should incorporate deliberate processes of testing and learning. This will allow for necessary changes to activities based on evidence, evolving priorities, feedback from beneficiaries and stakeholders, and emerging needs.

Governance Objectives

CBFA governance objectives and approaches will encompass a diverse range of functions aimed at supporting, funding, and delivering various interventions, notably:

- Providing grassroots support, capacity building, and technical assistance to local communities in unprotected frontier forest zones across the Congo Basin.
- Enhancing the enabling conditions for local communities to move towards more sustainable practices related to agriculture, agroforestry, and forestry.
- Ensuring interventions are effectively co-designed with local stakeholders to enable co-ownership and thus lasting impact.
- Empowering and protecting the most vulnerable and marginalised within communities, including women and girls, the disabled, and indigenous peoples.
- Acquiring initial and lasting government buy-in to secure long-term domestic support for interventions beyond programme timeframe.
- Supporting trusted partners already delivering successful interventions, allowing effective scaling of efforts, and initiation of new projects.
- Remaining flexible and responsive to unsolicited proposals to ensure opportunities are capitalised on across the region.

In delivering these objectives, CBFA should embrace continuous learning throughout each component to effectively address the challenges and changing circumstances to support smallholder farmers and achieve its objectives in the dynamic forest landscapes of the Congo Basin countries.

### ii. Governance Structure, Roles & Responsibilities

CBFA will see the majority of its efforts delivered through outsourced management approaches to ensure resourcing and expertise meet the programme's level of ambition. FCDO will set up the below structure set out in figure 9 to effectively manage the programme internally and interface with external delivery partners:
Figure 8 - CBFA Management Structure

Internal FCDO

The internal management team outlined above will be responsible for critical functions that will ensure successful delivery of the programme, including overseeing the entire programme development process; decision-making on and administration of component 1 and 2 activities including procurement; strategic direction of component 3 funding where appropriate; management of delivery partners, and programme assessment via MEL. The figure here articulates the expectations for a steady state, recognising that at the initial phases of the programme, demands will be higher, while the projected funded positions may take time to fill. Engagement on CBFA will need to be reconciled against APEX resource, but the expectation is that there will be more resource provided in Year 1, including support to the SRO from the relevant Team Leader. The CBFA team will work closely with the ARCAN team to manage the UK's contribution to CAFI, and the UK Board member will remain the main focal point for the UK's strategic engagement with CAFI.

Two programme funded posts will be created by CBFA, based on Kinshasa and Yaoundé. This was determined to be the best approach through an appropriate VfM analysis, indicating that effective delivery of locally orientated interventions would be best overseen through FCDO staff based in the region.

Routine management tasks will also fall under the team's purview, including regular financial forecasting, results monitoring, risk monitoring and preparation of Annual Reviews. The team will maintain strict compliance with the PrOF rules and establish effective communication with BE Kinshasa, BHC Yaoundé, and UK staff. This will also ensure continuous alignment with other HMG programming in the region, enabling capitalisation on opportunities for efficiency savings and complementarity where possible.

Component lead responsibilities will be delivered by the two project funded staff, sharing efforts based on the geographies of interventions within components. The PRO, PM, and advisory roles will be sourced from APEX.

Delivery Partners

The primary responsibility for delivery of CBFA's outputs lies with contracted Tier 1 suppliers, whose plans and actions must adhere to the specified contractual terms, whilst aligning with CBFA’s Theory of Change and logframe. Within the framework provided by the contracts and grants, the suppliers have the freedom to deliver outputs in the manner they and their local partners deem most effective.

To achieve successful delivery, Tier 1 suppliers will establish internal governance, capacity, and processes that facilitate a flexible approach, learning from experience and making necessary adjustments as required. It is essential to the design of the CBFA programme that the MEL Component has an effective, efficient and cooperative arrangement with the other tier 1 partners. Accordingly, the MEL Component will be represented at the different levels of programme governance.

These suppliers are accountable for ensuring compliance with FCDO's financial and management requirements, both for themselves and their downstream suppliers. They must manage risks and finances effectively, provide regular and comprehensive reporting to the FCDO team, and adhere to FCDO's safeguarding requirements.

Component Decision-making

Each component varies in terms of how FCDO will engage in decision-making processes related to process and delivery of outcomes:

  1. Component 1 will be managed by a Tier 1 supplier via consortium approach. This supplier will be sourced through competitive tender. Commercial TORs and contractual terms will provide details on who, how and when decision making takes place which will be managed by the FCDO with the aim to protect beneficiaries from economic losses. Responsibilities include disbursement of ringfenced funding, selection & management of downstream delivery partners, and reporting to FCDO. Key strategic decisions will be made by the FCDO internal team. This would include, for example, a potential role for FCDO in the selection of downstream partners and projects – for example a formal ‘no objection’. The MEL Component should sit in advisory capacity within these governance structures.

  1. Component 2 will be managed by a Tier 1 supplier once procured, and by the FCDO internal management team during the interim. This will be in line with agreed contractual modality which may include Accountable Grants and MOUs as relevant. The breakdown of funds under the component has not yet been decided but is likely to be delivered via FCDO’s framework, partner facility or INGO/NGO’s delivering in the region. Identified implementing partners will be responsible for managing downstream partner, provide FCDO with relevant assurances on enhanced due diligence and progress/results reporting. As with component 2, the MEL Component should sit in advisory capacity within these governance structures.

  1. Component 3 will effectively be co-managed with CAFI and the UK Board Member, liaising with the CBFA and ARCAN teams. FCDO will retain capacity to determine how ringfenced funding is spent, i.e., on specific project activities within CAFI's scope, with appropriate consideration of CAFI Executive Board processes in which the UK participates. This process would be kept under the singular FCDO agreement with CAFI. Internal disagreements will be escalated within APEX appropriate, e.g. decisions on suitability of a proposed intervention which the UK could fund. For reference, the CAFI overarching governance structure is detailed in figure 9 below.

  1. Component 4 will be managed by a Tier 1 supplier who is independent of the other components and specialises in Monitoring, Evaluation and Learning. The Advisory Steering Group will group will be the forum to set the direction for the MEL Component, with a focus on refining the overall purpose and objectives and resolving bottlenecks to delivery.

UK Membership
ARCAN
CBFA
Figure 9 - CAFI Governance Structure

The FCDO team will strive wherever practical to delegate decision-making authority to the suppliers across programme components. Empowering the suppliers to make prompt and appropriate decisions is essential for the successful implementation of flexible programme approaches. This approach aims to avoid unnecessary delays caused by having to seek FCDO permissions for every decision. The objective is to ensure that passing management responsibilities to implementing partners leads to tangible gains, rather than burdening them with excessive oversight requirements.

This approach relies on fostering trust and open communication between FCDO and the suppliers, aligning objectives for a shared understanding of CBFA's goals. Comprehensive recording of decisions and the underlying reasons will be a fundamental aspect of this collaborative process. By embracing this approach, FCDO aims to promote a more efficient and agile program implementation, where suppliers have the autonomy to act in accordance with CBFA's goals and adapt swiftly to changing circumstances.

### iii. Management Arrangements

CBFA will be managed by Africa Programmes & Expertise (APEX) within the Africa Directorate of FCDO. The Central Africa team within APEX will work closely with colleagues in the International Forests Unit and broader FCDO Energy, Climate and Environment (ECED) directorate teams, alongside key Other Government Departments like Defra and DESNZ to ensure expertise is effectively utilised. The programme will also draw on expertise from the two FCDO Posts across the Congo Basin, the British Embassy in Kinshasa, and the British High Commission in Yaoundé. A feedback loop will be established with relevant teams to ensure reciprocal, iterative learning, development of trust, and to maximise complementarity with existing activities.

Given CBFA will strive for agile flexibility, programme management is expected to be resource intensive. Component 1 will undergo a competitive tendering process in Year 1 (including EME, TOR drafting and launching an open procurement process in year 1), followed by bringing on board a lead implementing agency that will manage and implement the delivery through outer years; in Year 1, Component 2 will undergo procurement for a supplier in parallel to mobilisation by the FCDO team. Component 3 will undergo rapid mobilisation in year 1 given the nature of grants and financial execution. These will likely to be resource intensive in year 1 and 2 (TORs, selection of partner and agreeing deliverables and management structures in year 1); Component 4 will be delivered via a GEMFA framework, allowing for a faster procurement but will require close engagement with the FCDO programme team to ensure the MEL facility remains relevant to delivering the programmes results framework and TOC. A need is anticipated for more frequent engagement with Tier 1 suppliers to ensure augmentation and adaptations are conducted rapidly based on progress and real-time MEL.

As detailed in Figure 9, the FCDO internal management team will draw on a broad range of individuals with varying degrees of time commitment to the programme. The Senior Responsible Officer (SRO) will be responsible and accountable for CBFA overall, whilst the Programme Responsible Officer (PRO) will ensure day-to-day processes are delivered. A Programme Manager will drive forward commercial, financial, and management aspects of the programme. Each component will have a lead through programme-funded posts, supported by various FCDO specialists at the Department or Directorate level, including input from economists and MEL advisers.

Regular and clear communication between the SRO and PRO will ensure any encountered issues which may threaten programme feasibility or risk breaching risk tolerances and value for money thresholds are appropriately escalated. The PRO will maintain close relationships with component leads and identify such issues before reporting to the SRO, who will be responsible for escalating where necessary to Africa Directorate seniors.

Regular and clear communication between the CBFA and ARCAN SROs through established steering group meetings to ensure consistency and alignment approaches with respect to CAFI funding.

Management of Suppliers

Tier 1 Suppliers within CBFA will be managed through standard FCDO processes. Following PrOF guidance, the FCDO management team will document their management activities using the AMP platform to keep risk identification, financial management, and monitoring data up-to-date. During the inception and delivery phases, management arrangements will be refined to ensure effective oversight and collaboration between FCDO teams and suppliers, realised through the following prospective mechanisms:

- Monthly programme management meetings covering each component.
- Monthly technical meetings to address and resolve delivery challenges.
- Monthly senior management meetings covering grant approvals, risk management, and escalation.
- Monthly meetings of component leads to ensure alignment and complementarity.
- Quarterly meetings to cover strategic direction and effective planning.
- At least annual field trips to project sites for monitoring and real-time evaluation.
- Annual meetings with key partners, including suppliers and beneficiaries to review challenges and progress.
- Annual comprehensive team meetings to support delivery planning, training, and strategic development.

As CBFA progresses, there may be a need to establish coordination and governance mechanisms to align UK climate and nature programming across the Congo Basin. The FCDO management team will engage with relevant teams and established governance mechanisms to drive alignment between CBFA activities and broader UK efforts across the region.

### iv. Programme Inception, Mobilisation, and Operations

Once the CBFA Business Case is approved, the programme will be mobilised as per timelines established in the Financial Case. Given that each component varies in its delivery mechanism and design approach, some activities will be able to commence soon after programme inception, whilst others will take time to develop and initiate.

Component 1 is the most significant element of the programme, requiring a full tendering exercise, alongside co-design of activities with stakeholders. Combined, these processes form the mobilisation and inception phases, and are expected to take up to 24 months, with the co-design requiring approximately 12 months to allow for a comprehensive and inclusive process. Efforts will be made to ensure the tendering process is as efficient as possible to reduce timescales prior to inception and implementation. The operational phase will run for the remainder of the programme.

Component 2 enables the funding of trusted partners with an established presence across the Congo Basin and successful track records on delivery. It will also provide a facility to receive unsolicited proposals from across the region to foster an agile and responsive programmatic approach that has the capacity to quickly fund opportunities and 'low hanging fruit'. This is expected to take 3-6 months to mobilise, followed by disbursements to identified partners within the first year of the programme, overseen by the FCDO team whilst a Tier 1 Supplier is procured.

Component 3 capitalises on the regional importance and influence of CAFI, channelling UK funding into the institution, which can be ringfenced if appropriate, for preferred activities that are already in design and pertinent to CBFA.

Component 4 will be fulfilled through a competitive tender process and will run for the entirety of the programme, ensuring Monitoring, Evaluation and Learning is carried out across the three other components, whilst maintaining independence from each to avoid conflicts of interest. The mobilisation phase to assign a supplier will take around 6 months.

Stakeholder Engagement

The CBFA Business Case has been a collaborative effort by various experts from teams across FCDO and OGDs, building on significant experience in the field through design and implementation of previous relevant programming. Alongside internal lesson sharing, the CBFA Business Case has been developed after significant consultations with stakeholders across the region, including other donors, national and local governments, NGOs, civil society, and IPLCs. This has enabled a programme design which builds on and scales previous successes such as ILLUCBF whilst addressing historic failures through innovative, co-designed solutions.

For Component 1, identification and selection of priority local geographies and political economy analyses for each Congo Basin country will be handled by the Tier 1 supplier. These activities will enable the supplier and FCDO to make an informed decision on where and how to intervene. The supplier will then conduct Early Market Engagement (EME) as part of the co-design aspect, enabling more effective and receptive interventions that are more likely to endure beyond the programming lifecycle.

Component 2 geographies will be led by preferred partner and unsolicited proposal localities, and appraised by FCDO and the Tier 1 Supplier on a case-by-case basis. Rapid stakeholder engagement will be conducted for each robust proposal to identify and challenge any concerns from prospective beneficiaries and safeguard against fiduciary risk. Component 3 geographies will be led by CAFI indicative pipelining, with FCDO retaining oversight and decision-making. The CAFI Executive Board will constitute the primary appraisal governance for such activities.

Monitoring, Evaluation, and Learning

CBFA recognises the critical importance of MEL activities and will make a significant investment through component 4. Component 4 will work efficiently and effectively the FCDO team and the tier 1 suppliers for components 1 and 2 in particular to deliver a programme-wide MEL approach that meets the programmes needs for accountability, for ex ante analysis and ongoing learning in respect of programme interventions, and for the accumulation, analysis and communication of evidence to support broader current and planned UK efforts across the region, contributing towards a limited but growing evidence base on grassroots interventions for local communities related to primary deforestation drivers, which are unique to the Congo Basin compared to other major tropical basins globally.

The programme level MEL framework and plan will be completed once an appropriate component 4 supplier is selected. It will outline necessary approaches for three interwoven strands of work relating to verification of partner reporting, ongoing analysis and appraisal of programme interventions and a longer-term programme-level evaluation. The Tier 1 Suppliers for components 1 and 2 will hold responsibility for monitoring and reporting progress against the MEL framework, with the overall MEL Supplier appraising and evaluating these accordingly. Component 3 will follow CAFI's MEL approaches.

Tier 1 suppliers will be expected to develop appropriate mechanisms for collecting data and evidence. This will include sourcing and using feedback from the beneficiaries of CBFA interventions, and the possibility of using satellite imagery to understand changes in land use., Data will be collected from households, smallholders, other landholders, and relevant landscape and policy stakeholders and inclusive approaches to data collection, analysis and implementation of recommendations will be prioritised.
Exit Strategy

Achieving an enduring legacy will be dependent on CBFA's ability to effectively utilise public funds to drive grassroots behavioural change within local, forest-dependent communities. This is not achievable solely within a 7-year programme timeframe, and must be considered as part of a broader, long-term, sustained intervention in collaboration with other UK programming, international donors and the private sector.

Horizon-scanning will be conducted to identify opportunities within these stakeholder groups for continuation of interventions beyond CBFA's lifecycle. Partners supported through Component 2 may provide an appropriate conduit to continue the novel approaches and outputs delivered by Component 1. CAFI will remain a core regional body through which to deliver interventions and can provide continuity for elements of CBFA programming if deemed appropriate by the CAFI Executive Board. Alignment with other donor bilateral activities across the Congo Basin will be examined to identify potential sequencing and pipelining. Depending on the formulation of each component's activities, scope for private sector involvement and continuation may be an option, although this might be limited given the limited profitability of the prospective grassroots activities.

### v. Risk Management

The Congo Basin has historically been a high-risk region for climate and nature programming. Any interventions by CBFA must be carried out with robust and effective safeguards in place, but these efforts must not detract from or debilitate programme permeance, particularly given the ramifications from recent overly cautious efforts, i.e. slowed disbursement & action, the resulting frustration from the region, and a reduction in donor trust – which is key to programmatic effectiveness.

Given this, CBFA has been designed to ensure responsiveness to risk through taking a portfolio approach. The co-design approach of component 1, combined with the flexible nature of component 2 alongside anticipated trusted partners and an established channel through CAFI in component 3, enables the programme to spread risk across the delivery portfolio. This will enable CBFA to seize opportunities that arise from the region whilst keeping a handle on fiduciary and reputational risk.

Risk will be managed by applying standard FCDO practice with respect to risk registers and appetite. The risk register will be kept up to date, through at least quarterly review by the programme team, as well as through ongoing engagement with delivery partners as a regular (at least quarterly) standing agenda item for discussion. Any risks that extend beyond the risk appetite at the programme level will be escalated above the programme SRO as part of the departmental risk escalation process.

To align with FCDO’s new risk management approach, CBFA’s overall risk appetite across the seven categories is as follows:

Table 16 - CBFA Risk Category Ratings
Risk Area	Rating
Strategy & Context	Receptive (Major)
Policy & Programme Delivery	Receptive (Major)
Public Service Delivery & Operations	Cautious (Moderate)
People	Receptive (Major)
Financial & Fiduciary	Receptive (Major)
Safeguarding	Cautious (Moderate)
Reputational	Cautious (Moderate)

CBFA is the only UK climate & nature programme exclusively operating in the Congo Basin. To operate effectively in a challenging environment, it will have a higher risk appetite than comparative global programming, as highlighted by categorisation of Strategy and Context, Policy and Programme Delivery, People, and Financial & Fiduciary risks. The higher risk appetite across these categories will allow for a more tolerant threshold across the programme portfolio. CBFA will achieve a balanced delivery approach through offsetting any potential severe risks given components 2 and 3 are expected to be lower risk overall.

Areas of concern are related to generally unstable operating environments in certain regions of the Congo Basin, alongside severe fiduciary risks, poor governance, and limited access to potential sites of intervention. Component 1 carries the heaviest burden given its novel approach and objective of co-ownership with local, national and regional stakeholders. Tier 1 suppliers across the portfolio will be rigorously examined through a due diligence process to confirm they can deliver, whilst remaining aligned with FCDO policies. This includes capacity to manage and escalate risks in a timely and effective manner where necessary to allow for rapid treatment.

Whilst Tier 1 suppliers will retain the majority of responsibilities regarding risk management, the FCDO team will provide oversight and guidance for the management and treatment of risks where needed. The PRO and component leads will work with the suppliers to manage the AMP-based risk register, escalating to the SRO where necessary. Broader risks that extend beyond the programme, e.g. interaction with other programming, political and socio-economic challenges etc. will be discussed during biannual dedicated sessions which will complement the Annual Review cycle. If necessary, risks will be escalated to senior officials and ministers as appropriate.

The programme Summary Risk Register can be found below in table 13. This risk register rates the residual risks after mitigation steps have been taken, although it retains reference to those sufficiently well mitigated to have moderate or minor residual risk. The overall residual risk (overall net risk rating) for CBFA is ‘Major’.

Category	Risk Description (cause, event, consequence)	Mitigation Strategy	Risk
Strategy and Context	Unexpected changes in the political economy landscape, including increased conflict or social disturbances affect the ability of the programme to operate	Programme to work with Posts in the region to monitor political and other relevant strategic context factors, mitigating where possible. Duty of care to be emphasised for individuals involved in programme implementation activities. Threat of programme withdrawal should public officials, armies or militias be found to be undermining the benefits of CBFA.	Major
Safeguarding	Programme complexity and geographic spread make it difficult to fully assess safeguarding risks, and there is a failure to prevent a safeguarding incident	Ensure FCDO safeguarding policies are regularly reported on by implementing partners. Ensure safe whistleblowing line in place for downstream partners and consider building in beneficiary feedback mechanisms during the design stage	Major
Financial and Fiduciary	High fiduciary risk context and insufficient control leads to ineligible expenses, aid diversion or fraud taking place with programme resources	Programme team will prioritise management of fiduciary risks, cascading policy to partners in the delivery chain, and emphasising the importance of effective controls. A zero-tolerance approach is taken to identified instances of fraud.	Major
Reputational	Difficulties in scaling the programme in a timely manner, driven by budget constraints, operational delays or other factors, affects ability of the programme to help the UK achieve COP26 & COP27 commitments	Early stages of the programme to be effectively staffed internally, with components targeted at timely mobilisation. Programme Team to ensure good communication is maintained with all relevant internal stakeholders on programme spend, timeframes and COP/climate commitments	Major
Policy and Programme Delivery	Programme activities fail to engender sufficient local ownership to deliver last effect, e.g., not succeeding in including and partnering with Indigenous people and local communities, women and other marginalized groups, in addition to host governments	The programme design is strongly based on a co-design with communities approach - the terms of reference for the tendering process will require suppliers to drive inclusion in the programme	Major
Policy and Programme Delivery	Innovative tools such as PES that the programme invests in are not fit for purpose for the CB region, or contextual factors slow or prevent their successful application	The programme takes a proportionate approach to spending on high-risk activities; the programme TOR's to be built on design and build approach, allowing sufficient time to test approaches prior to scaling/ceasing.	Major
Policy and Programme Delivery	Large programme delivered by multiple partners affects data quality, access, and monitoring.	Ensure management expectations are clearly articulated in the terms of reference for the tendering process; Build in management related KPIs/or other partner assurances on sufficient management resources through the course of the programme; ensure all partners share data with the MEL partner.	Major
People	Insufficient central FCDO staff capacity to manage programme effectively., particularly on commercial and procurement expertise.	Ensure minimum staff requirement set out in BC are factored into future work force planning. Identify contingency plans (drawing support from OpEx & Commercial) if staff resources and/or governance arrangements as designed in BC are reduced or insufficient for the needs of the programme.	Moderate
Policy and Programme Delivery	Risk of poor coordination with relevant HMG forest and climate stakeholders at HQ and Post, leading to potential duplication & misalignment of efforts in the CB region, especially on programming.	The programme team will ensure good coordination with all other relevant central Africa efforts (has done through the design phase regarding programming alignment); the management case of CBFA includes a robust governance structure that will ensure good coherence with other efforts to avoid duplication, particularly on programming.	Minor

## Annexes

### i. Annex A – ILLUCBF PCR Lessons

The programme demonstrated the importance of taking a multi-pronged approach, working to strengthen:
- Community Forest legal standing;
- community, enterprise and government capacity and
- enabling policy environments.

Recommendation: this multi-pronged approach to be central to future community forest programme design.

Programme success relied on building strong coalitions of partners to benefit from diverse capacities and build platforms to advocate for legal and policy changes (IIED had 18 partners in 5 countries; RFUK had 4 main partners plus others; ICRAF had 4 local partners). This took strong leadership from lead partners to ensure common vision, capacity, coordination and reporting. Recommendation: Consortiums of partners with strong leads to be prioritised to deliver future similar programmes. Consortiums need to share a collective vision.

Synergies between the three components could have been stronger. Each component focused on a different approach to supporting CF’s. The overall programme theory of change and logframe were developed in consultation with implementing partners (IPs) and designed to support coordination, but IP’s reported against their individual logframes without reference to the overall programme logframe. A learning event involving all three components was appreciated but came late in the programme. Recommendation: Future multi-partner programmes should seek stronger ownership by IP’s of programme overall logframe including a requirement to report against the indicators in the overall logframe, establish joint governance structures with regular, scheduled coordination opportunities and support and incentives to coordinate e.g. indicators to measure joint working.

Progress towards gender equality and inclusion of indigenous groups was achieved but there is still far to go. Recommendation: Include equity issues from the beginning of the planning and design stages and resource implementation (dedicated gender expertise, best practices and tools, monitor throughout the project cycle.)

Value for money metrics were introduced late in the programme. Despite this, partners have undertaken analysis which demonstrate the VfM of the three components and provide a benchmark for other programmes. Recommendation: Future forestry programmes to build on the VfM work of ILLUCBF and establish VfM metrics from the outset.

A longer time frame was needed to maximise results and ensure sustainability (as foreseen in the business case which envisioned a second phase of the programme). Achieving rights to CF’s is an important step but supporting communities and enterprises to develop simple management plans, and access new markets and finance is needed for scale and sustainability. Recommendation: FCDO to continue to promote evidence and best practice from the programme with other HMG forestry programmes, other donors and CAFI to encourage ongoing support to CF’s.

The removal of the Monitoring, Evaluation and Learning component and programme funded adviser affected the programmes ability to support coordination between components and develop and share an evidence base to advocate for CF’s. Recommendation: Decisions on removing components should be informed by an analysis of the function of those components and alternatives to deliver these functions considered e.g. increased FCDO staff capacity or increased MEL resources to IP’s. IP’s should be required to report against FCDO logframe indicators.

The need to integrate CF interventions into broader forest & land use planning / landscape approaches to achieve scale, manage competing land use objectives (e.g. logging, agriculture, mining, conservation) and build on existing capacities e.g. farmer organisations. Recommendation: this lesson to be considered in future programme design.

### ii. Annex B – Climate & Environment Risk Screening

Risk Screening Tool
General Programme Identification / 1. Date: 11 October 2022 / 2. Country & Programme Title: Congo Basin Forest Action (CBFA) Programme, Congo Basin (Gabon, Cameroon, RoC, DRC) – Forests and Climate / 3. Lending or financing Modality: FCDO / 4. Department & Division: Africa Programmes & Expertise Department (APEX)
Climate screening factors	Supporting information	Score 0-3	Remarks
Exposure, vulnerability, and hazards
1. Which physical environment best describes the area the programme is taking place in?	See Table 1: Physical environment exposure zone examples.	1 + 2	Congo Basin: Humid, river valleys
2. What sectoral vulnerabilities can be identified?	See Table 2: Vulnerabilities by sector. / Consider the impact of these vulnerabilities both on the programme, and the potential for the programme to exacerbate these vulnerabilities.	3	Impacts on crop production from precip changes Changes in diversity Large scale climate drivers: ocean currents, ENSO Water availability and quality Changes in vector and water borne disease Impacts on resources extraction Multi-sector SMEs vulnerability
3. What relevant individual hazards can be identified?	See Table 3: List of hazards. / Add 1 for each natural hazard (up to a maximum of 4). If hazards are unknown use 3 as a risk value.	4	Flood Extreme temperature Heat wave Infectious disease Landslide Forest fire
4. Estimate the number of people potentially “exposed” to climate-related risks?	<100 score = 0 / 100-1000 score = 1 / 1000-10,000 = 2 / >10,000 score = 3	3
If the TOTAL value for the first 4 questions sums to 4 or less there is no need to complete the remaining questions. You will not be required to complete any further scoping or full CRAA. / The total value for the Climate Screening Factors = 13, so a CRAA has been completed.
Stakeholder engagement and adaptation support
5. Does the programme have the institutional capacity to successfully incorporate, manage and deliver climate risk management measures?	Yes/No / Yes, good capacity = 0 / No, poor capacity = 1 / Very poor capacity = 2	0	Yes, explicit element on stakeholder engagement and capacity building with forest protection as focus
6. Will potential hazards impact on communities, gender, people with disabilities or indigenous peoples?	Yes/No / Yes = 0 / No / Unsure = 1	0
7. Are there any demographic or socio-economic variables (i.e., population increase, settlement patterns, bio-physical/environmental conditions) that may increase exposure to hazard impacts?	Yes/No / Yes / Unsure = 1 / No = 0	1
8. Is it likely that the delivery/implementing partner has some practical knowledge of climate risk reduction measures for the programme?	Yes/No / Yes = 0 / No / Unsure = 1	0	Regional Hub: FCDO country offices with access to C+E advisors National Working Groups: Reputable NGO in each country should have practical knowledge of climate risk mgmt.
9. Will the programme reduce, leave unaltered, or increase the risk to project beneficiaries?	Reduce = 0 / Unaltered = 1 / Increase = 2	0	Objective of programme is to reduce risks.
10. Will the programme reduce, leave unaltered, or increase the risk to the localized environment/project dependent ecosystem?	Reduce = 0 / Unaltered = 1 / Increase = 2	0	Objective of programme is to reduce risks.
11. Will the programme improve or provide opportunities to increase adaptive capacity through any of the programme elements?	See Table 4: Adaptive Capacity. / Yes / No / Yes = 0 / No / Unsure = 1	0	Programme aims to increase institutional/gov collaboration There is significant (£90m) resources available to programme / Knowledge and information: this is a risk as in-country ‘human capital’ may be limited/is unknown.
12. Do country/institutional policies or climate laws significantly promote climate risk management measures?	Yes/No / Yes = 0 / No / Unsure = 1	1	This is recognised as a risk in the CANCAN BC.
13. Does the programme require a risk expert to introduce risk reduction measures in project design, implementation, or operations and maintenance?	Yes/No / Yes / Unsure = 1 or 2 (based on assessment of the level of risk) / No = 0	1
Total Risk Value (Range 0 to 25)	Severe Risk: 21-25 Major Risk: 15-20 Moderate Risk: 8-14 Low Risk: 0-7	16	State: Major / Severe, major, moderate or low
Low Risk (0-7): This range indicates the programme is either very low risk, or the proposal has considered risk management measures to minimize hazard impacts and associated risks, and that the programme may therefore have a potentially higher threshold against current and anticipated risks.
Moderate Risk (8-14): Climate related risks could possibly impact on the programme success, and at least light touch risk reduction measures should be incorporated into project design and activities.
Major Risk (15-20): Climate related risks could significantly impact on the programme success, and risk reduction measures should be incorporated into project design and activities.
Severe Risk (21-25): Climate related risks are likely to derail the programme. It is highly recommended that risk reduction measures be incorporated into programme design and activities, and that a further review of the programme proposal be undertaken. At this level of risk, consideration of the suitability of undertaking this programming activity at all should be given.
Environmental screening factors	Supporting information	Score 0-3	Remarks
Safeguarding and protection
1. Will your programme exacerbate risk to any of the five safeguarding categories?	See Table 5: Environmental Risks and Safeguarding. / Yes/No / Yes / Unsure = 1 / No = 0	0	Programme aims to protect forests, reducing air and water pollution, land degradation from extractive industries, and protecting biodiversity and water resources.
2. Will the programme include any measures or safeguards to mitigate against these risks?	See Table 5: Environmental Risks and Safeguarding. / Yes/No / Yes = 0 / No / Unsure = 1	0	The programme in itself is designed to safeguard against these risks.
3. Will the programme be operating in or near critical habitats?	Yes/No / Yes = 2 / Unsure = 1 / No = 0	2	Congo Basin
4. Will the programme consider opportunities to enhance the environment through your programme?	Yes/No / Yes = 0 / No / Unsure = 1	0	One objective of the programme is to strengthen sustainable environmental land mgmt. practices and reduce forest loss.
5. Will the programme go against a country’s biodiversity strategy or plans?	Yes/No / Yes / Unsure = 1 / No = 0	1
If the TOTAL value for the first 4 questions sums to 3 or less there is no need to complete the remaining questions. You will not be required to complete any further scoping or full EIA The total value for the Environmental Screening Factors = 3 so the remaining questions have not been completed and thus removed.
[note] Brooks, N. and Adger, N. (2004). Adaptive capacity refers to the ability of a system to adjust, modify or change its characteristics or actions to moderate potential damage, take advantage of opportunities, or cope with the consequences of shock or stress. https://www.unisdr.org/files/7995_APF.pdf#page=170

## References