## Annual Review Template

Title: Congo Basin Forest Action Programme (CBFA)
Programme Value £ (full life): 90,000,000		Review date: / 19/08/2025
Programme Code: 301464	AMP start date: / 19/08/2024	AMP end date: / 31/03/2031

Summary of Programme Performance
Year	2024-25
Overall Output Score	B
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0005764.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006855.xlsx

A. SUMMARY AND OVERVIEW
The Congo Basin Forest Action (CBFA) Programme is a £90 million, 7-year FCDO programme aiming to reduce deforestation and improve livelihoods for local communities in the Congo Basin by supporting sustainable forest and land management and reinforcing scientific capabilities. Headline ambitions including supporting improved management of up to 2 million hectares of forest, securing or strengthening land and resource rights for at least 100,000 people, and contributing to the reduction of greenhouse gas emissions in line with UK International Climate Finance commitments.

Summary supporting narrative for the overall score in this review
This annual review will only cover the mobilisation of the programme following approval in July 2024 until the end of July 2025. During this period two grants were implementing from November 2024 onwards:
- Yangambi Landscape project through the Center for International Forestry Research and World Agroforestry (CIFOR-ICRAF); and
- Congo Rainforest Alliance for Forest Training (CRAFT) for Sustainable Development through the University of Leeds within the Congo Basin Science Initiative.

Mobilisation of the commercial components of the project have faced delays with the commercial process and face a pause due to the ODA reduction to 0.3GNI which is why the programme has scored a B.

Major lessons and recommendations for the year ahead
Recognising that the main procurement process would be lengthy—and has taken even longer than anticipated—the Business Case included a provision to review unsolicited proposals. These proposals were assessed, and two were promptly mobilised, enabling the programme to begin delivering support while the formal procurement was still underway. This mixed procurement approach has been beneficial and should be considered in other similar programmes.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Since the publication of the Business Case, Component 3 has been removed, with the extra £20m reallocated to the FCDO Partners Facility, doubling this to £40m. This was done as the two major accountable grants being funded totalled £17.1m, i.e. already consuming the bulk of the original £20m allocated. The UK will continue any support for the Central African Forests Initiative via the FCDO ARCAN programme.
Beyond this change, Component 1 and 2 have also been commercially merged into a singular tender to ensure a more efficient and joined-up supplier management process moving forward.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? The programme is currently in its mobilisation phase. It is anticipated once all outputs are operational the programme will begin to generate evidence that it is contributing to the expected outcomes and impact.

Although it may be too early to confirm whether CBFA is on course to deliver against the expected programme impacts, the programme has been contributing towards reducing deforestation in the Congo Basin, and improving economic outcomes for forest dependent communities. This is evidenced by the ongoing support for the Yangambi landscape, which has driven forward more sustainable practices through knowledge development, technical assistance, and capacity building, including, training 1,200 farmers; awarding 49 scholarships to those in the local community (all women); a significant increase in crop yields, and 9,000 sustainable cookstoves sold – all culminating in reducing pressure on the surrounding forests, driving behavioural change in the long term, avoiding ecosystem loss, and reducing emissions. . The year ahead includes the six-month Inception Phase for C1A ‘Forests for Local Communities’, and the first six months of the Implementation Phase. This will enable a much broader piloting of the systems approach within geographic landscapes, and so will provide a robust testing of progress towards CBFA impacts and outcomes across the programme's entirety.

Overall, the ability to deliver these outcomes at the scale set out in the business case is dependent on retention of full funding for CBFA. Should the programme experience any cuts to its multiyear budget, this will likely result in a reduction of impact magnitude, through both C1A and C1B.

Thus far, there are no unexpected outcomes emerging, with outputs remaining well orientated towards local communities, national and regional capacity building, and development of knowledge per the theory of change – validated by the activities within both accountable grants underway.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The CBFA Programme represents the UK’s singular largest investment in forests, nature, and sustainable development in the Congo Basin. The results already achieved for the two active projects, within the first 12 months of operation, are a strong indication of the positive trajectory the programme should expect to follow in the coming years once all components are operational. The focal areas of direct and consultative support to local communities as the primary drivers of deforestation has already demonstrated results through the Yangambi landscape, and the VfM of building locally-led scientific capacity has provided significant strategic and diplomatic capital, alongside setting precedent in the region on reducing dependencies on western institutions. These efforts will be significantly expanded and reinforced as the primary contract comes online.

CBFA is central to the FCDO strategy for the Congo Basin, complementing two other significant centrally managed programmes by providing a focus on local communities in parallel to efforts on governance and the private sector, provided by FGMC (Forest Governance, Markets and Climate Programme) and IFSLU (Investments in Forest and Sustainable Land Use) respectively. UK convening and influencing efforts are well augmented by these funds on the ground, and demonstrate tangible action, building trust with the region ahead of COP30.
[note] IFSLU Phase 2: DevTracker Programme GB-GOV-1-301321
[note] 30th Conference of the Parties, UN Conference on Climate Change

## C. DETAILED OUTPUT SCORING

Output Title	Mobilisation of Forests for Local Communities project (Component 1)
Output number:		1	Output Score:	B
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Procurement completed for main supplier of Component 1, Forests for Local Communities	First draft Terms of Reference (ToR) to be shared with the market drafted by: 1 August 24 / Sourcing Strategy drafted by: 30 August 24 / Invitation to Tender (ITT), including revised TOR, issued by: 11 November 2024 / Bids reviewed by: 24 January 2025 / Contract awarded by: 1 April 2025	Not met expectations / First draft TOR shared: 2 August 2024 / Sourcing Strategy drafted: 12 November 2024 / ITT issued: 2 Jan 2025 / Bids reviewed: 31 March 2025 (technical review) / Contract not yet awarded due to delays in confirmation of budget.
Recruitment of two Project Funded Advisers: one in DRC and another in Cameroon, completed	Job description agreed and published by: 17 July 2024 / Interviews completed by: 13 September 2024 / Successful candidates offered by: 20 September 2024 / Successful candidates start by: 1 December 2024	Met expectations / Job description agreed and published: 17 July 2024 / Interviews: 23 September 2024 / Candidates offered: November 2024 / Candidates started: 7 January 2025

Briefly describe the output’s activities and provide supporting narrative for the score.

Procurement of main support for component 1AB: The first draft of the CBFA C1AB Terms of Reference was shared with the market in August 2024 as scheduled. The sourcing strategy and overall Invitation to Tender saw drafting and issuance by November and January respectively which was slightly later than planned due to resourcing constraints and listening to the market which requested a January to avoid Christmas leave. Bid reviews were conducted through March 2025 after a two-month bidding window. However post announcement of the ODA reductions to 0.3 GNI the team were instructed to pause the commercial process until budgets were confirmed.

Recruitment of two advisers: This occurred as scheduled with both staff members commencing employment after the Christmas break on the 7 January 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This mobilisation output was agreed once the programme was approved, there have been no changes to this output since its approval.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is the first CBFA Annual Review, thus no lessons and recommendations were available to reflect against.

Output Title	Mobilisation of CBFA Partners Facility and initial Grants (Component 2)
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Procurement completed for main supplier of Component 2, Partners Facility	First draft Terms of Reference (ToR) to be shared with the market drafted by: 1 August 2024 Sourcing Strategy drafted by: 30 August 2024 Invitation To Tender (ITT), including revised TOR, issued by: 11 November 2024 Bids reviewed by: 24 January 2025 Contract awarded by: 1 April 2025	It was decided in late Summer 2024 to incorporate Component 2 into Component 1 as a sub-component to improve efficiencies in the commercial process and bring programme operations under one consortium of partners. Therefore, the progress for this indicator is identical to the progress outlined above for C1.
Review and, if approved, mobilisation of up to two unsolicited proposals for initial Grants	Proposal reviewed by CBFA team and cross cutting advisers by: 1 October 2024 Due Diligence assessment completed by: 25 October 2024 Two agreements signed by both parties by: 1 November 2024	Met expectations / CIFOR Yangambi was signed on 29 November 2024 / CBSI CRAFT was signed on 29 November 2024.
Mobilisation of the CRAFT-Sustainable Development: Transforming Central Africa’s Scientific Capacity to Protect Forests and Improve Livelihoods Project	First project kick-off meeting held and CBSI Steering Committee meeting held. / Observatory kick-off meeting held. / PhD and MSc training place recruitment adverts online. / Process to appoint PhD and MSc trainees agreed / Staff recruitment completed for four roles filled.	Exceeded expectations / The project kick-off meeting and the first CBSI Steering Committee - July 2025 / Observatories kick-off meeting was held virtually in 2025. / PhD and MSc adverts received nearly 700 applicants. / Process to appoint PhD and MSc trainees agreed / Staff recruitment is completed with all four roles filled. / In additional a total of 29 scholarships were awarded.
Mobilisation of the Yangambi Engagement Landscape (YEL) project through CIFOR-ICRAF.	First project kick-off meeting. / First governance and technical meetings with local authorities. / Identify 10 students to support with scholarships including 5 male and 5 female students to start from the 1st of January. / Launch scholarships for final years (18-20 yrs old) with FCDO funds funding 49 women out of a total of 133 students. / Conducted the long-term on-farm training for 30 community-based facilitators. / Yangambi market construction - By mid-February negotiate FCDO part of contract with partner	Met expectations / Project kick-off meeting was held in December 2024, / Many governance and technical meetings with local authorities. / The project identified 10 (5 male and 5 female) scholarship students / Launch scholarships for final years (18-20 yrs old) completed with 49 female scholarships. / The 30 community-based facilitators also received their on-farm training as scheduled. / The construction of Yangambi Market is ongoing as planned.

Briefly describe the output’s activities and provide supporting narrative for the score.
The mobilisation and initial implementation of the two accountable grants under this component have met expectations.

Congo Rainforest Alliance for Forest Training (CRAFT) for Sustainable Development through the University of Leeds, is a major initiative under the Congo Basin Science Initiative (CBSI). It aims to transform scientific capacity and knowledge in the Congo Basin, the world’s second largest rainforest, to support sustainable development and forest protection. The programme is structured around six interdisciplinary Observatories: Climate and Meteorological, Hydrology and Freshwater, Vegetation, Soil and Biogeochemistry, Biodiversity, Land-Cover and Land Use Change, and Socio-ecological. Each Observatory is co-led by African and UK experts and focuses on training a new generation of scientists (PhD and MSc level), building technical capacity, and generating new, policy-relevant data and knowledge.

During its first quarter, the CRAFT project successfully launched a bilingual online scholarship system, receiving nearly 700 applications across Central Africa. Key staff were hired, partner due diligence was completed, and subcontracting began. Observatories collaboratively shortlisted MSc and PhD candidates, ensuring diversity and regional representation. The project demonstrated strong value for money by combining capacity building with data generation for policy impact. Outreach included media coverage and stakeholder engagement across universities and international forums. The first Steering Committee meeting was held in Libreville, July 2025.

Yangambi Landscape project through the Center for International Forestry Research and World Agroforestry (CIFOR-ICRAF) project is a long-term, community-based initiative in the Tshopo Province of the Democratic Republic of the Congo (DRC). It is designed to promote sustainable development, biodiversity conservation, and improved livelihoods through an “engagement landscape” approach, which emphasises deep, ongoing collaboration with local communities, authorities, and institutions.

During this first quarter, the Yangambi Engagement Landscape (YEL) project reached over 1,200 farmers through Farmer Field Schools and trained 30 Community-Based Facilitators. It awarded 49 scholarships (all to girls) and supported 58 farming groups. Agricultural yields increased significantly, with notable gains in crops like cassava, maize, and peanuts. Awareness campaigns reached over 3,000 people, and the project hosted the first exhibition of agricultural diversity. Feasibility studies for value chains and carbon credits began, alongside infrastructure development including a market site. Despite security challenges in eastern DRC, activities continued, and the project integrated smoothly with ongoing initiatives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This mobilisation output was agreed once the programme was approved. Part of this output, namely, the initially separate procurement of Component 2: CBFA Partner’s Facility, was merged with Component 1: Forests for Local Communities, effectively forming two subcomponents of a singular overarching commercial Terms of Reference. This aims to improve overall management of the contract, and improve knowledge sharing and scaling of best practice between grants and landscapes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead FCDO should ensure a phased handover of management over the six month period to the commercial supplier to reduce the risk of divergent approaches and set of clearly how these grants should be managed over the remainder of their lifespans.
Output Title	Mobilisation of CBFA Monitoring, Evaluation and Learning
Output number:		3	Output Score:	C
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Mobilisation of CBFA MEL project through GEMFA to align the start of the project with the implementing partners of component 1 and component 2. Including, to ensure independent review of the geographies proposed.	First draft Terms of Reference (ToR) drafted by: 24 October 2024 / ToR quality assured by EQUALS: 22 November 2024 / Sourcing Strategy drafted by: 10 December 2024 / Invitation To Tender (ITT), including revised TOR, issued through GEMFA by: / 7 January 2025 / Bids reviewed by: 7 March 2025 / Contract awarded by: 1 April 2025	Significantly not met expectations / First draft Terms of Reference (ToR) drafted by: 24 October 2024 – Achieved / ToR quality assured by EQUALS: 29th July 2025 - Achieved with ‘Excellent’ scoring / Sourcing Strategy drafted: Not achieved / Invitation To Tender (ITT), including revised TOR, issued through GEMFA: Not achieved / Bids reviewed by: Not achieved / Contract awarded: Not achieved

Briefly describe the output’s activities and provide supporting narrative for the score.
The first draft of the MEL ToR was completed in October 2024. The procurement was initially planned via the GEMFA framework; however, Commercial Directorate advised that a new GEMFA2 framework would be launched in June 2025 and recommended waiting for this. The launch of GEMFA2 was subsequently delayed to August 2025 due to recent ODA announcements. As a result, the team had to pause the process until further clarity and confirmation were received, which also delayed submission of the MEL ToR through the EQUALS process which provides external quality assurance on evaluation products.
[note] Global Evaluation and Monitoring Framework Agreement which pre-approved suppliers who can submit a tender for evaluation contracts.
[note] Evaluation Quality Assurance and Learning Service

Although the output was not achieved during the mobilisation phase, the commercial processes now in progress, including passing of EQUALS with an ‘Excellent’ marking in late July, with contracting expected to be completed by January 2026. In the interim, support from the CLEAN Helpdesk has been secured to ensure adequate MEL coverage during the programme’s inception phase.
[note] Climate, Environment and Nature Helpdesk

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This mobilisation output was agreed once the programme was approved and no further changes have been made. The deadlines will be updated for the next annual review.
## D: VALUE FOR MONEY

Key cost drivers and performance

The Value for Money (VfM) approach for Components 1, 2, and 4 of the CBFA Programme is structured around ensuring efficient, effective, economical, and equitable use of resources, tailored to the unique challenges of the Congo Basin.

Key considerations set out in the Business case focused on the type of agreement to be used for each component and the key cost drivers for each.

Key Cost Drivers
The programme was revised and is now divided into three components, each with distinct cost drivers:
Component	Contract Type	Key Cost Drivers
1. Forests for Local Communities	Commercial contract	Management and administrative fees, consultants’ fees, travel, delivery costs, fund management, and security costs.
2. FCDO Partners Facility	AGs, commercial contract, MoU	Staff and field costs, travel, security, livelihood activities, administrative and management fees.
4. Monitoring, Evaluation & Learning (MEL)	Commercial contract	Consultant fees, milestone-based payments, local/national staff costs, data collection, travel, and security costs.

Competitive procurement is planned to ensure cost comparison and value for money across components.

VfM performance of Accountable Grant partners to date:

Yangambi Landscape – CIFOR-ICRAF:
The project demonstrates good VFM through co-funding, resource sharing, local procurement, and adaptive management. Low initial expenditure is explained by the project’s phased start and escalation of conflict in Eastern DRC, which resulted in real and immediate risks to Yangambi, the surrounding area of operations, and the main exit route via the city of Kisangani. Threats of eastward advancement by M23 were ultimately unfounded, and a peace deal has been agreed, meaning spending is now expected to increase as implementation accelerates.

- Economy: Most activities are co-funded, optimising operational costs (e.g. shared use of vehicles and boats). Local staff mentoring and community-based facilitator programmes are ongoing, maximising the value of human resources. FCDO funds supported 5 MSc students (all women) and 49 technical institute students, leveraging co-funding from EU and Belgian Cooperation.
- Efficiency: Initial assessment of local/national suppliers completed to improve procurement and reduce costs. Annual work plans have been simplified and standardised, streamlining planning and resource allocation.
- Effectiveness: Despite security challenges, activities continued without interruption, thanks to strong engagement with government and communities. The project adapted to local conditions, maintaining progress even during periods of instability.
- Equity: Regular consultations ensured inclusivity, with adjustments to the scholarship programme based on local government input. Focus on supporting women and girls through scholarships and educational initiatives.
CRAFT Sustainable Landscapes project – University of Leeds:
The project is at an early stage, so VfM indicators are being developed with the University of Leeds for future measurement.
- Economy: Inputs (staff, systems) were acquired at appropriate quality and price. Staff recruitment and procurement (e.g., scholarship management system) followed University of Leeds procedures, ensuring competitive pricing and suitability.
- Efficiency: Inputs (promotion, application portal, staff) led to strong outputs—686 applications received, with a robust and efficient shortlisting process identifying talented candidates for every MSc and PhD project.
- Effectiveness: Outputs (student recruitment) are consistent with intended outcomes, though it is too early to measure research and policy impacts. Early costs were mainly for staffing and systems, representing a small fraction of total anticipated spend. The outreach and application process generated a large, high-quality applicant pool at low cost
- Equity: The programme attracted a diverse applicant pool (20.38% female, applicants from four countries, and inclusion of marginalised groups such as indigenous persons). The selection process ensured representation of women and marginalised groups at the interview stage.
VfM performance compared to the original VfM proposition in the business case
This annual review builds on the evidence in the business case on VfM. The VfM metrics (Annex 1) will be agreed and finalised and used to monitor VfM throughout the programme.

Assessment of whether the programme continues to represent value for money
This review is focused on the mobilisation of the programme, some initial results have been detailed above but it is too early to enable a full assessment of the VfM.

The VfM metrics for this programme will be finalised and confirmed with the main supplier to implement and monitor throughout the programme.

E: RISK

Overview of risk management
The risk level of the programme was assessed as Major from design and this remains through mobilisation, due to the fragile contexts in which the programme operates. A comprehensive risk register was established as agreements have been mobilised learning from the due diligence assessments and downstream mapping that was completed and previous programming in these contexts. Key risks identified include high fiduciary risks, political instability, challenges in scaling and timely delivery, and a failure to achieve local ownership and inclusion. Project specific risk registers have also been developed for each of the Accountable Grants that have been signed.

The CBFA Programme Team has prioritised management of fiduciary risks, cascading policy to partners in the delivery chain, and emphasising the importance of effective controls. A zero- tolerance approach is taken to inaction against identified instances of fraud. Furthermore, due to the high reputational risk of not delivering in a timely manner, the mobilisation phase of the programme has prioritised effective internal staffing and good communication with all relevant internal stakeholders on programme spend, timeframes and COP/climate commitments. To mitigate the risk of unexpected changes in the political economy landscape – the programme is working closely with Posts in the region and spreading risk across multiple locations.

Safeguarding risks are present in all contexts. Current implementing partners were sent a letter, alongside their agreement, highlighting the FCDO’s zero tolerance approach to aid diversion and sexual exploitation, abuse and harassment (SEAH). These risks and their mitigations have been discussed with partners, and they will be a standing agenda item in all partner meetings.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Summary of Signed Agreements
Project Name	Partner	Financial Arrangement	Value	Duration
Yangambi Engagement Landscape (YEL)	CIFOR-ICRAF	Accountable Grant	£8,000,000	01 December 2024 - 30 November 2029
Congo Rainforest Alliance for Forest Training (CRAFT) for / Sustainable Development	The University of Leeds	Accountable Grant	£9,112,378	01 January 2025 - 31 March 2030
WP3580 Towards a Congo Basin Pledge	Wilton Park Executive Agency	MoU	£165,172	30 October 2024 - 31 March 2025

This review covers some of the key findings from the mobilisation following review of proposals and completion of the due diligence assessment as well as the first three months of implementation by the accountable grant partners.

For both accountable grants FCDO has agreed narrative and financial reporting structures in the form of quarterly light-touch reports (including updated financial forecasts); biannual detailed financial reporting as well as a detailed annual report. We hold quarterly meetings to discuss the progress as reported and the first quarterly meeting occurred in June 2025.

Financial accounting is managed on an accrual basis. CIFOR-ICRAF provides FCDO with updated forecasts, and this is used to receipt/accrue monthly to ensure resource accounting procedures are maintained. Invoices are sent on a 6-monthly basis. We are yet to receive the first invoice which is due at in the first week of August 2025.

In March 2025, FCDO hosted a Wilton Park conference that brought together representatives from Cameroon, Central African Republic, Democratic Republic of Congo, Gabon, Republic of Congo, donor countries, multilateral development banks, climate funds, and regional and international civil society. FCDO was provided invoices which were processed on time. The remaining disbursement will be made when the final report from the conference is delivered, as agreed.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The role of monitoring and evaluation in the Congo Basin is vital in ensuring programmes deliver effectively in a challenging operating environment, whilst mitigating the significant risks prevalent across Central Africa. CBFA’s predecessor, Investing in Livelihoods and Land Use in the Congo Basin Forests (ILLUCBF) made a clear recommendation in its project completion report emphasising a focus on M&E for any future activities. CBFA will action this recommendation through a stronger emphasis on M&E as the programme scales via the primary contract. Stringent M&E responsibilities will be baked into FCDO’s agreement with the main supplier, and will be augmented by regular, in-depth FCDO visits to project sites, coupled with quarterly dedicated reporting to enable rapid understanding of and emerging risks, and ultimately, impact evaluations delivered throughout the programme timeframe to understand what is working and what isn’t.

FCDO staff managing this programme conducted a range of engagements with programme stakeholders during the mobilisation, primarily focused on the review of project proposals and organisation capacity through due diligence assessments.

Regular, at least quarterly, remote meetings with partners are held to ensure the team understand the evolving contexts, delivery challenges and remind partners of their reporting requirements if any risks, including fraud or safeguarding, emerge.

The FCDO programme team meet weekly, chaired by the Programme Responsible Owner (PRO) and attended by the Senior Responsible Owner (SRO), Advisers and Programme Managers to monitor delivery of the programme and discuss risks and emerging issues.

Programme stakeholders and beneficiaries have been recently met by the CBFA team and a visiting senior staff from London in all four countries currently being operated in. These engagements included meeting the academic staff from the CBSI, the recently announced scholars, and the delivery team from the Yangambi landscape. Overall feedback on UK funded efforts has been extremely positive thus far, not just from these direct stakeholders, but also from broader actors across the region, most notably senior members of government, including the ministers of environment in DRC, Republic of Congo, and Gabon.

This annual review has been completed by the FCDO programme team using a desk review of due diligence assessments completed to date and evidence from quarterly reports and monitoring visits.

Evidence and learning
The programme will monitor and learn lessons through a dedicated Monitoring, Evaluation and Learning (MEL) component, which will play a central role in quality assurance, evidence generation, and adaptive management of CBFA. This will be supplemented by ongoing FCDO monitoring visits and engagement.

Date of last narrative financial report received	YEL – Yangambi Landscape	02 May 2025
	CRAFT – University of Leeds	30 April 2025
Date of last audited annual statement	YEL – Yangambi Landscape	N/A
	CRAFT – University of Leeds	N/A

Annex 1: Value for Money Indicative Framework

Category	Metric
Economy	Costs of follow up and support. / Costs of evidence base creation. / Costs of training. / Costs of investment memorandum.
Efficiency	Activity Establishment Cost. / Cost per hectare. / Cost per beneficiary.
Effectiveness	Cost/tCO2 avoided. / Landscape overall revenue % increase.
Equity	% change in income of forest dependent communities. / % of activities led by women. / % of activities jobs delivered by women. / % of workshops attendance by women. / % of people supported with disabilities