Sudan Independent Monitoring and Analysis Programme
Programme Value: £7,500,000		Review date: 11/05/2025
Programme Code : 301472	AMP start date: 11/05/2023	AMP end date: 30/09/2027

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	D0005018.odt (live.com)
DevTracker Link to results framework:	D0005019.xlsx (live.com)

Acronyms
ALR	Action Learning Research
BOS	British Office Sudan
DDA	Due Diligence Assessment
DIT	Domain Intercept Technology
FCDO	Foreign, Commonwealth, and Development Office
FSDA	Financial Sector Deepening Africa
GBV	Gender-Based Violence
GESI	Gender Equality and Social Inclusion
HAC	Humanitarian Aid Commission
LQ	Learning Question
IAID	Internal Audit Department
ICAI	Independent Commission for Aid Impact
IPs	Implementing Partners
KPI	Key Performance Indicator
MEL	Monitoring, Evaluation, and Learning
ODA	Official Development Assistance
OPM	Oxford Policy Management
PLT	Programme Leadership Team
PM	Programme Manager
PRO	Programme Responsible Owner
RSF	Rapid Support Forces
SAF	Sudanese Armed Forces
SEIR	Sudan Economic Impact and Reform Programme
SFFGM2	Sudan Free of Female Genital Mutilation Programme Phase 2
SHPR	Sudan Humanitarian Preparedness and Response Programme
SIMAP	Sudan Independent Monitoring and Analysis Programme
SML	Social Media Listening
SOPs	Standard Operating Procedures
SQs	Sub-Questions
SRO	Senior Responsible Owner
SRs	Systems Reviews
SSGP	Sudan Stability and Growth Programme
TOC	Theory of Change
TOR	Terms of Reference
TPM	Third-Party Monitoring
UN	United Nations
UNFPA	United Nations Population Fund
UNICEF	United Nations Children’s Fund
USAID	United States Aid Agency
VfM	Value for Money
WFP	World Food Programme
WHO	World Health Organization
WS	Workstream
A. SUMMARY AND OVERVIEW
Description of programme
The Sudan Independent Monitoring and Analysis Programme (SIMAP) aims to strengthen the effectiveness of the UK’s policy and programme portfolio in Sudan through providing timely, objective information on delivery and contextual developments to inform decision-making in a fluid operating environment. The programme will be delivered through a commercial supplier, Oxford Policy Management (OPM), deploying a team of thematic and contextual experts to undertake activities to deliver three core outcomes:
1. Assurance & Capacity Building: Improving assurance of programme delivery and building the capacity of partners to deliver through field-based monitoring of programme delivery and results; assessments of implementing partner systems for collecting programme information and meeting FCDO priority compliance requirements, including making recommendations for improvements and providing targeted technical assistance.
2. Learning & Innovation: Enabling more innovative policy and programming approaches to be tested based on rapid feedback and learning mechanisms through design and implementation of a learning strategy to support FCDO and its partners with synthesising and acting on data and evidence generated by the programme and FCDO’s wider portfolio in Sudan; delivery of action learning research projects to test the potential of new and/or innovative approaches to policy or programme delivery; and enhanced collection of beneficiary feedback to inform the design and/or implementation of FCDO policy and programmes.
3. Strategy & Analysis: Increasing access to outcome-focused analysis to support strategic decision-making through demand-led research and analytical pieces on topics of strategic interest to the FCDO in Sudan, including desk-based reviews drawing on secondary sources and primary research conducted in Sudan.
The conflict in Sudan has brought devastating consequences to the population. These consequences include massive loss of life, the collapse of the state, severe disruption to livelihoods and food security, and the largest displacement crisis in the world. Despite this volatile setting, the FCDO, through British Office Sudan (BOS), continues to operate a diverse and evolving bilateral programme portfolio across the country.
BOS fully recognises that ongoing and future policy and programming decisions that will make a difference in Sudan rely on robust evidence. However, a range of challenges has translated into barriers to monitoring programmes and context in Sudan. Significant among these are operating outside the country, restrictions on travel for non-Sudanese nationals, security risks for those still working in Sudan, and the logistical challenges associated with Sudan’s vast and often remote geography.
In response to the devasting crisis in Sudan, the BOS bilateral aid budget has almost quadrupled, from £38m in FY22/23 when SIMAP was approved, to £140m this FY. As such SIMAP is even more critical for providing oversight and assurance on our portfolio. In addition, strict controls imposed by the authorities in Sudan and wider funding cuts across donors in 2025 means that there is a dearth of evidence and data on Sudan, increasing the importance of SIMAP to ensure evidence-based decision making.
This review covers programme activities between April 2024 and March 2025 which included completion of the inception phase (Apr - Nov 2024) and four months of implementation (Dec 2024 - Mar 2025).
Summary supporting narrative for the overall score in this review
The programme has scored an A and is meeting expectations in terms of delivery and achievements across the inception and implementation phases during this period under review. SIMAP successfully completed its inception phase in November 2024 evidenced by the achievement of all inception deliverables which contributes significantly to this review assessment.

Key achievements of the past year include;
- Completion of all inception phase deliverables, including: establishment of the programme governance structure, logframe and KPIs, development of research and learning strategies - which have established the priorities for monitoring, learning, and research, methodology notes and cross-cutting gender and conflict sensitivity strategies.
- The three successful TPM exercises undertaken during inception, followed by constructive debriefs in which very practical recommendations were shared with IPs. Despite delays, a strong emphasis on relationship building has provided the basis for new TPM exercises planned for the first quarter of year 2.
- SIMAP has contributed to Monitoring Evaluation & Learning (MEL) systems strengthening in a number of ways, for example through a series of in-depth reviews for the Sudan Humanitarian Preparedness and Response Programme (SHPR), Sudan Free of Female Genital Mutilation Programme Phase 2 (SFFGM2) and the Sudan Stability and Growth Programme (SSGP) on their MEL systems which identified a series of recommendations for programme teams which have been taken forward with partners, a fiduciary risk assessment ahead of an internal audit of the Sudan portfolio and through an indicator alignment exercise of the SHPR logframe.
- A learning-focused approach has shaped the SIMAP research offer. Priority learning questions have been further defined to establish scope and intention, and focused research endeavours have followed. Already, research findings on getting cash into Sudan have been well received and there are plans for dissemination of these findings and associated recommendations to other BOS Partners.
Major lessons and recommendations for the year ahead
Feedback from primary beneficiaries has been largely positive on the quality of products produced, understanding of the issue and delivery approach. SIMAP delivered all the inception deliverables and responded positively to changes in the agreed Terms of Reference (ToR) initiated by FCDO as part of the co-creation approach for the programme during the inception phase. The quality, delivery and timeliness has overall been strong.
Progress against recommendations in the previous AR
While an Annual Review was conducted last year, it only covered the initial procurement phase and as such did not have learning to build on from programme performance. Nevertheless, a set of recommendations was made last year, based on key lessons learned from other programmes in comparable contexts as well as the British Embassy Khartoum’s pilot third party monitoring programme in 2022. Of the eight recommendations made in the last annual review, six have been completed and incorporated into the ways of working.
There are two recommendations that remain ongoing for the FCDO programme team, related to coordination of TPM across donors and creating structures at BOS to facilitate learning. These are included in the key lessons and recommendations below.
Key Lessons & Recommendations
TPM adds value from both a programme implementation and funder assurance perspective but is challenging in the current context. Delays in the implementation of Q3 and Q4 TPM activities have been experienced due to a variety of decisions and circumstances, including the recent cuts to USAID funding which delayed programme implementation (specifically for WFP), some delayed responses from IPs including getting agreement on alignment of TPM activities to IPs SOPs and central agreements with FCDO, and other logistical challenges to operating in Sudan (e.g. obtaining HAC permissions).
Recommendation 1: BOS through SIMAP should continue to pursue TPM opportunities but should recognise that these might be fewer than originally anticipated in the logframe, without a change to the number of partners with which SIMAP can engage and/or a change to the contractual agreements which empower IPs to decide if and when TPM work can go ahead. Early planning and organisation, as well as continuous transparent engagement with IPs, is essential for ensuring that TPM runs smoothly.
Opportunities for primary data collection, through both in-person and remote methodologies, should be a focus of the year ahead. While mitigations to delays in TPM are likely to improve delivery, the complexity of the context and uncertainty over the future footprint of FCDO programming means that SIMAP should also look to diversify the activity in WS1 to include primary data collection, alongside TPM.
- Recommendation 2: To ensure that SIMAP makes full use of the enumerator capability in Sudan, FCDO should consider commissioning primary data gathering to enhance understanding of contextual and thematic realities on the ground.
- Recommendation 3: SIMAP could deploy remote technologies for data gathering alongside or as a substitute for fieldwork and in support of broad context monitoring (WS2) and more specific research (WS3).
Overall, opportunities to engage with IPs has been limited reducing the range of SIMAP support possibilities (for example MEL systems building support, action learning research). This is in part due to the fact that most are UN agencies and are financed by multiple donors of which FCDO and the support that can be provided through SIMAP play only a part.
- Recommendation 4: SIMAP should continue their approach to relationship building with existing IPs, through the TPM and MEL systems support work, extending this where possible. As FCDO designs and mobilises new programmes, it should look to ensure that expectations on engagement and data sharing with SIMAP are explicit in agreements and expand the offer of support to new local suppliers, where appropriate and feasible.
- Recommendation 5: FCDO should ensure a systematic response to data gaps identified by the MEL Systems Review, ensuring that SIMAP has regular access to updated programme documentation to be used as the basis of support for programme monitoring & support.
Initial attempts to engage implementing partners in Action Learning Research (ALR) has been difficult, especially considering that the IP approached for ALR was only in very early implementation and had other MEL priorities. While ALR will remain a key tool offered by SIMAP and may be utilised if there is interest and demand, recognising these challenges in getting traction/interest, it will not be a specific focus for the programme going forward.
Recommendation 6: SIMAP to update logframe indicator 2.2 to reflect the re-focus away from ALR and develop new output indictors for the following year which reflect the changed focus of WS2 (see below).
As the programme moves into implementation, structural changes to the SIMAP workstreams are needed to improve clarity on roles and responsibilities and create the space to build on opportunities identified during inception. Feedback from BOS colleagues suggests that the overall structure of SIMAP, across three workstreams, was unclear and the distinction between WS2 and WS3 could be made more explicit. In addition, a number of opportunities were identified during the inception phase that require changes to the way SIMAP is structured in order to implement. These include: (i) the opportunity for WS1 to conduct more primary data collection and building on opportunities for more innovative and experimental approaches to remote data gathering; (ii) adding strategic evidence gathering and collation to WS2 to support portfolio-level assessments of the overall BOS Country Plan; (iii) broadening the support provided through the MEL systems work. A proposed approach to the restructure is shown in Figure 1 above.
### Figure 1 Proposed SIMAP restructure and function
- Recommendation 7: SIMAP should expand the role of WS2 to incorporate the collection and collation of strategic evidence to support country plan development and reporting – to cover key statistics on context, on problem drivers and sub-national need and delivery mapping. Given the current stage of the programme, there has not been the opportunity yet for SIMAP to contribute to and monitor the strategic effectiveness of the Sudan Country Plan, but this is likely to change as FCDO move into designing the next phase of its Country Plan.
- Recommendation 8: SIMAP should restructure to create a fourth workstream offering support in programme design, data analysis and capacity building alongside new programmes and new implementing partners. There is scope for SIMAP to provide programme support beyond the review of MEL systems. Capacity building for BOS staff and possibly lower tier partners could be offered in the form of focused sessions of ‘bite-sized’ learning.
The volatile context of Sudan and uncertainty over broader FCDO priorities and resourcing for the years ahead requires a flexible approach to identify and proceed with non-previously planned research initiatives. Changes have already been introduced during the review period to respond to emerging needs, and Special Requests for research have already been acted upon. Currently, two pieces of research are being delivered under this category (Climate Resilience and Adaptation in Sudan; Safeguarding), and this responsive approach is expected to continue in the next year.
- Recommendation 9: SIMAP should continue to ensure that a flexible approach is taken to research outputs, making sure that enough resource is available to respond to emerging priorities when they come up.
- Recommendation 10: In order to continue responding to shifting research priorities, SIMAP should continue strategically growing the network of consultants, ensuring a range of international and local experts. The SIMAP team should continue to explore flexible approaches to contracting consultants - accepting that products and activities agreed in the TOR may be shifted at any time in their scope and timelines.
Based on the changes proposed above, the overall TOC and logframe should be reviewed to ensure it still accurately articulates the programme logic. The FCDO programme team and SIMAP should ensure that the theory of change is revised based on the changes proposed above, ensuring that the pathways to outcomes are clear and that key assumptions and their underpinning evidence are articulated. In particular, the review should consider how learning from inception and early implementation has impacted not only assumptions related to the external operating context, but also assess assumptions that relate to the translation of chosen outputs to outcomes and delivery modalities.
- Recommendation 11: FCDO and SIMAP should ensure a review of the programme Theory of change is conducted by Q2 and any changes are reflected in the programme logframe. This revision should incorporate a) reflections on lessons learned and their associated assumptions as well as b) contextual shifts which have changed the needs and priorities for support.
- Recommendation 12: While it is still early in the programme, the SIMAP team should look for opportunities to improve its output indicators to ensure it captures the full range of activity undertaken by SIMAP, as flagged in the review of the current set of output indicators in Section C below.
As the programme moves into implementation, SIMAP should establish clear programme management processes, ensuring finances and risk are regularly reviewed at the monthly programme board. Variance of actual spend to forecast during the first four months of delivery was significantly higher than expected, due to unpredictability in TPM fieldwork.
Recommendation 13: OPM should implement more robust financial oversight mechanisms for TPM activities, ensuring accurate breakdown of costs and expenses in monthly reports. OPM should focus on refining the accuracy of financial forecasts to reduce variances between projected and actual expenditures. Adopting a more realistic forecasting approach will enhance financial planning and resource allocation.
Coordination with donors and IPs on TPM remains a key challenge for the programme. FCDO should look to take more leadership in across the international community in the coming year. This is also in-line with early findings from the ongoing ICAI review on UK support to Sudan.
Recommendation 14: FCDO to use the core donor working group to discuss TPM coordination and look for opportunities to share learning, reduce burden on programme partners and maximise VFM.
Despite making good progress on the learning strategy, questions and associated research pieces, there is still a need to develop internal structures for learning at BOS – feeding into both the ongoing knowledge management strategy & plans to establish a more regular “thinking board” for BOS in the coming year. Once established, the uptake and engagement section of the learning strategy - specifically to the ‘where’ section of the learning strategy - requires further elaboration with FCDO and regular cross-workstream discussion.
Recommendation 15: SIMAP should continue to seek learning spaces and moments, when synthesis offers strategic learning and work with FCDO to continue to identify opportunities for uptake and engagement of products developed.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’, including any changes to outcome and impact indicators from the original business case.
SIMAP’s Theory of Change (ToC) describes how monitoring, learning, and analysis services will strengthen FCDO programmes and decision making to improve outcomes for targeted communities in Sudan. SIMAP will provide such services relevant to all programming funded by FCDO in Sudan.
The ToC suggests that SIMAP’s support will lead to improved effectiveness of the BOS policy and programming portfolio, which in turn will lead to improved outcomes for target communities in Sudan (Causal Pathway D). This will be achievable because:
- FCDO will have increased oversight of programme delivery and be better able to support IPs to improve programme performance (Causal Pathway A) if: SIMAP provides regular and robust evidence of programme delivery through TPM; and if SIMAP supports the strengthening of IPs’ own MEL systems and policy compliance through targeted TA.
- FCDO will have increased access to relevant analysis that supports strategic decision making (Causal Pathway C) if: SIMAP provides high-quality, demand-led research on priority themes and topics co-identified with BOS.
- FCDO will be able to support more innovative policy and programming approaches, and to share learning systematically to influence sector approaches in Sudan (Causal Pathway B), if: SIMAP provides learning opportunities for FCDO and IPs that respond to priority themes delivered through the SIMAP learning strategy; if SIMAP makes accessible regular summaries of evidence to stakeholders; and if SIMAP generates additional evidence on innovative approaches through ALR.
Critical assumptions (dependencies) include: IPs’ willingness to engage with regular TPM activity and absorb technical support; ability of SIMAP to secure permissions for data gathering in a way which safeguards enumerators; willingness of IPs to take part in action learning research.
### Figure 2: Diagrammatic representation of the SIMAP ToC

Overall, the TOC and intervention logic for SIMAP continues to hold although there are elements that require updating on the back of this review. In addition to structural changes proposed through this review and some slight changes to proposed activities, the programme should review the underpinning assumptions in light of critical shifts over the last year, including the ongoing deteriorating security context, reductions in aid budgets and associated staffing; policy redirection in relation to the next Sudan Country Plan; challenges associated with robust evidence and data sharing in the tighter financial environment.
- Recommendation: FCDO and SIMAP should ensure a review of the programme Theory of change is conducted by Q2 and any changes are reflected in the programme logframe. This revision should incorporate a) reflections on lessons learned and their associated assumptions as well as b) contextual shifts which have changed the needs and priorities for support.
- Recommendation: While it is still early in the programme, the SIMAP team should look for opportunities to improve its output indicators to ensure it captures the full range of activity undertaken by SIMAP, as flagged in the current set of output indicators in Section C below.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is only four months into implementation and as such it is very early in the programme to assess meaningfully its progress towards contributing towards expected outcomes and impact, but the programme is steadily gaining traction amongst BOS colleagues such that interest and demand for SIMAP support is increasing.
Table 1 below summarises the progress against outcome and impact level indicators. Given the stage the programme is at, this has been more about establishing baselines for impact & outcome indicators than demonstrating progress against each indicator.
### Table 1: SIMAP Impact and Outcome indicators
IMPACT	Impact Indicators	Progress FY24/25
Improved effectiveness of FCDO policy and programme portfolio, and improved outcomes for target communities in Sudan	Impact Indicator 1: Portfolio Quality Score for Sudan bilateral ODA portfolio (weighted average Annual Review score across all active programmes)	↓91.4 (Apr 25)– this has dropped from 104.4 in Aug/Sept 2024
	Impact Indicator 2: % of outcome-level targets met annually by Sudan bilateral ODA programmes	Baseline established for BOS portfolio / Outcome confidence RAGs as at 31 Mar 25: / SSGP: Amber/Red / SFFGM2: Green/Amber / SHPR: Amber/Red / SEIR: Amber
OUTCOME	Outcome Indicators	Progress FY24/25
FCDO (i) has increased oversight of programme delivery and can better manage risks; (ii) is able to support more innovative policy and programming approaches, and share learning systematically; and (iii) has increased access to relevant, outcome-focused analysis to support strategic decision-making and shape the response of the international community in Sudan.	Outcome Indicator 1: % of recommendations made by SIMAP implemented/actioned by programme partners	Too early in the programme to quantify but SIMAP has established a recommendation and feedback tracker to help monitor progress and early indications that the 12 recommendations from TPM pilots have been accepted by IPs
	Outcome Indicator 2: Examples of decisions taken by FCDO staff and/or implementing partners influenced by evidence produced by SIMAP to improve programming/policy	Too early in the programme to quantify but good feedback received on the first research products completed on the economy.

SIMAP maintains a recommendation and feedback tracker to help monitor progress towards this outcome and indicators. While it is early in SIMAP’s programme cycle (inception plus five months implementation) to secure comprehensive outcome level data, there are early signs of progress:
- At the portfolio-level the MEL systems reviews and fiduciary risk assessments have provided FCDO with insights into where and why there may be weaknesses in programme reporting and provided the basis for discussions between FCDO and programme partners.
- At the programme-level the systematic sharing of TPM learning has influenced decisions taken by implementing partners to improve programming.
- Research on getting cash and financing into Sudan has provided insights into problems relating to the introduction of new currency and proposed best ways forward for supporting the movement of cash into and around Sudan which is being shared with FCDO partners.
Over time, each SIMAP workstream will work collaboratively with FCDO to collate, reflect upon and determine best responses to the evidence and the associated recommendations produced by the SIMAP programme.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The purpose of SIMAP is to directly support the more effective delivery of UK aid in Sudan and maximise the impact. It will also generate learning which will inform all HMG activity as it relates to our ability to deliver our development objectives including, ODA, non-ODA and all other non-funded activity including diplomacy activities. For these reasons, this review recommends the programme continues.
## C. DETAILED OUTPUT SCORING
Output Title	Assurance & Capacity Building: FCDO receives regular, accurate verification and assurance reports on priority topics, as well as partner compliance and capacity assessments which identify key issues and make practical recommendations; implementing partners receive tailored technical assistance to improve practice
Output number:		1	Output Score:	A
Impact weighting (%):		60%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
% of FCDO staff who rate the quality of workstream deliverables as good or excellent	Finalise development of assessment rubric / >80% (launch after 6-months of implementation)	Met / The assessment rubric has been developed and while it is too early for the planned survey to be rolled out, early indications suggest positive feedback on both the TPM reports and MEL systems reviews
% of implementing partner staff who rate the quality of technical advice and deliverables provided by the supplier as good or excellent	Finalise development of assessment rubric / >75% (launch after 6-months of implementation)	Met / The assessment rubric has been developed and while it is too early for the planned survey to be rolled out, feedback received to date following delivery of the TPM debrief sessions with IPs is indicative of meeting this milestone.
Number of TPM visits completed to agreed specifications and standards in line with the agreed workplan - disaggregated by programme, region, method (remote vs in-person)	6 TPM visits completed	Partially met / To date 3 TPM activities have been completed. A planned further 4 TPM activities have been delayed but are on-track to be completed in Q1 of FY25/26.

Briefly describe the output’s activities and provide supporting narrative for the score.
Despite only partially meeting the final indicator on the number of TPM visits, this output scores an A, in part due to the significant effort over the past 6 months on TPM and the review team feeling that the milestone of 6 visits completed only four months into implementation was overly ambitious (see section below). The current logframe also does not have indicators linked to the work on MEL systems which has made good progress over the review period. This output corresponds to Workstream 1 (WS1) activities on TPM and MEL Systems Review, which are designed to provide a mechanism of oversight and monitoring for the FCDO on its projects and partners.
Third party monitoring
During the Inception Phase, three pilot TPM visits were successfully completed with UNICEF and UNFPA under the SSFGM2 programme, and with the Protection Consortium under the SHPR programme. Figure 3 below shows the location and focus of TPM completed and in progress over the last year.
### Figure 3: Map of completed and ongoing TPM activity by SIMAP

The TPM reports were well-received by BOS as well as the overarching learning report from the pilots which has been shared across BOS and is used in discussions with IPs more broadly on TPM. In addition to the TPM reports, debrief workshops were organised with IPs to reflect on key findings, lessons learnt and recommendations. For each of the debrief workshops, other programme IPs were also invited to encourage learning and information sharing within programmes. IPs took active part in the debrief workshops and the feedback on the workshops was positive. UNICEF described the workshops as helpful and constructive, and specifically mentioned that they hoped SIMAP would continue to include UNICEF, UNFPA and WHO in all debrief sessions for the SSFGM2 TPM activities.
A key focus of the TPM work this year has been establishing trusted relationships between SIMAP and the IPs through close collaboration and regular communication, allowing the programme to secure agreements from some IPs on the types of support for permission or other processes that they would be able to provide SIMAP. The SIMAP team have experienced some push-back from IPs on data-sharing requests and there have been challenges with securing the right permissions to operate in different parts of the country. Despite delays, SIMAP has worked closely with FCDO and IPs to develop the next round of TPM, which is expected to include in the coming month. This is a new way of working for many IPs and the efforts to build trust and the significant effort put in by SIMAP over the review period has helped to demonstrate to IPs that the TPM work implemented through SIMAP has the potential for mutual benefit through augmenting IPs’ own MEL and research capacities.
In addition to the TPM, WS1 has also begun to scope out additional primary research opportunities for next year. This has included internal discussions to add more specific “research questions” to TPM activities and to expand the amount of research-focused primary data gathering under WS1, using alternate data collection modalities, such as telephone surveys, digital avatars, and domain intercept technology (DIT) to disseminate surveys in Sudan where security and bureaucratic conditions are challenging.

MEL Systems Review
During the inception period, three large-scale MEL Systems Reviews (SRs) took place on SHPR, SFFGM2 and SSGP. These MEL SRs are large-scale, document-based reviews of partner’ programming material, including their theories of change, logframes, reporting mechanisms, evaluation plans, VfM frameworks and other fundamental components of MEL systems. MEL SRs aim to identify opportunities for strengthening across systems.
These MEL SRs received very positive feedback from across BOS, with the reports being found to be "substantive" and "meaningful” in verbal feedback. Verification sessions were designed after submitting the MEL SRs to discuss any questions and respond to any outstanding concerns from PROs. Validating findings from the MEL SRs enabled SIMAP and BOS to co-identify next steps that were the most useful to the PROs for SFFGM2, SHPR and SSGP. The validation conversations held between SIMAP and the PROs for each programme ensured that structures and processes not easily represented in physical documentation were able to be reflected within the findings of the MEL Systems Review, while also ensuring that these conversations allowed the PROs to highlight emerging needs, and opportunities for SIMAP to engage, that the MEL Systems Reviews revealed.
During the implementation phase, the MEL Systems Review has progressed with support to the SHPR programme, through an indicator alignment exercise, which aimed to strengthen the SHPR programme logframe in line with the projects it supports. The exercise demonstrated how the different projects within the SHPR portfolio ‘fit’ within the SHPR logframe, pairing project-level logframes to the SHPR logframe and highlighting where IP indicators are complementary to the SHPR programme logframe. The exercise also highlighted where the SHPR logframe could be adapted to better reflect the logframes of the individual implementing partners. FCDO will use this as the basis for changes to the SHPR logframe (as recommended by the recent IAID report). It will also be useful for planned capacity building with programme managers in FY25/26.
Describe any changes to this output during the past year, and any planned changes as a result of this review
Four TPM activities were planned in Q3/Q4 of this year. A combination of factors, outside the control of the programme, led to the delayed delivery of these activities, which will now be completed in Q1 of FY25/26, including:
- Issue of Stop Work Orders by USAID delayed engagement with IPs as they responded to this issue. In the case of the planned TPM with WFP this led to a delay in food distributions. These meant that the pre-Ramadan window for fieldwork was missed.
- Changes to the procedures with which approval are sought from HAC in SAF controlled areas led to further delays in beginning fieldwork.
- Negotiations over data sharing and the scope of fieldwork with one of the IPs required a shift in approach.

The MEL Systems Review work found that much of SIMAPs engagement is likely to be more directly in support of BOS, rather than implementing partners. As such, SIMAP’s engagement with IPs is expected to be largely indirect, with some of the practical implications of this being the potential for bottlenecked communications between the SIMAP team and the implementing partners. While this has not yet posed a substantial issue for the MEL Systems, it may pose a risk in future implementation.
Lessons learned this year and recommendations for the year ahead
Early SIMAP internal planning and continuous transparent engagement with IPs is essential for TPM: A full quarter is needed for the implementation of a TPM field visit because of the many factors that continuously cause delays, such as obtaining permissions and data-sharing with IPs. Keeping IPs informed on the progress of TPM activities has been helpful for ensuring timely responses to requests and maintaining engagement in the process. SIMAP intends to inform IPs of upcoming activities earlier in the process, before the start of a quarter, clearly indicating the anticipated timeline and engagement desired of IPs at each stage. SIMAP will continue to conduct debrief sessions with IPs to reflect on findings, offering a space to discuss, provide feedback on and provide additional documentation to explain specific findings.
Flexibility is required to conduct TPM with the current set of IPs. Due to the limited number of active IPs, and the limited number of IPs that SIMAP can work with (either due to the nature of work, or due to IP willingness to engage with SIMAP), annual TPM visit targets will likely have to be revised going forward. Furthermore, the combination of established SOPs not allowing spot checks, not sharing disaggregated data, strongly restricts the number of checks TPM can perform. Requiring IPs to report data with aggregates for location, gender and disability, would considerably increase TPM's ability to confirm adherence to selection criteria, prioritisation, and delivery data.
In recent months, SAF-controlled areas continue to change permissions requirements, and the administration in Port Sudan has become more established. This is resulting in the centralisation of some of the permission processes since most organisations run all their missions in SAF-controlled areas out of Port Sudan. Increasingly, the expectation is that HAC in Port Sudan gives permission before state-level HAC offices do. For this reason, SIMAP is exploring the establishment of permanent networks in Port Sudan to be able to directly engage with HAC in Port Sudan even if TPM activities are not taking place in Red Sea.
Opportunities for primary data collection, through both in-person and remote methodologies, should be a focus of the year ahead. While mitigations to delays in TPM are likely to improve delivery, the complexity of the context and uncertainty over the future footprint of FCDO programming means that SIMAP should also look to diversify the activity in WS1 to include primary data collection, alongside TPM. The diversification of activities of WS1 allows for the following additional mitigating measure: Preparing and obtaining permission of multiple primary data collection activities that can be inflated or accelerated in case TPM activities are delayed.

SFFGM2, SSGP and SHPR, are structured fundamentally differently from one another, highlighting the need for tailored MEL Systems support. This was a considerable finding from the MEL Systems Review, and it has allowed the unique structure of each programme to be more accurately reflected in conversations on monitoring, evaluation and learning systems. The operational context requires a high degree of flexibility, meaning that recommendations from the MEL Systems mechanism need to be actionable, realistic and easy to prioritise (usable). Expanding MEL systems work into a separate workstream should help to operationalise the findings from the MEL Systems work and will serve a broader programme support function.
Recommendations
- BOS through SIMAP should continue to pursue TPM opportunities but should recognise that these might be fewer than originally anticipated in the logframe, without a change to the number of partners with which SIMAP can engage and/or a change to the contractual agreements which empower IPs to decide if and when TPM work can go ahead. Early planning and organisation, as well as continuous transparent engagement with IPs, is essential for ensuring that TPM runs smoothly.
- To ensure that SIMAP makes full use of the enumerator capability in Sudan, FCDO should consider commissioning primary data gathering to enhance understanding of contextual and thematic realities on the ground. SIMAP could deploy remote technologies for data gathering alongside or as a substitute for fieldwork and in support of broad context monitoring (WS2) and more specific research (WS3).
- FCDO to use the core donor working group to discuss TPM coordination and look for opportunities to share learning and reduce burden on programme partners.
- SIMAP should restructure to create a fourth workstream offering support in programme design, data analysis and capacity building alongside new programmes and new implementing partners. There is scope for SIMAP to provide programme support beyond the review of MEL systems. Capacity building for BOS staff and possibly lower tier partners could be offered in the form of focused sessions of ‘bite-sized’ learning.
- SIMAP should continue their approach to relationship building with existing IPs, through the TPM and MEL systems support work, extending this where possible. As FCDO designs and mobilises new programmes, it should look to ensure that expectations on engagement and data sharing with SIMAP are explicit in agreements and expand the offer of support to new local suppliers, where appropriate and feasible.
- FCDO should ensure a systematic response to data gaps identified by the MEL Systems Review, ensuring that SIMAP has regular access to updated programme documentation to be used as the basis of support for programme monitoring & support.
Output Title	Learning & Innovation: Structured, useful and accessible opportunities for learning are provided to BOS teams and partners; action learning research on new or innovative areas of programming makes timely and useful recommendations to guide decision-making
Output number:		2	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
% of FCDO staff who rate the quality of learning opportunities and deliverables produced by the supplier as good or excellent	Finalise development of assessment rubric / >80% (launch after 6-months of implementation)	Met / The assessment rubric has been developed and while it is too early for the planned survey to be rolled out, early indications suggest positive feedback on WS2 deliverables completed to date.
Number and examples of pilot projects and/or new approaches tested by FCDO with monitoring or action learning support from SIMAP	> 1 example of pilot/new approach tested with support from SIMAP	Not met / A planned Action Learning Research activity with Financial Sector Deepening Africa has been cancelled, due to the programme no longer being taken forward.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output met one of its two milestones for this year and scores a B. This output corresponds to Workstream 2 (WS2) on learning & innovation workstream, which aims to facilitate structured useful and accessible opportunities and products for learning for BOS teams and partners. Recommendations for improvements to this output are given in the section below.
During inception WS2 laid the foundation for this approach through the development of an integrated, multi-workstream learning strategy. The learning strategy takes advantage of the data collection opportunities under WS1 (TPM) and shaped the research framing for WS3. The learning strategy represents the culmination of a grounded process of question development via close engagement with BOS to define learning priorities. It specifies ‘what’ BOS want to learn about via a set of agreed strategic learning themes, questions and sub questions and outlines ‘how’ (suggested methodologies for answering each question) and ‘where’ (potential uptake moments and processes) this question might be answered and used for learning.
The process began with refining the terms and concepts of prioritised sub-questions (SQs) through a light-touch literature review. This step was completed for five learning SQs, resulting in the delivery of five corresponding definition papers within the first quarter of implementation. These papers serve to establish the scope and intention for each prioritised learning SQ within the quarter, ensuring alignment with FCDO overarching objectives and allowing refinement of the questions for greater specificity. They also provide parameters for WS3 to develop research proposals and agree on entry points with FCDO.
The definition papers produced are as follows:
Table 3: Definitional papers produced to date and resulting follow-on WS3 actions
Goal Area	Original	Refined Sub Question	WS3 actions
Goal 1	1.2 What lessons are emerging (e.g. through community listening) around bottom-up localised conflict management and local governance for building resilience	1.2 - Through what approaches and structures can bottom-up local governance and localised conflict management be most effectively supported to enhance community resilience?	FCDO kick off call conducted and research proposal/team in development
Goal 2	2.2 How do cash/market -based approaches intersect with conflict dynamics – what are the potential negative effects to be mitigated? - what potential do these have to support local capacities for peace?	2.2 - In what ways do cash and market-based approaches as humanitarian responses in Sudan intersect with conflict dynamics and what are the programming implications?	Pending research proposal and FCDO kick off call
Goal 3	3.1 Pre & post conflict, how have women and girls’ types of decision making changed at different levels (e.g. household, community, local governance, institutional) and what are the implications for programming?	3.1 - How have women and girls’ roles in decision making changed at different levels, including household, community, formal governance (local and national), peace processes and humanitarian response? What are the linkages between changes at different levels? What implications do these changes have for programming?	FCDO kick off call conducted and research proposal/team in development with potential for WS1 primary data collection to compliment via social media listening
Goal 5	5.1 What are the legitimate (legal) innovative ways of getting cash into Sudan? Who and what is it supporting?	5.1 - Primary ways of getting cash and financing into Sudan – implications for programmatic improvements and risk management	Initial research delivered

Action Learning Research: Another key WS2 function is to deliver action learning research on new or innovative areas of programming to make timely and useful recommendations to guide decision-making. During inception and initial implementation SIMAP, with FCDO, explored opportunities to undertake ALR to provide evidence in support of answering of what works for stimulating the private sector in Sudan. Initial discussions with Financial Sector Deepening Africa (FSDA) and their delivery partner Wellspring Development were conducted to begin to identify potential entry points for ALR, but both eventually decided they could not commit to the initiative and the FSDA component of SSGP has subsequently ended. At this stage it has not be possible to identify any new opportunities. While ALR remains available as a tool, with BOS agreement, WS2 is now moving away from ALR.
Describe any changes to this output during the past year, and any planned changes as a result of this review
As part of the broader restructure of SIMAP (see overall recommendations), FCDO and the SIMAP team have discussed redesigning WS2 to focus more on strategic evidence and learning at the portfolio-level. The specificity around this is still in discussion however several specific functions have been outlined as focal for WS2 going forward, around collating key statistics and contextual metrics and supporting country business planning activity through detailed diagnostic work.
WS2 will retain the learning strategy development role, drawing on evidence sources across SIMAP workstreams, programme produced evidence and external sources to synthesise key learning for FCDO strategic processes. Ensuring coordination across SIMAP workstreams will continue helping to mitigate against the risk of siloed learning and engagement processes. WS2 will also retain a primary responsibility for uptake and engagement across BOS.
Lessons learned this year and recommendations for the year ahead
The learning strategy focuses on answering broad Learning Questions via incremental evidence building against sub-questions. Additionally, incremental SQ evidence may be complemented by other internal (BOS and SIMAP) and external evidence, at quarterly, six-monthly and annual moments to reflect and adapt to evolving contexts.
Given that SIMAP is early in implementation, the learning strategy is still nascent and requires longer to bed in and for evidence to build. It will also be crucial to maintain a level of flexibility with overall approach to learning to ensure SIMAP is able to respond to changing priorities for BOS. As the evidence is built this is intended to allow the SIMAP to facilitate BOS’ engagement with evidence periodically, to interpret what this means for both programming and country strategy and to adapt to emergent evidence and the evolving context. The volatility of the programming context means that it will be important to build in opportunities to revisit learning questions to ensure they remain strategically relevant. Considering the intentionally incremental nature of evidence building around these questions, it will take time for salient learning to be drawn against the learning questions.
Engagement cycles have been difficult to identify and internal structures need to be strengthened in BOS to support learning. Given institutional challenges and the time-poor context for BOS, this means that it has been difficult to identify opportunities for learning and reflection with BOS. An emergent solution may be for SIMAP to trial and test methods for engagement together with BOS to discover what works to maximise learning engagement. Thereafter, clearer products/process surrounding these learning and reflection points can be agreed to maximise uptake/engagement.
Initial attempts to engage implementing partners in Action Learning Research (ALR) has been difficult, especially considering that the IP approached for ALR was only in very early implementation and had other MEL priorities. While ALR will remain a key tool offered by SIMAP and may be utilised if there is interest and demand, recognising these challenges in getting traction/interest, it will not be a specific focus for the programme going forward.

Recommendations
- SIMAP should re-design WS2 to incorporate the collection and collation of strategic evidence to support country plan development and reporting – to cover key statistics on context, on problem drivers and sub-national need and delivery mapping. Given the current stage of the programme, there has not been the opportunity yet for SIMAP to contribute to and monitor the strategic effectiveness of the Sudan Country Plan but this is likely to change as FCDO move into designing the next phase of its Country Plan.
- SIMAP to update logframe indicator 2.2 to reflect the re-focus away from ALR and develop new output indictors for the following year which reflect the changed focus of WS2 (see below).
- SIMAP should continue to seek learning spaces and moments, when synthesis offers strategic learning and work with FCDO to continue to identify opportunities for uptake and engagement of products developed.

Output Title	Research & Analysis: FCDO stakeholders receive high-quality, rapid research and evidence reports on priority topics and themes
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
% of FCDO staff who rate the quality of research and analysis deliverables produced by the supplier as good or excellent	Finalise development of assessment rubric / >80% (launch after 6-months of implementation)	Met / The assessment rubric has been developed and while it is too early for the planned survey to be rolled out, early indications suggest positive feedback on the research outputs completed to date.
Number & percentage of research outputs delivered as per agreed MEL workplan	2	Met / 2

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output met its milestone in terms of research outputs and scores an A. This output is linked to Workstream 3 (WS3) which aims to undertake strategic analysis to inform development policy and approaches, improve contextual understanding and monitor strategic effectiveness. In practice, this workstream has done so by focusing on research aligned to the learning strategy and research as a response to special requests.
The two pieces of research delivered between January and March 2025 supported key priority areas for learning related to the learning strategy sub-question 5.1 - on Primary ways of getting cash and financing into Sudan – implications for programmatic improvements and risk management. Due to the rapidly changing context of Sudan, needs related to this sub-question evolved into the following research initiatives built around the questions below:
- 5.1.1: What are the lessons from other contexts that might help mitigate the likely challenges of an uneven introduction of a new currency note in Sudan and/or inform preparatory steps which manage risk well?
- 5.1.2: What are the possibilities for mobile money, and what recommendations can be made to guide collective next steps in this space?

Feedback received from the relevant goal lead indicates an appreciation of the quality and utility of these outputs and BOS are currently acting on the findings. The current plan for dissemination with other partners and uptake includes: (1) reviewing and summarising the products to enable sharing them more widely; (2) planning a presentation of the findings to key stakeholders; and (3) supporting identification of key opportunities for advocacy that supports collective steps moving forward.
Progress has also been made on research to better understand climate resilience and adaptation in Sudan and its implications for future programming. The final products of this initial research initiative on climate resilience are expected to be shared in April 2025.
Describe any changes to this output during the past year, and any planned changes as a result of this review
The volatile context of Sudan and uncertainty over broader FCDO priorities and resourcing for the years ahead requires a flexible approach to identify and proceed with non-previously planned research initiatives. Changes have already been introduced during the review period to respond to emerging needs, and Special Requests for research have already been acted upon. Currently, two pieces of research are being delivered under this category (SR1 on Climate Resilience and Adaptation in Sudan and SR2 on Safeguarding), and this responsive approach is expected to continue in the next year.
Lessons learned this year and recommendations for the year ahead
The difficulties in collecting data in the country require more innovative solutions to complement research activities and analysis in the country. SIMAP is identifying which research questions could benefit from innovative methods (see Section on Output 1 above). Social Media Listening (SML), alongside other methods such as digital avatars, and domain intercept technology (DIT) to disseminate surveys may help to overcome some of the security and bureaucratic challenges faced by data collection efforts to date.
Recommendations
- SIMAP should continue to ensure that a flexible approach is taken to research outputs, making sure that enough resource is available to respond to emerging priorities when they come up.
- In order to continue responding to shifting research priorities, SIMAP should continue strategically growing the network of consultants, ensuring a range of international and local experts. The SIMAP team should continue to explore flexible approaches to contracting consultants - accepting that products and activities agreed in the TOR may be shifted at any time in their scope and timelines.
## D: VALUE FOR MONEY
Key cost drivers and performance
The key cost drivers for SIMAP are primarily associated with technical expertise. This includes fees for the core working group, such as the team leader, workstream leads, analysts, TPM coordinators, and programme management staff. Travel costs have been minimal, and there have been no assets under the programme. An unexpected saving was realized in the security budget due to the inception phase extending up to November 2024. OPM has effectively managed costs in line with the agreed workplan. They have also developed a comprehensive Value for Money strategy and have reported against it as part of their annual report. Some details are included below.
VfM performance compared to the original VfM proposition in the business case
Economy is defined as: SIMAP manages resources economically buying inputs at the right quality and price. Judgements against the economy criterion are made on the basis of three sub-criteria:
1. OPM Management costs as a percentage of total costs compare well with appropriate benchmarks and over time. Management costs have remained at 10% which is in-line with the original contract budget for SIMAP. This percentage is expected to reduce overtime as SIMAP moves fully into implementation reflecting that, typically, more management time is required during programme set-up.
2. Average unit costs of key inputs of appropriate quality compare well with appropriate benchmarks (consultant fee rates, flights, local transport, hotels, etc). Fee rates have remained broadly in-line with the original budget with slightly lower rates for project leadership and project management, but a slightly higher weighted average fee rate for the Technical Advisor. This reflects the use of more senior members of the Short-Term Expert Pool to help shape the delivery of initial research products delivered through WS3. Expenses are also in-line with the original budget in the pro-forma.
3. SIMAP can demonstrate that it follows good practice to manage key economy drivers and costs. SIMAP follows good practice in managing its key cost drivers. Examples of these include: (i) delivery of TPM activities is predominantly through Consilient’s network of enumerators based in all states of Sudan, not only supporting SIMAP’s access across the country but minimising costs related to travel; (ii) all changes to personnel have been benchmarked against what FCDO was offered in the original budget in terms of fee rates, when offering like-for-like substitutions and short term experts are selected only on the basis of a demonstration of the additional value that they would bring to delivery; (iii) travel and events are supported via OPM’s offices in Nairobi and Ethiopia (given location of BOS) and support in sourcing accommodation and managing local travel.
Overall, we judge that SIMAP has offered Good VfM against the economy criteria.
Efficiency is defined as: SIMAP produces high quality outputs that enable stakeholders to make better decisions using the available resources. Judgements against the efficiency criterion are made on the basis of four sub-criteria:
1. Allocation of spend across the three SIMAP workstreams supports delivery of the overall goal of SIMAP as defined in the ToC (allocative efficiency) After just four full months of implementation it is too early to judge performance against some sub-criteria, specifically against allocative efficiency which provides judgements of how SIMAP is allocating resources in response to BOS’ emergent need.
2. Outputs are relevant and responsive, delivered at the required quality and quantity, on time and within budget (technical efficiency) SIMAP has largely met expectations in terms of its technical delivery in terms of timely submission of outputs, with the exception of the delivery of planned TPM activities that have been delayed into Q1 of FY25/26 largely as a result of factors of outside of SIMAP’s control. Nonetheless, feedback received to date on the quality of outputs across all workstreams has been positive from both BOS and IP stakeholders.
3. Evidence that SIMAP is managed adaptively to reflect evolving opportunities and risks, respond to stakeholder needs, builds on learning and resources are reallocated accordingly (dynamic efficiency) Whilst at this stage of delivery it is too early to evaluate progress against dynamic efficiency, lesson learning it is at the centre of SIMAP. The learning strategy, centred around the Country Plan Goals provides a structured framework for ensuring that evidence products are relevant. FCDO and SIMAP regularly discuss the prioritisation of work in particular as it relates to which TPM activities to prioritise, learning questions to answer, or in taking steers to answer Special Requests through the research workstream.
4. Strong relationship and communication between FCDO and SIMAP, ensuring effective collaboration and a co-design approach (relational efficiency) SIMAP has prioritised building relationships with BOS and its IPs in its first year. SIMAP has built a strong working relationship with the programme PRO and PM meeting every two weeks to discuss progress, issues arising and next steps. Monthly Programme Boards and Quarterly Steering Committees provide further opportunity for BOS to provide feedback on SIMAP’s performance. Significant efforts have been made to build relationships with IPs, prioritising early and continuous engagement with IPs. SIMAP has sought to involve IPs at all stages of the TPM process.
Overall we judge that SIMAP has offered Good VfM against the efficiency criteria.
Effectiveness is defined as: SIMAP is achieving its intended outcomes. Judgements against the efficiency criterion are made on the basis of one sub-criterion: Stakeholders, including FCDO and Implementing partners use evidence and learning produced by SIMAP to improve programming, policymaking or other strategic decisions. It is too early to make a judgement on whether SIMAP is showing effectiveness in its VfM but there are some early indications that the programme is beginning to contribute to its intended outcomes.
Equity is defined as: SIMAP is sensitive to the needs of different groups in Sudan, including minority or marginalised groups. Three inter-linked themes that underpin equity – Gender Equality and Social Inclusion (GESI), climate change and conflict – are identified as cross-cutting themes in the updated ToC developed during inception. Judgements against the equity criterion are made on the basis of three sub-criteria:
1. Outputs delivered by SIMAP are designed using conflict, contextual, and/or GESI analysis to ensure that needs of different groups are integrated. SIMAP incorporates GESI considerations into the design of many of its outputs. SIMAP has sought to ensure that safeguarding, gender and conflict-sensitivity considerations are reflected in SIMAP’s own TPM and primary data collection activities. This includes ensuring that primary data collections are safe for researchers, research participants and wider communities in line with FCDO safeguarding requirements.
2. Knowledge products produced by SIMAP target GESI SIMAP has delivered a series of knowledge products that directly address GESI considerations. Early in implementation SIMAP completed three pilot TPM activities all focused on providing GESI relevant evidence. There are also a number of pipeline research products that specifically target GESI (e.g. safeguarding research, GESI analysis)
3. GESI considerations are integrated into decision making. SIMAP seeks to ensure that GESI considerations are incorporated in programme decision-making processes. The inclusion of a Gender, Conflict, and Safeguarding Lead in SIMAP’s programme leadership team makes this explicit. In practice this role has provided cross-cutting support, where relevant across all three workstreams, which includes support to ensure appropriate safeguarding practices are applied during primary data collection, the design and implementation of the MEL Systems Review, the design of the learning strategy, and the delivery of specific learning or research products that respond to this learning strategy.
Overall, we judge that SIMAP has offered Excellent VfM against the equity criteria
Assessment of whether the programme continues to represent value for money
SIMAP continues to represent VfM, particularly given BOS's limited presence in Sudan. The rapid research outputs from SIMAP are vital for addressing key policy questions and guiding future programme designs. However, the effectiveness of SIMAP’s Third Party Monitoring is contingent upon the willingness of implementing partners to participate. This includes obtaining working permissions on behalf of SIMAP to accompany them on distribution trips. Challenges have arisen, particularly with some UN partners who reject TPM based on the single audit principle. Additionally, there have been delays in securing permissions to join trips, largely due to bureaucratic hurdles in Sudan.
Another significant issue is that SIMAP is currently restricted to conducting TPM only for humanitarian and FGM programmes, excluding governance and resilience programmes within the portfolio. This limitation raises concerns about whether SIMAP can be considered a comprehensive portfolio monitoring programme.
To ensure continued VfM, SIMAP needs to undergo restructuring to reduce dependency on the current TPM approach. This includes exploring alternative methods of primary data collection and integrating governance and resilience programmes into the monitoring framework.
E: RISK
Overview of risk management
The overall residual risk of SIMAP remains unchanged at moderate. The programme has varying levels of risk appetite towards specific risk categories: eager for strategy & context, policy & programme delivery, and financial and fiduciary risks; receptive for safeguarding; and cautious for people, reputational and public service delivery & operations.
The operating context during the year under review has continued to be extremely volatile and challenging, marked by ongoing conflict, insecurities, and severe access constraints, which have significantly impacted humanitarian operations and development programming. Risks are monitored and updated monthly by the programme team through the Aid Management Platform online risk register. Regular discussions with the implementing partner occur during monthly programme board meetings, where the partner submits an updated risk register. The programme team reviews the online risk register to ensure that all possible risks are listed, and any emerging risks are highlighted. Any risk that falls outside of appetite is escalated according to the procedure outlined in BOS’s risk management approach. SIMAP currently has no risk outside of appetite.
It is important to note that BOS did not conduct the due diligence assessment (DDA) for OPM, as they were contracted via FCDO’s framework agreement led by the central programme delivery commercial team. The DDA has been completed as part of this process, and BOS does not have access to this DDA.
Risk Appetite and Residual Risks
Strategy and Context: SIMAP’s risk appetite for strategy and context risks is Eager, which aligns with BOS’s risk appetite but is higher than FCDO’s Receptive appetite. Over the year, deteriorating security conditions in Sudan and worsening bureaucratic and administrative impediments have made it difficult for enumerators to obtain necessary permissions to access programme sites, hindering monitoring activities. The residual risk rating for strategy and context risks is Major, which is within appetite. The current risk appetite is deemed appropriate for the programme.
Safeguarding: The risk appetite for safeguarding risks is Receptive, similar to BOS’s appetite but higher than FCDO’s Cautious appetite. Safeguarding risks have significantly increased for all programmes operating in Sudan due to the escalating conflict. The high-risk appetite has allowed SIMAP the flexibility to send enumerators to hard-to-reach areas to verify results from implementing partners. The residual risk rating for safeguarding risks is Moderate, which is within appetite, enabling SIMAP to deliver effectively within this level of tolerance.
Reputational: For reputational risks, SIMAP’s appetite is Cautious, aligning with FCDO’s appetite but lower than BOS’s Receptive appetite. This cautious approach is due to SIMAP’s aim to maintain a relatively low profile in delivering UK aid-funded activities, ensuring perceived independence as an independent monitoring programme. Reputational risk has remained low throughout the year, peaking only in the last quarter following the reduction of ODA spend to 0.3%. The residual risk rating for reputational risk is Moderate, which is within appetite, allowing SIMAP to operate comfortably.
Policy and Programme Delivery: The risk appetite for policy and programme delivery is Eager, similar to BOS’s appetite but higher than FCDO’s Receptive appetite. This high appetite has facilitated flexibility in workplans while operating in an open conflict. Throughout the year, particularly after the implementation phase commenced in December, SIMAP faced challenges in completing TPM activities on time due to delayed responses and pushbacks from implementing partners. Despite these challenges, SIMAP was able to adapt timelines and methods to deliver results in most cases. The residual risk rating for policy and programme delivery risk is Moderate, which is within appetite, confirming the appropriateness of the current risk appetite.
Financial and Fiduciary: SIMAP’s risk appetite for financial and fiduciary risk is Eager, similar to BOS’s appetite but higher than FCDO’s Cautious appetite. This high appetite is essential for operating in Sudan’s active conflict, where the risk of aid diversion is significant. Financial and fiduciary risks arise from enumerators working in hard-to-reach areas without direct oversight, which may lead to bribery for access and subsequent aid diversion. The residual rating for financial and fiduciary risk is Moderate, which is within appetite, allowing SIMAP to operate effectively.
People: The risk appetite for people risk is Cautious, aligning with FCDO’s appetite but lower than BOS’s Receptive appetite. This cautious approach is necessary for SIMAP, a multi-year adaptive programme that requires effective oversight and management for smooth continuity and strong knowledge transfer. During the review year, SIMAP had no significant people risks, although there was one risk associated with staff turnover that created a gap between the end date of the previous PRO and the start date of the new one. This risk was managed by temporarily assigning the head of the programme hub as PRO, ensuring continuity through the programme manager. This risk is now closed.
Public Service Delivery and Operations: The risk appetite for public service delivery and operations is Cautious, consistent with both FCDO’s and BOS’s appetites. The programme has not encountered any risks in this category, nor do we anticipate any in the future.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
The programme team has developed a strong working relationship with OPM and Consilient, facilitated by regular structured meetings, including bi-weekly check-ins, monthly programme boards, and quarterly steering committee meetings. These meetings focus on progress updates, financial discussions, and risk management. Additionally, informal and ad-hoc meetings with OPM provide further opportunities for collaboration. OPM is responsive and timely in communications, although there have been occasional delays in sending materials when the team leader is on leave. Overall, the governance structure has proven effective for the programme’s current structure, with workstream leads delivering their tasks promptly.
The quality and timeliness of reporting for SIMAP have been generally positive. Two narrative reports, the inception report and the annual report, were submitted on time, despite the first drafts receiving substantial comments that were effectively addressed in the final versions. OPM also provides monthly financial reports, which include actuals and forecasts, submitted by the 23rd of each month; although there were initial delays, the team has since established a consistent submission rhythm. While the financial reports are of high quality, featuring detailed breakdowns, issues arose towards the year's end with the reporting of TPM costs as a lump sum, and accuracy concerns persist, with variances between forecasts and actuals reaching up to 40%.
OPM has made significant strides in proactive risk dialogue. OPM's initial risk management practices required improvement, as risk registers were submitted only upon request prior to monthly meetings, leading to some risks not being reviewed for extended periods. Following constructive feedback, the programme team now receives risk registers automatically each month, enhancing communication and transparency. OPM is now consistently identifynge new risks during structured meetings, and the recent introduction of a dedicated time slot for risk discussions has allowed for more thorough exploration of key issues, enhancing the overall effectiveness of risk dialogue.
OPM submitted a delivery chain map at the beginning of the inception phase, which was included in both the inception and annual reports. Notably, there were no changes to the delivery chain during the year under review. Additionally, OPM provided an asset management process guideline as part of the inception report; however, it is important to note that the programme currently has no assets.
Financial performance
The total budget for the SIMAP programme is £7.5 million, with £1.3 million allocated for the year under review. OPM spent £827,328 during this period. A portion of the remaining budget was allocated to a programme-funded role introduced in September, supported by a small change business case addendum. However, financial management throughout the review period has faced challenges, as indicated by significant underspending and considerable variances between forecasts and actual expenditures in most months. Towards the end of the review period, there were concerns regarding OPM's oversight of Consilient’s financial management, particularly following a contract amendment that enabled Consilient to forecast their needs for TPMs in advance and invoice accordingly, resulting in a notable increase in actuals.
Table 4: SIMAP Programme Financial Performance
	CA1 Proforma Total	Actuals to Date	Variance to CA1 Proforma	Variance %
Fees	£824,288.45	£660,158.60	£164,129.85	20%
Expenses	£298,642.46	£167,169.99	£131,472.47	44%
Total	£1,122,930.91	£827,328.59	£295,602.32	26%

Commercial performance
During the year under review, SIMAP underwent one contract amendment, which marked the transition from the inception to the implementation phase. This amendment included changes to key personnel, the finalisation of supplier performance KPIs for the implementation phase, adjustments to subcontractor fieldwork expense claims, and modifications to the commercial proforma to reflect budget line adjustments for implementation.
The performance KPIs comprise four programme management and three technical KPIs. Table 5 presents the current scoring against each of the seven KPIs.

Table 5 Key Performance Indicators

Key performance indicator	Performance against	Weighting	Proposed Score (out of 4)	Weighted Score
KPI 1 Financial management	Monthly submission of accurate invoice and forecast variance within 10% of budget, received by 23rd of each month	12.5%	1	13
KPI 2 Delivery	% deliverables submitted on time	12.5%	3	38
KPI 3 Relationship management	% of FCDO and IP staff who rate their engagement with the Supplier as good or excellent (with a focus on professionalism and utility of advice)	12.5%	3	38
KPI 4 Flexibility	Updates to schedule of work agreed within 10 working days of programme management board meetings	12.5%	4	50
KPI 5 Quality	% of FCDO staff that rate SIMAP deliverables as of good quality or higher (with a focus on accessibility and usefulness for supporting delivery and/or policy making)	17.5%	4	70
KPI 6 Utility & learning	% recommendations made by SIMAP implemented/actioned by IPs	17.5%	3	70
KPI 7 Capacity building	% of implementing staff that rate the quality of TA received from the supplier as good or excellent; example adaptations made by IPs in response to TA	15.0%	3	45
Total Score (Max 400)				305

FCDO performance
The SRO, PRO & Programme Manager have maintained regular communication with SIMAP staff from inception through to the current implementation phase, through: bi-weekly update meetings, monthly programme boards and quarterly steering committees. There has also been good engagement with BOS technical advisors on research deliverables and TPM. In the next year, the FCDO programme team should continue to build on this momentum, strengthen communication on SIMAP activities within BOS and look for more opportunities to engage parts of office that have not been able to engage with SIMAP to date.
Recommendations
OPM should implement more robust financial oversight mechanisms for TPM activities, ensuring accurate breakdown of costs and expenses in monthly reports. OPM should focus on refining the accuracy of financial forecasts to reduce variances between projected and actual expenditures. Adopting a more realistic forecasting approach will enhance financial planning and resource allocation.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring & Evaluation
While SIMAP plays a key role in improving the quality of monitoring and learning across BOS’s portfolio, it is important the programme has its own approach to assess progress against the Theory of Change and to support regular reviews.
In the reporting period, the SIMAP team have revised their programme log frame, as part of the inception phase deliverables, to track progress against each area of the ToC, aligning with programme value for money indicators. The log-frame will form the basis of Annual Reviews and provide insight into whether the programme is delivering as intended and what adjustments might need to be made. While specific indicators and methodologies will need to be discussed with OPM during the inception phase, indicative indicators at the impact and outcome level are provided in the table below.
The SIMAP team has developed internal tools to support monitoring progress against its logframe which include: (1) an output tracker to track the progress of deliverables against milestones; (2) a recommendations tracker to track recommendations made by SIMAP for BOS, IPs or other stakeholders; and (3) a feedback tracker to enable capture of feedback provided to SIMAP. These will be complemented by the bi-annual survey of FCDO staff, which will launch after the first 6-months of implementation and the annual survey of IPs, scheduled for the end of 2025.
SIMAP's SRO, PRO & Programme Manager have maintained regular communication with SIMAP staff from inception through to the current implementation phase, through: bi-weekly update meetings, monthly programme boards and quarterly steering committees.
During these meetings, the SIMAP team presents an update on progress against each component, flags issues arising and outlines next steps. SRO feedback and discussion around this update then informs SIMAP decision making for the next two weeks. In addition, the PRO and Programme Manager are in frequent ad hoc communication with the SIMAP team leader and component leads around specific issues as they arise.
Evidence & Learning
The generation of actionable learning is a core function of SIMAP’s approach including both support to BOS and IPs as well as ensuring that SIMAP continually learns from its own delivery with the view to enhancing performance over time. As such SIMAP has informal and formal structures to support the capture of lessons related to the delivery. Internally SIMAP, through bi-weekly Programme Team Leadership meetings, offers space to reflect on progress, blockers and potential solutions.

Where relevant the programme has sought to capture lessons from delivery during inception and the initial implementation phase, for example, the TPM Lessons Learned Summary Report capturing lessons learned from the TPM pilot. SIMAP’s Governance structures further support this specifically Quarterly BOS programme steering boards that provide a formal structure for BOS to provide feedback on SIMAP’s performance.

It is envisaged that this Annual Review process itself will provide an opportunity for the SIMAP team to reflect on its utility and performance based on BOS colleagues’ assessment as well as leveraging this for adapting its approach as it moves into the next 12 months of implementation.

Date of last narrative financial report	23 April 2025	Date of last audited annual statement