MOU Amendment No -08

Project Name- Ethiopia Crises to Resilience (EC2R) with British Red Cross

Project Number: 301474-406, 301474-407, 301474-417 and 301474-418

I refer to the Memorandum of Understanding (“Memorandum”) signed between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and the British Red Cross (BRC) on 24 August-2023, and subsequent amendments signed on 31 –January 2024, 27 June 2024, 25 July 2024, 30 October 2024, 31 January 2025, 19 –March 2025 and 17 –April 2025.

Following recent discussions, FCDO proposes to increase the amount made available to BRC by £1,960,403(one million nine hundred sixty thousand four hundred three pounds sterling) and extend the end date of the agreement.

I propose that the end date of 30 June 2025 in paragraph 2 of the Memorandum of Understanding of Amendment 6 be deleted and replaced with 31 March 2026.

I propose that the figures and words £9,109,500.58 (nine million one hundred nine thousand five hundred pounds sterling and fifty-eight pence) stated in paragraph 3 of MOU Amendment 7 is replaced by the figures and words of £11,069,903.58 (Eleven million sixty-nine thousand nine hundred three pounds sterling and fifty-eight pence).

This letter also gives confirmation to FCDO that:

- The total Red Cross allocation under the Ethiopia Crises to Resilience (EC2R) programme from 25/08/23 – 30/06/2025 stated in paragraph 4 of MOU Amendment no. 7 £16,584,149.72 is deleted and revised to £21,784,149.72 to reflect the total allocation made so far. This will be split into two ways between Ethiopian Red Cross Society (ERCS) (£ 10,714,246.14) and the British Red Cross (BRC) (£11,069,903.58). The programme date is also revised from 30/06/2025 to 31/03/2026. The ERCS will continue representing the main operational organisation in country with the BRC providing support on international procurement and technical support. FCDO will continue to have a separate MOUs with ERCS ad BRC to manage the financial transaction delivery of the service.
- The current disbursement of £1,960,403(one million nine hundred sixty thousand four hundred three pounds sterling) will be paid under the below project number:

Project Number: 301474-407: £1,960,403(one million nine hundred sixty thousand four hundred three pounds sterling) will be for Resource Departmental Expenditure Limits classified as RDEL in FCDO expenditure classification.
The payment will be made in the following tranches.

Amount	Timeline	Status
£1,049,402	August-2023	Paid
£552,120	January - 2024	Paid
£4,681,752.06	June – 2024	Paid
£2,270,000	July - 2024	Paid
£431,226.52	Oct-2024	Paid
£125,000	April-2025	Paid
£1,960,403	June - 2025	To be paid after parties have signed this agreement.

Unless clearly stated here, other terms and condition remain valid as stated under the original Memorandum of Understanding and other subsequent amendments signed between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth & Development Office (“FCDO”) and the British Red Cross (BRC).

8	This letter of amendment will place on record our common understanding of the above change and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 08-2025.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of the Partner:
Name:
Position:
Address/Contact Details:
Date: