## Annual Review

Title: Ethiopia Crises to Resilience (EC2R)
Programme Value £ (full life): £350m		Review date: 31/01/2026
Programme Code: 301474	AMP start date: 31/01/2022	AMP end date: 30/06/2026

Summary of Programme Performance

Year	2022	2023	2024	2025
Overall Output Score	A	A	A	A
Risk Rating	MAJOR	MAJOR	MAJOR	MAJOR

DevTracker Link to Business Case: https://iati.fcdo.gov.uk/iati_documents/D0002694.odt
DevTracker Link to results framework: D0005958.xlsx

## A: SUMMARY AND OVERVIEW

Description of programme.

The “Ethiopia Crises to Resilience” (EC2R) programme was designed to provide life-saving assistance to those currently in need and invest to reduce the impact of future shocks on vulnerable populations. EC2R aligns with the UK humanitarian framework to:

PRIORITISE: deliver lifesaving assistance to Ethiopia’s most vulnerable populations, with a focus on getting aid to the hardest-to-reach communities.
PROTECT: protect civilians affected by conflict and crises, with a focus on gender-based violence.
PREVENT: support the resilience of Ethiopia’s poorest households to cope with shocks through predictable social protection and improve the ability of systems to identify risks early.

The EC2R programme was initially approved through an emergency submission in January 2022 (£22 million). A business case to cover the emergency submission phase and extend the programme in both cost and time to March 2025 was approved in October 2022, with the first (non-retrospective) payments associated with the programme made in December 2022. A further Business Case Addendum was approved in December 2024, although HMT only formally approved FY2025-2026, noting that the outer years would be subject to the upcoming, multi-year Spending Review.

EC2R is a flexible £350 million programme which will:
1. Provide multi-sector humanitarian assistance to meet the needs of Ethiopia’s most vulnerable populations;
2. Support poor households so they are better able to withstand disasters and shocks; and
3. Invest in the humanitarian system so it can identify risks and respond early and cost-effectively.

This 2025 Annual Review covers the period of June 2024 – June 2025, with UNICEF, World Food Programme (WFP), Ethiopian Red Cross Society (ERCS), British Red Cross (BRC) and REACH results reported in August 2025 and results for the World Bank supported Productive Safety Net Programme (PSNP) reported in September 2025.

An external reviewer – a Humanitarian Adviser from another FCDO post – led this review to provide impartial scrutiny, working closely with British Embassy (BE) Addis Ababa’s Resilience and Humanitarian Team. The review involved field monitoring of humanitarian cash, PSNP, WASH (Water, Sanitation and Hygiene), health and nutrition activities in Tigray Region, and health and WASH activities in Oromia Region. The BE Addis Ababa Resilience and Humanitarian Team fed into the review, and technical advice was provided by FCDO’s central Humanitarian WASH Adviser. The review began with a desk review of key EC2R documents and reporting. A visit in September 2025 included interviews and discussion with BE Addis Ababa colleagues, staff from UNICEF, WFP, ICRC, Ethiopian Red Cross Society, Tigray Development Association (implementing on behalf of UNICEF), REACH, UN OCHA, a small number of local water and health boards, the staff of key facilities being supported by EC2R and importantly, the people being served by EC2R. The visit to the field sites included an inspection of infrastructure built using CDEL, and key services being delivered.

Summary supporting narrative for the overall score in this review.

The overall score for the programme is A as outputs have largely been met. However, there remain concerns, also highlighted in the 2024 Annual Review, about the programme’s ability to deliver on the outcomes and impact in the Theory of Change. Partners have delivered from a sector perspective, but the overall coordination of the programme, integrating sectors, and targeting geographies impacted by a humanitarian shock could be stronger and currently represents a missed opportunity.

EC2R remains relevant and speaks closely to the five top response priorities identified by UNOCHA in their Humanitarian Response Priorities and Gaps update of July 2025[1]:
[1] Ethiopia: Humanitarian Response Priorities and Critical Funding Requirements and Gaps (July - September 2025) - Ethiopia | ReliefWeb
- Integrated health and WASH response to ongoing cholera outbreaks: Despite progress under Ethiopia’s Cholera Elimination Plan (2022– 2028), cholera remains a serious public health threat due to persistent challenges in water, sanitation, and overstretched health systems. As of May 2025, 4,373 cases were reported, with active transmission in Oromia, Amhara, Afar, and Gambella.
- Food security and nutrition response areas affected by conflict/insecurity: Food insecurity remains critical despite improved national harvests in 2023–2024. Poor Belg rains compounded by conflict, displacement, and limited access, have deepened food and nutrition needs. Vulnerable groups, including IDPs and returnees, face deteriorating food consumption and rising malnutrition.
- Anticipatory action and rapid response to major floods and landslides in areas with high number of Internally Displaced Persons (IDPs) and/or affected by conflict/insecurity: The Ethiopian Meteorological Institute (EMI) forecasts normal to above-normal Kiremt rainfall (June–September 2025), increasing the risk of floods and landslides. Areas likely to be affected include central and southern Tigray, Afar, eastern Amhara, northern Somali (65% probability), and western parts of the country (60% probability).
- Multisectoral response to IDPs in densely populated sites: IDPs reside in over 200 collective centres and planned sites, and within informal settlements and host communities. Tigray and Amhara have the largest number of planned sites, while Somali, Afar, and Oromia host most informal sites. Service access remains extremely low: 22% for WASH, 44% for health, and 26% for education. Overcrowding, insufficient shelter, and protection concerns persist, with 128 sites reporting no shelter and 63% of IDPs reporting lack of privacy.
- Support to areas with recent IDP returns: At least 2.8 million IDPs have returned to their places of origin in the last three years - mainly in Tigray, Amhara, and Afar. In Western Oromia (East Wollega Zone). However, many remain without shelter, livelihoods, or access to essential services.
Furthermore, women and girls in Ethiopia face consistently high levels of violence, including conflict-related sexual violence (CRSV) and intimate partner violence (IPV), and rising levels of child marriage and female genital mutilation (FGM). GBV in Ethiopia is sustained by high levels of gender inequality and exacerbated by a complex intersection of drivers fuelled by various emergencies, such as ongoing conflicts, drought and seasonal flooding.

Output Score Breakdown

EC2R is a multi-sectoral programme targeting humanitarian needs, development and resilience, and technical assistance and evidence generation. The primary implementing partners contribute to a mixture of outputs, and Output 1 has been thematically divided into humanitarian sectors. The weighting of each output was adjusted in August 2025 to better reflect strategic priorities, level of effort and budget allocated to each output, and approved by the Development Director the same month.

Output	Weight	Score
Output 1.1 – Nutrition	21.2%	A+
Output 1.2 – Health	4.3%	A
Output 1.3 – WASH	7.8%	A
Output 1.4 – Cash	5.9%	A+
Output 1.5 – Protection	2.7%	A+
Output 1.6 – Education	3%	A
Output 2 – Humanitarian system capability	20%	B
Output 3 – Improved availability of humanitarian data	15%	A+
Output 4 – PSNP	20%	A

Major lessons and recommendations for the year ahead [1/2 page]

A number of the recommendations made in the 2024 Annual Review haven’t been fully delivered or haven’t yet had the desired impact. There are four major recommendations for FCDO Ethiopia to consider this year, some of which build on those from the 2024 Annual Review. These broadly cover two areas. One, tightening the programme strategy back in line with the Theory of Change, and two; simplifying the delivery mechanisms and management approach to improve the likelihood of outputs achieving the programme’s desired outcomes.
PROGRAMME DESIGN
PRIORITISE meeting lifesaving needs. Sharpen the lifesaving focus of the programme, in line with Output 1 in the Theory of Change. This will require:
  1. Integration – Consider how to better integrate Nutrition, Health, WASH and potentially education in emergencies and cash assistance to achieve outcomes over outputs. Targeting could be led by severity and scale of acute malnutrition. The team may want to consider dropping the Moderate Acute Malnutrition (MAM) component and focusing on prioritizing responding to Severe Acute Malnutrition (SAM) using the nutrition, health and WASH activities.
  2. Targeting – EC2R must tighten its geographic targeting at the strategic level and consider moving away from targeting geographically output by output as is done currently. In the spirit of the UK humanitarian framework, the Humanitarian Reset workstream, and in line with FCDO Ethiopia’s Resilience and Humanitarian team strategy, target hard-to-reach, conflict-affected areas and rapid onsets with a humanitarian response, balancing the partner’s risk and duty of care considerations. There may be opportunities to drive this given increased geographical targeting in the planning for Ethiopia’s HNRP 2026. This will involve difficult decisions about relocating some of EC2R’ activities away from geographies with needs; albeit development and governance-driven needs, not humanitarian shock-driven needs. EC2R should consider prioritizing and scaling up Anticipatory Action to respond to cyclical climatic stresses (discussed in PREVENT) in these locations.
1. PROTECT populations. Despite the headline focus in the Team’s strategy on women and girls, this isn’t reflected in the programme as it currently stands. The Team should consider:
  1. GBV – The scale and weighting (2.7%) of the GBV output relative to other areas of the programme is very low given its primacy in the Theory of Change. EC2R is delivering the GBV component through the mandated Child Protection actor, as opposed to a specialist GBV actor. The team should consider whether partner diversification should be considered, whether the approach should be scaled up with an increased proportion of budget and given a higher weighting.
  2. Indicators - Whilst the level of disaggregation at output level generates a lot of data on the number of women and girls accessing support (or assumed to access in Output 1.3 WASH), the indicators give very little indication of the outcomes on women and girls, and how that differs from men and boys. Indicators to understand to what extent support is gender sensitive will strengthen EC2R.
2. PREVENT and manage shocks. EC2R has a significant component seeking to prevent humanitarian need.
  1. PSNP – The team should consider whether to relocate PSNP into Output 2 (Humanitarian System Capability), alongside the support to ERCS through BRC. PSNP currently feels bolted onto EC2R rather than a core component of it, further undermining the coherence of the BC. The recommendation is to consider whether putting PSNP back into Output 2 (Humanitarian System Capability) makes it more of a core component of the design of EC2R, better reflecting the Theory of Change.
  2. Anticipatory Action – The anticipatory action results were very promising. In line with FCDO Humanitarian Reset priorities, consider scaling up anticipatory action and using this as one of the main response modalities to predictable climatic stresses. Build learning, evidence around effectiveness and VFM evidence base.
PROGRAMME MANAGEMENT
1. Simplify EC2R management – Whether internal to BE Addis Ababa, or among partners, almost all stakeholders suggested EC2R was too complicated and should be simplified. The below recommendations are approaches to support that end:
  1. Consortium structure - Act regarding the consortium structure. Whilst a clear rationale was developed to empower UNICEF to coordinate and lead EC2R, the review has highlighted that the current structure struggles to achieve some of what it was designed to do and generates unforeseen challenges. Whilst there may be some coordination, there are leadership challenges with the structure. As it is, the structure has prioritised activities over outcomes (see recommendation 1), FCDO is distanced from partners and reporting modalities have become overly complicated. The review recommends that FCDO should act. Low ambition action might be working with UNICEF and partners to review the structure and processes and empowering UNICEF to take more strategic leadership of EC2R. High ambition could be for FCDO to take a traditional approach to managing partners directly but pushing for an integrated approach, using quarterly governance meetings chaired by the SRO and PRO. This reviewer would recommend taking a higher ambition approach.
  2. Simplify reporting – The current reporting format needs review and should improve the focus on outcomes (over activities and their related challenges). FCDO should consider synchronizing the EC2R reporting period with the FY to make internal reporting more efficient, instead of a June-June annual report from partners. FCDO should reduce the number of indicators EC2R partners are reporting on, in line with the streamlined logframe.
  3. Logframe: Weightings in the logframe need refreshing in light of the humanitarian reset, staff resources facing each output and budget. Overall Output 1’s (Emergency Response) weighting could increase due to the level of funding and staff resources allocated to it, along with its criticality underpinning the Theory of Change. The team should also consider bringing PSNP back into Output 2, as it preserves and strengthens systems, back in line with the Theory of Change.
  4. Mapping interventions - Use REACH to develop dashboards with programme results by location and provide an overview of how EC2R is adapting geographically to conflict, to access challenges, multi-sector needs, nutrition severity and more. The dashboard should ensure inclusion of the topline ICRC footprint, as this is essential to understand the EC2R strategy and approach. This will better enable the delivery of recommendations 1-3.
  5. Use XHMG assets - Formalize use of BE Addis Ababa sectoral/thematic advisers that sit outside the Resilience and Humanitarian Team Structure. Relevant are Health, Education, Climate and Conflict advisers, and could be formalized as a proportion of their time on EC2R, a humanitarian-facing performance objective, joint visits and joint policy development. Additionally, draw on WASH advice to consider how best to responsibly exit from the sector, subject to priorities in the next FY.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The EC2R Theory of Change (ToC - figure 1 below) remains consistent with previous years, although changes to the logframe have resulted in the results framework having four outputs, despite the ToC having three. The recommendations above seek to address this.

Figure 1: EC2R Theory of Change
The Theory of Change rests on a number of assumptions as below:

Assumption	Status in October 2025
The scale of humanitarian need does not overwhelm the international humanitarian response	With dramatic funding decreases and a high likelihood needs increase through 2025, the international humanitarian response currently remains able to operate and meaningfully respond to urgent needs. It is possible that this assumption may not hold in the future, and the business case Theory of Change may require a revision to reflect that.
Humanitarian operators are able to access affected populations	Humanitarian access is a major challenge. Whilst a range of UK delivery partners have been selected to increase access to hard-to-reach populations, and access challenges have been built into the core design of EC2R, the access situation is deteriorating. Physical access to Tigray has improved since the 2020-23 conflict, but access to Amhara/Oromia is deteriorating. Data collection and evidence generation required to appropriately target humanitarian interventions is a major challenge, and in 2025, Ethiopia became the only IASC Humanitarian Response without a Humanitarian Needs and Response Plan due to lack of cohesion with the Government of Ethiopia on PIN (People In Need) numbers. This will need to be monitored during the next Annual Reporting period to ensure the assumption continues to hold.
Other donor contributions to the HRP and Government of Ethiopia contributions to the PSNP remain proportionate to the levels of need	The major challenge is that the level of financial need hasn’t been published in 2025 as the Government of Ethiopia (GoE) did not approve the UN’s consolidated Humanitarian Needs and Response Plan. By November 2025[2], donors had provided $643.7m funding in 2025, just over half of the $1.25b received in 2024. / PSNP 5 has however been fully funded. By May 2025, GoE had contributed $672.7 million, well above the $130 million target set as a Performance-Based Condition (PBC) for this year. PSNP 6, due to start in 2026, currently faces a 10% funding gap.
Humanitarian agencies and the Government are receptive to FCDO policy priorities	The UK’s policy priority areas continue to be both relevant and in sync with much of the international community in Ethiopia. Where there are policy differences with key stakeholders, the relationship remains sufficiently robust to ensure continued dialogue and lobbying. UK policy leadership such as the Ethiopia Fundraising Conference (2024) and Senior Officials Meeting (2025) are concrete examples of where this assumption continues to hold.
[2] UN OCHA Financial Tracking Services as of 11/11/2025 Ethiopia 2025 | Financial Tracking Service

The assumptions hold, although as with many other humanitarian emergencies in 2025, the major threat is to the assumption of continued proportionate funding. Whilst humanitarian access is also under threat, poor access was built into the core design of EC2R so the programme does to some extent mitigate for this.

At the time of the 2025/26 Annual Review, the assumptions underpinning the ToC remain valid. The Inputs and Outputs of the ToC target three core themes of the programme – addressing humanitarian needs, strengthening resilience, and creating and developing the use of evidence to enable effective programming of the former two goals. Tackling humanitarian needs represents the bulk of EC2R activities, the majority of the EC2R budget and most of the Resilience and Humanitarian Team’s time but only represents 45% of the impact weighting. The recommendations above seek to address this.

The Outcomes seek to reduce the needs of vulnerable people and improve their longer-term resilience to disasters and shocks, which aligns with the Impact goal of saving lives and reducing suffering.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The different programme outputs are all largely on track. As EC2R has progressed, it has been tweaked and adapted as you would expect in such a challenging context and given internal FCDO developments. The risk is that the logframe and design increasingly looks and feels different to the Theory of Change underpinning it. The recommendations made in this Annual Review have been designed to streamline EC2R, bring it closer to the ToC and simplify its management by the Resilience and Humanitarian Team in BE Addis Ababa. Progress against outcomes, where data exists is presented below.

Outcomes	Indicator(s)	Milestone(s) for this review	Progress
1. Multi-sector humanitarian assistance meets the needs of Ethiopia’s most vulnerable populations	Provide protection and safe access to critical, integrated and inclusive basic services.	Nutrition: Proportion of children 6-59 Months who are malnourished in Ethiopia does not increase beyond 10% of the baseline.	No data
		Health: Increase percentage of Measles-containing-vaccine (MCV 1) coverage from baseline in at-risk population (Baseline of 61% in 2023).	Exceeded expectations – A+ 81% National 86% Amhara 78% B/Gumuz 82% Oromia / 88% Tigray
		WASH: 7% of people (disaggregated) reached with at least one inclusive WASH service	Met expectations – A 16%
		Cash: 70% of the beneficiary households experienced moderate or little to no hunger since receipt of the Shock Responsive Cash Transfers (SRCT)	Exceeded expectations – A+ / 99%
		Cash: 30 % of the beneficiary households report consuming more than 4 food groups since receipt of the cash transfer.	Substantially Exceeded expectations - A++ 90%
		Protection - 60% of the community is aware and able to access child protection and gender-based violence (GBV) services when facing violence, abuse and exploitation.	Met expectations – A 70%
		Education - 80% of students enrolled in targeted schools have reached minimum attendance and quality of learning is improved.	Met expectations – A 80% (no data on min attendance)
2. Poor households are better able to withstand disasters and shocks.	Percentage of GoE contribution to core PSNP financing	Average number of months that Productive Safety Net Programme (PSNP) households report experiencing food shortages in the past 12 months.	To be measured in FY25/26 - no target for this reporting period.
		GoE contribute 40% of core Productive Safety Net Programme (PSNP) funding for EFY17 (excludes shock response component)	55% (in Ethiopian FY 17/18 = FY25/26)
3. Humanitarian systems are able to identify risks and respond early and cost-effectively.	Multisectoral data informing evidence-based humanitarian actors programming	Continued AAWG meetings/coordination, dissemination of information management (IM) outputs to a wide audience (humanitarian situation monitoring (HSM), technical assessments, climate related, etc outputs).	Met expectations – A / Over 80 participants from different organisations/clusters attended AIMWG meetings. Ethiopia Assessment and Analysis (AAWG) website counted with over 2,000 visits from individual users during that period.

The Mid-Term Evaluation of the EC2R Programme May 2024 – Jan 2025 provided some topline findings, outlined below:

- Relevance: The EC2R programme has strongly aligned with the critical needs of vulnerable populations affected by conflict and humanitarian shocks. By targeting key groups such as children, pregnant and lactating women, and People with Disabilities (PWDs), the programme effectively addresses immediate needs while contributing to broader humanitarian and development goals. The alignment with national policies and global humanitarian standards further underscores the programme's relevance. Moreover, stakeholders, including government offices both at regional and federal levels as well as contacted beneficiaries of the components, have provided positive feedback regarding the programme's focus, indicating a strong demand-driven approach.
- Efficiency: The programme has successfully utilized 75% of its total budget, reflecting effective resource allocation in several key areas such as, health services and cash transfers. However, certain programme components, particularly child protection, have experienced slower progress. These inefficiencies highlight the need for more adaptive management strategies and improved monitoring mechanisms to ensure timely implementation. Furthermore, procurement and distribution processes for essential supplies could benefit from further streamlining to enhance cost-effectiveness and reduce delays.
- Effectiveness and Quality of the programme: The effectiveness of the EC2R programme is reflected in its significant achievements in improving access to essential services such as water, sanitation, and hygiene (WASH), healthcare, and education. Beneficiary satisfaction levels, particularly in relation to cash transfer components, remain high, indicating the program’s tangible impact on improving household resilience. However, challenges persist in ensuring the accessibility of WASH facilities for PWDs, highlighting the need for more inclusive infrastructure planning. Moreover, while cash transfers have provided immediate relief, their long-term economic impact remains uncertain, necessitating a more comprehensive approach that integrates livelihood support and financial literacy training to ensure sustainable benefits.
- Lessons learned: A critical lesson from the programme is the value of fostering strong partnerships with government institutions, local actors, and community-based organizations. Such collaborations have been instrumental in enhancing programme outreach and effectiveness. Moreover, community engagement has emerged as a key determinant of programme success. Programmes that invest in strengthening local institutions and enhancing the capacity of service providers are more likely to yield long-term benefits for affected populations.
Furthermore, this review team would argue there has at times been too much focus on outputs over outcomes in the delivery of EC2R. There are two major drivers of this, both of which the recommendations in Section A seek to address.

1. The complexity of the programme. The original design was already ambitious, but the way the programme has adapted incrementally over the course of its implementation has further added complexity. Of those interviewed, almost no one could speak with any level of confidence about all components of the programme. The recommendations in Section A include taking the programme back, closer to the original Theory of Change and looking for opportunities to streamline and integrate outputs.
2. The management structures in the programme. The UNICEF-led consortium approach was innovative and designed to challenge some of the pre-existing status quo of humanitarian actors competing and not coordinating well. It may have achieved some of this aim.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

EC2R was designed to be ambitious, innovative and to some extent challenge the status quo. Some of those innovations have proved very effective, such as directly funding a National Red Cross Society, the evidence generation work in Output 3 and some of the different cash transfer modalities. Others have been less successful, and have generated unintended problems, the management structure being the obvious example. EC2R is vast, covers many sectors and huge geographic areas. Opportunities must be taken to streamline and consolidate, and to utilize the impressive advisory expertise across BE Addis Ababa to support the Resilience and Humanitarian Team’s strategic leadership of EC2R. The reviewer would argue that with those changes, the Business Case should continue to deliver for people impacted by shocks in Ethiopia.

As FCDO transitions under FCDO2030 and our development approach evolves in line with the four shifts and the Africa Approach, a new Business Case design will need to begin soon to take us through the new three-year Spending Review period and beyond. How this will look depends partly on final ODA allocations, though we have a clear sense of how we would manage with less or more than planned. The design should build on many of the innovative successes in EC2R but may require narrowing and further prioritization given the reduced 0.3% ODA landscape the team will need to grapple with.

## C. DETAILED OUTPUT SCORING

Output 1: Responding to Needs

Output Title	Nutrition - Number of children and pregnant / lactating women who received nutrition services for the prevention and treatment of wasting
Output number:		1.1	Output Score:	A+
Impact weighting (%):		21.2%	Weighting revised since last AR?	Yes, substantially increased from 8.44%.

Indicator(s)	Milestone(s) for this review	Progress
Number of children and pregnant lactating women who received nutrition services for the prevention and treatment of wasting	Indicator 1.1.1: 52,700 children who received treatment for SAM	Substantially Exceeded: A++ / UNICEF: 69,574 children 6-59 months were treated for SAM (35,483 girls, 34,091 boys)
	Indicator 1.1.2: % of children treated with SAM who have been cured, who defaulted, and who died >75% Recovery Rate <15% Defaulter Rate <10% Death Rate	Substantially Exceeded: A++ / UNICEF: / Amhara / Recovery rate – 92.85% / Defaulter rate – 5.75% / Death rate – 0.1 / Tigray / Recovery rate – 95.3% / Defaulter rate – 2.42% / Death rate – 0.1 / (the remaining % non-responders)
	Indicator 1.1.3: 494,243 children who received treatment and PBW treated for MAM: / WFP = 390,188 children under 5 and PBW / UNICEF: High risk MAM 104,055 (52,027 girls and 52,028 boys)	Substantially did not meet expectations: C / Total = 368,374 / WFP / WFP treated 192,044 children (94,099 boys and 97,945 girls) and 176,330 PBW / UNICEF / 0
	Indicator 1.1.4: 100% of facilities reporting on medical transfer of SAM children in outpatient therapeutic programme (OTP)	Met Expectation: A / UNICEF = 100%
	Indicator 1.1.5: 10,018 mothers/caretakers of under 2 children receive nutrition education and infant and young child feeding (IYCF) counselling at health facilities and community levels	Substantially Exceeded: A++ / UNICEF =15,405

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.1 scored a A+ as all output indicators scored an A++ with the exception of Indicator 1.1.3, which substantially did not meet expectations (C), and Indicator 1.1.4 where there was no possibility of scoring higher than 100% (A). Output 1.1 is EC2R’s major lifesaving component, reflected in the high impact weighting of 21.2%.

UNICEF-supported nutrition services in Amhara and Tigray demonstrated strong performance, consistently exceeding targets across key indicators.

Indicator 1.1.1 was surpassed due to intensified community mobilisation, expanded Enhanced Community-Based Nutrition (eCBN) efforts, and strategic RUTF dosage adjustments. The results of SAM treatment activity in Indicator 1.1.2 remain substantially higher than the SPHERE standards for recovery, set as the milestone. The eCBN model enabled outreach to an additional 3,000 children and trained 1,673 Village Health Leaders, strengthening community-level identification of SAM. The strong performance in Tigray, as evidenced by its high recovery rate and low defaulter/death rates was due to the focus on child screening and preventive measures, including expanded community-based nutrition services and greater engagement in IYCF practices. The lower admissions in Tigray compared to Amhara suggest a reduced incidence of acute malnutrition, a more stable population with less deterioration due to improved optimal feeding practices, and the increased impact of adolescent and maternal nutrition services in the implementation locations.

Indicator 1.1.3 substantially did not meet expectations for two major reasons. Firstly, the start-up of WFP’s Voucher for Treatment (FVT) modality faced significant delays due to an extended preparatory phase and major operational challenges, including retailer and staff selection, training, and system setup. Financial Service Providers also encountered technical and logistical issues, particularly in remote areas with limited network coverage. As a result, only 12% of targeted beneficiaries were reached by December 2024. A major scale-up occurred between May and June 2025, admitting 55% of beneficiaries following the implementation of an acceleration plan, with achievement of the remaining targets expected by October 2025. In the 2024 Annual Review, this indicator received a C score (substantially did not meet expectation) due to WFP’s substantial Ready to Use Supplementary Feeding (RUSF) procurement pipeline facing challenges. Secondly, high-risk MAM programming by UNICEF was temporarily paused following Ministry of Health (MoH) guidance during a constructive tripartite meeting between the Ministry of Health (MoH), FCDO, and UNICEF. The MoH proposed generating contextual evidence through a randomised controlled trial (RCT) to test whether the new global nutrition protocol of treating high risk MAM with Ready to Use Therapeutic Feeding (RUTF) should be applied in Ethiopia. Given funding shifts, the proposed study was postponed, and resources re-prioritised to safeguard the RUTF pipeline for SAM treatment.

Indicator 1.1.4 met expectations, and the reviewer received a high level of confidence in how this was managed during the field visit to Daero Hafesh Health Centre in Tigray. Indicator 1.1.5 substantially exceeded expectations due to utilising ‘Community Nutrition Days’ to deliver essential nutrition services. This success highlights the effectiveness of UNICEF’s community-based service delivery model, emphasizing the importance of accessible, localized, and integrated approaches. UNICEF used Capital Departmental Expenditure Limit (CDEL) funding, to work with a key nutrition commodity supplier in Ethiopia to develop an alternative formulation of locally produced RUTF. EC2R is in the process of procuring an extruder (machine) to be provided to Hilina Enriched Food PLC. The FCDO supports its investment in Hilina through multilateral funding provided to UNICEF, which then channels the funds to Hilina. All funds received by Hilina are fully refundable. Under the agreement, Hilina will absorb the full cost by supplying an equivalent value of Ready‑to‑Use Therapeutic Food (RUTF) for Ethiopia’s pipeline.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, four indicators were removed to simplify and streamline the reporting. These were i) the MAM recovery, default and death rates, ii) RUTF last mile distribution, iii) micronutrient provision and iv) Community Based Nutrition. Milestones were set early in the year and many increased to reflect the substantial increase in impact weighting given nutrition is the major lifesaving component within EC2R. Furthermore, the target in Indicator 1.1.3 was updated to include a significant proportion of last year’s unreached target (160,900).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against 2024 Annual Review recommendations:

- Underperformance of some indicators has demonstrated that EC2R programming priorities need to be clearly reiterated to all partners throughout the programme lifecycle to ensure that activities align with the programme goals. Following performance and access challenges relating to MAM, EC2R programming priorities were reiterated to all partners and performance has improved in the 2025 Annual Review period.
- The presence of outputs such as the defaulter rate have been noted as being less applicable to the output level of the programme. Milestones are to be reviewed on their appropriateness as output indicators, and further refinement may be required. The logframe was reviewed and updated in July 2025.
- The underperformance of MAM for U5s highlights that WFP must improve delivery of MAM activities and project communication after two years of underperforming on the same indicator. Security issues in Amhara, Tigray, Oromia, and parts of the Somali region affected implementation. This included lack of access due to ongoing conflict, increased road blockages by unknown armed groups and poor road conditions due to seasonal rains. Partner reporting suggests that WFP largely caught up during the 2025 Annual Review period following substantial under-achievements and delays the previous year.
- There is limited insight into high-risk MAM, which has presented some strategic issues. Partners should improve monitoring of high-risk MAM to ensure effective implementation. This remains a concern as the Ethiopian Disaster Risk Management Commission (EDRMC) is not allowing SMART or related nutrition assessments. Humanitarian access to generate assessment data remains a key policy priority for the team.
Reflections and recommendations from this 2025 Annual Review include:
There must be improved integration of the interventions to support nutrition, as the highest weighted output in the business case. During the Annual Review field monitoring visit in September 2025, the team visited Daero Hadash Health Centre, which was a robust example of integrated nutrition and health activities. However, when speaking to mothers utilising the services, it was clear that WASH and economic constraints were key drivers of malnutrition in their community, yet EC2R’s WASH activities seemed to be prioritised elsewhere, as was the humanitarian cash project. The different targeting approaches used by the different outputs result in EC2R being less likely to meet the outcomes in the Theory of Change and undermine the overall cohesion of this programme. Therefore:
- The recommendation is to move from independently managed outputs (outputs 1.1, 1.2, 1.3 and even sometimes 1.4), to an integrated nutrition approach to reach nutrition outcomes in areas of highest need with nutrition, health, WASH and cash levers.
- Consider dropping MAM interventions and focussing on treating SAM in areas suffering from humanitarian shock, such as displaced communities, communities in hard-to-reach areas and those suffering the impact of a significant climatic shock.

Output Title	Health - Improved access to health for the most vulnerable
Output number:		1.2	Output Score:	A
Impact weighting (%):		4.3%	Weighting revised since last AR?	Yes, reduced from 17.6% to 4.3%

Indicator(s)	Milestone(s) for this review	Progress
Improved access to health for the most vulnerable including 10% people with disability	Indicator 1.2.1: 168 health facilities supported by UNICEF and ERCS. UNICEF: to support 92 health facilities: / 65 Fixed HFs / 12 Outreach HFs / 15 Maternal Health and Nutrition Teams (MHNTs). / ERCS: 76 health facilities / 38 Fixed HFs / 38 Outreach HFs / 0 Maternal Health and Nutrition Teams (MHNTs).	Moderately Exceeded: A+ / Total 187 health facilities supported by UNICEF and ERCS / UNICEF: 111 Health facilities supported / 63 Fixed HFs / 37 Outreach HFs / 11 Maternal Health and Nutrition Teams (MHNTs). / ERCS: 76 health facilities / 38 Fixed HFs / 38 Outreach HFs / 0 Maternal Health and Nutrition Teams (MHNTs).
	Indicator 1.2.2: 364,714 medical consultations. / UNICEF: 309,722 / 120,791 Female / 83,624 Male / 52,652 Girls / 52,652 Boys / 30,972 with disability / ERCS: 54,992 / 24,746 Female / 8,250 Male / 10,998 Girls / 10,998 Boys / 5,499 with disability / 3,600 clients get access of referral linkage through services of 32 ambulances: / 2,520 Female / 1,080 Male	Moderately Exceeded: A+ / Total: 407,498 medical consultations / UNICEF: 352,311 / 114,944 Female / 94,038 Male / 74,160 Girls / 69,169 Boys / ERCS: 55,187 / 21,808 Female / 20,953 Male / 6,587 Girls / 5,841 Boys / 5,198 clients get access of referral linkage through services of 32 ambulances: / 3,639 Female / 1,559 Male
	Indicator 1.2.3: 35,396 zero dose children identified and linked to vaccination / UNICEF: 18,600 zero dose children identified & vaccinated / ERCS: 16,796 (8,398 girls, 8,398 boys) zero dose children identified and vaccinated	Substantially did not meet expectations: C / Total: 15,831 zero dose children identified and linked to vaccination / UNICEF: 8,823 zero dose children identified and vaccinated. / ERCS: 7,008 zero-dose children (3,504 boys, 3,504 girls) identified and vaccinated
	Indicator 1.2.4: 1,500,000 people reached through social behavioural change (SBC) / 850,000 females / 650,000 males / UNICEF: 800,000 people reached through SBC / 450,000 females / 350,000 males / ERCS: 700,000 people reached through SBC / 400,000 females / 300,000 males	Met expectations: A / Total: 1,451,913 people reached through SBC / 758,002 females / 693,911 males / UNICEF: 724,985 people reached through SBC / 387,269 females / 337,716 males / ERCS: 726,928 people reached through SBC / 370,733 females / 356,195 males

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.2 scored an A during this annual review period. Two of the four indicators moderately exceeded expectations and one met expectations, although one substantially did not meet expectations, as discussed below.

Indicator 1.2.1 was moderately exceeded by the scale-up of outreach services in conflict-affected Amhara. Of the facilities supported, 101 were fixed health facilities, 75 operated as outreach teams, and 11 were Mobile Health and Nutrition Teams (MHNTs). These health facilities were supported by both UNICEF and ERCS across Oromia (48), Amhara (88), Benishangul-Gumuz (30), Afar (5), Tigray (10), and Somali (6) regions. To ensure equitable access to life-saving care, especially for internally displaced populations (IDPs), conflict and drought-affected communities, the partners employed a mix of service delivery models tailored to each context, including the strengthening of static facilities, deployment of MHNTs, and expansion of outreach services. All supported facilities were equipped with essential medicines, medical supplies, and equipment, and benefited from technical assistance, staff training, and regular supervisory visits to ensure continuity and quality of care in the most hard-to-reach areas.

Indicator 1.2.2 was moderately exceeded. A total of 407,498 medical consultations were delivered across six regions; Afar, Amhara, Benishangul-Gumuz, Oromia, Somali and Tigray through 187 UNICEF and ERCS supported service delivery points. Of these consultations, 115,846 were provided to men, 135,897 to women, 75,010 to boys, and 80,745 to girls. This intervention significantly improved access to essential health services for vulnerable populations, particularly internally displaced people (IDPs), host communities in insecure areas, and drought-affected populations. Unfortunately, whilst this indicator had a target of people with disabilities, no subsequent partner reporting was available on consultations by people with disabilities.

Indicator 1.2.3 substantially did not meet expectations. A total of 15,831 zero-dose children were identified and linked to vaccination across six regions: Afar, Amhara, Benishangul-Gumuz, Oromia, Somali, and Tigray. However, several challenges hindered progress toward the immunization goal. These included limited functionality of maternity rooms, insufficient cold chain equipment, unreliable power sources in remote areas, and disruptions to mobile health outreach due to security-related access constraints. As a result of these combined infrastructure and access issues, only 45% of the targeted zero-dose children were reached with vaccination services. UNICEF reached 8,823 children in Afar, Benishangul-Gumuz, Oromia, and Somali whilst ERCS reached 7,008 children in Amhara, Benishangul-Gumuz, Oromia, and Tigray.

Indicator 1.2.4 met expectations. A total of 1,451,913 (693,911 male and 758,002 female) people were reached across the six operational regions of Amhara, Afar, Benishangul-Gumuz, Oromia, Tigray, and Somali with social and behaviour change (SBC) messages, promoting health-seeking behaviours, vaccination uptake, and maternal care utilization. These messages were disseminated through a mix of communication channels including television, radio, print media, and grassroots outreach using English, Amharic, and relevant local languages.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, two indicators were removed to simplify and streamline the reporting. These were i) health workers trained and ii) health facilities rehabilitated. Despite all milestones increasing since last year’s review, the impact weighting was substantially decreased from 17.58% to 4.3% in this review. One factor contributing to this was the need for the programme to refocus on lifesaving humanitarian response, not longer-term health support.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against 2024 Annual Review recommendations:
- Field monitoring visits that were accompanied by FCDO visibly showcased the effectiveness of SBC as an outreach and access mechanism. SBC investment should be encouraged to improve outreach and access in hard-to-reach areas, such as by providing SBC health workers training to perform treatments outside of Primary Health Care centres. Targets were substantially increased (by over 40%) and an additional 319,309 people were reached with SBC during the 2025 Annual Review reporting period (28% increase).
- Many regions still utilise manual record keeping, which ought to be improved upon. Partners should promote improved local record keeping procedures at the field level by health workers, where manual record keeping fails to ensure a robust and efficient medical service or provide transparency in the delivery chain. This is a structural, national issue which is out of scope of the EC2R humanitarian intervention but has been raised with FCDO Ethiopia’s Human Capital and Development Team who support MoH nationally in their efforts to improve digitisation of record keeping. On humanitarian supply chain the EC2R team are assessing the feasibility of increasing digitisation and efficacy of core (nutrition/health) commodity tracking.
- The current health strategy consists of a significant amount of routine health responses, rather than emergency interventions. The programme may wish to review the vaccination component of the programme, considering routine versus emergency, and alongside other UK investments in vaccine provision in Ethiopia, such as GAVI. EC2R reduced funding support for routine zero dose vaccinations and focussed on key disease outbreaks (malaria and cholera especially) in hard-to-reach and conflict affected areas.
Reflections and recommendations from this 2025 Annual Review include:
Two health facilities were visited during the Annual Review monitoring visit in September 2025. The Daero Hafash Health Centre supported by UNICEF and their downstream partner Tigray Development Organisation in Tigray, and the Negele Metema Health Center (Dodola Woreda) supported by ERCS in Oromia.
In Tigray, the targeting rationale was clearer. Government services had to some extent withdrawn during the conflict and were yet to be fully re-established. Despite being accessible and relatively well served, the area was also hosting IDPs, had a high GAM rate (38%), and the humanitarian rationale of targeting the area was strong. Targeting rationale was clear with information on pre-conflict rates, immediate post-conflict rates and current rates (back down to 23%). In Oromia, the humanitarian rationale for targeting a facility in Negele Metema was less clear. The facility required support, and it was clear that the health needs in the location were high. However, what the humanitarian shock was that was being responded to was less clear. Whilst data on GAM and cholera didn’t seem to be available, it was clear that both were issues. However, the driver of need wasn’t a humanitarian shock. It was poverty and rural development needs, for which a humanitarian intervention was less appropriate.
As such, a key recommendation is to strengthen targeting:
- Health interventions should be better integrated with nutrition. Targeting should focus primarily on conflict and hard-to-reach areas, and areas hosting significant numbers of IDPs. Whilst not the focus of the business case, if there is a specific nutrition or health crisis in an area less impacted by an obvious shock, a response could be considered. However, the threshold should be high and there needs to be robust data (despite the challenges) to justify it.
- A second recommendation is to use diplomatic, policy and other programme (for example, the Ending Preventable Deaths Programme) levers to encourage and support the Ethiopian government to re-establish key services at pre-conflict levels throughout Tigray. The humanitarian response is not equipped to fill this gap forever and must continue to work through government systems with a clear exit strategy as (and if) the situation stabilises.

Output Title	WASH - Number of people with improved access to WASH facilities
Output number:		1.3	Output Score:	A
Impact weighting (%):		7.8%	Weighting revised since last AR?	Yes, up from 5.63% in 2024.

Indicator(s)	Milestone(s) for this review	Progress
Number of people with Improved access to WASH facilities	Indicator 1.3.1: 250,140 people accessing a sufficient quantity (SPHERE standard) of safe water for drinking and domestic needs / 127,571 females / 122,569 males / 25,014 with disabilities / UNICEF ERCS / Total 150,000 100,140 / Female 76,500 51,071 / Male 73,500 49,069 / PWD 12,000 10,014	Moderately did not meet expectations: B / Below results are of individuals reached with clean water. However, the quantities delivered did not meet SPHERE standards. / No evidence to suggest accessibility for a blanket 10% people with disabilities so this disaggregation is not being reported on. / Total: 444,513 people accessing some amount of safe water for drinking and domestic needs / 226,702 females / 217,811 males / Water systems: / UNICEF / Water System UNICEF Water Trucking ERCS / Total 270,916 11,523 162,074 / Female 138,167 5,877 82,658 / Male 132,749 5,646 79,416 / PWD - - -
	Indicator 1.3.2: 41 schools with safe access to, and use of, appropriate WASH services / UNICEF: 25 schools / ERCS: 16 schools	Substantially Exceeded: A++ / Total: 51 schools with safe access to, and use, appropriate WASH services / UNICEF: 42 schools (1 in Amhara, 2 in Benishangul Gumuz, 2 in Oromia and 37 in Tigray) / ERCS: 9 schools (3 in Amhara, 1 in Benishangul Gumuz, 4 in Oromia and 1 in Tigray)
	Indicator 1.3.3: 376,800 people reached with hand-washing behaviour-change programmes: / 192,168 females / 184,632 males / 37,680 with disabilities / UNICEF ERCS / Total 226,800 150,000 / Female 115,668 76,500 / Male 111,132 73,500 / PWD 22,680 15,000	Moderately Exceeded: A+ / Total: 433,875 people reached with hand-washing behaviour-change programmes: / 221,276 females / 212,599 males / UNICEF ERCS / Total 229,361 204,514 / Female 116,974 104,302 / Male 112,387 100,212 / PWD - -
	Indicator 1.3.4: 69,320 people reached with critical WASH supplies (NFIs) / 35,353 females / 33,967 males / 6,932 with disabilities / UNICEF ERCS / Total 66,320 3,000 / Female 9,007 1,530 / Male 32,497 1,470 / PWD 6,632 300	Substantially Exceeded: A++ / Total: 103,122 people reached with critical WASH supplies (NFIs) / 52,592 females / 50,530 males / UNICEF ERCS / Total 99,167 3,955 / Female 50,575 2,017 / Male 48,592 1,938 / PWD - -

Briefly describe the output’s activities and provide supporting narrative for the score.

Output indicator 1.3 scored an A during this annual review period. Despite a lack of clarity on how much of Indicator 1.3.1 met the desired minimum SPHERE standard of 15 litres per person per day (lpppd), the reach is impressive. On balance, the indicator moderately did not meet expectations. That indicator however was the outlier, and the three other indicators substantially exceeded expectations.

Output 1.3.1 moderately did not meet expectations. The two water systems visited, in Adi Nebried (UNICEF, Tigray) and Edo (ERCS, Oromia) were not able to produce emergency quantities of safe water to the desired minimum SPHERE standard of 15 litres per person per day (lpppd). Upon discussions with UNICEF and ERCS and the respective water boards, the two water systems produced less than 10 lpppd in Adi Nebreid and around 1.3 lpppd in Edo. This did secure a temporary emergency safe water quantity of over 7.5 lpppd in Adi Nebried, which is an allowable SPHERE target in contexts where there are climate stressors on water availability, i.e. drought conditions or conflict. This temporary emergency provision allows affected communities to access enough safe water for drinking, cooking and some hygiene. For Edo only a survival minimum quantity of safe water for drinking only was provided, reducing affected household’s ability to manage hygiene, increasing exposure to water borne or faecal-orally transmitted diseases. The temporary allowable quantity of safe water is only a temporary standard and water providers should continue to aim to supply minimum emergency quantities of over 15 lpppd. Unfortunately, the indicator wording did not reflect this, so the results have not met expectations. Furthermore, there was no robust evidence presented to FCDO by the partner on accessibility for people with disabilities so there is no reporting back on the milestone targets.

The prioritization of pre-existing water systems with a larger catchment population, and extension of water systems distribution pipelines to connect more communities is the right approach to deliver safe water at scale, build resilience and deliver Value for Money (VFM) in such a protracted crisis. With these interventions, UNICEF and ERCS have ensured that the conflict and climate-affected people in targeted communities, including those in reached cholera hotspot areas, have access to emergency and durable safe water, sanitation and hygiene facilities. No major cholera outbreaks were recorded in the communities reached by the project’s WASH interventions during the reporting period, which the partner suggests is a testament to the improved WASH situation. Unfortunately in September 2025, during the time of the field visit there was a further Cholera outbreak, concentrated around gold mining areas with poorer WASH practices which attract people from other areas of Tigray, Extended water systems reduced the time taken by women and children to fetch water, and reduced GBV risks to women travelling large distances to collect water. The solarization of water systems previously run by diesel powered generators across all regions is resulting in cost savings for households and communities, including reducing fossil fuel emissions. The cost of a 20ltr jerry can has reduced from an average of 80ETB (£0.40) to 20ETB (£0.10), resulting in households increasing the quantity of safe water consumed and being able to spend on other critical needs.

At the time of the annual review monitoring visits, both these water systems were considered a success and there were no plans to increase the amount of water to SPHERE standards. However, for locations where water quantities are being provided at survival levels, (Edo), EC2R will need to review whether to expand capacity, and/or reconsider whether the geographic targeting makes sense.

Output indicator 1.3.2 substantially exceeded expectations. UNICEF and ERCS activities on construction, rehabilitation and support for operation and maintenance of latrines in schools ensured that 35,193 vulnerable people (17,245 males and 17,948 females, 3,20 disabilities) have new access to gender-segregated and disability inclusive toilets catering for women’s dignity and safety. In IDP camps, 76,000 IDPs (38,760 females and 37,240 males) with existing access to sanitation facilities were reached with support on the operation and maintenance of their sanitation facilities. In schools, the interventions will have a long-term effect on ensuring that girls practice Menstrual Hygiene Management (MHM), attend school and engage in public life during menstruation. In the IDP camps, the sanitation services ensured that the vulnerable population continued to have access and use of safe and inclusive sanitation facilities.

Output indicator 1.3.3 moderately exceeded expectations. UNICEF conducted hygiene promotion in communities and IDP sites by volunteers through house to house/ tent to tent visits, community dialogue sessions and campaigns on water and food hygiene at household level and sanitation were conducted in all the regions reaching 229,361 people (116,974 females and 112,387 males) across Amhara, Benishangul Gumuz, Oromia and Tigray. For ERCS 477 Hygiene Promotion Volunteers (234 males, 243 females) were trained across the four operational regions and conducted hygiene promotion activities to encourage better sanitation and hygiene practices through extensive house-to-house visits, mass sanitation and hygiene campaigns in markets and schools. Additionally, combined health and WASH messaging was conducted through television, radio, and social media.

Output indicator 1.3.4 substantially exceeded expectations. The distribution of WASH Non-Food Items (NFIs), including hygiene materials, supported improved hygiene practices and safe water handling across affected regions. UNICEF distributed WASH NFIs to 99,167 people (50,575 females and 48,592 males) and ERCS 3,955 people (2,055 females and 1,900 males) to promote Household Water Treatment (HWT) and ensure water safety for the prevention and control of transmission of water borne diseases like diarrhoea and cholera across. This indicator however substantially did not meet expectations in 2024 when UNICEF failed to provide NFIs to 114,267 of their intended target of 145,980 people. Procurement and distribution of WASH NFIs is conducted on a rolling basis, with cycles of new supplies coming in as replenishment, which does not always align with the EC2R logframe timeline. As such, indicator 1.3.4 has now substantially exceeded expectations, due to orders placed during the previous Annual Review reporting period. Cumulatively, for Milestones 2 to 4, there is still an underachievement of 35%, which is expected to be covered in the coming milestone.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, two indicators were removed to simplify and streamline the reporting. These were i) clean water in health facilities (despite connecting/rehabilitating activities resulting in 26 health facilities now receiving clean water through the reporting period, and ii) the number of people benefitting from improved sanitation in schools, health facilities, IDP camps, refugee camps and host communities (35,193 people). Impact weighting has increased, as have milestones this reporting period compared to last year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against 2024 Annual Review recommendations:
- Field monitoring visits (FMVs) that were accompanied by FCDO noted that there was room for improved sectoral collaboration, where centres rehabilitated under output 1.2 (Health) would also benefit from WASH rehabilitation. The 2025 reviewer has had the same reflection. EC2R partners have stressed the challenge in prioritisation between allocating WASH funding to support EC2R health facilities and the WASH Cluster prioritisation of most acute needs.
- Milestones had to be adjusted midyear due to a categorisation error (between schools and health care facilities). Partners should improve due diligence in project design to ensure errors such as these do not arise in future. This year EC2R started project design earlier and had longer for multiple rounds of reviews and redrafting. This has helped avoid similar issues.
- Procurement failures resulted in underperformance of WASH Non-Food Items. Procurement processes should be reviewed immediately to ensure that targets can be met in the future. UNICEF have still managed to improve procurement practice this year hence overperforming (by 45%) on WASH NFIs to make up for shortfall in previous reporting periods.
- The current strategy has highlighted that there is less cross-sectoral engagement from WASH activities. Programming would greatly benefit from improving overlap in activities. ERCS and UNICEF WASH have both placed a greater focus on integration with other sectors. For example, increasing WASH rehab for health facilities renovated under EC2R. FCDO have requested a balance as EC2R integration should not override cluster defined needs and alignment with the wider humanitarian response.
Reflections and recommendations from this 2025 Annual Review include:
As discussed above, there is a disconnect between the indicator for provision of clean water and the activities on the ground, resulting in a significant underachievement, despite the good work done. The quantity of safe water provided enabled provision at a temporary emergency level (above 7.5 lpppd, as guided by SPHERE in instances of chronic deficiencies of water, i.e. in drought or conflict) to most locations, providing enough safe water for drinking, cooking and hygienic use. One location visited during the review was only able to provide minimum survival quantities for drinking (1.3 lpppd). For future ongoing provision this temporary allowable quantity will need to increase to 15 litres per person per day to ensure SPHERE standard for emergency quantities are being met and temporary allowable provision ends.

In Tigray, previous government structures and supply pipelines have been disrupted. The reestablishment of these structures is the only sustainable approach to providing water in the region. The WASH Committees/Boards felt robust and built on what was already in place. Accountability mechanisms through to the Committees/Boards were reassuring and were well understood and respected by all. Partner reporting on disability disaggregation unfortunately wasn’t sufficiently credible (as it has been reported as 10% of total reach without a monitoring evidence base made available to justify it) for inclusion in the results table. Without more detailed monitoring processes, it will not be possible to understand how effective the approach is at reaching people with disabilities. The focus on solarisation has strengthened access to clean water for all as the price of clean water reduces substantially. Overall, the network approach feels right, alongside the emergency NFI and behaviour changing modalities.

However, a few specific recommendations are:
- Make geographic targeting more cohesive with nutrition and health outcomes. Both in the community and in facilities. Where there is a clear contradiction with WASH Cluster prioritisation, the EC2R partner should make clear in writing to FCDO the rationale of which option has been selected and why.
- Reconsider realistic indicators to reach with water networks. If SPHERE standard water provision is the target, undertake activities to deliver it. If not, rethink the target.
- Ensure indicators make use of household level monitoring data, bringing out water quality, water quantity and access to water. Blanket assumptions are insufficient.
- Improve disaggregation of results on PWD reached or served. This will require improved monitoring processes that can give FCDO confidence about EC2R’s inclusion agenda.

Output Title	Financial Assistance - Humanitarian cash programming is supporting vulnerable households through shock responsive cash transfers (SRCTs) and vouchers
Output number:		1.4	Output Score:	A+
Impact weighting (%):		5.9%	Weighting revised since last AR?	Yes, down from 6.33% in 2024.

Indicator(s)	Milestone(s) for this review	Progress
Humanitarian cash programming is supporting vulnerable households through shock responsive cash transfers and vouchers	Indicator 1.4.1: 58,132 households (approx. 258,203 individuals) receive SRCTs. / Of those households: / Two rounds: 33,860 households (158,894 individuals) in Amhara, Oromia, and Tigray receive two rounds of Shock Responsive Cash Transfers (SRCTs) / One round: 24,272 households (99,309 individuals) in Oromia receive one round of Shock Responsive Cash Transfers (SRCTs) for drought. / Grievance mechanisms: At least 80% of beneficiaries in Amhara and Oromia, and 70% of beneficiaries in Tigray are aware of grievance redress mechanisms / Disability top-up: 8,270 persons with disabilities provided with at least one-off top-up cash transfer. One-off top-up cash transfer provided to 5,512 PWDs (Amhara 491, Oromia 3,856, Tigray 1,165) and two rounds of disability top-ups provided to 2,758 PWDs in Oromia region through the drought response.	Met expectations: A / UNICEF: 60,332 conflict and drought-affected households (265,388 individuals) in Amhara, Oromia, and Tigray received Shock Responsive Cash Transfers (SRCTs). Of these households, 53.1% are headed by women, 139,301 (52%) are girls and women and 162,234 (62%) children under 18 years. / Two rounds: 36,418 conflict and drought affected households (166,079 individuals) were reached through two rounds SRCTs in Amhara, Oromia and Tigray. Of these households, 19,985 or 55.7% are women-headed. / One round: 24,449 drought-affected households of which 49.4% women-headed. / Grievance mechanisms: 76% of beneficiaries in Amhara, 75% in Oromia, and 83% in Tigray are aware of the Grievance Redress Mechanisms (GRM) in place for the programme. / Disability top-up: 8,787 households provided with at least one round of disability cash top-ups. Of these, 3,067 households in Oromia were provided with two rounds of disability cash top-ups as part of the drought response. 5,724 persons with disability in Amhara, Oromia and Tigray regions received a one-off disability top-up
	Indicator 1.4.2: 9,110 households receive fresh food vouchers for prevention of wasting	Moderately exceeded: A+ / WFP: A total of 10,785 households (57,446 individuals) in Amhara region received monthly fresh food vouchers for the prevention of wasting.
	Indicator 1.4.3: 66% of children 6 to 23 months receiving recommended minimum dietary diversity	Substantially Exceeded: A++ / WFP: 88% of beneficiaries met the recommended Minimum Dietary Diversity (MDD), consuming five or more of the eight recommended food groups. / 83% of children aged 6–23 months met the Minimum Acceptable Diet (MAD). / Women’s dietary diversity improved markedly, with 89.5% of beneficiaries consuming five or more food groups, compared to the national average of just 2% (FNS, 2023).
	Indicator 1.4.4: 125,055 people covered and assisted through forecast-based anticipatory actions against climate shocks. / ±10% Percentage of households with acceptable/borderline/poor food consumption score	Substantially exceeded expectations: A++ / WFP: A total of 125,657 vulnerable people received Multipurpose Cash Assistance (MPCA) during the October–December 2024 and March–May 2025 seasons. / In the treatment group, the proportion of households with acceptable Food Consumption Score (FCS) rose from 61% at baseline to 64% at PDM, before a slight decline to 55% at endline. / By contrast, the control group saw a sharp drop from 53% at baseline to just 23% at endline.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.4 has scored an A+ as one indicator met expectations, two moderately exceeded expectations and one substantially exceeded expectations.

Indicator 1.4.1 has met expectations and by all accounts performed well. The Annual Review monitoring visit in September 2025 spoke to beneficiaries of two rounds of Humanitarian Cash Transfers in Adi Hageray town in Tigray. The reviewer was surprised as most households shared that they had used a portion of the cash to invest in small livelihood opportunities. This did raise some questions about whether the Minimum Expenditure Basket (agreed by all partners in the Ethiopia Cash Working Group) was too high, or whether targeting was sufficiently prioritised as you would normally expect immediate needs to be paid for and/or debt to be paid off. Upon review of the Ethiopia Multi-Purpose Cash guidance note, one of the objectives of the multi-round cash is Short-term support to facilitate linkages of HHs to other types of assistance, services, or sources of income. Whilst it was positive to see an investment in household resilience (there were clearly some success stories), if overall humanitarian funding continues to reduce, FCDO should consider engaging with the Cash Working Group’s MPC Guidance Note to test whether further prioritisation is required. The visit confirmed that all beneficiaries were aware of complaints mechanisms, and they felt like robust, tried and tested structures. The Community Based Targeting approach felt like it was broadly accepted, and all knew to go back to the appeals committee and if needed to the Bureau of Social Affairs.

Indicator 1.4.2 was moderately exceeded although its impact in Indicator 1.4.3 was substantially exceeded. On the Annual Review Field Visits to the Daero Hafash Health Centre in Tigray and the Negele Metema Health Centre in Oromia, dietary diversity was consistently raised as one of the main drivers of Acute Malnutrition. The performance, especially of Indicator 1.4.3 highlights the relevance of these activities.

Indicator 1.4.4 substantially exceeded expectations, not because of the number of people receiving multi-purpose cash assistance (which was slightly above the target), but because of the impact with the treatment group of beneficiaries only dropping their food consumption score (FCS) by 6% through the lean seasons. A substantial improvement compared to the control group whose FCS dropped 30%.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, two indicators were removed, and one was incorporated elsewhere to simplify and streamline the reporting, whilst one was added. The removed indicators include i) new grievance redress mechanisms established, ii) cash transfers for women and care givers, whilst identification and registration of people with disabilities was incorporated into Indicator 1.4.1. Finally, with the opportunity to pilot an Anticipatory Action approach through cash transfers with £4m from the Resilience and Adaptation Fund (RAF), indicator 1.4.4 was added to the logframe. The impact weighting of this output was revised down slightly from 6.33% to 5.9%.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against 2024 Annual Review recommendations:
- Recommendation: There are concerns regarding the ability of WFP to deliver Fresh Food Vouchers (FFVs) and the ability to monitor this in a timely fashion. The programme team should work closely with WFP’s FFV project to ensure it is delivered effectively and held to account.
- Progress: Performance this year has improved, and WFP has officially overachieved against the milestone this year. However, this year’s milestone also includes the number of beneficiaries carried over from the last annum, whereby WFP only reached 63,648 of 101,600 intended beneficiaries, an underachievement of 37%.
Reflections and recommendations from this 2025 Annual Review include:
Output 4 is clearly a high performing output within the business case, and despite challenges getting some aspects fully functional, especially the Fresh Food Vouchers (Indicator 1.4.2), the impact of the cash transfers looks very impressive from the monitoring WFP have undertaken. Opportunities should be taken to further monitor and learn, potentially scaling up this component of the programme.
- FCDO should examine whether targeting for HCT (UNICEF) could be strengthened to ensure assistance is reaching those in most severe need.
- FFVs (WFP) have generated good nutritional results, although operational delays were noted and high delivery costs hindered overall value for money. FCDO could consider expanding their use, targeting areas that are conflict affected, hosting IDPs or with very high GAM levels.
- The Anticipatory Action MPCA (WFP) has also developed impressive results and could become the best modality to respond to predictable climatic events in EC2R and should continue to be tested. RAF funding has reduced this year, but FCDO should try to expand this work and build robust evidence around the impact, potentially with dedicated research or evidence collection using the resources in Output 3 to influence other donors, the humanitarian community and Ethiopian Government to scale it up.

Output Title	Protection - Number and proportion of crisis-affected girls, boys, women and men, who access prevention activities and comprehensive protection services-including MHPSS, social work support, health care, justice/legal services, and child protection assistance.
Output number:		1.5	Output Score:	A+
Impact weighting (%):		2.7%	Weighting revised since last AR?	Yes, down slightly from 2.8% in 2024

Indicator(s)	Milestone(s) for this review	Progress
Number and proportion of crisis-affected girls, boys, women and men, who access prevention activities and comprehensive protection services	Indicator 1.5.1: Number and proportion of crisis-affected girls, boys, women and men, who access prevention activities and comprehensive protection services-including MHPSS, social work support, health care, justice/legal services, and child protection assistance.	Met expectations: A / UNICEF: Total: 1,991 people / 1,966 Female (322 girls, 1,644 women) / 25 Male (22 boys, 3 men)
	Indicator 1.5.2: 16 health facilities supported to provide GBV services to survivors	Substantially exceeded expectations: A++ / UNICEF: A total of 27 health facilities were supported during the reporting period to strengthen their capacity to provide quality, survivor-centered GBV services.
	Indicator 1.5.3: 3,000 women and girls (including People with Disability PWD) accessing safe spaces	Substantially exceeded expectations: A++ / Total: 5,029 females / 1,244 girls / 3,785 women / 21 PWD
	Indicator 1.5.4: 12,250 girls and boys (including children with disability), and caregivers provided with community-based mental health and psychosocial support, including accessing child-friendly spaces, safe families and resilience programme	Substantially exceeded expectations: A++ / UNICEF: Total: 32,041 people / 17,649 children / 9,666 girls / 7,983 boys / 263 with disabilities / 14,392 caregivers / 10,483 women / 3,909 men
	Indicator 1.5.5: 5,965 girls and boys who have experienced (or are at risk of experiencing) violence reached by health, social work or justice/law enforcement services (CP case management) (includes children with disability)	Met expectations: A / UNICEF: Total: 5,700 children / 2,919 girls (382 with disabilities) / 2,781 boys (436 with disabilities)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1.5 has scored an A+. All indicators have performed well, either meeting or substantially exceeding expectations.

Indicator 1.5.1 has met expectations, as activities are performing well and there’s a positive level of integration across sectors. 1,991 survivors of gender-based violence (GBV) including those at risk were reached through coordinated health, social work, and justice/law enforcement services in 27 health facilities across various locations. No target was set as it is a demand-driven service and FCDO did not want to create false incentives for the partner.

Indicator 1.5.2 has substantially exceeded expectations as targets were substantially exceeded when 27 health facilities were supported during the reporting period to strengthen their capacity to provide quality, survivor-centered GBV services. These facilities benefited from a range of interventions aimed at enhancing their readiness and response to GBV cases.

Indicator 1.5.3 also substantially exceeded expectations as 5,029 girls and women (1,244 girls, 3,785; including 21 PWD) accessed safe spaces in the reporting period. Significantly above the target of 3,000 women and girls. WGSSs serve as entry points for accessing GBV care and support services and referrals to specialised services. Indicator 1.5.4 substantially exceeded expectations as 32,041 people benefited from community-based mental health and psychosocial support (MHPSS) services, more than double target of 12,250 people. These services were delivered through a range of platforms, including child-friendly spaces (CFS), socio emotional learning sessions, and parenting skill education programmes. Indicator 1.5.5 met expectations, just as 5,700 children, against a target of 5,965 children, were identified and supported through child protection case management services. These children had either experienced violence, abuse, neglect, or exploitation, or were at heightened risk of such harm.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, three indicators were removed, including i) the indicator measuring the distribution of dignity kits, ii) the indicator measuring risk education and survivor assistance interventions, and finally iii) the indicator managing the child protection of unaccompanied and separated children.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against 2024 Annual Review recommendations:

1. The current milestone for supporting survivors of GBV (or those at risk) deliberately uses no target to ensure quality is not sacrificed in favour of reach, though the programme design has no means of evaluating the quality of protection services. It is advised that UNICEF provide reports verifying “quality” is maintained, or that the programme team accepts the risk of applying a target to the milestone. The Programme Team did not apply a target to the milestone for this review. UNICEF has included quality analysis in the latest reporting. Quality assessments relied on survivor feedback at case closure, focusing on perceived service effectiveness, safety, dignity, empowerment, access barriers, tracking case outcomes, service timeliness, and the use of standardized tools for documentation and referrals. This feedback informed improvements in the continuum of care for GBV survivors.
2. Monitoring protection and the effectiveness of programming remains a challenge in all regions, and there is very little evidence establishing effective programming beyond reach. UNICEF must look to improve tracking of protection attitudes. UNICEF now has protection monitors in conflict-affected areas with bi-weekly reports and online meetings at regional level in Amhara and Afar. In all regions, UNICEF undertakes quarterly programme monitoring to verify and assess the progress and quality of interventions.
3. Sector leads noted issues with the Washington Group Short Set for enumerators. It must be revised/improved to better identify disability in the context of Ethiopia.
   (see also Section C Detailed Output Scoring Output 1.6 Education; Section G Monitoring, Evidence, and Learning recommendations). The Resilience and Humanitarian Team is working with the disability inclusion team to contextualize and adapt the emergency response to better respond to PWDs.
4. Protection activities have a limited presence in cross-sectoral activities. EC2R should improve protection integration at all levels of programming to encourage protection mainstreaming. This will be supported by a Violence Against Women and Children Helpdesk commission. The VAWG Commission was delivered on in February 2025 with a GBV Programme Analysis for Ethiopia. Protection now works closely with Education (accelerated learning, MHH rooms and technical guidance, identification for MHPSS and case management, referrals to communities) and Social Policy (Cash). Over the coming 12 months, there are increased activities linked with Nutrition and Health.
Reflections and recommendations from this 2025 Annual Review include:
The Violence Against Women and Children Helpdesk commission outlined that EC2R programme offers some integration of GBV across health, WASH, nutrition, education, protection, cash and social protection sectors. However, there are opportunities to further leverage the programme’s potential to deliver targeted GBViE specialised protection programming and integration in the next phase of EC2R, including the following options to consider:

- Consider diversifying partnerships to include a dedicated GBV partner in the portfolio. This could be a mechanism that enables partnership, either direct or indirect with women’s rights organisations, which could be greatly expanded to deliver a long-term sustainable and cost-effective approach to GBV prevention and response activities.
- UNICEF is a child protection actor. Build on that and take steps to better integrate GBV within Child Protection as per the examples outlined in the Violence Against Women and Children Helpdesk commission recommendations.
- Consider updating the logframe to measure the quality of GBV response services; expanding partnerships with women-led and women’s rights organisations to deliver sustained GBV programming; integrating GBV into specialised child protection programming and expanding GBV prevention programming.
- Take forward recommendations in the Violence Against Women and Children Helpdesk commission to integrate GBV across Health, Nutrition, Cash and Education components.
Output Title	Education – no. of emergency affected pre-primary and primary school girls and boys, including children with disabilities, in four targeted regions supported to resume and continue their education
Output number:		1.6	Output Score:	A
Impact weighting (%):		3%	Weighting revised since last AR?	Yes, reduced from 4.22%

Indicator(s)	Milestone(s) for this review	Progress
No. of emergency affected pre-primary and primary school girls and boys, including children with disabilities, in four targeted regions supported to resume and continue their education	Indicator 1.6.1: Children benefitted from access to and continuity of learning in formal or non-formal setting with a provision of scholastic and teaching-learning materials, and training to teachers, among other interventions: / Pre-primary level: 8,100 children, of which 4,050 girls. / Primary level: 53,400 children, of which 26,700 girls. / 8,950 children with disabilities (CWDs), benefiting from assistive devices and or special learning materials (including 100% of identified girls with disabilities).	Moderately exceeded expectations: A+ / UNICEF: / Pre-primary level: 9,817 children / 4,952 girls (323 with disability) / 4,865 boys (427 with disability) / Primary level: 58,035 children / 27,944 girls (3,394 with disability) / 30,091 boys (3,864 with disability) / Total Identified: 11,288 CWDs / 5,189 girls / 6,099 boys / Total Benefitting from assistive devices/learning materials*: 8,008 CWDs (3,717 girls/4,291 boys) / *Among the total, 1,539 children with disabilities (707 girls) also benefited during the previous June 2023 - June 2024 academic year, receiving 2 years of support.
	Indicator 1.6.2: 1,270 teachers trained on teaching pedagogy at pre-primary and primary level (381 female teachers)	Met expectations: A / UNICEF: / 1,367 teachers and facilitators (529 female) trained on teaching pedagogy, MHPSS, inclusive education, peace building and Education in Emergencies.
	Indicator 1.6.3: Children with disabilities (CWD) received assistive devices: 4,500	Met expectations: A / UNICEF: / Received assistive devices and medical care: 4,403 CWDs / Received assistive devices and/or assistive learning materials: 3,923 children (1,758 girls) / Received medical treatment: 480 out-of-school CWDs (230 girls)

Briefly describe the output’s activities and provide supporting narrative for the score.
- Output 1.6 has scored an A. All indicators have performed well and as planned, with one moderately over-achieving expectations.
- Indicator 1.6.1 moderately exceeded expectations, with good progress across all three major components, and all targets for disabilities and gender breakdown were either met or exceeded.
- Indicator 1.6.2 met expectations as 1,367 teachers and facilitators (529 female) trained on teaching pedagogy, MHPSS, inclusive education, peace building and Education in Emergencies.
- Indicator 1.6.3 met expectations as a total of 4,403 children with disabilities (CWDs) received critical support through the provision of assistive devices and medical care. Of these, 3,923 children benefitted from assistive devices and or assistive learning materials (1,758 girls), while 480 out-of-school CWDs (230 girls) received medical treatment, helping lay the foundation for their future integration into formal education during the current academic year.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
During the logframe revision of July 2025, two indicators were removed, including i) the number of schools rehabilitated and ii) the percentage of out of school children rejoining formal education. The weighting was reduced to Output 1.6, although the milestone targets were all increased compared to the previous year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress against 2024 Annual Review recommendations:

1. The milestone looking at children with disabilities presents some confusion on the results. The indicator “(100% identified girls)” should be reworded for clarity, as it is not indicative of the result. Updated and addressed during the logframe review in July 2025.
2. The milestone looking at children with disabilities has a recycled result (both for assistive devices and support) with different targets. The result and target should only appear once and not be recycled. Updated and addressed during the logframe review in July 2025.
3. Sector leads noted issues with the Washington Group Short Set for enumerators. It must be revised/improved to better identify disability in the context of Ethiopia. UNICEF started using Washington Group Questions combined with the ‘Child Functioning Module’ developed by UNICEF. UNICEF recognise the importance of strengthening the capacity and accountability among the enumerators and intends to roll out further training to them this year.
4. As a result of conflict in Amhara, there has been a sharp uptick in the number of children out of school – an estimated 8.8 million. Within this context, it is important to re-test whether the delivery modality provides adequate value for money and reach. UNICEF has been using a unit cost of 66 USD/child for the integrated child protection and education programming in Ethiopia. In the implementation of EC2R, UNICEF has been able to bring down the unit cost of the accelerated education programming to 42 USD per child. This was enabled through better integrating with the government and other humanitarian partners and prioritizing local procurement. Furthermore, given the majority of schools are closed in some Woredas in Amhara, the EC2R programme has taken initiative of implementing Home Based Learning (HBL) under the overall leadership of the Regional Education Bureau and with technical support from Education Cluster. This initiative is estimated to have a unit cost of 40 USD/child and UNICEF has already signed partnership agreement with Amhara Development Association (ADA) for this initiative to reach 11,900 children (50% girls and 10% children with disabilities).
5. Going forward, implementation of Accelerated Education Programmes (AEP) and Alternative Learning Programmes (ALP) in Tigray needs to be ensured. This should come alongside a reinforced focus on school rehabilitation, given over 9,000 schools were left devastated.[3] UNICEF is targeting 15,500 children in Tigray to provide education through AEP and or ALP. School rehabilitation is included under EC2R programme in Tigray to facilitate minor repairs and maintenance to make the school environment conducive to learning outcomes, although needs outstrip budgets. This year, 15 schools, comprising 59 classrooms were rehabilitated through targeted minor repairs. Next year, 54 classrooms will be maintained to operate classrooms (22 for pre-primary and 32 classrooms at primary level).
  [3] https://reliefweb.int/report/ethiopia/new-dawn-education-war-torn-ethiopia
Reflections and recommendations from this 2025 Annual Review include:
Four main recommendations have been developed based on this review:
- As the new Education Adviser joins BE Addis Ababa, ensure consistent high level advisory engagement in EC2R.
- Access to education suffers from many of the same challenges faced by access to other basic services. As such, the team should focus on and consider modalities to enable children in hard-to-reach areas access education, including scaling up remote home-based learning modalities, and doing so through close Cluster engagement.
- Efforts should be made to further integrate the Education in Emergencies component of the project with others, especially child protection, WASH and health/nutrition.
- Efforts must be made to prioritise getting children back into the State-provided formal education system and encouraging education services to be re-established and strengthened in areas where they withdrew due to conflict. Education in Emergencies must provide a bridge, not be the long-term solution.

Output 2: Preserving and strengthening systems

Output Title	Humanitarian system capability: support provided to improve humanitarian coordination, collaboration, and effectiveness
Output number:		2.1	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No change

Indicator(s)	Milestone(s) for this review	Progress
Support provided to improve humanitarian coordination, collaboration, and effectiveness	Indicator 2.1.1: Undertaking a collaborative multi-sectoral nutrition-focussed risk analysis using available data (surveys and routine) in consultation with stakeholders in key regions: / Development of the guidelines/methodology / Consultative workshops / Risk analysis reports	Moderately under-achieved: B / UNICEF: / The National Ethiopia Nutrition Coordination Unit (ENCU) supported 21 SMART surveys conducted by implementing partners in the second half of 2025; of these, 7 were directly managed by the regional ENCU team. / The ENCU finalised the guideline for the Multisectoral Nutrition-Centred Risk Analysis (MSNRA) and carried out the analysis in 5 regions in collaboration with relevant stakeholders. / The report is currently in its finalisation stage.
	Indicator 2.1.2: 30% of the people who reached with hand-washing behaviour-change programmes are able to demonstrate 3 critical handwashing times	Substantial underachievement: C / UNICEF and ERCS: 20% of the people who reached with hand-washing behaviour-change programmes are able to demonstrate 3 critical handwashing times (U-Report poll was used to collect data).
Support provided by BRC to strengthen and operationalise ERCS' organisational and programmatic capacity	Indicator 2.2.1: # topics supported with quality trainings and knowledge transfer to ERCS / Training: deliver 2 trainings on 3 topics / Learning: deliver 10 technical partner meetings, 1 learning moment and 4 monitoring visits / Monitoring: assessments, 2 reviews, M&E Framework reviewed and updated	Moderately under-achieved: B / BRC: / Trainings: 3 trainings completed (ToT on eCBHFA and Epidemic Control; Infection prevention and control at facility level and Psychological First Aid (PFA); and MHPSS ToT). / Learning: 2 learning moments, 6 technical partner meetings, and 3 monitoring visits completed. / Monitoring: 1 assessment (Health), 1 review, and review/update M&E Framework completed.
	Indicator 2.2.2: Provision of timely technical feedback on ERCS financial and narrative reports, to improve ERCS' capacity to provide accurate and FCDO-compliant reporting. / BRC: ERCS's Aid Diversion Policy reviewed for contextual relevance and action plan developed and operationalised	Met expectations: A / BRC: Quarterly technical support was provided to review ERCS’s financial reports, ensuring accuracy and alignment with FCDO compliance requirements. / ERCS’s Fraud and Corruption Policy was reviewed and revised and is pending final endorsement by the Governing Board.

Briefly describe the output’s activities and provide supporting narrative for the score.

National and international systems in Ethiopia have been overwhelmed by concurrent shocks. Responses have come late and have not been sufficiently prepared for emerging risks. Humanitarian systems designed to respond to climate shocks have struggled to respond to conflict-related needs. Coordination between humanitarian actors, and between Government and international actors, has been poor. Data on humanitarian needs is often late and of poor quality. Output 2 has been designed to improve coordination between development and humanitarian systems; ensuring that the delivery of humanitarian assistance supports, rather than undermines, local systems; and identifying areas where our development programmes can better anticipate risk and address humanitarian needs (e.g. the provision of services to displaced populations).

Output 2.1 has scored a B as three of the four indicators under-achieved. The high weighting attached to the output (20%) is not reflected in either the budget, or the staff time allocated to it.

Output Indicator 2.1.1 did moderately not meet expectations. The National ENCU supported 21 SMART surveys conducted by implementing partners in the second half of 2025; of these, 7 were directly managed by the regional ENCU team. The Nutrition Information System Working Group (NIS WG), led by the federal ENCU, played a key role in ensuring the quality and validity of data by actively participating in every stage of the survey process. The ENCU finalised the guideline for the Multisectoral Nutrition-Centred Risk Analysis (MSNRA) and carried out the analysis in 5 regions in collaboration with relevant stakeholders. The report hasn’t yet been finalised and is currently in its finalisation stage, which is why it has scored a B.

Once the analysis tool and initial report are endorsed by EDRMC and validated, the plan is to scale up the approach to other regions and conduct the analysis twice a year. The purpose of the MSNRA is to identify and forecast context-specific nutrition risks and to develop tailored preparedness plans for each region. Furthermore, MSNRA findings will inform woreda-level hotspot classification and contribute to the Humanitarian Response Plan (HRP).

Output Indicator 2.1.2 did significantly not meet expectations as only 20% of people who were reached with hand-washing behaviour-change programmes are able to demonstrate 3 critical handwashing times, significantly below the 30% target. A U-Report poll was conducted in Amhara, Benishangul Gumuz, Oromia and Tigray to assess the reach of handwashing behaviour change interventions, knowledge levels, and barriers to proper handwashing. The findings revealed that 85% of respondents were aware of critical handwashing times. Specifically, 66% reported washing hands before eating, 20% after using the toilet, 7% before preparing food, 1% after coughing, and 6% after handling garbage. On average 20% of respondents could identify at least three critical handwashing moments. The high awareness of handwashing before eating and after using the toilet is particularly important, as these are key control points for preventing the transmission of communicable diseases, especially diarrhoeal illnesses such as cholera.

Output Indicator 2.2.1 did moderately not meet expectations. This has been primarily driven by not reaching targets on joint monitoring visits and technical monitoring visits, although it is noted that these indicators rely on the capacity and availability of both organisations to succeed. It is further noted that revised indicators for the new FY have been amended and improved to better capture overall performance. However, Output Indicator 2.2.2 met expectations as quarterly technical support was provided to review ERCS’s financial reports, ensuring accuracy and alignment with FCDO compliance requirements. As the rollout of the new financial software progresses, continued structured support will be essential to ensure timely and accurate financial returns from field offices, while also reducing data entry fatigue at headquarters. ERCS’s Fraud and Corruption Policy was reviewed and revised to align with both national regulations and international best practices. The updated policy has been approved by the Senior Management Team and is pending final endorsement by the Governing Board. Dissemination has already begun, starting with HQ staff and volunteers, and extending to regional offices, which are tasked with cascading the policy to their respective teams. To reinforce understanding and accountability, the finance department will integrate policy awareness checks and refresher sessions into their routine branch support visits throughout the year.

Whilst not captured in the logframe, the Resilience and Humanitarian Team has invested heavily in the Standby Partnership (SBP) mechanism to fill key gaps in the interagency humanitarian response. Criteria for funding has been sharpened during the reporting period and now only funds SBP as a short-term measure for a critical emergency function, with some exit plan for transitioning out of SBP. The four SBPs EC2R has funded this reporting year amount to an investment of £471,198 GBP, as below:

UN Agency	Position/role	Duration
IOM	Senior Advisor EDRRR to Somali Regional President Office	Oct 2023 – Dec 2024
OCHA	Assessment Coordinator	Oct 2023 - Oct 2024
WHO	Sub-national cluster coordinator (Amhara)	Nov 2024 - Mar 2025
OCHA	Civil-Military coordination officer (Amhara)	Nov 2024 - September 2025

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, three indicators were removed related to output indicator 2.1: Support provided to improve humanitarian coordination, collaboration, and effectiveness. The indicator on i) Social and behavioural change in health, ii) protection referral system, and iii) disabled children accessing FCDO education programmes. The rationale for how and what to cut was to capture measures of quality given the majority of the logframe (Output 1) is heavily weighted towards quantitative number of outputs achieved.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress against 2024 Annual Review recommendations:
1. A variety of milestones within this indicator, particularly relating to SBC, fail to demonstrate the effectiveness of programming or have failed to be created with a realistic and achievable design. Milestones should be designed so that they can be assessed during the annual review cycle, and they should also be designed to clearly demonstrate the output’s intention.
  1. To similar effect, evaluation of SBC must be improved and or conducted to provide new and more robust evidence for this output. BE Addis Ababa have initiated a third-party monitoring (TPM) mechanism to focus on SBC and to measure the impact of activities without current measurable outcomes, such as health training. First results are expected in January 2026.
2. The relationship between Red Cross National Societies draws into question the effectiveness of its function. Procurement delays and ineffectiveness demonstrate a clear requirement for improvement, and wider contextual issues (such as international conflict, global shortages, global economic downturns) indicate a failure in either prolonged planning of programme design and/or procurement delivery chains. The EC2R team must manage BRC more effectively and strengthen the relationship that ERCS has with them in the coming year. A key challenge is that BRC has limited presence in Ethiopia, although it is noted that BRC has made great efforts to mitigate the impact of this through regular visits and frequent check-ins with stakeholders. This remains a work in progress and has resulted in a simplified proposal for this FY with very clear outputs on what BRC will deliver for their portion of funding. It also clarifies the relationship with other supporting national societies, including the Danish Red Cross who lead on procurement and the Netherlands Red Cross who have Health and WASH Delegates based in Addis Ababa to provide the technical programme support function to those sectors.
3. Reporting on milestones need to align with the annual review cycle. Some mid-term evaluations and review points fall after the annual review drafting. Reporting cycles remain a challenge, and there is a recommendation in section B relating to this. The Mid-Term Evaluation was finalised after last year’s Annual Review.
Reflections and recommendations from this 2025 Annual Review include:
There are three main recommendations relating to Output 2:
- As it currently stands, Output 2 is the least cohesive output and poorest performing in EC2R. The weighting was previously increased to 20% due to its strategic importance but neither 20% of the budget nor 20% of the team’s time goes to this output. This mismatch needs management attention and decisive action. One option may be to remove the indicators under 2.1 (2.1.1 going to Output 3, and 2.1.2 to Output 1.3) and incorporating PSNP (Output 4) into Output 2, alongside the work of building ECRS’ capacity. Both aspects would significantly support humanitarian system capability and provide a robust emphasis on localisation, in line with FCDO’s Humanitarian Reset Priorities. It would also help streamline EC2R’s logframe and reporting and bring it more closely in line with the Theory of Change.
- Indicator performance on EC2R’s components with the British Red Cross support to the Ethiopian Red Cross Society have moderately underachieved. This is further complicated by the lack of presence of BRC in Ethiopia. However, when speaking to the Resilience and Humanitarian Team, they are happier with performance and progress than in previous years and feel indicators 2.2.1 and 2.2.2. don’t necessarily capture the progress that’s been made. This component could have its indicators reviewed and other potential changes considered to improve and capture performance.
- EC2R is channelling significant budget through the Standby Partnership (SBP) mechanism to fill strategic gaps in the humanitarian architecture. This should be captured in an indicator.

Output 3: Use of Evidence

Output Title	Improved availability of humanitarian data and analysis
Output number:		3	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No change

Indicator(s)	Milestone(s) for this review	Progress
Improved availability of humanitarian data and analysis	Indicator 3.1.1: 2 assessments conducted during year 2 of the partnership (it can include SMART+, humanitarian situation monitoring (HSM), multi-sector needs assessment (MSNA), other sectoral assessments)	Substantially exceeded expectations: A++ / REACH: REACH conducted 2 SMART+ assessments in East Wollega and Arsi Zones of Oromia. Furthermore, preparations were completed for a SMART+ survey expected to take place in the Rift Valley Maize and Haricot Bean (RVM) livelihood zone. The assessment is pending government approval for implementation. / In addition, the 2024 MSNA was conducted in close collaboration with OCHA, clusters and humanitarian partners, and provided a comprehensive evidence-base for annual response planning, with it being used as a key source of information for the 2025 HNRP and prioritisation response plan. Furthermore, preparations for the 2025 MSNA were also completed, including finalising the methodology, questionnaire and geographical coverage. This was above and beyond expectations given the severe challenges of the operating environment in Ethiopia.
	Indicator 3.1.2: Assessment and analysis working group maintains an assessment registry, bi-weekly meetings with national cluster representatives and other information management actors and supports coordination efforts in close coordination with OCHA, support in drafting of humanitarian needs overview (HNO) report.	Moderately exceeded expectations: A+ / REACH: REACH successfully seconded one staff to work with OCHA. As co-chair of the Assessment and Information Management Working Group (AIMWG, formerly AAWG), REACH led meetings with IM actors and cluster representatives at the national level, supported coordination efforts in close collaboration with OCHA, and drafted key sections of the 2025 HNO.
	Indicator 3.1.3: 1 capacity user-focussed building workshop and up to 2 technical deep-dives	Moderately exceeded expectations: A+ / REACH: REACH developed six technical deep dives on various climate indices and exposures and held two capacity building workshops in February 2025.
	Indicator 3.1.4: (UNICEF) Findings of the national survey on persons with disability, the EDHS and effectiveness surveys disseminated and used for advocacy through two workshops (one with government stakeholders and one with UN and Civil society partners)	Achieved: A / UNICEF: The data collection for the Disability Survey and Ethiopia Demographic and Health Survey (EDHS) has been completed. The findings from the Disability Survey have been presented to stakeholders including government, UN and Civil Society Partners twice. The Disability Survey’s final report and dissemination materials, including factsheets and methodological briefs, were released in October 2025. Dissemination of final products and advocacy workshops took place on 24th January 2026.
EC2R partners are able to monitor needs and programming in hard-to-reach areas	Indicator 3.2.1: New product agreed in year 2 of programme (Humanitarian Situation Monitoring) to replace area-based assessments: Up to three rounds of Humanitarian Situation Monitoring in H2R and/or otherwise underserved areas, complemented by up to two rapid needs assessments	Moderately exceeded expectations: A+ / REACH: Two rounds of HSM were successfully conducted. / Three Rapid Needs Assessments (RNAs) were conducted and completed, one of which was conducted in Tigray. These were not published online due to lack of consensus with authorities over the results.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 has scored a A+ as one indicator substantially exceeded expectations, three moderately exceeded, one met expectation and one moderately under-achieved.

Output Indicator 3.1.1 substantially exceeded expectations. In consultation with FCDO, clusters, and other humanitarian and development actors, REACH implemented a SMART+ assessment in East Wollega[4] and Arsi[5] Zones of Oromia. Furthermore, preparations were completed for a SMART+ survey expected to take place in the Rift Valley Maize and Haricot Bean (RVM) livelihood zone. The assessment is pending government approval for implementation.
[4] East Wollega SMART+ Products: SMART+ Survey Factsheet in East Wollega; SMART+ Survey Report in East Wollega; SMART+ Dataset for East Wollega
[5] Arsi SMART+ Products: SMART+ Factsheet in Arsi Zone; SMART+ Survey Report in Arsi Zone; SMART+ Dataset for Arsi Zone

The 2024 MSNA was implemented in close collaboration with OCHA, clusters and humanitarian partners, and provided a comprehensive evidence-base for annual response planning, with it being used as a key source of information for the 2025 HNRP and prioritisation response plan. The outputs entailed a dataset, analysis tables, an MSNI Bulletin and MSNI Snapshot, six regional factsheets and one AAP snapshot and were disseminated widely to key partners and stakeholders. Six presentations and one joint analysis workshop were also held. Preparations for the 2025 MSNA were also completed, including finalising the methodology, questionnaire and geographical coverage.

Output Indicator 3.1.2 moderately exceeded expectations. REACH successfully seconded one staff to work with OCHA. As co-chair of the Assessment and Information Management Working Group (AIMWG, formerly AAWG), REACH led meetings with IM actors and cluster representatives at the national level, supported coordination efforts in close collaboration with OCHA, and drafted key sections of the 2025 HNO. It was clear speaking to the UN’s Office for the Coordination of Humanitarian Affairs (OCHA) how valued this was by OCHA and all the partners relying on the Working Group. This intervention came across as an innovative, and efficient approach to improve the learning and use of data and strengthen coordination within the data and evidence space more broadly.

Output Indicator 3.1.3 moderately exceeded expectations. REACH developed six technical deep dives on various climate indices and exposures, and held two capacity building workshops in February 2025, including on:
- Climate Indices Projections ATLAS
- Riverine Flood Impact Assessment ATLAS
- Landslide Exposure Assessment ATLAS
- Drought Exposure Assessment ATLAS
- Air Pollution Exposure Assessment ATLAS
- Heat Stress Exposure Assessment ATLAS
- Subnational Climate Hazard Exposure and Impact Assessment Excel Workbook

REACH also started preparatory work for its new climate workstream. In that context, the collaboration with ERCS was furthered and a workshop was held to identify areas of possible cooperation.

Output Indicator 3.1.4 achieved expectations. The data collection for the Disability Survey and Ethiopia Demographic and Health Survey (EDHS) has been completed. The findings from the Disability Survey have been presented to stakeholders including government, UN and Civil Society Partners twice. The output was reached despite some delays, as the Disability Survey’s final report and dissemination materials, including factsheets and methodological briefs, were released in October 2025, and dissemination of final products and advocacy workshops took place on 24th January 2026.

Output Indicator 3.2.1 moderately exceeded expectations. Two rounds of Humanitarian Situation Monitoring (HSM) were successfully conducted, assessing humanitarian needs in hard-to-reach, partially accessible, and otherwise underserved areas. The results of the first round of HSM were disseminated bilaterally to partners and were used to inform the 2025 HNRP process as well as the humanitarian prioritisation plan. Additionally, the findings of the second round of HSM were published online, and a prioritisation matrix was developed and shared bilaterally with partners:
- HSM Round 2 - Factsheet
- HSM Round 2 - Dataset
- HSM Round 2 - Analysis Tables

Three Rapid Needs Assessments (RNAs) were also conducted. The first one assessed the status of primary health care service provision capability, and focused on the Asgede district, Tigray. It resulted in a factsheet which was presented to partners and disseminated bilaterally. The second RNA took the shape of a rapid SMART+ survey, to verify recent spikes of acute malnutrition, childhood morbidity and health-seeking behaviours among children, and resulted in the below factsheet and report:
- Rapid SMART+ Survey Factsheet, West Guji Zone
- Rapid SMART+ Survey Report, West Guji Zone
The third, conducted in Tigray, couldn’t be published due to a lack of consensus with authorities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No major logframe changes have taken place over this reporting period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against 2024 Annual Review recommendations:
REACH assessed that the use of Service Capability Monitoring (SCM) was too labour-intensive and that Humanitarian Situation Monitoring (HSM) allows for a broader geographic study using less resourcing. However, the baseline study conducted in Shabelle, Somali and Central, Tigray are useful baseline datasets. FCDO should advise REACH to perform an end of programme SCM to provide monitoring data and feed into evaluation and ensure the baseline data has utility. This recommendation did not take place due to external challenges. Instead, the Resilience and Humanitarian Team did not push REACH to deliver an end of programme SCM which was seen as a nice to have, rather than a must have and requested REACH to focus on deliverables defined in the EC2R logframe.
Reflections and recommendations from this 2025 Annual Review include:
- The secondment of a REACH staff member to OCHA to co-chair the AIMWG stands out as good practice and a relatively low-cost intervention that has had outsize impact to improve coordination of humanitarian data and evidence in country, seemingly appreciated by all actors. The team should continue this, and take any future innovative opportunities to use REACH to have a disproportionate impact on the interagency evidence landscape.
- The use of the Ethiopian Red Cross Society to collect data in hard-to-reach locations was innovative and a key result of EC2R. The programme should continue to utilise REACH to build ERCS’ capacity to collect data in hard-to-reach areas on behalf of the humanitarian response.

Output 4: Building household resilience

Output Title	World Bank: PSNP functionality retained with timely transfers consistent with annual CPI increase
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No changes

Indicator(s)	Milestone(s) for this review	Progress
PSNP functionality retained with timely transfers consistent with annual CPI (Consumer Price Index) increase	Indicator 4.1.1: 90% of payments made to core beneficiary households according to the programme's performance standards for timeliness	Met expectations: A / 90% of payments delivered on time, according to the programme's performance standards for timeliness.
	Indicator 4.1.2: 75% increase in average wage rate relative to the annual general CPI increase, for cash transfers beneficiaries	Met expectations: A / 75% / Wage rate increase of 18.7% from January 2024, inflation by June 2023 of 19.9%. Only 80% of transfers in the EFY will be benefiting from the wage rate increase. (For 20% of the transfers (July -December 2024) this indicator was 0% as the increase was done in January 2025. For 80% of the transfers (January-June 2025) this indicator was 94% (18.7/19.9). Hence for the year we had a 75% increase (0.20*0 +0.80*94).)
	Indicator 4.1.3: Complete beneficiary database: 380 woredas with complete registration data available at Federal level	Moderately exceeded expectations: A+ / 444 woredas with complete registration data available at Federal level. 300 woredas with data for key program functions available in the federal Management Information System (MIS) server.
	Indicator 4.1.4: Total cumulative area of land treated through area enclosures, rangeland management, soil and water conservation, forage and forestry activities / 2025 annual 245,000 / 1,445,000 cumulative	Moderately exceeded expectations: A+ / By Mar 2025 PSNP has treated an additional 290,330 hectares. / Up to June 2024 the program had treated 1,489,553 hectares. By Mar 2025, the cumulative area is 1,779,884 hectares.
	Indicator 4.1.5: 1,500,000 core beneficiary households receiving their benefits in electronic accounts	Met expectations: A / 1,356,289 beneficiary households were paid through electronic accounts (CBE & Telebirr) in April 2025. This estimate assumes that all PW households in Tigray have had their accounts opened.
PSNP shock response component functionality and value for money/ efficiency	Indicator 4.2.1: PSNP publishes early warning dashboard and drought assistance response plan during every quarter	Moderately under-achieved: B / Early Warning dashboard prepared but not available to all institutions in the prioritization committee, and Drought Response Plan prepared quarterly.
	Indicator 4.2.2: Cumulative number of Early Childhood Development (ECD) centres set up in PSNP woredas - 30	Substantial underachievement: C / 0

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 scores an A as two indicators moderately exceeded expectations, three met expectations, one moderately underachieved and one substantially underachieved. The Government of Ethiopia’s (GoE’s) contribution to programme financing increased significantly following the World Bank Development Policy Financing operation, as part of the macroeconomic reform programme. By May 2025, GoE had contributed ETB 36,998,388,617.11 or US$ 672.7 million, well above the US$ 130 million target set as a Performance-Based Condition (PBC) for this year. Maintaining the 8m caseload and the number of transfers for beneficiaries mitigated the risks of any short-term negative impacts of the macroeconomic reforms whilst inflation slowed.

Output 4 is counted as International Climate Finance (ICF). The programme’s performance on climate mitigation and adaptation was mixed. Whilst only 19% beneficiary households reported relying on negative coping strategies, households still reported an average of 2.26 months of food shortages. However, the target for the amount of land covered by climate resilient Public Works projects, from range management to soil and water conservation was comfortably exceeded (1,779,884 hectares against a target of 1.66m). PSNP 6 design has a greater focus on climate resilient Public Works, honing in on best practice and learning for results under PSNP 5.

Output Indicator 4.1.1 met expectations as the target was reached as 90% of the payments delivered on time, according to the programme's performance standards for timeliness (for the core Public Works and Permanent Direct Support transfers these are within 30 days from the end of that month and are set out according to a region’s Public Works schedule). Timeliness of core transfers also increased from 81% in Ethiopian Financial Year EFY 2016 (July 2023 – July 2024) to 90% in EFY 2017 (July 2004 – July 2025). Further, GoE (Ministry of Agriculture) Food Security Coordination Office (FSCO) has fully moved to using a digital Management Information System (MIS) to provide the evidence required to report on this timeliness PBC.

Output Indicator 4.1.2 has been achieved as the Government of Ethiopia has raised the transfers by the targeted 75% of the Consumer Price Index (CPI).

Output Indicator 4.1.3 has moderately overachieved as 444 woredas now have complete registration data available at Federal level, against a target of 380. An achievement of 117%.

Output Indicator 4.1.4 has moderately exceeded expectations, using the annual number of hectares treated to measure performance, not the cumulative total which had already exceeded the milestone at the beginning of the year. This indicator relates to the number of hectares treated as part of the different public works activities under PSNP. These include soil and water conservation, rangeland management, forestry and agroforestry activities, gully control and rehabilitation of degraded lands.
Output Indicator 4.1.5 met expectations as the result remains within a 10% margin of the milestone. The target for PSNP5 was reduced down to 1,100,000 but this hadn’t yet been reflected in the logframe. The result against the indicator does make a significant assumption that all PW households in Tigray have had their accounts opened. Monitoring processes need to establish if that assumption holds.
Output Indicator 4.2.1 moderately under-achieved because whilst the Early Warning Dashboard was prepared, it is not available to all the institutions in the prioritization committee. Whilst the shock response system was in place, the number of beneficiaries targeted was low, there were delays in the delivery of these transfers and focus on some quarters was on vertical expansion to non-PSNP beneficiaries only despite the high levels of vulnerability amongst PSNP households.

Finally, Output Indicator 4.2.2 substantially under-achieved as none of the 30 Pilot Early Childhood Development (ECD) centres are yet to be completed, largely due to delays in procurement and capacity to deliver complex construction projects. The infrastructural construction/renovation of all the ECD centres are near completion and distribution of the tools and equipment required for the established centres are underway by Ministry of Women and Social Affairs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During the logframe revision of July 2025, one indicator was added, indicator 4.2.2 giving the target of 30 ECD Centres to be set up in PSNP Woredas. Milestones were reviewed for the year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress against 2024 Annual Review recommendations:
1. Field visits for PSNP highlighted funding constraints meant that regions were imposing caps to benefits based on household size with implications for the total number of beneficiaries under PSNP. It is recommended that FCDO work with the World Bank to assess this as the funding gap is likely to close in the current Ethiopian Financial Year. Caps imposed by regions have not had a negative impact on the number of total beneficiaries. PSNP 5 was designed to cover 8 million beneficiary households, the same number of beneficiaries as the previous phase. Guidance on PSNP5 removed the cap in favour of full family targeting, whilst allowing regions to have discretion. Under PSNP5 regions have been, in practice, keeping caps to ensure that they benefit a larger number of households in their woredas but keeping the overall caseload unchanged. Whilst finance gaps for PSNP in previous years have led to a reduction in the number of transfers to the caseload, during Ethiopian Financial Year 2017 (July 2024 to June 2025), there was no financing gap impact transfers.
2. The World Bank and GoE have put in several enhanced monitoring strategies to ensure assessment of PSNP functionality and effectiveness in conflict-affected settings. More could be done to increase the sampling of conflict-affected woredas in the World Bank’s third-party monitoring and national spot checks, including through phone surveys if woredas are inaccessible. The World Bank has made good progress in selecting conflict areas for monitoring this year. Spot-checks were carried out in 12 woredas in Amhara, 10 of which had been reported as “amber” at least once in the Traffic Light assessments (meaning conflict adaptations were necessary) submitted by GoE since December 2023; 2 of which had been reported as “amber” in the last year. Under the third cycle of third-party monitoring (TPM), conflict-affected woredas in Amhara were deliberately prioritized among the randomly selected woredas. This approach enabled a more thorough assessment of programme performance and its adaptability in conflict settings. However, there were security challenges and some woredas had to be replaced due to active conflicts and lack of access for monitoring teams. Phone surveys complemented the spot-checks and third-party monitoring.
Reflections and recommendations from this 2025 Annual Review include:
The UK’s role as Donor Chair of the PSNP Donor Group enables FCDO to exert influence into the design of PSNP 6 (starting in 2026). FCDO should seek to ensure:

- PSNP maintains or expands the current PSNP5 caseload of 8 million people. FCDO should use our role to ensure increases in the productivity aspects of PSNP (livelihoods and public works), do not come at the expense of the protection aspects (social protection current caseload of 8 million people). The UK must continue to work with the World Bank to influence government to not renege on their commitment to expand that core 8 million people figure.
- FCDO should use all available levers to encourage PSNP’s wealth ranking methodology through Community Based Targeting to be adapted for use in conflict settings. Furthermore, encouraging the rollout of digital mechanisms, such as Management Information Systems and digital IDs will enable PSNP to operate more effectively in conflict settings.
- FCDO should encourage further alignment between PSNP, and shock responsive social protection with humanitarian assistance, using FCDO’s role as chair of the PSNP Donor Group, co-chair of the Shock Response Technical Sub-Committee, and role on the Humanitarian and Resilience Donor Group to further this.
- Finally, milestones need review as discussed above, specifically indicators 4.1.4 and 4.1.5.

## D: VALUE FOR MONEY

Overview

The programme’s current VfM is strong and also sets out a forward-looking agenda, i.e., using local systems, strengthening markets, integrating delivery platforms, and improving targeting for vulnerable populations affected by shocks. These foundations remain sound, and implementation experience shows that many elements of the ToC have held up well in practice. Several pathways have delivered strong results, and the programme continues to complement the wider FCDO portfolio, particularly in resilience, heath and nutrition.

As the programme has evolved, it has adapted to emerging needs and opportunities. While these incremental adjustments have broadened the programme’s reach and innovation space, they have also added layers of complexity that make it harder for stakeholders to maintain full visibility across all components. This highly reflects the programme’s ambition and the challenging operating environment, though it does suggest an opportunity to refocus and streamline to preserve strategic coherence.

Economy

The programme continues to demonstrate strong economy, consistent with the original commitment to reduce long-term costs through localization and strategic capital investments. Local production of RUTF via Hilina Enriched Food, financed through CDEL and repaid in product, can reduce foreign exchange exposure and transport costs while strengthening national supply chains. Solarized health and WASH systems can also significantly lower the recurrent fuel expenditures, especially in remote and conflict-affected areas.

The Voucher for Treatment modality represents a targeted procurement approach that maximizes the impact of therapeutic commodities per beneficiary. The economic rationale of optimizing the use of high-value inputs and minimizing wastage remains strong. However, the unexpectedly prolonged timeframes for delivery of the intervention ultimately impacted the VfM negatively, as the resulting additional delivery costs and overheads ended up reducing the overall proportion of funds going directly to the beneficiaries. The Standby Partnership mechanism also provides good VfM by prioritizing short-term, critical emergency functions with clear exit strategies, avoiding prolonged expenditure for temporary capacity gaps.

Efficiency

Efficiency has improved in several areas due to digital systems, streamlined government delivery, and coordinated monitoring. PSNP performance is a strong example, where the government of Ethiopia co-financed US$672.7 million, far exceeding the US$130 million target, and enabled timely cash transfers to 8 million people. MIS integration, digital ID expansion across woredas, and third-party monitoring has helped maintain operational efficiency even in conflict settings. Health and SBC interventions are also another component that showed efficiency. A total of 407,498 consultations were delivered across 187 service points, more than 145 million people were reached with SBC messages, and 80% of facilities reported improved community knowledge. These reflect efficient scaling of essential services.

However, efficiency was hampered by programme complexity. Output 2.1 underperformed due to misaligned milestones, insufficient staffing for its 20% output weight and coordination challenges. Reducing the spread of the programme could prove effective in producing efficiency improvements. There is also potential for greater integration across pillars, especially health, nutrition and WASH. Linking health and nutrition proved effective and similar integration opportunities could also exist in other areas, such as aligning community-level WASH behaviour change with health outreach or embedding nutrition screening within safety net delivery platforms if it falls within what the programme is able to deliver. Increased integration would reduce duplication and enhance efficiency.

Effectiveness

The programme has strong effectiveness where delivery systems were robust. PSNP transfers and public works maintained caseload coverage and supported livelihoods. Health services reached diverse demographic groups maternal care and vaccination outreach improved health-seeking behaviours, and GBV services were maintained even in insecure areas. These outcomes show that key components of the ToC functioned as expected. Evidence generation under Output 3 remains a standout innovation, contributing substantially to adaptive programming and informing national systems. Cash transfer modalities like FvT also demonstrate strong potential when implemented without delays.

Yet several constraints limited full effectiveness. Insecure access and cold chain disruptions reduced zero-dose immunisation performance to 45% of target.

Equity

Equity performance remains strong and aligned with the programme. Targeting prioritized conflict-affected, remote and drought prone areas, ensuring support was directed to communities with the greatest needs. PSNP maintained full-family targeting avoiding household exclusion despite budget constraints. MIS and digital IDs improved fairness, and a balanced gender reach was recorded across consultations 115,846 men; 135,897 women; 75,010 boys; 80,745 girls), and GBV services were integrated within health and protection platforms. However, disability-disaggregated data remains limited, preventing a full assessment of inclusion. Operation constraints have also hindered access in high-risk areas stressing the ongoing need for adaptive, inclusive approaches.

Cost-Effectiveness

Cost-effectiveness remains generally strong. The programmes inclusion of localised production, solarization investments and digital systems have reduced long-term cost drivers and improved the cost-per-beneficiary in several components. The shift to a 0.3% ODA landscape will require strategic prioritization and narrowing of programme scope in future business case design. Identifying and scaling the most cost-effective elements while less effective or more administratively burdensome components may need consolidation.

Does the programme still represent Value for Money?

The programme still represents good value for money. It has demonstrated strong performance in economy, efficiency, and equity, combined with significant outcome achievements, supporting continuation. Targeted restructuring may be necessary with the programme’s complexity and the consortium management model having created inefficiencies. Streamlining structure and reducing fragmentation to harmonize procurement and realigning delivery with the original ToC are essential steps. Integration across pillars should also be explored to enhance impact and cost effectiveness. With these adjustments, and with strategic prioritization in light of the 0.3% ODA environment, the programme is well positioned to continue delivering meaningful results for the most vulnerable in Ethiopia.

E: RISK

Overview of risk management

The overall risk rating for the EC2R programme remains ‘major’. Relevant risks are identified across all risk categories in the risk register and are reviewed quarterly, most recently in August 2025. The Senior Responsible Owner (SRO), thematic lead advisors, Programme Responsible Owner (PRO), and the wider programme team work together to regularly review and manage these risks, as well as monitor progress on mitigation measures. Key risks identified through partner due diligence are incorporated into the programme risk register and tracked through the quarterly DDA follow-up action plan. Risks may be escalated to the EC2R risk register, and if necessary, to the Embassy’s Delivery Committee. All risks are in line with the Embassy’s overall risk appetite ‘Receptive’ for safeguarding, strategy and context, policy and programme delivery, and financial and fiduciary risk; and ‘Cautious’ for people, reputational risk and Public Service Delivery and Operations.
Strategy and Context (Severe):
Conflict and climate shocks continue to be the most significant risks on the programme. The escalation and spread of conflict in the Amhara and Oromia regions have led to increased humanitarian needs, with reports highlighting risks such as indiscriminate killings, sexual violence, child protection concerns, displacement, and disruption of essential services and systems. Ethiopia has also experienced five consecutive years of multiple climate shocks, including floods and droughts, which have exacerbated disease outbreaks (e.g. cholera and malaria), increased food security issues, and raised famine concerns.
To mitigate conflict risks, the team continuously monitors the situation to ensure partners demonstrate conflict sensitivity and uphold delivery standards in insecure environments. They work closely with UN agencies and other partners to ensure contingency plans are in place for conflict hotspots and maintain flexibility and oversight of funding agreements to enable rapid responses to emerging needs. Technical support has also been drawn from the Human Rights and Peacebuilding Programme (HARP), including Rift Valley and CIR.
For climate shock risks, the team tracks trends in collaboration with the UK Met Office, advocates for increased international climate finance (ICF) for affected areas and scales up EC2R funding to partners based on climate risk and anticipatory action, rather than reacting after shocks occur. Support is also provided to IRC for the Rapid Response Mechanism (RRM), ensuring preparedness and contingency plans are in place for swift responses to floods and emerging droughts.
Policy and programme delivery (severe):
Lack of humanitarian access, insecurity, and inadequate essential humanitarian supplies continue to pose significant delivery risks and have resulted in disruption to programme delivery throughout the reporting period. To mitigate these, the team is utilising UK diplomatic efforts in coordination with UN and other donors to advocate for improvements in humanitarian access; applying third party monitoring; funding partners such as ICRC with increased access to the most vulnerable and hardest to reach areas; and working with the humanitarian community to publicly denounce attacks on humanitarian aid workers and raise awareness of IHL commitments.
Safeguarding (severe):
High safeguarding and protection risks exist across crisis affected areas and settlement sites across Ethiopia. Underreporting of SEAH is widespread due to fear of retaliation, stigma or lack of trust in complaint channels.
To mitigate the risk, the team have conducted due diligence assessments on partners and reiterated our requirement for all EC2R funded projects have robust safeguarding plans (including accessible reporting mechanisms). The team sends quarterly reminders to all partners to report safeguarding cases and any other fraud or aid diversion risks and proactively follows up on due diligence recommendations quarterly. Incidents of SEAH and large-scale fraud will be actively covered during Third Party Monitoring data collection with FLASH Reporting systems in place for quick response. The Resilience and Humanitarian Team have also developed a Protection and Gender Mainstreaming Checklist for use on field visits which includes questions for partners on SEAH risks and mitigation measures, ensuring this is consistently addressed and monitored across the programme. Despite strengthened mitigation measures, including partner training, reporting guidance, and engagement with the PSEA Network, the residual risk of SEAH remains highly likely with severe impact. Zero reporting continues to indicate underreporting rather than absence of cases, which is being actively addressed with specific partners.

Financial and Fiduciary risk (major): A key risk is the potential diversion of UK funds or supplies, which could reduce programme impact and cause reputational damage. This risk is especially high in conflict-affected areas, where looting has occurred and maintaining regular programme oversight is challenging. Movement restrictions, deteriorating security due to armed violence, and changes in territorial control further limit the UK’s ability to monitor programme implementation effectively.
To assess the effectiveness of partner controls and risk mitigation measures, the team has carried out a series of field monitoring visits to Oromia, Afar, Tigray, Somali, Southern Ethiopia, and Benishangul regions during the reporting period. To further strengthen monitoring and oversight, a Third-Party Monitoring (TPM) mechanism has been mobilised through PANDA, with the inception phase taking place from August to October 2025. PANDA will provide "Light Touch Verification" products, conduct in-depth reviews, and deliver safeguarding flash reports. The approach can be adapted over time, allowing the team to adjust the geographical and thematic focus as needed.
Update on Partnership Principles

The 2024 PPA captures inputs from wide spectrums of areas and sectors including social protection. It concluded that there is a mixed level of commitment by the GoE to poverty reduction and domestic accountability while commitment to civil and political rights has shown continued deterioration. On the other hand, commitment to public financial management has shown continued improvement. In recognition of these challenges, the FCDO has introduced a series of controls. These include human rights and peacebuilding, public financial management, and monitoring including safeguarding.

The British Embassy regularly engages with Government of Ethiopia (GoE) counterparts to flag concerns around human rights and other elements of the Partnership Principles.

The overall Annual Assessment of Progress (ASP) has concluded that the fiduciary risk of making payments through GoE PFM systems is moderate. The structure of the PFM system broadly reflects good international practice; adequate laws, regulations and guidance are in place to govern practices. Budget formulation, execution and reporting are based on internationally accepted standards. There are positive developments over the last year to improve internal controls using digital systems.
On the other hand, weaknesses remain in some areas including procurement, transparency and in-year budget allocations.
PSNP has specific financial management and control arrangements. Ministry of Agriculture submits regular audit, commodity flow and utilisation, finance and programmatic reports. The World Bank provides additional controls through technical and programmatic oversight, monitoring including third-party monitoring and national spot checks and reviews of compliance with World Bank frameworks such as the Environmental and Social Safeguard Framework (ESMF).
Annual Statement of Progress (financial aid programmes only – delete if n/a)

Current level of fiduciary risk and direction of travel since last ASP	Moderate / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Major / Stable
Is a full FRA update required?	No: where the situation is stable or improving

Under the 2023 Fiduciary Risk Assessment of the Productive Safety Net Programme (PSNP), fiduciary risk was assessed as ‘moderate’. This is the same rating given in both the previous 2015 and the 2019 PSNP FRAs and is the same as the overall rating of ‘moderate’ given by DFID’s recent national PFM systems FRA (2019).

The key risk areas which have improved since the previous FRA in 2020 are:

• Transparency: Although budget and expenditure information is not always publicly posted, the beneficiary selection system is transparent and approved at a community level. However, GRM system is not functioning consistently well in several woredas, which increases risks of targeting errors Accounting: A general improvement in programme financial management staff turnover at regional and woreda level reported in regions visited attributed to incentives being provided to staff in the form of basic office equipment, transportation facilities and other necessary office equipment and logistics.

• Reporting: There has been a continued gradual improvement in the deployment and use of IT and MIS at sub-national level both as a reporting tool and as a key component of internal controls. There has been progress in further expanding the use of IBEX, R-PASS, and MIS in general for reporting.

• Payment methods: The use of e-payments through the Commercial Bank of Ethiopia has further increased, which is further improving the reliability of fiduciary control over cash disbursements. Few problems have been documented regarding fund diversion or losses through manual payments. ‘
Areas where improvements are on-going, or where performance has deteriorated, include the following:

• Food procurement and management: Ongoing issues raised in successive commodity audits should receive the full attention of senior government and development partner officials.

• Budget utilisation: Under-utilisation of the food component of the programme (non-execution of the FSCD and WFP budget heads) due partly to conflict but also procurement difficulties. Utilisation of the whole budget is important as it is a key indicator of how the programme is performing and how effective its management systems are in supporting the programme to achieve its goals.

• Internal control: Lapses and weaknesses documented in financial audits appear to be minor. However, these combine with sub-optimal internal audit arrangements throughout government to undermine programme financial management and accountability.

Since the FRA was conducted, the World Bank have commissioned a series of monitoring reports of the programme, including assessing to what extent PSNP beneficiaries are receiving their entitlements in conflict-affected settings, providing reassurance that households continue to receive their transfers.

The GoE has a credible PFM reform programme, with overall strategy and annualised work plan. The World Bank, EU, Gates Foundation, FCDO and AFD are providing support. While the support provided by each donor falls within the government’s strategy, coordination and alignment have yet to be strengthened. The UK is playing a convening role for the tax revenue support group while the World Bank is playing similar role for the rest of PFM reform group.

Sources: Annual Statement of Progress, Fiduciary Risk Assessment PSNP (2023), PSNP third-party monitoring and national spot check reports.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The programme works closely with six international organisations and one local Red Cross society. In 2024–2025, it made strong progress and achieved the majority of its planned outputs and outcomes. FCDO uses different delivery modalities for each partner: EC2R is implemented via MoU agreements with UNICEF, ICRC, WFP, and ERCS/BRC; an Administrative Agreement with the World Bank; and an Accountable Grant with REACH. Partners were selected for their technical expertise, experience in Ethiopia, and ability to address critical gaps in humanitarian response. All implementing partners submitted their biannual and annual progress, financial, and audit reports on time, and there has been proactive engagement on risks and delivery chain mapping. However, challenges remain especially regarding efficient and effective coordination between partners, as previously mentioned. Additionally, multilaterals face issues arising from a disconnect between the requirements set out in the framework arrangement and the realities on the ground. These include demands for reporting, delivery chain mapping (DCM) with disclosure of implementing partners, financial reporting and updates within specified timeframes, and meeting safeguarding requirements.

UNICEF

FCDO Ethiopia has a long-established partnership with UNICEF. Funding for UNICEF’s humanitarian multisectoral response has been provided since inception phase, covered by a multi-annual Memorandum of Understanding (MoU) which has been extended until June 2026. As of June 2025, UNICEF has utilised 90% of the total £41.3 million funding.
The volatile security situation in Amhara and Tigray has posed significant challenges to timely programme delivery and effective monitoring. Continued conflict among various interest groups in Tigray, along with prolonged drought and conflict in Afar, Amhara, and Tigray, has increased risks for both beneficiaries and staff, affecting access, safety, and overall programme effectiveness. Recent changes in the humanitarian funding environment (including within FCDO) have created additional uncertainty, affecting ongoing activities and the full utilisation of funds. UNICEF has had to cut several roles, including one GBV staff member (who left in November) and one Nutrition staff member (the supply and logistics specialist responsible for RUTF supply chain monitoring under EC2R). Overall, UNICEF reduced its workforce by 100 staff last year and is expected to make further staffing cuts after March this year. Despite these challenges, UNICEF has maintained a strong track record of delivery and demonstrated robust capacity for local-level implementation. Overall, UNICEF and its partners have met and exceeded most targets in nutrition, WASH, cash transfers, GBV response, and education, with a particular focus on inclusion, resilience, and support for vulnerable and conflict-affected communities.
UNICEF provides both narrative and financial reports according to the agreed reporting timeline. In addition, UNICEF provides counter aid diversion (CAD) and safeguarding reports, follows up on Due diligence assessment (DDA) recommendations and provides risk updates on a quarterly basis, as well as progress on the expenditure status before each disbursement.
UNICEF acts as lead partner in the EC2R partnership model and is responsible for driving improved coordination and the compilation of results reporting across all partners. While the coordination function has been well-resourced, there remain gaps in strategic leadership and cross-cutting technical input which would increase the programme’s effectiveness and overall impact. UNICEF’s leading role would benefit from increased senior oversight to support stronger collaboration, effective prioritisation, and strategic planning across the EC2R consortium.
WFP
FCDO has funded WFP through EC2R since the emergency submission phase of the programme. During the year 2024/25, a total funding of £29,343,000 has been provided for WFP which is fully committed as of June 2025. WFP provides updates on activities, financial reporting, DDA updates and other FCDO compliance measures on request.
As with other partners, security restrictions and the materialisation of other risks have hindered the delivery of specialised nutritious foods in some parts of Amhara, Oromia, and Somali regions throughout the reporting period. However, severe delays in reaching the expected number of MAM beneficiaries targeted within agreed timelines has become a significant challenge that has required extensive monitoring and engagement. In particular, WFP’s ‘voucher for treatment’ pilot has faced unprecedented challenges and has taken much longer to implement than anticipated, requiring FCDO to revise timelines accordingly, even across financial years. Furthermore, the delays in implementation have resulted in significant (five-fold) additional indirect costs, substantially decreasing the intervention’s value for money.
It is encouraging to see WFP’s initiative in promptly reporting aid diversion incidents compared to previous years. However, the number of incidents has significantly increased, particularly with the introduction of the new voucher treatment modality. Due to being overwhelmed by the rise in incidents, the WFP team has become hesitant to provide updates despite close follow-up from the FCDO team and has recommended that the FCDO Ethiopia team rely on the Office of Inspections and Investigations’ (OIGI) higher-level reporting in the future. This contrasts with previous years, when the team would regularly receive prompts responses to requests for further information of incidents. This issue has been escalated to the Strategic Delivery Unit in British Embassy Addis Ababa and flagged to the IAID team at HQ for further guidance,
Ethiopian Red Cross Society (ERCS)
Partnering with ERCS, a local NGO, has strengthened EC2R’s localisation agenda and supported its strategy to diversify delivery routes away from large multilateral agencies. Since signing an MoU with ERCS in August 2023, a total of £3,718,248 has been disbursed and committed for FY2024/25.
Despite initial challenges in financial and project management, ERCS’s performance has improved over time. The organisation now provides both narrative and financial reports in line with agreed timelines, although some follow-up is often required. Additionally, the ERCS team is improving its ability to meet FCDO’s compliance requirements. For example, they submit quarterly updates on DDA, Counter-Aid Diversion, and Delivery Chain Risk Mapping upon FCDO’s request. However, while DDA updates show progress in areas such as policy development and capacity building for staff at all levels, full implementation of these resources is still pending.
Beyond national security concerns and the reluctance of local private construction firms to undertake water supply and sanitation infrastructure works, ERCS faced challenges during the reporting period related to shortages of project materials, fuel, and rising prices for goods and services.
British Red Cross (BRC)
FCDO signed an agreement with BRC in August 2023 to support ERCS through technical assistance aimed at building ERCS’s capacity and facilitating international procurement. A total of £7,382,978.58 was disbursed in the last financial year, with all funds fully committed. Although BRC does not have an office in Addis, it has an EC2R-dedicated staff member working closely with the ERCS team. BRC’s robust procurement system is helping ERCS address foreign exchange challenges and strengthen its own procurement processes.
The original intent of BRC’s support was focused on procurement and technical assistance (TA). However, following recommendations in the last Annual Review to clarify expectations, FCDO requested BRC to include detailed information on the TA it would provide to ERCS. Consequently, BRC incorporated these details into its proposal, primarily under Output 2 of the system-strengthening section. Progress against this plan has been reflected in the joint report and captured in ERCS/BRC’s quarterly DDA updates. However, the actual outcomes of this output in terms of ERCS’s capacity development remain unclear and require further in-depth assessment.
World Bank

EC2R provides Category B Financial Aid to the Productive Safety Net Programme (PSNP) through a World Bank-managed Multi-Donor Trust Fund, with reporting aligned to trustee-established guidelines. In November 2024, £23 million was disbursed of which 100% was classified as International Climate Finance given the strong evidence that PSNP supports households’ improved resilience to drought and climate change. Although the pooled funding approach poses challenges for meeting UK compliance standards, the EC2R team has leveraged increased influence over delivery due to the UK chairmanship of the PSNP Donor Working Group. The Joint Review Implementation Support (JRIS) mission, conducted biannually by the World Bank, FCDO, and other donors in partnership with the Government of Ethiopia, plays a key role in driving robust monitoring and enhanced support to programme delivery.

The EFY 2017 Annual Report shows notable progress in system strengthening and coordination but also exposes persistent operational bottlenecks. The Management Information System (MIS) expanded to 480 woredas, with 90% syncing household data to the federal level, and the Fayda digital ID integration began with over 76,000 clients registered. Capacity-building efforts reached federal, regional, and woreda staff through multiple trainings, while regular Technical Committee meetings and JRIS missions improved oversight and accountability. However, challenges remain in timely procurement of key items such as solar pumps and Personal Protective Equipment (PPE), delays in reporting and financial reconciliation, and limited MIS coverage in some regions. Coordination across implementing agencies also requires strengthening, especially between MoF, MoA, and regional bureaus.

REACH
FCDO signed an agreement with REACH in September 2023 to improve the availability and quality of humanitarian data and evidence, with a particular focus on hard-to-reach areas. REACH has produced high-quality data and evidence products, which enhance the availability of humanitarian information, enable better needs assessments, and support preparedness and effective response.

In FY 2023/24, a total budget of £1.3 million was allocated and fully committed, reflecting an improvement from the previous year’s spend rate, which was only half of the total budget.

REACH provides quarterly and bi-annual reports, though often with delays and lower-than-expected forecasts, which affect payment schedules. Managing the rapid expansion of their team, from a small group focused on Tigray analysis to a larger country office by the end of FY 2023/24, has also been difficult. Nevertheless, progress has been made, including expansion into Oromia with SMART+ Surveys. The FCDO team and REACH have held multiple bilateral meetings to address these concerns and proactively identify solutions.

ICRC
FCDO signed a Memorandum of Understanding with ICRC in December 2023 to contribute to its annual appeals. ICRC is a key partner in achieving the programme’s strategic objective of prioritising lifesaving assistance by reaching the hardest-to-access communities. ICRC operates in areas where conflict is active and where other humanitarian actors face significant challenges in delivering aid.

As of this reporting period, total funding amounts to £21.9 million: £4.5 million for the 2023 appeal, £9.4 million for the 2024 appeal, and £8 million for the 2025 appeal. ICRC does not have a direct downstream delivery chain; instead, it manages project delivery to the last mile. From a financial perspective, 97% of the funding is implemented directly by ICRC, while the remaining 3% is allocated to the Ethiopian Red Cross Society for capacity building and system strengthening to support collaboration within the Red Cross Movement.

ICRC publishes mid-year and annual reports on the operations of its country delegation, which are made available on the donors’ extranet—a platform accessible only to donors. Each donor receives attributed results based on their percentage contribution to the annual appeal budget.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring

Each EC2R partner has their own Monitoring, Evaluation and Learning (MEAL) component embedded into their projects. Results are presented to FCDO either bi-annually (UNICEF, WFP, ERCS, BRC and REACH through joint donor reporting) or annually (ICRC and World Bank), which gives an overall insight into what is and is not working to allow for continuous improvement of the programme.

The Resilience and Humanitarian team also conduct frequent monitoring of the programme through regular engagement with partners and field visits to implementation sites around Ethiopia. Throughout the reporting period (June 2024 – June 2025), the team has conducted 17 visits around the country to monitor activities in all major sectors and implementation areas: Education, Rapid Response Mechanism, Nutrition, PSNP, Protection and GBV, Cash, Health and WASH. These visits were often conducted with cross-Embassy representation (e.g. joined by colleagues from Senior Leadership, Political and Human Capital Development Teams) which provided an additional layer of challenge and oversight. Despite severe travel restrictions, several of the field trips have also taken place in Amber and Red areas on FCDO’s Ethiopia travel advice map (e.g. Tigray, West Oromia), with the right mitigation measures in place. Back To Office Reports (BTORs) have been systematically produced, circulated and recorded, ensuring that lessons learned are shared with all relevant staff in both BE Addis Ababa and across FCDO (e.g. Humanitarian and Africa Departments in London).

Following recommendations from the last Annual Review, the programme team has engaged a Third-Party Monitoring (TPM) partner to observe partner activities and collate beneficiary feedback in hard-to-reach areas. In mid-2025, the team expanded their accountable grant with IMPACT to include a new stream of TPM activity facilitated by PANDA, a subsidiary of IMPACT specialising in monitoring and evaluation. The TPM workstream formally commenced in August 2025 (NB: outside of the current reporting period), and will consist of 2 rounds of data collection in hard-to-reach areas to develop 6 Light Touch Verification (LTV) reports (each focusing on a different partner and activity e.g. UNICEF Nutrition interventions in Tigray; ERCS Health and Hygiene programming in Benishangul-Gumuz, and WFP’s Nutrition interventions in Oromia); 1 Deep-Dive report on a specific topic, and a Lessons Learned Workshop scheduled for February 2026. LTVs and the Deep-Dive report will investigate beneficiary experiences, involvement and feedback of services provided in each location, and will include Flash Reporting on any incidents of SEAH, aid diversion or large-scale fraud which are detected during data collection. Reporting on the results and evidence generated by the TPM will be included in the next Annual Review.

Evaluation

The results currently being reported across EC2R delivery partners are predominantly output-focused, and there is limited evidence being generated on outcomes or overall impact. The programme team is working with partners to improve the quality of reporting from partners to focus on outcomes and impact, which will be reflected in the Joint Donors Mid-Year Report due in early 2026.

In terms of deeper evaluation, at least two partners (WFP and World Bank) have conducted an impact evaluation during the reporting period on specific interventions with their programming: WFP has contracted Addis Ababa University to conduct a Randomised Controlled Trial (RCT) comparing nutrition interventions across Ethiopia, while World Bank contracted Oxford University to conduct a RCT comparing livelihoods interventions (specifically the comparative advantage between grants and credit-based loans to households living in poverty). The EC2R programme team also aims to make an application into FCDO’s Strategic Impact Evaluation and Learning (SIEL) Programme in early 2026 with the aim of securing funding for a broader impact evaluation of the EC2R programme. The outcome of this will be included in the next Annual Review.

Evidence
The EC2R team have been aware of evidence gaps for informing learnings and improvements for EC2R throughout the reporting period. A “Mid-term Evaluation of Ethiopian Crises to Resilience Programme” was commissioned to address the gap - the report was finalised in January 2025 and provided useful insights into the programme’s process and implementation. However, there were challenges in the development of the report, including a heavy requirement for inputs from the Resilience and Humanitarian Team and additional concerns about the scope of the report, as funding was provided to UNICEF, who sub-contracted the project to the Centre for Evaluation and Development (C4ED). Given C4ED reported directly to UNICEF on the process, the Terms of Reference initially had a narrower focus on UNICEF’s activities rather than a broader approach on the full spectrum of EC2R partners and the programme as a whole, although this was rectified ahead of final publication.

Learning

Regular meetings between partners collaborating on EC2R are held quarterly to promote learning across the consortium. These include presentations from partners and collaborative workshops to share lessons on common issues and risks. A specific learning identified during the reporting period was the need to improve current reporting practices, given the excessive length of the report and disproportionate focus on outputs over outcomes. A collaborative effort to reframe the reporting template and generate easy-to-share learning products including infographics and visual tools will be encouraged in the year ahead.

Date of last narrative financial report	December 2025 for WB, September 2025 for ICRC, and 20 August 2025 for all partners.	Date of last audited annual statement	Refer to each partner’s section.