BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Ethiopia Crises to Resilience (EC2R)
Directorate/ Post	Africa and the Americas / Ethiopia	Contact name	Alex Marshall, Team Leader, Resilience and Humanitarian Team, BE Addis
Original programme budget	£240 million	Country or region targeted	Ethiopia
Cost extension value	£253 million	Original BC approver (Minister, DG, HoM, Director, Dep. Dir)	Minister
New increased or reduced programme budget	£493 million	Current programme start and end dates	18/01/2022 - 30/06/2026
Latest AR programme score and outcome confidence rating	AR score: A / Outcome confidence rating: Amber/Green	New programme end date (if applicable)	31 March 2028
Programme ID	301474 / https://iati.fcdo.gov.uk/iati_documents/D0002694.odt

Detailed information
Programme summary	The “Ethiopia Crises to Resilience” (EC2R) programme is designed to provide life-saving assistance to those currently in need, support households so they are better able to withstand disasters and shocks and invest to reduce the impact of future shocks on vulnerable populations. In line with the UK’s Humanitarian Framework and the 2023 White Paper on International Development, it is prioritising humanitarian assistance to the people in greatest need, protecting the people at most risk, and preventing and anticipating future shocks. It does so while building resilience by making social protection a key element of UK action to reduce extreme poverty and hunger and tackle climate risks. This responds to the Foreign Secretary’s priority to promote international development and address critical challenges. / Ethiopia continues to have one of the highest humanitarian caseloads in the world, with over 21 million people requiring assistance in 2024. While hotspots of acute need may shift over the coming years, overall needs are expected to remain elevated, driven by a combination of climate shocks, conflict, disease outbreaks and economic challenges. / Responding to the humanitarian crisis, the programme provides multi-sector support across three outcome areas: / Multi-sectoral humanitarian assistance meets the needs of Ethiopia’s most vulnerable populations. / Poor households are better able to withstand disasters and shocks. / Humanitarian systems are able to identify risks and respond early and cost-effectively. / The programme is performing well against these objectives, scoring an A (meets expectations) in all annual reviews to date (January 2023, 2024, and 2025). / A major lesson to date is the importance of the programme’s flexible approach, which has enabled it to respond with agility to the volatile context in Ethiopia where humanitarian needs continuously evolve.
Changes	This three-year time and £253 million cost extension (of which at least 50% is International Climate Finance) will provide the FCDO with a tested and well-functioning vehicle to continue to provide critical humanitarian assistance in Ethiopia. Through EC2R, FCDO Ethiopia has consolidated all its humanitarian assistance into one business case. It provides a strong framework to respond to humanitarian needs in both the short and medium term. It is also FCDO Ethiopia’s main instrument to support climate adaptation and deliver on the UK’s International Climate Finance commitments. / FCDO Ethiopia has considered the development of a successor business case but dismissed this as having limited value, as a new business case would not be materially different from the current programme. / With EC2R in its last year of implementation, now is therefore right time to extend the programme. This will avoid a cliff edge, ensure continuity in the UK’s humanitarian and climate support, and ability to meet UK priorities. It will also enable continued delivery through well-established delivery mechanisms and partners, enabling FCDO staff to focus on the humanitarian response rather than on new programme development, procurement and mobilisation. / In addition, in line with the UK’s Grand Bargain[1] commitments, an extension will provide the necessary programming horizon to facilitate multi-year arrangements that enable partners to plan and deliver more efficiently and effectively, including through local partners, which are currently responsible for more than half of EC2R implementation. / This time and cost extension is building on lessons from the first two years of the programme (2021-2023), extending and expanding the UK’s humanitarian support by scaling up activities under the three output areas agreed in the original business case: / Responding to emergency needs / Scaling up UK multi-sector support to health, nutrition, WASH, protection, humanitarian cash and emergency education to meet acute and evolving needs across Ethiopia. / Increasing the focus on resilience to climate and conflict shocks and stress by increasing our support for Ethiopia’s Productive Safety Net Programme (PSNP) and / where effective. / Investing in a rapid response mechanism to improve ability to anticipate shocks and speed up the delivery of immediate assistance to affected populations. / Preserving and strengthening systems / Strengthening the provision of high-quality risk analysis and early warning information to inform planning and implementation of climate smart or sensitive investments that anticipate, absorb, adapt, and mitigate climate change. / Continuing capacity support for humanitarian and government partners through strategic secondments and technical support to UN agencies and the Government of Ethiopia, to strengthen national systems, improve crisis preparedness and support a pivot towards building resilience. / Improving use of evidence / Expanding coverage of current evidence and analysis generation to improve the capability to carry out rapid assessments. / Rolling out Third Party Monitoring to give the programme ears and eyes on the ground. / Making provision for evaluation so systematic data on processes and results are collected independently at mid and end-term to facilitate accountability and lesson learning for a programme of this magnitude. / The original Theory of Change for the programme was built around the activities and outputs set out above and has been rigorously tested through implementation. This time and cost extension principally seeks to scale up the inputs, outputs and outcomes already agreed in the original business case, while also strengthening monitoring and evaluation. There are no material changes to approaches and objectives in the original business case, which was approved by the Investment and Delivery Committee (IADC) without a score as the business case was retrospective. In their review, the IADC noted the persuasive cost/benefit ratio for social protection and how VfM would be central to EC2R design and delivery, through the programme’s investments in more preparedness, support for cost-effective national systems, and efforts to reduce inefficiencies in the humanitarian architecture. During the extension period, the EC2R partnership model and the delivery of outputs focused on ‘preserving and strengthening systems’ will continue to drive this VfM proposition.
Implementation	A distinguishing feature of the EC2R programme is its partnership approach to implementation. Its governance, planning, and implementation structures have all been designed to promote collaboration between implementing partners, with the aim of reducing inappropriate competition between humanitarian actors, which often leads poor planning and coordination and fails to maximise intended outcomes. / This approach will be maintained and strengthened through the extension period, with the appointment of EC2R focal points funded through UNICEF. They will support the coordination of planning, implementation and reporting, while also increasing the expertise on climate change and Value for Money (VfM), two areas identified as capacity gaps for partners. / The programme will continue with its current core implementing partners: UNICEF, WFP, Ethiopian Red Cross, British Red Cross, ICRC, REACH and the World Bank. Existing MoUs and Accountable Grants will be amended to reflect the longer programming horizon, available funding and thematic focus areas. As set out in the original business case, new partnerships may be added to expand the diversity of partners, in line with Programme Operating Framework (PrOF) rules and with the approval of the EC2R Programme Steering Board. / The programme will continue the flexible approach which allows it to respond to changes in need or to the context by pivoting its support accordingly. The governance structure is key to enabling this. During the first two years of implementation, it has gone through minor adjustments which have clarified decision making and collaboration mechanisms both internally and externally with partners. / In accordance with this governance structure, the EC2R Programme Steering Board - which is chaired by the programme SRO and brings together the FCDO Ethiopia Development Director with relevant stakeholders in the Embassy - will remain the principal forum to provide strategic direction and programming decisions on the programme. In terms of day-to-day planning and implementation, the programme SRO and PRO will be supported by a team of cross-embassy advisers with expertise in the different sectoral areas of implementation (health, nutrition, WASH, protection, cash, social protection, and evidence/data) and a group of programme managers who will lead on the institutional relationship with implementing partners. A full overview of the programme governance structure is provided at Annex A. / In addition, the programme’s Internal Risk Facility (IRFs) is critical tool that will enable it to respond to crises, taking advantage of additional funding made available from the Humanitarian Crisis Reserve or ODA headroom elsewhere in FCDO. Since the original business case was approved, Her Majesty’s Treasury has provided new guidelines for the use of IRFs. Annex B sets out how these guidelines will be applied to EC2R.
Budget	This Addendum extends the lifetime of the EC2R programme from March 2025 to March 2028. It provides for an additional £253 million of UK support (£110m of which already approved by HMT), including at least 50% ICF, increasing the total support under the Ethiopia Crises to Resilience Programme from the HM Treasury approved amount of £240 million to £493 million over 7 years. / The cost extension is financially affordable and will be funded fully from within the annual ODA budget allocated to FCDO Ethiopia. Of the £330m extension originally requested in 2024, a maximum budget of £110m (£10m of which IRF) for spend in FY 2025-26 only was approved by HMT. The programme team were instructed to return to HMT for approval to spend in outer years, following the 2025 Spending Review. For both FY 2026-27 and 2027-28, FCDO Ethiopia has now been provisionally allocated £98.8m pa in bilateral ODA. Of this, £65m pa has been provisionally allocated to the humanitarian budget. Over the next two years (£130m), plus 10% Internal Risk Facility budget (£13m), this total comes to £143m. / Based on current evidence and UK commitments, this budget profile reflects the expectation that humanitarian needs will remain high and FCDO Ethiopia will continue to prioritise humanitarian and climate support within its portfolio. / All formalising agreements will contain break clauses so funding can be adjusted if needed. / The additional £253 million includes £230m for planned spend (£100m / £65m / £65m), and £23 million as additional 10% buffer under the Internal Risk Facility, to be drawn on if additional emergency funding is allocated to Ethiopia in future, from the Humanitarian Crisis Reserve or FCDO ODA headroom elsewhere. / Tables 1 and 2 set out the approved budget and spend for EC2R under the original business case and the proposed budget for the cost and time extension, respectively. / Table 1: Approved budget and spend for EC2R under the original business case / Original £240m Business Case Planned, Actual and Programmed Spend (£million) / 21/22 22/23 23/24 24/25 IRF Total / Planned in original Business Case 22.0 30.0 64.0 84.0 40.0 240.0 / Actual RDEL 22.0 30.5 76.4 128.9 / Actual CDEL 0.0 2.0 3.5 5.5 / Programmed RDEL 50.6 40.0 90.6 / Programmed CDEL 15.0 15.0 / Actual and Programmed TOTAL 22.0 32.5 79.9 65.6 40.0 240.0 / Of which ICF 7.8 8.3 19.6 29.0 17.8 82.5 / Table 2: Proposed cost extension for this addendum / Proposed Business Case addendum value (£million) / 25/26 / (already approved by HMT) 26/27 27/28 IRF (10%) Total BC Addendum Total new BC Value / EC2R Funding 100.00 65.00 65.00 23.00 253.00 493.00 / RDEL 85.00 55.25 55.25 19.55 215.05 / CDEL 15.00 9.75 9.75 3.45 37.95 / Of which ICF 57.00 32.50 32.50 11.50 133.50 / The budget for the three years covered by the cost and time extension will be programmed in ways that offer flexibility and adaptability to an ever-changing context. The oversight and decision making on resource allocation will be managed by the EC2R Programme Steering Board, with adjustments made based on partner performance and the relative impact interventions have in responding to needs. / Table 3: Proposed thematic profiling / Thematic areas BC Addendum Cost Extension Total % % ICF % ICF / FY £m Cost Extension £m Budget Allocation for 26-28 ONLY Budget Allocation 3 years TOTAL Spend / 25/26 (already approved) 26/ 27 27/ 28 / Responding to needs / Protection and Gender Services 7.0 10.0 10.0 27.0 14.0% 11% 13.5 50% / Nutrition 13.5 14.0 14.0 41.5 19.6% 16% 20.8 50% / Health 12.0 4.0 4.0 20.0 5.6% 8% 10.0 50% / WASH 12.0 2.0 2.0 16.0 2.8% 6% 8.0 50% / Humanitarian Cash 10.0 10.0 10.0 30.0 14.0% 12% 15.0 50% / Rapid Response Mechanism 0.0 5.0 5.0 10.0 7% (2% cash) 4% 5.0 50% / Emergency Education 7.0 4.0 4.0 15.0 5.6% 6% 7.50 50% / Sustaining systems / Social Protection 35.0 13.0 13.0 61.0 18.2% 24% 61.0 100%* / Analytical capability / Evidence and Analysis 1.5 1.25 1.25 4.0 1.7% 2% 2.0 50% / Technical Support 0.5 0.5 0.5 1.5 0.7% 1% 0.75 50% / Monitoring & Evaluation 1.5 1.25 1.25 4.0 1.7% 2% 2.0 50% / Internal Risk Facility 10.0 6.5 6.5 23.0 9.1% 9% 11.5 50% / Total BC extension 110.0 71.5 71.5 253.0 100% 152.0 60% / * The ICF marker for social protection programming in Ethiopia has been increased from 70% (as in the 2024 BCA) to 100%, approved by the BE Addis Climate and Environment Adviser.
Impact	Tick relevant box): / ☒ No impact or positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ Negative impact – no/negligible change to Business Case delivery ambition.
Risk	The overarching risk of EC2R programme remains ‘major’. Many of the same risks identified in the business case remain unchanged, with risks associated with climate shocks, conflict, lack of access and safeguarding featuring prominently in the programme risk register. / Although FCDO does not support in-kind food assistance through the EC2R programme, the EC2R programme team sought additional assurance from all partners in response to the food aid diversion. This resulted in updated and more detailed delivery chain risk maps, increased partner oversight, better beneficiary feedback mechanisms, improved partner third-party monitoring and strengthened controls at all levels. / The EC2R programme team will continue to push for a risk management approach that evolves and adapts over time.
Results / Monitoring and Evaluation	This cost and time extension will enable the EC2R programme to deliver the following anticipated additional results: / Nutrition – Over 306,130 children, mothers, adolescents, and pregnant women will be reached with nutrition services including treatment of Severe Acute Malnutrition (SAM), micronutrient supplementation, and nutrition education & counselling services. / Health – 487,029 people will be provided with access to primary health care services including antenatal care, vaccination, and skilled birth attendance. / WASH – 278,261 people will be given access to safe water for drinking and domestic needs in affected regions (estimated 50% females, including 16% people living with disability (PLWD)). / Humanitarian Cash Assistance - approx. 1million people (200,000 households) will receive Shock-Responsive Cash Transfers (56% headed by women and 10% eligible for the disability top-up). / Child protection and Gender based Violence - 218,571 individuals will be reached with specialised and non-specialised psychosocial support (70% girls and women, 10% people with disabilities). / Education – 38,714 children will directly benefit from education services annually at the pre-primary and primary levels (50% girls and 10% children with disabilities). / Productive Safety Net Programme (PSNP) – Up to 290,476 vulnerable individuals will receive support through Ethiopia’s flagship safety net per year (51% per cent women and over 15% with disabilities) / The EC2R logframe has been designed to capture results delivered in the above sectors. Subject to agreement of the time and cost extension, it will be extended to include additional results. / The Theory of Change set out in the original business case remains valid, although the assumption that the Government of Ethiopia maintains financing to basic services will need to be monitored in light of the most recent national budget.[2] Continued constraints in Government financing for health, education and WASH could limit the programme’s ability to meet the needs of the most vulnerable, as more people will require humanitarian assistance. This may require an adjustment to the level of ambition for the programme. / An independent mid-term and end-line evaluation will be commissioned to understand how well the programme is achieving its goals, as well as to determine what works well and what could be improved in EC2R and future programming.
[1] The Grand Bargain is an agreement between some of the largest donors and humanitarian organisations, setting out a series of commitments to improve the effectiveness and efficiency of humanitarian action. This includes a commitment to localisation of humanitarian delivery.
[2] The Ethiopia Federal Democratic Republic budget allocation to pro-poor sectors has dropped from 55% of the budget in 2021/22 to an estimated 33% in 2023/24 (source: Ministry of Finance and UNICEF)

Annex A – EC2R Internal and External Governance Structures
Internal structures:

FCDO EC2R Programme Steering board - Chaired by the SRO and quorum with the Development Director and team leaders. Acts as a link to management and decision making and sits under the Embassy Policy Board and Deliver Committee.

EC2R Joint Advisory Group - Led by the PRO and responsible for designing and delivering the overall programme, working with partners to develop and maintain the logframe, plan field monitoring visits and make recommendations for decisions to the EC2R Programme Steering Board.

EC2R partnerships and programme management team – led by the PRO with support from the SRO. Focuses on:

- effective partnership management
- strong financial management
- compliance with PrOF rules and FCDO legal obligations
- reporting and results, and
- risk management (e.g. due diligence, delivery chain mapping, aid diversion and safeguarding issues)

External Governance:

Strategic and operational collaboration – Led by the PRO on a quarterly basis, providing strategic engagement with deputy country representatives and operation leads within partner organisations. Focus on senior level engagement from partners on both strategic programme and operational planning, discussing opportunities and challenges.

Thematic collaboration – Led by partner focal points and centred around monthly meetings where FCDO technical leads meet with relevant partner technical leads to discuss opportunities and challenges and agree actions for their respective thematic sectors.

Regional collaboration – Led by partners in regions where EC2R is operational. Occurs monthly or on an ad hoc basis to support operational planning.

Annex B – EC2R INTERNAL RISK FACILITY (IRF)
Internal Risk Facility
The Internal Risk Facility (IRF) for the Ethiopia Crises to Resilience (EC2R) programme will provide pre-approved flexibility to scale up a rapid response to significant new risks and needs resulting from either a conflict, climate, or a disaster shock.

In line with Her Majesty Treasury (HMT) guidelines and FCDO PrOF Rule 9, the value of the IRF will be £23 million (10% of cost extension value).

Value for Money
The IRF will enable the UK to respond quickly, save lives, and prevent avoidable human suffering as new crises emerge. Evidence shows that acting early in this way increases speed (by over two weeks) and impact (between 50% and 160% at the portfolio level).[3] Without this facility, the UK risks not being able to respond in a timely, efficient, and effective way to future crises and potentially exposes the British Embassy in Ethiopia to political and reputational risk.
[3] The portfolio assessed consisted of over 80 different investments in six countries; return on investment at a portfolio level was £1: £1.50-£2.60 (median and mean respectively). https://www.humanitarian-preparedness.org/evidence.html

Triggers
The IRF will allow FCDO to respond wherever possible in advance, to mitigate impact of an event, or as quickly as possible after an event. The trigger mechanism has been informed by the FCDO’s published guidance framework setting out intervention criteria for humanitarian responses.[4] The triggers for the utilisation of the IRF will be based on the predictability and speed of the onset of crises (see illustration below) along two types of response:
[4] Policy and Guidance - Intervention Criteria Template with No Regrets.docx - All Documents (sharepoint.com)

1. An Anticipatory response - Using research to release funding based on:
  1. Detailed risk analysis of climate and disaster risk
  2. Vulnerability data for the population
  3. Weather and other forms of forecasts
2. A rapid onset - A sudden unforeseen escalation in a crisis generated by crises that are difficult to anticipate – such as a disease outbreaks, epidemics, conflict, or earthquakes.

Types of Interventions
The interventions funded by the IRF will be prioritised based on the type of response scenario and in accordance with the UK humanitarian policy objectives:

- PRIORITISE: deliver lifesaving assistance to Ethiopia’s most vulnerable populations, with a focus on getting aid to the hardest-to-reach communities.
- PROTECT: protect civilians affected by conflict and crises, with a focus on gender-based violence.
- PREVENT: support the resilience of Ethiopia’s poorest households to cope with shocks and improve the ability of national and international systems to identify and respond early to emerging risks.

Additional funding through the IRF will be used through existing EC2R implementing partners and channelled to thematic areas where EC2R and FCDO have existing programming, building on investments already made in health, nutrition, water and sanitation (WASH), protection (child protection and gender-based violence), shock responsive cash transfers, and education.

Management – Decision making and finance
Should there be a need for FCDO to respond quickly to a crisis, the IRF will provide a framework for the rapid allocation of funding from within the business case by bringing on stream funding held by the department or central FCDO departments, including from the Humanitarian Crisis Reserve. The decision to execute this would be made by the EC2R Programme Steering Board and confirmed by the Embassy Delivery Committee.

Based on assessments of the impacts of previous disasters, the IRF is appropriate for:

Anticipating small crises - Affecting up to 2 million people

Facilitating a catalytic role as part of a FCDO’s first phase response to medium to large scale emergencies - Affecting over 2 million + people.

Even in the event of a major disaster beyond the scale that could be addressed through the IRF, the IRF would provide an initial and catalytic role as part of a FCDO’s first phase response.

Humanitarian diplomacy
If the IRF is triggered, speed of disbursement will be prioritised to allow the UK’s own humanitarian diplomacy to register more effectively. The release of the IRF will provide an opportunity for UK Ministers to announce timely and relevant funding, demonstrating UK agility and relevance. This includes encouraging and leveraging additional support from other donors. This will contribute to making our technical asks and policy decisions land more effectively with a range of stakeholders whether national governments, humanitarian partners or member state counterparts at national, regional or international levels.