## ICM draft (1 year) (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned |  |  | xxx examples | xxxx examples
Achieved
Source
Programme reporting information and feedback from relevant stakeholders such as UN agencies, governments, healthcare providers, advocacy groups, communities.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
Programme reporting on progress on midwifery leadership, advocacy actions and actions to strengthen service delivery and quality
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned | Number of emergencies treated before the M-mama programme starts
Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | Systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | Landscaping completed; movement committee set up; capacity needs identified; marginalised groups reached
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Monitoring of lessons learnt for global sharing | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (6 months) | Milestone 2 (11 months) | Target (End of Year 1) | Assumptions
FCDO: Local associations are strengthened ICM: Selected national midwives associations are strengthened through ICM support and the utilization of ICM resources | FCDO: Local MA's operations are strengthened - capacity, financial stability, agility etc (Finance, governance, advocacy) | Planned |  | 3 MAs (Kenya, Pakistan, Malawi) undertake MAAC | 3 ICM reports on MAAC | 3 MAs 3 MAAC 3 ICM internal review reports
Achieved
| ICM: # of Member Association Assessment Checklist(MAAC) completed | Source
MAAC, ICM internal review report including MA management response
| Output Indicator 2.2 |  | Baseline | Milestone 1 (6 months) | Milestone 2 (11 months) | Target (End of Year 1)
| FCDO: Local MA's carry out actions to improve the quality of midwifery practice a) in countries and b) linked to global activities | Planned |  | 1) 1 workshop & report 2) 20 participants from MA | 1)1 workshop & report 2) 20 participants (cumulative 2 and 40) | 1) 2 workshop (cumulative) 2) 40 workshops participants
Achieved
| ICM: 1) # of advocacy workshops facilitated for 3 MAs 2) # of participants who attended the advocacy workshop | Source
1) Advocacy workshop report
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (6 months) | Milestone 2 (11 months) | Target (End of Year 1)
| Local MA's involve and reach the most marginalised groups -adolescents, those living with disabilities, conflict settings etc | Planned | 1 (Ready to Respond Module) | 1 revision of the current resource | 2 workshops | 1 revised resource and 2 workshops
Achieved
| ICM: # of revised and newly developed ICM's resources for MAs on Climate and Humanitarian Crises prepardeness | Source
ICM data repository (Resource, workshop materials)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Emergency transport is set up and improving access for pregnant women |  | Planned
| Emergency transport system is fully set up i.e. dispatch centres, network of accredited drivers, payment systems, community awareness raising etc. | Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Women and babies are using the service including those from the most marginalised groups (adolescents, those living with disabilities, those in conflict settings) to be transported a) between facilities b) from home to a facility. | Achieved
Source
Programme reporting and data collection
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Programme data collated and being used by government for planning and monitoring | Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Log Frame
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Year 2) | Milestone 2 (Year 3) | Milestone 3 (Year 4) | Target (EO Y5) | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (Year 2) | Milestone 2 (Year 3) | Milestone 3 (year 4) | Target (EO Y5) | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | An increase in cohesion and reach of systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | October 2025 MMAP completed in 2 countries, anchor partners, policy priorities and diverse, intersectional partners identified | April 2026 One movement advisory group per country formed with recommendations for criteria for grantmaking, clear articulation of in-country GM priorities which will form the basis of grant decisions, terms of reference, roles and responsibilities among advisory group, GFW, Comotion, and anchor partner agreed | April 2027 Based on Advisory Group's recommendations, the Anchor partner in each country, provides 5 to 15 grants per country (through 2 rounds of grantmaking) with systems set up to track and report on progress | 10-30 Marginalized groups reached with financial resources, capacity strengthening, and social capital for advocacy and movement building stories and reports of impact captured and shared | Anchor partners have the capacity to support grassroots organizations adequately with strong due diligence. Committees decide on distributing at least 15 - 20 grants rather than structuring their grantmaking processes differently. Resources are available and used effectively to support groups with capacity strengthening and opportunities to increase social capital.
|  | Achieved |  | Not scored as part of first Annual Review
Source
Movement Mapping Assessment Process (MMAP) tool Participatory design and approval of committee TOR Profile and Proposal forms in Salesforce (for equity indicators)
| Output Indicator 1.2 |  | Baseline (Year 2) | Milestone 1 (year 2) | Milestone 2 (year 3) | Milestone 3 (year 5) | Target (EO Y5)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned | October 2025 Movement priorities and needs identifed through MMAP process | March 2026 2 SMART workshops conducted with Movement Advisory Group and movement actors to define movement capacity needs and agree suitable advocacy approach. | March 2027 Shared advocacy agenda across movement actors per country established | 10-30 Grassroots, regional and global MNH actors meet to discuss and align advocacy efforts | 10-30 Diverse grassroots MNH actors report being stronger and more effective in their work, with stories of success shared and documented | Organizations wanting to work together and collaborate on advocacy for MNH rights at grassroots, regional, and global level. Committee members find results of MMAP and MCAT useful to design a cacpity strenghtening plan and advocacy approach. Movement actors are able to work within the political, economic, and social realities at the grassroots, regional, and global levels.
|  | Achieved | Not scored as part of first Annual Review
Source
Movement Committee Capacity Assessment tool (MCAT) Documented capacity strengthening plan MNH actors convening report SMART Advocacy Workshop report
| Output Indicator 1.3 |  | Baseline | Milestone 1 (year 1) | Milestone 2 (year 2) | Milestone 3 (year 5) | Target (EO Y5)
| Lessons learnt documented for regional and global sharing | Planned | GFW Learning agenda principles including use of participatory methods geared toward uplifting grassroots feminist knowledge production will inform project specific Learning, Evaluation and Analytics (LEA) | April 2025 Project communications plan developed to define moments, opportunities and channels to showcase the project and partnership to inform future learning for gov and feminist funds | March 2026 Project learning agenda developed and agreed in alignment with committee and grantee defined learning questions and advocacy approaches, underpinned by GFWs LEA principles Milestone 3 (Year 2): Comotion and GFW disseminate findings from Country-mapping desk exercise through 1 webinar and through the IMNHC 2026 March conference Milestone 4 (Year 3): Country mapping and MMAP survey findings and learnings are disseminated at the Women Deliver conference in April 2026 | Grantees have attended one international and one national conference to share learnings from project with new and established community of MNH and development actors At least one policy paper written and diseminated to releavnt partners across governments and the MNH ecosystem | Governments, funders and MNH actors have a better understanding of how relationships between government and feminist funds work in practice, and have stories of impact to inform their future funding for grassroots advocacy | Grassroots organizations, committees, and GFW adequately collect, document, and manage data and information on lessons learnt for global dissemination The Learning Agenda includes relevant learning questions and activities to inform target Project Communications Plan includes relevant activities to reach its goal of informing future learning for govt and feminist funds.
|  | Achieved |  | Complete - Scored in Year 1 Annual Review
Source
Documented learning agenda Project communications plan Policy paper Grantee satisfaction endline survey to understand grantees' lessons learnt over the 5 years of the activity
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (year 1) | Milestone 2 (Year 2) | Milestone 3 (Year 3) | Target (End of year 3) | Assumptions
ICM strengthens the operations of national midwives associations (MAs) to better advocate, lead and operate with the most marginalised groups to improve midwifery practice and promote the profession. | Member Associations systems, functions, plans and capacity strengthened to enable advocacy and leadership. | Planned |  | 1) 2 Member Association Assessment Checklists (MAACs) to identify areas for strengthening completed and review reports written 2) 2 capacity strengthening action plans developed | 1) 1 Member Association Assessment Checklists (MAACs) to identify areas for strengthening completed and review reports written 2) 1 capacity strengthening action plans developed 3) Capacity strengthening action plans begin implementation with evidence of changes to functions, plans and capacity | Completion of implementation of 3 capacity strengthening action plans with success stories , narrative and visual evidence gathered. | No target - expect completion in Year 3 | 1. Active engagement and commitment from MAs: The selected MAs will actively engage in the capacity assessment process (MAAC) and will be committed to implementing the action plans developed as a result of the assessment. Without this engagement and ownership, progress toward strengthening operations, advocacy, and preparedness may be hindered. 2. ICM has a strong due diligence system: ICM can effectively identify suitable MAs and support them in successfully executing planned activities by applying thorough due diligence. 3. Support for MAs: Technical expertise and support will be available and accessible to MAs for implementing the action plans related to advocacy, capacity building, and humanitarian preparedness. This assumes that ICM or partners will have the necessary resources to guide MAs effectively. 4. Political stability and absence of major disruptions: The implementation of the planned activities will not be significantly disrupted by political instability, natural disasters, or pandemics. A stable environment is necessary for MAs to carry out their work effectively. 5. Stable funding: Consistent and predictable funding will be available to support the implementation of capacity-building, advocacy, and humanitarian crisis preparedness activities. Without financial stability, both ICM and MAs may face difficulties in sustaining their operations and implementing the necessary improvements.
|  | Achieved |  | Complete: 2 checklists completed (Pakistan, Malawi) and the full report with findings and recommendations drafted following a desk review and interviews. 2 capacity strengthening action plan developed for Pakistan and Malawi. Malawi’s action plan is waiting for final sign off in Q1 of Year 2.
Source
ICM data repository (MAAC reports, ICM reports, monitoring reports; minutes and calls; FCDO field visit)
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Year 1) | Milestone 2 (Year 2) | Milestone 3 (Year 3) | Target (End of year 3)
| Midwifery associations leading and advocating for improved midwifery practice and to promoting the profession. | Planned |  | 1) 1 advocacy training completed 2) 3 advocacy needs assessments completed and action plans developed | 1) 1 advocacy training (Malawi) completed 2) Advocacy activities started by 3 MAs | 1) National advocacy activities to improve the quality of midwifery practice implemented as per actions plans by 3 MAs 2) Global advocacy activity to improve the quality of midwifery practice implemented 3) Evidence of impact of advocacy activities gathered through data and success stories. | 1) Advocacy action plans fully implemented with all 3 MAs actively and regularly engaged in advocacy and leadership, clearly linking their work to global advocacy and showing evidence of impact.
|  | Achieved |  | Exceeded: Advocacy skills workshop in Kenya, Malawi. 3 Advocacy Needs Assessments were completed in Year 1.
Source
ICM data repository (Advocacy training resources, action plans, monitoring reports)
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (Year 1) | Milestone 2 (Year 2) | Milestone 3 (Year 3) | Target (End of year 3)
| MAs supported and strengthened to work in humanitarian crisese and to reach and include marginalised groups such as adolescents and those living with disabilities. | Planned |  | 1) 1 situational analysis of MAs' involvement with marginalized groups completed 2) Resources and support structure for MAs in humanitarian settings revised | 1) 1 Training of Trainers (ToT) on ICM's humanitarian resources completed and ToT on working with and inclusion of marginalised groups 2) ICM's Biennial Membership Survey 2025 updated with a section on working with marginalized groups and reported on | 1) Trained midwives completed roll-out of ToT 2) Follow up actions to Biennial Survey decided and implemented | 1) 3 MAs strengthened their preparedness, response skills in humanitarian crises 2) Evidence if inclusion of midwives from marginalised groups in MAs and engagement with marginalised groups of women and babies.
|  | Achieved |  | Complete: 1 situational analysis in Kenya. 1 resource (ICM’s Ready to Respond training package) for associations in humanitarian settings revised and 1 new resource (Empowering Midwives as Climate Champions) developed. 1 Training of Trainers on ICM’s ‘Empowering Midwives as Climate Champions’ completed
Source
ICM data repository (Humanitarian crisis prepardness and response resources, training results, roll-out of ToT statistics, Biennial Membership Survey data)
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (Year 1) | Milestone 2 (Year 2) | Milestone 3 (Year 3) | Target (End of year 3)
| ICM contributes to policy initiatives, reforms, or legislative changes at national, regional, or global levels that have a positive impact on the midwifery profession. Contributions may include technical support, advocacy, partnership, capacity building, or provision of evidence and resources. This is to capture and demonstrate ICM’s influence in shaping supportive environments for midwives through policy and legislation. | Planned |  |  |  |  | 1) ICM conducts an annual survey among MAs to assess and document their progress in advancing midwifery. | Collection of data, success stories, and narratives on policy initiatives and/or legislative changes supporting midwives, to which ICM and/or MAs have contributed.
Achieved
Source
ICM data repository (Humanitarian crisis prepardness and response resources, training results, roll-out of ToT statistics, Biennial Membership Survey data)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 |  | Assumptions
| Maternal and newborn emergencies are transported, and are reaching in a timely and cost-effective manner to an appropriate health facility and are followed up to track outcomes | Planned | 1 m-mama dispatch centre in operation | 15 dispatchers who have been trained and are actively working in m-mama dispatch centers. | 9 districts where 118 has been zero-rated and connected to m-mama dispatch center. | 150 community drivers with active MOUs to provide transport who have been trained on m-mama.
Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | 2026-03-01
| Quality maternal and neonatal health services are provided in health facilities by the Government of Malawi | Planned | 15 CEmONC-designated health facilities in Central Region assessed by m-mama team during clinical assessment process
Achieved
Source
Programme reporting and data collection
| Output Indicator 3.3 |  | 2026-01-01 | 2026-01-01 | 2026-03-01
| The Government of Malawi budgets for, manages, and operates the mmama emergency referral and transport system | Planned | 9 districts where an EmRTS Focal Person has been appointed and trained on mmama by end of January 2026 | 100% of health facilities in Central Region where, by end of January 2026, at least one staff member has been oriented to the availability, purpose, and method of activating mmama (via toll-free number) | 90% of GoM representatives in attendance at monthly operational M&E meetings (EmRTS Focal People from 9 of out 9 districts in Central Region participate)
Source
Programme reporting
| Output Indicator 3.4 |  | 2026-03-01
| Public is aware of the system, is using it, and is satisfied with its services | Planned | Information, education, and communication plan developed to engage public throughout districts in Central Region
IMPACT WEIGHTING (%) |  | Achieved
INPUTS (£)
| FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR)
FCDO (FTEs)
Note on D38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Comment from Isla: Please add dates, it’s important to know what we are assessing for what annual review (reminder: annual review deadline is April 23rd) Reply: Done
Note on E60: ====== ID#AAABbup05hI tc={5792CE5A-7C0C-4CAC-9828-E79EB956F0B5} (2025-01-31 06:22:24) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could reduce number 3) here if not possible
Note on C63: ====== ID#AAABbup05gs tc={3E6DBC23-F265-4B22-BFB4-967D4A86BFCA} (2025-01-31 06:22:24) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do give a link or an idea of what is in the MAAC please
Note on E65: ====== ID#AAABbup05hc tc={BB39225C-FD46-4395-B075-A52E8F7D3664} (2025-01-31 06:22:24) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should the needs assessment not precede the training? Not sure I understand what the training is exactly. Would we not expect 3 advocacy needs assessments in year 1 in this case and 1 training?

## ICM draft (2) (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned |  |  | xxx examples | xxxx examples
Achieved
Source
Programme reporting information and feedback from relevant stakeholders such as UN agencies, governments, healthcare providers, advocacy groups, communities.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
Programme reporting on progress on midwifery leadership, advocacy actions and actions to strengthen service delivery and quality
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned | Number of emergencies treated before the M-mama programme starts
Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | Systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | Landscaping completed; movement committee set up; capacity needs identified; marginalised groups reached
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Monitoring of lessons learnt for global sharing | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
FCDO: Local associations are strengthened ICM: Selected national midwives associations are strengthened through ICM support and the utilization of ICM resources | FCDO: Local MA's operations are strengthened - capacity, financial stability, agility etc | Planned |  | 2 countries | 1 country (Cumulative 3) | Total 4 countries who submitted ICM's MA Checklist
Achieved
| ICM: Number of countries who use and submitted ICM's MA checklist (MA) to identify the current stance and situation (Malawi, Pakistan) | Source
MAC report submitted by the MA
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| FCDO: Local MA's carry out actions to improve the quality of midwifery practice a) in countries and b) linked to global activities | Planned |  | 1 | 1 (Cumulative 2) | Total 3 resources updated/developed
Achieved
| ICM: Number of updated/newly developed ICM resources for MAs (OP 2.2.1) | Source
ICM data
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Local MA's involve and reach the most marginalised groups -adolescents, those living with disabilities, conflict settings etc | Planned |  | 200 register and participate at ICM AF&EM Regional conferences 25 burasy midwives from low-and middle-income countries | 200 register and participate at ICM EU Regional conferences (Cumulative 400) 3 bursary midwives from low-and middle-income countries | 400 total registration in both conferences
Achieved
| ICM: Number of participants in ICM resource dissemination workshops ICM 2: Number of bursary midwives attending the regional conferences from low-and middle-income countries | Source
ICM Regional Conference registration record
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Emergency transport is set up and improving access for pregnant women |  | Planned
| Emergency transport system is fully set up i.e. dispatch centres, network of accredited drivers, payment systems, community awareness raising etc. | Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Women and babies are using the service including those from the most marginalised groups (adolescents, those living with disabilities, those in conflict settings) to be transported a) between facilities b) from home to a facility. | Achieved
Source
Programme reporting and data collection
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Programme data collated and being used by government for planning and monitoring | Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## ICM draft (3) (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned |  |  | xxx examples | xxxx examples
Achieved
Source
Programme reporting information and feedback from relevant stakeholders such as UN agencies, governments, healthcare providers, advocacy groups, communities.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
Programme reporting on progress on midwifery leadership, advocacy actions and actions to strengthen service delivery and quality
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned | Number of emergencies treated before the M-mama programme starts
Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | Systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | Landscaping completed; movement committee set up; capacity needs identified; marginalised groups reached
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Monitoring of lessons learnt for global sharing | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
FCDO: Local associations are strengthened ICM: Selected national midwives associations are strengthened through ICM support and the utilization of ICM resources | FCDO: Local MA's operations are strengthened - capacity, financial stability, agility etc | Planned | 2 | Advocacy workshop: 1 Participants: 30 | Advocacy workshop 2 (Cumulative 3) Participants: 60 (cumulative 90) | 4 total workshops 120 total participants
|  | Achieved | Bangladesh & Morocco
| ICM: Number of MAs who participated in ICM advocacy workshop (Output 8.1.3) Number of participants in ICM advocacy workshop | Source
Participants list for the advocacy workshop
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| FCDO: Local MA's carry out actions to improve the quality of midwifery practice a) in countries and b) linked to global activities | Planned | 2 | 1 (cumulative 3) | 1 (cumulative 4) | 4 total advocacy action plans (March 2025)
Achieved
| ICM: Number of MAs who developed advocacy action plans (Output 2.1.4) | Source
MA advocacy action plans shared with ICM
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Local MA's involve and reach the most marginalised groups -adolescents, those living with disabilities, conflict settings etc | Planned | 0 | 1 resource developed | 2 resources developed (cumulative 3) | 3 total resources developed by ICM (March 2025)
Achieved
| ICM: Number of newly developed ICM's resources for MAs on Climate and Humanitarian Crises prepardeness (Output 10.1.5) | Source
ICM Resource repository
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Emergency transport is set up and improving access for pregnant women |  | Planned
| Emergency transport system is fully set up i.e. dispatch centres, network of accredited drivers, payment systems, community awareness raising etc. | Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Women and babies are using the service including those from the most marginalised groups (adolescents, those living with disabilities, those in conflict settings) to be transported a) between facilities b) from home to a facility. | Achieved
Source
Programme reporting and data collection
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Programme data collated and being used by government for planning and monitoring | Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## ICM draft (4) (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned |  |  | xxx examples | xxxx examples
Achieved
Source
Programme reporting information and feedback from relevant stakeholders such as UN agencies, governments, healthcare providers, advocacy groups, communities.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
Programme reporting on progress on midwifery leadership, advocacy actions and actions to strengthen service delivery and quality
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned | Number of emergencies treated before the M-mama programme starts
Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | Systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | Landscaping completed; movement committee set up; capacity needs identified; marginalised groups reached
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Monitoring of lessons learnt for global sharing | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
FCDO: Local associations are strengthened ICM: Selected national midwives associations are strengthened through ICM support and the utilization of ICM resources | FCDO: Local MA's operations are strengthened - capacity, financial stability, agility etc | Planned | 0 | 1 | 2 (cumulative 3) | Total 3 resource mobilization plans
Achieved
| ICM: Number of MAs that develop Resource Mobilization Plans (Output 1.1.2) | Source
Selected MAs share their resource mobilization plans with ICM
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| FCDO: Local MA's carry out actions to improve the quality of midwifery practice a) in countries and b) linked to global activities | Planned | 0 | 1 | 2 (cumulative 3) | Total 3 direct investment agreement
Achieved
| ICM: Number of Direct investment agreement in selected MAs (BMGF deliverable) | Source
Project agreement with selected MAs
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Local MA's involve and reach the most marginalised groups -adolescents, those living with disabilities, conflict settings etc | Planned | 0 | 30 | 60 (Cumulative 90) | Total 100 trained midwives
Achieved
| ICM: Number of midwife who are trained with ICM's "Ready to Respond" training modules | Source
Participants list
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Emergency transport is set up and improving access for pregnant women |  | Planned
| Emergency transport system is fully set up i.e. dispatch centres, network of accredited drivers, payment systems, community awareness raising etc. | Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Women and babies are using the service including those from the most marginalised groups (adolescents, those living with disabilities, those in conflict settings) to be transported a) between facilities b) from home to a facility. | Achieved
Source
Programme reporting and data collection
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Programme data collated and being used by government for planning and monitoring | Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## ICM draft (5) (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned |  |  | xxx examples | xxxx examples
Achieved
Source
Programme reporting information and feedback from relevant stakeholders such as UN agencies, governments, healthcare providers, advocacy groups, communities.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
Programme reporting on progress on midwifery leadership, advocacy actions and actions to strengthen service delivery and quality
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned | Number of emergencies treated before the M-mama programme starts
Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | Systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | Landscaping completed; movement committee set up; capacity needs identified; marginalised groups reached
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Monitoring of lessons learnt for global sharing | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
FCDO: Local associations are strengthened ICM: ICM becomes a sustainable and innovative organization to support and strengthen its member associations | FCDO: Local MA's operations are strengthened - capacity, financial stability, agility etc | Planned | 0 | 1 Resource mobilization plan 1 Leadership Plan 1 MA Strengthening Plan | 1 Global midwives' Hub Strategic Development Plan 1 Fund forwarding policy for MAs in humanitarian Crises 1 Updated education plan | Total 6 plans created/updated
Achieved
| ICM: Number of plans created/updated by ICM | Source
ICM data repository
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| FCDO: Local MA's carry out actions to improve the quality of midwifery practice a) in countries and b) linked to global activities | Planned | 0 | 6 workshops in Kigali | 6 workshops in Berlin (cumulative) | Total 12 ICM workshops
Achieved
| ICM: Number ICM workshops created and facilitated for the Regional Conferences | Source
Regional Conference Programme book
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Local MA's involve and reach the most marginalised groups -adolescents, those living with disabilities, conflict settings etc | Planned | 0
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Emergency transport is set up and improving access for pregnant women |  | Planned
| Emergency transport system is fully set up i.e. dispatch centres, network of accredited drivers, payment systems, community awareness raising etc. | Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Women and babies are using the service including those from the most marginalised groups (adolescents, those living with disabilities, those in conflict settings) to be transported a) between facilities b) from home to a facility. | Achieved
Source
Programme reporting and data collection
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
| Programme data collated and being used by government for planning and monitoring | Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## ICM draft (3 years-2) (hidden)
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Contribute to the reduction of maternal and newborn mortality in EPD flagship countries by 2030 and a drop in global maternal and newborn mortality. | Reduced maternal mortality ratio by by 5-10% (MMR, number of maternal deaths per 100,000 live births) - SDG 3.1.1 in flagship countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.STA.MMRT?end=2017&locations=XO&name_desc=true&start=2000 and the World Health Organization's Global Health Observatory https://www.who.int/data/gho/indicator-metadata-registry/imr-details/26
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| End preventable deaths of newborns by 5-10% - SDG 3.2: under-five mortality rate (U5MR) per 1000 live births in selected flagships countries | Planned
Achieved
Source
Data is tracked through the World Bank Data Bank: https://data.worldbank.org/indicator/SH.DYN.MORT?locations=XO Milestones and target estimates based on 1990 - 2020 trend that saw an average annual reduction in U5MR at approximately 2 per 1000 births
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  |  | Assumptions
Women and babies empowered and able to access quality services | Increased evidence of grassroots advocacy leading to changes in maternal and newborn health policies, planning, financing or service delivery. | Planned |  |  | xxx examples | xxxx examples | xxxx examples | xxxx examples
Achieved
Source
Programme reporting information and feedback from relevant stakeholders such as UN agencies, governments, healthcare providers, advocacy groups, communities.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Strengthened midwifery profession in focus countries as demonstrated by increased leadership positions, national level advocacy, improvement in service delivery and quality | Planned
Achieved
Source
Programme reporting on progress on midwifery leadership, advocacy actions and actions to strengthen service delivery and quality
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increase in pregnancy and newborn emergencies treated due to emergency referral systems. | Planned | Number of emergencies treated before the M-mama programme starts
Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) |  |  | Assumptions
Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building | Systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc) | Planned |  | Landscaping completed; movement committee set up; capacity needs identified; marginalised groups reached
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| An increase in grassroots MNH activites and a) activities that include marginalised groups b) activities that link with global advocacy efforts | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Monitoring of lessons learnt for global sharing | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 (YEAR 1: Sep 2024 - Mar 2025) |  | Baseline | Milestone 1 (Sep-Dec 2024) | Milestone 2 (Jan-Mar 2025) | Target (end of year 1) |  |  | Assumptions
FCDO: Local associations are strengthened ICM: Selected national midwives associations' capacities are strengthened through ICM support to improve midwifery practice and advocate for midwifery ICM v2: ICM supports selected national midwives associations in strengthening their operations, advocacy, and awareness of marginalized groups to improve midwifery practice and promote the profession. | FCDO: Local MA's operations are strengthened - capacity, financial stability, agility etc (Finance, governance, advocacy) | Planned |  | 1)3 MAs undertake MAAC 2) 3 ICM internal review report, including MA management response | 1) 3 MAs develop an action plan for capacity strengthening of MAs after completing MAAC 2) 1 monitoring plan and 1 data capturing tool are co-developed by ICM and MAs | Milestone 1-2 are all achieved
Achieved
| ICM: Areas of MAs capacity strengthening identified through MAAC, action plan developed and implemented ICM v2: Three MAs complete the whole cycle of MAAC, develop capacity-strengthening action plans, and co-develop monitoring plans and data capturing tool | Source
ICM data repository (MAAC reports, ICM reports, minutes, calls)
| Output Indicator 2.2 (YEAR 2: Apr 2025 - Mar 2026) |  | Baseline | Milestone 1 (Apr-Jun 2025) | Milestone 2 (Jul-Sep 2025) | Milestone 3 (Oct-Mar 2026) | Target (end of year 2)
| FCDO: Local MA's carry out actions to improve the quality of midwifery practice a) in countries and b) linked to global activities | Planned |  | 3 MAs participate in SMART advocacy training | 1)3 MAs develop SMART indicators and action plan 2) 1 monitoring plan and 1 data capturing tool are co-developed by ICM and MAs | 1) 3 Mas implement dvocacy action plan 2) 2 progress check meetings 3) 1 final reports from each MAs on Advocacy success stories | Milestone 1-3 are all achieved
Achieved
| ICM: Selected MAs advocacy capacity is strengthened ICM v2: Selected MAs participate in the SMART advocacy training, develop SMART indicators and action plan, contribute to the development of monitoring plans to keep the repository of success stories and lesson learnts | Source
ICM data repository (Advocacy training resources, action plans, monitoring reports)
IMPACT WEIGHTING (%) | Output Indicator 2.3 (YEAR 3: Apr 2026 -Mar 2027) |  | Baseline | Milestone 1 (Oct-Dec 2025) | Milestone 2 (Jan-Mar 2026) | Milestone 3 (Apr-Sep 2026) | Milestone 4 (Oct-Mar 2026) | Target (end of year 3)
| Local MA's involve and reach the most marginalised groups -adolescents (and youth -adolescent mothers), those living with disabilities, conflict settings etc | Planned |  | 1 ICM Biennial Survey is distributed and includes questions about MA's involvement with the most marginalized groups. | 1 survey results report | 1 training module developed to reduce the stigma and discrimination against the most marginalized group | 1 Pilot ToT using the resource with selected MAs and assess the training's impact using the Kirkpatrick Approach. | Milestone 1-4 are all achieved
Achieved
| ICM: Selected MAs' skills in humanitarian crisis preparedness and response have improved. ICM v2 :ICM collects information on the current state of MAs work for marginalized groups through the Biennial MA Survey, and uses the results to develop resources that can reduce and measure the change in stigma and discrimination against these groups. | Source
ICM data repository (Training results, pre-and post-test results, roll out of ToT statistics)
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Target (date) | Assumptions
Emergency transport is set up and improving access for pregnant women |  | Planned
| Emergency transport system is fully set up i.e. dispatch centres, network of accredited drivers, payment systems, community awareness raising etc. | Achieved
Source
Programme reporting
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Target (date)
Planned
| Women and babies are using the service including those from the most marginalised groups (adolescents, those living with disabilities, those in conflict settings) to be transported a) between facilities b) from home to a facility. | Achieved
Source
Programme reporting and data collection
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Target (date) | Target (date)
Planned
| Programme data collated and being used by government for planning and monitoring | Achieved
Source
Programme reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note on B67: ====== ID#AAABbup05gc tc={37F72F38-5343-4ADF-A986-B9990091F5E3} (2025-01-31 06:22:24) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All 3 MAs carry out the action plan?
Note on B70: ====== ID#AAABbup05g0 tc={5BD30149-B4F8-492E-B157-D17C38976F0B} (2025-01-31 06:22:24) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include the question on the biennial membership survey Reply: Focus on reducing stigma and discrimination
Note on B72: ====== ID#AAABbup05hY tc={0CF2EFC2-B39B-4588-8195-8F7EC448B04D} (2025-01-31 06:22:24) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need further discussion with the team

## Change frame Year 2
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Output 2, Indicator 2.1 | Milestone 2 (Year 2) - 4) Other MAs identified for MAAC -> Deleted Other MAs (besides Kenya, Malawi, and Pakistan) will not be selected for MAAC in Year 2. MAAC was piloted in Year 1 with Malawi and Pakistan, and key lessons were drawn from that experience: 1) Implementing MAAC required more time and resources from both ICM and the MAs than initially anticipated—particularly because it was used more as a capacity-strengthening tool rather than a decision-making tool to assess whether an MA is ready to receive and manage funds in an accountable and transparent manner. ICM is currently reflecting on how to adapt the MAAC approach to make its implementation more lean while maintaining its rigor; 2) Conducting MAAC without clear follow-up actions based on its outcomes (e.g. disbursement of funds) would offer limited value. As such, ICM will focus in Year 2 on the three current MAs—Pakistan, Malawi, and Kenya (with Kenya still in the process of rolling out MAAC)—to support the implementation of the action plans developed through the MAAC process. | Yeiwon Cho | 2025-09-09
2 | Output 2, Indicator 2.2 | Milestone 2 (Year 2) - 2 advocacy trainings completed -> 1 advocacy training (Malawi) completed 1 advocacy training (Malawi) will be completed in Year 2. Under ICM's Gates project, we are inviting several Member Associations (MAs) in East Africa—specifically from Kenya, Malawi, Uganda, and Ethiopia—to strengthen midwifery associations with advocacy skills and, through this, support targeted midwifery advocacy implementation at both national and regional levels. 2 focal persons from AMAMI in Malawi will participate in this regional workshop. Upon returning to Malawi, and with support from FCDO funding, they will roll out an advocacy training for AMAMI members and stakeholders, applying what they have learned at the regional workshop. Additionally, one advocacy training initially planned for MAP (Pakistan) will not take place, as it is not a current priority for the association, which already has strong advocacy capacity. Instead, they have chosen to focus their efforts on stakeholder meetings related to key midwifery issues. | Yeiwon Cho | 2025-09-09
3 | Output 2, Indicator 2.3 | Milestone 2 (Year 2) 3 Training of Trainers (ToTs) on ICM's humanitarian resources completed and ToT on working with and inclusion of marginalised groups -> 1) 1 Training of Trainers (ToTs) on ICM's humanitarian resources completed and ToT on working with and inclusion of marginalised groups The number of ToTs has been adjusted, as one was already completed in Year 1 in Kenya. Pakistan will conduct its ToT in Year 2. Malawi will have a soft introduction ToT during the Regional Advocacy Incubator meeting, with one day dedicated to ICM’s humanitarian resource workshop. A full in-person ToT for Malawi is planned for Year 3. | Yeiwon Cho | 2025-09-09
4 | New Global Indicator | Number of global standards/resources updated or created by ICM FCDO suggested that ICM include a global-level indicator in the logframe to capture some of its global work. ICM proposes to include the above-mentioned indicator, which can be supported by case stories demonstrating how ICM’s global standards, resources, or position papers have been used. | Yeiwon Cho | 2025-09-09
4 | New Global Indicator | Number of policy initiatives and/or legislative changes that support midwives to which ICM and/or MAs contributed (success stories and narratives) FCDO recommended that ICM include a global-level indicator in the logframe to better reflect its global contributions. In response, ICM proposes to adopt the above indicator, which will enable measuring the progress of long-term advocacy wins at the policy level. This indicator is one of ICMs outcome-level key performance indicators. Since this indicator was introduced toward the end of Year 2, ICM will align it with the Year 3 milestone. It will then be further refined during the development of the logframe for Years 4–6. | Yeiwon Cho | 2025-11-12
5 | Output 1, Indicator 1.1 | Milestone 1 adjusted from being completed in September 2025 to October 2025. Comment from GFW: Milestones tied to MMAP have been shifted slightly, with completion of the MMAP reports now expected by October 2025 (instead of September), in order to allow more time for grounded implementation in both countries. Subsequent milestones that build on MMAP remain unchanged since the MMAP timeline was only adjusted by 1 month. Across these changes, we’ve tried to preserve the ambition and integrity of the original indicators, while making sure the timeline better reflects how things are playing out on the ground. | Isla Marshall | 23/10/2025
6 | Output 1, Indicator 1.1 | Miestone 2 changed the wording to reflect the change in GFW's approach. Previous wording: One committee per country formed with structure, process and criteria for grantmaking, terms of reference agreed Rationale: the orignal project was anchored in Global Fund for Women’s Movement-Led Approach (MLA) which is a participatory grantmaking model that shifts decision-making power to grassroots feminist movements. MLA is inherently time-intensive. In discussion with FCOD, GFW agreed adapting the model might be wise in this context, particularly given the potential for a truncated project timeline and reduced funding. Even beyond these potential constraints, we wonder whether the MLA’s longer lead time—especially around establishing and operationalizing a Movement Committee—is the best fit for this project and its overall aims. | Isla Marshall | 23/10/2025
7 | Output 1, Indicator 1.1 | Milestone 3 - The wording was adjusted to reflect the change in approach. Previous wording: Based on committees' grantmaking processes, 10 - 20 grants provided by Movement committees in each country (total of 20-40 grants) with systems set up to track and report on progress | Isla Marshall | 23/10/2025
8 | Output 1, Indicator 1.1 | Target - As above, GFW have adjusted the target amount of marginalised groups down from 20-40 in the orignal log frame to 10-30. This is to make available sufficient budget for partners and the size of grant will determine the amount of grantees. | Isla Marshall | 23/10/2025
9 | Output 1, Indicator 1.2 | Baseline adjusted from being completed in September 2025 to October 2025. Use the same rationale as output indicator 1.1 | Isla Marshall | 23/10/2025
10 | Output 2, Indicator 1.2 | Milestone 1 - they brought forward the initial target of April 2027 to March to reflect adjusted timings with new approach | Isla Marshall | 23/10/2025
11 | Output 2, Indicator 1.2 | Milestone 2 - Adjusted the date from the orginal log frame: December 2027 2 workshops held and shared advocacy agenda between movement committee and grantees established | Isla Marshall | 23/10/2025
12 | Output 2, Indicator 1.2 | Milestone 3 and Target - As above, GFW have adjusted the target amount of marginalised groups down from 20-40 in the orignal log frame to 10-30. This is to make available sufficient budget for partners and the size of grant will determine the amount of grantees. | Isla Marshall | 23/10/2025
13 | Output 2, Indicator 1.3 | Milestone 2 - GFW added Milestone 3 (Year 2): Comotion and GFW disseminate findings from Country-mapping desk exercise through 1 webinar and through the IMNHC 2026 March conference Milestone 4 (Year 3): Country mapping and MMAP survey findings and learnings are disseminated at the Women Deliver conference in April 2026 | Isla Marshall | 23/10/2025

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Workplan draft (hidden)
Activities to be included
Follow up on Kigali workshop: contextualized data usage on GMH for Malawi and Kenya
1 monitoring plan and 1 data capturing tool co-developed
1 MA in-country monitoring visit completed
Section on working with marginalized groups included in biennial survey