## Annual Review Template

Title: Maternal and Newborn Health and Rights
Programme Value £ (full life): £5,830,000		Review date: 25 April 2026
Programme Code: 301476	AMP start date: 29/05/2024	AMP end date: 01/05/2034

Summary of Programme Performance
Year	2025	2026
Overall Output Score	A	B
Overall programme risk rating	Moderate	Moderate

DevTracker Link to Business Case:	D0006509.odt
DevTracker Link to results framework:	S30147619.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Maternal and Newborn Health and Rights (MNH) programme was approved in April 2024. Its primary objective is to reduce global maternal and newborn mortality by leveraging targeted funding to:

- Strengthen the capacity of local midwifery associations, recognising midwifery as a key driver for improved maternal and newborn outcomes.
- Empower women and girls, particularly those who are most marginalised, to claim their rights and hold governments accountable.
- Provide initial funding to expand successful innovations in emergency transport for pregnant women, adapting these solutions to new countries and contexts.

Given the increasing challenges to sexual and reproductive health and rights, it is essential to support national and local organisations and movements that are actively resisting and countering threats within their communities. By investing in innovative approaches, FCDO seeks to showcase a modernised development strategy. Through capturing lessons learned and demonstrating the effectiveness of these innovations, the programme aims to inspire others - including national governments and the broader global community - to scale up these successful models.

The MNH programme comprises of three distinct projects:

1. Grassroots Advocacy: Global Fund for Women (GFW)
GFW is working to build a ‘Birth Justice’ movement in Nigeria and Kenya, where the strongest grassroots efforts have been identified. With FCDO support, GFW provides funding and coordination to emerging movements, fostering a more unified and organised approach to address persistent social and cultural barriers in maternal and newborn health.

2. Strengthening Midwifery Associations: International Confederation of Midwives (ICM)
Through core funding to the ICM secretariat, this project aims to enhance the capacity of local midwifery associations, focusing now on Kenya and Malawi after the withdrawal from Pakistan. The goal is to strengthen the midwifery profession and encourage midwives to take on advocacy and leadership roles.

3. Emergency Maternal Transport: Vodafone Foundation
Core funding to the Vodafone Foundation supports the m-mama initiative, which helps governments establish national emergency transport systems for pregnant women. The m-mama service provides affordable emergency transport, connecting mothers and newborns to essential, life-saving healthcare. This was seed funding for a 6-month period and went live this year. To allow maximum flexibility given short funding duration, and considering political constraints, it was not restricted to specific locations, allowing for broader reach and impact.

Each project seeks to prioritise support for the most marginalised populations, including those affected by crisis, conflict, or climate change.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme is assessed as a B for this review period. In Year 2, delivery across the programme showed credible progress, but milestone achievement against agreed deadlines was mixed, with several Year 2 milestones not completed within the review period.
- Under Output 1 (grassroots advocacy and movement building - GFW), foundational activities progressed as planned. The implementation approach adopted in Year 2 remained materially consistent with the sequencing, adaptive management principles and movement-building methodology explicitly endorsed by FCDO in the 2025 Annual Review. However, delivery timelines under Output 1 were affected by substantial budget revision processes undertaken at FCDO’s guidance during the review period. This required significant adjustments to GFW’s annual spending projections and implementation planning. As a result of this, some milestones were not yet complete at the point of the annual review – but were on track to be completed by June.
- Output 2 (midwifery leadership, advocacy and inclusion - ICM) performed comparatively strongly, with most milestones achieved and some areas exceeding expectations, supporting confidence in longer-term outcome pathways.
- Performance under Output 3 (emergency referral and transport – m-mama) fell materially below expectations, as the system was not operational during the review period and key service level milestones were not met. While preparatory and enabling activities progressed which should stand the project in good stead should the Malawian Government decide to continue it, the absence of operational delivery means this output did not deliver its intended results this year.

Taken together, the overall B score reflects moderate under delivery against Year 2 milestones across more than one output, offset by strong progress in some areas. The score recognises that milestone delays that are largely due to sequencing, contextual constraints and in-year adaptations rather than systemic delivery failure.

Major lessons and recommendations for the year ahead [1/2 page]

Within the context of constrained resources, the Maternal and Newborn Health Programme should be taken forward for early programme closure in FY26/27. FCDO will discuss with Global Fund for Women how best to ensure responsible transition or exit within the course of the next year. FCDO to consider consolidating the component (output 2) on midwifery with the wider Grassroots programme to consolidate resources and maximise the available budget. This approach could also improve team resourcing and facilitate the sharing of lessons learned and best practice.

A key finding of the Birth Justice Country Mapping Insights Report produced by Global Fund for Women and Comotion in collaboration with movement actors was the disconnect between national strategies and community realities. Multiple interviewees noted that maternal health is still “owned” by health professionals and global development actors, not communities. National frameworks tend to focus on technocratic solutions such as service delivery or system reform rather than rights-based frameworks prioritising lived experience. As such these frameworks often fail to reflect lived realities such as obstetric violence, abortion stigma, GBV and health needs of refugees and other marginalised groups. This understanding should inform the set up and operationalisation of the new Centre of Expertise on Global Health, to ensure we take a rights-based approach to health-systems strengthening technical assistance.

Strengthening professional associations is a medium-term investment requiring sustained accompaniment, not just training. Evidence from Year 2 shows that combining diagnostics, mentoring and peer learning is more effective than standalone interventions, and that early flexibility improves uptake and ownership. These lessons have relevance beyond this programme, contributing to wider FCDO learning on locally led systems strengthening, professional advocacy and adaptive programme management in constrained policy environments

A key lesson for the Vodafone Foundation project is acknowledging the difficulty of standing-up a new public health initiative during an election year. FCDO acknowledged difficulty of this – hence the decision to provide core funding rather than concentrate solely on ‘go live’ in Malawi, because we thought it better to support vodafone’s wider operations. However, the log frame focused on delivery in Malawi – which was not possible this year. New FCDO Global Health Centre of Expertise technical assistance will need to be similarly cognisant of the potential for delays due to political changes and/or uncertainty into programme design and planning. Given the m-mama project will now be focussing on re-engagement with government at Ministerial and Presidential levels to Go Live in Malawi, it could be helpful for BHC Lilongwe to stay in touch with them, particularly on maternal health matters, and to support any further progress update for the Project Completion Report.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change (ToC), including any changes to outcome and impact indicators from the original business case. [1/2 page]

The Maternal and Newborn Health and Rights (MNH) programme’s Theory of Change remains unchanged from that approved in the Business Case and continues to be valid. The programme aims to contribute to reductions in maternal and newborn mortality by strengthening midwifery systems, grassroots advocacy and emergency referral mechanisms, with a particular focus on the most marginalised. The ToC assumes that investing in professional midwifery leadership, locally led advocacy and timely access to emergency care will lead to improved policy environments, better quality of care and increased utilisation of services by women and newborns.

Year 2 implementation broadly supports the ToC logic and assumptions. Evidence from partner reporting confirms that a phased, adaptive approach to capacity and movement strengthening is needed given varying baseline capacity and political contexts. There have been no changes to outcome or impact indicators since programme approval, and no new evidence that would challenge the programme’s core design or require a Business Case addendum, should the programme continue. Adaptations made during implementation have been at output level and are consistent with PrOF guidance on adaptive management.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme was on track to contribute to its intended outcomes, recognising that it remains at an early to mid-stage of implementation and that outcomes are expected to materialise over the medium term. Progress under the midwifery association output (ICM) demonstrates credible movement along the pathway from capacity strengthening to leadership and advocacy, with emerging evidence of improved governance, advocacy readiness and engagement with policy stakeholders. While measurable policy change is not yet expected, current progress aligns with outcome indicators and the programme’s sequencing assumptions.

Despite delays to achievement of milestones, the grassroots advocacy and movement building component is progressing as designed, with Year 2 appropriately focused on governance, landscape analysis and movement mapping rather than downstream outcomes. This aligns with the ToC assumption that sustainable advocacy and normative change require careful sequencing and local ownership.

Progress towards outcomes linked to emergency referral systems are currently constrained due to delayed implementation; preparatory work continues, affecting timing but not the validity of the causal pathway. However, FCDO funding for this component has now completed.

Across all components, delivery reflects Leave No One Behind priorities, including attention to adolescents, people with disabilities and humanitarian settings, with no evidence of adverse impacts on gender equality or protected characteristics.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Evidence from Year 2 indicates that the Theory of Change remains sound, outputs are being delivered in line with the approved design, and early outcome level progress is emerging as expected for this stage. However, FCDO resource constraints necessitate that the programme is brought forward for early programme closure over the course of the financial year 26/27. Component 2, on midwifery, shows the strongest promise, and offers unique value in the context of the wider portfolio, and so will be considered for consolidation within a larger Grassroots and Counter Rollback Programme. Any potential exit from the Global Fund for Women project will be most effective if it is done collaboratively with the partner to ensure it is responsible and opportunities for learning are maximised.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Grassroots MNH organisations identified, strengthened and given small grants for advocacy and movement building
Output number:		1	Output Score:	B
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 An increase in cohesion and reach of systems set up for grassroots MNH, including reaching the most marginalised women, babies and girls (adolescents, those living with disabilities, conflict settings etc)	Milestone 1 (Year 2): October 2025 / MMAP completed in 2 countries, anchor partners, policy priorities and diverse, intersectional partners identified	Milestone 1 (Year 2): / Completed in October 2025
	Milestone 2 (Year 3): / April 2026 / One movement advisory group per country formed with recommendations for criteria for grant making, clear articulation of in-country GM priorities which will form the basis of grant decisions, terms of reference, roles and responsibilities among advisory group, GFW, Comotion, and anchor partner agreed	On track for completion by April 2026. Advisory Groups are formed and will begin deliberation on process and criteria for grant making. Not assessed as part of Year 2 Annual Review.
1.2 An increase in grassroots MNH activities and a) activities that include marginalised groups b) activities that link with global advocacy efforts	Milestone 1 (Year 2): / March 2026 / 2 SMART workshops conducted with Movement Advisory Group and movement actors to define movement capacity needs and agree suitable advocacy approach.	Milestone 1 (Year 2): / Expected to complete by end of June
1.3 Lessons learnt documented for regional and global sharing	Milestone 2 (Year 2): / March 2026 / Project learning agenda developed and agreed in alignment with committee and grantee defined learning questions and advocacy approaches, underpinned by GFWs LEA principles	Milestone 2 (Year 2): / Expected to complete by end of June
	Milestone 3 (Year 2): Comotion and GFW disseminate findings from Country-mapping desk exercise through 1 webinar and through the IMNHC 2026 March conference	Milestone 3 (Year 2): / Completed, and side event for IMNHC delivered March 24th 2026.
	Milestone 4 (Year 3): Country mapping and MMAP survey findings and learnings are disseminated at the Women Deliver conference in April 2026	Milestone 4 (Year 3): / On track for completion. Not assessed as part of Year 2 Annual Review.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

During Year 2, the programme focused on establishing the foundations required to identify and strengthen grassroots MNH organisations through a participatory, movement-informed approach. Core activities included comprehensive country and movement mapping, engagement with grassroots actors and the establishment of governance mechanisms—including widely representative movement committees comprising grassroots actors to drive funding decisions in two countries—that place decision-making power closer to affected communities. The narrative evidence demonstrates strong foundational delivery aligned with programme design and approved sequencing assumptions.

A Movement Mapping Assessment Process (MMAP) was completed in Kenya and Nigeria, engaging 321 grassroots and civil society actors. This process identified active MNH and Birth Justice organisations, mapped relationships and gaps within the movement, and highlighted under-represented groups including adolescents, persons with disabilities, rural communities, sex workers and traditional birth attendants. The findings directly informed the formation of Movement Advisory Groups (MAGs) in each country, ensuring diverse representation and providing a mechanism for grassroots actors to shape priorities, eligibility criteria and advocacy approaches.

Anchor partners with strong participatory grant making capability – UHAI EASHRI in Kenya and ICEHD in Nigeria – were identified and contracted to support movement strengthening and downstream management. Orientation and onboarding processes for anchor partners and MAG members are underway to ensure shared understanding of safeguarding, conflict of interest, grant processes and advocacy objectives.

Grant disbursement was intentionally sequenced after governance, safeguarding, advisory structures, and movement mapping — consistent with the agreed movement-building model. While no small grants had been disbursed by the end of the reporting period, this reflects the intentional phasing of the programme rather than underperformance, consistent with the movement-led implementation model endorsed by FCDO in the 2025 Annual Review. The sequencing of governance, safeguarding, movement mapping, and participatory structures prior to disbursement was a deliberate risk-management and legitimacy-building measure. Delays in SMART workshops and finalisation of the learning agenda were linked to later-than-planned contracting and the need for deeper orientation with movement actors to ensure quality, legitimacy and safeguarding of the participatory process. These milestones are now expected to complete by June 2026, enabling the first round of grassroots grant making early in Year 3.

Overall, though some milestones were not yet complete at time of writing, the review team recognises that movement-building programmes require deliberate sequencing and relationship-building and that this is more important than punctuality alone. The logframe was amended in October to reflect feedback from GFW – it would be important to ensure it is regularly updated over this next year to ensure performance is adequately reflected. We are content that the programme’s emphasis on safe, inclusive and movement‑led delivery means that early investment in identification, governance and safeguarding was necessary and appropriate, even where this delayed grant disbursement in the short-term. Identification of grassroots organisations and systems strengthening are progressing well, and the programme is positioned to deliver grant making and advocacy outcomes in the next phase. The main challenge has been balancing movement-led approaches with time and funding constraints, which has been addressed through a shift to a movement-informed grant making model to reduce delays while maintaining grassroots leadership.

However, as part of the move to a smaller aid budget, we have had to make difficult decisions about our ODA programmes, and 26/27 is the last year that FCDO can provide funding to GFW for this work. FCDO will work with partners collaboratively to understand preferences for how best to use available spend in 26/27 to close out FCDO involvement. This may mean supporting GWF to continue this project as they seek funding support from other donors, or it may mean early close out. FCDO should update the logframe with key deliverables over the next year, once a plan has been mutually agreed.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The main change this year has been a shift from the previously agreed Movement-Led Approach (MLA) to a hybrid model due to the risk of a shortened timeline and reduced funding in response to FCDO ODA reductions and associated delivery uncertainty. This adaptation was undertaken proactively to accelerate feasible downstream delivery while preserving core movement-led principles and safeguarding standards. The hybrid approach has an informal advisory body rather than a formal movement committee which provides strategic input and feedback on grantee selection, drawing on movement mapping and partner expertise, but does not have final decision-making authority. This approach aims to channel funds more quickly downstream (the original MLA approach didn’t transfer grants until year 3 of the programme) and a major consideration was because of the financial risks of ODA cuts from FCDO (a risk that has now materialised). The log frame was adjusted in accordance with this.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Annual Review 2025 Recommendations	Progress
GFW and FCDO should continue to build a trusting and long-term relationship. This could include informal catch ups, in-person meetings and shared thinking about collaboration around global moments identified in the Communications Plan. GFW should share any learning from previous movement building work, such as Climate Justice, to ensure that the Birth Justice has enhanced decision-making and innovative solutions to challenges. This will maximise the chances of building a strong, sustainable and authentic movement.	Regular and open dialogue between FCDO, GFW and Comotion has continued throughout the year, including informal finance and programme catch‑ups alongside quarterly governance meetings. / Transparency around ODA reductions and budget uncertainty enabled early joint planning, including re‑forecasting and scenario discussions to minimise downstream risk. / In-person engagement with Comotion around IMNHC 2026 supported shared strategic thinking on how to position Birth Justice learning within global MNH policy spaces.
FCDO should consider innovative ways to mitigate potential financial risk to GFW. This could include seeking opportunities to bring funds forward during the next financial year, to ensure financial stability and safeguard against potential cuts in outer years.	GFW conducted a budget refresh (Aug–Oct 2025), reflecting the change in approach and mitigating against financial risk – e.g. Q1 financial report there was a predicted £650k underspend against the budget allocation (£1,132,801). GFW moving away from the MLA helped to ensure that available budget was optimised. / Mid-to-long term scenario planning is underway to manage funding cuts.
Building movements and coordinating grassroots advocacy is a new area for the UK particularly on maternal and newborn health. We should continue to be flexible and responsive to GFW’s recommendations and asks of us as a donor. For example, focusing on a slow set up is a change to other programmes in which FCDO would aim to ensure onward granting to grassroots actors as quickly as possible. However, GFW advocate that this is needed in order to create long-term, sustainable and impactful movements.	FCDO and GFW engaged in ongoing consultation and reflection on the appropriate pace and model for movement‑building within MNH, recognising this as a newer area of UK programming. / Agreement was reached to prioritise deliberate sequencing, including extended setup, mapping and governance formation, before grant disbursement. / The decision to move away from a full MLA followed joint assessment of delivery risks, timelines and safeguarding considerations, demonstrating flexibility and responsiveness to GFW’s technical advice.

Suggestions for Annual Review 2026 Recommendations:

A key finding of the Birth Justice Country Mapping Insights Report was the disconnect between national strategies and community realities. Multiple interviewees noted that maternal health is still “owned” by health professionals and global development actors, not communities. National frameworks tend to focus on technocratic solutions such as service delivery or system reform rather than rights-based frameworks prioritising lived experience. As such these frameworks often fail to reflect lived realities such as obstetric violence, abortion stigma, GBV and health needs of refugees and other marginalised groups. This understanding should inform the set up and operationalisation of the new Centre of Expertise on Global Health, to ensure we take a rights-based approach to health-systems strengthening technical assistance.

There is wider opportunity for learning and reflection about how best to support and build rights-based movements on maternal and newborn health. Our assumption was that policy and advocacy space around maternal and newborn health tended to be technical. In contrast, rights-based advocacy on SRHR focused instead predominantly on issues such as family planning, abortion and CSE. One concern was that the birth justice actors identified through this programme again identified abortion and GBV as advocacy priorities, rather than respectful, quality maternal care (though this could have come into a wider definition of GBV), and/or miscarriage and baby loss. It is unclear at this early stage why this might be the case, and whether there exists a grassroots movement around wider ‘birth justice’ as we might understand it. It is possible that this sort of programming is better led by teams closer to specific country contexts, rather than at the centre, as those advisers might be better placed to identify and understand nascent movements.

Output Title	ICM strengthens the operations of national midwives associations (MAs) to better advocate, lead and operate with the most marginalised groups to improve midwifery practice and promote the profession.
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	Yes – down from 50% due to inclusion of Output 3 this year

Indicator(s)	Milestone(s) for this review	Progress
2.1 Member Associations (MA) systems, functions, plans and capacity strengthened to enable advocacy and leadership.	1) 1 Member Association Assessment Checklists (MAACs) to identify areas for strengthening completed and review reports written / 2) 1 capacity strengthening action plans developed / 3) Capacity strengthening action plans begin implementation with evidence of changes to functions, plans and capacity	1) 1 MAAC completed and MAAC Report with findings and recommendations drafted. / 2) 2 capacity strengthening action plans developed. / 3) MAs began implementing their capacity strengthening action plans with evidence of changes to functions, plans and capacity.
2.2 Midwifery associations leading and advocating for improved midwifery practice and to promoting the profession.	1) 1 advocacy training (Malawi) completed / 2) Advocacy activities started by 3 MAs	1) 1 advocacy training completed. / 2) Advocacy activities started by 2 MAs.
2.3 MAs supported and strengthened to work in humanitarian crises and to reach and include marginalised groups such as adolescents and those living with disabilities.	1) 1 Training of Trainers (ToT) on ICM's humanitarian resources completed and ToT on working with and inclusion of marginalised groups / 2) ICM's Biennial Membership Survey 2025 updated with a section on working with marginalized groups and reported on	1) 1 Training of Trainers (ToT) on ICM's humanitarian resources ToT on working with and inclusion of marginalised groups completed in Year 1 and 1 ToT planned for Year 3. / 2) ICM's Biennial Membership Survey 2025 updated with a section on working with marginalised groups and reported on.
2.4 ICM contributes to policy initiatives, reforms, or legislative changes at national, regional, or global levels that have a positive impact on the midwifery profession. Contributions may include technical support, advocacy, partnership, capacity building, or provision of evidence and resources. This is to capture and demonstrate ICM’s influence in shaping supportive environments for midwives through policy and legislation.	This indicator was added in Year 2; it will be measured for the first time in Year 3.	Not applicable for Year 2.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

During Year 2, the ICM output focused on consolidating and operationalising the foundations established in Year 1, responding directly to previous Annual Review learning that early investment should prioritise Member Association (MA) readiness, governance and advocacy capability before scaling delivery. Core activities included completion and rollout of the Member Association Assessment Checklist, development of MA capacity strengthening action plans, delivery of targeted advocacy skills training, and continued investment in humanitarian and equity focused midwifery resources. These activities directly support the output indicators on strengthened MA systems, leadership and advocacy engagement, as set out in the logframe and Theory of Change.

Overall, the output is on track to achieve its end of programme objectives. Progress against Year 2 milestones demonstrates that MAs in Malawi and Kenya are increasingly able to engage in national policy dialogue, convene stakeholders and articulate priorities. Advocacy training and needs assessments have moved beyond diagnostic stages into application, with early examples of MAs independently convening policy actors and refining advocacy strategies. This reflects a shift, anticipated in the 2025 Annual Review, from capacity assessment to active leadership and influence, while remaining realistic about the time required for advocacy investments to yield measurable policy change.

However, progress has been uneven across contexts, reflecting differing starting capacities and political environments. Pakistan has advanced more rapidly in advocacy, requiring adaptation of Secretariat support, however, face different challenges in governance that affect their ability to receive funding. Malawi and Kenya remain at earlier stages of translating skills into sustained policy engagement. These differences do not indicate underperformance, but they underline the continued relevance of last year’s lesson that MA strengthening must remain flexible, sequenced and tailored. Continued attention will be required in Year 3 to ensure that capacity gains translate into durable institutional influence rather than one‑off engagement.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

In line with the 2025 Annual Review recommendation to maintain an adaptive approach, no changes were made to the output’s objectives or core indicators during Year 2. However, delivery was adjusted to reflect learning on differential MA capacity. Following in-depth discussion and concerns around governance structures for the MA in Pakistan, ICM made the difficult decision not to proceed with providing additional direct funding to that MA at this point.

Planned changes following this review include clearer articulation of interim advocacy milestones and improved capture of ICM’s global advocacy contributions within the logframe (supported by some additional spend, repurposed from elsewhere in the programme), as recommended in the previous AR. Any agreed adjustments will be formally recorded in the change frame of the logframe, in accordance with FCDO guidance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The programme has made strong progress against the specific recommendations set out in the 2025 Annual Review. In response to recommendations on governance, safeguarding and risk management, ICM has implemented the Member Association Assessment Checklist, strengthened MA risk registers, identified risk leads, and made safeguarding reporting mechanisms more accessible. These actions directly address prior concerns around fiduciary assurance and accountability. In response to the recommendation to better reflect ICM’s global role, Year 2 reporting more clearly evidences how global advocacy initiatives, such as the PUSH 2.0 campaign and technical engagement in global policy processes, reinforce and amplify country level MA work, although further refinement of indicators is still required.

Key lessons this year reinforce last year’s findings that strengthening professional associations is a medium-term investment requiring sustained accompaniment, not just training. Evidence from Year 2 shows that combining diagnostics, mentoring and peer learning is more effective than standalone interventions, and that early flexibility improves uptake and ownership. These lessons have relevance beyond this programme, contributing to wider FCDO learning on locally led systems strengthening, professional advocacy and adaptive programme management in constrained policy environments. Learning priorities for the coming year include better tracking of advocacy contribution pathways, clearer documentation of policy influence over time, and formal integration of ICM’s global advocacy outputs into programme level results reporting.

Output Title	Emergency transport is set up and improving access for pregnant women
Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes – up from 0%. This output was not measured last year due to delays in starting.

Indicator(s)	Milestone(s) for this review	Progress
3.1 Maternal and newborn emergencies are transported, and are reaching in a timely and cost-effective manner to an appropriate health facility and are followed up to track outcomes	1 m-mama dispatch centre in operation	0 - Dispatch Centre is set up and integrated for m-mama, however, Emergency Referral and Transport System (EmRTS) not yet live (Malawi – due to a changed political context)
	15 dispatchers who have / been trained and are actively working in m-mama dispatch centres.	18 dispatchers have been trained however EmRTS not yet live (Malawi)
	9 districts where 117 has / been zero-rated and connected to m-mama dispatch centre.	0 - Toll free line is not yet operational and EmRTS not yet live (Malawi)
	150 community drivers / with active MOUs to provide / transport who have been trained on m-mama.	924 drivers are pending final training and signature of MoU due to delays caused by ongoing political issues (Malawi)
3.2 Quality maternal and neonatal health services are provided in health facilities by the Government of Malawi	15 CEmONC-designated / health facilities in Central / Region assessed by m-mama team during clinical assessment process	26 Clinical Assessment completed across all Central region selected facilities
3.3 The Government of Malawi budgets for, manages, and operates the m-mama emergency referral and transport system	9 districts where an EmRTS Focal Person has been appointed and trained on m-mama by end of January 2026	9 District EmRTS Focal People officially appointed
	100% of health facilities in / Central Region where, by end of January 2026, at least one staff member has been oriented to the availability, purpose, and method of activating m-mama (via toll-free number)	100% - All health facilities within Central region have been oriented on m-mama – average of 3 staff members per facility
	90% of GoM / representatives in attendance at monthly operational M&E meetings (EmRTS Focal People / from 9 of out 9 districts in / Central Region participate)	0% - Agreed with districts to conduct bi-monthly M&E meetings once EmRTS will be live
3.4 Public is aware of the system, is using it, and is satisfied with its services	Information, education, and communication plan developed to engage public throughout districts in Central Region	Completed - Strategy has been developed – however, new government expressed conflicting views on community to facility referrals – additional political buy-in is required

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

During Year 2, this output focused on establishing the technical, institutional and governance foundations required to operationalise the m-mama Emergency Referral and Transport System (EmRTS) in Malawi, alongside continued national scale delivery in Tanzania through non-FCDO funding. The move to Malawi was a change from an initial proposal which focused on operation set-up in Kenya, because political support for the project in Kenya had become untenable. Whilst activities focussed on Malawi, FCDO funding could be used as core-funding to m-mama project overall, given the constraints on funding availability. Activities during the reporting period prioritised system readiness, government ownership and sustainability rather than full operational delivery. FCDO funding for the Vodafone Foundation partnership was operational for 6 months only and concluded at the end of Year 2 (31 March 2026).

In Malawi, substantial preparatory progress was achieved prior to the end of FCDO funding. A national dispatch centre was established within existing government infrastructure, a toll-free emergency number was allocated, and 18 dispatchers were recruited and trained, exceeding annual targets. Baseline clinical and facility level assessments were completed across 26 health facilities in the Central Region, and governance arrangements were formalised through the establishment of a National Steering Committee and appointment of EmRTS Focal People in all nine Central Region districts. Community engagement and facility orientation activities reached 100% of targeted facilities, and 924 eligible community drivers were identified, significantly exceeding planned targets, although final training and contracting were not completed by the end of the funding period.

Despite this progress, the system was not operational during Year 2, and no emergency transports were delivered under FCDO funding in Malawi. Planned milestones relating to dispatch centre operation, toll‑free line activation, community driver contracting and routine M&E meetings were not achieved within the review period. Delays were driven primarily by political transition and changes in senior leadership within the Ministry of Health, which slowed approval of critical legal and operational processes and were largely outside the control of the delivery partner.

Overall, the output is assessed as partially off track for the review period. While enabling milestones were delivered to a high standard and provide a strong foundation for future operation, the absence of live service delivery before the end of FCDO funding represents a material shortfall against Year 2 expectations. The score reflects both the scale of preparatory achievement and the clear limitations imposed by political and timing constraints, with delivery risk at the point of exit concentrated on the transition from readiness to operation under government leadership and alternative funding.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes were made to the output’s objectives, indicators or end of programme targets during Year 2. However, delivery was adjusted in response to contextual constraints, with greater emphasis placed on governance, system readiness and district level preparation while awaiting high-level approvals required for Go Live. As FCDO funding for Vodafone Foundation concluded on 31 March 2026, no further delivery is planned under this output within the MNH programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress was made against relevant recommendations and risks identified in the previous Annual Review, particularly in relation to government ownership, sustainability and diversification of funding. Consistent with the original design, FCDO funding supported timebound system setup, while the Government of Malawi committed to assuming recurrent costs and long-term operation. The year also saw continued diversification of m-mama’s funding base beyond FCDO, reducing reliance on a single donor and strengthening resilience against fiscal uncertainty. Safeguarding recommendations from due diligence were progressed, including updated safeguarding policies, refresher training and the introduction of an in-app beneficiary feedback mechanism.

A key lesson from Year 2 is that political economy risks are the primary determinant of delivery timelines for nationally embedded system reforms, even where technical readiness is high. The experience in Malawi underlines the importance of sustained high level political engagement alongside district level ownership to avoid bottlenecks at central approval stages. The year also demonstrated the value of continued investment in readiness activities during periods of delay, ensuring that once approvals are secured the system can move rapidly to operational delivery rather than restarting preparatory work.

New FCDO Global Health Centre of Expertise technical assistance will need to be similarly cognisant of the potential for delays due to political changes and/or uncertainty into programme design and planning.

As m-mama/Vodafone Foundation will be focusing on re-engagement with government at Ministerial and Presidential levels in order to Go Live in Malawi, it could be helpful for BHC Lilongwe to stay in touch with them, particularly on maternal health matters, and to support any further progress update for the Project Completion Report.
## D: VALUE FOR MONEY (1 page)

The MNH Programme business case set out a Value for Money (VfM) proposition based on FCDO’s principles of economy, efficiency, effectiveness, equity and cost-effectiveness. Overall, the business case assessed the programme as representing value for money for the UK taxpayer. This review updates that assessment using evidence from Year 2 partner reporting and annexes.

The programme continues to operate with a relatively small budget compared to other FCDO investments with a deliberate focus on strengthening systems, institutions and movements rather than financing large‑scale service delivery. Partner reporting demonstrates that this approach remains appropriate in the current context of constrained global health financing, ongoing attacks on SRHR and persistently high maternal and newborn mortality rates. Evidence from Year 2 suggests that relatively limited resources are being deployed in ways that are likely to contribute to sustainable, longer‑term change, however, given wider resource constraints, we have had to take the difficult decision for early programme closure – though we will seek to consolidate work with ICM as part of other programmes, and ensure responsible exit from our investment with GFW.

Economy

Overall, the programme demonstrates a reasonable cost base relative to its scope and ambition, with partners actively managing resources and aligning expenditure with delivery priorities. Across the programme, the main cost drivers relate to targeted grants, partner staffing and the administration required to manage these responsibly. Year 2 reporting shows that partners have taken steps to manage costs proactively in response to delivery realities and funding uncertainty. For example, Global Fund for Women undertook a consortium‑wide re‑budgeting and re‑forecasting exercise to realign resources towards in‑country anchor partners and downstream grant making, ensuring that funding is focused on priority activities. Similarly, the International Confederation of Midwives (ICM) used a mix of partial core funding and targeted country‑level funding to support capacity strengthening and oversight functions that would be difficult to deliver efficiently through project‑by‑project funding alone. Overall, examples such as these suggest inputs are being procured and deployed at a cost that is proportionate to the programme’s objectives and risk.

Efficiency

The programme’s design continues to prioritise efficiency through leverage and coordination, rather than scale of spend. Evidence from Year 2 indicates that relatively modest investments are being used to engage and strengthen actors with national, regional and, in some cases, global reach. Across partners, efficiency is achieved by working through existing networks, institutions and delivery models rather than creating parallel structures. For example, ICM’s support to national Midwives’ Associations builds on extensive membership networks, enabling engagement in national policy and advocacy processes without the need for large delivery teams or infrastructure. This evidence suggests that resources are being converted into outputs in a way that maximises reach and influence relative to cost.

Effectiveness

Year 2 reporting indicates that the programme continues to take a phased and deliberate approach to implementation, with a strong focus on laying the foundations for effective delivery rather than accelerating disbursement. This is appropriate given the programme’s theory of change and ambition to deliver durable change. Partners report progress in establishing systems, governance arrangements and capacity necessary for future results. For example, both Global Fund for Women have focused on strengthening partner capacity, risk management and oversight mechanisms intended to support effective delivery over the remainder of the programme. While many outcomes are expected in later years, Year 2 evidence suggests that the programme is on a credible trajectory towards achieving its intended results.

Equity

Equity remains a strength of the programme’s VfM. Across partners, reporting demonstrates a consistent focus on reaching groups who face structural barriers to accessing maternal and newborn health services. Evidence shows that equity considerations are being embedded in programme design rather than treated as an add-on. Global Fund for Women has used movement mapping and related tools to identify representation gaps and ensure funding and advocacy are informed by the needs of marginalised groups, including adolescents, people with disabilities, those in humanitarian settings and those affected by climate change. ICM reporting similarly highlights targeted work to assess and strengthen engagement with marginalised populations, including through situational analyses, advocacy strategies and humanitarian preparedness activities.

Cost‑effectiveness

The programme’s cost‑effectiveness continues to rest on its potential to generate benefits that extend beyond the life of the programme. The latest reporting indicates that investments are primarily focused on strengthening institutions, movements and systems, which are expected to continue delivering benefits without sustained high levels of donor funding.

Based on the above assessment against the 5 Es, there remains sufficient evidence that the programme continues to represent value for money. However, it will be of vital importance to ensure that over the next year FCDO and partners work together to ensure that funds are best deployed to generate benefits that extend beyond the life of the programme, given that this is the last year in which we can offer funding to GFW.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The programme risk register has been kept up to date, and key risks have been reviewed at each quarter. An updated risk register can be found below in Annex A. Headline risks for each category are as follows:

Strategy and Context: The global operating environment for sexual and reproductive health and rights (SRHR) continues to deteriorate, with increasing political and ideological opposition constraining advocacy space and, in some contexts, affecting service delivery and policy engagement. Partner reports indicate that these pressures are already being felt, particularly around politically sensitive issues such as safe abortion, bodily autonomy, and the rights of marginalised groups (particularly relating to the expansion of the Global Gag Rule). Political transitions at country level have further reinforced delivery uncertainty, with shifts in leadership slowing decision￼making and affecting the pace of implementation. To mitigate these risks, the SRO and PRO have worked closely with teams at post (particularly in Malawi with Vodafone foundation, and in Nigeria with GFW) to ensure join up. The programme maintains regular engagement with implementing and advocacy partners to understand emerging constraints, adapt approaches where required, and ensure SRHR and maternal and newborn health (MNH) perspectives are amplified during key global moments, including at the International Conference on Maternal, Newborn and Child Health.

Reputational: Ongoing fiscal uncertainty, combined with a volatile political and donor landscape, continues to present reputational risk for FCDO and programme partners. Reductions or delays in ODA, alongside delivery disruption caused by political transitions, risk undermining programme credibility if not proactively managed. There is also a reputational risk where ambitious milestones are affected by factors outside partners’ control, such as delayed government endorsement or changes in national priorities. To mitigate this, the SRO and PRO have maintained close oversight of delivery feasibility, feeding into internal commissioning processes, and ensuring a joined￼up approach with related programmes. Clear and early communication with partners on funding changes, delivery risks and adjustments remains a priority.

Policy and Programme Delivery: Programme delivery risks in 2026 centre on sequencing, coordination and the enabling role of political buy‑in. Partner reports highlight that while technical capacity and implementation readiness are strong, delivery timelines can be affected by political transitions, limited government engagement, or the scale and ambition of multi‑partner advocacy models. There is also a risk that large volumes of programme‑generated data are under‑utilised, limiting learning and advocacy impact. These risks are being mitigated through adaptive programme management, including re‑phasing activities, clarifying roles and responsibilities across consortia, strengthening data systems and analysis, and reinforcing links between local, national and global advocacy. Regular engagement with partners enables early identification of delivery pressures, ensuring expectations remain realistic and that activities continue to align with programme objectives and available resources.

People: Following turnover during 2025 and early 2026 and pausing of recruitment due to the FCDO restructure, sustained delivery with a lean team continues to carry a risk to programme management quality and timeliness. To mitigate this, leadership has surged temporary cover where required, including getting support from the Project Delivery Support Unit (PDSU), and redistributed team members across the departments programme portfolio, protected time for core contract and performance management, and sequenced workload around known peaks with clear expectations for partners. Leadership has also started to identify key priorities and what can be paused or consolidated within the wider programme portfolio whilst workloads greatly exceed the resource available. The SRO and PRO have maintained regular cadence on reporting and risk review. This maintains continuity of oversight while recruitment and restructure plans progress.

Safeguarding: Safeguarding remains a key programme risk, particularly given the focus on reaching marginalised and vulnerable populations, including adolescents, displaced communities and persons with disabilities. Partner evidence highlights systemic barriers to safe, inclusive access to care, including gaps in disability inclusive practice and safeguarding capacity at local level. While no systemic safeguarding failures have been identified, these risks require ongoing vigilance. Mitigation measures include regular safeguarding dialogue with partners, robust due diligence, routine follow‑up on any incidents or concerns and encouraging partners to allocate adequate budget and capacity for safeguarding prevention and response. Disability inclusion is increasingly treated as both a safeguarding and quality‑of‑care consideration, with partners supported to strengthen inclusive policies, training and monitoring.

Financial and Fiduciary: Financial and fiduciary risk remains moderate and is closely linked to delivery timing rather than weaknesses in partner financial systems. Political delays and phased roll￼out approaches create a risk of underspend or re￼profiling, while downstream delivery models require continued oversight to mitigate risks of mismanagement or fraud. These risks are mitigated through proportionate due diligence, quarterly financial reviews, monthly burn rate monitoring where appropriate, and active reforecasting to prioritise high impact activities. Where delays occur, budgets are adjusted transparently and with senior approval to maintain value for money and minimise disruption to partners. All partners are required to follow FCDO counter fraud procedures, with clear escalation routes in place should concerns arise.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Overall, partner performance during the reporting period provides appropriate assurance on financial management, commercial compliance and fiduciary oversight, alongside delivery progress. Partners have engaged constructively with FCDO, provided timely reporting and taken steps to manage financial and operational risks in a challenging and uncertain funding environment.

GFW demonstrated sound financial management and constructive engagement with FCDO commercial and assurance processes during Year 2. Financial and narrative reporting has been submitted in line with agreed templates and deadlines, providing sufficient visibility of expenditure, utilisation and emerging risks. In response to funding uncertainty beyond March 2027, GFW led a consortium wide re‑budgeting and re‑forecasting exercise to realign resources with programme priorities and strengthen financial resilience. They continued to meet due diligence requirements, maintaining a consortium‑level risk register and reporting quarterly on financial and fiduciary risks. Updates against FCDO Due Diligence Assessment (DDA) recommendations are clearly documented, including compliance with IATI reporting requirements and agreed arrangements for tracking and reporting on FCDO‑funded assets.

ICM also continues to demonstrate strong commercial and financial performance, supported by clear systems and robust oversight arrangements. Reporting has been submitted on time alongside clear tracking of expenditure against agreed budgets. Financial oversight is strengthened through regular monitoring at both confederation and national association level, including review of financial statements, audits, expenditure records and asset inventories. ICM has responded positively to FCDO due diligence requirements, implementing a Due Diligence Assessment recommendations tracker that provides transparent oversight of actions and progress. Capacity strengthening support has included recruitment of dedicated finance staff within national associations and improvements to financial systems and procedures, enhancing accountability and reporting quality. The structured close-out of the Pakistan component further demonstrates ICM’s willingness to take timely action to manage financial and reputational risk where delivery assurance cannot be maintained.

Vodafone Foundation/m-mama reporting provides a lighter but proportionate level of financial detail, reflecting the nature of the partnership and delivery model. Reporting submitted during the period offers sufficient visibility of expenditure, delivery progress and budget position to support FCDO oversight. Vodafone has engaged openly with FCDO on commercial and financial matters, including adapting budget profiles and delivery timelines in response to operational delays. These adjustments have helped mitigate the risk of underspend and support effective financial planning. A robust due diligence assessment is in place, providing assurance regarding governance, financial controls and accountability arrangements.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation during the review period was undertaken primarily through structured narrative and financial reporting from all three delivery partners, supported by detailed technical annexes, assessments and analytical products. ICM monitoring focused on progress against agreed milestones for Member Association (MA) capacity strengthening, advocacy development and inclusion, using tools such as the Member Association Assessment Checklist, advocacy needs assessments, biannual surveys and thematic reports, which informed ongoing engagement between ICM and supported associations. GFW monitoring reflected the programme’s early and intentionally phased stage, focusing on programme setup, governance, movement landscaping and preparatory stakeholder engagement, with evidence used to refine sequencing and design rather than assess downstream outcomes. Vodafone Foundation monitoring remained more light touch due to the paused status of implementation, but reporting provided updates on preparatory work, contextual developments and readiness activities. There is no external M&E supplier engaged; monitoring and learning are embedded within partner delivery models, with FCDO oversight provided through review of Year 2 submissions and annexes as part of the Annual Review process.

Evidence for the programme strengthened over the year, particularly through qualitative and diagnostic products, reflecting the current programme phase. ICM generated multiple assessments and surveys evidencing MA governance, advocacy confidence and engagement with marginalised groups, while GFW reporting documented emerging evidence on grassroots advocacy ecosystems and movement dynamics. Across partners, monitoring data and evidence increasingly reflect Leave No One Behind considerations, including adolescents, people with disabilities, humanitarian settings and climate vulnerability, informed by vulnerability assessments and adolescent pregnancy mapping. Quantitative disaggregation by age, sex, disability or geography remains limited at this stage, which is appropriate given the focus on systems and movement strengthening rather than service delivery.

Learning has been captured through partner discussions, documentation of lessons within reports and annexes, and use of monitoring findings to adjust delivery approaches. Key learning from Year 2 highlights the importance of phased and context-specific capacity strengthening, the effectiveness of combining diagnostics with mentoring and peer learning, and the value of grounding advocacy in locally generated evidence. These lessons are relevant both for this programme and for wider FCDO work on locally led systems strengthening and grassroots advocacy.

Date of last narrative financial report	16/03/2026	Date of last audited annual statement	N/A

Annex A: Risk Register

Risk Description	Risk Category	Gross Risk	Mitigation Strategy	Residual Risk
The UK Government has made the decision to reduce Overseas Development Assistance (ODA) from 0.5% to 0.3% of GNI. This has the potential to impact the 3 projects within this programme in future years.	Reputational	Severe	FCDO SRO and PRO will feed into commissions internally and ensure a joined-up approach with other WROs programmes. We will consider the impact of stopping funding to partners and communicate updates to programme partners early to allow maximum time for planning.	Severe
Growing global opposition to Sexual and Reproductive Health and Rights (SRHR), including increased politicisation of multilateral fora. The risk is that the operating environment for SRHR becomes more constrained, limiting partners’ ability to deliver services and advocate effectively. This can lead to reduced access to SRHR services for women and girls, and weakened UN capacity to speak out on key issues such as safe abortion.	Strategy & Context	Severe	Implement a coordinated FCDO-wide approach to counter rollback of SRHR at bilateral, multilateral and country levels. Engage proactively with delivery and advocacy partners to assess impact and adapt programming accordingly. Ensure strategic planning for key multilateral events (e.g. CSW, CPD) includes SRHR and maternal and newborn health (MNH) partners to amplify messaging and influence outcomes.	Severe
If the programme team continues to operate with limited capacity, there is a risk that programme management will fall below expected standards, which could lead to delays, reduced quality of delivery, and reputational damage to FCDO.	People	Moderate	Ensure time is built into programme team’s capacity for ongoing programme management. Consider the programme for early closure/consolidation with the Grassroots and Counter Rollback programme.	Moderate
Weak safeguarding systems or cultures within one or more implementing partners, could mean a safeguarding incident occurs (e.g. SEAH, bullying, harassment), affecting staff or beneficiaries. This could lead to harm to individuals, reputational damage to FCDO, and disruption to programme delivery.	Safeguarding	Major	Maintain regular dialogue with partners, including leadership, to assess and strengthen safeguarding culture and systems. Ensure all partners have robust safeguarding policies and due diligence processes, with particular attention to protecting marginalised groups. Monitor safeguarding and fraud cases through routine follow-up and reporting mechanisms. Encourage partners to allocate budget for safeguarding, including capacity building for prevention and response.	Moderate
One or more implementing partners (including downstream partners) affected by financial mismanagement or fiduciary incident, including fraud.	Financial & Fiduciary	Major	Ensure that partners have the corrects due diligence process in place and, if necessary, external audit provisions are made. Where downstream partners do not have sufficient accounting systems, GFW will work with them to build capacity. FCDO programme team will review quarterly. If fraud occurs, FCDO will follow our own counter-fraud and bribery guidance, ensuring the partner is communicating regularly with FCDO, conducting a robust investigation and taking further action if required. Consistent with PrOF Rule 19, any suspicion or allegation that FCDO funds or FCDO funded work is being exposed to fraud, bribery, corruption or theft should be reported immediately to the IAID Fraud Investigations Team.	Moderate
Large amount of data generated on facilities, transport, outcomes is not collated which can impact results and high-level outcomes of the programme - this one can be closed as funding is not continued beyond 31/3/26	Policy & Programme Delivery	Moderate	Ensure that Vodafone has systems in place to collect and analyse this data or is able to help the government in selected operating environment.	Moderate
The Birth Justice focus areas (e.g., maternal health and abortion access in Nigeria; GBV and adolescent SRHR in Kenya) are not clearly defined and may overlap with existing FCDO-funded initiatives. The focus areas evolve into activities that duplicate current funding streams rather than addressing distinct MNH bottlenecks. This could lead to inefficient use of resources, reduced impact of FCDO investments, and missed opportunities to tackle priority MNH challenges.	Policy & Programme Delivery	Major	FCDO programme team will clarify GFW Focus Areas Early, for example by requesting detailed definitions and scope of each focus area from GFW once available or has part of the written report. If necessary, coordinate with the grassroots programme through internal meetings to identify any areas of duplication. Work closely with teams at Post to ensure alignment with post priorities and understanding of context.	Minor
Budget allocations are set for the next three years, and there is no guarantee that any underutilised budget will return to the programme in future years. Inaccurate forecasting and budgets may cause the programme to experience financial underspend and underutilisation of allocated budget. This could lead to reduced delivery of planned activities, reputational risk for FCDO, and potential impact on maternal and newborn health outcomes.	Financial & Fiduciary	Moderate	To reduce the risk of financial underspend and underutilised budget, the FCDO programme will implement monthly financial reviews and reprofile budgets to prioritise high-impact activities. We have reallocated money between projects this year to minimise risk of underspend before the end of the financial year. We sought senior level approval and have finalised paperwork (Accountable Grant Amendment) to put this in place.	Minor
Programme partners are working in isolation despite having complementary projects which contribute to reducing maternal and newborn mortality (grassroots advocacy, emergency transport, and strengthening midwifery) and all collect valuable data and knowledge. Opportunities to link partners and share learning may be missed, resulting in limited collaboration and reduced synergy across interventions. This could lead to duplication of effort, weaker advocacy impact, less efficient use of resources, and missed opportunities to improve maternal and newborn health outcomes.	Policy & Programme Delivery	Major	To ensure that these projects have the maximum impact, FCDO will ensure a link up to global work happening in the space, if either partner is not already aware. Core funding can also go to ICM's global work to compliment this. Both partners have demonstrated during the inception of the programme they are involved in or attending key SRHR events, such as CPD and CSW. To address the risk of missed collaboration opportunities, the programme should look to establish semi-regular coordination meetings and a shared communication platform for partners. These actions will be monitored to ensure timely implementation and improved synergy across interventions.	Minor
The new agreement with Vodafone is limited to the current financial year, with ambitious milestones set in the logframe. Vodafone may struggle to deliver against agreed milestones within the short timeframe. Risk to programme delivery and achievement of intended outcomes, with potential reputational impact for FCDO if targets are missed.	Policy & Programme Delivery	Major	Shift to core funding enables Vodafone to access and deploy resources more flexibly and rapidly, without location-specific constraints. Maintain regular engagement with Vodafone to monitor progress and identify delivery risks early. Review logframe milestones to assess feasibility and adjust expectations where necessary, ensuring alignment with available time and capacity.	Minor