llBusiness Case – Portfolio Risk Assurance Programme (PRAP III)

Summary Sheet

Country Plan Summary: / [A more inclusive, prosperous and stable Pakistan, less reliant on external finance, more resilient to shocks, contributing to regional stability, while becoming a diminishing source of threats (criminal and security) to the UK, and supporting the UK’s global geopolitical interests. This is delivered through six campaign goals: / Regional Stability: A more internationally engaged, regionally connected Pakistan avoids conflict and constructively supports a stable, secure and more prosperous region; plays a productive role globally, including on Ukraine and in multilateral forums. / Threats to the UK: Enhanced co-operation between the UK and Pakistan manages and reduces threats to the UK and UK nationals from criminality, terrorism and irregular migration. / Health and Education: Step change in Pakistan’s human capital - effective, inclusive, and resilient health and education systems providing quality services for all, with a special focus on women and girls, resulting in a healthier and more literate population. / Climate, Resilience, Environment and Water: Pakistan adopts a more resilient and cleaner growth path by preparing for, responding to and reducing the impact of climate change and biodiversity loss. / Open Societies: Pakistan becomes a more open society, in which the rights of women and girls, minorities and vulnerable groups are better protected, the government is held to account, and the state is better able to manage interconnected crises and provide services to citizens. / Economy and Trade: Pakistan’s economic trajectory back on track through greater macroeconomic stability, increased green, private sector led growth, and an enhanced more mutually prosperous trade and investment partnership with the UK.

Title: Portfolio Risk Assurance Programme III (PRAP)
Programme summary (100 words maximum): / The Portfolio Risk Assurance Programme III (PRAP III) will strengthen the Pakistan Network’s ability to identify, manage and address governance, management, financial, safeguarding risks, and help improve Value for Money (VFM) at programme level in a challenging external risk environment. The programme will focus on assurance, by playing an advisory role, building capacity of implementing partners and developing tools to mitigate risks for all Official Development Assistance (ODA) and non-ODA programmes including those funded through the Conflict, Stability and Security Fund (CSSF) and, in due course, the Integrated Security Fund (ISF).
What is the rationale for UK Aid spending? (200 words maximum): / Pakistan is a challenging operating context to deliver the Development and CSSF portfolio due to conflict, natural disasters (e.g., the recent floods), economic and political instability and risks of aid diversion. / Transparency International ranked Pakistan 140 out of 180 countries in the Corruption Perception Index 2022. There are multiple forms of corruption in Pakistan with political patronage, conflicts of interest, personal gains and influence peddling commonplace. These include petty corruption around access to public services or to bypass the law; grand corruption through flaws in public contracting and procurement; and direct misappropriation of public funds by senior officials. / Pakistan has been on the “grey list” of the Financial Action Task Force (FATF) since 2018 because of “strategic counter-terrorist financing-related deficiencies”. Pakistan was removed from the list in Oct 2022 after substantive progress made and assurance provided by the Government of Pakistan (GoP). / Pakistan is characterised by high levels of violence and insecurity, poverty, inequality, and deteriorating human rights which makes it a complex environment in terms of safeguarding and reporting. Economic and social exploitation and exclusion result from the systematic discrimination and marginalisation of women, children, religious minorities and other vulnerable groups, such as those with disabilities and transgendered. / Foreign Commonwealth and Development Office (FCDO) programming in Pakistan is transitioning from direct service delivery to system strengthening to reflect Pakistan’s middle income country status. The portfolio remains high risk with anticipated spend over the next five years up to £400 million (subject to approval of budget). It is therefore necessary to take additional measures to ensure the funds are protected, spent well and that programmes do no harm. Based on learning from previous programmes, PRAP III will focus on advisory support and demand-driven technical assistance in, achieving VFM, safeguarding, and protection against aid diversion.
Programme Value: up to £2 million		Country/ Region or Sector: Pakistan
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact name		Moeen Akhter
Threshold for final approval of Business Case: / Development Director
Date of Approval of Concept Note:	09/02/2022	Name and role of Approver Annabel Gerry, Development Director
Date of Approval of Business Case:	dd/mm/yyyy	Name and role of Approver Jo Moir, Development Director
Programme Code: 301477	AMP Start Date: 01 Oct 2023	AMP End Date: 31/09/2028
Overall programme risk rating:	Moderate
[note] https://www.transparency.org/en/cpi/2022/index/pak

Acronyms

ASP	Annual Statement of Progress
BHC	British High Commission
CPI	Corruption Perception Index
CSSF	Conflict, Stability and Security Fund
DEPA	Data Evidence and Portfolio Assurance
FATF	Financial Action Task Force
FCDO	Foreign Commonwealth and Development Office
FRA	Fiduciary Risk Assessment
GoP	Government of Pakistan
IAID	Internal Audit and Investigations Department
ISF	Integrated Security Fund
KPI	Key Performance Indicator
ODA	Official Development Assistance
PDF	Programme Delivery Forum
PET	Programme Effectiveness and Transparency Team
PRAP II	Portfolio Risk Assurance Programme II
PRO	Programme Responsible Owner
PrOF	Programme Operating Framework
SRO	Senior Responsible Owner
TA	Technical Assistance
TORs	Terms of Reference
VFM	Value for Money

## Strategic Case

A. Context and need for a FCDO intervention:

A challenging fiduciary environment
1. In 2020, Pakistan's Corruption Perceptions Index (CPI) score was 31 and it was ranked 124 out of 180 countries. According to Transparency International, the country's corruption perception score deteriorated to 27 in 2022 moving to 140 in the ranking. Political Patronage, conflicts of interest, personal gains and influence peddling are commonplace. There are multiple and extensive chains of both petty corruption to access public services or to bypass the law, and grand corruption through flaws in public contracting and procurement as well as direct misappropriation of public funds by senior officials. Widespread corruption can act as a drag on the delivery of most of HMG’s objectives in Pakistan. There are active fraud cases that are currently open at BHC Islamabad, which fluctuates a little as new ones are added or closed but has remained around the same level in the last few years.

2. Since 1995, when Pakistan was first included in the Corruption Perception Index (CPI) of Transparency International, it has generally performed poorly. From 2012 to 2015, the CPI scores marginally improved from 27 to 30 (Maximum 100; with 0 being highly corrupt, while 100 being very clean) bringing Pakistan to 117 out of 175 countries in 2015 on the corruption ladder. This relative improvement in Pakistan’s rank was a result of both partial improvement in Pakistan’s score and worsening scores for countries such as Syria. Since 2016, Pakistan’s CPI rating has deteriorated significantly due to lack of reforms to tackle corruption in Pakistan as well as due to other countries performing better. The chart below gives an overview of Pakistan’s performance in the last ten years against CPI.
[note] The CPI uses expert opinion to measure perceived levels of public sector corruption.
[note] Pakistan Corruption Rank - 2022 Data - 2023 Forecast - 1995-2021 Historical - Chart (tradingeconomics.com)

Pakistan’s Corruption Perception Index Ranking (2012 -2022)

3. Research has shown that sexual exploitation, abuse, and harassment (SEAH) is primarily experienced by women, girls and those that are disadvantaged, including children, people with disabilities and transgender individuals. In Pakistan, there is major inequality based on geography, gender, ethnicity, disability and faith and a significant modern slavery problem amongst the poor, minorities, women, and children. According to the “Global Gender Gap Report 2022” published by the World Economic Forum (WEF), Pakistan ranked 145th out of 146 countries surveyed for the gender parity index. The country ranked 7th among eight countries in South Asia, only better than Afghanistan. 22.6 million children do not attend school and half of the population, including two thirds of women, cannot read or write. In this operating context safeguarding risks are high.
[note] https://www3.weforum.org/docs/WEF_GGGR_2022.pdf

4. The recent Pakistan floods and economic crises exacerbate these risks. The Government of Pakistan estimates up to £30bn in flood damage, much of this borne by the most vulnerable at a time of increasing food prices and economic instability. More than 664,000 people are in displacement camps making them more vulnerable to abuse, sexual and physical violence and exploitation. There is a continued need to focus our efforts to safeguard FCDO programme beneficiaries and implementation staff. In addition, the economic crisis with inflation rates reaching above 30% has put immense financial burden on masses to meet their needs, increasing fraud and corruption risks.

Effectiveness of current arrangements
5. FCDO has been using a range of tools and methods to manage fiduciary and safeguarding risks, including:

Fiduciary:
- Fiduciary Risk Assessments (FRAs), which look at the public finance systems of governments (at an aggregate level) when Financial Aid is being given or considered.
- Risk registers to regularly review and update risks in line with FCDO Risk Management Policy.
- Due diligence assessments which assess the control design and operating effectiveness of non-government/private sector implementing partners, including enhanced due diligence to include safeguarding.
- Independent audits of our programmes, which are usually ‘statement’ and/or ‘compliance’ audits, confirming funds have been used as intended; and
- Programme reviews and evaluations, such as Annual Reviews and impact evaluations, which concentrate on results, management arrangements and value for money.
- Counter Aid Diversion Action Plan focused on increasing staff awareness of aid diversion risks and setting out the tools/training available to staff to address these risks.
- Third party monitoring and beneficiary feedback integrated into individual programme delivery across the portfolio.
- Building capacity across the Pakistan Network on safeguarding and trainings on Value for Money through PRAP II.
Safeguarding:
- Safeguarding Strategy and Action Plan to provide guidance across teams.
- Support through the Regional Safeguarding Hub to build the capacity.
- Enhanced due diligence to cover safeguarding.
- Safeguarding weeks and trainings for all staff to raise awareness.
6. These tools are vital and help to mitigate the risks but even taken together, still leave potential gaps in FCDO’s risk management approach given the high-risk fiduciary and delivery environment and significant safeguarding challenges. FRAs are becoming a less important tool to provide assurance with a shift in the portfolio from financial aid and large-scale service delivery to system strengthening and technical assistance. Although arguably the change in the portfolio reduces its exposure to fiduciary and safeguarding risks, the external operating context calls for additional measures including independent technical support to manage these risks in a standardised way across the portfolio. This shift in the portfolio has been thoroughly considered during the design of this programme. The design is also influenced by lessons learnt from the previous iterations of the programme. Based on the shift in the portfolio and lessons learnt, the new areas of support have been identified. These include value for money, support to the implementing partners to manage safeguarding risks, and providing support to CSSF/ISF programmes.
Programme genesis
7. BHC started to use dedicated assurance programming to respond to the risks identified above with the implementation of an 18-month pilot programme which ran till 2013. That was followed by a three-year first phase of the PRAP which completed in 2016 and a successor PRAP II programme that covered the duration from 2016 to 2022. The support provided through these programmes evolved from conducting due diligence, to risk assurance and then to advisory support over the years. The spending cuts and COVID-19 further limited BHC’s ability to directly monitor programmes and PRAP II played a key role in the last two years by conducting spot checks and providing an assurance function.

Lessons Learned:
8. One of the key lessons learnt from PRAP II is that timely identification of risks not only offers the opportunity to safeguard funds but also helps ensure value for money. The baselines reviews helped identify risks early on and proposed mitigating measures in a timely manner. The follow up progress reviews noted significant improvements against the actions agreed after these reviews. For example, one of the progress reviews identified 59 risks during baseline reviews, out of which 39 were fully resolved, progress was ongoing against 19 risks and one risk became irrelevant with a change of context by the time PRAP II ended. There are currently 17 approved programmes managed by BHC Islamabad with an overall estimated spend of over £400m in the next five years. These programmes will continue to need support provided by PRAP. As of January 2023, there are 23 safeguarding and 27 fiduciary and financial risks under these programmes.
9. Despite support provided over the years and the increased capacity of BHC staff, there continues to be demand for this independent assurance mechanism. The lessons from the PRAP II clearly highlight the need to have a quality assurance mechanism in place to ensure a consistent application of value for money frameworks across the full range of the FCDO’s development work including to recognise the shift from large scale service delivery programmes to policy support and system strengthening, and to better demonstrate the impact of all the levers we are using to deliver development impact. Similarly, PRAP II also identified the need to build the capacity of the delivery partners to manage safeguarding risks. In addition, CSSF/ISF programmes need support in managing risks and building controls.

The proposed response
10. BHC Islamabad proposes to meet this challenge by running a third phase of the Portfolio Risk Assurance Programme, managed within the Programme Effectiveness and Transparency (PET) Team. This will commission independent experts to conduct specialist reviews of the highest risk elements of our ODA and non-ODA portfolio. The second phase of the PRAP programme which ended in August 2022 conducted 41 reviews and cash-flow tracking exercises across a range of sectors and types of implementing partners, assessing governance and management processes, and developing action plans to help improve those processes and procedures. The proposed programme will build on learning from the PRAP II programme and create more space for not only assessing the risks but helping FCDO programmes to effectively mitigate these risks. The programme will support all of the Campaign Goals in the Country Plan by providing an extra level of assurance on programme delivery across the ODA and non-ODA portfolio.
11. The Programme will continue to act as an independent facility, rather than a mandatory requirement - conducting reviews, providing training and supporting implementation of policies only when agreed between the PRAP III Senior Responsible Owner and the programme teams, with support tailored specifically to the programme context. The work will only be contracted out in areas where we do not have internal expertise and will help to ensure consistency and standardisation across our delivery partners and programme teams. The evidence from PRAP II shows that all 41 pieces of work commissioned through PRAP II were activities that were not possible to be completed in-house. These activities required specialised skills and expertise that were not available in-house, as well as activities in geographic locations which were not accessible for the FCDO staff. Data, Evidence and Portfolio Assurance Group (DEPA) takes responsibility for filtering out the requests from programme teams which could be completed in-house.

12. The intended impact of the programme is ‘Improved efficiency and effectiveness of FCDO's bilateral programmes (including CSSF) in Pakistan, and the intended outcomes of the programme are:
- Improved risk management of BHC Islamabad programmes.
- Improved understanding, measurement, and management of value for money within the portfolio.

13. The main components of the proposed programme are:
- Review and advise on the highest risk elements of our portfolio, ensuring there are robust governance, management and financial controls to mitigate fiduciary risks.
- Conduct comprehensive cash flow tracking reviews following complete delivery chain from implementing partner through to downstream beneficiary/recipients.
- Support and build the capacity of FCDO staff in interpreting finance and assurance reports and adequate follow up.
- Help implementing partners develop tools to identify, manage and mitigate risks.
- Demand driven support to respond to specific areas including targeted forensic audit in the areas of interest to specific programmes. For example, on ground support to the Counter Fraud Unit (CFU) to protect HMG investments.
- Conduct value for money reviews of selected programmes, identify challenges, ensure lesson learning across portfolio and build capacity of the implementing partners to assess VfM.
- Support the implementation of safeguarding policies by delivery partners and conduct periodic reviews when required.

Essential issues to consider:

Gender Equality and Inclusion:
14. Although this programme will not directly contribute to addressing gender inequality, it will indirectly have a positive impact through providing assurance that FCDO funds (including CSSF/ISF) are being properly spent and accounted for, including on programmes with direct or indirect gender components. The programme will collect gender and age disaggregated data for PRAP reviews and identify any gaps identified through these reviews. The safeguarding component of the programme will help protect implementing partner, staff and beneficiaries by creating awareness and implementation of policies.

Public Sector Equality Duty
16. BHC Islamabad will require delivery partners to disaggregate data by sex, age, disability and geography while conducting reviews on behalf of programme teams and highlight any gaps and safeguarding risks that can be addressed. PRAP III’s focus on safeguarding will help to support the elimination of discrimination, harassment and victimisation across FCDO programming. All PRAP III delivery partners will be required to demonstrate compliance with the six areas of FCDO’s Due Diligence Assessment. First tier partners will be reminded of their responsibility to ensure appropriate safeguarding standards have been cascaded down the delivery chain, and to provide evidence standards have been shared and all partners are clear about those expectations. Protection and safeguarding are core components of FCDO’s accountability to target populations, and we will require partners put in place systems to enable grievances and safeguarding issues to be reported and investigated, including feedback loops to update people on the outcome of investigations and follow up of agreed recommendations.

Climate and Environment:
17. This programme will have negligible climate and environment impact as a result of its activities. However, BHC will ensure that the procurement process secures an organisation that is committed to minimise its carbon and environmental footprint.

18. This might include, for instance, committing to keeping international travel to a minimum, or minimising any local impact as a result of their operations. The programme will also provide support on VfM, risk, safeguarding for Climate/Resilience programmes ensuring they achieve greatest impact with resources available.

Partnership Principles Assessment
19. The Partnership Principles Assessment (PPA) sets out FCDO’s assessment of commitments made by the Government of Pakistan to four principles; (1) reducing poverty and progress towards achieving the Sustainable Development Goals, (2) respecting human rights and international obligations, (3) strengthening financial management and reducing the risk of funds being misused through weak administration or corruption, and (4) strengthening domestic accountability.

20. Our overall judgment is that the Federal Government of Pakistan is demonstrating a reasonably credible commitment to two of the four partnership principles namely: poverty reduction and financial management. However, there are causes for concern in certain areas of human rights where the trajectory of progress has been downward. Progress toward the attainment of the SDGs and poverty reduction is proceeding at a slow pace with the rapid population growth creating more pressure. Progress on the protection of human rights is mixed. On public financial management and anti-corruption, the direction of travel is broadly neutral, although some evidence indicates improvements. There has been mixed progress towards strengthening domestic accountability with a reduction in civic space and media freedom. Substantial reform is needed in all partnership principles areas (especially on the implementation of commitments where these are in place).

21. The PRAP II consultants were regularly permitted access to Government of Pakistan systems and records (Covid-19 restrictions permitting). This demonstrated the commitment to improve fiscal management, not only for the FCDO funds but with the government’s own funds.

Conflict and Fragility
22. The programme is intended to prevent (or uncover) fraud and corruption. In that respect, the programme may have an impact on conflict and fragility to the extent that fraud and corruption has roots in the social and political dynamics that affect levels of conflict and fragility.

For example:
- Reviews may reveal political drivers behind corrupt, fraudulent or inefficient practices that are intertwined with local power balances;
- The primary beneficiaries of corrupt or fraudulent practices revealed by review findings may play important social or political roles, including in the delivery of programme objectives;
- Review findings may affect relationships between politicians and bureaucrats, for example if bureaucrats are placed under pressure to act inappropriately before, during or after the conduct of the audit; and
- Reviews may well identify questionable practices on behalf of specific individuals that could lead to prosecution, potentially with political and social consequences.

23. While these concerns are real, they do not allow FCDO to divert from its zero-tolerance policy towards fraud and corruption and Do No Harm approach. The programme will be sensitive to political issues around corruption and fraud, and where these issues are perceived to be potentially destabilising, their treatment will be elevated to the appropriate level and managed in conjunction with colleagues in the wider Mission.

Counter Terrorist Financing
25. The Financial Action Task Force (FATF), a global money laundering and terrorism financing watchdog, removed Pakistan from a list of countries under “increased monitoring”, also known as the "grey list" in October 2022, after Pakistan made significant progress in improving its anti-money laundering and combating financing terror regime. The Pakistani Taliban (Tehreek-i-Taliban Pakistan) remains the largest militant organisation in the country. It has links to Al Qaeda and continues to launch sporadic attacks. The enhanced controls BHC Islamabad has in place provide assurance that every effort is made to ensure UK funding does not reach non-state armed groups and is only spent on the intended purpose across the development and CSSF portfolio. Partners will be made aware and informed of any changes in UK Counter Terrorism legislation.

B. Impact and Outcome:
26. The impact of the programme will be improved efficiency and effectiveness of FCDO bilateral programmes in Pakistan (ODA and non-ODA). This will be achieved by reducing the exposure of our funds to critical and high fraud and corruption risks, and ensuring implementation of safeguarding policies, as evidenced through the individual review findings. The programmes’ effectiveness will be improved because safeguarded funds have a higher chance of reaching the intended beneficiaries while efficiency will be improved by addressing governance and system flaws within the partner organisations and streamlining the flow of funds to beneficiaries. The programme will also help build capacity across BHC programmes to measure the VFM and report on it, which will contribute directly to achieving the intended impact of the programme.

27. To achieve this, the programme will help build overall capacity in managing risks that will enable better funding decisions by reducing the risk inherent in delivery models and partners. This will be achieved by partner organisations taking positive action to manage the risk identified through programme reviews. The programme will also promote and ensure consistency and standardisation of how FCDO and the implementing partners working at different scale address these risks and assess the value for money.

Risks
24. The overall risk of the programme is assessed as Moderate. The top risk to be carefully monitored throughout the programme would be reputational because of programme potentially uncovering any cases of fiduciary and safeguarding nature. BHC Islamabad will ensure that the risks in the programme are carefully monitored and managed in line with PrOF guidelines and FCDO Risk Management Policy. Risks in the programme will be reviewed on a monthly basis and compared to the programme level risk appetite with risks escalated if they are outside the programme risk appetites.

## Appraisal Case

28. The option to continue with existing model has been discounted at the Concept Note stage as there are new requirements identified as part of the PRAP II lesson learning exercise. These new requirements include providing support to CSSF/ISF programmes, VFM and safeguarding.

Feasible Options

29. The following options have been analysed:

Do nothing – BHC Islamabad does not continue with a facility for specialist reviews of high-risk areas after the closure of PRAP II programme.

Independent programme – BHC Islamabad continues with an independent programme led by the Programme Effectiveness and Transparency Team in DEPA, working in partnership with programme teams.

Embedded –Specialist reviews are embedded in individual programmes and managed by individual programme teams, with no central coordination.

Option 1: Counterfactual

30. BHC Islamabad does not continue with a facility for specialist reviews of high-risk areas after the closure of PRAP II programme.

31. BHC approach to fiduciary risk management prior to the PRAP had been typical of that found in other posts with a range of tools and expertise used to mitigate risks. The support through PRAP programmes has been running for two successive programmes in the last ten years, helping to enhance staff capacity in managing and mitigating risks. The shape of the portfolio is also transitioning from higher risk focus on financial aid and direct service delivery to lower risk system strengthening and technical assistance. On this basis, there is an argument that BHC Islamabad does not need to continue with the PRAP approach.

32. However, this argument ignores the fact that the complexity of operating context for the FCDO’s bilateral programme in Pakistan has increased significantly due to COVID-19, ODA cuts, staff turnover, massive floods, deteriorating economic situation, and difficulties in directly monitoring programmes in some parts of the country due to security concerns which are worsening for the first time in several years. Moreover, staff do not have the technical expertise to conduct risk assurance reviews (e.g., cashflow tracking) themselves as it requires specialist skills. All 41 reviews commissioned by the PRAP II in the last year were those that could not be completed in-house. These reviews required specialised skills as well as access to geographic locations that are not accessible for the FCDO staff. FCDO staff already follow VFM guidelines to assess the programmes, however, a sample study of four FCDO funded TA programmes conducted under PRAP II showed clear areas for improvement in terms of identifying and monitoring the VFM indicators and ensuring implementing partners have the capability to track VFM.

33. In a challenging fiduciary risk and safeguarding environment with limited oversight due to lack of access and resources to do it in all implementation areas, we judge the option of concluding the support provided through an independent programme, and having no successor, to be inadequate.

Option 2: Independent Programme

34. BHC Islamabad creates an independently managed PRAP successor programme led by the Programme Effectiveness and Transparency Team in DEPA, working in partnership with programme teams.

35. Under this option, BHC Islamabad will contract a suitable international commercial supplier in partnership with a national NGO to provide review, assurance and capability building services for the FCDO funded programmes. The programme will be the single dedicated facility to provide support to all FCDO programmes - ODA and non-ODA. In absence of such an arrangement, all on-going programmes might need to set up separate contracts based on their assurance and capability building needs which would result in a significant amount of time and effort to procure and manage these contracts by individual programme teams and Commercial Directorate at HQs. One independent programme would ensure consistency and standardisation across the ODA and non-ODA portfolio, improve lesson learning across teams and achieve better VfM.

36. The independent programme will be very effective in providing support to CSSF team in Pakistan. For example, in some cases, the CSSF programmes are delivered through organisations that are new to FCDO and its compliance requirements. Such partners across the portfolio may have less capacity to focus on risk assurance and VFM. PRAP III with strong expertise in place will provide much needed support to such organisations working with BHC Islamabad to deliver the CSSF portfolio.

37. For a relatively small amount of money PRAP III will better protect at least £400m of UK tax-payers funds to be spent in the next five years by providing an additional level of assurance on the ODA and non-ODA portfolio. It will build the capacity of implementing partners by providing technical expertise on fiduciary risk management and mitigation, safeguarding and improving the quality of the VfM framework and measurement. By extending the support to new areas compared to PRAP II, the programme will respond to learning and needs identified across the FCDO bilateral programming.

38. The independent programme will enable the dedicated BHC team to effectively manage the work of the supplier, learning continuously and improving how the facility works, applying consistent quality standards, managing costs through the application of standardised unit cost analysis, and generally being a clear, single point of contact for liaison with the reviewers (who themselves would have a clear, single point of contact). It is also more efficient by saving programme teams substantial time in management and administration. In summary, the independent programme is the most efficient and transparent arrangement to achieve the objectives of this programme.

Option 3: Embedded Programme

39. The conduct of specialist reviews is embedded in individual programmes and managed by individual programme teams, with no central coordination

40. Under this option, responsibility for all fiduciary risk management including use of specialist reviews, safeguarding capacity building and VFM frameworks, would rest with programme teams. Reviews would be funded from programme budgets, with specialists contracted separately and teams using their own programme staff to manage, administer and follow up on reviews.

41. The main advantage of this option is programme teams would have greater ownership of the reviews and findings since they would need to invest significant time and resources into the scoping and implementation of the reviews and capacity building efforts. Moreover, with multiple suppliers across the portfolio, it will be possible to make comparisons between them and determine if there are technical weaknesses.

42. The main disadvantages are that without additional central capacity it becomes more administratively burdensome and programme teams may struggle to cope with the additional resources associated with the programme. It is likely to result in additional responsibility of managing multiple contracts across office. In addition, there is limited capacity within BHC Islamabad and centre to procure and manage multiple contracts. In addition, funding within each of the existing programmes will not be available for this kind of support. There is also a risk that some teams may not prioritise this additional level of assurance due to limited ability to manage.

43. Finally, it will not be possible to ensure lesson learning, promoting standardisation and consistency of approach if such assurance mechanism is embedded separately in each programme.

The preferred option is Option 2

44. The ‘do nothing’ option is not preferred because, the financial and safeguarding risks in the portfolio are too significant. Moreover, new areas of support including support to CSSF team have been identified through PRAP II along with unmet needs for demand driven reviews including more hands-on approach to manage safeguarding risks. It is important to note that the PRAP II programme continued to respond to demand driven requests until the end with services having to be prioritised due to time and resource constraints in the final year.

45. Option 3 is not preferred as the focus, clarity and potential for cross-learning that centralised management allows outweigh any advantages from greater ownership by programme teams. There are also value for money concerns with option 3 – it would result in multiple different contracts with multiple different auditors, increasing transaction costs and making quality consistency more difficult.

46. Option 2 is preferred as it provides the best chance for the optimum use of specialist resources, while still being flexible enough to allow programme teams and the office as a whole to guide when and how those resources are used. It also offers excellent value for money to have one central contract in place to provide assurance and demand driven specialist reviews across BHC. It is a well embedded model that has worked very well over the years, and there is continued demand from the programme teams for such support to be in place. However, DEPA will take the responsibility to make sure that the reviews are contracted only in areas that cannot be completed in-house.

Assessing the strength of the evidence base for each feasible option

Option	Evidence rating
1	Medium strength evidence that the option is ineffective – Pakistan remains a high-risk environment with staff not having access to regularly visit all the programme sites. Although a range of tools are used across the portfolio to mitigate, manage fiduciary and safeguarding risks and manage/measure VfM, given the operating context an additional layer of programme assurance is required for bringing in technical expertise to provide more in-depth reviews and improve consistency, standardisation and learning.
2	Strong evidence the option will be effective – the original Continuous Financial and Risk Management programme and the two phases of the PRAP programmes in the last ten years have demonstrated the efficiency and effectiveness of the programme over a more than ten-year period. There continues to be demand from the programme teams in BHC Islamabad for support even after the closure of PRAP II programme. The programme has promoted learning and standardisation across portfolio. The evidence shows that capacity built through the first phase has been sustained e.g., with programme teams conducting quality due diligence in house during the second phase. Similarly, improving governance structures of relatively new and smaller partners in the previous phase will help these organisations in improved delivery. Moreover, the programme has been able to put controls in place to keep track of progress on review recommendations to ensure follow-up. There are examples of similar standalone programmes outside Pakistan that have successfully provided similar services. (For example, Africa Regional Department Cross-Portfolio Third Party Monitoring (TPM)).
3	Medium – with staff turnover, there is limited programme management capacity in BHC Islamabad to manage multiple independent contracts. In addition, the supplier base for such specialised services is very limited in Pakistan. It also doesn’t meet the objective of standardisation and learning across programmes.

Options appraisal of delivery mechanisms

47. Option 1: Multilateral Organisations: entering into an agreement with a multilateral organisation is not a preferred option due to lack of expertise in conducing such reviews. The multilateral organisations will have potential conflict of interest as they are also acting as delivery partners for various programmes funded by BHC Islamabad. However, an MoU can be considered with one of the UN agencies, e.g., UNOPS. The advantage is that it might help improve access to other multilateral organisations.

48. Option 2: INGOs/NGOs: an Accountable Grant Agreement (AGA) with an INGO/NGO. This could be a viable option to deliver the safeguarding component of the programme, however, INGOs/NGOs are not likely to have expertise to conduct financial baseline reviews, VFM analysis, cashflow tracking and demand-driven TA on various aspects of risk assurance.

49. Option 3 (International commercial supplier with a national NGO partner): an international commercial partner in partnership with a reputed local NGO partner (Preferred). This should ensure impartial and consistent professional integrity of the reviews and protection of the in-country partners while having strong presence in country, given the sensitivity of the work. The disadvantage is that it will take longer to complete this procurement process but once in place it will ensure consistency and timely delivery in coming years. We will also explore the option of working with a multilateral organisation with expertise in project management (e.g. UNOPS) to improve access to the multilateral implementing partners. We will also consider the option to procure services of international commercial supplier and a national NGO separately however, combining both in one arrangement will be more efficient. We plan to test these delivery options through an Early Market Engagement (EME) session with the potential partners to ensure that this option provides support in all areas envisaged in this Business Case.

What are the costs and benefits of each feasible option?

Costs:
50. The total cost of the programme will be up to £2m over five years. The budget will be reviewed at the mid-point in line with the progress of the programme and spending review to assess if there is need to align the budget for the remaining duration of the programme.

Benefits:
51. The programme demonstrates UK’s commitment to Value for Money, safeguarding and zero tolerance on fraud. It sends a clear signal to all our partners that governance, fiduciary controls and risk management must be fit for purpose. At the impact level the programme will improve the efficiency and effectiveness of FCDO funding in Pakistan. The programme is designed to improve VFM as well as eliminate fraud and corruption as a result of reviews to be carried out by the PRAP III programme and capacity building of staff to manage risks. In summary, the maximum budget for this programme will be approximately 0.8 percent of the UK in Pakistan’s anticipated ODA budget (based on FY23/24 allocation), which offers excellent VFM. The programme will also have a wider impact on non-UK funding by helping partners to strengthen systems and through capacity building to improve fiduciary and safeguarding risks of wider range of funds. It will also give confidence to programme teams about risks and how they are being managed, enabling better discussions with implementing partners based on evidence from reviews.

52. The programme will derive benefits by delivering the following components:

Specialist reviews – assessing and improving risk management:
53. Specialist reviews will be conducted by independent international and national experts on the elements of the ODA and non-ODA portfolio considered to be highest risk. In most instances, this will involve focussing on an implementing partner, systems in place and capacity to manage risks. In some cases, reviews may be conducted on a business process rather than an agency, for example, cash flow tracking (which may involve reviewing the work at multiple levels in the process). Most reviews will concentrate on financial controls, use of funds, implementation of organisational policies, for example policies on safeguarding, and ability to measure VFM and achievement of intended results and impact. The reviews will conclude in concrete recommendations for the BHC programme team and SRO. These specialist reviews provide additional assurance that complements ongoing risk management by BHC programme managers.

54. The cost of these reviews constitute a small portion of the size of the programme but add significant value. For example, PRAP II programme carried out a process review of the Innovation Challenge Fund (ICF) component of Sub National Governance (SNG) Programme II and made recommendations to streamline the process. The cost of this review was £23,000 for this £36 million programme. This review helped SNG II programme identify 9 areas for improvement (out of which 3 were high risk) and recommended remedial actions.

Cash flow tracking – for stronger controls in place to make sure that funds reach intended beneficiaries:
55. One of the major opportunities for corruption is the various points in the financial flows where funds are released on the basis of some form of evidence that payment is due. Such processes often lack adequate controls in terms of a documented process. In reality, the opportunity for corruption is potentially available for a different amount of payment to be passed to the next link in the chain, or for the evidence to be falsified. This approach will identify high risk programmes that are susceptible to such corruption. These reviews will document the financial flow process and confirm the authenticity of the cash value being processed between payee and recipient. These reviews will also corroborate the evidence for supporting payment release by checking the validity of the data or examination of goods or services delivered. One such example from PRAP II is the cash flow tracking exercise completed for the £50 million Financial Inclusion Programme. The cost of this review was £25,000 which provided assurance on financial controls of a significant investment. We recognise the challenge of conducting such reviews for the multilateral organisations when they are engaged as delivery partners. The access to their financial systems is limited so we will work with multilaterals to discuss where we can best support.

Interpreting finance and assurance reports – to understand and verify the financial standing of projects:
56. An important programme management tool at staff disposal are programme audits. Independent annual audited statements are required from all commercially contracted partners and grant recipients. Understanding and making appropriate use of these reports is vital, including adequate follow up, in ensuring effective financial oversight of programmes.

57. The supplier will be required to build the capacity of BHC staff in interpreting these statements and called upon on an ad hoc basis to support programme staff to interpret audit reports received from various sources, and quality assure the findings and recommend/support follow ups planned by the programme teams. The supplier will also provide staff with a range of tools including but not limited to, staff briefing sessions and checklists and guides. This is required over and above the work of BHC staff and the learning and development provided by FCDO and the CSSF because it requires strong technical expertise in some cases.

Targeted technical advice – to meet unforeseen needs:
58. This component will aim to cover all of BHC’s high risk programmes, and other programmes where teams request in-depth analysis. But in addition to this, BHC is likely to need occasional demand-based expertise that cannot be precisely forecast. Learning from PRAP II, such demand driven reviews will be required where it is not possible for the BHC staff to engage directly, access to the review location is not possible, in-house capacity does not exist, and when it is efficient and economical to conduct such review through PRAP as compared to another outsourcing option. For example, PRAP II responded to 13 demand driven TA requests by programme teams from 2021 to 2022.

VFM reviews – to better measure and report VFM:
59. Based on learning from the PRAP II programme which highlighted inconsistency in measuring value for money by FCDO funded technical assistance programmes, a sample-based review of TA programmes will be conducted in the first year of the programme to assess the impact and learning from the review conducted in 2020/21. Based on the needs identified through this review, measures will be taken to align the VFM approach across programmes and follow up reviews will be conducted. The ability to assess and measure value for money varies across portfolio including the CSSF programme. The CSSF programmes are delivered through organisations that may be new to FCDO and its compliance requirements. Such partners across the portfolio may have less capacity and experience to focus on risk assurance and VFM. Under PRAP II, mapping and analysis of 68 indicators across the four selected TA programmes was carried out at a cost of £35,000 which helped identify areas of improvement in data analysis and VFM reporting,

Safeguarding – delivery teams and beneficiaries:
60. Reviews will assess delivery partner implementation of safeguarding policies, follow up on enhanced due diligence recommendations, in particularly risky programmes with a focus on women and girls, children, minorities (2/3rd of the portfolio) and provide capacity building where required. For example, the CSSF partners work in sensitive areas like policing, countering narcotics and sex offender registers. Development programming works with women and girls. Safeguarding is of particular concern in all these sensitive areas of programming where PRAP III can help improve understanding of the safeguarding polices as well as ability to implement the policies.

Capacity building – to ensure sustainability of learnings from PRAP III:
61. This Business Case is for five years and follows the three predecessor programmes (Continuous Audit Programme, PRAP, and PRAP II). The earlier PRAP programmes had envisaged the PRAP approach concluding at the end of the previous Business Case period. However, continued FCDO investment, evolving needs for assurance, combined with the high fraud and corruption environment mean that there is a need to continue to build programme assurance capability and continue the PRAP programme approach.

62. To ensure ownership of reviews by the programme SROs and the implementing teams, the PRAP-III implementing partner will design and deliver training sessions on all key areas of support provided through PRAP III to ensure sustainability. The programme will equip the implementing teams and FCDO staff with necessary knowledge and tools to ensure continuation of assurance function after the programme ends. Similarly, the implementing partner will develop a VFM indicator bank to ensure teams continue to benefit in terms of identifying the right indicators and measures after the support through PRAP III ends.

Theory of Change for Preferred Option

63. The intended impact of the programme is to improve the efficiency and effectiveness of the BHC portfolio. The theory of change is that this impact can be achieved by better managing fiduciary and safeguarding risks, and by better measuring and managing value for money. The assumption is that if risks and VfM are better managed there is a higher chance that funds reach intended beneficiaries, that staff, delivery partners and beneficiaries will be safeguarded and barriers to economic, efficient, effective and equitable programming will be overcome.

64. The programme aims to increase the knowledge and understanding of the delivery environment through which the FCDO funds are channelled. It is assumed that this increased knowledge, quick access to technical expertise and increased capacity among delivery partners will enable better funding decisions, either by taking action to reduce the risk inherent in delivery partners or by stopping such arrangements. The assumption is that this will be achieved by partner organisations taking positive action to address review findings to reduce their critical and high-risk findings. The programme will improve how programmes measure VFM and safeguarding policies are implemented effectively. The theory of change assumes BHC colleagues and implementing partners will engage with the proposed mix of reviews and capacity building in such a way that high quality and actionable knowledge and understanding is generated, understood and applied.

What measures can be used to assess Value for Money for the intervention?

65. Economy will be delivered through contracting a consortium of an international commercial supplier working closely with an in-country team and a national NGO. The combination of using an international supplier with a team in Pakistan is a tested model that has worked well in the previous phases of the programme. Using local expertise will allow simple and cost-effective access to areas of Pakistan and implementing organisations that international consultants would struggle to access and would likely incur higher costs. Throughout the life of the programme, the balance between the international team and the in-country team will be monitored to ensure further value for money. For example, more than 85% of the budget spend accounted for local inputs in the last two years of the PRAP II. The same will be used as baseline to monitor economy of PRAP III. In another example, the cost of completing a cash-flow tracking exercise of the £50m Financial Inclusion Programme was 0.05% of its overall budget.

66. Efficiency is how inputs (money and staff) are converted into outputs (review reports), capacity building of BHC partners (number of trainings), and the extent to which the programme portfolio will be covered by PRAP III support (% of programmes benefitting). Gains will be made by having a standalone programme with centralised management because it:

- Allows a single point of management for a single supplier, delivering economies of scale.
- Enables more focused quality assurance and lesson learning; and
- Results in the application of consistent standards, methodologies and reporting formats across all of the design, field work and audit reports.

67. Effectiveness is a measure of how outputs (review reports) are converted into outcomes (positive steps taken to address review recommendations).

68. The overall effectiveness will be measured through the improved programme management of BHC programmes, reductions in fiduciary risk, management of risks outside appetite (number of risks escalated), uptake of recommendations of the PRAP III reviews (actions completed within specified timeframe), ability to monitor value for money (use of better indicators) and effective management and reporting of safeguarding risks. Each review report is expected to highlight areas of management and financial weaknesses within the systems and controls of implementing partners to be addressed to improve performance. In addition, relevant programme teams are supported to understand risks and value for money in a more professional manner than previously.

69. It is anticipated that an increased due diligence of expenditure and understanding of risks will further enhance BHC Islamabad’s reputation within the donor community, protect UK taxpayers’ money, and forge even more effective working relationships at the highest levels of government.

70. The supplier will be clearly briefed on the result-focused nature of this intervention, with emphasis on delivering results and ensuring Value for Money for the BHC portfolio through a strengthened control environment.

72. Cost Effectiveness will be ensured by improved efficiency and effectiveness of FCDO’s ODA and non-ODA bilateral programmes in Pakistan. This will be measured through in house annual quality assurance of programme ARs and PCRs by DEPA.

71. Equity will be ensured by prioritising/including activities in the annual work plan on the basis of risks attached to the programme or intervention, size and or complexity in the programme and or where access to observe the programme is limited. At the programme level, the improvements through PRAP III support are expected to equally benefit all beneficiaries through effective implementation of safeguarding policies with a specific focus on women and girls. Some of the programmes expected to benefit will be voice and accountability, primary education and humanitarian programmes where the beneficiaries are the most marginalised communities. Moreover, the programme will ensure women are part of the implementing team and will be covering programmes which impact on the most vulnerable as part of safeguarding support.

VFM Indicators
Economy	- xx% of the budget spend accounted for local inputs throughout the life of the programme (assessed annually) / - xx% budget savings on each review commissioned by rationalising the expert inputs.
Efficiency	- xx number of programmes using PRAP III facility every year. / (Having a single supplier will enable more focused quality assurance and reduced transaction costs).
Effectiveness	- xx% of recommendations made by PRAP III implemented by the programme teams. / - xx number of lesson learning sessions planned each year. / - xx number of delivery partner staff trained through PRAP III designed and delivered trainings.
Cost Effectiveness	- xx number of programmes assessed as effectively managing the risks and measuring value for money (through DEPA quality assurance of ARs/PCRs)
Equity	- xx number of reviews completed for programmes focusing on vulnerable beneficiaries / - xx number of safeguarding reviews completed / - xx number of implementing partners training on effective implementation of safeguarding policies.

E. Summary Value for Money Statement for the preferred option

73. The preferred option will provide Value for Money if:
1. It provides significant added value to the rigorous risk management systems currently in place with minimum transactions costs concurrently,
2. The programme teams proactively use this facility and take actions against agreed recommendations.
3. Enhances the assurance of FCDO reporting to the UK taxpayer.
## Commercial Case

Delivery Approach
74. This programme will be delivered through a consortium of an international commercial partner with strong presence in country and in collaboration with a national NGO. The proposed consortium will be well positioned to deliver the aims and objectives effectively, while bringing the necessary independence and adequately addressing any perceived conflict of interest between FCDO and implementing partners. An Early Market Engagement will be planned to apprise potential partners of engaging in delivery of this programme and seek their feedback on implementation modality. We will also explore to engage multilateral organisations with expertise in project management (e.g. UNOPS). The table below summarises our delivery approach:

Key considerations	Approach
What capabilities we are procuring?	A consortium of an international commercial supplier and a national NGO: / International commercial supplier with demonstrated experience in providing portfolio level risk assurance including support in areas like value for money, risk management, cash flow tracking and demand driven TA. / A national NGO with experience in safeguarding risk management, building capacity of staff and ensuring effectiveness of safeguarding polices.
How do we plan to source these expertise?	A competitive bidding process through a suitable framework agreement. In absence of a suitable framework agreement, we plan to run an open OJEU procurement process.
How will we manage the supplier?	We plan to contract supplier through a hybrid contract with payments related to both quality inputs, and successfully delivery of milestones
How will we manage commercial risks?	The supplier will be expected to proactively declare their actual or perceived conflict of interest if they are engaged in delivery of a FCDO funded bilateral or centrally managed programme, and how they plan to mitigate the conflict of interest. The other commercial risk could be lack of level playing field and transparency which will be mitigated by sharing the same level of information with all potential partners. The risk of cost escalation will be mitigated by putting in place a payment by results or hybrid model to control costs and monitoring key costs closely.
How will ensure value for money?	The value for money will be ensured by clear prioritisation of areas of work and programmes to be supported by PRAP III to ensure that the facility is used where it adds value and not for core programme management tasks that can be managed in house.

75. We have actively considered two options although due to the nature of work and expertise required to deliver this programme, international competitive bidding is our preferred option:

Option 1 (not preferred): Procurement through FCDO’s in-country Commercial Team:
76. The procurement of services through a local procurement managed by in-country commercial team to deliver this programme could be quicker but needs to be done again every year due to an upper limit of £125,000 set by the OJEU rules. This procurement will be completed in four to six weeks however needs to be repeated at least four times to have a delivery partner in place throughout the life of the programme. Since it is going to be a competitive process, it is possible to have a different delivery partner every year which makes handing over the work and sustainability very challenging. Moreover, it will take time every year to complete the contracting and on-boarding of a new partner resulting in loss of time and effort.

Option 2 (Preferred): Open competition through Framework Agreements / OJEU (find a tender service):
77. At this point there is no framework agreement in place that meets the programme requirements, however, there is a possibility that new framework agreements are signed in the first half of the 2023/24 financial year, which will open further options for the procurement of services to deliver this programme. Open competition through OJEU will be the fallback plan if none of the existing or new frameworks are suitable to delivery this programme. In both cases, the lead partner will be required to have in-country presence and be able to partner with a national NGO with experience in safeguarding policies and practices.

78. What are we buying? the programme will address various aspects of financial probity, risk management, value for money and safeguarding assurance. Using recognised international audit methodology and experience the appointed supplier will examine the financial and management activities of programme implementation units through which FCDO funds flow. The supplier will also help adapt best international practices on assessing and measuring value for money. The national NGO, as part of the consortium will lead the safeguarding work by reviewing and improving the safeguarding risk management policies of the delivery partners for all FCDO programmes. The chosen procurement route will give FCDO access to a strong network of international experts, in-country experts with local knowledge of challenges and local solutions.

79. The investment for this programme will be up to £2m for five years. Competitive tendering the service requirements will drive added value for the programme investment and comply with the legislative requirements of the Commercial Directorate. FCDO will ensure that all pertinent information is made available to all interested parties, giving them the opportunity to compete on an equal basis and improve the prospect of comparable technical bids from which to select on a Value for Money basis.

Bid Evaluation Criteria:
- Capability to operate in across Pakistan where BHC programmes are implemented.
- Technical expertise in risk management, assurance, advisory support, safeguarding and value for money.
- Established partnership with a national NGO with proven experience in safeguarding.
- Ability to quality assure all products/reports produced by the technical experts and timely delivery.
- Well embedded fraud, corruption and safeguarding policies.

Contract Management capability
80. The model of an international commercial supplier in partnership with a national NGO is the preferred model. This should ensure impartial and consistent professional integrity of the reviews and protection of the partners, given the sensitivity of the work. The TORs will place a substantial weight on demonstration of results delivery in comparable operating environments.

81. The design is a rolling review of the financial, management, advisory and safeguarding activities of implementing partners and derives commercial advantage for BHC in the following four areas:

1) Ensuring BHC’s project investment is used for its intended purpose.
2) Competitively driving value from the local supply base.
3) Building audit function capability/capacity locally, and
4) Ensuring safeguarding standards are maintained

82. The appointed supplier will be expected to demonstrate how successful delivery will be achieved, and how continuous quality improvement and cost reduction will be achieved and maintained over the intervention duration. Contract for the earlier phases of the programme have been input-based. This new phase of the programme will move to a hybrid contract with some costs paid on an input basis, but majority of payments made against successful delivery of quality outputs. The key performance indicators will include:

- The supplier’s ability to respond to programme teams request in a timely manner, and within budget.
- A yearly workplan with all agreed tasks in consultation with the programme teams.
- Regular progress reports on all streams of ongoing work.
- Capacity building / training calendar prepared well in advance, and trainings well attended by the delivery partners.
- Lesson learning sessions regularly organised to ensure continuous improvements throughout the progress.
- Take up of the recommendations made to improve the risk management of programmes.

Break points:
83. The contract will have adequate provision for variation in form of break points to adapt to changes that occur during the life of the programme, including scale up and down. To achieve this, a detailed contract management plan will be developed and agreed between BHC and the supplier. Key review points for the contracts will be annually throughout the duration of implementation. Continuation from each review point will be contingent on supplier performance, programme results, satisfactory work plans and a continuing VfM rationale. BHC through the contract will retain the flexibility to amend work plans and budgets within the agreed scope, when required. The contract will have a provision to extend the contract for another two years if there are any met needs and funds are still available.

Value for Money (VfM):
84. The partner will supply the programme with access to a strong network of national expertise with quality assurance by international experts, provide an efficient means of exercising fiduciary control, managing risk and ensuring the intervention supports value for money and safeguarding aspects of FCDO programmes. The terms of reference for each review will be agreed with the commissioning programme teams and will always contain clear deliverables which would be linked to remuneration and the delivery of key results.

85. BHC will expect an open book accounting for cost transparency. BHC will drive savings by using economy, efficiency effectiveness, cost effectiveness and equity indicators in a strong VfM framework that will be developed by the partner during the first two months of the programme. BHC will set out clear expectations for the implementing partner on driving VfM and hold awareness raising sessions for the implementing partner to improve VfM including recording of savings.

Key costs and key cost drivers
86. The key cost for this technical assistance will be the consultancy fee rates. Currency fluctuations and high rates of inflation are likely to be the key cost driver for the project as the Pakistani Rupee, GBP parity has shown substantial volatility in the last year. Pakistan is generally perceived as a difficult working environment, with access to many areas circumscribed by security restrictions. Duty of Care will be the sole responsibility of the implementing partner, and security will attract a cost premium. BHC will complete a risk assessment of the project, which will be shared with all bidders as part of tender packages. We will use FCDO benchmarking data facilitated by PCD to review and evaluate the proposals submitted by specialists.

## Financial Case

Overall Programme Budget:

87. The programme budget is up to £2 Million over five years. The programme will be funded from programme resources (RDEL). This budget will be spent on technical assistance to provide support across FCDO ODA and non-ODA programmes. The programme will have two main components, one focusing on overall risk management and VFM (estimated value £1.6 m) and a second component focusing on safeguarding support (estimated value £0.4 m).

88. The budget is split across five years from 2022 to 2026. An overview of costs is provided in the table below.

Component: 301477-101	FY 2023-24 (£)	FY 2024-25(£)	FY 2025-26 (£)	FY 2026-27 (£)	FY 2027-28 (£)
Budget	£100,000	£500,000	£525,000	£500,000	£375,000
Total Budget (£m)		£2,000,000.00

Estimated Quarterly Forecast (to be firmed up during the implementation)

Year	Q1	Q2	Q3	Q4	Total (£)
FY 2023-24 (£)				100,000	100,000
FY 2024-25(£)	125,000	125,000	125,000	125,000	500,000
FY 2025-26 (£)	125,000	150,000	125,000	125,000	525,000
FY 2026-27 (£)	125,000	125,000	125,000	125,000	500,000
FY 2027-28 (£)	100,000	125,000	100,000	50,000	375,000

Flow of funds:
89. A commercial contract will be signed with one of the reputed international commercial suppliers that demonstrates the skills and expertise required for programme implementation. The programme funds will be disbursed to the programme partner in arrears in accordance with an agreed work plan and payment schedule. The selected partner will be the recipient of all the payments.

90. The project does not involve financial aid and there will be no costs incurred by third party organisations. The programme will be funded from FCDO’s bilateral ODA budget for Pakistan. The programme is expected to commence the procurement process from August 2023. The budget will be reviewed on a yearly basis in line with the progress of the programme and to align with Spending Review allocations. All activities under this programme are ODA eligible.

91. The annual work plan will be agreed upon at the beginning of the financial year to allow the selected partner to provide an annual forecast. This will be revisited on a rolling monthly basis, with updates to forecasts done as necessary. The budget will be reviewed and agreed separately for each work task agreed with the supplier to keep the costs rationalised and within overall budget. It will include a careful review of input costs proposed by the supplier.

Cost profiling and planning:
92. The intention is to maintain a flexible call down pot of money that responds to the programme needs as they are identified. The programme costs have been estimated using two sets of information:
- Average costs for each audit review and progress review, derived from an analysis of spending on PRAP II.
- Estimated requirements for baseline reviews and progress reviews, advisory and safeguarding support in future years, derived from an analysis of the FCDO pipeline.

93. It is intended that this programme will cover all specialist reviews of the FCDO bilateral programming in Pakistan over the next five years, ensuring we do not need to conduct multiple tenders or manage multiple suppliers. The specialist reviews will include base line reviews, cash flow tracking, spot checks in areas not accessible for BHC staff, reviews of VFM frameworks, safeguarding policies of delivery partners and other demand driven reviews that could help improve the delivery of BHC programmes.

94. As the programme will start in the third quarter of the 2023-24 financial year, spending is estimated to be lower this year. Demand for major reviews is also envisaged to drop in the later years of the programme, with more spending on building capability.

Financial and Fraud Risk Assessment:
95. With direct contracting of the supplier by BHC, we judge this programme to have low financial and fraud risks. The programme will procure services in line with the identified needs of the programmes, thus ensuring that BHC pays only when confident of the receipt and quality of agreed deliverables that are approved by the requesting programme team. This will be assessed in line with the TORs agreed for each task. However, the programme will make it more likely that fraud and corruption will be uncovered.

96. Where fraud is identified, BHC’s response will be in accordance with FCDO procedures, and our zero-tolerance policy as directed by the FCDO Internal Audit and Investigations Department (IAID). This does not mean an automatic suspension of contract. Decisions on suspension will be made on a case-by-case basis, using a balanced assessment of risk and reward and measures that can be applied to safeguard investments.

97. There is also a risk that the overall funding situation changes, and the funds may not be available for this programme. To mitigate this risk, the programme budget will be reviewed annually in line with the activities agreed with the programme teams, and a key consideration will be given to the availability of budget.

PRAP-III Audit:
98. The partner will be subject to an annual independent audit by an auditor of international stature. Annual audited statements of the organisation and programme specific quarterly reports received from partners will be reviewed by the Programme Responsible Owner (PRO) and in case of any observations, these will be followed up with the supplier.

Expenditure Monitoring, Reporting and Accounting
99. Expenditure will be monitored and accounted for based on agreed work plans and budgets within the limits of the contract. Payments will be made monthly in arrears as per normal FCDO contract guidelines. Detailed finances will be decided between the programme team and the supplier after the risk-based plan is submitted, depending on the number of reviews being carried out.

100. Invoices submitted by the supplier will follow a format agreed in advance by BHC, likely to include the supplier’s time and expenses against each entity. The team will have regular meetings with the supplier on a fortnightly basis for updates on the ongoing activities. All budgets will be forecasted on a monthly basis to ensure a tight financial oversight of the overall disbursement. The team will ensure that the overall variance of the programme each quarter is less than 5% of the total cost disbursed. The team will have regular meetings with the financial team to ensure accruals and prepayments are recorded and invoices are disbursed following the standard procedures.

101. Also, partners will be required to provide quarterly reports against agreed deliverables. These will be scrutinised by the designated SRO and PRO to ensure funds are spent according to agreed priorities and costs demonstrate VfM.

Are there any accounting considerations arising from the project?
102. There are no accounting considerations? arising from the project due to simple nature of the funding provided, with no assets being created or complex financial arrangements put in place to deliver this programme.

Tax Considerations:
Relating to occasions of Disclosure of Tax Avoidance Schemes in line with the General Anti-Abuse Rule, partners will be bound to represent and warrant that as at the commencement date of the contract, they have notified FCDO in writing of any Occasions of Tax Non-Compliance or any litigation involving them linked to any Occasions of Tax Non-Compliance. If, at any point during the term of the agreement, an Occasion of Tax Non-Compliance occurs, the partner will be bound to:
- notify FCDO in writing of such within five working days of its occurrence: and
- provide details to FCDO of the steps the partner is taking to address this and prevent the same from recurring, together with any mitigating factors.

It will be clearly set out in the TORs that where partners will be liable to be taxed in the UK or pay national insurance contributions in respect of consideration received under the agreement or contract, the partner will be bound to:
- at all times comply with the Income Tax (Earnings and Pensions) Act 2003 and all other statutes and regulations relating to income tax, and the Social Security Contributions and Benefits Act 1992 and all other statutes and regulations relating to national insurance contributions, in respect of that consideration; and
- indemnify FCDO against any income tax, national insurance and social security contributions and any other liability, deduction, contribution, assessment, or claim arising from or made in connection with the provision of the Services by the partner or any of its personnel.

Box: Anticipated Delivery Chain

FCDO

Programme Management, Compliance and facilitating partners in planning learning sessions.

Partners and Deliverables Monitoring.

FCDO Executed Activities

PRAP-III

Consultancy fees of the technical experts
contract with supplier/partner organisation – Selected through Call for Proposals

Beneficiaries (FCDO programme teams)

Technical Assistance –
£ 2m

Risks and Mitigation Measures: See Management Case for details.

## Management Case

103. This section sets out arrangements and structures for the implementation of Portfolio Risk Assurance Programme (PRAP III). This includes programme management within BHC and programme management arrangements of the selected partner. It explains the programme monitoring and evaluation arrangements and summarises the key risks and how these will be managed in the programme. This programme is expected to work with the majority, if not all, FCDO bilateral programmes in Pakistan at some point based on the needs identified during the duration of the programme, therefore the management roles and responsibilities will be as follows:

- The supplier will work to the overall terms of reference for their contract, but they will liaise with BHC programme teams to draft individual scopes of work before embarking on a review for a programme.
- The Programme Effectiveness Team (PET) in the BHC will lead the delivery of this programme. The SRO (30%) and the PRO (50%) within PET will be responsible for agreeing a prioritised six-monthly work plan in consultation with the supplier and the programme teams, ensuring outputs are delivered on time, quality assuring the final reports and feeding back results to teams. The team will be supported by an in-house Social Development Advisor (10%) and an Economist (10%).
- The programme teams will be responsible for following up to ensure timely completion of the recommendations coming out of the reviews.

Management Arrangements
104. The programme will be implemented by BHC through a consortium of an international commercial supplier and a national NGO with strong expertise in portfolio risk assurance, value for money and safeguarding. The PET within BHC will facilitate the coordination between the supplier and programme teams through regular review of progress against agreed actions.

Phases of the programme:

Inception phase
105. The programme will have an inception phase of three months to fully streamline the communication with the implementing partners and embed the management arrangements. During the inception period, reporting arrangements would be agreed with the Implementing partner which includes six-monthly costed workplan, budget for the financial year and delivery mechanism. The workplan will be developed in consultation with programme teams based on their needs for support. This will allow further in-depth design work and results identification. BHC’s interaction with the partner organisation will be through formal fortnightly and quarterly meetings with the partner including representatives from the international partner and national NGO.

Implementation phase
106. During the implementation phase, the programme is expected to deliver the results as agreed with the partners during the inception phase. The implementation plan and priorities will be agreed on a six-monthly basis, with quarterly updates, following the annual review of the programme. Programme delivery will be based on a clear strategy and implementation plans.

Programme Exit:
107. The final year of the programme will focus on sustainability of the support provided over the years. The focus will be consolidation and closure of on-going support and capacity building of BHC staff for coming years in absence of external support provided by a successor programme to PRAP III. The knowledge products produced during the implementation of the programme will be proactively shared with the programme teams. Similarly, refresher training sessions will be organised after the exit of the programme for both FCDO staff and delivery partners to retain the knowledge and build capacity of new staff / partners.

Division of roles and responsibilities
108. The division of roles and responsibilities will be as follows:

Implementing Partners ’s Responsibility:
109. The Implementing partner will be responsible for carrying out on demand reviews for bilateral programmes listed on an agreed plan with the programme teams and building capability of BHC team in VFM and managing safeguarding risks. The performance will be managed by the PET team in line with the needs identified by programme teams. The supplier will be responsible for drafting the TORs for each review and proposing a team of experts in line with the requirement, set out the data and information required, carry out field activities and keep BHC up to date on progress. Similarly, the partner will work closely with the BHC to design and deliver the capability plan across programmes.

Programme Effectiveness and Transparency Team:
110. The Programme Effectiveness and Transparency Team in the BHC Islamabad under Data Evidence Portfolio Assurance (DEPA) group, will lead on the implementation of this programme. The SRO and PRO will be responsible for:

- Agreeing a prioritised work plan to ensure that PRAP III is supporting only those activities that cannot be completed internally;
- Commissioning reviews;
- Ensuring outputs are delivered on time;
- Quality assuring the final reports and feeding back results to teams;
- Holding SROs responsible for taking forward remedial actions;
- Keeping track of progress against VFM & Safeguarding framework; and
- Assessing the collective impact of the reviews undertaken and sharing lessons and findings with the wider office with help from the implementing partner.

Individual Team Responsibilities
111. Programme teams will be responsible for tailoring the scope of individual programme reviews to ensure that issues assessed by each review meet the needs of the relevant programme and that the reviews are informed by the latest developments on the ground.

112. The programme team will be responsible for managing the relationship between the PRAP III team and their programme partners, for example making sure partners understand why the review is taking place, how findings will be shared, facilitating access to the organisation undergoing the review, and being present during other key moments. The final report from each review will be shared with the PRAP II SRO, who will then share it with the appropriate SRO and programme team or in case of a piece of work that cuts across office/portfolio respective individuals/teams will be notified.

113. The relevant SRO/teams will be responsible for following up on the recommendations of the review and ensuring the implementation of any action plan.

114. To ensure high quality commercial outcomes, BHC will:

- Hold fortnightly meetings with the supplier to monitor progress of ongoing activities, followed up by an updated activity log from the supplier which will be circulated to all relevant programme teams;
- Monitor programmatic and financial performance through annual reports; and
- Conduct Annual Reviews to assess performance against targets.

115. BHC will put in place, a risk management framework with specific responsibilities for both BHC and implementing partners for managing and mitigating risks, which will be monitored through the contract implementation.

Risk Management
116. The overall rating for the programme is assessed as moderate. BHC Islamabad will ensure that the risks in the programme are carefully monitored and managed in line with PrOF guidelines and FCDO Risk Management Policy. Risks in the programme will be reviewed on a monthly basis and compared to the programme level risk appetite with risks escalated if they are outside the programme risk appetites. The detailed matrix (see Annex) shows the risks that are relevant to the programme, possible mitigating measures and residual risk rating for each category of risk, however, the risks will be reviewed in detail to develop a risk register during the inception phase of the programme. The risk appetite for PRAP III is aligned with the approved BHC risk appetite and will be reviewed at least annually in line with the FCDO Risk Management Policy. The table below shows the risk appetite of BHC and PRAP III programme for each of the seven categories:

Category	Pakistan Network Appetite	PRAP III Appetite
Strategy and Context	Eager	Receptive
Policy & Programme Delivery	Eager	Receptive
Public Service Delivery and Operations	Receptive	Cautious
Financial and Fiduciary	Receptive	Cautious
Safeguards	Cautious	Minimal
Reputational	Cautious	Cautious
People	Cautious	Cautious

Monitoring and Evaluation
117. A robust monitoring framework will be developed during the inception phase and will be tracked by the SRO and PRO during the implementation of the programme to assess progress and performance against the log frame.

118. The progress against the agreed milestones will be monitored on the conclusion of each review and assessments made by the programme teams. Value will be judged on whether the suggestions and recommendations made through the review are followed up by programme partners and internally via BHC programme staff.

119. The programme against the agreed workplan will be reported on quarterly basis. The quarterly reports will include a narrative description of progress as well as a financial report against agreed forecast and spend during each quarter. The quarterly narrative reports will clearly document the progress against agreed means of verification and key performance indicators.

120. The programme progress will be reviewed annually through mandatory Annual Reviews (ARs). The ARs will independently review progress against log frame and agreed quarterly milestones. The ARs will assess the progress against agreed VFM and Monitoring frameworks put together during inception phase of the programme. In addition, the ARs of other programmes will be quality assured by the PET team to ensure that learning form the programme is reflected in tracking VFM and managing the safeguarding risks.

121. Overall, the PRAP III’s effectiveness depends on how proactively the programme teams use this facility and follow up on recommendations to manage risks. There is no dedicated evaluation component of the programme, however, the process and performance will be assessed through the ARs to improve the impact of the programme’s activities. Through the ARs, the programme team will assess how the capacity of staff and implementing partners has improved, enabling them to better identify, mitigate and mange risks. The impact of this support will also be monitored through regular monthly management reviews to determine how effectively the risks have been mitigated.

Sustainability
122. PRAP I and II prioritised building capacity of BHC staff. As a result of the improved capability, it was no longer necessary for the PRAP programme to directly carry out or track due diligence assessments in the last three years. Although risk management is carried out in-house PRAP has provided an excellent independent resource to programme teams providing technical expertise on fiduciary risk management and control and reviewing programme delivery in locations that are inaccessible to BHC staff. Going forward, the capacity building component of the programme under PRAP III will focus on delivery partners and improving value for money and managing safeguarding risks.

123. The sustainability will be achieved through engagement of programme teams in commissioning the reviews, monitoring the progress, taking ownership of the recommendations and follow up. The final year of the programme will mainly focus on sustainability through capacity building of delivery partners and staff as well as putting systems in place to sustain the impact of PRAP III. For example, the implementing partner will be required to develop a bank of VFM indicators suited for the TA programmes. Similarly, a framework will be developed to ensure effective implementation of safeguarding polices by implementing partners working at all levels.

Safeguarding
124. Through PRAP III, we intend to develop a mechanism for a third-party review and assessment of the safeguarding systems. This will allow us to identify the risks at an early stage and undertake mitigation measures. Specifically,

- PRAP can assess the capacity and capability of our partners on safeguarding policy, how is it being implemented and suggest recommendations.
- PRAP can follow up on progress of those recommendations. If required, PRAP can also offer extra safeguarding support and training.
- We will ensure that PRAP III role is not investigative. Any investigations will be done by implementing partners with support from safeguarding team.

Annex: DRAFT PRAP III Risk Register (to be finalised during the inception phase)

Description of risk	Probability	Impact	Overall	Mitigating Action	Probability	Impact	Overall
Brief description of the risk	Identify the likelihood of the risk materialising using the 5 risk ratings	Identify the impact of the risk materialising using the 5 risk ratings	Identify the overall risk using the 5 risk ratings	List associated controls and mitigation action	Identify the likelihood of the risk materialising using the 5 risk ratings	Identify the impact of the risk materialising using the 5 risk ratings	Identify the overall risk using the 5 risk ratings
Public Service Delivery & Operations: SROs neglect usual due diligence practices and become complacent due to PRAP III activities.	Possible	Major	Major	Use PRAP to highlight common issues and gaps and develop checklist of key things SROs accountable for. Remind SROs/PROs of their responsibility. Manage expectations of team in terms of how much PRAP III can support.	Unlikely	Moderate	Minor
Public Service Delivery & Operations: Duplication of work with other BHC processes	Possible	Major	Major	The reviews will only be done when it will add value out with BHC processes. The PRAP SRO will review each demand on a case-by-case basis to ensure BHC processes are undertaken by teams and that when reviews are undertaken by Implementing Partners, there is a clear need to do so to ensure value for money.	Unlikely	Moderate	Minor
Policy & programme delivery: Travel restrictions stop reviews from proceeding - this could be triggered by a rise in yet another wave of or worsening security situation or pause on budget.	Possible	Major	Major	The contracted firm should be fully vaccinated in order to use local office/partner to make travelling throughout Pakistan more feasible and they have explored how to operate reviews virtually. / All partners will access to security assessments by BHC. / Programme plans will be flexible enough to scale up and down in case budget constraints.	Possible	Major	Major
Strategy & Context: worsening political and/or economic situation could mean that implementing Partners are unable to undertake work.	Possible	Moderate	Moderate	Implementing Partners are undertaking work virtually where possible and communicated to partners where field work is not possible and re-scheduled work. Continue to monitor work plan and situation has improved where they have been able to support a number of teams virtually until the situation gets improved.	Unlikely	Moderate	Minor
Reputational: Reviews identifying high risks are reported by the media - this could be triggered by sharing the findings too widely.	Likely	Major	Major	All reviews will be treated as confidential documents and findings will not be released publicly.	Unlikely	Minor	Minor
Public service delivery & operations: Perception of interfering with programmes - this could be triggered by poor communication.	Likely	Major	Major	Clearly explaining at the start of each review what PRAPs role will be. programme teams (SRO/PROs) will be fully involved in each stage of the process and will involve partners in action planning to make any actions collaborative with PRAP’s Implementing partners. Use key government meetings to stress this.	Possible	Moderate	Moderate
Fiduciary: Risk that expenditure does not represent value for money for FCDO	Possible	Major	Minor	All procurement under the programme will be conducted using FCDO’s procurement rules. Value for money assessments of the project will be conducted as part of its annual reviews. / Ensuring scope of work under the programme is based on demand from programme teams.	Unlikely	Major	Minor
People: Lack of capacity/buy in from programme partner or team to help facilitate reviews, causing delays.	Possible	Major	Major	Clear communication of what is expected and realistic timelines in ToRs. Any delays communicated in advance and added in the PRAP Activity log.	Unlikely	Major	Moderate
Public service delivery & operations: Scope of reviews could include private sector companies who are competitors of the supplier or the supplier themselves could be working for BHC on the programmes that need to be audited. This could present a conflict of interest.	Possible	Major	Major	Robust conflict of interest policy is drawn up between BHC and supplier and is reviewed on an annual basis. Suppliers declare any conflict of interest at the start of reviews and ensure the teams who work on PRAP do not work on any work related to the partners reviewed. A COI tracker is kept and discussed at each progress meeting.	Unlikely	Major	Moderate
Safeguarding: Sexual exploitation, abuse or harassment of staff, or beneficiaries, especially during community engagements	Possible	Major	Major	- Policies and procedures to expressly prohibit exploitation and abuse including whistleblowing of such acts are in place. - Trainings of partners on safeguarding and spot checks are conducted during field visits. / - Implementing partners briefed on safeguards and zero tolerance policies on harassment. / - Partners to promote principles of non-discrimination, Do No Harm and safeguarding.	Possible	Minor	Minor