## Annual Review Template

Title: UN Population Fund (UNFPA) Core
Programme Value £ (full life): £40,25m		Review date: 29/06/2025
Programme Code: 301478	AMP start date: 29/03/2023	AMP end date: 30/09/2025

Summary of Programme Performance
Year	1	2
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	D0002977.odt
DevTracker Link to results framework:	D0005551.xlsx

Acronyms

ERM	Enterprise Risk Management
FCDO	Foreign Commonwealth and Development Office
GNI / HNAP	Gross National Income / National Adaptation Plan for Health
HTF / ICPD / NDC	Humanitarian Thematic Fund / International Conference on Population and Development / Nationally Determined Contributions
ODA / OIOS	Overseas Development Assistance / Office of Internal Oversight Services
OPT	Occupied Palestinian Territories
PCR	Project Completion Review
PSEAH	Protection from Sexual Exploitation, Abuse and Harassment
QCPR	Quadrennial Comprehensive Policy Review
SDG	Sustainable Development Goal
SRHR	Sexual and Reproductive Health and Rights
UNFPA	United Nations Population Fund
VfM	Value for Money

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The UK’s core contribution to the United Nations Population Fund (UNFPA) provides flexible, unearmarked funding to advance the rights and empowerment of women and girls globally. Through this support, UNFPA is able to deliver on its mandate to promote universal access to sexual and reproductive health and rights (SRHR), including access to contraception, safe pregnancy and childbirth, and protection from gender-based violence and harmful practices.

UK funding enables UNFPA to make progress towards its three transformative results: (1) ending the unmet need for family planning; (2) ending preventable maternal deaths; and (3) ending gender-based violence and harmful practices, including female genital mutilation and child, early and forced marriage. These objectives are closely aligned with the UK’s renewed commitment to its international development priorities, which include empowering women and girls and promoting global health equity.

The UNFPA Core Programme business case was approved in December 2022 with an initial value of £24 million, and following approval by Ministers, was increased to £40.25 million via two business case addendums:
- The first business case addendum approved in the first quarter of 2024, providing additional funding of £4.25m to UNFPA’s humanitarian response in the Occupied Palestinian Territories (OPTs). Funds were deployed rapidly and allocated to UNFPA’s humanitarian appeal to support SRHR services in the OPTs.
- In November 2024, Ministers approved an additional £6 million to uplift UNFPA’s core funding as part of a one-off support package. Within the same addendum, Ministers allocated a further £6 million to the Humanitarian Thematic Fund (HTF). The HTF provides rapid, flexible funding to support UNFPA’s response in underfunded or emerging humanitarian crises. Whilst the HTF funding was disbursed in March 2025, the disbursement of the core funding uplift is currently delayed. Results from these allocations will be captured in UNFPA’s next reporting cycle and assessed in the Project Completion Report (PCR).

The programme received an ‘A’ score in its first annual review, reflecting strong performance and alignment with UK development priorities.

Summary supporting narrative for the overall score in this review [1-2 paragraphs
The UNFPA Core Programme has been awarded an overall score of A, reflecting strong delivery across its strategic outputs despite a challenging global context. In 2024, UNFPA achieved or exceeded most output-level targets. Output 1 (Policy and Programme Delivery) and Output 3 (Expanded Partnerships for Impact) both performed strongly, with Output 3 exceeding expectations. Output 2 (Organisational Effectiveness and Efficiency) was revised down to a B due to delays in investigation case closures and partial achievement of some milestones. However, the organisation made notable progress in risk management and internal reforms, including the rollout of a revised Enterprise Risk Management (ERM) policy and improvements in recruitment efficiency.

Major lessons and recommendations for the year ahead [1/2 page]
UNFPA should engage in the UN80 processes, articulating a clear vision for how it can best fulfil its mandate. UNFPA should prioritise fostering collaboration across agencies, reducing duplication and improving responsiveness to contextual challenges. Continued leadership and innovation in their areas will be crucial to ensuring that UNFPA is adaptable, fit for purpose and continues to achieve its aims in the evolving international landscape.

Whilst the organisation has taken positive steps to improve operational efficiency and broaden its funding base, these efforts are unlikely to fully compensate for the decline in traditional donor resources. UNFPA should strengthen its resource mobilisation strategy, developing a more strategic and sustainable approach to financing in the next strategic plan, with a focus on securing and transitioning to domestic resources. Learning lessons from the supplies partnership success on domestic resource mobilisation, UNFPA should rollout further mechanisms that can support domestic resource pathways for accelerated transition. Donor financing remains a critical element of the financing mix for the medium term and UNFPA is encouraged to continue strengthening its financial resilience in response to a challenging and uncertain funding environment.

UNFPA should ensure that the findings of the Mid-Term Review of the Strategic Plan (2022-2025) and the 2024 MOPAN assessment are fully reflected in the design and prioritisation of its future programming. These assessments provide critical insights into organisational performance, effectiveness, and strategic alignment. FCDO recommends that UNFPA continues to use this evidence to inform the development of its next strategic plan, strengthening its results framework, delivery model, and accountability mechanisms.

UNFPA must play a key normative role as part of global debates around demography, particularly as relates to pointing out the dangers of talking about ‘too many’, or ‘too few’, as they set out in their 2023 State of the World Population Report. However, the UK shares the concerns of other Board Members about adding this as a fourth transformative result, without a more formal proposition of what a transformative result would look like on this subject.

Whilst an investigation has now concluded into allegations concerning UNFPA’s Executive Director and found no evidence of wrongdoing, FCDO recommends that UNFPA along with Office of Internal Oversight Services (OIOS) ensure full transparency to member states. FCDO also recommends that UNFPA provide regular updates on the leadership transition process, including progress on the recruitment of a new Executive Director, to maintain donor confidence and institutional credibility.

Delays in disbursing the £6 million core funding uplift and the £6 million allocation to the HTF, both approved in late 2024, have impacted financial planning. These delays are due to the absence of signed agreements following the Foreign Secretary’s announcement to reduce ODA to 0.3% of GNI. It is recommended that agreements for both funding streams be finalised by July 2025 and that a time extension to the business case be approved to enable UNFPA to utilise the remaining funds effectively, taking the programme beyond its original scheduled end in September 2025.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]
The UNPFA Core programme’s impact is framed around UNFPA’s three transformative results. Achievement of these transformative results is instrumental in driving progress towards several key Sustainable Development Goals (SDGs), particularly SDG 3 (Good Health and Well-being), SDG 5 (Gender Equality), and SDG 10 (Reduced Inequalities).

At outcome level, the programme contributes to achieving economic growth, poverty reduction and social development. Progress towards these outcomes is measured by:
1. Increased support from a broader donor base
2. UNFPA providing effective leadership on SRHR, GBV, and data across development and humanitarian
3. Accelerated normative and operational results by UNFPA.
UNFPA's theory of change outlines 3 specific outputs that are essential for achieving its strategic outcomes. These outputs represent the immediate results of UNFPA's activities and interventions, and they serve as critical steps towards achieving the wider goal of achieving universal access to SRHR.

Figure 1: UNFPA's Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Impact
2024 marked the thirtieth anniversary of the international conference on population and development (ICPD). The ICPD Programme of Action, which UNFPA is responsible for delivering, has served as a catalyst for expanding rights and choices and has reinforced the centrality of human rights, gender equality, and population dynamics in sustainable development. The anniversary was a moment for UNFPA to take stock of progress (results below) and reflect on lessons learned.

- Between 2000 and 2023, the number of women dying from preventable complications of pregnancy and childbirth declined by 40 per cent;
- Since 2000, the number of girls (aged 15-19 years) giving birth has dropped by more than a third;
- Since 1990, the number of women using modern contraceptives has doubled;
- Since 1994, the unmet need for family planning for any method has decreased by 20 per cent worldwide;
- Adolescent girls have reached parity with boys in primary school enrolment, and now exceed boys in post-secondary enrolment;
- Between 2000 and 2022, the estimated HIV global incidence rate has declined from 0.48 to 0.17;
- Between 2000 and 2021, the universal health coverage index, which measures service coverage, increased globally by 41 per cent.
Table 1: Progress towards impact indicators
Impact Indicator	2023	2024	2024 log frame milestone	By 2030
1 – Annual rate of reduction of unmet need for family planning	Stagnated	Stagnated	9.5%	34%
2 – Proportion of women and girls subjected to physical, sexual or psychological violence	12.5% (2018 data)	12.5% / (2018 data)	8%	>1%
3 – Annual rate of reduction in maternal mortality	Not available	Not available	5%	20%

As demonstrated in Table 1, UNFPA have not provided any update to their data on progress towards outcome indicators for the duration of this business case. The absence of updated 2024 data in the UNFPA scorecard for key indicators such as the annual rate of reduction of unmet need for family planning, proportion of women and girls subjected to violence, and maternal mortality reduction can be reasonably justified by several factors, namely that:

- These indicators rely on large-scale population-based surveys and national health information systems, which are not conducted annually in many countries, instead this is updated every 2-3 years.
- They require extensive time for data collection, cleaning, validation, and analysis and often have a lag between data collection and publication.
- Additionally, the nature of the indicators means they require a multi-year trend analysis as they change gradually over time, rather than year to year.
However, ongoing trends can be interpreted from UNFPA’s 2024 scorecard:

Impact indicator 1: While the overall demand for family planning hasn’t changed since 2021, more women, especially in the least developed countries, are now using modern contraceptive methods. This shows progress in giving women better access to family planning, which is key to their health and empowerment. UNFPA have supported progress here by:
- Supporting a 7% increase in donor funding for family planning between 2022 and 2023.
- Helping over 24 countries get access to new or less common reproductive health supplies.
- Ensuring all 54 high-priority countries had plans in place to manage supplies.
- Supporting over 80 countries in running effective logistics systems for reproductive health products.

Impact indicator 2: Globally, 12.5% of women aged 15-49 who have ever been in a relationship experienced physical and/or sexual violence from a partner. While data remains limited, several countries have reported notable progress in tackling gender-based violence.
As of 2024:
- 78.8% of countries have legal frameworks addressing violence against women.
- Around 75% of countries have laws ensuring full and equal access to sexual and reproductive health care, information, and education

Impact indicator 3: Since 2000, the global maternal mortality ratio has fallen by over 40%. Although maternal deaths temporarily rose during the COVID-19 pandemic, recent data show a reversal of that trend. In the least developed countries, maternal mortality has been cut by more than half. Notably, for the first time, no country is classified as having an ‘extremely high’ maternal mortality ratio, marking a major global milestone. In 2024, several countries introduced initiatives to scale up the reduction of maternal deaths in the UNFPA strategic plan, 2022-2025. For example, Moldova enhanced the resilience of seven perinatal hospitals near the Ukrainian border; this resulted in the safe delivery of more than 15,000 newborns.

Outcomes
Despite some success, further progress on sexual and reproductive health and rights has been very challenging, in part this is due to ongoing crises (health pandemics, conflict and climate-related crises) but also because SRHR faces an ever-growing pushback. Progress on the two indicators tracked at outcome level in the logframe has also been challenging. No progress was reported towards increasing the proportion of women who make their own informed decisions around SRHR, with the 2023 and 2024 rates remaining at 56%. No new data is available to illustrate any progress towards Outcome Indicator 2. The most recent data is 76 countries in 2022.

Outcome Indicator	2023	2024	2024 log frame milestone	By 2030
1 – Proportion of women who make their own informed decisions regarding sexual relations, contraceptive use and reproductive health care	56%	56%	60%	90%
2 – Number of countries with laws and regulations that guarantee full and equal access to sexual and reproductive health care, information and education	No data available	No data available	78%	85%

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The UNFPA Core Programme should continue through to its planned end date of September 2025. Despite a difficult external context, the programme has made progress on most outputs, with some slower progress on others, with all three outputs scoring A, B and A+ respectively in 2024. These scores reflect UNFPA’s effective delivery across policy and programme implementation, organisational efficiency, and expanded partnerships. Notably, Output 3 exceeded expectations, demonstrating UNFPA’s ability to drive operational efficiency, delivering key reform objectives and leveraging thematic funding despite a challenging financial environment.
While progress on impact and outcome indicators has been constrained by data availability and the nature of long-term change, the programme continues to show meaningful contributions to the three transformative results. UNFPA’s leadership in safeguarding, decentralisation, and humanitarian response has been particularly impactful, and it has continued to position itself as a resilient and adaptive partner. In 2024, UNFPA fully achieved all six outputs in their current strategic plan. In addition, UNFPA reported the highest output-level performance to date in 2024.
The programme faces new, and critical external challenges, including significant funding cuts and the withdrawal of USAID funding, which have increased pressure on UNFPA’s financial sustainability. Additionally, the £6 million uplift to core funding approved in November 2024 has not yet been released, and delays in disbursement risk undermining delivery in the final months of the programme. Given that the business case is due to conclude in September 2025, it would be inefficient and counterproductive to end the programme prematurely, particularly when the final tranche of funding is already approved and aligned with strategic priorities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Policy and Programme Delivery - UNFPA core delivers with high ambition to meet UNFPA’s strategic aims ensuring progress towards universal access to sexual and reproductive health & rights
Output number:		1	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
INDICATOR 1.1: Proportion of countries that have integrated sexual and reproductive health and reproductive rights and Programme of Action of the International Conference on Population and Development priorities into the national climate policies.	35%	Met: 2024 actuals: 34%
INDICATOR 1.2: Proportion of countries that have a mechanism where women, adolescents and youth have access to a safe and accessible channel to report sexual exploitation and abuse (PSEA)	41%	Exceeded: 2024 actuals: 89%
INDICATOR 1.3: Proportion of countries affected by humanitarian crisis that have a functioning inter-agency coordination mechanism or platform to address sexual and reproductive health and reproductive rights	75%	Exceeded: 2024 actuals: 80%
INDICATOR 1.3.1Number of Inter-Agency Reproductive Health Kits Delivered in the OPTs through UK funding	762	Not met: 781 Inter-Agency Reproductive Health kits were procured with UK funding. Of these, 88 kits were distributed to health facilities.

Briefly describe the output’s activities and provide supporting narrative for the score.
UNFPA has made strong progress under Output 1 in 2024, with three indicators exceeding targets and one narrowly missing. The output continues to drive inclusive, rights-based programming across development and humanitarian contexts.

UNFPA supported governments to integrate SRHR into climate policies, effectively meeting the 35% milestone (actual: 34%). UNFPA’s technical support, advocacy, and data tools have positioned it as a key actor in gender-responsive climate action. Climate change is being mainstreamed into all of UNFPA’s work with ccountry programme documents routinely integrating climate change resilience strengthening interventions.

UNFPA worked on advocacy and technical guidance, for example working with Queen Mary University conducting a regional review of Nationally Determined Contributions (NDCs). The report analyzed 119 countries across the regions of UNFPA with the findings launched in May 2024 on the sidelines of the African Population Conference in Malawi ahead of COP 29: Taking Stock: Sexual and Reproductive Health and Rights in Climate Commitment. This evidence-based approach was then used to advocate directly with national governments, for the inclusion of SRHR in their climate policies. UNFPA also provided technical assistance and guidance to government ministries responsible for developing and updating NDCs and other climate strategies and capacity to ensure they address the SRHR dimensions of climate change.

A key example of this is UNFPA’s work in Bangladesh. The country office has positioned SRH in the Bangladesh National Action Plan by supporting the Ministry of Health in the development of a National Adaptation Plan for Health (HNAP) for Bangladesh. This is part of UNFPA Bangladesh's overall drive to strengthen the national health system by building resilience to the ongoing climate crisis. UNFPA has also taken the lead in developing modules on climate change and SRHR for different groups of health-care providers. Through this initiative, 300 providers were trained in two sub-districts of Bangladesh. The module for nurses and midwives is also being integrated into the government’s formal training on Nursing and Midwifery.
Over the course of the reporting period, UNPFA have substantially exceeded their set milestone on indicator 1.2, with their final figure more than doubling the set milestone. The main deliverable this year was launch of the first Strategy on Protection from Sexual Exploitation, Abuse, and Harassment (PSEAH). This included new reporting systems, training, and a pilot misconduct disclosure scheme, reinforcing UNFPA’s leadership in safeguarding.

UNFPA also exceeded its target for inter-agency coordination in humanitarian settings (80% vs. 75%). Between 2021 and 2024, UNFPA strengthened the link between its development and humanitarian work, ensuring it could respond quickly and effectively to crises. Due to its strong field presence and partnerships, especially with women and youth-led organisations, UNFPA remained active before, during, and after emergencies.

At the global level, UNFPA coordinated closely with partners through key platforms like the Inter-Agency Standing Committee and the Joint Steering Committee on Humanitarian-Development Collaboration. On the ground, collaboration with UN agencies, NGOs, and local authorities helped deliver integrated support.

In 2024, a total of 781 Inter-Agency Reproductive Health (IARH) kits were procured with UK funding. Of these, 88 kits were distributed to health facilities in Gaza, supporting access to sexual and reproductive health services for 11,777 women. The effective delivery of medical supplies was significantly hindered by the ongoing humanitarian aid blockade. The delays in distributing these kits arose from the context which UNFPA was operating in, resulting in them missing this milestone. UNFPA continue to monitor the situation, delivering supplies when access allows. In 2025, UNFPA procured an additional 25 IARH kits and continued distribution efforts, successfully delivering another 60 kits across the West Bank and Gaza. However, access corridors to Gaza have been closed since 2 March 2025, delaying the dispatch and distribution of the remaining kits. These will be delivered once operational access resumes. UNFPA continue to coordinate with other humanitarian actors as well as diplomatic efforts to resume humanitarian efforts.

Whilst this milestone was missed UK funding contributed to other areas of the humanitarian response more successfully. In the Gaza Strip, despite the ongoing conflict, over 90 per cent of births occurred in health facilities, supported through coordinated delivery of the Minimum Initial Service Package. Across the Gaza Strip, mobile health and midwifery teams reached over 25,000 women in shelters with antenatal, postnatal, family planning, STI consultations, and psychological support. Facility-based lifesaving services such as safe deliveries and gynaecological procedures benefited more than 6,000 additional women and girls. New mothers and newborns received postpartum kits with tailored items to help meet essential hygiene and care needs. UK funding supported the health and protection of women and girls across the OPTs. UK funding also supported GBV survivors and women at risk through enabling GBV safe space service provision in addition to facilitating the distribution of dignity kits containing menstrual health and hygiene items for women and girls in Gaza promoting health, reducing risks, and preserving dignity during a time of severe local shortages of these items.

In the West Bank, UK funding strengthened national preparedness by equipping ambulances and personnel with emergency delivery kits and training, helping ensure lifesaving support to emergency childbirths amid movement restrictions and insecurity. Youth-friendly health services reached over 15,000 young people, complemented by peer-led education and digital platforms and helplines, reaching thousands of youth with counselling and information on adolescent health and rights etc.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Output Indicator 1.2 Removed: The indicator tracking UNFPA’s work on rights-based comprehensive SRHR was removed to streamline reporting and ensure consistency with the outputs presented in UNFPA’s annual report. This area is now monitored through the FCDO’s UNFPA Supplies logframe.

New Humanitarian Indicator Added: In line with the recommendation from the previous Annual Review, a new FCDO-specific output indicator was introduced to track the progress and impact of earmarked humanitarian funding in the Occupied Palestinian Territories. This allows for more targeted monitoring of UK support in crisis-affected settings.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from the 2024 Annual Review	Progress
UNFPA should prioritise efforts to assess the proportion of countries increasing domestic resources towards SRH and ending GBV and leverage results to inform future domestic resource mobilisation strategies, including through building staff capacity and learning from successful examples of innovative approaches to mobilise domestic resources such as the UNFPA Supplies Match Fund.	Ongoing: In 2024, UNFPA continued to advocate for increased domestic investment in SRHR through its global and regional programmes. These efforts included technical support to governments to integrate SRHR and GBV prevention into national health policies and financing frameworks.
UNFPA should continue its successful efforts to normalise Comprehensive Abortion Care including through issuing its operational guidelines as a part of a broader set of actions towards fulfilling its mandate on comprehensive SRHR	Complete. UNFPA have continued to strengthen its work on Comprehensive Abortion Care. In 2024 the work grew to include 11 countries in East and Southern Africa, 6 countries in West and Central Africa and 17 countries across Latin America and the Caribbean. A few key highlights of this work include: / 369 facilities supported across three UNFPA regions / 3,219 healthcare providers trained on CAC / 1035 healthcare providers trained on VCAT / 5 countries where CAC/PAC has been integrated into the HMIS / 4 countries conducting strategic assessments and other operational research
UNFPA should continue to strengthen its approach to preventing sexual exploitation, abuse and harassment (PSEAH) as a priority, working closely with the FCDO, other member states, programme countries, partners and UN agencies in developing and implementing the upcoming 2-year PSEAH strategy. UNFPA has enhanced its technical and thought leadership on PSEAH and should focus on improving implementing partner capacity on PSEAH as a priority.	Complete. The first ever UNFPA two-year PSEAH Strategy was launched in July 2024. This two-year strategy is a critical milestone for UNFPA to meet their obligation to maintain a safe, protective and respectful workplace for all their personnel and the communities they serve.
UNFPA and the FCDO should thoroughly review the log frame and update Output 1.1 and 1.2 and its milestones. UNFPA. The FCDO should also ensure that this reflects its spend in 2024 towards UNFPA’s humanitarian response in the Occupied Palestinian Territories	Complete. Details of log frame changes set out in paragraph above on changes to output .

Output Title	Organisational Effectiveness and Efficiency - UNFPA Core funding is underpinned by a robust operational and governance model with strong risk mitigation controls providing assurance to donors
Output number:		2	Output Score:	B
Impact weighting (%):		33%	Weighting revised since last AR?	Yes, revised down from an A

Indicator(s)	Milestone(s) for this review	Progress
INDICATOR 2.1: / Proportion of new country programmes that meet organisational quality standards for the criteria of “strategic direction” / Proportion of new country programmes addressing the rights of persons with disabilities	a) 82% / b) 90%	Partially met: / a) 78% / b) 89%
INDICATOR 2.2: / Average recruitment time: / Organisational / Humanitarian-funded positions	a) 90 days / b) 70 days	Met: / a) 76 / b) 71
INDICATOR 2.3: Proportion of UNFPA country offices, with validated risk assessments, that have approved risk response action plans by the head of the office within three months of validation.	75%	Milestone not recorded due to change in process. With the implementation of the new Enterprise Risk Management (ERM) policy, country offices are no longer required to conduct an annual risk assessment by default. Instead, the need for a risk assessment is now determined based on specific criteria, with a minimum requirement of at least one assessment per country programme. For the year 2024, the designated business units conducted risk assessments and developed corresponding risk response plans. These assessments and response designs were subsequently reviewed and validated by the regional risk committee.
INDICATOR 2.4 Robust processes and controls are in place to mitigate risks during last mile distribution providing donors with assurance	40 in-country assessments are completed by the Last Mile Assurance Team (2023 LMA cycle), and all recommendations from the in-country assessments are taken forward in a timely manner.	Partially met: In 2024, UNFPA conducted 37 in-country assessments
INDICATOR 2.5 Average lead time for the investigation of high priority cases related to fraud, misconduct and wrongdoing (from receipt to closure).	24 months	Not met: In 2024, high priority cases were closed 35 months after receipt.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 2 focuses on improving internal systems and processes, to ensure that UNFPA can operate effectively and efficiently. Overall, UNFPA has demonstrated strong performance in 2024 in strengthening internal systems and processes. The organisation received a positive assessment from the 2024 MOPAN review, with 52 out of 57 micro-indicators rated as satisfactory or highly satisfactory.

In 2024, 9 country programmes were reviewed to assess their alignment with organisational quality standards and disability inclusion. The percentages outlined within the 2024 progress against milestones (78% and 89% retrospectively) reflects the initial quality score, before UNFPA’s internal quality assurance process. It is important to note that after this review, 100% of country programmes meet the required standards before being submitted to the Executive Board.

Recruitment efficiency improved significantly, with the average lead time reduced to 76 days, well below the 90-day target. Vacancies are advertised on UNFPA’s website and local posts outside HQ are advertised locally. After the closing date, all applications are reviewed against job specifications and a number of candidates are shortlisted for assessment. Candidates are evaluated by means of a competency-based interview and this may then be supplemented by additional assessment tools. The candidates’ references and academic qualifications are reviewed and verified, before the selection report and hiring recommendation are submitted to the Compliance Review Board.

UNFPA has made notable progress in strengthening its enterprise risk management (ERM) systems, as documented in the 2024 MOPAN assessment. UNFPA launched its first formal ERM policy in April 2022. The policy integrates oversight functions across the organisation and has been accompanied by measures to strengthen accountability, transparency, and responsible decision-making. The establishment of more robust and independent oversight mechanisms has further reinforced UNFPA’s risk governance framework. In 2024 UNFPA continued to embed the ERM policy across its network. A key development was the refinement of risk ownership structures, with clearer roles and responsibilities assigned to country, regional, and HQ teams.

UNFPA also made substantial progress in audit and investigation, reducing the backlog of open cases and investing in new technologies and temporary staffing to support to Office of Audit and Investigation Service (OAIS). UNFPA has put in place benchmarks for the timely conclusion of investigations of PSEAH and is also among a handful of UN agencies that plan to supplement the ClearCheck system by piloting the misconduct disclosure scheme that includes the names of UN perpetrators as well as those from NGOs. However, despite significant improvements in this area, it took on average 35 months to close a high priority case in 2024. This misses their target by a significant 11 months.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
During the 2024 reporting period, Output 2 was adjusted to reflect significant improvements in UNFPA’s approach to risk management. At the time the original indicators were developed, UNFPA employed a standardised risk assessment process across all business units, using uniform risk factors that did not account for the specific operational contexts of different units. This approach proved to be time-consuming and insufficiently responsive to emerging risks.

In response to audit recommendations and internal reviews, UNFPA introduced a revised ERM policy in 2024. The updated policy includes a clearly defined risk appetite statement and a more dynamic structure for identifying and managing emerging risks. These changes have enhanced the organisation’s ability to tailor risk assessments to local contexts, improve efficiency, and strengthen accountability. As a result, this output was not scored as the previous milestone is outdated whilst waiting for the updated indicator from UNFPA. The FCDO programme team should update the logframe to better capture these institutional improvements and align with the evolving risk management framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

2024 Annual Review Recommendations	Progress
Building on successful operationalisation of the ERM approach and recommendations from the recent report of the Oversight Advisory Committee, UNFPA should continue to strengthen its risk management practices and capacity at country level and in particular on last mile assurance and investigations.	Complete. UNFPA have made significant improvements to their risk management policies and procedures as noted in the MOPAN assessment.
UNFPA should continue to strengthen its approach to Audit and Investigation including in the management of its cases. Although UNFPA’s OAIS closed a record number of cases last year, there is still a backlog of cases which UNFPA should prioritise concluding. UNFPA should prioritise implementing the recommendations set out by OAIS	Complete. UNFPA has continued to invest significantly in its OAIS, especially in investigations. In the 2022-2025 Mid-Term Review of its budget, UNFPA approved $2.7 million to strengthen OAIS. / This funding helped hire temporary staff to: / Clear the backlog of cases, / Handle the growing number of new cases, / And support the use of new technologies. / As of 31 December 2024, there were 283 open cases, down from 314.

Recommendations for 2025:
ERM Implementation: Continue embedding the updated ERM policy across all levels, with a focus on strengthening risk ownership and last-mile assurance at country level. Suggest new wording for Output indicator 2.3 in line with the refreshed risk management.

Audit and Investigation: Sustain investment in OAIS to fully clear the backlog of cases and maintain timely case management. Significant attention should be given to reduce the case completion time from 35 months.

Output Title	UNFPA Expanded partnerships for Impact Indicators
Output number:		3	Output Score:	A+
Impact weighting (%):		33%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
OUTPUT INDICATOR 3.1 Operational efficiency gains realised in USD	$8.5	$14.7m - exceeded
OUTPUT INDICATOR 3.2 Proportion of UNFPA offices in United Nations common premises (QCPR)	74%	79% - exceeded
OUTPUT INDICATOR 3.3 Proportion of UNFPA co-financing funded through pooled funds and thematic funding mechanisms: / (a) Pooled funds / (b) Thematic funding mechanisms	a) $187m / b) $140m	a) $141m – not met / b) $241m - exceeded

Briefly describe the output’s activities and provide supporting narrative for the score.

In 2024, UNFPA have made significant progress on strengthening partnerships. For example, the HQ optimisation process has meant the organisation has decentralised its operations to foster agility and build effective partnerships. It has delegated greater programmatic and financial responsibility to regional and country offices, enhancing its ability to respond to crises such as COVID-19 and improve partnerships and humanitarian actions. As part of its HQ Optimisation initiative, UNFPA is consolidating divisions and relocating many posts to Nairobi in order to bring the organisation closer to those it serves[1].
[1] mopan-unfpa-assessment-report-2025.pdf

Moreover, UNFPA has made progress on the management of the HQ optimisation process, creating a system to track how well the initiative is working. This system uses some existing performance indicators from the UNFPA Strategic Plan (2022-2025) and adds new ones to measure the impact of the new organisational structure. For risk management, UNFPA is carefully identifying and handling any risks related to this major organisational change. UNFPA has held regular breifings on the process giving transparent and informative sessions to member states as well as responding to questions and requests for more information.

UNFPA has continued to deliver on efficiency gains, exceeding the FCDO milestone for this review. UNFPA achieved an overall operational efficiency gain of $14.7 million. Of these gains, $7.6 million were generated from UNFPA-specific initiatives, $1.8 million were from bilateral initiatives with partner United Nations organisations, and $ 5.3 million through business operation strategies.

Expanding UNFPA’s presence in UN common premises supports greater coherence, efficiency, and collaboration across the UN system. Co-location of agencies facilitates joint planning, shared services, and integrated programming, particularly important in fragile and humanitarian contexts where coordination is critical. It also reduces operational costs through shared infrastructure and services, allowing more resources to be directed toward programme delivery. UNFPA has performed well, exceeding targets towards growing the proportion of UNFPA offices located within UN common premises.

UNFPA has made significant progress in co-financing through thematic funding mechanisms, exceeding the milestone target. However, pooled funding contributions fell short of the milestone, indicating a need for continued focus on diversifying and strengthening pooled funding channels.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No major changes to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

2024 Annual Review Recommendations	Progress
UNFPA should do more to proactively manage the change management process to realise a successful transition to a new structure for the programme division in 2024 and the longer-term relocation to Nairobi by September 2025. Risk management should include a dedicated approach to manage risks of continued staff attrition and impacts to staff wellbeing and morale during the transition period ahead. UNFPA should continue efforts to drive transparency and close collaboration with the Executive Board on the process, given the importance of a successful transition in continuing progress towards the transformative results at this critical time.	Complete. UNFPA created a system to track how well the HQ Optimisation initiative is working. This system uses some existing performance indicators from the UNFPA Strategic Plan (2022-2025) and adds new ones to measure the impact of the new organisational structure. / For risk management, UNFPA is carefully identifying and handling any risks related to this major organisational change. / A risk register (a list of potential risks) was created by the Enterprise Risk Management (ERM) Coordinator with help from the Project Coordinator. / The Chief Risk Officer oversees this process. / A risk matrix was also developed to show the risks during the transition and the expected results, along with actions to reduce those risks. / These risks are regularly reviewed, updated, and managed. / Risk management is a regular topic at the biweekly meetings of the Project Reference Group, which leads the HQ Optimisation project.
UNFPA should continue to champion efforts to strengthen UN efficiency and common business operations across its work, taking advantage of the leadership role it has played to date.	In progress. UNFPA is aligning its upcoming strategic plan (for 2026-2029) with QCPR priorities to ensure system-wide coherence and transformative results, scale up joint programming, and leverage strategic partnerships, including with other United Nations entities. Building on its leadership in UNDS reform, UNFPA continues to focus on achieving efficiencies, impact, and innovation, future proofing delivery in an increasingly complex and uncertain global environment[2].
[2] UNFPA Information note on UNDS reform 2025 - FINAL - 18Apr25.pdf

Recommendations for 2025
Pooled Funding: UNFPA should strengthen efforts to increase pooled funding contributions, including through enhanced donor engagement and alignment with joint programming priorities.

Transition Monitoring: Continue to monitor the impact of the HQ Optimisation initiative on staff wellbeing, programme delivery, and partnership effectiveness, ensuring lessons inform the 2026-2029 strategic plan.

UN Coherence: In line with the ambitions of UN80 and broader UN reform efforts, UNFPA should prioritise fostering collaboration across agencies, reducing duplication and improving responsiveness to contextual challenges. Continued leadership and innovation in their areas will be crucial to ensuring that UNFPA is adaptable, fit for purpose and continues to achieve its aims in the evolving international landscape.

## D: VALUE FOR MONEY (1 page)

This programme continues to provide strong value for money for the UK taxpayer. UNFPA has demonstrated a clear commitment to reform, operational efficiency, and delivery of results aligned with UK priorities on SRHR, gender equality, and humanitarian response. In 2024, the organisation exceeded its efficiency targets, strengthened internal systems, and maintained a strong focus on equity and safeguarding. These achievements are particularly significant in the context of a constrained global funding environment and the recent withdrawal of USAID core funding. UNFPA’s ability to adapt, decentralise, and deliver measurable impact with fewer resources reinforces its position as a strategic and cost-effective multilateral partner for the UK.

Economy: UNFPA continues to demonstrate strong cost control and procurement discipline. In 2024, it achieved $14.7 million in operational efficiency gains, exceeding the FCDO milestone. These savings were generated through internal reforms, bilateral initiatives, and participation in UN-wide business operations strategies. The HQ Optimisation initiative, including relocation of posts to Nairobi, is expected to further reduce overheads and improve cost-efficiency.

Efficiency: UNFPA has improved internal systems and decentralised decision-making, enabling faster and more responsive delivery. The 2024 MOPAN assessment found UNFPA’s operational systems to be robust, with 52 of 57 micro-indicators rated satisfactory or highly satisfactory. The organisation’s growing presence in UN common premises (79% of offices) supports shared services and cost savings, while enhancing coordination and visibility.

Effectiveness: Although impact has proved hard to measure, UNFPA has made progress toward its strategic objectives, particularly in advancing SRHR, gender equality, and humanitarian response. The Mid-Term Review of the Strategic Plan (2022-2025) confirmed that while the three transformative results (3TRs) remain ambitious, UNFPA has adapted its delivery model to improve impact.

Equity: UNFPA continues to prioritise equity in its programming, with a strong focus on reaching women, girls, and vulnerable populations in fragile and crisis-affected settings. The decentralisation of programme and financial authority to country offices has improved responsiveness to local needs. in humanitarian contexts, UNFPA has exceeded in building partnerships with locally-led organisations. UNFPA’s leadership on PSEAH and survivor-centred approaches further reinforces its commitment to equity and safeguarding.

Cost-effectiveness: Every $1 invested in family planning delivers returns of over $8 by averting unintended pregnancies and reducing costs of maternal health care. Reducing unintended pregnancies enables girls to continue their education and develop their professional skills, thereby increasing women’s participation in the economy and society. In the context of a tightening global funding environment and the recent withdrawal of USAID core funding, cost-effectiveness has become even more critical. UNFPA’s ability to deliver measurable results, such as exceeding efficiency targets and scaling thematic funding demonstrates its capacity to do more with less. Continued focus on strategic prioritisation, pooled resources, and joint delivery mechanisms will be essential to sustain impact and mitigate the effects of reduced donor flexibility.

UNFPA continues to make progress in diversifying its donor base, including by strengthening engagement with emerging donors, increasing contributions from international financial institutions (IFIs) and the private sector, and exploring innovative financing mechanisms. Domestic financing progress within the UNFPA Supplies Partnership has exceeded expectations in the initial years of implementation – proving that co-financing incentives can work to secure funding lines in national budgets for SRH commodities. This reflects a strategic shift from traditional funding to a ‘funding and financing’ approach.

However, whilst the initial steps have been taken, progress has been slower than anticipated. In the context of a constrained global environment, it is crucial that UNFPA prioritise these efforts. Focus should continue on domestic resource mobilisation across UNFPA to create more sustainable financing for SRH and GBV services and commodities in countries. A more clearly defined and ambitious strategy on innovative and co-financing mechanisms will be essential to enhance financial sustainability and ensure that UNFPA can deliver.

Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, there is sufficient evidence for the programme to continue.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]
The programme’s risk rating remains Major, reflecting a combination of reputational, financial, and strategic risks that have intensified over the past year. The SRO and PRO for the programme have continued to actively identify, manage and mitigate risks to the programme.

There are several contextual risks that impact UNFPA’s ability to achieve its strategic priorities. This includes the withdrawal of funding from USAID, possible reductions in UK and other major donors ODA budgets, and an increase in the severity and widespread rollback in the rights of women and girls. These risks require proactive risk mitigation. The development of the 2026-29 Strategic Plan is a key moment to safeguard UNFPA’s mission and impact and demonstrate their commitment to innovative financing.

Whilst an investigation has now concluded into allegations concerning UNFPA’s Executive Director and found no evidence of wrongdoing, FCDO recommends that UNFPA along with Office of Internal Oversight Services (OIOS) ensure full transparency to member states. The organisation is encouraged to communicate clearly on the steps taken to investigate and resolve the matter, in line with UN values and safeguarding standards. FCDO also recommends that UNFPA provide regular updates on the leadership transition process, including progress on the recruitment of a new Executive Director, to maintain donor confidence and institutional credibility.

A headline risk from each FCDO risk category has been included in the Figure 2 below:

Category	Description	Gross	Mitigation	Residual
Safeguarding	Allegations of misconduct involving the Executive Director have raised serious safeguarding concerns, with potential implications for institutional credibility and donor confidence.	Severe	UNFPA has launched its first dedicated two-year PSEAH Strategy and strengthened internal safeguarding systems, including the deployment of full-time PSEA staff in priority countries and piloting a misconduct disclosure scheme. FCDO recommends continued transparency in the investigation process and regular updates on the leadership transition, including recruitment of a new Executive Director.	Major
Financial	The withdrawal of USAID core funding and broader reductions in traditional donor contributions pose a significant threat to UNFPA’s financial sustainability and ability to deliver on its mandate.	Severe	UNFPA has exceeded its operational efficiency targets and expanded thematic funding, but pooled funding contributions remain below target. FCDO recommends that UNFPA strengthen its resource mobilisation strategy, diversify its donor base, and prioritise sustainable, flexible financing in the next strategic plan.	Major
Strategy and Context	The ongoing UN80 reform process may deprioritise sexual and reproductive health and rights (SRHR) within the broader UN development system, undermining UNFPA’s strategic positioning and impact.	Major	UNFPA is actively engaging in UNDS reform processes and aligning its next strategic plan with QCPR priorities. Continued leadership in joint programming, common premises, and shared services will be critical to maintaining visibility and influence. FCDO encourages UNFPA to advocate for SRHR as a cross-cutting priority in UN reform discussions.	Moderate
People	Global rollback of women and girls rights demotivate or scare UNFPA staff from actively promoting and delivering SRHR interventions. UNFPA staff are also put at risk in some contexts for advocating for universal access to the full range of SRHR interventions, including safe abortion	Severe	UNFPA should continue to protect their staff in all contexts. We should encourage an open dialogue about the risks faced on the ground between country offices and the centre, and the central team and FCDO. As far as possible, UNFPA should continue to be vocal about the importance of safe abortion as an essential and lifesaving medical intervention in all contexts.	Severe
Reputational	Following the Prime Ministers announcement, an increase in defence spending will be funded by reducing Official Development Assistance (ODA) from 0.5% to 0.3% of GNI. A reduction in ODA could mean withdrawing from or reducing funding to programmes, impact our ongoing partnerships and presence as a leading donor on SRHR.	Major	Continue to advocate for importance of SRHR internally. Communicate any decisions as early as possible to partners to minimise disruption and be willing to be flexible and adaptive to release payments as and when the constraints allow it.	Major
Policy and Programme	Resistance to comprehensive SRHR within UNFPA limits implementation of Strategic Plan objectives and UK policy priorities.	Major	Use bilateral engagement, executive board opportunities, due diligence and Country Programme Document review processes to encourage effective human resource management including leadership appointments.	Moderate

Figure 2 - Headline risks across FCDO risk categories
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
The FCDO maintains a strong and collaborative relationship with UNFPA, underpinned by regular biweekly engagement between the FCDO and UNFPA, as well as strong engagement with UNFPA and the UK Mission to the UN in New York and Geneva. This close partnership has enabled proactive dialogue on programme delivery, risk management, and strategic alignment, contributing to the programme’s overall effectiveness and responsiveness.

Delays in the release of the £6 million core funding uplift, approved in November 2024, have impacted financial planning. This delay is due to the absence of a signed agreement, following the Foreign Secretary’s announcement to reduce ODA to 0.3% of GNI. A recommendation of this review is to finalise and sign the agreement by June 2025 to enable disbursement within the current financial year.

This also remains the same for the £6m payment to the HTF in 2025. No formal agreement is currently in place to facilitate this. It is therefore recommended that a time extension to the business case is approved to allow UNFPA sufficient time to utilise the remaining funds effectively, particularly given the programme’s scheduled end date of September 2025.

From a delivery perspective, UNFPA has continued to meet or exceed expectations across most outputs, with strong performance in operational efficiency, safeguarding, and humanitarian response. The organisation has also demonstrated compliance with FCDO’s Gender Equality Duty and continues to prioritise equity and inclusion across its programming.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring of the UNFPA Core Programme has been primarily driven by regular engagement between FCDO and UNFPA, as well as reporting and briefing to the executive board. A strategic dialogue was also held in April 2025 with FCDO’s global health director and deputy director with UNFPA’s executive director. This gave an opportunity for high level engagement to discuss strategic priorities and deep dive into technical areas of UNFPA’s work. Moreover, many high-level bilateral meetings with UNFPA and FCDO seniors have taken place over the course of the year to raise any issues and learn key updates. The strong working relationship between the two organisations has enabled continuous oversight of programme delivery, risk management, and strategic alignment. These engagements have served as the primary mechanism for tracking progress and addressing implementation challenges.

FCDO has relied on UNFPA’s global scorecard, strategic plan updates, and external assessments such as the 2024 MOPAN review and the Mid-Term Review of the Strategic Plan (2022–2025) to inform this review. Furthermore, UNFPA hold informal briefings for donors to attend to review the progress of work funded through contributions to the HTF.

This is the final Annual Review of the current business case, which is scheduled to conclude in September 2025. A Project Completion Report (PCR) will be written following programme closure. The PCR will provide a comprehensive assessment of programme achievements and will capture the results of the delayed disbursement of the £6 million core funding uplift and the £6 million allocation to the HTF.

FCDO will continue to engage closely with UNFPA to ensure that the final months of the programme are managed effectively and that outstanding funds are disbursed and monitored in line with UK priorities and VFM.

Date of last narrative financial report	17 April 2025 / Last narrative financial report	Date of last audited annual statement	24 July 2024 / Audited financial narrative and statement for 2023